## ITP Rev 1
INSPECTION & TEST PLAN
Client: |  | Stratford District Council |  |  |  | SCCL Job Number |  |  | ITP Number |  | Client Job Number
[6 empty] | 2025/007 |  |  | 20 |  | Contract R2403
Description: |  | Opunake Road Resilience Project-Dropout RP9.550 |  |  |  | Prepared By |  | ITP Revision |  | ITP Date | Code(s)
[6 empty] | Kendall Hale |  | 0 |  | 2025-02-18 | TQS2:2005
Abbreviations: |  | H = Hold W = Witness R = Review I = Inspection M = Monitor |  | SCCL = Superior Civil Construction Ltd E = Engineer SC = Sub Contractor SUP = Supervisor CM= Contracts Manager OP = Operator QA = Quality Manager STMS = Traffic Manager
Hold: Work may not proceed past the hold point without the party imposing the hold point attendance to witness the activity. Witness: An inspection point which will be witnessed or verified. Review: Documentation to be reviewed and approved. Inspection: A formal inspection activity to be undertaken and a report produced. Monitor: An activity which is subject to ongoing monitoring.
SEQ NO | TASK | RESPONSIBILITY | INSPECTION FUNCTION | APPLICABLE DOCUMENTS | INSP FREQ | INSPECTOR / RESULT
[6 empty] | SCCL | SCCL SIGN | Engineer | E SIGN | COMMENTS
DOCUMENT REVIEW
1 | Receive work scope and review drawings & documents | SCCL | Check contract documents and drawings issued for construction, note test and inspection requirements, build contract specific test and quality plan. | Contract Documents NZS 3910:2013 TNZ Specifications | 100% | SUP H |  | R
2 | Submit ITP & Quality Plan for client approval | SCCL | SDC and Engineer to review and approve | Contract Documents NZS 3910:2013 TNZ Specifications | 100% | SUP H |  | R
Establishment and material supply
3 | Setting out | SCCL | Locate and set-out position of works | Specifications and Drawings | Prior to commencing work | SUP, E H |  | H, I
4 | Service identification | SCCL | Locate and pot-hole existing services | Worksafe guide for safety with underground services, NZTA Minimum Standard for Utility Identification and Protection | Prior to clearance and trenching | SUP H |  | W
5 | Machinery is fit for purpose | SCCL | Undertake pre-starts and machinery checksheets | Eroad prestart method | 3x daily | SUP & QA, M |  | R
6 | Traffic Management | SCCL | Establish and maintain road closure and shoulder closure traffic management | Approved Traffic Management Plan | Every two hours during work hours | STMS, SUP, H, M |  | H, R
Excavation and Retaining Wall Construction
7 | Environmental and Erosion | SCCL | Installation and maintenance of erosion controlmeasures | Guidlines for earthworks in the Taranaki Region - October 2006, NZS4404:2010 | Daily | SUP, QA |  | I
8 | Excavation | SCCL | Inspection of open trench | NZS4404:2010, NZTA F/1:1997, TRC & WRC Guidlines TNZ F/3 | Prior to and during task | SUP, QA, H |  | I
9 | Earthworks - Subgrade Strength and cut to fill | SCCL | CBR value of 7 for subgrade surfaces, Scala 2 blows per 100mm minmum target 3 blows per 100mm or shear vane 100kPA minimum | Technical Specifications, NZS4402 part 6 and NZTA F/1, Taranaki Regional Council | Upon completion of cut to waste, During cut to fill operations and where poor strength material is encounted | SUP, QA, H |  | H, I
10 | Pile Foundations | SCCL | Ensure piles are augered to the correct dimensions as per the contruction drawings, concrete is ordered and placed at 20MPa and horizontal positioning not exceeding +/- 50mm | Techincal specifications, contract drawings | Upon set out, Prior to placing concrete and during concrete placement | CM, SUP, QA. H, I |  | H, I
11 | Steel Piles | SCCL | Ensure steel piles are 200 UB25 .4 grade 300 complying with AS/NZS 3679 and placed at 1.85m centres, on the correct laid back degrees. | Technical Specifications, Contract drawings and AS/NZS 3679 | Prior to use and upon installation | SUP, QA, H, I |  | H, I
12 | Structural Steel | SCCL | Ensure structural steel is manufactured to AS/NZS 3678, AS/NZS 3679.1 and fabricated to AS/NZS 3404 | Techincal specifications, contract drawings, AS/NZS 3678, AS/NZS 3679.1 and fabricated to AS/NZS 3404 | Prior to and during installation | SUP, QA I |  | I
13 | 150 machine rounded retaining wall infills | SCCL | Check retaining wall infills, ensure all infills are equal rounds and tanalised pine H5 | Technical Specifications, Contract drawings, HZS3631:1988, NZMP3640:1992 | Upon arrival to site and during installation | SUP, QA, W, I |  | I
14 | Mechanical Ground Anchors | SCCL | Check to ensure ground anchors are SR2, anchor rod diameter is 38mm and minmimum length of, anchor spacing is 1.85mm and pre drilled holes are grouted. Testing meets working load of 285kN | Technical Specifications, Subcontractors installation proceedures and AS/NZS 4680 | Prior to and during installation | SUP, QA, CM, I,R |  | I,R
15 | Subsoil and pannel drainage | SCCL | Check positioning is as per design, specification is as per required in the techincal specifications and wrapped in geotextile and clean drainage chip. | Contruction drawings, techinical specifications and NZTA F/2 | Prior to and during installation | SUP, QA. W,I |  | I
16 | Imported fill - Granular hardfill | SCCL | Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 25 every 500mm lift or 3 blows per 100mm with a scala penotrometer. | Technical Specifications, NZS 4404:2010 | Prior to and during installation | SUP, QA, I, M |  | I, R
17 | Rock Rip Rap Installation | SCCL | Confirm grading, size and rock desnity meet specification | Technical Specifications, NZS 4404:2010 | Prior to and during installation | SUP, QA M |  | I, R
Pavement and Reinstatement
18 | AP65 Sub-base | SCCL | Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 40 every 200mm lift | Contract documents, NZS 4402:2010, NZTA B/2:2005 | Prior to placement | SUP, QA, M, I |  | I, R
19 | AP40 Basecourse | SCCL | Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 40 every 150mm lift | Contract documents, NZS 4402:2010, NZTA B/2:2005 | Prior to placement | SUP, QA, M, I |  | I, R
20 | Sealing | SCCL | Pavement pre-seal inspection & Signoff Pavement design to be 130/150 cutback bitumen. | Contract Documents NZS 4404:2010, NZTA P/3, NZTA M/6 | Prior to Sealing | SUP, QA H, I |  | I
21 | Site Rails | SCCL | Ensure site rails are constructed as per the contract documents NZTA requirements | Techincal specifications and NZS 4404:2010 | Prior to and during construction | SUP, QA, M, I |  | I
Concrete
22 | Concrete Kerb | SCCL | Concrete aprons Concrete compressive strength of 25 Mpa | NZS4404:2010 Section 4, NZS 3109:1997, NZS 3104:2003 | Upon ordering and during placement | SUP, QA, M, I |  | I
Completion
23 | Completion of works | SCCL | Punchlist items closed out Tidy area, Engineer's final inspection | Contract Documents | On Completion | QA H |  | H, I
24 | Complete AS Built dwgs submit to Client for approval | SCCL | Transmit to client for final review | Technical Specifications Contact drawings ISO 9001 | Upon final inspection | QA H |  | I, R