## ITP Rev 1
INSPECTION & TEST PLAN
Client: |  | Stratford District Council |  |  |  | WCL Job Number |  |  | ITP Number |  | Client Job Number
[6 empty] | 2025/005 |  |  | 17 |  | Contract R2402
Description: |  | Wawiri Road Culvert 127 - 0127 Replacement |  |  |  | Prepared By |  | ITP Revision |  | ITP Date | Code(s)
[6 empty] | Kendall Hale |  | 0 |  | 2025-01-22 | TQS2:2005
Abbreviations: |  | H = Hold W = Witness R = Review I = Inspection M = Monitor |  | SCCL = Superior Civil Construction Ltd E = Engineer SC = Sub Contractor SUP = Supervisor S = Storeman OP = Operator QA = Quality Manager STMS = Traffic Manager
Hold: Work may not proceed past the hold point without the party imposing the hold point attendance to witness the activity. Witness: An inspection point which will be witnessed or verified. Review: Documentation to be reviewed and approved. Inspection: A formal inspection activity to be undertaken and a report produced. Monitor: An activity which is subject to ongoing monitoring.
SEQ NO | TASK | RESPONSIBILITY | INSPECTION FUNCTION | APPLICABLE DOCUMENTS | INSP FREQ | INSPECTOR / RESULT
[6 empty] | SCCL | SCCL SIGN | Engineer | E SIGN | COMMENTS
DOCUMENT REVIEW
1 | Receive work scope and review drawings & documents | SCCL | Check contract documents and drawings, note test and inspection requirements, build contract specific test and quality plan. | Contract Documents NZS 3910:2013 TNZ Specifications | 100% | SUP H |  | R
2 | Submit ITP & Quality Plan for client approval | SCCL | SDC and Engineer to review and approve | Contract Documents NZS 3910:2013 TNZ Specifications | 100% | SUP H |  | R
Establishment and material supply
3 | Setting out | SCCL | Locate and set-out position of works | Specifications and Drawings | Prior to commencing work | SUP, E H |  | H, I
4 | Service identification | SCCL | Locate and pot-hole existing services | Worksafe guide for safety with underground services, NZTA Minimum Standard for Utility Identification and Protection | Prior to clearance and trenching | SUP H
5 | Machinery is fit for purpose | SCCL | Undertake pre-starts and machinery checksheets | Eroad prestart method | 3x daily | SUP & QA, M |  | R
6 | Traffic Management | SCCL | Establish and maintain road closure and shoulder closure traffic management | Approved Traffic Management Plan | Every two hours during work hours | STMS, SUP, H, M |  | H, R
Trenching and installation
7 | Environmental and Erosion | SCCL | Installation and maintenance of erosion controlmeasures | Guidlines for earthworks in the Taranaki Region - October 2006, NZS4404:2010 | Daily | SUP, QA |  | I
8 | Excavation | SCCL | Inspection of open trench | NZS4404:2010, NZTA F/1:1997, TRC & WRC Guidlines TNZ F/3 | Prior to and during task | SUP, QA, H |  | I
9 | Earthworks - Subgrade Strength | SCCL | Scala CBR 7 equivalent | Technical Specifications, NZS4402 part 6 and TNZ B/2 | Upon completion of excavation and where poor strength material is encounted | SUP, QA, H |  | H, I
10 | Bedding - 20mm Clean | SCCL | Bedding side support and overlay depth 300mm as per drawings | Technical Specifications, drawings and NZS4404:2010 H2 | Prior to use and upon completion | SUP, QA, H, I |  | H, I
11 | Hynds 2m x 2m Box Culvert Units and Concrete Aprons | SCCL | Confirm pipes and fittings comply with specifications, concrete apron strength 25 MPa | NZS4404:2010 Section 4, NZS 3109:1997, NZS 3104:2003 | Prior to and during installation | SUP, QA I |  | I
12 | Box Culvert Grade | SCCL | Check box culvert units during installtion are at 1% grade and are constructed as per suppliers | Technical Specifications | Prior to and during installation | SUP, QA, W, I |  | I
13 | Imported fill - Granular hardfill | SCCL | Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 25 every 500mm lift | Technical Specifications, NZS 4404:2010 | Prior to and during installation | SUP, QA, I, M |  | I, R
14 | Rock Rip Rap Installation | SCCL | Confirm grading, size and rock desnity meet specification | Technical Specifications, NZS 4404:2010 | Prior to and during installation | SUP, QA M |  | I, R
REINSTATEMENT
15 | AP65 Sub-base | SCCL | Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 40 every 200mm lift | Contract documents, NZS 4402:2010, NZTA B/2:2005 | Prior to placement | SUP, QA, M, I |  | I, R
16 | AP40 Basecourse | SCCL | Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 40 every 150mm lift | Contract documents, NZS 4402:2010, NZTA B/2:2005 | Prior to placement | SUP, QA, M, I |  | I, R
17 | Sealing | SCCL | Pavement pre-seal inspection & Signoff | Contract Documents NZS 4404:2010, NZTA P/3 | Prior to Sealing | SUP, QA H, I |  | I
18 | Sealing | SCCL | Obtain confirmation that Sealing materials and process is in accordance with contract documents and specifications | Contract Documents NZS 4404:2010, NZTA P/3 | Prior to Sealing | SUP, QA, M, I |  | I, R
19 | Site Rails | SCCL | Ensure site rails are constructed as per the contract documents NZTA requirements | Techincal specifications and NZS 4404:2010 | Prior to and during construction | SUP, QA, M, I |  | I
Pavement & Testing
19 | Concrete | SCCL | Concrete aprons Concrete compressive strength of 25 Mpa | NZS4404:2010 Section 4, NZS 3109:1997, NZS 3104:2003 | Upon ordering and during placement | SUP, QA, M, I |  | I
Completion
20 | Completion of works | SCCL | Punchlist items closed out Tidy area, Engineer's final inspection | Contract Documents | On Completion | QA H |  | H, I
21 | Complete AS Built dwgs submit to Client for approval | SCCL | Transmit to client for final review | Technical Specifications Contact drawings ISO 9001 | Upon final inspection | QA H |  | I, R