## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP032 - STDC Unsealed Roads Maintenance | itp |  |  |  |  | ITP032 - STDC Unsealed Roads Maintenance Rev 1
section | DOCUMENT REVIEW
checkpoint | 1 - Receive work scope and review documents
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Check contract documents and drawings, note test and inspection requirements, build contract specific test and quality plan.
label | APPLICABLE DOCUMENTS - Contract Documents NZS 3910:2013, Contract Specifications, TNZ Specifications
label | INSP FREQ - 100%
label | INSPECTOR / RESULT: SCCL - QA, H
label | INSPECTOR / RESULT: Engineer - R
holdpoint | HOLD POINT
checkpoint | 2 - Submit ITP & Quality Plan for client approval
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - STDC and Engineer to review and approve
label | APPLICABLE DOCUMENTS - Contract Documents NZS 3910:2013, Contract Specifications, TNZ Specifications
label | INSP FREQ - 100%
label | INSPECTOR / RESULT: SCCL - QA, H
label | INSPECTOR / RESULT: Engineer - R
holdpoint | HOLD POINT
section | Establishment and material supply
checkpoint | 3 - Maintenance Programme
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Discuss maintenance requirments and Programme roads, as directed by contract engineer
label | APPLICABLE DOCUMENTS - Contract Documents, Specifications and Drawings, Programme
label | INSP FREQ - Prior to commencing work
label | INSPECTOR / RESULT: SCCL - QA, SUP, E H, R, M, W
label | INSPECTOR / RESULT: Engineer - H, R, M
holdpoint | HOLD POINT
checkpoint | 4 - Site Set Up and Establishment
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Inspect existing road surface concentrating on existing grades/cross falls, ensure they are within specfication 4 - 6%, inspect surface water channels and side drains
label | APPLICABLE DOCUMENTS - Contract Specifications, SCCL Maintenace Grading and Maintenance Aggregates Inspection Form
label | INSP FREQ - Prior to physical works commencing
label | INSPECTOR / RESULT: SCCL - QA, SUP, E, H, I, M
label | INSPECTOR / RESULT: Engineer - I
holdpoint | HOLD POINT
checkpoint | 5 - Service identification
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Locate and pot-hole existing services
label | APPLICABLE DOCUMENTS - Worksafe guide for safety with underground services, NZTA Minimum Standard for Utility Identification and Protection
label | INSP FREQ - Prior to side drain clearing and any deep ripping
label | INSPECTOR / RESULT: SCCL - QA, SUP, H, I
label | INSPECTOR / RESULT: Engineer -
holdpoint | HOLD POINT
checkpoint | 6 - Machinery is fit for purpose
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Ensure machinery is fitted with VHF/UHF and Satellite Phone communication, First Aid Kit, Fire Extenguisher and Spill Kit, Flashing Beacon Light, Required Signage and Alarms and Undertake pre-starts and machinery checksheet via Eroad App
label | APPLICABLE DOCUMENTS - Contract Doucments, CoPTTM, NZGTTM, Worksafe and Eroad prestart method
label | INSP FREQ - 3x daily
label | INSPECTOR / RESULT: SCCL - SUP & QA, M, I
label | INSPECTOR / RESULT: Engineer - R
checkpoint | 7 - Traffic Management
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Establish and maintain generic traffic management plans, ensure signage is highly visable and in qood condition.
label | APPLICABLE DOCUMENTS - Approved Traffic Management Plan
label | INSP FREQ - Every two hours during work hours
label | INSPECTOR / RESULT: SCCL - QA,STMS, SUP, H, M,I
label | INSPECTOR / RESULT: Engineer - H, R
holdpoint | HOLD POINT
checkpoint | 8 - Environmental and Erosion
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Installation and maintenance of erosion controlmeasures as required, inspect weather reports and programme works accordingly
label | APPLICABLE DOCUMENTS - Contract Documents, Guidlines for earthworks in the Taranaki Region - October 2006, NZS4404:2010
label | INSP FREQ - Daily
label | INSPECTOR / RESULT: SCCL - SUP, QA
label | INSPECTOR / RESULT: Engineer - I
section | Environmental and Excavation
checkpoint | 9 - Excavation on unmetalled Roads
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Obtain site access from property owner, inspect existing surface, complete maintenance shaping and side drain clearing/slip removal
label | APPLICABLE DOCUMENTS - NZS4404:2010, TRC & WRC Guidlines (Freshwater Plan)
label | INSP FREQ - Prior to and during task
label | INSPECTOR / RESULT: SCCL - SUP, QA, H, I, M
label | INSPECTOR / RESULT: Engineer - I
holdpoint | HOLD POINT
section | Surface and Shape Restoration
checkpoint | 10 - Surface and Shape Restoration/Maintenance Grading
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Confirm grading, size and rock desnity meet specification
label | APPLICABLE DOCUMENTS - Technical Specifications, NZS 4404:2010
label | INSP FREQ - Prior to and during installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, M
label | INSPECTOR / RESULT: Engineer - I, R
section | Maintenance Aggregates
checkpoint | 11 - Spply and Placement of Maintenance Aggregates, AP65 Sub-base
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Must be approved by Engineer prior to use and inspected via NDM with a minimum MDD of 90% upon completion, to be constructed at 100mm nominal thickness
label | APPLICABLE DOCUMENTS - Contract documents, NZS 4402:2010, NZTA B/2:2005 and NZTA M/4
label | INSP FREQ - Prior to placement
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I, R
checkpoint | 12 - Spply and Placement of Maintenance Aggregates, AP40 Basecourse
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Must be approved by Engineer prior to use and inspected via NDM with a minimum MDD of 90% upon completion, to be constructed at 75mm nominal thickness
label | APPLICABLE DOCUMENTS - Contract documents, NZS 4402:2010, NZTA B/2:2005 and NZTA M/4
label | INSP FREQ - Prior to placement
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I, R
checkpoint | 13 - Spply and Placement of Maintenance Aggregates, AP30
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Must be approved by Engineer prior to use and inspected via NDM with a minimum MDD of 90% upon completion, to be constructed at 45mm nominal thickness
label | APPLICABLE DOCUMENTS - Contract documents, NZS 4402:2010, NZTA B/2:2005 and NZTA M/4
label | INSP FREQ - Prior to Sealing
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I
section | Completion
checkpoint | 14 - Completion of works
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Punchlist items closed out
label | ○ Tidy area, quality managers final inspection
label | APPLICABLE DOCUMENTS - Contract Documents, technical specifications
label | INSP FREQ - On Completion
label | INSPECTOR / RESULT: SCCL - QA, H, I
label | INSPECTOR / RESULT: Engineer - H, I
holdpoint | HOLD POINT
checkpoint | 15 - Complete payment claim requirments, collection of truck docets, completed lengths of surface and shape restoration, RP from - RP to Client for approval
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Transmit to client for final review
label | APPLICABLE DOCUMENTS - Technical Specifications NZS 3910:2013, Construction Contracts Act, SCCL Claim Format
label | INSP FREQ - Upon final inspection
label | INSPECTOR / RESULT: SCCL - QA, SUP, CM, R, M, I
label | INSPECTOR / RESULT: Engineer - I, R
checklist | ITP020 - Opunake Road Dropout | itp |  |  |  |  | ITP020 - Opunake Road Dropout Rev 0
section | DOCUMENT REVIEW
checkpoint | 1 - Receive work scope and review drawings & documents
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Check contract documents and drawings issued for construction, note test and inspection requirements, build contract specific test and quality plan.
label | APPLICABLE DOCUMENTS - Contract Documents NZS 3910:2013 TNZ Specifications
label | INSP FREQ - 100%
label | INSPECTOR / RESULT: SCCL - SUP, H
label | INSPECTOR / RESULT: Engineer - R
holdpoint | HOLD POINT
checkpoint | 2 - Submit ITP & Quality Plan for client approval
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - SDC and Engineer to review and approve
label | APPLICABLE DOCUMENTS - Contract Documents NZS 3910:2013 TNZ Specifications
label | INSP FREQ - 100%
label | INSPECTOR / RESULT: SCCL - SUP, H
label | INSPECTOR / RESULT: Engineer - R
holdpoint | HOLD POINT
section | Establishment and material supply
checkpoint | 3 - Setting out
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Locate and set-out position of works
label | APPLICABLE DOCUMENTS - Specifications and Drawings
label | INSP FREQ - Prior to commencing work
label | INSPECTOR / RESULT: SCCL - SUP, E, H
label | INSPECTOR / RESULT: Engineer - H, I
holdpoint | HOLD POINT
checkpoint | 4 - Service identification
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Locate and pot-hole existing services
label | APPLICABLE DOCUMENTS - Worksafe guide for safety with underground services, NZTA Minimum Standard for Utility Identification and Protection
label | INSP FREQ - Prior to clearance and trenching
label | INSPECTOR / RESULT: SCCL - SUP, H
label | INSPECTOR / RESULT: Engineer - W
holdpoint | HOLD POINT
checkpoint | 5 - Machinery is fit for purpose
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Undertake pre-starts and machinery checksheets
label | APPLICABLE DOCUMENTS - Eroad prestart method
label | INSP FREQ - 3x daily
label | INSPECTOR / RESULT: SCCL - SUP & QA, M
label | INSPECTOR / RESULT: Engineer - R
checkpoint | 6 - Traffic Management
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Establish and maintain road closure and shoulder closure traffic management
label | APPLICABLE DOCUMENTS - Approved Traffic Management Plan
label | INSP FREQ - Every two hours during work hours
label | INSPECTOR / RESULT: SCCL - STMS, SUP, H, M
label | INSPECTOR / RESULT: Engineer - H, R
holdpoint | HOLD POINT
section | Excavation and Retaining Wall Construction
checkpoint | 7 - Environmental and Erosion
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Installation and maintenance of erosion controlmeasures
label | APPLICABLE DOCUMENTS - Guidlines for earthworks in the Taranaki Region - October 2006, NZS4404:2010
label | INSP FREQ - Daily
label | INSPECTOR / RESULT: SCCL - SUP, QA
label | INSPECTOR / RESULT: Engineer - I
checkpoint | 8 - Excavation
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Inspection of open trench
label | APPLICABLE DOCUMENTS - NZS4404:2010, NZTA F/1:1997, TRC & WRC Guidlines TNZ F/3
label | INSP FREQ - Prior to and during task
label | INSPECTOR / RESULT: SCCL - SUP, QA, H
label | INSPECTOR / RESULT: Engineer - I
holdpoint | HOLD POINT
checkpoint | 9 - Earthworks - Subgrade Strength and cut to fill
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - CBR value of 7 for subgrade surfaces, Scala 2 blows per 100mm minmum target 3 blows per 100mm or shear vane 100kPA minimum
label | APPLICABLE DOCUMENTS - Technical Specifications, NZS4402 part 6 and NZTA F/1, Taranaki Regional Council
label | INSP FREQ - Upon completion of cut to waste, During cut to fill operations and where poor strength material is encounted
label | INSPECTOR / RESULT: SCCL - SUP, QA, H
label | INSPECTOR / RESULT: Engineer - H, I
holdpoint | HOLD POINT
checkpoint | 10 - Pile Foundations
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Ensure piles are augered to the correct dimensions as per the contruction drawings, concrete is ordered and placed at 20MPa and horizontal positioning not exceeding +/- 50mm
label | APPLICABLE DOCUMENTS - Techincal specifications, contract drawings
label | INSP FREQ - Upon set out, Prior to placing concrete and during concrete placement
label | INSPECTOR / RESULT: SCCL - CM, SUP, QA, H, I
label | INSPECTOR / RESULT: Engineer - H, I
holdpoint | HOLD POINT
checkpoint | 11 - Steel Piles
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Ensure steel piles are 200 UB25 .4 grade 300 complying with AS/NZS 3679 and placed at 1.85m centres, on the correct laid back degrees.
label | APPLICABLE DOCUMENTS - Technical Specifications, Contract drawings and AS/NZS 3679
label | INSP FREQ - Prior to use and upon installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, H, I
label | INSPECTOR / RESULT: Engineer - H, I
holdpoint | HOLD POINT
checkpoint | 12 - Structural Steel
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Ensure structural steel is manufactured to AS/NZS 3678, AS/NZS 3679.1 and fabricated to AS/NZS 3404
label | APPLICABLE DOCUMENTS - Techincal specifications, contract drawings, AS/NZS 3678, AS/NZS 3679.1 and fabricated to AS/NZS 3404
label | INSP FREQ - Prior to and during installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, I
label | INSPECTOR / RESULT: Engineer - I
checkpoint | 13 - 150 machine rounded retaining wall infills
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Check retaining wall infills, ensure all infills are equal rounds and tanalised pine H5
label | APPLICABLE DOCUMENTS - Technical Specifications, Contract drawings, HZS3631:1988, NZMP3640:1992
label | INSP FREQ - Upon arrival to site and during installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, W, I
label | INSPECTOR / RESULT: Engineer - I
checkpoint | 14 - Mechanical Ground Anchors
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Check to ensure ground anchors are SR2, anchor rod diameter is 38mm and minmimum length of, anchor spacing is 1.85mm and pre drilled holes are grouted. Testing meets working load of 285kN
label | APPLICABLE DOCUMENTS - Technical Specifications, Subcontractors installation proceedures and AS/NZS 4680
label | INSP FREQ - Prior to and during installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, CM, I,R
label | INSPECTOR / RESULT: Engineer - I,R
checkpoint | 15 - Subsoil and pannel drainage
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Check positioning is as per design, specification is as per required in the techincal specifications and wrapped in geotextile and clean drainage chip.
label | APPLICABLE DOCUMENTS - Contruction drawings, techinical specifications and NZTA F/2
label | INSP FREQ - Prior to and during installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, W,I
label | INSPECTOR / RESULT: Engineer - I
checkpoint | 16 - Imported fill - Granular hardfill
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 25 every 500mm lift or 3 blows per 100mm with a scala penotrometer.
label | APPLICABLE DOCUMENTS - Technical Specifications, NZS 4404:2010
label | INSP FREQ - Prior to and during installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, I, M
label | INSPECTOR / RESULT: Engineer - I, R
checkpoint | 17 - Rock Rip Rap Installation
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Confirm grading, size and rock desnity meet specification
label | APPLICABLE DOCUMENTS - Technical Specifications, NZS 4404:2010
label | INSP FREQ - Prior to and during installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, M
label | INSPECTOR / RESULT: Engineer - I, R
section | Pavement and Reinstatement
checkpoint | 18 - AP65 Sub-base
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 40 every 200mm lift
label | APPLICABLE DOCUMENTS - Contract documents, NZS 4402:2010, NZTA B/2:2005
label | INSP FREQ - Prior to placement
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I, R
checkpoint | 19 - AP40 Basecourse
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 40 every 150mm lift
label | APPLICABLE DOCUMENTS - Contract documents, NZS 4402:2010, NZTA B/2:2005
label | INSP FREQ - Prior to placement
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I, R
checkpoint | 20 - Sealing
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Pavement pre-seal inspection & Signoff Pavement design to be 130/150 cutback bitumen.
label | APPLICABLE DOCUMENTS - Contract Documents NZS 4404:2010, NZTA P/3, NZTA M/6
label | INSP FREQ - Prior to Sealing
label | INSPECTOR / RESULT: SCCL - SUP, QA, H, I
label | INSPECTOR / RESULT: Engineer - I
holdpoint | HOLD POINT
checkpoint | 21 - Site Rails
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Ensure site rails are constructed as per the contract documents NZTA requirements
label | APPLICABLE DOCUMENTS - Techincal specifications and NZS 4404:2010
label | INSP FREQ - Prior to and during construction
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I
section | Concrete
checkpoint | 22 - Concrete Kerb
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Concrete aprons
label | ○ Concrete compressive strength of 25 Mpa
label | APPLICABLE DOCUMENTS - NZS4404:2010 Section 4, NZS 3109:1997, NZS 3104:2003
label | INSP FREQ - Upon ordering and during placement
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I
section | Completion
checkpoint | 23 - Completion of works
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Punchlist items closed out
label | ○ Tidy area, Engineer's final inspection
label | APPLICABLE DOCUMENTS - Contract Documents
label | INSP FREQ - On Completion
label | INSPECTOR / RESULT: SCCL - QA, H
label | INSPECTOR / RESULT: Engineer - H, I
holdpoint | HOLD POINT
checkpoint | 24 - Complete AS Built dwgs submit to Client for approval
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Transmit to client for final review
label | APPLICABLE DOCUMENTS - Technical Specifications Contact drawings ISO 9001
label | INSP FREQ - Upon final inspection
label | INSPECTOR / RESULT: SCCL - QA, H
label | INSPECTOR / RESULT: Engineer - I, R
holdpoint | HOLD POINT
checklist | ITP017 - Wawiri Road | itp |  |  |  |  | ITP017 - Wawiri Road Rev 0
section | DOCUMENT REVIEW
checkpoint | 1 - Receive work scope and review drawings & documents
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Check contract documents and drawings, note test and inspection requirements, build contract specific test and quality plan.
label | APPLICABLE DOCUMENTS - Contract Documents NZS 3910:2013 TNZ Specifications
label | INSP FREQ - 100%
label | INSPECTOR / RESULT: SCCL - SUP, H
label | INSPECTOR / RESULT: Engineer - R
holdpoint | HOLD POINT
checkpoint | 2 - Submit ITP & Quality Plan for client approval
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - SDC and Engineer to review and approve
label | APPLICABLE DOCUMENTS - Contract Documents NZS 3910:2013 TNZ Specifications
label | INSP FREQ - 100%
label | INSPECTOR / RESULT: SCCL - SUP, H
label | INSPECTOR / RESULT: Engineer - R
holdpoint | HOLD POINT
section | Establishment and material supply
checkpoint | 3 - Setting out
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Locate and set-out position of works
label | APPLICABLE DOCUMENTS - Specifications and Drawings
label | INSP FREQ - Prior to commencing work
label | INSPECTOR / RESULT: SCCL - SUP, E, H
label | INSPECTOR / RESULT: Engineer - H, I
holdpoint | HOLD POINT
checkpoint | 4 - Service identification
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Locate and pot-hole existing services
label | APPLICABLE DOCUMENTS - Worksafe guide for safety with underground services, NZTA Minimum Standard for Utility Identification and Protection
label | INSP FREQ - Prior to clearance and trenching
label | INSPECTOR / RESULT: SCCL - SUP, H
label | INSPECTOR / RESULT: Engineer -
holdpoint | HOLD POINT
checkpoint | 5 - Machinery is fit for purpose
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Undertake pre-starts and machinery checksheets
label | APPLICABLE DOCUMENTS - Eroad prestart method
label | INSP FREQ - 3x daily
label | INSPECTOR / RESULT: SCCL - SUP & QA, M
label | INSPECTOR / RESULT: Engineer - R
checkpoint | 6 - Traffic Management
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Establish and maintain road closure and shoulder closure traffic management
label | APPLICABLE DOCUMENTS - Approved Traffic Management Plan
label | INSP FREQ - Every two hours during work hours
label | INSPECTOR / RESULT: SCCL - STMS, SUP, H, M
label | INSPECTOR / RESULT: Engineer - H, R
holdpoint | HOLD POINT
section | Trenching and installation
checkpoint | 7 - Environmental and Erosion
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Installation and maintenance of erosion controlmeasures
label | APPLICABLE DOCUMENTS - Guidlines for earthworks in the Taranaki Region - October 2006, NZS4404:2010
label | INSP FREQ - Daily
label | INSPECTOR / RESULT: SCCL - SUP, QA
label | INSPECTOR / RESULT: Engineer - I
checkpoint | 8 - Excavation
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Inspection of open trench
label | APPLICABLE DOCUMENTS - NZS4404:2010, NZTA F/1:1997, TRC & WRC Guidlines TNZ F/3
label | INSP FREQ - Prior to and during task
label | INSPECTOR / RESULT: SCCL - SUP, QA, H
label | INSPECTOR / RESULT: Engineer - I
holdpoint | HOLD POINT
checkpoint | 9 - Earthworks - Subgrade Strength
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Scala CBR 7 equivalent
label | APPLICABLE DOCUMENTS - Technical Specifications, NZS4402 part 6 and TNZ B/2
label | INSP FREQ - Upon completion of excavation and where poor strength material is encounted
label | INSPECTOR / RESULT: SCCL - SUP, QA, H
label | INSPECTOR / RESULT: Engineer - H, I
holdpoint | HOLD POINT
checkpoint | 10 - Bedding - 20mm Clean
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Bedding side support and overlay depth 300mm as per drawings
label | APPLICABLE DOCUMENTS - Technical Specifications, drawings and NZS4404:2010 H2
label | INSP FREQ - Prior to use and upon completion
label | INSPECTOR / RESULT: SCCL - SUP, QA, H, I
label | INSPECTOR / RESULT: Engineer - H, I
holdpoint | HOLD POINT
checkpoint | 11 - Hynds 2m x 2m Box Culvert Units and Concrete Aprons
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Confirm pipes and fittings comply with specifications, concrete apron strength 25 MPa
label | APPLICABLE DOCUMENTS - NZS4404:2010 Section 4, NZS 3109:1997, NZS 3104:2003
label | INSP FREQ - Prior to and during installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, I
label | INSPECTOR / RESULT: Engineer - I
checkpoint | 12 - Box Culvert Grade
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Check box culvert units during installtion are at 1% grade and are constructed as per suppliers
label | APPLICABLE DOCUMENTS - Technical Specifications
label | INSP FREQ - Prior to and during installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, W, I
label | INSPECTOR / RESULT: Engineer - I
checkpoint | 13 - Imported fill - Granular hardfill
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 25 every 500mm lift
label | APPLICABLE DOCUMENTS - Technical Specifications, NZS 4404:2010
label | INSP FREQ - Prior to and during installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, I, M
label | INSPECTOR / RESULT: Engineer - I, R
checkpoint | 14 - Rock Rip Rap Installation
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Confirm grading, size and rock desnity meet specification
label | APPLICABLE DOCUMENTS - Technical Specifications, NZS 4404:2010
label | INSP FREQ - Prior to and during installation
label | INSPECTOR / RESULT: SCCL - SUP, QA, M
label | INSPECTOR / RESULT: Engineer - I, R
section | REINSTATEMENT
checkpoint | 15 - AP65 Sub-base
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 40 every 200mm lift
label | APPLICABLE DOCUMENTS - Contract documents, NZS 4402:2010, NZTA B/2:2005
label | INSP FREQ - Prior to placement
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I, R
checkpoint | 16 - AP40 Basecourse
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Must be approved by Engineer prior to use and inspected via clegg hammer with a minimum CIV of 40 every 150mm lift
label | APPLICABLE DOCUMENTS - Contract documents, NZS 4402:2010, NZTA B/2:2005
label | INSP FREQ - Prior to placement
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I, R
checkpoint | 17 - Sealing
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Pavement pre-seal inspection & Signoff
label | APPLICABLE DOCUMENTS - Contract Documents NZS 4404:2010, NZTA P/3
label | INSP FREQ - Prior to Sealing
label | INSPECTOR / RESULT: SCCL - SUP, QA, H, I
label | INSPECTOR / RESULT: Engineer - I
holdpoint | HOLD POINT
checkpoint | 18 - Sealing
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Obtain confirmation that Sealing materials and process is in accordance with contract documents and specifications
label | APPLICABLE DOCUMENTS - Contract Documents NZS 4404:2010, NZTA P/3
label | INSP FREQ - Prior to Sealing
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I, R
section | Pavement & Testing
checkpoint | 19 - Site Rails
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Ensure site rails are constructed as per the contract documents NZTA requirements
label | APPLICABLE DOCUMENTS - Techincal specifications and NZS 4404:2010
label | INSP FREQ - Prior to and during construction
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I
checkpoint | 19 - Concrete
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Concrete aprons
label | ○ Concrete compressive strength of 25 Mpa
label | APPLICABLE DOCUMENTS - NZS4404:2010 Section 4, NZS 3109:1997, NZS 3104:2003
label | INSP FREQ - Upon ordering and during placement
label | INSPECTOR / RESULT: SCCL - SUP, QA, M, I
label | INSPECTOR / RESULT: Engineer - I
section | Completion
checkpoint | 20 - Completion of works
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Punchlist items closed out
label | ○ Tidy area, Engineer's final inspection
label | APPLICABLE DOCUMENTS - Contract Documents
label | INSP FREQ - On Completion
label | INSPECTOR / RESULT: SCCL - QA, H
label | INSPECTOR / RESULT: Engineer - H, I
holdpoint | HOLD POINT
checkpoint | 21 - Complete AS Built dwgs submit to Client for approval
label | RESPONSIBILITY - SCCL
label | INSPECTION FUNCTION - Transmit to client for final review
label | APPLICABLE DOCUMENTS - Technical Specifications Contact drawings ISO 9001
label | INSP FREQ - Upon final inspection
label | INSPECTOR / RESULT: SCCL - QA, H
label | INSPECTOR / RESULT: Engineer - I, R
holdpoint | HOLD POINT