## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | Richmond Area Cycleway and Raised Crossings |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 553802 |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Tasman District Council |  |  |  |  | B | Report by Breach | C | Contractor | Downer
Contract Number: | C1378 |  |  |  |  | C | Check | SC1 | Subcontractor | Nelmac
Area/ Sub-System: | Transport Choices |  | Lot ID Number: |  |  | D | Dimension Inspection | SC2 | Subcontractor | IKC
[6 empty] | E | Examine | SC3 | Subcontractor | Civil Engineering Labs
ITP Number: | 1 |  | Version: | 1 |  | H | Hold Point | SC4 | Subcontractor | Town and Country Surveyors
ITP Description: | Richmond Area Cycleway and Raised Crossings, all works areas |  |  |  |  | I | Inspection | EN | Engineer | WSP
Discipline: | Civil Construction |  |  |  |  | M | Monitor on Random Basis | CU | Customer | Tasman District Council
Specification: | [5 empty] | O | Operation
[6 empty] | R | Review
Drawings: | Sheet C350 - C391 |  |  |  |  | S | Subcontractor
[6 empty] | V | Visual Verification
Prepared By: (Name) | Tyler Peppin |  | Date: | 2023-12-10 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
1 | Preliminary and General
1.1 | Service Locates | / | Services located by Delta, Chorus and TDC prior to commencing works. | Photos | Once for each location | Hold Point | W, H | Downer
1.2 | Potholing of Services | Potholing plan to be submitted to Engineer five working days prior to possession of site. Plan to include timing and locations of potholing. | Engineer accepts potholing plan, potholing of services happens, asbuilts and photos of potholed services. | As-Builts, Photos | Multiple times at each location | Hold Point | W,A,H | Downer, WSP
1.3 | Temp. Traffic Management | Temp. Traffic Management to be set up daily before work can commence | Temp. Traffic Management set up by qualified STMS according to approved plans. | Approved TMP | Every Day | Hold Point | A,H | Downer
1.4 | Shutdown of Water Mains | Letters with information related to water shutdowns to be delivered to affected residents by Downer | Letters to be delivered a minumum of three working days prior to shutdowns | / | When Required | Hold Point | A,H | Downer
1.5 | Letter Drop | Letters to be forwarded to Engineer 5 days prior to distribution for approval | Approved letters distributed to directly affected residents atleast one week prior to works | / | Once for each location | Hold Point | A,H | Downer, WSP
1.6 | Bulk Water Permit | The contractor shall obtain a permit from the Principal in order to take bulk water form the Councils water supply. | Bulk Water Permit obtained from the Principal | Bulk Water Permit | Once | Hold Point | H | Downer, Tasman District Council
1.7 | As-Built Drawings and Plans | As-Built drawings shall be completed throughout the construction period as appropriate stages of work are complete,so these can be checked as work proceeds. As build plans are required. | As-builts are obtained by competent surveyor, loaded onto Auto CAD for plans | / | Every Stage | / | / | Downer, Town and Country Surveyors
1.8 | Drainage Network and Water Supply Protection | Drainage network and water supply to be protected and maintained in service prior to works commencing | Protection in place as per approved EMP | Approved EMP | Once for each location | Hold Point | H,V | Downer
1.9 | Utility Establishment | The Contractor shall arrange with the utility operator concerned for the use of such utilities as are required for the purpose of the contract, shall establish accounts, and pay for all such services consumed, and shall reinstate the connections on completion. | Accounts established with utility providers. | / | Once | Hold Point | H,A | Downer
1.1O | Preperation of Documents | Documents to be reviewed by Engineer and TDC prior to works | Approved Documents | / | Once | Hold Point | H | Downer, Tasman District Council, WSP
1.11 | Installation of Project Signs | Layout to be approved by Engineer prior to installation | Approved project signs installed at both ends of sites prior to works | / | Once for each location | Hold Point | H | Downer, WSP
2 | Champion Rd/Kareti Drive
2.1 | Site Clearance | Removal of all vegetation, trimming of overhanging branches and encroaching shrubs, removal of trees and their root systems to 1.0m clear of any pavement or services construction. Removal and storage of existing signs | Site clearance undertaken, all obstacles removed | Photos | Once | Visual Verification | V | Downer, Nelmac
2.2 | Removal of existing pedestrian crossing islands | / | Existing pedesterian crossing islands are removed | Photos | Once | Visual Verification | V | Downer
2.3 | Reinstate road surface | Reinstaing the road surface where the pedestrian crossings were removed | Road surface is reinstated | Photos | Once | Visual Verification | V | Downer
2.4 | Removal of kerb drop down + reinstate to full height kerb | Cleggs to be done on basecourse | Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25 | Inspection | Once | Hold Point | V, I, H | Downer, IKC
2.5 | Construct new asphalt raised table | / | New asphalt raised table is contructed as per design - Refer detail shown on C390 | Photos | Once | Visual Verification | V | Downer
2.6 | Sawcut and remove existing concrete footpath | / | Existing concrete footpath is removed as per plan. | Photos | Once | Visual Verification | V | Downer
2.7 | Cut to waste - 200mm depth | / | Removed material is disposed of at contractors dump site | Photos | Once | Visual Verification | V | Downer
2.8 | Construct new concrete footpath widening - width varies 0.7 - 1.2m | Clegg hammer tests on basecourse before concreting. | As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. Refer detail shown on C391. (100mm Concrete, 100mm AP40.) | Inspection | Once | Hold Point | V,I,H | Downer, IKC
2.9 | Install new kerb drop down cycle ramp entry - 3m |  | New kerb drop down cycle ramp entry constructed as per plan | Photos | Four Times | Visual Verification | V | Downer
3 | Champion Rd/Hill Street
3.1 | Site Clearance | Removal of all vegetation, trimming of overhanging branches and encroaching shrubs, removal of trees and their root systems to 1.0m clear of any pavement or services construction. Removal and storage of existing signs | Site clearance undertaken, all obstacles removed | Photos | Once | Visual Verification | V | Downer, Nelmac
3.2 | Removal of kerb drop down + reinstate to full height kerb | Cleggs to be done on basecourse | Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25 | Inspection | Once | Hold Point | V, I, H | Downer, IKC
3.3 | Sawcut and remove existing concrete footpath | / | Existing concrete footpath is removed as per plan. | Photos | Once | Visual Verification | V | Downer
3.4 | Construct new asphalt raised table on Champion Rd | / | New asphalt raised table is contructed as per design - Refer detail shown on C390 | Photos | Once | Visual Verification | V | Downer
3.5 | Construct new asphalt raised table on Hill St | / | New asphalt raised table is contructed as per design - Refer detail shown on C390 | Photos | Once | Visual Verification | V | Downer
3.6 | Cut to waste - 200mm depth | / | Removed material is disposed of at contractors dump site | Photos | Once | Visual Verification | V | Downer
3.7 | Construct new concrete footpath | Clegg hammer tests on basecourse before concreting. | As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. Refer detail shown on C391. (100mm Concrete, 100mm AP40.) | Inspection | Once | Hold Point | V,I, H | Downer, IKC
3.8 | Install new kerb drop down cycle ramp entry - 3m | / | New kerb drop down cycle ramp entry constructed as per plan | Photos | Four Times | Visual Verification | V | Downer
3.9 | Construct new grass berm | / | As per NTLDM | Photos | Once | Visual Verification | V | Downer
4 | Berryfields Access
4.1 | Remove garden and vegetation and reinstate asphalt footpath | Clegg hammer tests on basecourse before asphalting. | As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. (25mm thick AC and 150mm of AP40.) | Inspection | Once | Hold Point | V,I,H | Downer
4.2 | New kerb and channel | Cleggs to be done on basecourse | Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25 | Inspection | Once | Hold Point | V,I,H | Downer, IKC
4.3 | New mountable kerb on existing seal surface | Cleggs to be done on basecourse | Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25 | Inspection | Once | Hold Point | V,I,H | Downer, IKC
4.4 | New exposed aggregate reinforced concrete | / | 100mm thick reinforced exposed aggregate concrete, 100mm AP40. To NTLDM standards | Photos | Once | Visual Verification | V | Downer
4.5 | Construct new reinforced concrete flush pads | / | 0.5m x 0.2m, 100mm AP40. To NTLDM standards | Photos | Once | Visual Verification | V | Downer
4.6 | Construct new asphalt speed hump. | / | As per design, 3m wide x 100mm high. Refer to detail shown on C390 | Photos | Twice | Visual Verification | V | Downer
4.7 | Construct new asphalt speed hump. | / | As per design, 6m wide x 100mm high. Refer to detail shown on C390 | Photos | Twice | Visual Verification | V | Downer
4.8 | Prepare and lay asphalt to match existing surface at speed hump | Pre Seal Inspection | Pass pre seal inspection, approval to lay asphalt | Inspection | Once | Hold Point | V,I,H | Downer, WSP
4.9 | Install new kerb drop down cycle ramp entry - 3m | / | New kerb drop down cycle ramp entry constructed as per plan | Photos | Once | Visual Verification | V | Downer
4.1O | Install timber edging | / | 100 x 25 timber h4 treated. As per NTLDM | Photos | Once | Visual Verification | V | Downer
4.11 | Prepare existing pavement and place AP40 basecourse | NDM on basecourse | 150mm AP40, NDMs: ≥ 98% ave at MDD. ≥ 95% min | Inspection | Once | Hold Point | V,I,H | Downer, Civil Engineering Labs
4.12 | Two coat chipseal | / | As per design | Photos | Once | Visual Verification | V | Downer
4.13 | Construct new garden areas | / | As per specification (planting done by others) | Photos | Once | Visual Verification | V | Downer
4.14 | Supply and install steel powder coated fence | / | 1.2m high | Photos | Once | Visual Verification | V | Downer
4.15 | Supply and install hoop cycle racks | / | As per NTLDM | Photos | Four Times | Visual Verification | V | Downer
5 | Church Street
5.1 | Construct new asphalt raised table on Champion Rd | / | New asphalt raised table is contructed as per design - Refer detail shown on C390 | Photos | Once | Visual Verification | V | Downer
5.2 | Install new kerb drop down cycle ramp entry - 3m | / | New kerb drop down cycle ramp entry constructed as per plan | Photos | Once | Visual Verification | V | Downer
5.3 | Remove and dispose existing kerb and channel | / | As per design. | Photos | Once | Visual Verification | V | Downer
5.4 | New kerb and channel including shoulder reinstatement | Cleggs to be done on basecourse | Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25 | Inspection | Once | Hold Point | V,I,H | Downer, IKC
5.5 | Cut to waste - 200mm depth | / | Removed material is disposed of at contractors dump site | Photos | Once | Visual Verification | V | Downer
5.6 | Remove and dispose of existing asphalt | / | As per design. | Photos | Once | Visual Verification | V | Downer
5.7 | Construct new concrete footpath widening - width varies 0.8 - 1.55m | Clegg hammer tests on basecourse before concreting. | As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. Refer detail shown on C391. (100mm Concrete, 100mm AP40.) | Inspection | Once | Hold Point | V,I,H | Downer, IKC
5.8 | Construct new driveway enterance - excluding kerb and channel | Cleggs to be done on subgrade, NDMs to be done on basecourse | Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. To NTLDM standards | Inspection | Once | Hold Point | V,I,H | Downer, Civil Engineering Labs
5.9 | Lay asphalt to driveway enterance to match existing footpath | Pre Seal Inspection | Pass pre seal inspection, approval to lay asphalt | Inspection | Once | Hold Point | V,I,H | Downer, WSP
5.1O | Relocate existing timber fence to boundary | Survey Set Out | New set out along boundary line for relocation of existing fence. | Inspection | Once | Hold Point | V,I,H | Downer, Town and Country Surveyors
6 | Dorset Street
6.1 | Site Clearance | Removal of all vegetation, trimming of overhanging branches and encroaching shrubs, removal of trees and their root systems to 1.0m clear of any pavement or services construction. Removal and storage of existing signs | Site clearance undertaken, all obstacles removed | Photos | Once | Visual Verification | V | Downer, Nelmac
6.2 | Remove existing fence at 15 Cambridge Street | / | As per design. | Photos | Once | Visual Verification | V | Downer
6.3 | Remove and dispose of existing kerb and channel | / | As per design. | Photos | Once | Visual Verification | V | Downer
6.4 | New kerb and channel including shoulder reinstatement | Cleggs to be done on basecourse | Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25 | Inspection | Once | Hold Point | V,I,H | Downer, IKC
6.5 | Construct new asphalt raised table | / | New asphalt raised table is contructed as per design - Refer detail shown on C390 | Photos | Once | Visual Verification | V | Downer
6.6 | Sawcut and remove existing asphalt footpath and construct new asphalt footpath | Clegg hammer tests on basecourse before asphalting. | As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. (25mm thick AC and 150mm of AP40.) | Inspection | Once | Hold Point | V,I,H | Downer
7 | Cambridge Street and Oxford Street
7.1 | Removal of existing traffic islands | / | Existing traffic islands are removed | Photos | Once | Visual Verification | V | Downer
7.2 | Reinstate road surface with asphalt | Reinstaing the road surface with asphalt where the pedestrian crossings were removed | Road surface is reinstated with asphalt | Photos | Once | Visual Verification | V | Downer
7.3 | Removal of existing build outs on Oxford Street | / | Existing build outs are removed | Photos | Once | Visual Verification | V | Downer
7.4 | Replace existing timber lap boundary fence as shown | / | As per design. | Photos | Once | Visual Verification | V | Downer
7.5 | Remove and dispose of existing kerb and channel | / | As per design. | Photos | Once | Visual Verification | V | Downer
7.6 | Cut to waste - 200mm depth | / | Removed material is disposed of at contractors dump site | Photos | Once | Visual Verification | V | Downer
7.7 | Construct new asphalt raised table (Cambridge Street) | / | New asphalt raised table is contructed as per design - Refer detail shown on C390 | Photos | Once | Visual Verification | V | Downer
7.8 | Construct new asphalt raised table (Oxford Street) | / | New asphalt raised table is contructed as per design - Refer detail shown on C390 | Photos | Once | Visual Verification | V | Downer
7.9 | Sawcut and remove existing asphalt footpath and construct new asphalt footpath | Clegg hammer tests on basecourse before asphalting. | As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. (25mm thick AC and 150mm of AP40.) | Inspection | Once | Hold Point | V,I,H | Downer
7.1O | Construct new asphalt footpath widening. 0.9m width | Clegg hammer tests on basecourse before asphalting. | As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. (25mm thick AC and 150mm of AP40.) | Inspection | Once | Hold Point | V,I,H | Downer
7.11 | Install new kerb drop down cycle ramp entry - 3m | / | New kerb drop down cycle ramp entry constructed as per plan | Photos | Once | Visual Verification | V | Downer
8 | Utilities
8.1 | Installation of New Stormwater Sumps | Cleggs to be done on AP65, NDMs to be done on basecourse. | Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. As per design specifications and NTLDM. Depth to connecting pipes invert 1.0-1.5 m. | Inspection | Twenty One Times | Hold Point | V,I,H | Downer, Tasman District Council, WSP, Civil Engineering Labs
8.2 | Installation of DN100 uPVC Pipe Connections | Cleggs to be done on AP65, NDMs to be done on basecourse. | As per design and NTLDM. Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. Depth of 1.0-1.5m in carrageway | Inspection | When Required | Hold Point | V,I,H | Downer, Tasman District Council, WSP, Civil Engineering Labs
8.3 | Installation of DN225 Class 4 RCRRJ Pipe Connections | Cleggs to be done on AP65, NDMs to be done on basecourse. | As per design and NTLDM. Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. Depth of 1.0-1.5m in carrageway | Inspection | When Required | Hold Point | V,I,H | Downer, Tasman District Council, WSP, Civil Engineering Labs
8.4 | Installation of new DN300 Class 4 RCRRJ Pipe Connections | Cleggs to be done on AP65, NDMs to be done on basecourse. | As per design and NTLDM. Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. Depth of 1.0-1.5m in carrageway | Inspection | When Required | Hold Point | V,I,H | Downer, Tasman District Council, WSP, Civil Engineering Labs
8.5 | DN300 direct connection to existing DN1050 stormwater line | / | Refer to NTLDM SD526 (pg 233) | Photos | Twice | Visual Verification | V | Downer
8.6 | Install new 1050mm dia concrete manholes | Cleggs to be done on AP65, NDMs to be done on basecourse. | Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. As per design and reference to NTLDM SD511 and SD512 (pg. 218-219). Depth of 1.5-2M | Inspection | Twice | Hold Point | V,I,H | Downer, Tasman District Council, WSP, Civil Engineering Labs
8.7 | Install new 1350mm dia concrete manholes | Cleggs to be done on AP65, NDMs to be done on basecourse. | Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. As per design and reference to NTLDM SD511 and SD512 (pg. 218-219). Depth of 1.5-2M | Inspection | Twice | Hold Point | V,I,H | Downer, Tasman District Council, WSP, Civil Engineering Labs
8.8 | Removal and disposal of existing sumps and leads and backfill with compacted aggregate | Cleggs to be done on AP65, NDMs to be done on basecourse. | Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. As per design and NTLDM | Inspection | Twice | Hold Point | V,I,H | Downer, Tasman District Council, WSP, Civil Engineering Labs
8.9 | Raise existing stormwater manhole lid to new finished level | / | Reference to material note 7 and NTLDM | Photos | Three Times | Visual Verification | V | Downer
8.1O | Raise existing water valves | / | As per design and NTLDM | Photos | Four Times | Visual Verification | V | Downer
8.11 | Raise existing water meter box | / | As per design and NTLDM | Photos | Four Times | Visual Verification | V | Downer

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.10

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
5.10
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: