## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DG-QA-TP018 Inspection and Test Plan (ITP) | itp |  |  |  |  | DG-QA-TP018 Inspection and Test Plan (ITP)
section | 1 - Preliminary and General
checkpoint | 1.1 - Service Locates
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Services located by Delta, Chorus and TDC prior to commencing works.
label | Verifying Document - Photos
label | Frequency - Once for each location
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - W, H
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Potholing of Services
label | Inspection Point: Quality Control Activity - Potholing plan to be submitted to Engineer five working days prior to possession of site. Plan to include timing and locations of potholing.
label | Acceptance Criteria - Engineer accepts potholing plan, potholing of services happens, asbuilts and photos of potholed services.
label | Verifying Document - As-Builts, Photos
label | Frequency - Multiple times at each location
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - W,A,H
label | Inspection: By (Role Key) - Downer, WSP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Temp. Traffic Management
label | Inspection Point: Quality Control Activity - Temp. Traffic Management to be set up daily before work can commence
label | Acceptance Criteria - Temp. Traffic Management set up by qualified STMS according to approved plans.
label | Verifying Document - Approved TMP
label | Frequency - Every Day
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - A,H
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Shutdown of Water Mains
label | Inspection Point: Quality Control Activity - Letters with information related to water shutdowns to be delivered to affected residents by Downer
label | Acceptance Criteria - Letters to be delivered a minumum of three working days prior to shutdowns
label | Verifying Document - /
label | Frequency - When Required
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - A,H
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Letter Drop
label | Inspection Point: Quality Control Activity - Letters to be forwarded to Engineer 5 days prior to distribution for approval
label | Acceptance Criteria - Approved letters distributed to directly affected residents atleast one week prior to works
label | Verifying Document - /
label | Frequency - Once for each location
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - A,H
label | Inspection: By (Role Key) - Downer, WSP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Bulk Water Permit
label | Inspection Point: Quality Control Activity - The contractor shall obtain a permit from the Principal in order to take bulk water form the Councils water supply.
label | Acceptance Criteria - Bulk Water Permit obtained from the Principal
label | Verifying Document - Bulk Water Permit
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - Downer, Tasman District Council
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - As-Built Drawings and Plans
label | Inspection Point: Quality Control Activity - As-Built drawings shall be completed throughout the construction period as appropriate stages of work are complete,so these can be checked as work proceeds. As build plans are required.
label | Acceptance Criteria - As-builts are obtained by competent surveyor, loaded onto Auto CAD for plans
label | Verifying Document - /
label | Frequency - Every Stage
label | Inspection Type (Visual, other) - /
label | Inspection: Key - /
label | Inspection: By (Role Key) - Downer, Town and Country Surveyors
checkpoint | 1.8 - Drainage Network and Water Supply Protection
label | Inspection Point: Quality Control Activity - Drainage network and water supply to be protected and maintained in service prior to works commencing
label | Acceptance Criteria - Protection in place as per approved EMP
label | Verifying Document - Approved EMP
label | Frequency - Once for each location
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H,V
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - Utility Establishment
label | Inspection Point: Quality Control Activity - The Contractor shall arrange with the utility operator concerned for the use of such utilities as are required for the purpose of the contract, shall establish accounts, and pay for all such services consumed, and shall reinstate the connections on completion.
label | Acceptance Criteria - Accounts established with utility providers.
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H,A
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.10 - Preperation of Documents
label | Inspection Point: Quality Control Activity - Documents to be reviewed by Engineer and TDC prior to works
label | Acceptance Criteria - Approved Documents
label | Verifying Document - /
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - Downer, Tasman District Council, WSP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.11 - Installation of Project Signs
label | Inspection Point: Quality Control Activity - Layout to be approved by Engineer prior to installation
label | Acceptance Criteria - Approved project signs installed at both ends of sites prior to works
label | Verifying Document - /
label | Frequency - Once for each location
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - Downer, WSP
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Champion Rd/Kareti Drive
checkpoint | 2.1 - Site Clearance
label | Inspection Point: Quality Control Activity - Removal of all vegetation, trimming of overhanging branches and encroaching shrubs, removal of trees and their root systems to 1.0m clear of any pavement or services construction. Removal and storage of existing signs
label | Acceptance Criteria - Site clearance undertaken, all obstacles removed
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer, Nelmac
checkpoint | 2.2 - Removal of existing pedestrian crossing islands
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Existing pedesterian crossing islands are removed
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 2.3 - Reinstate road surface
label | Inspection Point: Quality Control Activity - Reinstaing the road surface where the pedestrian crossings were removed
label | Acceptance Criteria - Road surface is reinstated
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 2.4 - Removal of kerb drop down + reinstate to full height kerb
label | Inspection Point: Quality Control Activity - Cleggs to be done on basecourse
label | Acceptance Criteria - Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V, I, H
label | Inspection: By (Role Key) - Downer, IKC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Construct new asphalt raised table
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - New asphalt raised table is contructed as per design - Refer detail shown on C390
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 2.6 - Sawcut and remove existing concrete footpath
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Existing concrete footpath is removed as per plan.
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 2.7 - Cut to waste - 200mm depth
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Removed material is disposed of at contractors dump site
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 2.8 - Construct new concrete footpath widening - width varies 0.7 - 1.2m
label | Inspection Point: Quality Control Activity - Clegg hammer tests on basecourse before concreting.
label | Acceptance Criteria - As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. Refer detail shown on C391. (100mm Concrete, 100mm AP40.)
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, IKC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Install new kerb drop down cycle ramp entry - 3m
label | Acceptance Criteria - New kerb drop down cycle ramp entry constructed as per plan
label | Verifying Document - Photos
label | Frequency - Four Times
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
section | 3 - Champion Rd/Hill Street
checkpoint | 3.1 - Site Clearance
label | Inspection Point: Quality Control Activity - Removal of all vegetation, trimming of overhanging branches and encroaching shrubs, removal of trees and their root systems to 1.0m clear of any pavement or services construction. Removal and storage of existing signs
label | Acceptance Criteria - Site clearance undertaken, all obstacles removed
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer, Nelmac
checkpoint | 3.2 - Removal of kerb drop down + reinstate to full height kerb
label | Inspection Point: Quality Control Activity - Cleggs to be done on basecourse
label | Acceptance Criteria - Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V, I, H
label | Inspection: By (Role Key) - Downer, IKC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Sawcut and remove existing concrete footpath
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Existing concrete footpath is removed as per plan.
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 3.4 - Construct new asphalt raised table on Champion Rd
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - New asphalt raised table is contructed as per design - Refer detail shown on C390
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 3.5 - Construct new asphalt raised table on Hill St
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - New asphalt raised table is contructed as per design - Refer detail shown on C390
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 3.6 - Cut to waste - 200mm depth
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Removed material is disposed of at contractors dump site
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 3.7 - Construct new concrete footpath
label | Inspection Point: Quality Control Activity - Clegg hammer tests on basecourse before concreting.
label | Acceptance Criteria - As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. Refer detail shown on C391. (100mm Concrete, 100mm AP40.)
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I, H
label | Inspection: By (Role Key) - Downer, IKC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Install new kerb drop down cycle ramp entry - 3m
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - New kerb drop down cycle ramp entry constructed as per plan
label | Verifying Document - Photos
label | Frequency - Four Times
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 3.9 - Construct new grass berm
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per NTLDM
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
section | 4 - Berryfields Access
checkpoint | 4.1 - Remove garden and vegetation and reinstate asphalt footpath
label | Inspection Point: Quality Control Activity - Clegg hammer tests on basecourse before asphalting.
label | Acceptance Criteria - As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. (25mm thick AC and 150mm of AP40.)
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - New kerb and channel
label | Inspection Point: Quality Control Activity - Cleggs to be done on basecourse
label | Acceptance Criteria - Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, IKC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - New mountable kerb on existing seal surface
label | Inspection Point: Quality Control Activity - Cleggs to be done on basecourse
label | Acceptance Criteria - Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, IKC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - New exposed aggregate reinforced concrete
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - 100mm thick reinforced exposed aggregate concrete, 100mm AP40. To NTLDM standards
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 4.5 - Construct new reinforced concrete flush pads
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - 0.5m x 0.2m, 100mm AP40. To NTLDM standards
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 4.6 - Construct new asphalt speed hump.
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per design, 3m wide x 100mm high. Refer to detail shown on C390
label | Verifying Document - Photos
label | Frequency - Twice
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 4.7 - Construct new asphalt speed hump.
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per design, 6m wide x 100mm high. Refer to detail shown on C390
label | Verifying Document - Photos
label | Frequency - Twice
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 4.8 - Prepare and lay asphalt to match existing surface at speed hump
label | Inspection Point: Quality Control Activity - Pre Seal Inspection
label | Acceptance Criteria - Pass pre seal inspection, approval to lay asphalt
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, WSP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.9 - Install new kerb drop down cycle ramp entry - 3m
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - New kerb drop down cycle ramp entry constructed as per plan
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 4.10 - Install timber edging
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - 100 x 25 timber h4 treated. As per NTLDM
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 4.11 - Prepare existing pavement and place AP40 basecourse
label | Inspection Point: Quality Control Activity - NDM on basecourse
label | Acceptance Criteria - 150mm AP40, NDMs: ≥ 98% ave at MDD. ≥ 95% min
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, Civil Engineering Labs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.12 - Two coat chipseal
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per design
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 4.13 - Construct new garden areas
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per specification (planting done by others)
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 4.14 - Supply and install steel powder coated fence
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - 1.2m high
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 4.15 - Supply and install hoop cycle racks
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per NTLDM
label | Verifying Document - Photos
label | Frequency - Four Times
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
section | 5 - Church Street
checkpoint | 5.1 - Construct new asphalt raised table on Champion Rd
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - New asphalt raised table is contructed as per design - Refer detail shown on C390
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 5.2 - Install new kerb drop down cycle ramp entry - 3m
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - New kerb drop down cycle ramp entry constructed as per plan
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 5.3 - Remove and dispose existing kerb and channel
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per design.
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 5.4 - New kerb and channel including shoulder reinstatement
label | Inspection Point: Quality Control Activity - Cleggs to be done on basecourse
label | Acceptance Criteria - Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, IKC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Cut to waste - 200mm depth
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Removed material is disposed of at contractors dump site
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 5.6 - Remove and dispose of existing asphalt
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per design.
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 5.7 - Construct new concrete footpath widening - width varies 0.8 - 1.55m
label | Inspection Point: Quality Control Activity - Clegg hammer tests on basecourse before concreting.
label | Acceptance Criteria - As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. Refer detail shown on C391. (100mm Concrete, 100mm AP40.)
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, IKC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 - Construct new driveway enterance - excluding kerb and channel
label | Inspection Point: Quality Control Activity - Cleggs to be done on subgrade, NDMs to be done on basecourse
label | Acceptance Criteria - Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. To NTLDM standards
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, Civil Engineering Labs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.9 - Lay asphalt to driveway enterance to match existing footpath
label | Inspection Point: Quality Control Activity - Pre Seal Inspection
label | Acceptance Criteria - Pass pre seal inspection, approval to lay asphalt
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, WSP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.10 - Relocate existing timber fence to boundary
label | Inspection Point: Quality Control Activity - Survey Set Out
label | Acceptance Criteria - New set out along boundary line for relocation of existing fence.
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, Town and Country Surveyors
holdpoint | AUTHORITY HOLDPOINT
section | 6 - Dorset Street
checkpoint | 6.1 - Site Clearance
label | Inspection Point: Quality Control Activity - Removal of all vegetation, trimming of overhanging branches and encroaching shrubs, removal of trees and their root systems to 1.0m clear of any pavement or services construction. Removal and storage of existing signs
label | Acceptance Criteria - Site clearance undertaken, all obstacles removed
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer, Nelmac
checkpoint | 6.2 - Remove existing fence at 15 Cambridge Street
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per design.
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 6.3 - Remove and dispose of existing kerb and channel
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per design.
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 6.4 - New kerb and channel including shoulder reinstatement
label | Inspection Point: Quality Control Activity - Cleggs to be done on basecourse
label | Acceptance Criteria - Refer to detail on sheet C390. Clegg Inpact Value to be greater than 25
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, IKC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.5 - Construct new asphalt raised table
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - New asphalt raised table is contructed as per design - Refer detail shown on C390
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 6.6 - Sawcut and remove existing asphalt footpath and construct new asphalt footpath
label | Inspection Point: Quality Control Activity - Clegg hammer tests on basecourse before asphalting.
label | Acceptance Criteria - As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. (25mm thick AC and 150mm of AP40.)
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
section | 7 - Cambridge Street and Oxford Street
checkpoint | 7.1 - Removal of existing traffic islands
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Existing traffic islands are removed
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 7.2 - Reinstate road surface with asphalt
label | Inspection Point: Quality Control Activity - Reinstaing the road surface with asphalt where the pedestrian crossings were removed
label | Acceptance Criteria - Road surface is reinstated with asphalt
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 7.3 - Removal of existing build outs on Oxford Street
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Existing build outs are removed
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 7.4 - Replace existing timber lap boundary fence as shown
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per design.
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 7.5 - Remove and dispose of existing kerb and channel
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per design.
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 7.6 - Cut to waste - 200mm depth
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Removed material is disposed of at contractors dump site
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 7.7 - Construct new asphalt raised table (Cambridge Street)
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - New asphalt raised table is contructed as per design - Refer detail shown on C390
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 7.8 - Construct new asphalt raised table (Oxford Street)
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - New asphalt raised table is contructed as per design - Refer detail shown on C390
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 7.9 - Sawcut and remove existing asphalt footpath and construct new asphalt footpath
label | Inspection Point: Quality Control Activity - Clegg hammer tests on basecourse before asphalting.
label | Acceptance Criteria - As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. (25mm thick AC and 150mm of AP40.)
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.10 - Construct new asphalt footpath widening. 0.9m width
label | Inspection Point: Quality Control Activity - Clegg hammer tests on basecourse before asphalting.
label | Acceptance Criteria - As per NTLDM 4.22.4 - Clegg Inpact Value to be greater than 25. (25mm thick AC and 150mm of AP40.)
label | Verifying Document - Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.11 - Install new kerb drop down cycle ramp entry - 3m
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - New kerb drop down cycle ramp entry constructed as per plan
label | Verifying Document - Photos
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
section | 8 - Utilities
checkpoint | 8.1 - Installation of New Stormwater Sumps
label | Inspection Point: Quality Control Activity - Cleggs to be done on AP65, NDMs to be done on basecourse.
label | Acceptance Criteria - Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. As per design specifications and NTLDM. Depth to connecting pipes invert 1.0-1.5 m.
label | Verifying Document - Inspection
label | Frequency - Twenty One Times
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, Tasman District Council, WSP, Civil Engineering Labs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 - Installation of DN100 uPVC Pipe Connections
label | Inspection Point: Quality Control Activity - Cleggs to be done on AP65, NDMs to be done on basecourse.
label | Acceptance Criteria - As per design and NTLDM. Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. Depth of 1.0-1.5m in carrageway
label | Verifying Document - Inspection
label | Frequency - When Required
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, Tasman District Council, WSP, Civil Engineering Labs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.3 - Installation of DN225 Class 4 RCRRJ Pipe Connections
label | Inspection Point: Quality Control Activity - Cleggs to be done on AP65, NDMs to be done on basecourse.
label | Acceptance Criteria - As per design and NTLDM. Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. Depth of 1.0-1.5m in carrageway
label | Verifying Document - Inspection
label | Frequency - When Required
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, Tasman District Council, WSP, Civil Engineering Labs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.4 - Installation of new DN300 Class 4 RCRRJ Pipe Connections
label | Inspection Point: Quality Control Activity - Cleggs to be done on AP65, NDMs to be done on basecourse.
label | Acceptance Criteria - As per design and NTLDM. Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. Depth of 1.0-1.5m in carrageway
label | Verifying Document - Inspection
label | Frequency - When Required
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, Tasman District Council, WSP, Civil Engineering Labs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.5 - DN300 direct connection to existing DN1050 stormwater line
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Refer to NTLDM SD526 (pg 233)
label | Verifying Document - Photos
label | Frequency - Twice
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 8.6 - Install new 1050mm dia concrete manholes
label | Inspection Point: Quality Control Activity - Cleggs to be done on AP65, NDMs to be done on basecourse.
label | Acceptance Criteria - Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. As per design and reference to NTLDM SD511 and SD512 (pg. 218-219). Depth of 1.5-2M
label | Verifying Document - Inspection
label | Frequency - Twice
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, Tasman District Council, WSP, Civil Engineering Labs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.7 - Install new 1350mm dia concrete manholes
label | Inspection Point: Quality Control Activity - Cleggs to be done on AP65, NDMs to be done on basecourse.
label | Acceptance Criteria - Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. As per design and reference to NTLDM SD511 and SD512 (pg. 218-219). Depth of 1.5-2M
label | Verifying Document - Inspection
label | Frequency - Twice
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, Tasman District Council, WSP, Civil Engineering Labs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.8 - Removal and disposal of existing sumps and leads and backfill with compacted aggregate
label | Inspection Point: Quality Control Activity - Cleggs to be done on AP65, NDMs to be done on basecourse.
label | Acceptance Criteria - Clegg Inpact Value to be greater than 25. NDMs: ≥ 98% ave at MDD. ≥ 95% min. As per design and NTLDM
label | Verifying Document - Inspection
label | Frequency - Twice
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - V,I,H
label | Inspection: By (Role Key) - Downer, Tasman District Council, WSP, Civil Engineering Labs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.9 - Raise existing stormwater manhole lid to new finished level
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - Reference to material note 7 and NTLDM
label | Verifying Document - Photos
label | Frequency - Three Times
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 8.10 - Raise existing water valves
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per design and NTLDM
label | Verifying Document - Photos
label | Frequency - Four Times
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer
checkpoint | 8.11 - Raise existing water meter box
label | Inspection Point: Quality Control Activity - /
label | Acceptance Criteria - As per design and NTLDM
label | Verifying Document - Photos
label | Frequency - Four Times
label | Inspection Type (Visual, other) - Visual Verification
label | Inspection: Key - V
label | Inspection: By (Role Key) - Downer