## ChecklistsITCs
Delete rows that aren't applicable to the project, then create the project breakdown and send to CONQA
type | name | values | prefix | postfix
checklist | Site Establishment and Safety Checklist | Pass, Fail
checkpoint | Delivery and goods lift location
checkpoint | Delivery requirements i.e. booking process
checkpoint | On site storage / office location
checkpoint | Site specific restrictions i.e. noise / starting times
checklist | Ductwork Checklist | Pass, Fail
checkpoint | Rectangular duct installed as per latest drawing | Yes, No
checkpoint | Duct flanges firmly bolted and sealed where required | Yes, No
checkpoint | Cleats installed as required | Yes, No
checkpoint | Correct hanger spacing / supports installed | Yes, No
checkpoint | Ductwork insulated where required and damage free | Yes, No, N/A
checkpoint | Ductwork restrained for wind/seismic where required | Yes, No, N/A
checkpoint | Any required ductwork leakage testing | Yes, No, N/A
checkpoint | Spiral installed as per latest drawing | Yes, No, N/A
checkpoint | Spiral joins sealed correctly | Yes, No, N/A
checkpoint | Correct hanger spacing / supports installed for spiral | Yes, No, N/A
checkpoint | Spiral insulated where required and damage free | Yes, No, N/A
checkpoint | Additional taping/sealing to medium/high pressure spiral | Yes, No, N/A
checkpoint | Pops & flex installed as per latest drawing | Yes, No, N/A
checkpoint | Correct hanger spacing / supports installed for flex | Yes, No, N/A
checkpoint | Free from support off other services | Yes, No, N/A
checkpoint | Flexible duct connections completed correctly | Yes, No, N/A
checkpoint | Blade dampers installed as documented and left in the open position | Yes, No, N/A
checkpoint | BD pop access panel coordinated and marked | Yes, No, N/A
checkpoint | Cushion boxes installed as per latest drawing | Yes, No
checkpoint | Balancing dampers installed as documented and left in the open position | Yes, No, N/A
checkpoint | Location of register coordinted with other services and marked on plan or floor | Yes, No
checkpoint | Volume Control Dampers installed as per latest drawing | Yes, No
checkpoint | Motorised dampers installed as per latest drawing / actuator fit off | Yes, No, N/A
checkpoint | Smoke dampers installed as per latest drawing / actuator fit off | Yes, No, N/A
checkpoint | Damper access panels coordinated and marked | Yes, No
checklist | Equipment Checklist | Pass, Fail
checkpoint | Correct unit correctly supported as per project engineering requirements | Yes, No
checkpoint | Correct unit installed as per latest drawing | Yes, No
checkpoint | Flexible connections installed and sealed | Yes, No
checkpoint | Access to filter bank / filters installed | Yes, No, N/A
checkpoint | Access to all relevant controls and isolators | Yes, No
checkpoint | Access panel coordinated and marked | Yes, No
checkpoint | Seismic bracing to requirements | Yes, No, N/A
checkpoint | Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below) | Yes, No
checklist | Pipework Checklist
checkpoint | Installed as per latest drawing | Yes, No
checkpoint | Correct heights i.e. underside as per drawings | Yes, No
checkpoint | Pipe fittings complete | Yes, No
checkpoint | Clips complete | Yes, No
checkpoint | Insulation complete | Yes, No
checkpoint | Air bleed complete (installed at all floor high points) | Yes, No
checkpoint | Correct flow and return checked | Yes, No
checkpoint | Access to valve sets checked' | Yes, No
checkpoint | No other services suspended from pipe work | Yes, No
checkpoint | Damage free | Yes, No
checkpoint | Piping cleaned and flushed | Yes, No, N/A
checkpoint | Pipe tested and recorded as per Pipe Testing ITP | Yes, No, N/A
checkpoint | Initial pipe pressure test (attach photo below) | Yes, No, N/A
checkpoint | 24hr pipe pressure test (attach photo below) | Yes, No, N/A
Checklist | Fire Damper | Pass, Fail
checkpoint | Fire damper installed as per latest drawing | Yes, No
checkpoint | Fire damper installed as per manufacturer's installation guide | Yes, No
checkpoint | Fire Damper labelled with Mechonik's sticker | Yes, No
checkpoint | Damper access installed in duct | Yes, No
checkpoint | Access panel installed on RCP for maintenance/ inspection access | Yes, No
Checklist | Drains | Pass, Fail
checkpoint | Drain trapped where required | Yes, No
checkpoint | Correct hanger spacing / fall | Yes, No
checkpoint | Drain tested | Pass, Fail
checkpoint | Drain pump installed level and tested | Yes, No
checkpoint | Drain terminates at a tundish | Yes, No
checkpoint | Drains, pump and tundish access for maintenance. | Yes, No
checklist | Outdoor Equipment | Pass, Fail
checkpoint | Unit correctly supported as per project engineering requirements | Yes, No, N/A
checkpoint | Correct unit installed as per latest drawing | Yes, No, N/A
checkpoint | Access to all relevant controls, isolators and maintenance items | Yes, No, N/A
checkpoint | Floor or Platform Mounted Thermal Plant correctly supported as per project engineering requirements | Yes, No, N/A
checkpoint | Maintenance and ventilation clearance maintained as per manufacturer's specs | Yes, No, N/A
checkpoint | All manufacturer specific requirements have been provided in addition to project requirements | Yes, No, N/A
checklist | Grille Fit-Off Checklist | Pass, Fail, N/A
checkpoint | Grilles installed in correct location as per latest duct layout / RCP | Yes, No
checkpoint | Correct grille type installed | Yes, No
checkpoint | Grille installed flush and square | Yes, No
checkpoint | Are all grilles installed correctly? Air leaks, vibration or failure | Yes, No
checkpoint | Grille color as per schedule | Yes, No
checkpoint | Grille left clean of fingerprints and caps installed where required | Yes, No
checkpoint | Grille fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below) | Yes, No
checklist | Refrigeration Pipe Checklist | Pass, Fail, N/A
checkpoint | Correct IDU & ODU installed as per latest drawing & schedule | Yes, No
checkpoint | Installed as per latest drawings | Yes, No
checkpoint | No other services suspended from pipe work (Attach Photos below) | Yes, No
checkpoint | Installation damage free (Any Issues comment/attach Photos below) | Yes, No
checkpoint | Correct supports used and support spacing | Yes, No
checkpoint | Pipe labelled after insulation - provide photo evidence | Yes, No
checkpoint | Pipe mains installation completed to drawings/specification | Yes, No
checkpoint | Pipework system pressure tested | Pass, Fail, N/A
checkpoint | Area left clean and tidy - photos of cleanliness or issues | Yes, No
checklist | All Subbie Rough-in Progression Checklist | Complete, Incomplete
checkpoint | All work in zone completed and appear compliant | Yes, No
label | Pass once all work complete
checklist | All Subbie Fit off & Testing Progression Checklist | Complete, Incomplete
checkpoint | All work in zone completed and appear compliant | Yes, No
label | Pass once all work complete
checklist | As Builts Checklist | Complete, Incomplete
button | Update As-Built's of any known changes | Yes, No
checklist | Penetration Details
checkpoint | Wall penetration sealing to requirements

## TO BUILD - FCU
Project Breakdown |  |  | Checklists
PROJECT NAME: PHILLIP ISLAND COMMUNITY HOSPITAL
OHS |  |  | Site Establishment and Safety Checklist
| Level 1 | FCU-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
Grille Fit-Off Checklist
FCU-1-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
Grille Fit-Off Checklist
FCU-1-04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
Grille Fit-Off Checklist
FCU-1-05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
Grille Fit-Off Checklist
FCU-1-06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
Grille Fit-Off Checklist
FCU-1-07
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
Grille Fit-Off Checklist
FCU-1-08
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
Grille Fit-Off Checklist
FCU-1-09
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
Grille Fit-Off Checklist
FCU-1-10
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
Grille Fit-Off Checklist
| Level 2 | FCU-2-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
Grille Fit-Off Checklist
| Level 3 Roof | FCU-R-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
Grille Fit-Off Checklist

## TO BUILD - AHU
Project Breakdown |  |  | Checklists
PROJECT NAME: PHILLIP ISLAND COMMUNITY HOSPITAL
OHS |  |  | Site Establishment and Safety Checklist
| Level 3 Roof | AHU-R-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-07
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-08
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-09
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-10
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-11
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-12
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-13
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
AHU-R-14
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist
HRU-GEF-R-09
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Outdoor Equipment
Pipework Checklist

## TO BUILD - Fans
Project Breakdown |  |  | Checklists
PROJECT NAME: PHILLIP ISLAND COMMUNITY HOSPITAL
OHS |  |  | Site Establishment and Safety Checklist
Site QA | Level 1 | GEF-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-1-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-1-03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-1-04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-1-05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-1-06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-1-07
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-1-09
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-1-10
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-1-11
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-1-12
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-1-13
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
TEF-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
OAF-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
OAF-1-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
OAF-1-04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
| Level 2 | GEF-2-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-2-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
| Level 3 Roof | GEF-R-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-R-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-R-03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-R-04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-R-05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
GEF-R-06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
TEF-R-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
TEF-R-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
TEF-R-03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
ISO-R-01A
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
ISO-R-01B
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
RAF-R-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
RAF-R-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
RAF-R-03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
RAF-R-04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
RAF-R-06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
RAF-R-07
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
RAF-R-08
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
RAF-R-09
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
RAF-R-10
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
RAF-R-12
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
RAF-R-14
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist

## TO BUILD - VAV
Project Breakdown |  |  | Checklists
PROJECT NAME: PHILLIP ISLAND COMMUNITY HOSPITAL
OHS |  |  | Site Establishment and Safety Checklist
Site QA | Level 1 | VAV-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
Pipework Checklist
VAV-1-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
Pipework Checklist
VAV-1-03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
Pipework Checklist
VAV-1-04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
Pipework Checklist
VAV-1-05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
Pipework Checklist
VAV-1-06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist
Pipework Checklist
| Level 2 | VAV-2-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Grille Fit-Off Checklist

## TO BUILD - HUMIDIFIER
Project Breakdown |  |  | Checklists
PROJECT NAME: PHILLIP ISLAND COMMUNITY HOSPITAL
OHS |  |  | Site Establishment and Safety Checklist
Site QA | Level 3 Roof | HUM-AHU-R-05ZA
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
HUM-AHU-R-05ZB
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
HUM-AHU-R-06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
HUM-AHU-R-07
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
HUM-AHU-R-10ZA
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
HUM-AHU-R-10ZB
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
HUM-AHU-R-14ZA
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist
HUM-AHU-R-14ZB
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Drains
Equipment Checklist
Pipework Checklist

## TO BUILD - SPLIT DX
Project Breakdown |  |  | Checklists
PROJECT NAME: PHILLIP ISLAND COMMUNITY HOSPITAL
OHS |  |  | Site Establishment and Safety Checklist
Site QA | Level 1 | AC-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Drains
Equipment Checklist
Refrigeration Pipe Checklist
CU-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Drains
Outdoor Equipment
Refrigeration Pipe Checklist

## TO BUILD - HEATING COILS
Project Breakdown |  |  | Checklists
PROJECT NAME: PHILLIP ISLAND COMMUNITY HOSPITAL
OHS |  |  | Site Establishment and Safety Checklist
Site QA | Level 1 | HC-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Pipework Checklist
HC-1-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Pipework Checklist
HC-1-03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Pipework Checklist
HC-1-04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Pipework Checklist
HC-1-05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Pipework Checklist
HC-1-06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Equipment Checklist
Pipework Checklist

## TO BUILD - CHILLERS
Project Breakdown |  |  | Checklists
PROJECT NAME: PHILLIP ISLAND COMMUNITY HOSPITAL
OHS |  |  | Site Establishment and Safety Checklist
Site QA | Level 1 Plantroom | CH-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
CH-1-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist

## TO BUILD - PUMPS
Project Breakdown |  |  | Checklists
PROJECT NAME: PHILLIP ISLAND COMMUNITY HOSPITAL
OHS |  |  | Site Establishment and Safety Checklist
Site QA | Level 1 Plantroom | PCHWP-1-01A
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
PCHWP-1-01B
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
PCHWP-1-02A
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
PCHWP-1-02B
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
PHHWP-1-01A
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
PHHWP-1-01B
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
PHHWP-1-02A
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
PHHWP-1-02B
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
SCHWP-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
SCHWP-1-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
SCHWP-1-03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
SHHWP-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
SHHWP-1-02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
SHHWP-1-03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
| Level 3 Roof | CP-HRU-GEF-R-09
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist

## TO BUILD - ANCILLARIES
Project Breakdown |  |  | Checklists
PROJECT NAME: PHILLIP ISLAND COMMUNITY HOSPITAL
OHS |  |  | Site Establishment and Safety Checklist
Site QA | Level 1 Plantroom | EXP-CHW
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
EXP-HHW
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
CHWT-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
HHWT-1-01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
AFU-CHW
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
AFU-HHW
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
ADS-CHW
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist
ADS-HHW
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Outdoor Equipment
Pipework Checklist