## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Fire Damper |  |  |  |  | Yes | Fire Damper | 41e4a9ce-8611-42ec-922f-865be857f854
checkpoint-status |  |  | checkpoint | Fire damper installed as per latest drawing
checkpoint-status |  |  | checkpoint | Fire damper installed as per manufacturer's installation guide
checkpoint-status |  |  | checkpoint | Fire Damper labelled with Mechonik's sticker
checkpoint-status |  |  | checkpoint | Damper access installed in duct
checkpoint-status |  |  | checkpoint | Access panel installed on RCP for maintenance/ inspection access
checklist-flat |  |  | checklist | All Subbie Fit off & Testing Progression |  |  |  |  | Yes | All Subbie Fit off & Testing Progression Checklist | 50938951-f9f3-477d-a014-a72c565fc742
checkpoint-status |  |  | checkpoint | All work in zone completed and appear compliant
label | d090225d-c612-5bc2-9d60-bbec4a912df1 |  | note | Pass once all work complete
checklist-flat |  |  | checklist | Penetration Details |  |  |  |  | Yes | Penetration Details | 55ec342a-ae25-4b9f-8af1-be463e8a9a3b
checkpoint-status |  |  | checkpoint | Wall penetration sealing to requirements
checklist-flat |  |  | checklist | As Builts |  |  |  |  | Yes | As Builts Checklist | 621bf9c8-78cf-4814-80ef-66b58a5eae8c
checkpoint-status |  |  | checkpoint | Update As-Built's of any known changes
checklist-flat |  |  | checklist | Ductwork |  |  |  |  | Yes | Ductwork Checklist | 67ddb982-368f-49c1-932e-0ceefe38b899
checkpoint-status |  |  | checkpoint | Rectangular duct installed as per latest drawing
checkpoint-status |  |  | checkpoint | Duct flanges firmly bolted and sealed where required
checkpoint-status |  |  | checkpoint | Cleats installed as required
checkpoint-status |  |  | checkpoint | Correct hanger spacing / supports installed
checkpoint-status |  |  | checkpoint | Ductwork insulated where required and damage free
checkpoint-status |  |  | checkpoint | Ductwork restrained for wind/seismic where required
checkpoint-status |  |  | checkpoint | Any required ductwork leakage testing
checkpoint-status |  |  | checkpoint | Spiral installed as per latest drawing
checkpoint-status |  |  | checkpoint | Spiral joins sealed correctly
checkpoint-status |  |  | checkpoint | Correct hanger spacing / supports installed for spiral
checkpoint-status |  |  | checkpoint | Spiral insulated where required and damage free
checkpoint-status |  |  | checkpoint | Additional taping/sealing to medium/high pressure spiral
checkpoint-status |  |  | checkpoint | Pops & flex installed as per latest drawing
checkpoint-status |  |  | checkpoint | Correct hanger spacing / supports installed for flex
checkpoint-status |  |  | checkpoint | Free from support off other services
checkpoint-status |  |  | checkpoint | Flexible duct connections completed correctly
checkpoint-status |  |  | checkpoint | Blade dampers installed as documented and left in the open position
checkpoint-status |  |  | checkpoint | BD pop access panel coordinated and marked
checkpoint-status |  |  | checkpoint | Cushion boxes installed as per latest drawing
checkpoint-status |  |  | checkpoint | Balancing dampers installed as documented and left in the open position
checkpoint-status |  |  | checkpoint | Location of register coordinted with other services and marked on plan or floor
checkpoint-status |  |  | checkpoint | Volume Control Dampers installed as per latest drawing
checkpoint-status |  |  | checkpoint | Motorised dampers installed as per latest drawing / actuator fit off
checkpoint-status |  |  | checkpoint | Smoke dampers installed as per latest drawing / actuator fit off
checkpoint-status |  |  | checkpoint | Damper access panels coordinated and marked
checklist-flat |  |  | checklist | All Subbie Rough-in Progression |  |  |  |  | Yes | All Subbie Rough-in Progression Checklist | 6e6fcb7a-a4a4-4415-ba14-f426f7e4113e
checkpoint-status |  |  | checkpoint | All work in zone completed and appear compliant
label | a2a747ef-119a-53a9-b546-7dca898754e6 |  | note | Pass once all work complete
checklist-flat |  |  | checklist | Drains |  |  |  |  | Yes | Drains | 7f7e3919-c5c7-4296-b3a6-3c7e5ace9292
checkpoint-status |  |  | checkpoint | Drain trapped where required
checkpoint-status |  |  | checkpoint | Correct hanger spacing / fall
checkpoint-status |  |  | checkpoint | Drain tested
checkpoint-status |  |  | checkpoint | Drain pump installed level and tested
checkpoint-status |  |  | checkpoint | Drain terminates at a tundish
checkpoint-status |  |  | checkpoint | Drains, pump and tundish access for maintenance.
checklist-flat |  |  | checklist | Equipment |  |  |  |  | Yes | Equipment Checklist | 89a121d0-77d6-4706-bc47-f946faf4d29e
checkpoint-status |  |  | checkpoint | Correct unit correctly supported as per project engineering requirements
checkpoint-status |  |  | checkpoint | Correct unit installed as per latest drawing
checkpoint-status |  |  | checkpoint | Flexible connections installed and sealed
checkpoint-status |  |  | checkpoint | Access to filter bank / filters installed
checkpoint-status |  |  | checkpoint | Access to all relevant controls and isolators
checkpoint-status |  |  | checkpoint | Access panel coordinated and marked
checkpoint-status |  |  | checkpoint | Seismic bracing to requirements
checkpoint-status |  |  | checkpoint | Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist-flat |  |  | checklist | Pipework |  |  |  |  | Yes | Pipework Checklist | 9143b11e-c4a0-4b93-807a-9d8181cbada4
checkpoint-status |  |  | checkpoint | Installed as per latest drawing
checkpoint-status |  |  | checkpoint | Correct heights i.e. underside as per drawings
checkpoint-status |  |  | checkpoint | Pipe fittings complete
checkpoint-status |  |  | checkpoint | Clips complete
checkpoint-status |  |  | checkpoint | Insulation complete
checkpoint-status |  |  | checkpoint | Air bleed complete (installed at all floor high points)
checkpoint-status |  |  | checkpoint | Correct flow and return checked
checkpoint-status |  |  | checkpoint | Access to valve sets checked'
checkpoint-status |  |  | checkpoint | No other services suspended from pipe work
checkpoint-status |  |  | checkpoint | Damage free
checkpoint-status |  |  | checkpoint | Piping cleaned and flushed
checkpoint-status |  |  | checkpoint | Pipe tested and recorded as per Pipe Testing ITP
checkpoint-status |  |  | checkpoint | Initial pipe pressure test (attach photo below)
checkpoint-status |  |  | checkpoint | 24hr pipe pressure test (attach photo below)
checklist-flat |  |  | checklist | Site Establishment and Safety |  |  |  |  | Yes | Site Establishment and Safety Checklist | dbbe2d0c-9baa-4ef1-932f-f5091409b046
checkpoint-status |  |  | checkpoint | Delivery and goods lift location
checkpoint-status |  |  | checkpoint | Delivery requirements i.e. booking process
checkpoint-status |  |  | checkpoint | On site storage / office location
checkpoint-status |  |  | checkpoint | Site specific restrictions i.e. noise / starting times
checklist-flat |  |  | checklist | Outdoor Equipment |  |  |  |  | Yes | Outdoor Equipment | e08da7b7-f994-451f-a167-91efe7ad4a39
checkpoint-status |  |  | checkpoint | Unit correctly supported as per project engineering requirements
checkpoint-status |  |  | checkpoint | Correct unit installed as per latest drawing
checkpoint-status |  |  | checkpoint | Access to all relevant controls, isolators and maintenance items
checkpoint-status |  |  | checkpoint | Floor or Platform Mounted Thermal Plant correctly supported as per project engineering requirements
checkpoint-status |  |  | checkpoint | Maintenance and ventilation clearance maintained as per manufacturer's specs
checkpoint-status |  |  | checkpoint | All manufacturer specific requirements have been provided in addition to project requirements
checklist-flat |  |  | checklist | Refrigeration Pipe |  |  |  |  | Yes | Refrigeration Pipe Checklist | e5c4a4d4-c557-4b84-a43a-cfc06d6e0869
checkpoint-status |  |  | checkpoint | Correct IDU & ODU installed as per latest drawing & schedule
checkpoint-status |  |  | checkpoint | Installed as per latest drawings
checkpoint-status |  |  | checkpoint | No other services suspended from pipe work (Attach Photos below)
checkpoint-status |  |  | checkpoint | Installation damage free (Any Issues comment/attach Photos below)
checkpoint-status |  |  | checkpoint | Correct supports used and support spacing
checkpoint-status |  |  | checkpoint | Pipe labelled after insulation - provide photo evidence
checkpoint-status |  |  | checkpoint | Pipe mains installation completed to drawings/specification
checkpoint-status |  |  | checkpoint | Pipework system pressure tested
checkpoint-status |  |  | checkpoint | Area left clean and tidy - photos of cleanliness or issues
checklist-flat |  |  | checklist | Grille Fit-Off |  |  |  |  | Yes | Grille Fit-Off Checklist | ed88aaf8-e270-4095-b2b0-a2cee01b04b1
checkpoint-status |  |  | checkpoint | Grilles installed in correct location as per latest duct layout / RCP
checkpoint-status |  |  | checkpoint | Correct grille type installed
checkpoint-status |  |  | checkpoint | Grille installed flush and square
checkpoint-status |  |  | checkpoint | Are all grilles installed correctly? Air leaks, vibration or failure
checkpoint-status |  |  | checkpoint | Grille color as per schedule
checkpoint-status |  |  | checkpoint | Grille left clean of fingerprints and caps installed where required
checkpoint-status |  |  | checkpoint | Grille fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below)