## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Pre Sheet Sign off |  |  |  |  | Yes | Pre-Sheet wall Sign-Off | 1f1eabdd-569a-43ae-b98a-b15732fc5e07
section | Electrical - Apps Electrical - Pass once below is completed
checkpoint | Rough-in Complete
checkpoint | Cutouts Marked
checkpoint | Noggins installed as marked
checkpoint | Pressure boxes installed
checkpoint | Pressure box rough-in sealed
checkpoint | FR GPO boxes installed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Hydraulics - Planet Plumbing - Pass once below is completed
checkpoint | Rough-in complete
checkpoint | Cut outs marked
checkpoint | Noggins installed as marked
checkpoint | Access panel / Valve box locations framed as marked
checkpoint | Lagging complete
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Mechanical - DE-ELLIS - Pass once below is completed
checkpoint | Rough-in complete
checkpoint | Cut outs marked
checkpoint | Pressure boxes installed
checkpoint | Pressure box rough-in sealed
checkpoint | Noggins installed as marked
checkpoint | Access panel locations framed as marked
checkpoint | Lagging complete
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Medical Gas - DE-ELLIS -Pass once below is completed
checkpoint | Rough-in complete
checkpoint | Cut outs marked
checkpoint | Pressure boxes installed
checkpoint | Pressure box rough-in sealed
checkpoint | Access panel / Valve box locations framed as marked
checkpoint | Noggins installed as marked
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Pneumatic Piping - DE-ELLIS -Pass once below is completed
checkpoint | Rough-in complete
checkpoint | Cut outs marked
checkpoint | Noggins installed as marked
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Wet Fire - Contract Fire -Pass once below is completed
checkpoint | Rough-in complete
checkpoint | Cut outs marked
checkpoint | Noggins installed as marked (Fire extinguishers)
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Dry Fire - Jaycon -Pass once below is completed
checkpoint | Rough-in complete
checkpoint | Cut outs marked
checkpoint | Noggins installed as marked
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Security- Honeywell - Pass once below is completed
checkpoint | Rough-in complete
checkpoint | Cut outs marked
checkpoint | Pressure boxes installed
checkpoint | Pressure box rough-in sealed
checkpoint | Fire rated boxes installed
checkpoint | Noggins installed as marked
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Data - SKS - Pass once below is completed
checkpoint | Rough-in complete
checkpoint | Cut outs marked
checkpoint | Pressure boxes installed
checkpoint | Pressure box rough-in sealed
checkpoint | Fire rated boxes installed
checkpoint | Noggins installed as marked
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Nurse Call - Pass once below is completed
checkpoint | Rough-in complete
checkpoint | Pressure boxes installed
checkpoint | Pressure box rough-in sealed
checkpoint | Fire rated boxes installed
checkpoint | Cut outs marked
checkpoint | Noggins installed as marked
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | AV - SKS - Pass once below is completed
checkpoint | Rough-in complete
checkpoint | Pressure boxes installed
checkpoint | Pressure box rough-in sealed
checkpoint | Fire rated boxes installed
checkpoint | Cut outs marked
checkpoint | Noggins installed as marked / TV support
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Joinery - GOSA/Jacaranda -Pass once below is completed
checkpoint | Noggins installed as marked
checkpoint | Cut outs framed as marked (mental health)
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Sanitary Hardware - Casello - Pass once below is completed
checkpoint | Cut outs framed as marked (mental health)
checkpoint | Noggins installed as marked
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | Plaster - Expo / Express - Pass once below is completed
checkpoint | All rough-in complete
checkpoint | Studs installed @ correct centres (max 600mm) and framing noggins as per wall type
checkpoint | Wall cavity clean / no waste / vacuumed
checkpoint | No screws in head track
checkpoint | Secondary steel (walls) as marked - (drug safe / drop down rails / gun safes etc)
checkpoint | Door frames installed and filled when in fire rated wall
checkpoint | Special door openings framing and noggins for autoclosers etc
checkpoint | Insulation installed
checkpoint | Noggins installed as marked
holdpoint | Sign Off
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign Off
section | MPX FINAL SIGN-OFF
checkpoint | All services signed off
checkpoint | Wall cavity clean and free of any rubbish / dust
checkpoint | Photos taken of all walls prior to sheeting
checkpoint | MPX sign-off
holdpoint | Sign Off
checklist | Pre Ceiling Sign off |  |  |  |  | Yes | Pre sheet install Ceilings | 6f7ff414-49e5-4181-a832-f1ade14d77b5
section | Electrical - Apps Electrical - Pass once below is completed
checkpoint | Ceiling fitting / rough-in complete and correctly located
checkpoint | Access Panel Openings Constructed and equipment is accessible
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | Ceiling noggins installed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Hydraulics - Planet Plumbing - Pass once below is completed
checkpoint | All pipes connected
checkpoint | All pipes through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Access Panel openings constructed and isolation valves accessible
checkpoint | Lagging complete to pipes and drains
checkpoint | Pressure test completed and passed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Mechanical - DE-ELLIS - Pass once below is completed
checkpoint | In ceiling fit off complete
checkpoint | All penetrations through fire rated / smoke /pressurized walls are all sealed
checkpoint | Fire dampers installed correctly and sealed and labeled
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Access Panel Openings Constructed and equipment is accessible for servicing
checkpoint | Lagging complete to pipes
checkpoint | Pressure test completed and passed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Medical Gas - DE-ELLIS -Pass once below is completed
checkpoint | In ceiling fit off complete
checkpoint | All pipes through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Pressure test completed and passed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Pneumatic Piping - DE-ELLIS -Pass once below is completed
checkpoint | In ceiling fit off complete
checkpoint | All pipes through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Pressure test completed and passed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Wet Fire - Contract Fire -Pass once below is completed
checkpoint | In ceiling sprinklers / detectors have been fitted off / spray pattern unobstructed
checkpoint | Fit off to ceiling grid complete
checkpoint | All pipes through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Pressure test completed and passed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Dry Fire - Jaycon -Pass once below is completed
checkpoint | In ceiling rough in complete and cables correctly located
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Security- Honeywell -Pass once below is completed
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Data - SKS -Pass once below is completed
checkpoint | In ceiling rough in complete and cables correctly located
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Nurse Call -Pass once below is completed
checkpoint | In ceiling rough in complete and cables correctly located
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | AV - SKS -Pass once below is completed
checkpoint | In ceiling rough in complete and cables correctly located
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | TV support poles / noggins installed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Patient lifters- -Pass once below is completed
checkpoint | Patient lifter track / hanger system installed
checkpoint | Patient lifter track / hanger system load test completed and passed
checkpoint | Power supply correctly located
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Equipment pendants - Device Technologies -Pass once below is completed
checkpoint | Pendant supports clear of ceiling grid and level correct
checkpoint | Pendant services rough in complete (Power and Medical gas)
checkpoint | Framed opening in ceiling installed as per detail
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Plaster - Express / Expo - Pass once below is completed
checkpoint | All penetrations through fire rated / smoke / pressurized walls are all sealed
checkpoint | All walls caulked to slab and soffitt / joints and screws stopped
checkpoint | Ceiling grid installed as per design
checkpoint | Thermal and acoustic insulation installed
checkpoint | Ceiling Grid frame is clear from Ceiling Services
checkpoint | Access Panel Openings Constructed as marked
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | MPX FINAL SIGN-OFF
checkpoint | All subcontractors signed off
checkpoint | Photos taken of all ceiling system / services prior to sheeting
checkpoint | MPX sign-off
holdpoint | Sign off
checklist | Pre Grid Sign off |  |  |  |  | Yes | Pre grid install Ceilings | ce362607-e859-41de-9f2f-774b74529ace
section | Electrical - Apps Electrical - Pass once below is completed
checkpoint | Rough in complete
checkpoint | Access Panel / ceiling set out location marked
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Hydraulics - Planet Plumbing - Pass once below is completed
checkpoint | Rough in complete including lagging to drains and pipes
checkpoint | All pipes through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Access Panel locations marked and isolation valves accessible
checkpoint | Pressure test completed and passed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Mechanical - DE-ELLIS - Pass once below is completed
checkpoint | Rough in complete including lagging to drains and pipes
checkpoint | All penetrations through fire rated / smoke /pressurized walls are all sealed
checkpoint | Fire dampers installed correctly and sealed and labeled
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Access Panel / ceiling set out location marked
checkpoint | Pressure test completed and passed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Medical Gas - DE-ELLIS -Pass once below is completed
checkpoint | Rough in complete
checkpoint | All pipes through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Pressure test completed and passed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Pneumatic Piping - DE-ELLIS -Pass once below is completed
checkpoint | Rough in complete
checkpoint | All pipes through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Pressure test completed and passed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Wet Fire - Contract Fire -Pass once below is completed
checkpoint | Rough in complete
checkpoint | All pipes through fire rated / smoke / pressurized walls are all sealed
checkpoint | Ceiling set out marked
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | In ceiling sprinklers / detectors have been fitted off / spray pattern unobstructed
checkpoint | Pressure test completed and passed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Dry Fire - Jaycon -Pass once below is completed
checkpoint | Rough in complete
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | Ceiling set out marked
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Security- Honeywell -Pass once below is completed
checkpoint | Rough in complete
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Data - SKS -Pass once below is completed
checkpoint | Rough in complete
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Service separation to power verified
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Nurse Call - APPS Electrical-Pass once below is completed
checkpoint | Rough in complete
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | AV - SKS -Pass once below is completed
checkpoint | Rough in complete
checkpoint | All cables through fire rated / smoke / pressurized walls are all sealed
checkpoint | TV support poles installed
checkpoint | Fire rated penetrations have stickers, and photos taken
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Patient lifters- -Pass once below is completed
checkpoint | Patient lifter track / hanger system installed
checkpoint | Patient lifter track / hanger system load test completed and passed
checkpoint | Power supply correctly located
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Equipment pendants - Device technologies -Pass once below is completed
checkpoint | Pendant supports installed
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | Plaster - Express / Expo - Pass once below is completed
checkpoint | All penetrations through fire rated / smoke / pressurized walls are all sealed
checkpoint | All walls caulked to slab and soffitt / joints and screws stopped
checkpoint | No screws in top track
checkpoint | Screws installed to correct centers as per specification to walls
checkpoint | Subcontractor presheet works complete (S/C to sign)
holdpoint | Sign off
section | MPX FINAL SIGN-OFF
checkpoint | All subcontractors signed off
checkpoint | Building Surveyor Fire Wall inspection complete
checkpoint | No Fixings to Head Track or Between Stud & Top Track
checkpoint | Photos taken of all walls prior to sheeting
checkpoint | MPX sign-off
holdpoint | Sign off