## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | CC0394 - ITP-004 - Storm Water Drainage | itp |  |  |  | Yes | CC0394 - ITP-004 - Storm Water Drainage REV0 | 97625f6e-fd62-47be-a45c-3f2bef96873d
checkpoint-group | Lot Conformance.
checkpoint-status | Lot Conformance
select | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 1.0
checkpoint-status | 1.1 - Determine Lot Size
label | Ref docs - IFC Drawings
label | Acceptance criteria - Pit to Pit
label | Acceptance
text
label | to
text
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | Work Lot Map
checkpoint-status | 1.2 - Survey Set-out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Prior to excavations being carried out, the contractor shall engage a suitably qualified surveyor to set out all drainage lines including manholes, temporary benchmarks, sewage wet wells etc.
label | • Clearly mark limits of works.
label | • Chainage, offsets, cut/fill level, cutting slopes, grades and cross sections specified or shown on the drawings, etc.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
label | RJE Key - S
checkpoint-status | 1.3 - Approved Material Type
label | Ref docs - IFC Drawings AS1260
label | Acceptance criteria - In accordance with IFC Drawings:
label | • Storm Pro
label | • PVC
label | • All pipework to be clearly labelled & detectable to identify it as stormwater drainage.
text | Acceptance | Yes,No,N/A | Pipe Size/Class
label | Key - H
label | Resp - SE
label | RJE Key - H
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 2.0 Excavation of Drainage Trench
checkpoint-status | 2.1 - Excavation
label | Ref docs - IFC Drawings AS3500
label | Acceptance criteria - All excavations subject to inspection prior to the installation of services and throughout the duration of the excavation.
label | • Excavate to the lines, levels and grades as required for in ground services specified in accordance with the requirements of AS 3500.
label | • Keep trench width & depth to that required by the service & its bedding method.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
label | RJE Key - S
checkpoint-status | 2.2 - Removal of Obstructions
label | Acceptance criteria - Remove obstructions including roots, stumps, boulders and the like which may interfere with the proper functioning of the service
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
label | RJE Key - S
checkpoint-status | 2.3 - Water Management
label | Acceptance criteria - Symal shall maintain all excavations in a well-drained condition.
label | • No bedding material or pipe work shall be placed in excavations containing standing or running water.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
label | RJE Key - S
checkpoint-status | 2.4 - Bedding Material
label | Ref docs - IFC Drawings
label | Acceptance criteria - All pipes shall be installed with 5mm A grade crushed rock or similar to AS3725
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
label | RJE Key - S
checkpoint-status | 2.6 - Compaction of Bedding
label | Ref docs - IFC Drawings
label | Acceptance criteria - Bedding material shall be compacted to refusal handheld mechanical equipment.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
label | RJE Key - S
checkpoint-group | 3.0 Installation of Drainage Pipe
checkpoint-status | 3.1 - Pipe Installation
label | Ref docs - AS 3500
label | Acceptance criteria - All excavations subject to inspection prior to the installation of services and throughout the duration of the excavation.
label | • Pipes shall be bedded evenly to ensure sockets to not bear on the base of the trench
label | • Pipe laying shall commence at upstream end at downstream end of the run. All pipes shall be laid with sockets pointing upstream.
label | • Lay at min grade 1:100
label | • Excavate to the lines, levels and grades as required for in ground services specified in accordance with the requirements of AS 3500.
label | • Keep trench width & depth to that required by the service & its bedding method.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
label | RJE Key - S
checkpoint-status | 3.2 - Pipe Grade
label | Ref docs - IFC Drawings
label | Acceptance criteria - Install piping in straight lines at uniform grades without sags.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
label | RJE Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | CCTV Report
checkpoint-status | 3.3 - Tolerances
label | Acceptance criteria - Unless otherwise specified, tolerances as follows:
label | • Offset of entry pits required to match lines of kerbs or barriers ±20mm
label | • Plan location of pits other than offsets to kerb lines or barriers ±100mm
label | • Invert level of pipes at pits ±50mm
label | • Departure from design grade of pipe runs ±10mm in 10m provided minimum grade is not less than 1:250
button | Acceptance | Yes,No,N/A
label | Key - R
label | Resp - SE
label | RJE Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | As-Built
checkpoint-status | 3.4 - Pipe Fittings, Supports & Fixings
label | Ref docs - AS3500
label | Acceptance criteria - Provide all bends, junctions, inspection openings and other fittings as necessary for the completion of all systems.
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp - SE
label | RJE Key - S
checkpoint-status | 3.5 - Pit Install
label | Ref docs - AS3500 IFC Drawings
label | Acceptance criteria - Pits are to be constructed in accordance with project specifications, with internal surfaces and exposed surfaces finished smooth & true. All pipe break-ins are to be made neat and finished smooth without gaps/cavities.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
label | RJE Key - S
checkpoint-status | 3.6 - Survey of Installed Services
label | Acceptance criteria - Accurately record the routes of underground cables and pipes before backfilling. Include on the record drawings.
button | Acceptance | Yes,No,N/A
label | Key - R
label | Resp - SE
label | RJE Key - S
checkpoint-group | 4.0 Backfill
checkpoint-status | 4.1 - Backfill Material
label | Ref docs - IFC Drawings
label | Acceptance criteria - After pipes & fittings have been set in the correct position, jointed, and tested, further bedding material shall be used to fill all recesses below sockets, and bottoms of trenches.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
checkpoint-status | 4.2 - Layer Thickness
label | Ref docs - IFC Drawings
label | Acceptance criteria - Backfill material must be placed and compacted in maximum 150mm layers.
label | • Backfill trenches as soon as possible after satisfactory testing & approval of laid and bedded service.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
label | RJE Key - S
checkpoint-group | 5.0 Conformance Check
checkpoint-status | 5.1 - Clean & Finish
label | Ref docs - IFC Drawings
label | Acceptance criteria - On completion, each drainage line shall be free from dirt, debris, or other impediments.
button | Acceptance | Yes,No,N/A
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | CCTV Report
checkpoint-status | 5.2 - Visual Inspection
label | Acceptance criteria - Do not cover or conceal work until it has been tested. Leave pipe joints exposed to enable witness testing.
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp - SE