## Temp (hidden)
Project Structure |  |  |  |  | Checklists
OHS
| SWMS |  |  |  | Ability to Add
| Site Safety Plan |  |  |  | Ability to Add
| Incident Report |  |  |  | Ability to Add
| Toolbox Meetings |  |  |  | Ability to Add
| Working Permits |  |  |  | Ability to Add
Site Issues |  |  |  |  | Ability to Add
Variations/Transmittals |  |  |  |  | Ability to Add
Greenstar |  |  |  |  | Ability to Add
Deliveries |  |  |  |  | Ability to Add
Site QA
Rough In
|  | Office A | Ground Floor
|  |  |  | FCU-AG.1 | Rough In Checklist AC & M.W
|  |  |  | FCU-AG.2 | Rough In Checklist AC & M.W
|  |  |  | FCU-AG.3 | Rough In Checklist AC & M.W
|  |  |  | FCU-AG.4 | Rough In Checklist AC & M.W
|  |  |  | FCU-AG.5 | Rough In Checklist AC & M.W
|  |  |  | FCU-AG.6 | Rough In Checklist AC & M.W
|  |  |  | FCU-AG.7 | Rough In Checklist AC & M.W
|  |  |  | FCU-AG.8 | Rough In Checklist AC & M.W
|  |  |  | FCU-AG.9 | Rough In Checklist AC & M.W
Floor Level 1
|  |  |  | FCU-A1.1 | Rough In Checklist AC & M.W
|  |  |  | FCU-A1.2 | Rough In Checklist AC & M.W
|  |  |  | FCU-A1.3 | Rough In Checklist AC & M.W
|  |  |  | FCU-A1.4 | Rough In Checklist AC & M.W
|  |  |  | FCU-A1.5 | Rough In Checklist AC & M.W
|  |  |  | FCU-A1.6 | Rough In Checklist AC & M.W
|  |  |  | FCU-A1.7 | Rough In Checklist AC & M.W
|  |  |  | FCU-A1.8 | Rough In Checklist AC & M.W
|  |  |  | FCU-A1.9 | Rough In Checklist AC & M.W
Warehouse A Office
|  |  | Dispatch Office | FCU-WA.1 | Rough In Checklist AC & M.W
|  |  | Print DP Office | FCU-WA.2 | Rough In Checklist AC & M.W
|  |  | Trans Uban | FCU-WA.3 | Rough In Checklist AC & M.W
Office B
|  |  |  | FC-B.1 | Rough In Checklist AC & M.W
|  |  |  | CU-B.1 | Rough In Checklist AC & M.W
|  |  |  | FC-B.2 | Rough In Checklist AC & M.W
|  |  |  | CU-B.2 | Rough In Checklist AC & M.W
|  |  |  | FC-B.3 | Rough In Checklist AC & M.W
|  |  |  | CU-B.3 | Rough In Checklist AC & M.W
|  |  |  | FC-B.4 | Rough In Checklist AC & M.W
|  |  |  | CU-B.4 | Rough In Checklist AC & M.W
|  |  |  | TEF-B.1 | Rough In Checklist Fans
|  |  |  | TEF-B.2 | Rough In Checklist Fans
|  |  |  | EF-B.1 | Rough In Checklist Fans
Dock Office B
|  |  |  | FC-B.5 | Rough In Checklist AC & M.W
|  |  |  | CU-B.5 | Rough In Checklist AC & M.W
Warehouse A Roof
|  |  |  | SEF-A-1 | Rough In Checklist Fans
|  |  |  | SEF-A-2 | Rough In Checklist Fans
Warehouse B Roof
|  |  |  | SEF-B-1 | Rough In Checklist Fans
|  |  |  | SEF-B-2 | Rough In Checklist Fans
|  |  |  | SEF-B-3 | Rough In Checklist Fans
Warehouse MSSB
|  |  |  | MSSB-A | MSSB Checklist
|  |  |  | MSSB-A-ESS | MSSB Checklist
|  |  |  | MSSB-B | MSSB Checklist
|  |  |  | MSSB-B-ESS | MSSB Checklist
Office A Fans
|  |  |  | TEF-A-1.1 | Rough In Checklist Fans
|  |  |  | TEF-A-G.1 | Rough In Checklist Fans
|  |  |  | TEF-A-G.2 | Rough In Checklist Fans
|  |  |  | OAF-A-G.1 | Rough In Checklist Fans
Warehouse
|  |  |  | BCEF-A-1 | Rough In Checklist Fans
|  |  |  | TEF-WA-1 | Rough In Checklist Fans
Office B Fans
|  |  |  | TEF-B.1 | Rough In Checklist Fans
|  |  |  | TEF-B.2 | Rough In Checklist Fans
|  |  |  | EF-B.1 | Rough In Checklist Fans
Fit Off
Office A
|  |  |  | FC-A.1 | Fit Off Checklist AC & MW
|  |  |  | CU-A.1 | Fit Off Checklist AC & MW
|  |  |  | FC-A.2 | Fit Off Checklist AC & MW
|  |  |  | CU-A.2 | Fit Off Checklist AC & MW
|  |  |  | FC-A.3 | Fit Off Checklist AC & MW
|  |  |  | CU-A.3 | Fit Off Checklist AC & MW
|  |  |  | FC-A.4 | Fit Off Checklist AC & MW
|  |  |  | CU-A.4 | Fit Off Checklist AC & MW
Dock Office A
|  |  |  | FC-A.5 | Fit Off Checklist AC & MW
|  |  |  | CU-A.5 | Fit Off Checklist AC & MW
Office B
|  |  |  | FC-B.1 | Fit Off Checklist AC & MW
|  |  |  | CU-B.1 | Fit Off Checklist AC & MW
|  |  |  | FC-B.2 | Fit Off Checklist AC & MW
|  |  |  | CU-B.2 | Fit Off Checklist AC & MW
|  |  |  | FC-B.3 | Fit Off Checklist AC & MW
|  |  |  | CU-B.3 | Fit Off Checklist AC & MW
|  |  |  | FC-B.4 | Fit Off Checklist AC & MW
|  |  |  | CU-B.4 | Fit Off Checklist AC & MW
|  |  |  | TEF-B.1 | Fit Off Checklist Fan
|  |  |  | TEF-B.2 | Fit Off Checklist Fan
|  |  |  | EF-B.1 | Fit Off Checklist Fan
Dock Office B
|  |  |  | FC-B.5 | Fit Off Checklist AC & MW
|  |  |  | CU-B.5 | Fit Off Checklist AC & MW
Warehouse A Roof
|  |  |  | SEF-A-1 | Fit Off Checklist Fan
|  |  |  | SEF-A-2 | Fit Off Checklist Fan
Warehouse B Roof
|  |  |  | SEF-B-1 | Fit Off Checklist Fan
|  |  |  | SEF-B-2 | Fit Off Checklist Fan
|  |  |  | SEF-B-3 | Fit Off Checklist Fan
Office A Fans
|  |  |  | TEF-A.1 | Fit Off Checklist Fan
|  |  |  | TEF-A.2 | Fit Off Checklist Fan
|  |  |  | EF-A.1 | Fit Off Checklist Fan
Office B Fans
|  |  |  | TEF-B.1 | Fit Off Checklist Fan
|  |  |  | TEF-B.2 | Fit Off Checklist Fan
|  |  |  | EF-B.1 | Fit Off Checklist Fan
| Fire Dampers |  |  |  | Ability to Add
| MSSB |  |  |  | MSSB Checklist

## Project Structure TEST (hidden)
OHS
| SWMS |  |  |  |  | Ability to Add
| Site Safety Plan |  |  |  |  | Ability to Add
| Incident Report |  |  |  |  | Ability to Add
| Toolbox Meetings |  |  |  |  | Ability to Add
| Working Permits |  |  |  |  | Ability to Add
Site Issues | [5 empty] | Ability to Add
Variations/Transmittals | [5 empty] | Ability to Add
Greenstar | [5 empty] | Ability to Add
Deliveries | [5 empty] | Ability to Add
Site QA
| Office A | Ground Floor
|  |  |  | FCU-AG.1 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-AG.1 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-AG.2 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-AG.2 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-AG.3 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-AG.3 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-AG.4 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-AG.4 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-AG.5 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-AG.5 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-AG.6 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-AG.6 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-AG.7 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-AG.7 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-AG.8 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-AG.8 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-AG.9 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-AG.9 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
Level 1
|  |  |  | FCU-A1.1 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-A1.1 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-A1.2 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-A1.2 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-A1.3 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-A1.3 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-A1.4 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-A1.4 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-A1.5 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-A1.5 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-A1.6 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-A1.6 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-A1.7 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-A1.7 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-A1.8 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-A1.8 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-A1.9 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-A1.9 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
Warehouse A Office
|  |  | Dispatch Office | FCU-WA.1 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-WA.1 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  | Print DP Office | FCU-WA.2 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-WA.2 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  | Trans Uban | FCU-WA.3 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-WA.3 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  | Office A Fans | Office A
|  |  |  | TEF-A-1.1 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | TEF-A-G.1 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | TEF-A-G.2 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | OAF-A-G.1 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
Warehouse A Equipment Room
|  |  |  | GEF-A-1 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | GEF-A-2 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | GEF-A-3 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | GEF-A-4 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
|  | Building A Fire Damper | Main Switchroom
|  |  |  | FD-1 |  | Fire Damper Checklist
|  |  |  | FD-2 |  | Fire Damper Checklist
|  | Office B | Floor Level 1
|  |  |  | FCU-B1.1 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-B1.1 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-B1.2 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-B1.2 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-B1.3 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-B1.3 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-B1.4 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-B1.4 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | FCU-B1.5 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | Comissioning | Commissioning Checklist
|  |  |  | CU-B1.5 | Rough In | Rough In Checklist AC Outdoor unit
[5 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning | Commissioning Checklist
|  | Office B Fans | Office B
|  |  |  | TEF-BG.1 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | TEF-B1.1 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
Warehouse B Smoke Fans
|  |  |  | SEF-B.1 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | SEF-B.2 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | SEF-B.3 | Rough In | Rough In Checklist Fans
[5 empty] | Fit off | Fit Off Checklist Fan
|  | MSSB | Warehouse A MSSB
|  |  |  | MSSB-A |  | MSSB Checklist
Warehouse B MSSB
|  |  |  | MSSB-B |  | MSSB Checklist

## Project Structure V2 (2)
Project Name | Brunt Rd, New School Education Precinct
Job Number | 975
Builder: | Sj Higgins
Project Manager: | Brent Cavallo
| Delivery Dockets | Delivery Docket
| Builders Works & Site Issues | Builders Works & Site Issues
| Drafting & Design Issues | Drafting & Design Issues
| Defects | Defect
| AS Built Markups | As Built Markups |  |  |  | Matrices Link
QA
Building 1
Single Split
IDU-B1-06
AC High wall mounted Rough In
AC High wall mounted Fit Off
AC Outdoor unit (Stand Alone) Fit Off
AC Outdoor unit (Stand Alone) Commissioning
Cassette
|  |  |  | IDU-B1-01A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B1-01A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Outdoor Unit
ODU-B1-01
AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Cassette
|  |  |  | IDU-B1-02A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B1-02B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B1-02C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B1-03A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B1-03B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B1-04E | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Ducted
|  |  |  | IDU-B1-05A | AC Ducted Unit Rough In
AC Ducted Unit Pipework & Drains
AC Ducted Unit Ductwork
AC Ducted Unit Flex & Cushion Boxes
AC Ducted Unit Fit Off
AC Ducted Unit Commissioning
|  |  |  | IDU-B1-05B | AC Ducted Unit Rough In
AC Ducted Unit Pipework & Drains
AC Ducted Unit Ductwork
AC Ducted Unit Flex & Cushion Boxes
AC Ducted Unit Fit Off
AC Ducted Unit Commissioning
Branch Box
|  |  |  | BS.B1-01 | AC Branch Box Rough In
Branch Box Pipe & Drains
Outdoor Unit
|  |  |  | ODU-B1-02 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Cassette
|  |  |  | IDU-B1-04A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B1-04B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B1-04C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B1-04D | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B1-03C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B1-02D | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Ducted
|  |  |  | IDU-B1-03D | AC Ducted Unit Rough In
AC Ducted Unit Pipework & Drains
AC Ducted Unit Ductwork
AC Ducted Unit Flex & Cushion Boxes
AC Ducted Unit Fit Off
AC Ducted Unit Commissioning
|  |  |  | IDU-B1-05C | AC Ducted Unit Rough In
AC Ducted Unit Pipework & Drains
AC Ducted Unit Ductwork
AC Ducted Unit Flex & Cushion Boxes
AC Ducted Unit Fit Off
AC Ducted Unit Commissioning
Branch Box
|  |  |  | BS.B1-02 | AC Branch Box Rough In
Branch Box Pipe & Drains
Outdoor Unit
|  |  |  | ODU-B1-03 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Exhaust Fan
|  |  |  | CEF-B1-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | TEF-B1-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | GEF-B1-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
Outside Air
|  |  |  | OAF-B1-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | OAF-B1-02 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | OAF-B1-03 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | OAF-B1-04 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
RC
|  |  |  | All RC | Roof Cowl (RC)
Building 2
Single Split
IDU-B2-04
AC High wall mounted Rough In
AC High wall mounted Fit Off
AC Outdoor unit (Stand Alone) Fit Off
AC Outdoor unit (Stand Alone) Commissioning
Cassette
|  |  |  | IDU-B2-01A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-01B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-01C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-01D | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-01E | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-01F | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Branch Box
|  |  |  | BS.B2-01 | AC Branch Box Rough In
Branch Box Pipe & Drains
Outdoor Unit
|  |  |  | ODU-B2-01 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Cassette
|  |  |  | IDU-B2-02A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-02B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-02C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Branch Box
|  |  |  | BS.B2-02 | AC Branch Box Rough In
Branch Box Pipe & Drains
Outdoor Unit
|  |  |  | ODU-B2-02 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Cassette
|  |  |  | IDU-B2-03A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-03B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-03C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-03D | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-03E | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B2-03F | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Branch Box
|  |  |  | BS.B2-03 | AC Branch Box Rough In
Branch Box Pipe & Drains
Outdoor Unit
|  |  |  | ODU-B2-03 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Exhaust Fan
|  |  |  | GEF-B2-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | CEF-B2-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | TEF-B2-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
RC
|  |  |  | All RC | Roof Cowl (RC)
Building 3
Single Split
IDU-B3-04
AC High wall mounted Rough In
AC High wall mounted Fit Off
AC Outdoor unit (Stand Alone) Fit Off
AC Outdoor unit (Stand Alone) Commissioning
Cassette
|  |  |  | IDU-B3-01A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B3-01B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B3-01C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B3-01D | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B3-01E | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Ducted
|  |  |  | IDU-B3-01F | AC Ducted Unit Rough In
AC Ducted Unit Pipework & Drains
AC Ducted Unit Ductwork
AC Ducted Unit Flex & Cushion Boxes
AC Ducted Unit Fit Off
AC Ducted Unit Commissioning
Branch Box
|  |  |  | BS.B3-01 | AC Branch Box Rough In
Branch Box Pipe & Drains
Outdoor Unit
|  |  |  | ODU-B3-01 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Cassette
|  |  |  | IDU-B3-02A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B3-02B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B3-02C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B3-02D | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Branch Box
|  |  |  | BS.B3-02 | AC Branch Box Rough In
Branch Box Pipe & Drains
Outdoor Unit
|  |  |  | ODU-B3-02 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Cassette
|  |  |  | IDU-B3-03A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B3-03B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B3-03C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B3-03D | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B3-03E | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Ducted
|  |  |  | IDU-B3-01G | AC Ducted Unit Rough In
AC Ducted Unit Pipework & Drains
AC Ducted Unit Ductwork
AC Ducted Unit Flex & Cushion Boxes
AC Ducted Unit Fit Off
AC Ducted Unit Commissioning
Branch Box
|  |  |  | BS.B3-03 | AC Branch Box Rough In
Branch Box Pipe & Drains
Outdoor Unit
|  |  |  | ODU-B3-03 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Exhaust Fan
|  |  |  | GEF-B3-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | TEF-B3-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | TEF-B3-02 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | CEF-B3-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
Building 3
Cassette
|  |  |  | IDU-B4-01A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B4-01B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B4-01C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B4-01D | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B4-01E | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Ducted
|  |  |  | IDU-B4-01F | AC Ducted Unit Rough In
AC Ducted Unit Pipework & Drains
AC Ducted Unit Ductwork
AC Ducted Unit Flex & Cushion Boxes
AC Ducted Unit Fit Off
AC Ducted Unit Commissioning
Branch Box
|  |  |  | BS.B4-01 | AC Branch Box Rough In
Branch Box Pipe & Drains
Outdoor Unit
|  |  |  | ODU-B4-01 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
RC
|  |  |  | All RC | Roof Cowl (RC)
Building 4
Single Split
IDU-B4-04
AC High wall mounted Rough In
AC High wall mounted Fit Off
AC Outdoor unit (Stand Alone) Fit Off
AC Outdoor unit (Stand Alone) Commissioning
Cassette
|  |  |  | IDU-B4-02A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B4-02B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B4-02C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B4-02D | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Branch Box
|  |  |  | BS.B4-02 | AC Branch Box Rough In
Branch Box Pipe & Drains
Outdoor Unit
|  |  |  | ODU-B4-02 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Cassette
|  |  |  | IDU-B4-03A | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B4-03B | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B4-03C | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B4-03D | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
|  |  |  | IDU-B4-03F | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Ducted
|  |  |  | IDU-B4-01G | AC Ducted Unit Rough In
AC Ducted Unit Pipework & Drains
AC Ducted Unit Ductwork
AC Ducted Unit Flex & Cushion Boxes
AC Ducted Unit Fit Off
AC Ducted Unit Commissioning
Branch Box
|  |  |  | BS.B4-03 | AC Branch Box Rough In
Branch Box Pipe & Drains
Outdoor Unit
|  |  |  | ODU-B4-03 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Exhaust Fan
|  |  |  | GEF-B4-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | TEF-B4-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | TEF-B4-02 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | CEF-B4-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
Outside Air
|  |  |  | OAF-B4-02A | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | OAF-B4-02B | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
RC
|  |  |  | All RC | Roof Cowl (RC)
Building 5
Cassette
|  |  |  | IDU-B5-04 | Cassette Rough In
Cassette Pipework & Drains
Cassette Fit Off
Cassette Commissioning
Ducted
|  |  |  | IDU-B5-01 | AC Ducted Unit Rough In
AC Ducted Unit Pipework & Drains
AC Ducted Unit Ductwork
AC Ducted Unit Flex & Cushion Boxes
AC Ducted Unit Fit Off
AC Ducted Unit Commissioning
|  |  |  | IDU-B5-03 | AC Ducted Unit Rough In
AC Ducted Unit Pipework & Drains
AC Ducted Unit Ductwork
AC Ducted Unit Flex & Cushion Boxes
AC Ducted Unit Fit Off
AC Ducted Unit Commissioning
Hi Wall Split
|  |  |  | IDU-B5-02 | AC High wall mounted Rough In
AC High wall mounted Fit Off
Outdoor Unit
|  |  |  | ODU-B5-01 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
|  |  |  | ODU-B5-02 | AC Outdoor unit (Stand Alone) Fit Off
AC Outdoor unit (Stand Alone) Commissioning
|  |  |  | ODU-B5-03 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
|  |  |  | ODU-B5-04 | AC Outdoor unit (VRF) Fit Off
AC Outdoor unit (VRF) Commissioning
Exhaust Fan
|  |  |  | SEF-B5-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | SPF-B5-02 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | SPF-B-03 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | TEF-B5-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | TEF-B-02 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | TEF-B-03 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | GEF-B5-01 | Fans Rough In
Fan Fit Off
Fan Commissioning
Outside Air
|  |  |  | KSF-B1-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
Roof
|  |  |  | KEF-B5-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | EF-B5-01 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | EF-B5-02 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
|  |  |  | EF-B5-03 | Fans Rough In
Fan Ductwork
Fan Flex & Cushion Boxes
Fan Fit Off
Fan Commissioning
RC
|  |  |  | All RC | Roof Cowl (RC)

## Project Structure V2 (hidden)
Project Name | Sunshine Plaza Office
Job Number | 891
Builder: | SJ Higgins
Project Manager: | Hanz Cortez-Cubillan
| Delivery Dockets | Delivery Docket
| Builders Works & Site Issues | Builders Works & Site Issues
| Drafting & Design Issues | Drafting & Design Issues
| Defects | Defect
| QA | Ground Floor | VAV | SME-00-01 | VAV-5.22
|  |  |  | SME-00-02 | VAV-1.2
VAV-1.3
VAV-1.4
VAV-5.7
VAV-5.8
|  |  |  | SME-00-03 | VAV-4.10
VAV-4.11
VAV-4.21
VAV-5.23
VAV-5.24
|  |  |  | SME-00-04 | VAV-5.9
VAV-5.10
VAV-5.11
VAV-5.17
VAV-5.20
|  |  | ERV Units | SME-00-01 | ERV-1
|  |  | AC Units | SME-00-04 | AC-1
AC-2
|  |  | AC Pipework | SME-00-24 | Refig
|  |  | FCU Units | SME-00-01 | FCU-1
FCU-5
|  |  |  | SME-00-02 | FCU-6
|  |  |  | SME-00-03 | FCU-3
FCU-4
|  |  |  | SME-00-04 | FCU-2
FCU-8
|  |  | Ground floor Pipework | SME-00-21 | CHW Pipework
|  |  |  | SME-00-22 | CHW Pipework
|  |  |  | SME-00-23 | CHW Pipework
|  |  |  | SME-00-24 | CHW Pipework
|  |  | FANS | SME-00-01 | F-1
F-6
|  |  |  | SME-00-03 | F-8
F-9
|  |  | Penetrations | SME-00-04 | FD-001-01
|  | Mezz-Plant Room (Low Level) | VAV | SME-MZ-01 | VAV-1.1
VAV-2.1
VAV-2.3
VAV-3.1
VAV-3.4
VAV-4.1
VAV-4.2
VAV-4.3
VAV-4.7
VAV-4.17
|  |  |  | SME-MZ-02 | VAV-5.1
VAV-5.2
VAV-5.4
VAV-5.5
VAV-5.19
VAV-5.21
VAV-6.2
VAV-6.3
|  |  |  | SME-MZ-03 | VAV-2.2
VAV-3.5
VAV-3.6
VAV-3.7
VAV-4.4
VAV-4.5
VAV-4.13
VAV-4.15
VAV-4.16
VAV-4.18
VAV-4.19
VAV-4.20
|  |  |  | SME-MZ-04 | VAV-3.2
VAV-5.14
VAV-5.15
VAV-5.16
VAV-6.1
|  |  | AHU | SE-MZ-PR | AHU-1
AHU-2
AHU-3
AHU-4
|  |  | Mezz- Level Pipework | SME-MZ-21 | CHW Pipework
|  |  |  | SME-MZ-22 | CHW Pipework
|  |  |  | SME-MZ-23 | CHW Pipework
|  |  |  | SME-MZ-24 | CHW Pipework
|  |  |  | SME-MZ-25 | CHW Pipework
|  |  | Fans | SME-MZ-02 | F-4
|  |  |  | SME-MZ-03 | F-7
|  | Roof Level | AHU | SME-MZ-02 | AHU-5
AHU-6
|  |  | Chillers | M041 | CH-1
CH-2
|  |  | Pumps | M041 | P-1
P-2
P-3
P-4
P-5
P-6
|  |  | Expansion Tank | M041 | ET-1
ET-2
|  |  | Buffer Tank | M041 | BT-1
|  |  | Roof Pipework | M041 | CHW Pipework
|  |  | Auto-Refill Units | M041 | AFU-1
AFU-2
|  |  | Buffer Tank | M041 | BT-1
|  |  | Boilers | M041 | WH-1
WH-2
|  |  | Fans | M041 | F-5

## Equipment Schedule (hidden)
VAV | SME-00-01 | VAV-5.22
VAV | SME-00-02 | VAV-1.2
VAV | SME-00-02 | VAV-1.3
VAV | SME-00-02 | VAV-1.4
VAV | SME-00-02 | VAV-5.7
VAV | SME-00-02 | VAV-5.8
VAV | SME-00-03 | VAV-4.10
VAV | SME-00-03 | VAV-4.11
VAV | SME-00-03 | VAV-4.21
VAV | SME-00-03 | VAV-5.23
VAV | SME-00-03 | VAV-5.24
VAV | SME-00-04 | VAV-5.9
VAV | SME-00-04 | VAV-5.10
VAV | SME-00-04 | VAV-5.11
VAV | SME-00-04 | VAV-5.17
VAV | SME-00-04 | VAV-5.20
ERV | SME-00-01 | ERV-1
AC Units | SME-00-04 | AC-1
AC Units | SME-00-04 | AC-2
AC Pipework | SME-00-24 | AC Pipework
FCU Units | SME-00-01 | FCU-1
FCU Units | SME-00-01 | FCU-5
FCU Units | SME-00-02 | FCU-6
FCU Units | SME-00-03 | FCU-3
FCU Units | SME-00-03 | FCU-4
FCU Units | SME-00-04 | FCU-2
FCU Units | SME-00-04 | FCU-8
Ground floor Pipework | SME-00-21 | CHW Pipework
Ground floor Pipework | SME-00-22 | CHW Pipework
Ground floor Pipework | SME-00-23 | CHW Pipework
Ground floor Pipework | SME-00-24 | CHW Pipework
Fan | SME-00-01 | F-1
Fan | SME-00-01 | F-6
Fan | SME-00-03 | F-8
Fan | SME-00-03 | F-9
Penetrations | SME-00-04 | FD-001-01
VAV | SME-MZ-01 | VAV-1.1
VAV | SME-MZ-01 | VAV-2.1
VAV | SME-MZ-01 | VAV-2.3
VAV | SME-MZ-01 | VAV-3.1
VAV | SME-MZ-01 | VAV-3.4
VAV | SME-MZ-01 | VAV-4.1
VAV | SME-MZ-01 | VAV-4.2
VAV | SME-MZ-01 | VAV-4.3
VAV | SME-MZ-01 | VAV-4.7
VAV | SME-MZ-01 | VAV-4.17
VAV | SME-MZ-02 | VAV-5.1
VAV | SME-MZ-02 | VAV-5.2
VAV | SME-MZ-02 | VAV-5.4
VAV | SME-MZ-02 | VAV-5.5
VAV | SME-MZ-02 | VAV-5.19
VAV | SME-MZ-02 | VAV-5.21
VAV | SME-MZ-02 | VAV-6.2
VAV | SME-MZ-02 | VAV-6.3
VAV | SME-MZ-03 | VAV-2.2
VAV | SME-MZ-03 | VAV-3.5
VAV | SME-MZ-03 | VAV-3.6
VAV | SME-MZ-03 | VAV-3.7
VAV | SME-MZ-03 | VAV-4.4
VAV | SME-MZ-03 | VAV-4.5
VAV | SME-MZ-03 | VAV-4.13
VAV | SME-MZ-03 | VAV-4.15
VAV | SME-MZ-03 | VAV-4.16
VAV | SME-MZ-03 | VAV-4.18
VAV | SME-MZ-03 | VAV-4.19
VAV | SME-MZ-03 | VAV-4.20
VAV | SME-MZ-04 | VAV-3.2
VAV | SME-MZ-04 | VAV-5.14
VAV | SME-MZ-04 | VAV-5.15
VAV | SME-MZ-04 | VAV-5.16
VAV | SME-MZ-04 | VAV-6.1
AHU | SE-MZ-PR | AHU-1
AHU | SE-MZ-PR | AHU-2
AHU | SE-MZ-PR | AHU-3
AHU | SE-MZ-PR | AHU-4
Mezz- Level Pipework | SME-MZ-21 | CHW Pipework
Mezz- Level Pipework | SME-MZ-22 | CHW Pipework
Mezz- Level Pipework | SME-MZ-23 | CHW Pipework
Mezz- Level Pipework | SME-MZ-24 | CHW Pipework
Mezz- Level Pipework | SME-MZ-25 | CHW Pipework
Fans | SME-MZ-02 | F-4
Fans | SME-MZ-03 | F-7
AHU | SME-MZ-02 | AHU-5
AHU | SME-MZ-02 | AHU-6
Chillers | M041 | CH-1
Chillers |  | CH-2
Pumps | M041 | P-1
Pumps | M041 | P-2
Pumps | M041 | P-3
Pumps | M041 | P-4
Pumps | M041 | P-5
Pumps | M041 | P-6
Expansion Tank | M041 | ET-1
Expansion Tank | M041 | ET-2
Buffer Tank | M041 | BT-1
Auto-Refill Units | M041 | AFU-1
Auto-Refill Units | M041 | AFU-2
Buffer Tank | M041 | BT-1
Boilers | M041 | WH-1
Boilers | M041 | WH-2
Fans | M041 | F-5
Roof Pipework | M041 | CHW Pipework

## Project Structure V1 - For Use (hidden)
Project Name
Job Number
Builder:
Project Manager:
Safety Plan and SWMS
Toolbox Meetings
Work Permits
Delivery Dockets
Builders Works & Site Issues
Day Rate Works
Drafting & Design Issues
Demolition works
QA
|  | AC Units | FCU-AG.2 | Checklist Inserted
Checklist Inserted
|  |  | FCU-AG.3 | Checklist Inserted
Checklist Inserted
|  |  | FCU-AG.4 | Checklist Inserted
Checklist Inserted
|  |  | FCU-AG.2 | Checklist Inserted
Checklist Inserted
|  | Fans | Fan 1 | Checklist Inserted
Checklist Inserted
|  |  | Fan 4 | Checklist Inserted
Checklist Inserted
Penetrations
|  |  | PP1 | Checklist Inserted
Checklist Inserted
|  |  | FD 1 | Checklist Inserted

## Project Structure TEST (2) (hidden)
OHS
| SWMS | [5 empty] | Ability to Add
| Site Safety Plan | [5 empty] | Ability to Add
| Incident Report | [5 empty] | Ability to Add
| Toolbox Meetings | [5 empty] | Ability to Add
| Working Permits | [5 empty] | Ability to Add
Site Issues | [6 empty] | Ability to Add
Variations/Transmittals | [6 empty] | Ability to Add
Greenstar | [6 empty] | Ability to Add
Deliveries | [6 empty] | Ability to Add
Site QA
|  | Office A | Ground Floor
|  |  |  | FCU-AG.1/CU-AG.1 | FCU-AG.1 | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[6 empty] | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-AG.1 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-AG.2 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-AG.2 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-AG.3 | Rough In | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-AG.3 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-AG.4 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-AG.4 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-AG.5 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-AG.5 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-AG.6 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-AG.6 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-AG.7 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-AG.7 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-AG.8 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-AG.8 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-AG.9 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-AG.9 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  | Office A | Level 1
|  |  |  | FCU-A1.1 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-A1.1 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-A1.2 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-A1.2 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-A1.3 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-A1.3 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-A1.4 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-A1.4 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-A1.5 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-A1.5 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-A1.6 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-A1.6 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-A1.7 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-A1.7 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-A1.8 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-A1.8 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-A1.9 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-A1.9 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
Warehouse A Office
|  |  | Dispatch Office | FCU-WA.1 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-WA.1 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  | Print DP Office | FCU-WA.2 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-WA.2 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  | Trans Uban | FCU-WA.3 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-WA.3 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  | Office A Fans | Office A
|  |  |  | TEF-A-1.1 |  | Rough In | Rough In Checklist Fans
[6 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | TEF-A-G.1 |  | Rough In | Rough In Checklist Fans
[6 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | TEF-A-G.2 |  | Rough In | Rough In Checklist Fans
[6 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | OAF-A-G.1 |  | Rough In | Rough In Checklist Fans
[6 empty] | Fit off | Fit Off Checklist Fan
Warehouse A Equipment Room
|  |  |  | GEF-A-1 |  | Rough In | Rough In Checklist Fans
[6 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | GEF-A-2 |  | Rough In | Rough In Checklist Fans
[6 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | GEF-A-3 |  | Rough In | Rough In Checklist Fans
[6 empty] | Fit off | Fit Off Checklist Fan
|  |  |  | GEF-A-4 |  | Rough In | Rough In Checklist Fans
[6 empty] | Fit off | Fit Off Checklist Fan
|  | Building A Fire Damper | Main Switchroom
|  |  |  | FD-1 |  |  | Fire Damper Checklist
|  |  |  | FD-2 |  |  | Fire Damper Checklist
|  | Office B | Floor Level 1
|  |  |  | FCU-B1.1 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-B1.1 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-B1.2 | Rough In | Rough In | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off | Fit off | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-B1.2 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-B1.3 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-B1.3 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-B1.4 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-B1.4 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  |  |  | FCU-B1.5 | Rough In |  | Rough In Checklist AC Ducted Ceiling Unit
[5 empty] | Fit off |  | Fit Off Checklist AC Ducted Ceiling Unit
[5 empty] | CU-B1.5 | Rough In | Rough In Checklist AC Outdoor unit
[6 empty] | Fit off | Fit Off Checklist AC Outdoor unit
[5 empty] | Comissioning |  | Commissioning Checklist
|  | Office B Fans | Office B
|  |  |  | TEF-BG.1 | Rough In |  | Rough In Checklist Fans
[5 empty] | Fit off |  | Fit Off Checklist Fan
|  |  |  | TEF-B1.1 | Rough In |  | Rough In Checklist Fans
[5 empty] | Fit off |  | Fit Off Checklist Fan
Warehouse B Smoke Fans
|  |  |  | SEF-B.1 | Rough In |  | Rough In Checklist Fans
[5 empty] | Fit off |  | Fit Off Checklist Fan
|  |  |  | SEF-B.2 | Rough In |  | Rough In Checklist Fans
[5 empty] | Fit off |  | Fit Off Checklist Fan
|  |  |  | SEF-B.3 | Rough In |  | Rough In Checklist Fans
[5 empty] | Fit off |  | Fit Off Checklist Fan
|  | MSSB | Warehouse A MSSB
|  |  |  | MSSB-A |  |  | MSSB Checklist
Warehouse B MSSB
|  |  |  | MSSB-B |  |  | MSSB Checklist

## Project Structure (hidden)
OHS
| SWMS |  |  |  | Ability to Add
| Site Safety Plan |  |  |  | Ability to Add
| Incident Report |  |  |  | Ability to Add
| Toolbox Meetings |  |  |  | Ability to Add
| Working Permits |  |  |  | Ability to Add
Site Issues |  |  |  |  | Ability to Add
Variations/Transmittals |  |  |  |  | Ability to Add
Greenstar |  |  |  |  | Ability to Add
Deliveries |  |  |  |  | Ability to Add
Site QA
Rough In
|  | Office A | Ground Floor
|  |  |  | FCU-AG.1 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.1 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.2 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.2 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.3 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.3 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.4 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.4 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.5 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.5 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.6 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.6 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.7 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.7 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.8 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.8 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.9 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.9 | Rough In Checklist AC Outdoor unit
Floor Level 1
|  |  |  | FCU-A1.1 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.1 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.2 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.2 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.3 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.3 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.4 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.4 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.5 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.5 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.6 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.6 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.7 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.7 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.8 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.8 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.9 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.9 | Rough In Checklist AC Outdoor unit
Warehouse A Office
|  |  | Dispatch Office | FCU-WA.1 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-WA.1 | Rough In Checklist AC Outdoor unit
|  |  | Print DP Office | FCU-WA.2 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-WA.2 | Rough In Checklist AC Outdoor unit
|  |  | Trans Uban | FCU-WA.3 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-WA.3 | Rough In Checklist AC Outdoor unit
|  | Office A Fans | Office A
|  |  |  | TEF-A-1.1 | Rough In Checklist Fans
|  |  |  | TEF-A-G.1 | Rough In Checklist Fans
|  |  |  | TEF-A-G.2 | Rough In Checklist Fans
|  |  |  | OAF-A-G.1 | Rough In Checklist Fans
Warehouse A Equipment Room
|  |  |  | GEF-A-1 | Rough In Checklist Fans
|  |  |  | GEF-A-2 | Rough In Checklist Fans
|  |  |  | GEF-A-3 | Rough In Checklist Fans
|  |  |  | GEF-A-4 | Rough In Checklist Fans
|  | Building A Fire Damper | Main Switchroom
|  |  |  | FD-1 | Fire Damper Checklist
|  |  |  | FD-2 | Fire Damper Checklist
|  | Office B | Floor Level 1
|  |  |  | FCU-B1.1 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-B1.1 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-B1.2 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-B1.2 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-B1.3 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-B1.3 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-B1.4 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-B1.4 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-B1.5 | Rough In Checklist AC Ducted Ceiling Unit
|  |  |  | CU-B1.5 | Rough In Checklist AC Outdoor unit
|  | Office B Fans | Office B
|  |  |  | TEF-BG.1 | Rough In Checklist Fans
|  |  |  | TEF-B1.1 | Rough In Checklist Fans
Warehouse B Smoke Fans
|  |  |  | SEF-B.1 | Rough In Checklist Fans
|  |  |  | SEF-B.2 | Rough In Checklist Fans
|  |  |  | SEF-B.3 | Rough In Checklist Fans
|  | MSSB | Warehouse A MSSB
|  |  |  | MSSB-A | MSSB Checklist
Warehouse B MSSB
|  |  |  | MSSB-B | MSSB Checklist
Fit Off
|  | Office A | Ground Floor
|  |  |  | FCU-AG.1 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.1 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.2 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.2 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.3 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.3 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.4 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.4 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.5 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.5 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.6 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.6 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.7 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.7 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.8 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.8 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-AG.9 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-AG.9 | Rough In Checklist AC Outdoor unit
Floor Level 1
|  |  |  | FCU-A1.1 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.1 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.2 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.2 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.3 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.3 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.4 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.4 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.5 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.5 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.6 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.6 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.7 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.7 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.8 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.8 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-A1.9 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-A1.9 | Rough In Checklist AC Outdoor unit
Warehouse A Office
|  |  | Dispatch Office | FCU-WA.1 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-WA.1 | Rough In Checklist AC Outdoor unit
|  |  | Print DP Office | FCU-WA.2 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-WA.2 | Rough In Checklist AC Outdoor unit
|  |  | Trans Uban | FCU-WA.3 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-WA.3 | Rough In Checklist AC Outdoor unit
|  | Office A Fans | Office A
|  |  |  | TEF-A-1.1 | Fit Off Checklist Fan
|  |  |  | TEF-A-G.1 | Fit Off Checklist Fan
|  |  |  | TEF-A-G.2 | Fit Off Checklist Fan
|  |  |  | OAF-A-G.1 | Fit Off Checklist Fan
Warehouse A Equipment Room
|  |  |  | GEF-A-1 | Fit Off Checklist Fan
|  |  |  | GEF-A-2 | Fit Off Checklist Fan
|  |  |  | GEF-A-3 | Fit Off Checklist Fan
|  |  |  | GEF-A-4 | Fit Off Checklist Fan
|  | Building A Fire Damper | Main Switchroom
|  |  |  | FD-1 | Fire Damper Checklist
|  |  |  | FD-2 | Fire Damper Checklist
|  | Office B | Floor Level 1
|  |  |  | FCU-B1.1 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-B1.1 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-B1.2 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-B1.2 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-B1.3 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-B1.3 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-B1.4 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-B1.4 | Rough In Checklist AC Outdoor unit
|  |  |  | FCU-B1.5 | Fit Off Checklist AC Ducted Ceiling Unit
|  |  |  | CU-B1.5 | Rough In Checklist AC Outdoor unit
|  | Office B Fans | Office B
|  |  |  | TEF-BG.1 | Fit Off Checklist Fan
|  |  |  | TEF-B1.1 | Fit Off Checklist Fan
Warehouse B Smoke Fans
|  |  |  | SEF-B.1 | Fit Off Checklist Fan
|  |  |  | SEF-B.2 | Fit Off Checklist Fan
|  |  |  | SEF-B.3 | Fit Off Checklist Fan
|  | MSSB | Warehouse A MSSB
|  |  |  | MSSB-A | MSSB Checklist
Warehouse B MSSB
|  |  |  | MSSB-B | MSSB Checklist

## Matrices Overall Progress
Rough In | Fit Off | Commissioning

## Resources V1 - For Use
checklist | Project Details
checkpoint-no status | Project Details:
label | Project Number:
label | Builder:
label | Project Manager:
checklist | SWMS | Ability to add
checkpoint | SWMS & Safety Plan submitted
checklist | Toolbox Meetings | Ability to add
checkpoint | Site Meetings
checklist | Working Permits | Ability to add
checkpoint | Please take a photo of work permit
text | Description of Permit
text | Work Area
checklist | Delivery Docket | Ability to add
checkpoint | Please take photo of delivery docket
text | Date
text | Work Area
text | Material
text | Supplier/Subcontractor
checklist | Builders Works & Site Issues | Ability to add
checkpoint | Need ability to add new checklist that we can name on site |  | Need ability to add a basic checklist that we can label on site
checklist | Day Rate Works | Ability to add
checkpoint | Need ability to add new checklist that we can name on site |  | Need ability to add a basic checklist that we can label on site
checklist | Drafting & Design Issues | Ability to add
checkpoint | Need ability to add new checklist that we can name on site
checklist | As Built Markups | Ability to add
checkpoint | Need ability to add new checklist that we can name on site
checklist | Cassette Rough In | Ability to add
checkpoint | Unit Model Number correct, vibration mounts installed & unit Labelled
Checklist | Cassette Pipework & Drains | Ability to add
checkpoint | Condensate drain installed including hose clamps
checkpoint | Refrigeration pipework installed including insulation over flare nuts
checklist | Cassette Fit Off | Ability to add
checkpoint | Fascia fitted square and plug loom connected
checklist | Cassette Commissioning | Ability to add
checkpoint | check drain fitted of at tundish with air break
checkpoint | Check Operation of unit heat/cool & louvre operation
checklist | CHW FCU Rough In | Ability to add
checkpoint | Unit Model Number correct, vibration mounts installed & unit Labelled
checklist | CHW FCU Pipework & Drains | Ability to add
checkpoint | CHW pipework roughed in and connected to unit
checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
checklist | CHW FCU Ductwork | Ability to add
checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checklist | CHW FCU Flex & Cushion Boxes | Ability to add
checkpoint | All flexible ductwork installed
checkpoint | All cushion heads installed and setout noted
checklist | CHW FCU Fit Off | Ability to add
checkpoint | Grilles/louvres installed
checkpoint | Filters installed and are removable
checkpoint | check drain fitted off at tundish with air break
checklist | CHW FCU Commissioning | Ability to add
checkpoint | Check Operation of unit
checkpoint | Check for noise and vibration
checklist | AC Ducted Unit Rough In | Ability to add
checkpoint | Unit Model Number correct, vibration mounts installed & unit Labelled
checklist | AC Ducted Unit Pipework & Drains | Ability to add
checkpoint | Pipework roughed in
checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
checklist | AC Ducted Unit Ductwork | Ability to add
checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checklist | AC Ducted Unit Flex & Cushion Boxes | Ability to add
checkpoint | All flexible ductwork installed
checkpoint | All cushion heads installed and setout noted
checklist | AC Ducted Unit Fit Off | Ability to add
checkpoint | Filters installed and are removable
checkpoint | Condensate drains installed and terminated to correct location and tested
checkpoint | Grilles/louvres installed
checklist | AC Ducted Unit Commissioning | Ability to add
checkpoint | Check Operation of unit
checkpoint | Check for noise and vibration
checklist | AC High wall mounted Rough In | Ability to add
checkpoint | Refrigeration pipework roughed in to correct location
checkpoint | Condensate drains installed to tundish/waste point provided
checklist | AC High wall mounted Fit Off | Ability to add
checkpoint | Wall mount fitted off and checked for level
checkpoint | Condensate drains terminated at tundish and tested
checklist | AC Outdoor unit (Stand Alone) Fit Off | Ability to add
checkpoint | Unit Model Number correct, vibration mounts installed & unit Labelled
checkpoint | Condensate drains installed to tundish/waste point provided
checkpoint | System pressure tested to 400PSI
checklist | AC Outdoor unit (Stand Alone) Commissioning | Ability to add
checkpoint | System evacuated and valves opened
checkpoint | Operation checked
checklist | AC Branch Box Rough In | Ability to add
checkpoint | Model Number correct, vibration mounts installed & unit Labelled
checklist | Branch Box Pipe & Drains | Ability to add
checkpoint | Refrigeration pipework roughed in
checkpoint | Condensate drain pipework installed and hose clamps fitted
checklist | Fans Rough In | Ability to add
checkpoint | Fan Model Number correct, vibration mounts installed & Fan Labelled
checklist | Fan Ductwork | Ability to add
checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checklist | Fan Flex & Cushion Boxes | Ability to add
checkpoint | All flexible ductwork installed
checkpoint | All cushion heads installed and setout noted
checklist | Fan Fit Off | Ability to add
checkpoint | Filters installed and are removable
checkpoint | Grilles/louvres installed
checklist | Fan Commissioning | Ability to add
checkpoint | Check for noise and vibration
checklist | Evap Cooler Rough In | Ability to add
checkpoint | Evap Model Number correct, vibration mounts installed & Labelled
checklist | Evap Cooler Pipework & Drains | Ability to add
checkpoint | Water connection complete
checkpoint | Drain to point of discharge installed
checklist | Evap Ductwork
checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checklist | Evap Flex & Cushion Boxes
checkpoint | All flexible ductwork installed
checkpoint | All cushion heads installed and setout noted
checklist | Evap Commissioning
checkpoint | Unit Operational, checked for vibration and noise
checklist | AHU Rough In | Ability to add
checkpoint | Model Number correct, vibration mounts installed & Labelled
checklist | AHU Pipework & Drains
checkpoint | Pipework roughed in
checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
checklist | AHU Ductwork
checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checklist | AHU Flex & Cushion Boxes
checkpoint | All flexible ductwork installed
checkpoint | All cushion heads installed and setout noted
checklist | AHU Fit Off
checkpoint | Grilles/louvres installed
checkpoint | Filters installed and are removable
checkpoint | Condensate drains terminated at tundish and tested
checklist | AHU Commissioning
checkpoint | Unit Operational, checked for vibration and noise
checklist | ERV Rough In | Ability to add
checkpoint | Model Number correct, vibration mounts installed & Labelled
checklist | ERV Pipework & Drains
checkpoint | Pipework roughed in
checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
checklist | ERV Ductwork
checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checkpoint | Cowls installed
checklist | ERV Flex & Cushion Boxes
checkpoint | All flexible ductwork installed
checkpoint | All cushion heads installed and setout noted
checklist | ERV Fit Off
checkpoint | Grilles/louvres installed
checkpoint | Filters installed and are removable
checkpoint | check drain fitted of at tundish with air break
checklist | ERV Commissioning
checkpoint | Unit Operational, checked for vibration and noise
checklist | MSSB Checklist | Ability to add
checkpoint | MSSB mounted in position
checkpoint | MSSB Fitted off
checkpoint | Main power connected to MSSB
checklist | Fire Damper & Pipework Penetration Checklist | Ability to add
checkpoint | Fire treatment installed correctly, sealed and labelled
checklist | Installation Overview | Ability to add
checkpoint | Installation progress - Weekly Photo's of highlighted plans required
checklist | CHW & HHW Pipework | Ability to add
checkpoint | Pipework installed as per Shop Drawings & Schematic
checkpoint | Pipework Pressure Tested
checkpoint | Pipework checked for leaks & Labelled correctly
checkpoint | Pipework lagging and cladding complete
checklist | Refrigeration Pipe | Ability to add
checkpoint | Pipework installed as per Schematic and Shop Drawings
checkpoint | Actual Pipe Meters Recorded on schematic
checkpoint | Pipework Pressure Tested @400 psi
checklist | Demo | Ability to add
checkpoint | All flexible connections & cushion heads Demo as per drawing.
checkpoint | All Rubbish Removed Area Clean And Tidy
checklist | Demo & Decommission | Ability to add
checkpoint | Electrical isolated and made safe
checkpoint | All Rubbish Removed Area Clean And Tidy
checklist | Radiators (HHW) ROUGH IN | Ability to add
checkpoint | backing plate installed prior to plaster
checklist | Radiators (HHW) Fit Off | Ability to add
checkpoint | Radiator Installed c/w pipework covers
checkpoint | Checked for leaks
checkpoint | Low temperature cover installed (As Applicable)
checklist | Boiler | Ability to add
checkpoint | Model Number correct & Labelled
checkpoint | Pipework connected and no leaks
checkpoint | Gas connected and leak tested
checkpoint | Flue installed
checkpoint | Operation tested
checklist | Pumps | Ability to add
checkpoint | Model Number correct, vibration mounts installed & Labelled
checkpoint | Pipework connected and no leaks
checkpoint | Operation tested
checklist | Chiller | Ability to add
checkpoint | Model Number correct, vibration mounts installed & Labelled
checkpoint | Pipework connected and no leaks
checkpoint | Operation tested
checklist | Expansion Tank | Ability to add
checkpoint | Model Number correct, vibration mounts installed & Labelled
checkpoint | Pipework connected and no leaks
checklist | Auto Refill Units | Ability to add
checkpoint | Model Number correct, installed & Labelled
checkpoint | Pipework connected and no leaks
checklist | Defect | Ability to add
checkpoint | Defect rectified
checklist | VAV | Ability to add
checkpoint | VAV installed, Model Number correct & unit Labelled
checklist | AC Outdoor unit (VRF) Fit Off | Ability to add
checkpoint | Unit Model Number correct, vibration mounts installed & unit Labelled
checkpoint | Condensate drains installed to tundish/waste point provided
checkpoint | System pressure tested to 400PSI
checklist | AC Outdoor unit (VRF) Commissioning | Ability to add
checkpoint | System evacuated and valves opened - Photo of vac stat required
checkpoint | Operation checked
checklist | AC Outdoor unit (VRV) Fit Off | Ability to add
checkpoint | Unit Model Number correct, vibration mounts installed & unit Labelled
checkpoint | Condensate drains installed to tundish/waste point provided
checkpoint | System pressure tested to 400PSI
checklist | AC Outdoor unit (VRV) Commissioning | Ability to add
checkpoint | System evacuated and valves opened - Photo of vac stat required
checkpoint | Operation checked
checklist | Package Unit | Ability to add
checkpoint | Unit Model Number correct, vibration mounts installed & unit Labelled
checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checkpoint | Overflashings installed
checkpoint | Drains installed to waste point
checkpoint | Operation tested
checklist | Roof Cowl (RC) | Ability to add
checkpoint | RC Model Number correct, installed & RC Labelled
checkpoint
checklist | Flexible Connection & Cushin Heads | Ability to add
checkpoint | All flexible connections & cushion heads are Installed s per drawings, including ductwork connections.

## Layout test (hidden)
Site QA
| Office A | Ground Floor
FCU-AG.1
|  |  |  | Rough In | Equipment installed into position and correctly aligned and in direction of flow | Yes | No | Pending | N/A | One Photo for proof
Vibration isolation installed
All solid ductwork installed
All flexible/canvas ductwork installed
Dampers installed (NRD, VC, FD, MVCD) Correctly
Condensate drains installed to tundish/waste point provided
Electrical installation roughed in to unit
Controls installation roughed in to unit
Fire Shutdown cable roughed in
Refrigeration pipework roughed in
Refrigeration pipework under pressurization
General area inspection for defects
Installed as per shop drawings
Works area tidy and clean of debris
|  |  |  | Fit off | Equipment installed into position and correctly aligned and in direction of flow
Outside equipment installed into position and correctly aligned
Vibration isolation installed
All solid ductwork installed
All flexible/canvas ductwork installed
Dampers installed (NRD, VC, FD, MVCD) Correctly
Solid ductwork capped, covered, sealed and seams weatherproofed
Overflashings installed and weatherproofed
All equipment/materials correctly insulated as required
Water supplied to equipment
Condensate drains installed to tundish/waste point provided
Electrical installation roughed in to unit
Controls installation roughed in to unit
Fire Shutdown cable roughed in
VSD installed including electrical and controls
Refrigeration pipework as per drawing
General area inspection for defects
Installed as per shop drawings
Works area tidy and clean of debris
|  |  |  | CU-AG.1 | Rough In
Fit off
Comissioning

## Layout (hidden)
Ground Floor
FCU-AG.1
|  | Rough In | Equipment installed into position and correctly aligned and in direction of flow
Vibration isolation installed
All solid ductwork installed
All flexible/canvas ductwork installed
Dampers installed (NRD, VC, FD, MVCD) Correctly
Condensate drains installed to tundish/waste point provided
Electrical installation roughed in to unit
Controls installation roughed in to unit
Fire Shutdown cable roughed in
Refrigeration pipework roughed in
Refrigeration pipework under pressurization
General area inspection for defects
Installed as per shop drawings
Works area tidy and clean of debris
|  | Fit Off | Refrigeration pipework under pressurization
Refrigeration pipework connected to equipment, Vacuum tested
Boxes, Grilles/louvres installed
Filters installed and are removable
Dampers (NRD, VC, FD, MVCD) Fully Open Correctly
Condensate drains installed and terminated to correct location and tested
Electrical installation fitted off
Control works fitted off including all sensors, controllers
Equipment model and serial name plate
Fire Shutdown connected
General area inspection for defects
Labels installed
All equipment/materials correctly insulated as required
Works area tidy and clean of debris
Entire system installed as per shop drawings
Equipment ready for commissioning
|  | CU-AG.2 | Rough In | Outside equipment installed into position and correctly aligned
Refrigeration pipework roughed in
Refrigeration pipework under pressurization
Vibration isolation installed
Outside equipment mounted feet installed
Overflashings installed and weatherproofed
Condensate drains installed to tundish/waste point provided
Electrical installation roughed in to unit
Controls installation roughed in to unit
Condenser Model & Serial Numbers
General area inspection for defects
Installed as per shop drawings
All equipment/materials correctly insulated as required
Works area tidy and clean of debris
|  |  | Fit off | Refrigeration pipework under pressurization
Refrigeration pipework connected to equipment, Vacuum tested
Electrical installation fitted off
Overflashings installed and weatherproofed
drains installed and terminated to correct location and tested (If Needed)
Electrical installation roughed in to unit
Control works fitted off including all sensors, controllers
Equipment model and serial name plate
Fire Shutdown connected
General area inspection for defects
All equipment/materials correctly insulated as required
Works area tidy and clean of debris
Entire system installed as per shop drawings
Equipment ready for commissioning
Comissioning

## Layout (2) (hidden)
Ground Floor
| CU-AG.1 | Rough In | Outside equipment installed into position and correctly aligned
Refrigeration pipework roughed in
Refrigeration pipework under pressurization
Vibration isolation installed
Outside equipment mounted feet installed
Overflashings installed and weatherproofed
Condensate drains installed to tundish/waste point provided
Electrical installation roughed in to unit
Controls installation roughed in to unit
Condenser Model & Serial Numbers
General area inspection for defects
Installed as per shop drawings
All equipment/materials correctly insulated as required
Works area tidy and clean of debris
|  | Fit Off | Refrigeration pipework under pressurization
Refrigeration pipework connected to equipment, Vacuum tested
Electrical installation fitted off
Overflashings installed and weatherproofed
drains installed and terminated to correct location and tested (If Needed)
Electrical installation roughed in to unit
Control works fitted off including all sensors, controllers
Equipment model and serial name plate
Fire Shutdown connected
General area inspection for defects
All equipment/materials correctly insulated as required
Works area tidy and clean of debris
Entire system installed as per shop drawings
Equipment ready for commissioning
|  | Branch Box | Rough In | Equipment installed into position and correctly aligned
Refrigeration pipework roughed in
Refrigeration pipework under pressurization
Branch Box Model & Serial Numbers
General area inspection for defects
Installed as per shop drawings
All equipment/materials correctly insulated as required
Works area tidy and clean of debris
|  |  | Fitoff | Refrigeration pipework under pressurization
Refrigeration pipework connected to equipment, Vacuum tested
Equipment model and serial name plate
General area inspection for defects
All equipment/materials correctly insulated as required
Works area tidy and clean of debris
Entire system installed as per shop drawings
Equipment ready for commissioning
|  | FCU-AG.1 | Rough In
Equipment installed into position and correctly aligned and in direction of flow
Vibration isolation installed
All solid ductwork installed
All flexible/canvas ductwork installed
Dampers installed (NRD, VC, FD, MVCD) Correctly
Condensate drains installed to tundish/waste point provided
Electrical installation roughed in to unit
Controls installation roughed in to unit
Fire Shutdown cable roughed in
Refrigeration pipework roughed in
Refrigeration pipework under pressurization
General area inspection for defects
Installed as per shop drawings
Works area tidy and clean of debris
|  |  | Fitoff | Refrigeration pipework under pressurization
Refrigeration pipework connected to equipment, Vacuum tested
Boxes, Grilles/louvres installed
Filters installed and are removable
Dampers (NRD, VC, FD, MVCD) Fully Open Correctly
Condensate drains installed and terminated to correct location and tested
Electrical installation fitted off
Control works fitted off including all sensors, controllers
Equipment model and serial name plate
Fire Shutdown connected
General area inspection for defects
Labels installed
All equipment/materials correctly insulated as required
Works area tidy and clean of debris
Entire system installed as per shop drawings
Equipment ready for commissioning
|  | FCU-AG.2 | Rough In
Equipment installed into position and correctly aligned and in direction of flow
Vibration isolation installed
All solid ductwork installed
All flexible/canvas ductwork installed
Dampers installed (NRD, VC, FD, MVCD) Correctly
Condensate drains installed to tundish/waste point provided
Electrical installation roughed in to unit
Controls installation roughed in to unit
Fire Shutdown cable roughed in
Refrigeration pipework roughed in
Refrigeration pipework under pressurization
General area inspection for defects
Installed as per shop drawings
Works area tidy and clean of debris
|  |  | Fitoff | Refrigeration pipework under pressurization
Refrigeration pipework connected to equipment, Vacuum tested
Boxes, Grilles/louvres installed
Filters installed and are removable
Dampers (NRD, VC, FD, MVCD) Fully Open Correctly
Condensate drains installed and terminated to correct location and tested
Electrical installation fitted off
Control works fitted off including all sensors, controllers
Equipment model and serial name plate
Fire Shutdown connected
General area inspection for defects
Labels installed
All equipment/materials correctly insulated as required
Works area tidy and clean of debris
Entire system installed as per shop drawings
Equipment ready for commissioning
|  | FCU-AG.3 | Rough In
Equipment installed into position and correctly aligned and in direction of flow
Vibration isolation installed
All solid ductwork installed
All flexible/canvas ductwork installed
Dampers installed (NRD, VC, FD, MVCD) Correctly
Condensate drains installed to tundish/waste point provided
Electrical installation roughed in to unit
Controls installation roughed in to unit
Fire Shutdown cable roughed in
Refrigeration pipework roughed in
Refrigeration pipework under pressurization
General area inspection for defects
Installed as per shop drawings
Works area tidy and clean of debris
|  |  | Fitoff | Refrigeration pipework under pressurization
Refrigeration pipework connected to equipment, Vacuum tested
Boxes, Grilles/louvres installed
Filters installed and are removable
Dampers (NRD, VC, FD, MVCD) Fully Open Correctly
Condensate drains installed and terminated to correct location and tested
Electrical installation fitted off
Control works fitted off including all sensors, controllers
Equipment model and serial name plate
Fire Shutdown connected
General area inspection for defects
Labels installed
All equipment/materials correctly insulated as required
Works area tidy and clean of debris
Entire system installed as per shop drawings
Equipment ready for commissioning
Commissioning