## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP 03 - Partition Walls |  |  |  |  | Yes | SYS - ITP 03 - Partition Walls (old version) | 0fd662f9-bc26-4b0a-80ce-49f31d1af2b5
checkpoint-status |  |  | checkpoint | Set out walls
label | 7aa7afa3-e348-55c7-977b-28c596267a65 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Furring channel to walls
label | f0ec7198-d377-5c1b-9304-ea237ad200c7 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Metal stud wall frame
label | aed5c61b-a89a-5475-9340-bbb109c71a39 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Noggins
label | 498937a0-eadf-5afc-ad7e-3bc2838fa5cb |  | note | As per scope of work. Studco Wall design & installation manual Volume 3.2 Studco Wall design & installation manual
label | f6b0fe28-0fab-59f0-b476-cded925f32f1 |  | note | Volume 3.2 Architectural Specification – 0522 Partition – Framed and Lined Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Check no screws in deflection head
label | e36db3b3-0ac2-5c39-b6fb-6b0d90ef9394 |  | note | No screws in deflection head
checkpoint-status |  |  | checkpoint | Service Check for pre installation of sheets
label | b96df76b-d0e3-54bf-b21e-1dd287067c53 |  | note | All service checklists are signed off by relevant trades
label | a3e84183-316a-57dc-a9e6-67ffc44f38ce |  | note | Central Equity and Building Surveyor Sign Off's attached below
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Sheet all walls
label | 78b0f33e-b352-584b-aac8-2f1f548362c6 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Check wall types before installation (F/R, Acoustic, Wet Area, PBD etc).
label | e6301aab-b925-5501-8a50-88d26c1134d7 |  | note | Boral installation manual revision 2016 and, Ecowool insulation installation guide. Australian Standard: AS/NZS 2589.1:1997
checkpoint-status |  |  | checkpoint | Caulking
label | 8fd60736-a5fb-54dd-9373-638c7fd77905 |  | note | Boral installation manual revision 2016 Australian Standard: AS 1530.4-2014, AS4072.1-2005, AS1157-1972
checkpoint-status |  |  | checkpoint | Check insulation in walls
label | 98c85149-4708-5325-9a1c-d30454d1704c |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Ecowool Installation Guidelines Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 : 1999, AS/NZS1530 Part 1: 1994
checkpoint-status |  |  | checkpoint | Stopping to walls
label | df463a4e-d871-59cb-a47e-f0bcc83d6e74 |  | note | Boral installation manual revision 2016 Australian Standard: AS/NZS 2589.1:1997
checkpoint-status |  |  | checkpoint | Sanding to walls
label | eeaa1778-951a-562f-aaf5-7334aab1d6e2 |  | note | Boral installation manual revision 2016 Australian Standard: AS/NZS 2589.1:1997
checkpoint-status |  |  | checkpoint | Clean up
label | 1ebf5441-dbdd-50b9-9501-706140a15e09 |  | note | Waste all cleaned. Tools and materials placed well.
checkpoint-status |  |  | checkpoint | Check walls for patching
label | a22ecc9e-c990-5b32-87cc-8faba2a221ab |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol.
checkpoint-status |  |  | checkpoint | Materials Receipt Inspection
label | ffe6f776-4716-50f0-991c-35efec085e2f |  | note | Refer to ITP No: 5 Incoming Goods
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | ITP 04 - Suspended Ceiling Revision |  |  |  |  | Yes | SYS - ITP 04 - Suspended Ceiling Revision (old version) | 15d6d1f0-b203-47f7-8a99-7235c898d25a
checkpoint-status |  |  | checkpoint | Frame ceilings
label | 565bf082-2c4d-54cb-b884-ab161de99ef6 |  | note | Reflected Ceiling Plan approved by Kapitol. Studco installation guide. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Bulkhead framing
label | 6d4ec3b5-1a95-5d2e-a200-c6e706e88767 |  | note | Reflected Ceiling Plan approved by Kapitol. Studco installation guide. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Trim out access panels
label | c402f676-bdf2-5166-90ed-77d87f5b2787 |  | note | Reflected Ceiling Plan approved by Kapitol. Studco installation guide. Australian Standard - AS1530.4:2014
checkpoint-status |  |  | checkpoint | Insulation to ceilings
label | 116c1342-2837-5ffd-a661-563c034d979f |  | note | Reflected Ceiling Plan approved by Kapitol. Ecowool insulation installation guide Acoustic Specification approved by
label | 062e2a36-1d8a-5d69-87ef-4c6fc25533aa |  | note | SLR Global Environmental Solutions Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 : 1999, AS/NZS1530 Part 1: 1994
checkpoint-status |  |  | checkpoint | Service Check for pre installation of sheets
label | e6ade3ac-23fc-53ab-a673-61cbd570225b |  | note | All service checklists are signed off by relevant trades
label | 870bf51b-899e-5fae-95fb-595deee26cbc |  | note | Central Equity and Building Surveyor Sign Off's attached below
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Sheets to ceiling
label | ee1a8eb4-6b1f-5dc0-b629-983362c30b7f |  | note | Reflected Ceiling Plan approved by Kapitol. Acoustic Specification approved by SLR Global Environmental Solutions Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Stopping to ceilings
label | 6f73c7fa-9192-5745-b96e-348916611672 |  | note | Boral installation manual revision 2016. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Sanding to ceilings
label | bc39ecbd-fcc7-5ff3-9a73-2dada2d7c298 |  | note | Boral installation manual revision 2016. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Fit access hatch frame
label | f7156664-4b66-541a-aeff-fb639d4f9c65 |  | note | Reflected Ceiling Plan approved by Kapitol. Australian Standard - AS1530.4:2014
checkpoint-status |  |  | checkpoint | Cut out for lights
label | d300f33d-9676-5a42-846d-1b2818f44c82 |  | note | Reflected Ceiling Plan approved by Kapitol.
checkpoint-status |  |  | checkpoint | Clean up
label | a8172b59-4e8c-51a8-881d-20bf53ec0af9 |  | note | Waste all cleaned. Tools and materials placed well.
checkpoint-status |  |  | checkpoint | Check ceilings for patching
label | 51e4eb40-d9d7-595b-bf10-5387217f18a1 |  | note | Reflected Ceiling Plan approved by Kapitol.
checkpoint-status |  |  | checkpoint | Materials Receipt Inspection
label | 2e38fd0a-ffbc-556e-aacf-7a580fcc9297 |  | note | Refer to ITP No: 5 Incoming Goods
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | ITP 02 - Speedpanel |  |  |  |  | Yes | ITP 02 - Speedpanel | 6ab90f66-950a-43bb-8101-87efa3a1d305
checkpoint-status |  |  | checkpoint | Set out Speedpanel walls
label | b5e797e5-7284-5e62-87ea-783de2c8f821 |  | note | Wall Type and Wall types & Setout drawings approved by Kapitol and Architectural Specification
label | 6a431812-b412-5421-8cea-f76694da0c18 |  | note | Speedpanel installation guide revision 1. Australian Standard AS1530.4
checkpoint-status |  |  | checkpoint | Install Speedpanel
label | 6b421474-59f2-5eb9-9da0-52709e588939 |  | note | Wall Type and Wall types & Setout drawings approved by Kapitol and Architectural Specification
label | 06c60769-0b00-587c-8fe6-c11f66755a57 |  | note | Speedpanel installation guide revision 1. Australian Standard AS1530.4
checkpoint-status |  |  | checkpoint | Caulking
label | fb53785d-5bed-544a-9084-e38f5d78b633 |  | note | Speedpanel installation guide revision 1 Australian Standard AS1530.4
checkpoint-status |  |  | checkpoint | Clean up
label | b7f1b952-4c4d-5b66-96d9-b30f116b56ab |  | note | Waste all cleaned. Tools and materials placed well.
checkpoint-status |  |  | checkpoint | Materials Receipt Inspection
label | 2d897fc5-0675-5ffe-9f86-42c70259a235 |  | note | Refer to ITP No: 5 Incoming Goods
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | ITP 04 - Suspended Ceiling Revision |  |  |  |  | Yes | ITP 04 - Suspended Ceiling Revision | 8c110286-1c31-46b7-89d3-811ea50df5e6
checkpoint-status |  |  | checkpoint | Frame ceilings
label | 540aaca0-dea5-5f2a-b4bf-088854d3c6a4 |  | note | Reflected Ceiling Plan approved by Kapitol. Studco installation guide. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Bulkhead framing
label | 749f5900-df63-5a06-8a53-3d3eb09c1878 |  | note | Reflected Ceiling Plan approved by Kapitol. Studco installation guide. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Trim out access panels
label | ca091a36-6841-5db9-9d3b-3551a92cf979 |  | note | Reflected Ceiling Plan approved by Kapitol. Studco installation guide. Australian Standard - AS1530.4:2014
checkpoint-status |  |  | checkpoint | Insulation to ceilings
label | 318885d3-c4fe-5cc4-967b-947d3685bdca |  | note | Reflected Ceiling Plan approved by Kapitol. Ecowool insulation installation guide Acoustic Specification approved by
label | b840d94e-92e5-551e-9bbc-6b63729377c8 |  | note | SLR Global Environmental Solutions Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 : 1999, AS/NZS1530 Part 1: 1994
checkpoint-status |  |  | checkpoint | Service Check for pre installation of sheets
label | 1a693e21-c41a-54e2-87d2-6950e235036c |  | note | All service checklists are signed off by relevant trades
label | 4e9bd759-048e-5767-b369-5f76e722b792 |  | note | Photo of completed ceiling sign off sheet attached
checkpoint-status |  |  | checkpoint | Sheets to ceiling
label | 5650176d-aea9-5f64-9e4a-90a11a99e5dc |  | note | Reflected Ceiling Plan approved by Kapitol. Acoustic Specification approved by SLR Global Environmental Solutions Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Stopping to ceilings
label | 9ec1fef7-b788-5966-86ee-d8792a6163aa |  | note | Boral installation manual revision 2016. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Sanding to ceilings
label | 95b7749d-dc2c-5db3-8302-a41035da586a |  | note | Boral installation manual revision 2016. Australian Standard AS/NZS 2785:2000
checkpoint-status |  |  | checkpoint | Fit access hatch frame
label | 3ca93d54-5f98-552e-addc-fd71f56b3c0a |  | note | Reflected Ceiling Plan approved by Kapitol. Australian Standard - AS1530.4:2014
checkpoint-status |  |  | checkpoint | Cut out for lights
label | a24f0881-58a3-505c-92dd-e6b0eef6548a |  | note | Reflected Ceiling Plan approved by Kapitol.
checkpoint-status |  |  | checkpoint | Clean up
label | 6e3c9113-100e-5682-a454-14dbc8746864 |  | note | Waste all cleaned. Tools and materials placed well.
checkpoint-status |  |  | checkpoint | Check ceilings for patching
label | eaed70f6-db55-5a3d-b373-461670e3bd6d |  | note | Reflected Ceiling Plan approved by Kapitol.
checkpoint-status |  |  | checkpoint | Materials Receipt Inspection
label | 0114e157-9343-5cd1-a43a-8e10d38ef398 |  | note | Refer to ITP No: 5 Incoming Goods
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | ITP 05 - Incoming Goods |  |  |  |  | Yes | ITP 05 - Incoming Goods | b7525990-b560-470f-a352-4c9fabb0d8b3
checkpoint-status |  |  | checkpoint | Check the items
label | f9b7e3d6-3cca-5141-b2b0-6647912903c4 |  | note | • The items received match the description on the order • Appearance of master carton and unit package is intact • The items are not damaged/deteriorative/wet • The items are not dirty/dusty
checkpoint-status |  |  | checkpoint | Check Quantity
label | d277d515-7d9c-5357-a454-c11b4b676be4 |  | note | • The correct items were shipped • No items are missing • Quantity of items received matches quantity indicated on invoice • Quantity of items received matches quantity requested on order
checkpoint-status |  |  | checkpoint | Check the label
label | 462f79c3-0365-566c-9f68-a7da8dddc159 |  | note | • Manufacturer/Distributor's name is not missing • "upwards", "moisture proof" marking or label is not missing • Warning statement is not missing
checkpoint-status |  |  | checkpoint | Material Receipt Inspection
label | d388a812-3bd2-5d95-a927-8e223778a736 |  | note | • Foreman/Leading Hand to keep a record for all material delivery receipt
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | ITP 03 - Partition Walls |  |  |  |  | Yes | ITP 03 - Partition Walls | cae0c5b6-5a3b-43ca-9adf-e98da4651198
checkpoint-status |  |  | checkpoint | Set out walls
label | ff5b561d-7bb1-5b0b-905f-ba2cc096f4ba |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Furring channel to walls
label | 46d756f4-32ab-50fc-a48f-fc4978c38809 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Metal stud wall frame
label | 57620d31-f659-5609-b582-b3247a2dc62e |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Noggins
label | 65af4b11-0d88-5bde-a33d-436f53444307 |  | note | As per scope of work. Studco Wall design & installation manual Volume 3.2 Studco Wall design & installation manual
label | a8b23f0b-1282-5a78-9c68-b0dd8fe087cd |  | note | Volume 3.2 Architectural Specification – 0522 Partition – Framed and Lined Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
checkpoint-status |  |  | checkpoint | Check no screws in deflection head
label | 3d8caf4e-79a1-52fc-9fd9-de325444bf1a |  | note | No screws in deflection head
checkpoint-status |  |  | checkpoint | Service Check for pre installation of sheets
label | ff1a9a3d-6fde-52b8-81b9-beafe046a4fb |  | note | All service checklists are signed off by relevant trades
label | 2498850b-ea34-5d63-87ba-fad0c5a1886c |  | note | Photo of completed wall sign off sheet attached
checkpoint-status |  |  | checkpoint | Sheet all walls
label | 4278fb58-e8dc-5bb7-9a06-6dfd41b83d61 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Check wall types before installation (F/R, Acoustic, Wet Area, PBD etc).
label | ff0c386e-89cf-5aa6-95fb-3250adbe1c9a |  | note | Boral installation manual revision 2016 and, Ecowool insulation installation guide. Australian Standard: AS/NZS 2589.1:1997
checkpoint-status |  |  | checkpoint | Caulking
label | 7bfe8a31-2112-52c4-9059-a4ea9dd91eb7 |  | note | Boral installation manual revision 2016 Australian Standard: AS 1530.4-2014, AS4072.1-2005, AS1157-1972
checkpoint-status |  |  | checkpoint | Check insulation in walls
label | 84be7bf9-720c-59fe-8805-9e439cf1d376 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol. Ecowool Installation Guidelines Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 : 1999, AS/NZS1530 Part 1: 1994
checkpoint-status |  |  | checkpoint | Stopping to walls
label | ef0b5232-39f1-5021-94f1-90a35c4f8363 |  | note | Boral installation manual revision 2016 Australian Standard: AS/NZS 2589.1:1997
checkpoint-status |  |  | checkpoint | Sanding to walls
label | 2bb31e47-6c67-59ad-bc09-8c4c0335e238 |  | note | Boral installation manual revision 2016 Australian Standard: AS/NZS 2589.1:1997
checkpoint-status |  |  | checkpoint | Clean up
label | 7f6036cd-bc40-5ec8-a482-c1f9a79256af |  | note | Waste all cleaned. Tools and materials placed well.
checkpoint-status |  |  | checkpoint | Check walls for patching
label | 2a470d1e-a513-518d-8474-65f9f8690c24 |  | note | Wall Types Plan and Wall Type & Setout Plan approved by Kapitol.
checkpoint-status |  |  | checkpoint | Materials Receipt Inspection
label | 21e1976c-11b3-57a6-9bfb-0324bc554dac |  | note | Refer to ITP No: 5 Incoming Goods
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | ITP 01 - Rigid Board |  |  |  |  | Yes | ITP 01 - Rigid Board | dc4819ee-03e6-4471-9be0-85c62a44e37c
checkpoint-status |  |  | checkpoint | Set out Rigid Board
label | 39c00b11-1723-599c-888c-9eef81bd40a1 |  | note | Reflected Ceiling Plan and JV3 report provided by Wood&Grieve Engineers and Kapitol. Australia Standard AS/NZS 4859.1:2018
checkpoint-status |  |  | checkpoint | Install Rigid Board
label | ae221eac-84bf-5531-a88e-49d60de6641d |  | note | Reflected Ceiling Plan and JV3 report provided by Wood&Grieve Engineers and Kapitol. Australia Standard AS/NZS 4859.1:2018
checkpoint-status |  |  | checkpoint | Tape & Seal
label | 970c76da-b7cd-51cd-9f30-460036d85351 |  | note | Rigid Board installation guide and Australia Standard AS/NZS 4859.1:2018
checkpoint-status |  |  | checkpoint | Clean up
label | 7b18ab29-f401-5c3c-bbcc-102158da39d1 |  | note | Waste all cleaned. Tools and materials placed well.
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgment of Works
holdpoint |  |  | signoff | Request Signoff