## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | e6e869c5-ca49-44f1-9174-67fee29e70f5 |  | checklist | Pre Wire |  |  |  |  | Yes | Stage 8 - Pre Wire | 0cbe4226-22fb-4004-8e12-517326febfa6
checkpoint-status | ac51a48d-defe-471a-af24-da9c36fd45b6 |  | checkpoint | Area is left clean and tidy, and approval to start work is obtained
checkpoint-status | 357ec8e4-53b0-4273-a78f-9b0af8e5c1c7 |  | checkpoint | Internal cabling complete
checkpoint-status | 526bde8f-e605-47a6-9f3a-574dd6ffdc01 |  | checkpoint | Main cabling complete (Photos Attached)
checkpoint-status | 65b87b8c-1db3-43de-b8d4-af13ee687718 |  | checkpoint | Building entry point (Photos Attached)
checkpoint-status | 4a16f9db-ffc1-4885-9fd9-934023a566d3 |  | checkpoint | Fire boxes installed (Photos Attached)
checkpoint-status | 7df5b834-7f35-4947-aa49-608c790bad3c |  | checkpoint | Flush boxes installed
checkpoint-status | 34e18d3f-1494-495b-8689-4d919e5a9abf |  | checkpoint | Sub-reticulation installed (Attach Photos)
checklist-flat | cda0f8b0-dc95-40f7-862a-0ebdf5d609ac |  | checklist | PRE - S - First Fix - Nurse Call, Data & Communications & Security |  |  |  |  | Yes | PRE - S - First Fix - Nurse Call, Data & Communications & Security | 15a5ab91-4cdd-4032-bcba-8e31b593fdff
checkpoint-status | 18d36d12-aa8f-4428-9363-70b43308f2c4 |  | checkpoint | Framework available and acceptable
checkpoint-status | 1dab7c9d-303c-4cea-80af-514434dc5b7d |  | checkpoint | Cabling completed and acceptable
checkpoint-status | 6a08cf9a-9b8f-423e-8160-9e38b6af582d |  | checkpoint | Nogs installed and acceptable
checkpoint-status | 6588f3e3-5686-4230-8dcc-3beca34838e0 |  | checkpoint | Flush/Fire boxes installed and acceptable
checkpoint-status | 42e2c813-e1b6-4e4e-9c07-6f3fad61bd74 |  | checkpoint | Fire Baffles installed and acceptable
checkpoint-status | 832a0dca-b70c-4f1a-86d2-aa5e958b1cbe |  | checkpoint | Fire penetrations completed, sealed and acceptable
checkpoint-status | 57bcbe66-772f-469f-950b-bf1c544968ba |  | checkpoint | First Fix complete and acceptable and area clean and tidy for next trade
checkpoint-status | 3b93de10-72d9-47c1-8115-1fe2378fdbcd |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | d85628b8-8221-49e4-831e-25ae4bda615e |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | a45672a8-6f38-4e3e-b09a-8a0b51196000 |  | checklist | S - S - Electrical - Cable Trays |  |  |  |  | Yes | S - S - Electrical - Cable Trays | 2f85f703-1fd9-414c-bb23-9334a7b9ddbb
checkpoint-status | 06d56d8c-dc3a-4869-8735-07381c68331e |  | checkpoint | Tray ready to start
checkpoint-status | bc49b3f1-da09-443d-99c3-d4aafb18a6e6 |  | checkpoint | Building to correct Drawings (BIM model)
checkpoint-status | b435195c-6b39-4e16-bc06-7e85ffec5b43 |  | checkpoint | Correct Tray / Basket size used
checkpoint-status | 6e7c1103-9031-4efb-b0b4-4c08f450e19f |  | checkpoint | Tray height correct of RL
checkpoint-status | 65c1748e-050a-4814-9e78-8f95ec9c4c7a |  | checkpoint | Tray position as per BIM model measurements
checkpoint-status | 8e9de55d-a45c-4923-ae9f-90e09efef520 |  | checkpoint | Tray level
checkpoint-status | f3792a36-02e7-4831-8be1-8f35fd0ce231 |  | checkpoint | Tray locked down
checkpoint-status | 1031ed48-34ce-44d0-b1d8-0a4acc2add49 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 72f01f80-5cf3-4dae-b98e-f16d1e043cd6 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | aa3ff3bc-8cbc-4b69-af26-2d5ebf286a80 |  | checklist | Termination and Testing |  |  |  |  | Yes | Stage 8 - Termination and Testing | 322ea478-342b-4a9d-89df-11c935803a43
checkpoint-status | 7641099c-04ed-4fe2-9ac1-1ba063d41f28 |  | checkpoint | Area is left clean and tidy, and approval to start work is obtained
checkpoint-status | d131e72c-571b-47fd-bc84-b1b801cce47d |  | checkpoint | Install DB
checkpoint-status | b899c40f-07a9-4b28-aa5b-f7f2a82c4f40 |  | checkpoint | Fit off DB (Photos Attached)
checkpoint-status | ba1adc96-0d97-4e18-88f7-d7550028d121 |  | checkpoint | LAN test internals (Add signature)
checklist-flat | e3ca5228-bb56-494e-a67a-a42673eab56e |  | checklist | Plinth Commissioning |  |  |  |  | Yes | Stage 8 - Plinth Commissioning | 3fceb45a-c87b-4d17-a888-0e2abf9de365
checkpoint-status | 9e2fcea7-5ce6-4d5c-ae5c-0ca7e8e3682c |  | checkpoint | Nurse Call Terminated (Photos Attached)
checkpoint-status | f5a26c48-9248-4ea3-975b-20c3d9630be1 |  | checkpoint | MATV Terminated (Photos Attached)
checkpoint-status | 336f5f1a-47a4-4b74-94af-23708ca10804 |  | checkpoint | Fibre spliced (Photos Attached)
checkpoint-status | 99c0f4ef-f22c-4766-aacf-8b2663600edc |  | checkpoint | Power Supply installed (Photos Attached)
checkpoint-status | ab8a919a-020e-4fa4-bb6f-3f3de5ac0cfe |  | checkpoint | Krone module terminated (Photos Attached)
checklist-flat | b832124c-9219-4bbd-be25-922a397477a1 |  | checklist | F - S - Underground services |  |  |  |  | Yes | F - S - Underground services | 939e0d3d-f5c9-4a6b-8736-f11925345378
checkpoint-status | c8d20aad-321a-4fdb-8bb3-1eaf437fdbea |  | checkpoint | Electrical services/conduits installed at correct location
checkpoint-status | 3f642e94-8886-447c-94c1-01b69b2039e5 |  | checkpoint | Hydraulic services installed at correct location
checkpoint-status | de9eae5f-4884-48ef-8134-e3cb0898ad0c |  | checkpoint | Telecommunications installed at correct location
checkpoint-status | 1980da7b-6654-450d-ade6-2f6e3e963214 |  | checkpoint | Any other relevant services installed in correct location
checkpoint-status | ba1b5c6f-1d23-47e4-bc41-2f8bd9186be8 |  | checkpoint | All Subfloor services correctly installed to respective area
checkpoint-status | 6ec1ffd6-e721-43c1-b291-89ac65c34472 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 5ad0db36-c3e7-4faf-867d-492975f894ff |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 4a065910-e75f-4a23-a719-9d76d6320dcc |  | checklist | PRE - S - Fire Penetration |  |  |  |  | Yes | PRE - S - Fire Penetration | 97477967-0836-4b60-bf4b-903c35aa139d
checkpoint-status | b6993fef-1b66-4373-a4e2-8f04be643172 |  | checkpoint | Penetration Details
select | 7764fda4-fb4b-5ca5-af0a-f8c79cacebb0 |  | dropdown | Area of Installation | Wall, Floor, Ceiling
select | 1dd87087-0512-5a59-ad78-82715e31adc1 |  | dropdown | Fire Rating (Minutes) | FRR 30, FRR 60, FRR 120, FRR 180, Other
text | b2630018-afab-5285-8e2a-14d55e7f6748 |  | textbox | If other - specify here:
boolean | e37d46c7-7b6d-5abb-9058-237fe49da180 |  | tickbox | Penetration Type | Cables, Copper Pipe, PVC Pipe, PPR, DUX, Stainless Steel Pipe, Galvanized Steel Pipe, Metal Duct, PVC Duct, Pair Coil
text | 2f1bc4df-fc01-56aa-99bf-050c7124c1cc |  | textbox | If other - specify here:
boolean | e0d1aeb5-28de-5fc4-b232-d9dbbd1bbb1c |  | tickbox | Service Type | Sprinkler Services, Data & Security Systems, Hydraulics/ Plumbing, Electricals, Mechanical, Other
text | 6a315af6-7bf0-5242-8c76-024ae67d13a2 |  | textbox | If other - specify here:
select | 6fb47a15-ff83-5abe-a0ef-c98fd1b62884 |  | dropdown | Product Used | Collars, Pipe Wraps, Fire Plates, Cast-In Collars, Fire Bonds, Boss FyreBox 150 x 600, Boss FyreBox 150 x 300, Cable Transit, Cable Collar, Fire Mortar, Compressed Material Wool, Fire Rated Fabric, Flexicoat Sealant, Fire Dampers, Fire Pillow, Downlight Cover, Ablative Coating, Fire Shield, Protecta FR Putty Cord, Intumescent Sealant, Fire Mastic Sealant, Weather Resistant Fire Sealant, Fire Foam, Kaowool, Bulkhead Batt, Other
text | 60a37b2f-b8e4-5900-b6de-3486a1d43e4b |  | textbox | If other - specify here:
select | 0a41c111-cfa6-5437-a344-5696f82db7a6 |  | dropdown | Fire Sealant Used | Yes, No, N/A
holdpoint | 3445101d-92da-4d03-aaa1-0246f927a43b |  | signoff | Raise Remedial / Request Signoff
checkpoint-status | 3a5522af-cad1-4646-8dc3-ad0803c74ae5 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 72f5317c-6217-4aa7-84ec-73ad5a13cf30 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 847758eb-2158-41d7-9b71-35a4bbe680ac |  | checklist | POST - S - Second Fix - Nurse Call, Data & Communications & Security |  |  |  |  | Yes | POST - S - Second Fix - Nurse Call, Data & Communications & Security | 9ed29349-dc45-4e75-a589-3ee05b227355
checkpoint-status | ed0778b3-10fb-44c5-aeaf-960beaa6a768 |  | checkpoint | LAN test completed and acceptable
checkpoint-status | b01c7d22-af39-477c-b809-41cfb3577d82 |  | checkpoint | MATV terminated and acceptable
checkpoint-status | fbdebc79-92af-46d7-b9c4-0a2133312848 |  | checkpoint | Distribution Box terminated and acceptable
checkpoint-status | 8c2a1268-9399-48d9-95a5-8b908f7874ee |  | checkpoint | Nurse Call faceplates fitted off and acceptable
checkpoint-status | a12d1255-065c-4383-8a9d-6f01478b6d1d |  | checkpoint | MATV/Data faceplates fitted off and acceptable
checkpoint-status | c5416bca-5549-4621-bc11-3dc93f340309 |  | checkpoint | Camera faceplates fitted off and acceptable
checkpoint-status | 120c31ab-c382-49ee-8f92-2dd2d2393b57 |  | checkpoint | Intercom faceplates fitted off and acceptable
checkpoint-status | a96f298b-c29e-4d2e-8823-794e5f1602a5 |  | checkpoint | AC-Mags faceplates fitted off and acceptable
checkpoint-status | b9efa64e-040b-48e0-9d4e-9261188d8729 |  | checkpoint | AC-Plates fitted off and acceptable
checkpoint-status | 23f155c7-2c73-4007-9d12-ad29bfb9fa5f |  | checkpoint | Second Fix complete and acceptable and area clean and tidy for next trade
checkpoint-status | edb5df96-b794-47cc-8b0d-7092294cc136 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 97e3bef4-d4ac-40d3-b5c8-8afe8f2e75d7 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 442f51bb-86b4-4135-b89a-bac16f60a933 |  | checklist | F - R - Underground services |  |  |  |  | Yes | F - R - Underground services | a590bd7b-3047-4c38-b7d6-e9dec0ca3d56
checkpoint-status | 2deaa21d-2de1-4e92-b2fa-9c0864be80f5 |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status | 2306b685-d13b-4c2d-a3b9-a535b3519a17 |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint | ed556ec4-af32-485f-9ecc-0387236525e4 |  | signoff | Raise remedial / Request Signoff
checkpoint-status | 1eba99ed-6d44-4e68-9bba-60872293ce57 |  | checkpoint | All underground services installation completed as per the specifications
checklist-flat | 4c005c6b-89e0-4b70-bbcc-8dac976b2498 |  | checklist | Fit Off |  |  |  |  | Yes | Stage 8 - Fit Off | ba42d113-2541-405f-8e7e-bb9955e4a270
checkpoint-status | 5b8d6a76-d5e7-4f90-9939-15cfe3bd4061 |  | checkpoint | Area is left clean and tidy, and approval to start work is obtained
checkpoint-status | c6a82596-ad42-4541-8b2a-9023e32843b2 |  | checkpoint | TV/DATA Fit Off (Photos Attached)
checkpoint-status | 619a247c-1ef3-40ba-937d-70c01dbca867 |  | checkpoint | Nurse Call Fit Off (Photos Attached)
checkpoint-status | 6e40679c-62e8-40a6-bf76-4473b20322e1 |  | checkpoint | Smoke Alarms and CO detectors (Photos Attached)
checkpoint-status | c688c05d-5c4a-483a-91d6-77cd415b1f3d |  | checkpoint | 6 core Fibre spliced (Photos Attached)
checklist-flat | e479a420-7f7f-437a-8003-89dfb26a88dd |  | checklist | F - S - Underground services |  |  |  |  | Yes | F - S - Underground services | c6ce9a45-49f2-4fe1-b537-0e03f9285d05
checkpoint-status | aa3fb43a-9e84-4e3b-aed3-d33c57582705 |  | checkpoint | Electrical services/conduits installed at correct location
checkpoint-status | f374511c-0c56-4204-b5a6-43e1048c4174 |  | checkpoint | Hydraulic services installed at correct location
checkpoint-status | 9e0ebb6d-d9a6-4031-af67-b8df8f3aa505 |  | checkpoint | Telecommunications installed at correct location
checkpoint-status | 6a9135b2-e7e7-420a-a30d-3830476e8469 |  | checkpoint | Any other relevant services installed in correct location
checkpoint-status | 72aa5e35-4d46-4d9b-a606-480c1e781ac6 |  | checkpoint | All Subfloor services correctly installed to respective area
checkpoint-status | 4a3d8115-b35e-4b0f-8d16-f71ecc785786 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | bac4f218-c19b-45be-90fa-2ec7a1f3534a |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 86a9c00d-4df5-49d1-bbf7-129b5ab03c73 |  | checklist | F - S - Backfilling |  |  |  |  | Yes | F - S - Backfilling | f3fd974e-3ef2-466e-9070-20c7a4d8745e
checkpoint-status | 67dba346-e8f4-4a1a-ab8a-46602b9fb9e2 |  | checkpoint | Waterproofing membrane installed
checkpoint-status | a455a166-072c-484c-a7fd-e0026eb1db28 |  | checkpoint | Area clean of debris
checkpoint-status | f226b714-2765-4765-b58d-ad17556c2a7d |  | checkpoint | Backfill completed correctly and heights checked/ correct
checkpoint-status | b3063733-062e-4a74-bda8-f9f6b5ad5327 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 2335cf43-bd9b-45fa-bbbe-0cf613f9b339 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS