## Master List Templates
Id | Type | Name | Values | Prompting Name
d5edd73c-b54a-41c5-b43a-75fa11528a09 | checklist | 1. Prepour (Secondary and Primary cage inspections) |  | Cage:
da4f98a0-8614-4fd6-ac43-c17351e2a819 | section | Reinforcement Cage Inspection (Secondary Welding)
28f6aee5-36b0-4966-afe5-1908ae388d44 | checkpoint-no-value | Cage inspection details
a12aee59-fab4-58f1-bdb2-874f033d3898 | textbox | Cage Length (+/- 50mm)
7b0dfeec-da61-4e92-ac5e-5a6e8cae9fb8 | checkpoint-no-value | Pole Cap
6212ee1b-480b-5604-a0ae-056383a6be76 | textbox | Size
7f6f320c-f0cf-58cd-ac7f-61be61c5d2e0 | button | 4No. Welds | Y, N
84dc4651-c718-5e60-a6e6-2c6ba19c7b83 | textbox | Seated Square (+/- 2mm)
d5954709-d4f9-4551-89d0-9212a42a2cd6 | checkpoint-no-value | Fittings Drawing Number
6eba38d5-f80d-5ed9-8ee9-37feb02595fb | textbox | No.
de2cf11a-067d-4729-bbb1-0fb4215c4020 | checkpoint | Correct Type & Number of Studs
6bf02e81-5131-4d1d-960a-0b6df2e18bbb | checkpoint-no-value | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS (record amount visually inspected)
a87d756e-647f-547f-88d2-637ddfb53f2c | textbox | - Tubes & Hole Formers (±3 mm)
3c1424fe-8465-5756-9138-eaeb96de0e62 | textbox | - Earths (+/-10 mm)
d683c163-cc26-5504-a29e-8877fd5239b4 | textbox | - Steps (+/-10 mm)
5a57e313-8cf4-5f91-8c58-5230622f7de5 | textbox | - Others (+/-10 mm)
af8ed886-0c16-5302-b47c-e9b1648bd32e | textbox | - Splice Wires (+/- 0mm)
a6a6fda3-8a28-555c-a298-31f6255f6b04 | textbox | FWB (+/- 0mm)
70258266-c588-42b9-961c-4b42d47702fb | checkpoint | ANTI-ACCESS Wires
0e02dabe-41a6-4077-91f4-3ba1474ddab0 | signoff | Accepted? (Y / N) (Initial)
99119a72-7096-4fd2-86ed-39ee4cb1b2c8 | section | Reinforcement Primary Cage Inspection
2b4ac30a-2a87-41c0-99f9-68abce086380 | checkpoint | Cage Diameter Check (mm)
246e84c8-5882-5d42-9037-f5ab9cd8c341 | note | Distance from Tip (m)
56f69229-0ca4-5ead-b400-48bf7c36207a | textbox | Tip
bd15674c-050d-5870-a456-371361a81dab | textbox | 1
1a803f76-9c3f-5ff4-bba2-c558721c6994 | textbox | 2
b10e1562-25f6-537c-ba2f-c7d9408de1ec | textbox | 3
f3510cd1-caf0-5173-9bd2-f801e9c9d1c2 | textbox | 4
9fdc6569-5419-5d30-8e38-332ccfce09a8 | textbox | 5
7f6cb4b7-ffb4-5324-87f0-c5e84461164f | textbox | 6
af9dbf0d-592a-5496-a281-62451733764e | textbox | 7
0f28fe46-52f8-5cac-8e24-57ca60433de1 | textbox | 8
297160b4-985e-5acd-b3de-b0779316b452 | textbox | 9
3cedc558-7262-5c7a-ad55-b3bf7a0e7e11 | textbox | 10
abb9bb95-e4cd-5610-aa29-6024422be967 | textbox | 11
2da01ae3-35ad-5b1f-9b9e-9f20dfcb471e | textbox | 12
9c113825-8d2c-5312-8a64-23637ad7a2ff | textbox | 13
3d8aff04-3871-5a32-8516-f97f2c0cf30f | textbox | 14
74f160e8-0d0d-53c8-901b-09774790e4e8 | textbox | 15
a8bb4efc-839a-531b-a804-587e5e720c54 | textbox | 16
64853837-d54b-5d67-bbc9-e74b43f52388 | textbox | 17
9bd573c9-5850-5db7-a0bb-ffe688e143c6 | textbox | 18
07a26924-6b71-560c-b7c5-dccbfc76365b | textbox | 19
8d9d5255-c74e-5cbc-a87a-b7e9a7e19c4b | textbox | 20
37377c22-2ca6-5db3-9ec7-f7c5676e0661 | textbox | 21
8e37db82-1a65-55a2-ab0b-b7244ecdcfc2 | textbox | 22
8a507c0a-faa7-5e93-8b5c-117f9c48902e | textbox | 23
22db83f3-b6f4-5370-8c48-6783ffdb557b | textbox | 24
79567ae8-8540-4817-a3fd-36e5abc40f5b | checkpoint | Check Pitch Finish - Distance from Tip
50b25b8c-fcbd-5429-9219-654d0f2ee038 | textbox | 40 tip
2b355bc4-1f3b-5289-8c30-8f03aa1cccc4 | textbox | 80 tip
626cdb5e-0b4e-552c-82dd-47b1a051e020 | textbox | 160
a011abcd-46db-5669-b576-ac1ba0caf7e1 | textbox | 80 butt
94aa81e5-4468-5036-993e-34bc9289d42f | textbox | 40 butt
8e039770-6d8e-5d36-b2cf-797da9a1d1db | textbox | Other
957bee6e-c8f8-4a20-a985-93afe4502c8e | checkpoint | Check Longitudinal Start Distance from Cage Tip
d8114925-f7e4-58e9-9d8e-422d53b85316 | note | Number of longitudinals
3f1cac91-34df-5d6d-8e3c-d3f800382bad | textbox | 4
5f932ad2-b3c4-5120-a046-94ef5de088a0 | textbox | 8
50c832ed-6e75-5799-902b-e0e7da925401 | textbox | 12
06ac7afd-aa67-57f3-81d0-a9f69cf3cdee | textbox | 16
f1f955d0-75e6-5137-a1cb-c2492c71df1e | textbox | 20
691de0bc-83e7-5c2d-ae68-eadeb63cd9fb | textbox | 24
89218e4f-396a-5799-ac54-b6907608bc06 | textbox | 28
9f7cc304-08a7-57eb-978e-c0e66d138fd3 | textbox | 32
85f46b13-3daf-5140-ac64-cbafe6e46e0e | textbox | 36
7721c84a-6c2a-5957-a0c9-0c16a050772f | textbox | 40
aaa10200-b777-5322-af1d-1f8ec0cb9f47 | textbox | 44
8f9ede12-ae1a-57e7-9521-3cdda9fe6512 | textbox | 48
192aab2f-3fc4-4d0a-b930-88a878fc1e03 | signoff | Accepted? (Y / N) (Initial)
fd927f6c-a38c-48ed-bc37-60b54723bf78 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 3246 |  | 11/16 P/COR - Cage:
7a837aa2-c13c-4ddb-8dab-a824b39a7790 | section | Reinforcement Cage Inspection (Secondary Welding)
053acf10-b4e1-4feb-af01-725d657e76b1 | checkpoint-no-value | Cage inspection details
f77ea5fe-f44b-5ac3-a3bf-16699f8bf203 | note | Fittings Drawing Number: 3246
e3a078d6-6173-5775-a959-727a13d5490e | textbox | Cage Length (+/- 50mm)
1c0cdd38-4b92-4c90-938d-2cc7d2b052b3 | checkpoint | Correct Type & Number of Studs
b0767ab1-3ed0-4df0-863b-79931f297934 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
839220b0-d1b0-5317-a014-72a5a444e9d1 | note | 6
c4079d1b-38cb-458a-884f-8ccbc47001c2 | checkpoint | - Earths (+/-10 mm)
194de852-f62c-58ee-8858-0662b7074d27 | note | 3
1d4db3ac-4b38-4f62-9d47-d0201c7e9ed4 | checkpoint | - Others (+/-10 mm)
bc1a13b3-0e25-57f6-80b2-6355ca545aa5 | note | 1
bcd23654-171e-4dfa-9481-570eb6f08879 | checkpoint | - Splice Wires (+/- 0mm)
892b48d1-6dfb-557f-9550-fd4492c75a0d | note | 2
3e45d487-78fa-49fd-89cf-ee75053f4808 | checkpoint | ANTI-ACCESS Wires
8bc67854-501e-4554-95aa-2a49f083d59f | section | Cage Diameter Check
4608a904-a9af-4b53-9081-75c02782b3de | checkpoint | Cage Details
f71a9c05-9493-58b8-bbd2-681a41ed8941 | note | Primary Reingocement Drawign No.: 1765
3a3bfd27-bf9e-5432-aa2d-3a7a3b35b142 | note | Longotudinal Size: 9.88
511c6212-4c68-50f5-a01b-6b880d929152 | note | Circumferential Size: 5.55
7cd5f225-9753-522e-a887-e9333f5215c7 | note | Distance from Tip (m) Min - Max
c94b2ffc-088f-42bb-af5f-2de1a28ca988 | checkpoint | TIP 195 - 200
e2b155a6-f73a-469b-bbd2-3adda96a4f56 | checkpoint | 1m 210 - 215
b527df89-52fa-461c-9baa-e981573898da | checkpoint | 2m 225 - 230
31c49ebe-c8ff-4bf5-af2d-ea307e01a57f | checkpoint | 3m 240 - 245
f955df48-c2f5-4f8b-ba42-f77e89f7f4dd | checkpoint | 4m 255 - 260
ab26215e-a7dd-454a-8b0e-c33a3e4fb46a | checkpoint | 5m 270 - 275
a3a04f28-38de-4c2a-85d4-e89779a04035 | checkpoint | 6m 285 - 290
d53855d7-e97a-4424-9486-6bc1b9e19fd4 | checkpoint | 7m 300 - 305
c39d1b43-ff45-4a0f-bbe0-c18301ee799f | checkpoint | 8m 315 - 320
d72d211b-6e35-4cda-9775-92c8423d2bf9 | checkpoint | 9m 330 - 335
436898e8-7fa8-49ff-85fe-1aaf1c1885ef | checkpoint | 10m 345 - 350
f4e743d9-4b92-4a02-bbe0-7e761e1ea55e | checkpoint | 11m 360 - 365
b0691bd5-c229-4482-8ee7-4c06725dea69 | section | Check Pitch Finish - Distance from Tip
53680034-e9f9-498e-a230-9bdbec24a309 | checkpoint | Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
fa09eb79-10e4-42b9-b554-f991a9fb11ce | checkpoint | Circumferential Pitch - 160 pitch for 11m (1.5m>11m)
3e930b34-795c-4104-9828-f45bc0827dd2 | section | Longitudinals
430a8bd6-fbb7-463c-9a30-6b7fd6625ddf | checkpoint-no-value | Longitudinals Details
0bee6f51-ebd6-5a5f-a619-ba1317a6791a | note | Number of Longitudinal
bb1329f9-27e6-5be7-87c1-878c120c6ada | note | Longitudinal introduction Min
f29580c8-de76-5d0c-b2e8-49b344d8d072 | note | Longitudinal introduction Max
11e9f38e-5400-4915-82da-a71ee1fde362 | checkpoint | 12 (1.4 -1.6)
e67e494f-3591-4637-860f-1af611cafbfc | checkpoint | 16 (4.4 - 4.6)
4fdc290b-e6f3-4ea7-80e7-6f7f27c63f86 | checkpoint | 20 (6.9 - 7.1)
3975ae13-fc9d-4447-8226-ede21d0ec1c4 | checkpoint | 24 (9.9 - 10.1)
03615099-d038-4f6d-8cbc-459250fcffaf | checkpoint | 28 (13.9 - 14.1)
517361fb-7b23-42cb-b975-b6f691338a0e | checkpoint | Acceptance
e844d2fd-8332-427a-bae9-cea313a22ea4 | signoff | Accepted? (Y / N) (Initial)
138297f0-5dfe-4523-9d4f-f881585602c4 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 3248 |  | 12.5/16 P/COR - Cage:
a088705a-9487-4e9f-9475-435e7697cc4c | section | Reinforcement Cage Inspection (Secondary Welding)
e1a7128f-1f69-4178-846c-740bb4adf8ab | checkpoint-no-value | Cage inspection details
24e31726-fcb4-57ba-92c4-b91217809e6b | note | Fittings Drawing Number: 3248
64bf3951-4ce4-57e3-9d2e-48a3156fcf96 | textbox | Cage Length (+/- 50mm)
b86ec3e4-5366-417b-b4d6-a4adf22407ba | checkpoint | Pole Cap - M24
a2fd89d1-c529-4055-a7d0-6ee4dfd0af75 | checkpoint | Correct Type & Number of Studs
141c3e37-b01c-4c60-a6a9-d306f9acc1f1 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
e3ab6daf-dd41-580a-8202-eee901266c54 | note | 6
22714eaa-7082-49f6-be40-73dca55d7f6d | checkpoint | - Earths (+/-10 mm)
59b49db2-6b14-558a-a0bf-fec37382f4fe | note | 4
7ff025c8-febf-4f85-a1c1-7a5bb86a4c7a | checkpoint | - Others (+/-10 mm)
6feb116f-f872-531c-88c6-e887fc25af7a | note | 1
68b4ed1e-a61f-4b30-a00c-98dd705a9113 | checkpoint | - Splice Wires (+/- 0mm)
7372c2f5-b5b6-521b-8c9f-15908de774c8 | note | 6
4165988c-0375-48d3-8153-3eb5ba065137 | checkpoint | ANTI-ACCESS Wires
76f40190-da91-4173-9136-3ce06a6404cd | section | Cage Diameter Check
dee40e2f-2bf5-4edd-9498-f70fb6dffd9e | checkpoint | Cage Details
10eac8bd-9bf3-5b9e-99ef-6072f6bbf77c | note | Primary Reingocement Drawign No.: 1764
587059be-acb4-533b-9540-34622b785507 | note | Longotudinal Size: 9.88
b7f08c9a-5ef8-547c-b77c-efea5b281ee4 | note | Circumferential Size: 5.55
dbe44649-e854-5b85-96d5-8d81310802db | note | Distance from Tip (m) Min - Max
5f3a81ac-4606-4aa6-b040-7709e1c5c4a1 | checkpoint | TIP 195 - 200
dc565062-e87b-4810-a952-78679a1df3fb | checkpoint | 1m 210 - 215
24434473-a158-48e3-a2e8-c9ad99817a0c | checkpoint | 2m 225 - 230
4d56a6c3-4bab-4a3a-b323-8eb1222c93ef | checkpoint | 3m 240 - 245
bc50446c-1eba-4929-9c6b-4cd498db5861 | checkpoint | 4m 255 - 260
ccab1662-2343-4b37-a29a-eda146b2eb2a | checkpoint | 5m 270 - 275
53b36099-fdee-45c4-a3e3-e1395e58310e | checkpoint | 6m 285 - 290
53dd7435-dff9-4543-9c87-3f9ec17ccc0f | checkpoint | 7m 300 - 305
19dc07a7-16c0-4c65-9535-b2f67fa56c7b | checkpoint | 8m 315 - 320
81cda88a-e3a5-44a2-aa0d-71588372a17a | checkpoint | 9m 330 - 335
da260fca-6a33-4843-98b6-2dd3fafae504 | checkpoint | 10m 345 - 350
17f8ae39-6b4e-4c49-a92e-ef5e58c2150e | checkpoint | 11m 360 - 365
89d4285d-cd39-4dd3-872a-eff7ca2d538c | checkpoint | 12m 375 - 380
2da44623-f73e-40aa-ac9d-4d3abcb45252 | checkpoint | 13m 390 - 395
b3ed21f7-f0ae-4fc3-90dd-d4fdb0455bab | section | Check Pitch Finish - Distance from Tip
1e398136-6c14-4e7f-81c5-a66a2210cf52 | checkpoint | Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
763485db-35e6-4ecb-8c75-6417e57f3e4d | checkpoint | Circumferential Pitch - 160 pitch for 11m (1.5m>12.5m)
32185a4c-7db7-463c-82dd-2f177f2884a8 | section | Longitudinals
41a6da3a-dab1-460c-b3ed-aaf2a593bd10 | checkpoint-no-value | Longitudinals Details
5e52dbc5-9fc3-56a4-83d7-18deae539f1e | note | Number of Longitudinal
3fb431c9-694c-5954-9371-c1e1b93fd3f3 | note | Longitudinal introduction Min
5fd75918-263c-569d-81a2-0e13baf41176 | note | Longitudinal introduction Max
7717066d-31d5-4184-a8de-1bd945dc6e23 | checkpoint | 12 (1.4 -1.6)
726b599f-b209-43a3-871f-6c30eefd1a94 | checkpoint | 16 (4.4 - 4.6)
389d4e9c-294e-439c-a013-13e18025a199 | checkpoint | 20 (6.9 - 7.1)
b07f0fde-f29a-4bd3-98e9-0fd0030f8b58 | checkpoint | 24 (9.9 - 10.1)
dd8dcfdf-3d1c-42cc-a7c9-79f342ed65d4 | checkpoint | 28 (13.9 - 14.1)
777313bb-29f5-43ed-b22d-85a5a3379532 | checkpoint | Acceptance
1a3ff9e5-9e70-4e2f-be6e-708dc5a969b2 | signoff | Accepted? (Y / N) (Initial)
d2973624-523a-4fed-8cfe-d187a49bac85 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 3249 |  | 12.5/24 P/COR - Cage:
56cd6fe7-e17b-4b2f-8f50-19108b3e9dec | section | Reinforcement Cage Inspection (Secondary Welding)
af8e7a41-30a9-4a70-806e-38239d677707 | checkpoint-no-value | Cage inspection details
9b0fb319-d7aa-599b-b41b-e163f6e4f407 | note | Fittings Drawing Number: 3249
2837cbd5-4c17-51af-bd12-eb5e426ac114 | textbox | Cage Length (+/- 50mm)
1a331a1c-a72d-496e-9160-eecd31103c72 | checkpoint | Pole Cap - M24
ac40409e-5703-4f84-b99b-490d8085e905 | checkpoint | Correct Type & Number of Studs
712dcc76-bb8c-46f3-8a2a-1cff7215b160 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
de7b03b6-2f33-5af8-acd5-853bc065b94c | note | 6
af57ba30-0d0a-4b49-8978-2c2949a3b2fb | checkpoint | - Earths (+/-10 mm)
6997d620-e698-53aa-8ae6-7aa547479cb5 | note | 5
86b336f4-32ee-46e7-acab-dd8dfa41dc4d | checkpoint | - Others (+/-10 mm)
437eaf52-17e4-5eee-b96f-f2de4da0d242 | note | 1
fc4c84c9-6b0e-4dbd-ab08-5497c6fc8165 | checkpoint | - Splice Wires (+/- 0mm)
9f10eaa1-ed09-53f3-80d2-282b09299a27 | note | 6
bf2c230f-cde2-4ec2-8e4e-9b5e2276d58c | checkpoint | ANTI-ACCESS Wires
754da598-b2f8-4679-82ff-3716815bc9dc | section | Cage Diameter Check
5c39e25c-5693-474f-869a-7b14397a4689 | checkpoint | Cage Details
e27e8997-ad02-572d-8249-08cd74aeda2e | note | Primary Reingocement Drawign No.: 1766
7a6e558e-4cc5-5fff-8126-93fdf23ac970 | note | Longotudinal Size: 9.88
a8d01f3f-0285-57ce-b348-9414e44b0d85 | note | Circumferential Size: 5.55
d6847821-25d1-580c-8190-eb3106ac0d46 | note | Distance from Tip (m) Min - Max
cb792c45-a6fb-41db-8d1d-af3eb700ef18 | checkpoint | TIP 195 - 200
98a30e39-ccec-4a85-a9d8-600da5412e7c | checkpoint | 1m 210 - 215
7bb38bc4-f286-4913-bdcd-5000fee0f701 | checkpoint | 2m 225 - 230
99a508c1-1937-46d3-b9cb-550d591e7809 | checkpoint | 3m 240 - 245
b7c3a544-99d1-4299-8cb4-191035eeb281 | checkpoint | 4m 255 - 260
cb9fdd8f-7347-491b-9cd2-3f314ccbca9b | checkpoint | 5m 270 - 275
3c91be7f-0046-44c3-9ddd-f8dffc1b0b2d | checkpoint | 6m 285 - 290
d3eb8b99-d49b-4521-aacc-e7c43a2adf8d | checkpoint | 7m 300 - 305
facedf93-eb53-4c91-8f55-75e6ee13c132 | checkpoint | 8m 315 - 320
19e5d559-8298-41ce-9259-2cfab6c1ed9d | checkpoint | 9m 330 - 335
070b97d6-2087-4389-9684-f80e19ba62cc | checkpoint | 10m 345 - 350
de46653b-6be6-49b8-ba9a-b43d5bd66f6c | checkpoint | 11m 360 - 365
4f9b4851-aacb-4dc8-8770-ac69e0397c00 | checkpoint | 12m 375 - 380
a85638bd-5b0c-48a0-8ec8-20949787045e | checkpoint | 13m 390 - 395
de5abeb3-68da-430f-8c91-bb94cae39fae | section | Check Pitch Finish - Distance from Tip
069bc1fe-e4b5-479a-a4f8-1ccfd9890c52 | checkpoint | Circumferential Pitch - 80 pitch for 0.5m (Tip>0.5m)
39a54ecb-27b8-4de3-817b-8f84789e8652 | checkpoint | Circumferential Pitch - 160 pitch for 9.1m (1.5m>10.6m)
d9847f2a-1563-4326-966b-6676545089cc | checkpoint | Circumferential Pitch - 80 pitch for 1.9m (10.6m>12.5m)
f096bb37-f70b-4c93-85a5-3958a9161d60 | section | Longitudinals
4c28218a-9486-4f5d-9f2c-d36b28febd47 | checkpoint-no-value | Longitudinals Details
c9d63758-4882-53d5-9496-6f77d442a0d8 | note | Number of Longitudinal
9bc1b02d-03d7-554b-aad5-f76cd25b76ac | note | Longitudinal introduction Min
5a6ba63c-ac26-5c1b-8d8f-604d6c28fe70 | note | Longitudinal introduction Max
1f648762-8d1b-4ce1-b570-a030450aa474 | checkpoint | 16 (1.4 - 1.6)
86bd4edb-39e8-4a65-9e28-c440cfd96552 | checkpoint | 20 (2.4 - 2.6)
72ac5c43-ef6d-4a3c-9d89-70fc25e675a9 | checkpoint | 24 (4.4 - 4.6)
07e49ec5-4a67-4194-936f-a4fde0e7d212 | checkpoint | 28 (8.4 - 8.6)
ad56e298-2cdc-4093-b928-b4278008d93a | checkpoint | Acceptance
8991065c-cf4e-4b8d-aa4c-14ff8efe357d | signoff | Accepted? (Y / N) (Initial)
26756598-5be8-4a0f-9038-e7e32419dcc4 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5589 |  | 11/16 SPAN - Cage:
c73bdafb-b7d4-4d09-8093-f1112a3791cd | section | Reinforcement Cage Inspection (Secondary Welding)
e667259d-007b-4e2f-afa5-33712c87571c | checkpoint-no-value | Cage inspection details
0736ec19-ee30-536d-b6d9-d32259a99d81 | note | Fittings Drawing Number: 5589
a92bde2a-e9c1-51c5-8ccb-1b084e00731e | textbox | Cage Length (+/- 50mm)
a0adf7c0-6298-45bc-8e58-6f66a18bcdef | checkpoint | Correct Type & Number of Studs
1f1fa794-d0e2-46b5-b550-ea99275900e4 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
2705fc95-abad-5ad7-913b-9cbf55a426fb | note | 6
902e6167-42f0-41cd-8778-d71bd56bb9ab | checkpoint | - Earths (+/-10 mm)
cf8e75d4-db1a-5ae9-b646-838f82bacc6f | note | 2
7ddb9318-e6d6-4f4f-8aa0-f522e74b9f50 | checkpoint | - Splice Wires (+/- 0mm)
a9351838-f772-5389-8410-715bd7f696cb | note | 2
1ae766a8-e6ce-4050-aac8-18a2e6e2afa0 | checkpoint | ANTI-ACCESS Wires
d35c27b5-315a-41ae-9e19-c368ccf522c4 | section | Cage Diameter Check
4a5cd9b9-ef53-4dfa-837c-a4aacf7a61bf | checkpoint | Cage Details
add99e13-f631-55a2-8ea9-3c4cf10dd74d | note | Primary Reingocement Drawign No.: 1765
0737e1d7-e2de-5525-b0b1-5e56d1dbe5fe | note | Longotudinal Size: 9.88
a96a1e4f-837d-566b-8fa1-afdea66f2f0e | note | Circumferential Size: 5.55
bffdace4-68e9-5e40-ac3d-53c02ce70617 | note | Distance from Tip (m) Min - Max
9c84e708-8b5c-4f3c-b413-7cb9251642fd | checkpoint | TIP 195 - 200
2821902d-2c93-4959-9577-be005183ae32 | checkpoint | 1m 210 - 215
874cb1d0-c2e2-4c1c-a8f3-47d107a00b77 | checkpoint | 2m 225 - 230
699f870c-f03f-4ca4-8057-f91052567c35 | checkpoint | 3m 240 - 245
fb6fe380-ac18-4224-9665-3d62c06b7dc2 | checkpoint | 4m 255 - 260
06193018-06a6-41f9-903b-235d55a8b763 | checkpoint | 5m 270 - 275
eed5df72-c223-4b73-8844-49754f4402f1 | checkpoint | 6m 285 - 290
7f7b37b5-bc7d-4431-9c79-8d062ba4f1ed | checkpoint | 7m 300 - 305
78fc2b04-2d1a-4c8f-a47e-aa732140a992 | checkpoint | 8m 315 - 320
bc48975f-fa35-453e-9d2f-da5acee060fc | checkpoint | 9m 330 - 335
848c1a4c-23f1-4309-b148-9e9df0fd27bd | checkpoint | 10m 345 - 350
2d6bbb4f-2bf7-4147-b52e-ca8b3062d536 | checkpoint | 11m 360 - 365
26e4ac03-51ca-4cd6-b26f-760a07733f87 | section | Check Pitch Finish - Distance from Tip
d112fc3f-6072-4a18-9fc6-8196b250b9a0 | checkpoint | Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
c562b6cf-3532-4a14-9d88-db0ef999ae2e | checkpoint | Circumferential Pitch - 160 pitch for 11m (1.5m>11m)
9d5c4848-49e2-4217-9372-d187caf964c3 | section | Longitudinals
bc0e8581-f220-495c-b876-e6511d41a161 | checkpoint-no-value | Longitudinals Details
6d332a3a-b59b-5d65-ac68-c8c4519218d4 | note | Number of Longitudinal
ab77be31-c5fb-5877-a547-4cc5410139d4 | note | Longitudinal introduction Min
415c962c-5e0d-58ec-bca4-94fe387c027d | note | Longitudinal introduction Max
eb3dd763-b117-49d5-b0e3-b81f887a253b | checkpoint | 12 (1.4 -1.6)
1fe0024f-5ad8-4851-a36f-dcdd1564f4ef | checkpoint | 16 (4.4 - 4.6)
b92925fd-090d-409e-9cdd-f6218e711429 | checkpoint | 20 (6.9 - 7.1)
a97905f2-ed13-40fd-9dac-e18f5291c4f3 | checkpoint | 24 (9.9 - 10.1)
5dd1cf85-a976-46db-acb9-8f33a680c3d2 | checkpoint | 28 (13.9 - 14.1)
aa8793b9-f554-4c02-8192-834db141f1c1 | checkpoint | Acceptance
0d29615a-fd36-4330-b185-b7c269608c49 | signoff | Accepted? (Y / N) (Initial)
6fef6a68-0533-4108-999a-346725b445a8 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5593 |  | 12.5/24 SPAN W/S - Cage:
f6e5c00e-0df8-41ae-ba2c-c4e4307b33e1 | section | Reinforcement Cage Inspection (Secondary Welding)
473baf41-a997-495b-beb0-a3569f440bc0 | checkpoint-no-value | Cage inspection details
7e3fd408-4e86-5ac0-865a-942d43fffef6 | note | Fittings Drawing Number: 5593
64af15b4-50d5-59ab-82ba-5b89e35efabe | textbox | Cage Length (+/- 50mm)
fb91c63f-8889-4bc2-909a-5f06b01ab3aa | checkpoint | Pole Cap - M24
04396cf2-6475-41ae-bc50-2c23c706c252 | checkpoint | Correct Type & Number of Studs
5a15b685-79b4-493c-a2fe-d730af92baea | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
b8f7c6ff-82bb-5190-bc90-c67272eaf8dd | note | 6
ff262906-4fef-4d7f-893b-16a894346e25 | checkpoint | - Earths (+/-10 mm)
430b5dbb-9081-5956-870c-dbd6a9b1ebf0 | note | 4
188fdc77-cb73-417c-bebb-4e418f10c8b0 | checkpoint | - Steps (+/-10 mm)
11b01569-b0a8-5886-ac94-9bd0ea285b2d | note | 7
786d51ea-67bf-46f2-99c2-64009cea5451 | checkpoint | - Splice Wires (+/- 0mm)
f23877e7-8384-5f7f-92b2-23048e18295d | note | 6
51f95ff4-15fe-48cc-aa2e-fb2b6a83f6a4 | checkpoint | ANTI-ACCESS Wires
f3b71e3d-82ae-4c9e-bdf6-8e605f09925b | section | Cage Diameter Check
49b5d406-dd32-488e-8603-62bb0e0ecd27 | checkpoint | Cage Details
7619ffec-d23e-547d-9e95-f0b474368bc1 | note | Primary Reingocement Drawign No.: 1766
57842c89-65f9-50e1-8d48-a4ad52942cdf | note | Longotudinal Size: 9.88
386600b5-12c2-5025-a743-bc13e816fe0f | note | Circumferential Size: 5.55
cfa9a8b0-9b35-5b1f-a48f-b69debbf9961 | note | Distance from Tip (m) Min - Max
9d2f9f80-c5da-4f7e-8320-07cec418f041 | checkpoint | TIP 195 - 200
7fe6e1f8-86f1-4b78-aea8-ad4241f756b2 | checkpoint | 1m 210 - 215
37c7b200-3d23-4fc3-8dd0-7958120e329e | checkpoint | 2m 225 - 230
8039b8ca-d144-4d70-86d8-088583db8927 | checkpoint | 3m 240 - 245
50fcf54d-9c5c-4872-b35f-dce6d6e7fb80 | checkpoint | 4m 255 - 260
0cbe41bc-19ba-49b8-bd80-e69c08e120fc | checkpoint | 5m 270 - 275
76de285e-128b-4263-a855-2c95992feaa5 | checkpoint | 6m 285 - 290
c0dd5fc1-3895-489f-a3dc-946eb4f2d487 | checkpoint | 7m 300 - 305
e470f3eb-d433-4e04-a498-e55c0d0208a8 | checkpoint | 8m 315 - 320
b527a725-3adb-42e9-a956-12fe38def5c0 | checkpoint | 9m 330 - 335
da152e27-9ae7-48cb-a10b-2dff0c4b9a3b | checkpoint | 10m 345 - 350
ed0c4547-51f8-4357-b5a6-62073bb07516 | checkpoint | 11m 360 - 365
67373cc5-584e-481d-85ff-0f0fafcb3272 | checkpoint | 12m 375 - 380
ec05959f-e3e3-4854-b321-e19303fa2b25 | checkpoint | 13m 390 - 395
dac2dab2-82a5-47e5-85b2-9bbadfece30d | section | Check Pitch Finish - Distance from Tip
ec08196c-fe37-4134-b1fc-e1a5f2a82a63 | checkpoint | Circumferential Pitch - 80 pitch for 0.5m (Tip>0.5m)
479d886c-88e2-4252-8661-2eeb2b7ca121 | checkpoint | Circumferential Pitch - 160 pitch for 9.1m (1.5m>10.6m)
c151c6ef-211f-48e6-a77c-7227b62d1d8f | checkpoint | Circumferential Pitch - 80 pitch for 1.9m (10.6m>12.5m)
33b6ad9b-2737-4434-8794-a8ece11ed45e | section | Longitudinals
355411e9-fec6-4e59-a19b-1f915fb47944 | checkpoint-no-value | Longitudinals Details
36536db3-92d3-5d20-b913-0ca98f133704 | note | Number of Longitudinal
8d434f0d-b28e-5e1d-a305-91c54a6332ca | note | Longitudinal introduction Min
a3d060bc-8e94-5e8e-81fb-269dadb7c964 | note | Longitudinal introduction Max
43715909-72e6-4e4a-a8ab-cd6a276c275e | checkpoint | 16 (1.4 - 1.6)
c31a6fc8-e106-4041-9d3b-9a9ecf513393 | checkpoint | 20 (2.4 - 2.6)
2ad4962d-08ff-4d15-9f37-aa2938bc9faf | checkpoint | 24 (4.4 - 4.6)
fbed1f1e-1537-49d5-8118-7833160652aa | checkpoint | 28 (8.4 - 8.6)
ea35251d-1072-445e-a4df-ebd8a2c88020 | checkpoint | Acceptance
cacf9107-ba24-43c1-947b-62c9e62245c4 | signoff | Accepted? (Y / N) (Initial)
3828ab13-7bfd-4733-b2e5-df918d0d74fc | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5594 |  | 12.5/16 SPAN W/S - Cage:
f27c050b-d801-4714-aa38-9eb7252e707f | section | Reinforcement Cage Inspection (Secondary Welding)
93b0b319-f988-4ae7-987f-a9a2a69b131e | checkpoint-no-value | Cage inspection details
82fe3052-cbab-573f-8902-3cf1df87385a | note | Fittings Drawing Number: 5594
de3b377a-8ef4-5326-a155-3eb2d442c07b | textbox | Cage Length (+/- 50mm)
64c0d07f-e62c-4795-8469-f394208052bd | checkpoint | Pole Cap - M24
b293f3c7-3ebf-442d-8f21-ef30f82d7fe5 | checkpoint | Correct Type & Number of Studs
a7f7a90e-d2d8-46da-ac6c-831153cca327 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
f9426846-a7b1-556b-9cea-40f4b22c9173 | note | 6
93b84c79-49e7-4949-8554-1359bae45ead | checkpoint | - Earths (+/-10 mm)
f384b6c0-abaa-5ea7-a33b-bfef4c432e75 | note | 4
c6e7e469-a033-4341-99f9-e70a568f765d | checkpoint | - Steps (+/-10 mm)
2cb18d18-c74c-589e-bf8e-f0c67833cd22 | note | 7
ca05cb3c-10af-4725-8688-772cafb0e459 | checkpoint | - Splice Wires (+/- 0mm)
3423f176-3591-5354-a994-7ea372bf3bc6 | note | 6
485a3147-50e4-482d-8e18-fe95ab4e9163 | checkpoint | ANTI-ACCESS Wires
07f43247-01ee-4969-881e-8b006f82ac4d | section | Cage Diameter Check
ef9fd327-576a-4c15-a08d-b68367e206c0 | checkpoint | Cage Details
1f273cb3-abb1-5d2a-86bf-f6c0c39f9487 | note | Primary Reingocement Drawign No.: 1764
a6df44d1-f3ed-505c-a7fe-4ff272708895 | note | Longotudinal Size: 9.88
78595ebf-ecb9-56e2-baba-0e2e49c2eba4 | note | Circumferential Size: 5.55
27a120d0-c24f-5b82-a400-88e55e9ab8e0 | note | Distance from Tip (m) Min - Max
529a4571-a342-4db8-841c-45161c0a6012 | checkpoint | TIP 195 - 200
9144abad-c403-4061-8f89-fe2a97a04958 | checkpoint | 1m 210 - 215
e04f2de0-0706-4213-8b37-57a6efed5a5f | checkpoint | 2m 225 - 230
89a1aac1-e81f-4419-8928-871f826f083b | checkpoint | 3m 240 - 245
69601bdd-4791-46e7-8596-6e371b1322c7 | checkpoint | 4m 255 - 260
2ae1b60c-e7b1-4f37-bb47-d03becb3c19e | checkpoint | 5m 270 - 275
031554e8-02c6-4a90-8d47-452e866947c9 | checkpoint | 6m 285 - 290
361d5b0b-6a29-4bd9-bd8e-31c344616092 | checkpoint | 7m 300 - 305
04b4301e-ff5a-4ae3-9305-46bec40a3a3e | checkpoint | 8m 315 - 320
ffba53a4-733e-4193-8e9c-8701a31a7719 | checkpoint | 9m 330 - 335
ee382448-8118-4e10-8694-e3a26e1f0e85 | checkpoint | 10m 345 - 350
821edc55-bada-46ff-a0ca-1b1f3668804f | checkpoint | 11m 360 - 365
ba63d7c8-f3ec-4b14-be61-dc5bd6872895 | checkpoint | 12m 375 - 380
13f3ec45-8b3d-45de-b82e-7e137689e13d | checkpoint | 13m 390 - 395
159040f8-7a45-40cf-a3a4-41f4d65f783a | section | Check Pitch Finish - Distance from Tip
a7e49f18-a1ee-4840-84d5-583ce21aa245 | checkpoint | Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
fea45de1-aabf-4a19-af19-f2dc68fb637f | checkpoint | Circumferential Pitch - 160 pitch for 11m (1.5m>12.5m)
438146ba-a2a3-4bcb-a79f-35e11531bbc4 | section | Longitudinals
c6844705-1892-4494-80d2-530df6a57f8e | checkpoint-no-value | Longitudinals Details
897d632b-de8a-58f7-afeb-6cb75967e86c | note | Number of Longitudinal
93568b1e-75ae-5c33-8087-2304db809802 | note | Longitudinal introduction Min
e4ab5efb-a53e-5289-bd01-bb6ec40e5730 | note | Longitudinal introduction Max
b71ad0df-5ab9-42e7-8ab4-3733622496b8 | checkpoint | 12 (1.4 -1.6)
0fa21303-81ec-4800-bf17-9006e85c98b1 | checkpoint | 16 (4.4 - 4.6)
07d89d18-f5fb-4ed1-b7d4-39e6a0fbedf5 | checkpoint | 20 (6.9 - 7.1)
bfa3ea27-d8e0-4b34-97b5-1f4cfd93703f | checkpoint | 24 (9.9 - 10.1)
705b1420-66bf-4239-ad6f-d8cbaadbcf00 | checkpoint | 28 (13.9 - 14.1)
ece5c504-995f-4392-9257-0f8a21401d75 | checkpoint | Acceptance
6780aac2-d3cf-4c8f-915e-0bf2d544a45a | signoff | Accepted? (Y / N) (Initial)
b9751522-4e1a-4492-bcd9-a58a054eb4dc | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5595 |  | 12.5/16 SPAN N/S - Cage:
db9cb702-e411-4189-ba04-ee6bdd5be38f | section | Reinforcement Cage Inspection (Secondary Welding)
2882432a-1787-43df-9949-fff00850bd50 | checkpoint-no-value | Cage inspection details
148cc336-3e14-528f-bdc8-3247d60083e0 | note | Fittings Drawing Number: 5595
63c9460c-cb46-5a5f-9671-1b39bb49724c | textbox | Cage Length (+/- 50mm)
42ef8c96-dd04-423a-9233-2351a673522e | checkpoint | Pole Cap - M24
011545f4-c4d0-4ae9-99b5-7ed1be4d2f1a | checkpoint | Correct Type & Number of Studs
c4978b4e-8c5c-4e66-961c-e714a60f7c65 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
1e0c14c9-be0e-5e9d-9727-fa43eaebae64 | note | 6
e7c74590-5f01-467d-be37-ef105c830cd2 | checkpoint | - Earths (+/-10 mm)
c4754220-b7a5-501b-8240-291dd9e797af | note | 4
0329b24f-8489-4d1e-869d-fdd658b3dc20 | checkpoint | - Splice Wires (+/- 0mm)
20884513-df4e-5e0a-853e-472364ee65fa | note | 6
603a23b6-988d-4737-acef-c98d0cb8549b | checkpoint | ANTI-ACCESS Wires
b35a9d04-41a4-4efc-af30-33e5795bbf91 | section | Cage Diameter Check
ce0f7c09-5143-4325-b718-302807762da9 | checkpoint | Cage Details
6238ae9d-2024-5f93-824a-c31a7eeaceca | note | Primary Reingocement Drawign No.: 1764
c8e7149b-16df-5c0b-b2c3-097f59931de0 | note | Longotudinal Size: 9.88
2c77af15-819a-5dc3-b370-9ee61b6553a0 | note | Circumferential Size: 5.55
928ba04f-070e-5a74-aa39-41d7b1ff10af | note | Distance from Tip (m) Min - Max
2efe8d69-6d77-4af7-926e-5115c288b01f | checkpoint | TIP 195 - 200
91cc0500-30df-43b5-9a50-e69e280a057c | checkpoint | 1m 210 - 215
60dba6c0-a6e7-433a-90b7-9072a1f8a399 | checkpoint | 2m 225 - 230
1b385a74-71e6-4c5b-b93b-8edfefddf05c | checkpoint | 3m 240 - 245
c7f503e0-b37b-4207-b6cb-333fe43e9e75 | checkpoint | 4m 255 - 260
48f65ac1-a62e-48fa-a737-4a723ff634b3 | checkpoint | 5m 270 - 275
0d7e0798-7de1-4f63-92b6-b0d488a64a3b | checkpoint | 6m 285 - 290
b8565312-88c8-49bd-8f76-ac0732637c21 | checkpoint | 7m 300 - 305
6bcbff47-4a27-4358-ac7e-278263477526 | checkpoint | 8m 315 - 320
127373fb-a390-49a9-bfdf-c4bd4c242c0d | checkpoint | 9m 330 - 335
014a055c-e589-429c-8966-ac05d36013aa | checkpoint | 10m 345 - 350
d303fca0-bf8d-4bc8-8d24-df9bef8eef7c | checkpoint | 11m 360 - 365
a966158c-66dd-4fac-986d-62cca768e08d | checkpoint | 12m 375 - 380
7f65e54b-c83e-49bd-9935-4b0fe857901a | checkpoint | 13m 390 - 395
a263e59c-83b0-4353-856a-123ef3c75e34 | section | Check Pitch Finish - Distance from Tip
a8827e6d-2eb0-41b0-a3f1-9d1905f810ef | checkpoint | Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
0871f9b3-f385-4dd3-9dfd-0e62fb8dce6d | checkpoint | Circumferential Pitch - 160 pitch for 11m (1.5m>12.5m)
ae881694-b8d5-4821-9207-4d39a3af0e57 | section | Longitudinals
cd8974b2-0e0d-4a41-8507-ef701b7a49d2 | checkpoint-no-value | Longitudinals Details
331109f1-e8d3-5d09-884c-2b2a5bf057c7 | note | Number of Longitudinal
26fd10ca-e0a8-5322-a945-5433f3432062 | note | Longitudinal introduction Min
efcaa250-af69-555b-8aef-4b4b5965fae5 | note | Longitudinal introduction Max
c355aec6-f15b-49e1-8a3e-1ce21be9ae77 | checkpoint | 12 (1.4 -1.6)
3258cd4a-4872-44c2-909f-afc1000a3baa | checkpoint | 16 (4.4 - 4.6)
691fb529-0e78-4f31-a806-fe5a87d817ed | checkpoint | 20 (6.9 - 7.1)
77bdac51-7691-47b2-b435-a4992f474c37 | checkpoint | 24 (9.9 - 10.1)
47c9df14-425d-4c8c-a2c1-6c1542e4e3a5 | checkpoint | 28 (13.9 - 14.1)
87a1af3a-135f-479f-a68d-3d18ee0ff339 | checkpoint | Acceptance
32bef75f-d20d-4287-8e22-8e4e6e919968 | signoff | Accepted? (Y / N) (Initial)
70ac589e-ab75-4655-8661-2e059dcefbba | checklist | 2. Postpour (Visual Quality and Finished product inspections) |  | Product Number:
c2856e22-fed6-4e75-b6dc-d0bd31137c44 | section | Finished Product inspection
c685d966-84a2-48eb-80ac-bafea08dac5f | checkpoint-no-value | Details
d22bcb4e-39c1-5a60-8820-07214df4aa6c | textbox | Product Size and Type
e2201ce3-821e-5bf7-ab85-a8920ef55a02 | number | Mould Number
31a70758-5787-5481-921f-d66a7696b350 | textbox | Drawing Number
d3355cf4-e096-4528-aa89-6175f6f65fbb | checkpoint-no-value | Inspection
d665f2eb-576c-55e3-9fea-41cd86723148 | textbox | PRODUCT LENGTH (±50 mm)
c094f088-9c11-5210-a46c-5e5d14580f94 | button | CAPS TAPPED & PLUGGED? (Y / N) | Y,N
1aa3f5ef-b462-52c0-95d4-6b8f426a9a91 | button | FITTINGS TAPPED & PLUGGED? (Y / N) | Y,N
6d106673-da28-5ae0-a260-1236e1b4ecda | button | Joint configuration & PCD check - Result passed check (Y / N) | Y,N
0f35aff7-f203-5cf7-8e62-201e9fba647a | textbox | WALL THICKNESS - TIP
f77e18e8-80d1-547a-8472-df9379cba854 | textbox | WALL THICKNESS - BUTT
0f35ad16-e216-46cd-81f3-a20f5418af05 | checkpoint-no-value | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS (record amount visually inspected)
af75e346-45ce-5b21-a049-6011a721a5d8 | textbox | - Tubes & Hole Formers (±3 mm)
b1352b62-e84e-5611-ad51-25de53716efe | textbox | - Earths (±10 mm)
4f2fd9ba-1f31-5614-8371-f3e1dd902e52 | textbox | - Steps (±10 mm)
650396a6-e10e-5acb-a9b1-475a5879cd14 | textbox | - Others (±10 mm)
e5aa6f2c-6ee7-4c1d-ae2d-65e12d7eb87e | checkpoint | ANTI-ACCESS WIRES (Y / N / NR)
c8c86378-982a-4751-986a-9f39ec606849 | checkpoint | INTERNAL CLEAN - DEBRIS CLEANED FROM COMMS POLES (Y / N)
b09fef6d-74b7-53e6-8cb5-4d9e5cd18875 | textbox | Quality Code (red)
5ae10731-3cd0-4b76-b2e0-4a5b0867db18 | signoff | ACCEPTED? (Y / N) (Initial)
a9c7f156-1c01-43bf-ae69-7306ea239a03 | section | Visual Quality
49a54f8c-fd67-4e13-b0cd-d778f4d4a384 | checkpoint | Visual inspection
dd43bcab-04e8-5327-8116-7a7d171bc7f9 | note | RAISE ISSUE FOR EACH OCCURRENCE
64388d55-91db-5c2b-a5be-10caafdbfc68 | note | 1. Exposed reinforcement
2c981b1f-667d-51ae-80e7-451947b7d672 | note | 2. Squareness of ends
daeaa09a-3bdb-589c-acb1-5fdf8a4bab27 | note | 3. External finish
4439f630-2ad2-5d75-8030-46c7ff2003c5 | note | 4. Bulges or dents
3a06e9d1-d47f-5da3-9b82-684d550e04e1 | note | 5. Chips / Hammer marks
7b8076e5-f8fb-5c42-9292-7f6ea0c18c15 | note | 6. Flexural / Longitudinal Cracks
7f3783b6-5e00-5694-9c31-5e553087aaf8 | note | 7. Stud / Lug / Tip Ferrules incorrect
49678347-7666-5f2f-81fe-62a39bcd26a2 | note | 8. Deep fittings
d82be945-f8d5-5b4b-97fd-aa617f9000f9 | note | 9. Plastic Plugs missing
3a2aa2b3-1e71-56bd-a03a-38f4fd28f228 | note | 10. Slumps / Fall-ins
d49921dd-b4fd-50a0-afd3-65bed932addd | note | 11. Seams not washed-in
768b0aa0-811c-52c6-ba60-68a6be43f11a | note | 12. Mould Stick
e53ac214-fb3c-53cf-8472-9392de8d26f5 | note | 13. Product Identification incorrect
915de46a-ef74-5ebf-a093-a21d4cec517b | note | 14. Internal Finish
1424209a-ff67-5a65-b332-6ce5d1bd3ef4 | note | 15. Branding Incorrect
cefe7a66-dd35-5882-99ef-8d7c3d39300d | note | 16. Depth Marker incorrect location
bbce09f3-51da-578d-a12f-9de137268c79 | note | 17. Seam Bleeds
cc2c231d-0d9f-5ce7-bd77-a72371842005 | note | 18. Tip / Butt Bleed
6dab859c-255f-56c9-96ce-612a3f1a9612 | note | 19. Fitting Datum incorrect
7e9c553a-0a8a-5af2-8335-1e4991875b5c | note | 20. Class (Strength) incorrect
2f298ec4-c853-540f-b447-010115c0cb9d | note | Total Faults
994155f5-7588-5776-b68d-6905fafca203 | note | Action taken to rectify
fb88e286-73f5-438e-bedb-82121222ef1e | signoff | Inspected by
9f43d29d-87d8-4c69-95c3-7247912f6fcf | checklist | Elements |  | Cage Size/Type
ba351753-6855-479c-8301-044d31e034ae | section | Reinforcement Cage Inspection (Secondary Welding)
2d90e12e-1485-4891-991b-2b88c4fd665d | checkpoint-no-value | Cage inspection details
243b7423-7691-5653-83d2-37ab1d5b334a | textbox | Cage Length (+/- 50mm)
ca29dcd1-3a75-476b-bf05-433b8db9ed17 | checkpoint-no-value | Pole Cap
752a5ed2-1aaf-5e74-9596-5b9fe5efad50 | textbox | Size
eed3c2ab-d6e9-51a6-9d00-3d2309c0c68d | button | 4No. Welds | Y, N
66fc150f-525c-5ca7-aa8f-5a7275d86672 | textbox | Seated Square (+/- 2mm)
537b4e5e-7071-4455-af1c-2b5e46656cd9 | checkpoint | Correct Type & Number of Studs
0396f288-620a-4bf8-aae5-dedcb21e9775 | checkpoint-no-value | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS (record amount visually inspected)
22726210-52b4-54ce-8bb3-8d6e1a5a666e | textbox | - Tubes & Hole Formers (±3 mm)
3ae43d19-2cd3-5628-aa0b-53bfdea62032 | textbox | - Earths (+/-10 mm)
796f706b-af6f-5af3-8820-cb9c7f11a5cf | textbox | - Steps (+/-10 mm)
5575f6cd-8520-5809-bebf-6ef40fafb979 | textbox | - Others (+/-10 mm)
6bfe45c6-de6f-5bea-af10-5f43149429da | textbox | - Splice Wires (+/- 0mm)
ae866389-02d1-5eb9-8bce-8c662dd1098b | textbox | FWB (+/- 0mm)
38a0d4ea-d4a5-4e41-aa0c-b58d4d5502a3 | checkpoint | ANTI-ACCESS Wires
f6391b4e-efa3-4826-a30a-76a2e2313f5f | signoff | Accepted? (Y / N) (Initial)
2c1a3bd0-8ca3-4c6d-b8bc-217a30aa44d1 | section | Reinforcement Primary Cage Inspection
650593f1-4368-458a-8a1b-002e2172fc9e | checkpoint | Cage Diameter Check (mm)
53e7c94c-12b6-598e-aa84-9cc929db8cf3 | note | Distance from Tip (m)
4c24b1c4-768e-5f03-b492-17f299b430d2 | textbox | Tip
348edc82-2759-52cc-8e30-de459732a213 | textbox | 1
f84c7c56-26b9-562b-a698-fa306b728171 | textbox | 2
7357fa5a-249d-5c0a-bfad-30706d40aa3d | textbox | 3
209f5731-9679-5d6b-88a1-9b2f702155f3 | textbox | 4
26445418-740d-5f74-ae06-7b40d966c93a | textbox | 5
159a934e-37d9-5d1c-8ac7-d2f183971aa6 | textbox | 6
633ad04d-06b0-5a9b-a85c-ae03ae4bdc5c | textbox | 7
ce1be6d1-511e-530c-832b-86d63f8672a8 | textbox | 8
663f2722-76b5-52dc-8be8-2d799b3c4e3d | textbox | 9
c963ed56-54bf-5112-8349-202dd97b1eeb | textbox | 10
747c336e-fa45-5e0f-bc68-b3443d2d3c38 | textbox | 11
2581279a-f138-5f5a-be76-ccff4ac09b74 | textbox | 12
58bd9ec6-0543-581d-8305-2ff3fe6fcc95 | textbox | 13
96cf7b10-6c83-5a93-b7d8-19d7bda0fac8 | textbox | 14
a2f50a7a-2fbb-5fea-b7e3-c5a129528003 | textbox | 15
506e1ea9-448d-583f-820b-ed0f28d1ed5d | textbox | 16
18a3d994-dc79-5494-8d3b-3ccbfc9a01c4 | textbox | 17
3b1c6bc3-007e-5522-8299-0596dea3238a | textbox | 18
2dc35959-41d1-58c3-992d-b58568558da3 | textbox | 19
455e666e-fbc4-5b70-b606-44073dff0db5 | textbox | 20
ed222dc4-1105-558c-ba96-f7c32a4f259e | textbox | 21
284b7d56-596a-5384-b0ca-ed5dc69dcf16 | textbox | 22
72b7f8e8-e2f7-5317-adf7-944b92443933 | textbox | 23
171d10cd-5e4c-5986-8855-e689b30d7683 | textbox | 24
7819de97-1d90-4fce-b798-cef3f862d46f | checkpoint | Check Pitch Finish - Distance from Tip
ab4f35a3-46b7-56be-a059-90e15b4f3d50 | textbox | 40 tip
5aeb2e9f-2db1-5367-82d3-b86ae071ce1c | textbox | 80 tip
06cd8731-e9b5-51a0-af5c-d33b2de7a242 | textbox | 160
df3c3707-dbc4-521c-a19c-81a108019fa5 | textbox | 80 butt
a15f0d19-4078-565f-a112-26f225659052 | textbox | 40 butt
820e58b8-67ce-5696-9ebe-d70a8479f053 | textbox | Other
70fa2381-02d1-40f9-8333-c7c01b85477c | checkpoint | Check Longitudinal Start Distance from Cage Tip
3efab5be-f167-5e7d-a34e-7983408dac6a | note | Number of longitudinals
5f9bbc94-b5d2-54ce-adfc-b36ea9055ea3 | textbox | 4
4aa38a3d-db55-5736-bb2c-569deffa7b7e | textbox | 8
5486e1a3-9bff-54b8-b03f-139d17c4dd7f | textbox | 12
543da35d-22e3-5b5d-8d78-60ef1c1742ce | textbox | 16
141ab7c6-2b17-5388-a279-c15ebfe50873 | textbox | 20
6475faaa-ecb6-5e4e-a009-957453c6b21a | textbox | 24
85b321c8-eba9-50a3-b644-0b2f6907f925 | textbox | 28
e600fd7c-76f1-5483-8614-e849aec02759 | textbox | 32
ea0c5813-b3bd-59da-81bb-73861463e410 | textbox | 36
2244efe1-d24f-5ede-a24d-3e18ad1012b3 | textbox | 40
5dce0b0a-4242-56e3-87e3-e373079f4d4a | textbox | 44
9510fb14-5ec6-567d-9e70-e1323d4f5a04 | textbox | 48
c877c51a-4a0b-4aea-81af-08270f6bf871 | signoff | Accepted? (Y / N) (Initial)
2a82037e-ad49-43c1-a22d-4af19dec7d4d | section | Finished Product inspection
dc26e183-096c-41d8-a3c3-211fc189e060 | checkpoint-no-value | Details
0591d46c-8312-5a59-8efc-af22d149c5ef | note | Enter PRODUCT NUMBER in the Cage Conformance Section
aeee76f5-a55c-5e59-abc3-83daac1a7a49 | note | Enter MOULD NUMBER in the Cage Conformance Section
e3be5cfa-0eb6-46cf-8687-a4c495ebd60a | checkpoint-no-value | Inspection
8888b2a8-9313-56e6-9ef9-86518fdb211d | textbox | PRODUCT LENGTH (±50 mm)
81b9dfec-0818-5f8d-a9f0-cb302be28165 | button | CAPS TAPPED & PLUGGED? (Y / N) | Y,N
a0bf08e8-1f6d-5600-a3cd-a410c52f7fc7 | button | FITTINGS TAPPED & PLUGGED? (Y / N) | Y,N
56fcc856-8a4f-5a71-9191-e21366450677 | button | Joint configuration & PCD check - Result passed check (Y / N) | Y,N
75c1538c-edaa-5e22-82b0-2d48f52fac16 | textbox | WALL THICKNESS - TIP
641a21de-71db-5996-9e58-a8fd06cf09a2 | textbox | WALL THICKNESS - BUTT
0c29c5cf-8cce-48d6-a8e1-a922515dfa20 | checkpoint-no-value | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS (record amount visually inspected)
d1799893-3f2b-5862-9907-04a548c7fa06 | textbox | - Tubes & Hole Formers (±3 mm)
946e0877-f7d1-5275-8b1e-2f21d3a6311a | textbox | - Earths (±10 mm)
c57c191d-312b-5413-b6a0-b4bfb117373d | textbox | - Steps (±10 mm)
c0044b96-ecc8-5fd7-9cd6-ce1b0b3b1bf1 | textbox | - Others (±10 mm)
3526f2f4-69db-4864-b054-9a0cabf6d31a | checkpoint | ANTI-ACCESS WIRES (Y / N / NR)
e2454f53-322e-44f2-8024-6f75b2507900 | checkpoint | INTERNAL CLEAN - DEBRIS CLEANED FROM COMMS POLES (Y / N)
59b74302-63fe-566c-b1f2-5401d4a3ac2f | textbox | Quality Code (red)
eef533cc-f7d7-4ede-aecb-3ea3a57236c0 | signoff | ACCEPTED? (Y / N) (Initial)
041c16ff-f724-4d35-a376-32b40e815843 | checklist | Visual Quality Inspection |  | Type/Size/Number -
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
97eedbfd-2dfc-4d5e-9029-3476d2e38cdb | checkpoint | Record the results
b284b871-74c6-5de3-974b-693dd335526f | date | Date
a7007cdf-a203-5422-b844-8f08d927402e | textbox | Product Type
7b0e11f4-6d2f-56ec-a9db-5008febd4feb | textbox | Product Size
930e9021-323e-5417-aa0f-62928debd78d | textbox | Product No.
22000747-4278-563d-8bc1-9aa074338838 | textbox | Shift
fb3066a1-6937-468c-88cb-383592c1ebbd | checkpoint-no-value | RECORD THE NUMBER OF OCCURRENCES
8300ec68-4cb2-52ea-8794-6acc6a3c85b9 | textbox | 1. Exposed reinforcement
04013850-deab-5bc5-be16-95aeef46e22d | textbox | 2. Squareness of ends
36cdbef3-8e2b-5227-b10d-36b5eb7d29c2 | textbox | 3. External finish
26796a10-55b7-538d-84fa-d603808beea2 | textbox | 4. Bulges or dents
c5c2bf92-a83c-5070-ae54-a90c9d738796 | textbox | 5. Chips / Hammer marks
eba02e5b-38d1-5670-8398-0bd226e847a0 | textbox | 6. Flexural / Longitudinal Cracks
c4cf2083-176e-5c01-a133-ff6fc24b7812 | textbox | 7. Stud / Lug / Tip Ferrules incorrect
12e02a0f-230c-54e3-94ae-c32880cbc981 | textbox | 8. Deep fittings
e80cedec-dbf7-5208-8a66-2d4ef5b75600 | textbox | 9. Plastic Plugs missing
fd0fc9af-3267-5031-ae1d-ffea4489bcf2 | textbox | 10. Slumps / Fall-ins
224b2d4a-3f15-54c3-ac01-ac931c345bc7 | textbox | 11. Seams not washed-in
355faa10-82fa-5a34-9349-466bda65af4a | textbox | 12. Mould Stick
4b882fcf-918f-53c7-8bbd-dbb6903bc73a | textbox | 13. Product Identification incorrect
2b39016b-b1cb-5584-9be7-bba02384e25d | textbox | 14. Internal Finish
5717c67a-45b2-5c0a-8103-e9ce686c64d6 | textbox | 15. Branding Incorrect
a96e51cc-5391-5cd4-803e-8229dd4945a0 | textbox | 16. Depth Marker incorrect location
0d959023-92b3-5b28-8768-836a4529e699 | textbox | 17. Seam Bleeds
09cc3599-f6d8-5715-964d-fbd33d396ac2 | textbox | 18. Tip / Butt Bleed
866e771d-ee7b-5ed8-976f-289e8c0989ce | textbox | 19. Fitting Datum incorrect
4de85248-c6f5-5857-a7f8-918a84bbf28a | textbox | 20. Class (Strength) incorrect
fb6edde4-76fe-5146-9e99-1f4802aca42c | textbox | Total Faults
6dfcddee-3695-5e65-af51-381fe9cd649e | textbox | Action taken to rectify
88126b26-b724-439b-a929-8690441f41e7 | signoff | Inspected by