## CHK-CIV-RSS Fill Installation
ConQA Team Notes:
Document Title: |  | CHK-009-CIV-FRMS-RSS Walls-Fill Placement
Check list Description: |  | RSS Walls-Fill Placement
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 03/06/2024
ITP created by: |  | Kamel ALHOBAKI
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | To be Available for Ferris Rd Only
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Soil reinforcement-Straps | VR682.08 VR682.17 IFC Drawings | Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels. Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing. | Visual | Each strap | IP | SE/PE | This Checklist
2 | Soil reinforcement-Straps | Installation manual | Correct number of reinforcing element shall be attached to each panel/wire facing units | Visual | Each panel/wire facing unit | IP | SE/PE | This Checklist
3 | Pre-cast Panel Soil reinforcements-Bolts Connections | IFC Drawings Schedule of lenghts: MRP-103-C-RFL-DRG-35-RBK-CSW-1303 to 1604 Connections arrangement: MRP-103-C-RFL-DRG-35-RBK-CSW-2002 to 2003 | Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel Finger tight nut or use a wrench so thread emerges from top of nut | Visual | Each Fill Layer | IP | SE/PE | This Checklist
4 | Wire Wall Soil reinforcements-Connections | IFC Drawings Schedule of lengths & Connections arrangement: MRP-103-C-RFL-DRG-35-RBK-CSW-1901 to 1903 | Grid Strips are to be installed to the wire facing units in correct length and to the correct locations based on the number of grid-strips. - The first layer of grid-strips are to be ziptied or connected via hog rings to the facing units. | Visual | Each Fill Layer | IP | SE/PE | This Checklist
5 | Soil reinforcements-Plan arrangement | IFC Drawings Arrangements: MRP-103-C-RFL-DRG-35-RBK-CSW-1101 to 1105 | Plan positions of Grid Strips are to be as IFC Drawings. - Grid Strips to be placed perpendicular to back of panel where possible. - Grid strips shall not overlap | Visual | Where applicable | IP | SE/PE | This Checklist
6 | Soil reinforcements-vertical/horizontal deviation | IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-1002 MRP-103-C-RFL-DRG-35-RBK-CSW-1102 - 1103 MRP-103-C-RFL-DRG-35-RBK-CSW-1701 | Where grid strips are in the same horizontal plane, ensure 75mm Min horizontal clearance between grid strips | Measure Survey | Each fill Layer | IP | Surveyoe/SE | This Checklist
7 | Soil reinforcements-clash with drainage | IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-1101 - 1105. | Avoid clash with stormawater pipe as per IFC drawings SKEW TOP LAYER OF GRID-STRIPS HORIZONTALLY TO AVOID CLASH WITH DRAINAGE PIT TYP. MAX ALLOWANCE SKEW ANGLE =20 DEG. | Visual | RW02 and RW03 stormwater and grid-strip interface | IP | SE/PE | This Checklist
8 | Fill-Placement | VR204.10 | Select backfill shall be placed in accordance with Vicroads section 204. Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm. Fill dispensation to be granted by superintendent to increase thickness layers. All RSS fill layers to be spread from face of panel to tail of soil reinforcing straps. | Measure Visual | Each fill layer | IP | SE/PE | This Checklist
9 | Fill-Placement compaction | 204.111 | 0 - 0.15 m Light weight hand operated DPU 0.15 - 0.30 m Less than 5T Roller 0.3 - 1.2 m Less than 10T Roller 1.2 - 2.4 m Less than 20T Roller >2.4 m Less than 35T Roller | Visual | Each fill layer | IP | SE/PE | This Checklist
10 | Fill Test roll | VR 204.12 | All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling Static Smooth drum roller with a mass >12T; or Tandem truck or water cart with a mass >20T. No visible deformation or springing during test roll. Unstable areas rectified as per agreed method. | Visual | Every Fill Layer | HP | Nominated Authority | This Checklist
11 | Select back fill-Compaction Testing | IFC Drawings VR 204.14 VR 682.16 | Testing frequency shall be in accordance with Vicroad Specification section 204.14 Moisture content shall achieve minimum characteristic value of density ratio: 98% Moisture content of backfill shall be maintained evenly at all times. Moisture content shall be +0%/-2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content must be allowed to dry. Attach: Compaction test results | Documet review | Each Fill Layer or every second layer as agreed | IP | Nominated Authority/PE | Attached Test Results
12 | Select back fill-Test frequency | IFC Drawings VR 204.14 VR 682.16 | After three consecutive lots of like material have achieved the specified requirement, reduce frequency of testing of subsequent lots to the minimum requirement specified in table 204.142: | Documet review | Each Fill Layer or every second layer as agreed | IP | Nominated Authority/PE | Referenced Lots in This Checklist
13 | Survey Conformance Asbuilt | MRPA Quality Management Plan | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances | Documet review | Each Fill Layer | IP | SE/PE | Attach: Survey Conformance As Built
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /