## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CHK-009-CIV-FRMS-RSS Walls-Fill Placement | [5 empty] | CHK-009-CIV-FRMS-RSS Walls-Fill Placement Rev 0
section | Details
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-009-CIV-FRMS-RSS Walls-Fill Placement
label | Checklist Description: RSS Walls-Fill Placement
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 03/06/2024
label | ITP created by: Kamel ALHOBAKI
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1 - Soil reinforcement-Straps
label | Reference - VR682.08, VR682.17 IFC Drawings
label | Acceptance Criteria - Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
label | ○ Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
label | Method - Visual
label | Frequency - Each strap
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 2 - Soil reinforcement-Straps
label | Reference - Installation manual
label | Acceptance Criteria - Correct number of reinforcing element shall be attached to each panel/wire facing units
label | Method - Visual
label | Frequency - Each panel/wire facing unit
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 3 - Pre-cast Panel Soil reinforcements-Bolts Connections
label | Reference - IFC Drawings
label | ○ Schedule of lengths:
label | — MRP-103-C-RFL-DRG-35-RBK-CSW-1303 to 1604
label | ○ Connections arrangement:
label | — MRP-103-C-RFL-DRG-35-RBK-CSW-2002 to 2003
label | Acceptance Criteria - Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
label | ○ Finger tight nut or use a wrench so thread emerges from top of nut
label | Method - Visual
label | Frequency - Each Fill Layer
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 4 - Wire Wall Soil reinforcements-Connections
label | Reference - IFC Drawings
label | ○ Schedule of lengths & Connections arrangement:
label | — MRP-103-C-RFL-DRG-35-RBK-CSW-1901 to 1903
label | Acceptance Criteria - Grid Strips are to be installed to the wire facing units in correct length and to the correct locations based on the number of grid-strips.
label | ○ The first layer of grid-strips are to be ziptied or connected via hog rings to the facing units.
label | Method - Visual
label | Frequency - Each Fill Layer
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 5 - Soil reinforcements-Plan arrangement
label | Reference - IFC Drawings
label | ○ Arrangements:
label | — MRP-103-C-RFL-DRG-35-RBK-CSW-1101 to 1105
label | Acceptance Criteria - Plan positions of Grid Strips are to be as IFC Drawings.
label | ○ Grid Strips to be placed perpendicular to back of panel where possible.
label | ○ Grid strips shall not overlap
label | Method - Visual
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 6 - Soil reinforcements-vertical/horizontal deviation
label | Reference - IFC Drawings
label | ○ MRP-103-C-RFL-DRG-35-RBK-CSW-1002
label | ○ MRP-103-C-RFL-DRG-35-RBK-CSW-1102 - 1103
label | ○ MRP-103-C-RFL-DRG-35-RBK-CSW-1701
label | Acceptance Criteria - Where grid strips are in the same horizontal plane, ensure 75mm Min horizontal clearance between grid strips
label | Method - Measure, Survey
label | Frequency - Each fill Layer
label | Category - IP
label | Responsibility - Surveyoe/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Soil reinforcements-clash with drainage
label | Reference - IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-1101 - 1105.
label | Acceptance Criteria - Avoid clash with stormawater pipe as per IFC drawings
label | ○ SKEW TOP LAYER OF GRID-STRIPS HORIZONTALLY TO AVOID CLASH WITH DRAINAGE PIT TYP. MAX ALLOWANCE SKEW ANGLE =20 DEG.
label | Method - Visual
label | Frequency - RW02 and RW03 stormwater and grid-strip interface
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 8 - Fill-Placement
label | Reference - VR204.10
label | Acceptance Criteria - Select backfill shall be placed in accordance with Vicroads section 204.
label | ○ Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm.
label | ○ Fill dispensation to be granted by superintendent to increase thickness layers.
label | ○ All RSS fill layers to be spread from face of panel to tail of soil reinforcing straps.
label | Method - Measure, Visual
label | Frequency - Each fill layer
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 9 - Fill-Placement compaction
label | Reference - 204.111
label | Acceptance Criteria - 0 - 0.15 m Light weight hand operated DPU
label | ○ 0.15 - 0.30 m Less than 5T Roller
label | ○ 0.3 - 1.2 m Less than 10T Roller
label | ○ 1.2 - 2.4 m Less than 20T Roller
label | ○ >2.4 m Less than 35T Roller
label | Method - Visual
label | Frequency - Each fill layer
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 10 - Fill Test roll
label | Reference - VR 204.12
label | Acceptance Criteria - All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
label | ○ Static Smooth drum roller with a mass >12T; or
label | ○ Tandem truck or water cart with a mass >20T.
label | ○ No visible deformation or springing during test roll.
label | ○ Unstable areas rectified as per agreed method.
label | Method - Visual
label | Frequency - Every Fill Layer
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This Checklist
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Select back fill-Compaction Testing
label | Reference - IFC Drawings VR 204.14, VR 682.16
label | Acceptance Criteria - Testing frequency shall be in accordance with Vicroad Specification section 204.14
label | ○ Moisture content shall achieve minimum characteristic value of density ratio: 98%
label | ○ Moisture content of backfill shall be maintained evenly at all times. Moisture content shall be +0%/-2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content must be allowed to dry.
label | ○ Attach: Compaction test results
label | Method - Document review
label | Frequency - Each Fill Layer or every second layer as agreed
label | Category - IP
label | Responsibility - Nominated Authority/PE
label | Verifying Documents - Attached Test Results
date | Date Completed:
checkpoint | 12 - Select back fill-Test frequency
label | Reference - IFC Drawings VR 204.14, VR 682.16
label | Acceptance Criteria - After three consecutive lots of like material have achieved the specified requirement, reduce frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
label | Method - Document review
label | Frequency - Each Fill Layer or every second layer as agreed
label | Category - IP
label | Responsibility - Nominated Authority/PE
label | Verifying Documents - Referenced Lots in This Checklist
date | Date Completed:
checkpoint | 13 - Survey Conformance Asbuilt
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
label | Method - Document review
label | Frequency - Each Fill Layer
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - Attach: Survey Conformance As Built
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | CHK-010-CIV-FRMS-RSS Walls-Pre-cast Panel Installation | [5 empty] | CHK-010-CIV-FRMS-RSS Walls-Pre-cast Panel Installation Rev 0
section | Details
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-010-CIV-FRMS-RSS Walls-Pre-cast Panel Installation
label | Checklist Description: RSS Walls - Panel Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 03/06/2024
label | ITP created by: Kamel Alshobaki
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1 - Panels-survey set out-Tolerance
label | Reference - VR 682.20 IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-1001
label | Acceptance Criteria - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | Method - Measure
label | Frequency - Base course panels
label | Category - IP
label | Responsibility - Surveyor/PE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 2 - Mark-up panel for construction team
label | Reference - IFC Drawing:
label | ○ MRP-103-C-RFL-DRG-35-RBK-CSW-1101 to 1105
label | ○ MRP-103-C-RFL-DRG-35-RBK-CSW-1108 to 1404
label | Acceptance Criteria - Mark number of strips per row on the back of each panel.
label | ○ Mark design location (Wall number, row and column) as per elevation drawings on the back of each panel
label | Method - Visual
label | Frequency - Each panel
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 3 - Panel installation
label | Reference - IFC Drawing:
label | ○ Instructions: MRP-103-C-RFL-DRG-35-RBK-CSW-2001
label | ○ Weephole Locations: MRP-103-C-RFL-DRG-35-RBK-CSW-1108 to 1404
label | ○ Archtectural pattern drawings: MRP-103-C-RFL-DRG-35-RBK-CSW-1104 to 1604
label | Acceptance Criteria - RSS Panels are to be installed as per IFC Drawings and specified schedule.
label | ○ Check for correct architectural pattern
label | ○ Check for Weephole Locations
label | ○ Check the 1 in 40 slope is to be maintained
label | Method - Visual, Measure
label | Frequency - Each panel
label | Category - WP
label | Responsibility - SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 4 - Bearing Pad Installation
label | Reference - IFC Drawing:
label | ○ Instructions:
label | — MRP-103-C-RFL-DRG-35-RBK-CSW-2003
label | Acceptance Criteria - 3 x bearing pads must be installed per panel - Centre of the outer bearing pads must be 200mm+/-10mm from the edge of the panel
label | ○ Check the 19mm nominal gap to be maintained
label | ○ Install 3 Bearing Pads at rear on top of panels
label | ○ Above must be checked with Surveyor prior to backfill
label | ○ Note bearing pads shall not be installed under base row panels
label | Method - Visual
label | Frequency - Each panel
label | Category - WP
label | Responsibility - SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 5 - Panel installation-Abutment interfaces
label | Reference - IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-1106
label | Acceptance Criteria - Panel installation and abutment interfaces
label | ○ 30mm nominal gap between panels and Abutment wall is to be mainatined
label | ○ 150mm wide x 14mm Folded Galvanized plates (Grade 250) drill and fix to as per IFC drawings with Galvanized M12x75 Long Excalibur screwbolts at 500 CTRS Typical each wall.
label | ○ 600mm wide BITAC tape installed
label | Method - Measure
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 6 - Filter fabric -Installation
label | Reference - IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-2003, VR682.11
label | Acceptance Criteria - Install Filter Fabric against all vertical and horizontal joints
label | Method - Visual
label | Frequency - Each course of panel installation
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 7 - Drainage-Strip Drain
label | Reference - VR682.11
label | Acceptance Criteria - Install 300mm wide strip drain between precast wall panel vertical joints.
label | ○ Strip drain to be encapsulated by nonwoven geotextile in accordance with section 682.11
label | ○ At every vertival joint between panels in RSS wall, ensure no gap is formed bewteen strip drian and RSS panels
label | Method - Visual
label | Frequency - Each course of panel installation
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 8 - Panel installation-Survey reference points
label | Reference - VR 682.20
label | Acceptance Criteria - To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | Method - Visual
label | Frequency - Each course of panel installation
label | Category - IP
label | Responsibility - Surveyor/SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 9 - Traceability of precast units and records
label | Reference - VR 620.09
label | Acceptance Criteria - Unique ID of precast panel is recorded.
label | ○ ATTACH: marked-up elevation drawings or installation record with reference to panel ID
label | Method - Visual
label | Frequency - Each panel
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 10 - Panels installation-Conformance Survey
label | Reference - IFC Drawings
label | ○ VR 682.06
label | ○ VR 682.17
label | ○ VR 682.20
label | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | ○ Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | ○ Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | ○ Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full length of the gap
label | ○ The wall level shall not deviate from the specified level by more than ±20mm
label | ○ The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | ○ The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
label | ○ Attach: Survey Report
label | Method - Survey, Measure
label | Frequency - Each course of panel installation
label | Category - HP*
label | Responsibility - Surveyor/PE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP