## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-251-CIV-FRMS-RSS Wall Main | itp |  |  |  |  | ITP-251-CIV-FRMS-RSS Wall Main Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-251-CIV-FRMS-RSS Wall Main
label | ITP Description: FRMS-RSS Wall Main
label | Discipline (e.g. CIV/STR/RAIL): 251-CIV
label | Revision Number: 0
label | Revision Date: 03/06/25
label | ITP created by: Kamel Alshobaki
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 682 November 2018
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 204 December 2015
label | 1.3 - Non Dependent
label | Reference - IFC drawings
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Concrete-Leveling Pad
label | Reference - IFC drawings
label | Acceptance Criteria - Concrete compressive strength grade must not be less than N25 for levelling course and backing blocks;
textbox | Reference: Teambinder MA number:
label | Method - Document Review
label | Frequency - Each element
label | Category - HP*
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - Material approval
date | Date Completed:
checkpoint | 2.2 - Select fill
label | Reference - IFC Drawings VR 682
label | Acceptance Criteria - Select fill shall comply with the requirements of the RSS designer:
label | — UNIT WEIGHT (Max): = 17 kN/m³
label | — COHESION (Min): ≥ 0 kPa
label | — INTERNAL FRICTION ANGLE (Min): = 36°
label | ○ Gradation:
label | — 150mm : 100% PASSING
label | — 37.5mm : 60 TO 100% PASSING
label | — 9.5mm : 25 TO 100% PASSING
label | — 2.36mm : 15 TO 100% PASSING
label | — 0.6mm : 10 TO 100% PASSING
label | — 0.075mm : 0 TO 15% PASSING
label | ○ Electrochemical Properties:
label | — pH: 5 - 10
label | — RESISTIVITY >1000 Ω-cm
label | — CHLORIDES <200 mg/kg
label | — SULPHATES <200 mg/kg
label | — ORGANIC CONTENT 0%
label | ○ Structural Properties:
label | — COEFFICIENT OF UNIFORMITY ≥ 5
label | — LIQUID LIMIT ≤ 30%
label | — PLASTICITY INDEX ≤ 12
label | ○ The select backfill must meet the minimum requirements of Vicroads Type A filling
textbox | Reference: Material approval in Teambinder
label | Method - Document Review
label | Frequency - Each material specification
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - General fill
label | Reference - IFC Drawings VR 204
label | Acceptance Criteria - Backfill behind the reinforced block shall be Vicroads Type A or better in accordance with Vicroads standard specification 204:
label | Select General fill shall comply with the requirements of the RSS designer (RW01-RW04):
label | ○ UNIT WEIGHT: = 17 kN/m³
label | ○ COHESION (MIN): = 0 kPa
label | ○ INTERNAL FRICTION ANGLE (Min): = 30°
textbox | Reference: Material approval in Teambinder
label | Method - Document Review
label | Frequency - Each material specification
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Subsurface Pipe
label | Reference - IFC Drawings MRP-103-C-AUR-DRG-35-RBK-CSW-0101
label | Acceptance Criteria - 100mm SUBSURFACE PIPE WRAPPED IN GEOTEXTILE ENCASED IN FREE DRAINAGE GRANULAR FILL
textbox | Reference: Teambinder MA number:
label | Method - Document review, Measure
label | Frequency - Each wall
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documents
checkpoint | 3.1 - RSS Panels
label | Reference - IFC drawings
label | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | — 1. Concrete strength;
label | — 2.Date of manufacture;
label | — 3.Unique Identification number;
label | — 4.Mass;
label | — 5.Confirmation of number, type and capacity of lifting inserts;
label | — 6.Quality assurance sign-off.
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Post-pour check sheet / ITP
label | vi. Covermeter check record
label | vii. Record of dimensional measurements
label | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
textbox | Reference: Precast panels MDR Lot in TeamBinder:
label | Method - Document Review
label | Frequency - Once for each type of panels
label | Category - HP
label | Responsibility - PE
label | Verifying Documents - Precast panels Birth certificates and MDR Lot
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Foundation
label | Reference - IFC Drawings MRP-103-C-AUR-DRG-35-RBK-CSW-0101
label | Acceptance Criteria - Foundation material under RSS wakk (RT01 to RT04) shall adhere with minimum design bearing capacity.
label | Max Wall Height
label | ○ <2.5m - 75/150kPa
label | ○ 2.5 - 4.5m - 90/180kPa
label | ○ 4.5 - 5.5m - 100/200kPa
label | ○ 5.5 - 6.5m - 110/220kPa
label | ○ 6.5 - 7.5m - 115/230kPa
label | ○ 7.5-8.5m - 125/250kPa
label | Method - Test, Document Review, Visual
label | Frequency - Each retaining Wall
label | Category - HP*
label | Responsibility - PE/Geotechnical Engineer, Foundation geotechnical assessment
label | Verifying Documents - This ITP Signed off, Test results
date | Date Completed:
checkpoint | 4.2 - Foundation
label | Reference - VR 204.12, VR 204.11
label | Acceptance Criteria - Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
label | ○ No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
label | Method - Visual
label | Frequency - Each retaining Wall
label | Category - HP
label | Responsibility - PE/Niminated Authority
label | Verifying Documents - This ITP Signed off
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Levelling Pad-Survey Set out
label | Reference - IFC Drawings VR 682.20, MRP-103-C-FRL-DRG-35-RBK-CSW-1001
label | Acceptance Criteria - Survey to set up and validate all works meets levels and locations with the right tolerances as per IFC Drawings and Vicroads Specification.
label | ○ Levelling course level shall not deviate from the specified level by more than +/- 3mm
label | Method - Measure, Visual
label | Frequency - Each retaining Wall
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP Signed off
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Form Levelling pad
label | Reference - IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-1201
label | Acceptance Criteria - Form timber shutters or Earth form to edge of levelling pad
label | ○ Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
label | Method - Measure, Visual
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed off
date | Date Completed:
checkpoint | 5.2 - Leveling Pad Concrete Pour
label | Reference - IFC Drawings VR610
label | Acceptance Criteria - Concrete to be placed in accordance with VR610.
label | ○ Attach: Concrete Delivery Docket
label | Method - Visual
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Concrete Pour record, Concrete Delivery Docket
date | Date Completed:
checkpoint | 5.3 - Leveling Pad Concrete Testing
label | Reference - IFC Drawings VR Section 610.16 (b) & (d)
label | Acceptance Criteria - Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
label | ○ Concrete strength (Min): N25 MPa
label | ○ Attach: Concrete test report
label | Method - Document Review
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - PE
label | Verifying Documents - Attach Concrete Test Report
date | Date Completed:
checkpoint | 5.4 - Levelling Pad-Post Pour Survey-Levelling Course
label | Reference - IFC Drawings MRP-103-C-FRL-DRG-35-RBK-CSW-1001
label | Acceptance Criteria - Levelling course level shall not deviate from the specified level by more than ±3mm
label | ○ 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
label | ○ Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | Method - Measure, Visual
label | Frequency - Each retaining Wall
label | Category - IP
label | Responsibility - PE/Surveyor
label | Verifying Documents - Attach Survey Report
date | Date Completed:
checkpoint | 5.5 - Drainage-base of the Wall
label | Reference - IFC Drawings MRP-103-C-FRL-DRG-35-RBK-CSW-0151
label | Acceptance Criteria - to install 300mmx300mmGranular backfill in Geotextile BIDIM A24 around 100mm Dia. Perforted plastic pipewith 0.5% min fall to weepholes in RSS panels.
label | ○ Geotextile BIDIM A24
label | ○ 300mmx300mm Granular backfill
label | ○ 100mm Dia. Perforted plastic pipe
label | ○ Perforated pipe to have 0.5% minimum fall
label | Method - Visual
label | Frequency - Each wall
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed off
date | Date Completed:
checkpoint | 5.6 - Settlement Monitoring horizontal inclinometer
label | Reference - IFC drawings MRP-103-C-FRL-DRG-35-RBK-CSW-0021, VR 682.15
label | Acceptance Criteria - Survey Pin and Inclinometer survey procedure us as follows:
label | ○ Inclinometers shall be installed prior ro placement of any fill
label | ○ RSS Wall and abutment wall survey pins shall be installed immediately following construction of the first level of RSS wall/Abutment wall and prior to any fill placement
label | ○ Traffic barrier survey pins shall be installed following construction of pavement and barriers
label | ○ All survey pins shall have appopriate stick-up from finished surface level for continous settlement throughout construction/post construction
label | ○ Pavement construction shall not commence until monitoring from inclinometers and RSS wall/abutment wall survey pins indicate ground movements have reached at least 90% of construction settlements and confirmed by the geoechnical engineer
label | ○ Settlment Monitoring readings shall be taken at maximum one week intervals or for every one metre of fill placement (whichever is more frequent) unitl settlement stablisers or advised by the geotechnical engineer
label | ○ If at any stage prior ro the to the completion of the RSS placement, the total settlement exceeds 100mm, fill placement must be suspendedm and direction sought from the design engineer.
label | ○ Survey pins and horizontal inclinometer shall be installed to monitor ground movement throughout and after the RSS wall construction.
label | ○ Only hand operated equipment shall be used within 1m distance from inclinometers
label | ○ Geotechnical instruments shall be preserved and protected for monitoring until the conclusion of post construction. Damaged or malfuctioning inclinometers shall be reported and replaced where possible.
label | Method - Document Review
label | Frequency - Each Inclinometer
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - Teambinder approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - Wall Post construction monitoring
label | Reference - IFC Drawings VR 682.20, VR 682.151
label | Acceptance Criteria - The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
label | Method - Measure, Survey
label | Frequency - Each wall
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Survey Report
date | Date Completed:
checkpoint | 6.2 - Settlement Monitoring
label | Reference - IFC Drawings VR 682.15, VR 682.20
label | Acceptance Criteria - RSS wall base level:
label | — Start of wall construction to completion of wall construction (before pavement placement) Approx vertical settlement < 20mm
label | — Completion of pavement construction to end of defects liability period (2 years after practical completion) Approx vertical settlement < 15mm
label | ○ Pavement level (Top of RSS wall):
label | — Start of Pavement construction to completion of pavement construction Approx vertical settlement < 20mm
label | — 10 years following practical completion of payment < 50mm
label | ○ Settlement monitoring readings shall be taken at maximum one week intervals or for every one metre of fill placement (whichever is more frequent) until settlement stabilised or advised by the geotechnical engineer
label | ○ If RSS fill placement total settlement >50mm, fill placement must be suspended, and the mitigation method reviewed by the superintendent and DTP before recommencing fill placement.
label | Method - Measure, Survey, Document Review
label | Frequency - 1m of fill
label | Category - HP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Settlement monitoring results
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP