## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | 02.01 - Traffic Management | itp | 02.01 - Traffic Management |  | c053f43b-7645-4957-8e48-84bd21515ae6
| section | Details
| checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
1bc4b829-7190-57cf-a2e5-21fef27f038b | note | Acceptance Criteria & Frequency (Project Specific) - Written
85becad5-6e21-544e-820b-59bc06482d42 | note | Check Item - Check Item
4fc48fc7-4186-5e70-98ee-fb156ec1452d | note | Reference - MRTS02.1 Cl5.2
| checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the contractor that the Traffic Management Plan has been submitted and approved
83b20c19-eda4-5ec5-bec8-5d60bde9a663 | note | Acceptance Criteria & Frequency (Project Specific) - Written Approval
80485ff5-a569-5884-ab8f-b5d6529e2991 | note | Check Item - Hold Point 1
ddde38e2-265b-5490-9248-e506389d5fe0 | note | Reference - MRTS02 Cl 5.3
| signoff | HOLD POINT
| checkpoint | All TGS's prepared by a suitably qualified person and submitted and approved by the Administrator
04beb202-f592-52a4-b4c5-c1bf9bddae98 | note | Acceptance Criteria & Frequency (Project Specific) - Written Submission
98582cb2-28d6-5f23-bfdf-cc338d028e4b | note | Check Item - Hold Point 2
989c70da-5052-5bd6-89fd-16545444663f | note | Reference - MRTS02 Cl 6.2
| signoff | HOLD POINT
| checkpoint | Submission of Traffic Management Inspection Report
a434b92d-27c0-5a84-ab4a-05e6bfc69c00 | note | Acceptance Criteria & Frequency (Project Specific) - Written
26729e5a-2778-5c57-8a6e-1b5ae72f1b89 | note | Check Item - Milestone
0c414005-88d6-538c-8f72-615ea5305d87 | note | Reference - MRTS02 Cl 7.5
| checkpoint | Final Verification
9a0c21bf-48de-5914-8fcc-f4f37554ed73 | note | Project Manager Verify that the Above has been Constructed according to Specification
4ef3a448-fdf2-5e11-bbf9-00319b557e51 | textbox | Print Name:
0611e85c-b866-5921-8fcb-cd9b4c024d8a | date | Date:
a70a9ba1-36de-511a-b4c8-0c0b227692e1 | note | Client Verify that the Above has been Constructed according to Specification
8befa5ae-b5c4-54fa-b702-34f7947fdad6 | textbox | Print Name:
76452ece-7b1b-53ff-94fa-1cd54117d8ea | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs | itp | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs |  | d36ca61b-8b6f-4823-855d-7a3f93ba3ce1
| section | Details
| checkpoint | Items to be salvaged identified in accordance with Annexure MRTS03.1 Cl. 2.1. Items to be removed without damage and stored at a location as nominated in MRTS03.1 Cl. 2.2.
ad08eef8-5fc3-53fe-8966-6b7ab916f004 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f39b9653-f0e2-5c31-9a36-cb057e555045 | note | Check Item - Check Item
29ee84c9-e04c-5056-92db-fda7e903448e | note | Reference - MRTS03.1
| checkpoint | Any Kerb and Channel or concrete slab to be removed is sawcut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
04089610-93f4-5c37-b1cf-9b49bb9942c3 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9455e5fb-c004-5460-a905-1a51df08578d | note | Check Item - Check Item
93f1b6f9-9f49-509a-ab88-e9a088331120 | note | Reference - MRTS03 Cl. 9.4
| checkpoint | Non Salvageable components, kerbs, gullies and access chambers removed or demolished as per drawings/specifications.
662bfbf5-7d6e-5dc4-b8c7-0f21cce768f1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6034c455-3f94-5e1e-94ce-901e654d0cbd | note | Check Item - Check Item
ed22f28e-4428-5de4-bcfe-4dc455bfd1b7 | note | Reference - MRTS03 Cl. 9.2 & 9.5
| checkpoint | Excavations backfilled where shown on the drawings or required to leave the area in a safe and free draining state. Kerb excavations backfilled to flush with the surrounding area.
80356e77-d086-5907-b951-ca1329d03218 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1f3de524-6890-5a65-ab4e-f89b0b4b9988 | note | Check Item - Check Item
0824a729-236a-56f0-9728-e310cd4a8da4 | note | Reference - MRTS03 Cl. 9.2 Cl. 9.4
| checkpoint | Final Verification
858fb8ae-4873-5d27-9c60-17cf6dc53521 | note | Project Manager Verify that the Above has been Constructed according to Specification
18f005a6-4451-55e6-9312-daa8ac04f66f | textbox | Print Name:
e59649f5-826e-53ef-bc36-c787ae0207ea | date | Date:
46f05bab-79ff-543e-b2ea-ca2fbb1a591a | note | Client Verify that the Above has been Constructed according to Specification
059c7af5-4277-52e3-b8c4-6bbea9a796b6 | textbox | Print Name:
bcbad750-361e-5daf-9b90-265a6bda8324 | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 04.01 - Clear and Grub Stripping of Topsoil | itp | 04.01 - Clear and Grub Stripping of Topsoil |  | e0fe55a6-9eac-4f01-a329-ec913df3fe4e
| section | Details
| checkpoint | Clearing limit plan prepared and approved by Prinicpal with boundary limits clearly marked
c48f5900-0689-5e09-8cca-3f5cc9f558b5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f10aa17c-58c1-5241-9ea3-498db2211cba | note | Check Item - Check Item
020656be-78ea-5480-b9b9-2a3f8f869dfa | note | Reference - MRTS04.1 Cl1.1, 1.2, 1.4 & MRTS51 Cl3.1, 3.3, 3.7
| checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the area concerned.
db94fd30-d6bf-5b83-a7e8-7bd10cbfa7a1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7e054e4f-04b8-532a-9771-abe4b79ef99b | note | Check Item - Hold Point 1
3002f3f9-266b-5543-a218-642b24df00fb | note | Reference - MRTS04 Cl7.2.2
| signoff | HOLD POINT
| checkpoint | Marketable timber shall be clearly marked by contractor Prior to clearing. Marked trees felled and handled avoiding damage to the trunks. The trunks trimmed and stacked in neat manageable stockpiles approved by the Administrator at spacings of not more than 500 metres.
5fbf9305-21e4-59a8-a2b6-aa7552a5c57f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
076bc22a-fb16-5b8f-92b0-6d35d20d3e45 | note | Check Item - Hold Point 2
fbea8437-2a8b-507b-a65c-9b2a7790126f | note | Reference - MRTS04 Cl7.2.3
| signoff | HOLD POINT
| checkpoint | Material suitable for organic mulch shall be in accordance with MRTS16B Vegetation Ground Works
0030f327-8447-5ddd-9272-25c5420789e5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, MRTS16B
45c1aae9-530e-5416-a765-1a208d8e603a | note | Check Item - Check Item
2024c403-a64d-54e4-a75d-cbc866b5f606 | note | Reference - MRTS04 Cl7.2.4
| checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
d624008e-1653-5462-bed3-5c2ed36bae53 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1c003cf4-1128-5f24-bcc4-f3a9a0cf1e72 | note | Check Item - Check Item
61320cb5-780a-52a5-a51e-db40eb3cc8d3 | note | Reference - MRTS04 Cl7.2.5
| checkpoint | Topsoil stripped as required in Cl 2.1 of Annexure MRTS.04.01. Depth of excavation shall be specified in the Cl 2.1 of Annexure MRTS04.01 or as directed.
636f1682-e159-538d-ac74-a55375380cb4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ab68b10f-c317-59e2-9d1b-0f49f756ef40 | note | Check Item - Check Item
f43f1e11-499c-5e0c-bbe2-049c10a1292d | note | Reference - MRTS04 Cl8.2
| checkpoint | Surplus material and material considered not suitable for use as planting media in accordance with Cl 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed of in accordance with Cl 11
d8cc3b90-fce3-5671-ac72-51878ae608a9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
035abdcd-786e-5f7c-afd0-4662aecc5f9b | note | Check Item - Check Item
3ea966b1-e601-54d2-84b0-b00cfec36444 | note | Reference - MRTS04 Cl8.4.2
| checkpoint | Material not removed from within drip lines of trees except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retainined are preserved where practical.
ab3c100f-c6c5-5fef-9e81-891794a4231f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
61746790-7158-5052-8f32-4f93736f295b | note | Check Item - Check Item
79e45256-95dd-5cce-960e-2c5fc66189e3 | note | Reference - MRTS04 Cl8.4.3
| checkpoint | Stripped material shall be stockpiled in the locations shown on the drawings, as stated in Clause 2.2 of Annexure MRTS04.1
f0e6ae5e-9e25-569d-aa63-b9c480406a4f | note | Topsoil Stockpiles are;
8530e99c-ad45-5f20-b21f-638daf1366e2 | note | ○ Less than 3m High
ae2736bc-56b9-5f33-97d7-6de629040158 | note | ○ Less than 10m wide
ee0546a3-ed01-55e1-b57b-a2a936c9a92e | note | ○ Appropriately battered, drained or otherwise protected to prevent erosion and segregation
8ee90b82-72bc-51e0-9e7f-0c43ab7d62cc | note | ○ Stockpiled for the minimum duration
1c4df0b1-5444-502b-9f86-f7e82b3ae581 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d73322fb-6ed9-5f1b-9443-fcecb5ab7a09 | note | Check Item - Check Item
721d12fc-6bf7-53f6-9761-ab8c4e878d21 | note | Reference - MRTS04 Cl8.4.4
| checkpoint | Quality Verification Requirements, Test Method
00982310-97fe-5cfb-8ef2-6134686b6008 | note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
204b7881-af0c-5d1c-b901-d6db824a48a3 | note | Check Item - MRTS04
32a6ffa4-70bd-5efe-a313-a8287dca82d0 | note | Reference - Table A1
| checkpoint | Geometrics, Clearance Limits
37cac557-22cb-57bc-a00d-49f4592d96e9 | note | Acceptance Criteria & Frequency (Project Specific) - 1000m, 10m grid, 2 per lot
d46e4c63-0866-54e2-ae4e-c61cfb02d7ab | note | Check Item - Check Item
1ad6d4eb-3f11-586b-8a7f-c9c6c01fbd4b | note | Reference - MRTS04 Table A.2
| checkpoint | Geometrics, Vertical (Stripping of Topsoil only)
783a3654-96ab-5d54-b25f-372c623b4cf0 | note | Acceptance Criteria & Frequency (Project Specific) - 1 test per 100m per side
1fee9741-9fd0-5e20-8a70-81f76fd9a4aa | note | Check Item - Check Item
53c1be1e-6fc0-5f0c-9aae-44a824f7c952 | note | Reference - MRTS04 Table A.2
| checkpoint | Final Verification
32be7046-1665-5720-8851-8b622ef03b16 | note | Project Manager Verify that the Above has been Constructed according to Specification
19d2243e-aec7-5fb7-8f4e-8420dc69569c | textbox | Print Name:
29737577-4326-56a7-9833-2cb6cb2166dd | date | Date:
ccf126cb-d317-5b30-ab40-205d0858688c | note | Client Verify that the Above has been Constructed according to Specification
349b0619-4235-5a5f-836f-9121085e3104 | textbox | Print Name:
20fecf5c-e02e-5df5-960a-5ffb7daf6f10 | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 04.06 - General Excavation | itp | 04.06 - General Excavation |  | fec2d04e-d059-4e4a-a00f-091e5b3e0b77
| section | Details
| checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceeding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL11.3
5f3a2039-7a53-5840-87ca-fb22dbc6ea49 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e00e6980-1961-5a23-9e32-f6523640ab18 | note | Check Item - Hold Point 4
9c271143-f690-5096-925a-0022f76e2f3d | note | Reference - MRTS04 Cl9.4
| signoff | HOLD POINT
| checkpoint | Where material can be reasonably be expected to contain a possible acid sulphate potential, the test results shall be documented and reported to the Administrator.
ff9dfc37-f1df-5d47-a1a8-6a49ce87a699 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b04e1f8f-57f4-541a-b1cb-ee9ce70393b9 | note | Check Item - Hold Point 5
479badb3-2314-56cf-8638-97c4f9b06707 | note | Reference - MRTS04 Cl10.1.4
| signoff | HOLD POINT
| checkpoint | Work stopped when excavation has reached subgrade level. Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3
d01b54cc-761a-5ae9-bf86-6861253aaf2f | note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 Table 15.3-A, Table 15.3-B
5da74b65-2d3f-5711-8046-4dab6d2d6813 | note | Check Item - Hold Point 8
0b2fde21-fd9f-54a2-aefb-0d1d4350128f | note | Reference - MRTS04 Cl13.3.2.1 Cl18.3.3
| signoff | HOLD POINT
| checkpoint | Bottom of excavation other than subgrade compacted to RDD 95% and completed to tolerances specified
97b19bb6-1321-5da0-80c5-34b6ea95259b | note | Acceptance Criteria & Frequency (Project Specific) - 95% RDD Table 15.3-A, Table 15.3-B, Tolerances: Table 6.3.1
d09263f7-1664-509a-b432-53eed601dda7 | note | Check Item - Check Item
8d1b3ffa-92c1-50b5-8635-049384cc1b67 | note | Reference - MRTS04 Table 6.3.1
| checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings.
193f1905-5b86-5544-9ee8-6f978969a9d9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, Tolerances: Table 6.3.1
40246444-8013-530c-8061-d027a92d0028 | note | Check Item - Check Item
c956bd7a-6bf8-5cf8-ba04-078d5a6740e5 | note | Reference - MRTS04 Cl13.3.1 Table 6.3.1
| checkpoint | Treatment of Batters shall commence as soon as practicable, but not later than 14 days after substantial completion of earthworks on each section.
179f2460-a4bc-5d04-8e16-bec69545da61 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
710faf63-e7ad-5cde-8b30-a6133b6fc6ba | note | Check Item - Witness Point 7
e3d80a06-bc0d-59b0-bbef-c1bf70947f9a | note | Reference - MRTS04 Cl16
| checkpoint | Dewatering of excavations comply with requirements of EMP
24614271-6cdf-54b5-8361-b256809e36a0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9161193d-589b-5358-9aae-6e65ea61bc19 | note | Check Item - Check Item
559f0196-b3f3-51aa-9bf9-517c01b40f3f | note | Reference - MRTS04 Cl13.3.8
| checkpoint | Construction Testing Requirements: Test Method
97f947bb-1466-5be3-9877-ae87e833827c | note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
1dbdacdb-4be1-5f70-9674-8e34887c38df | note | Check Item - MRTS04
6c67286c-f5ae-53b8-83d8-2fe92b94b55d | note | Reference - Table A2.1
| checkpoint | Compaction: AS1289.5.4.1 or AS1289.5.7.1, To a depth 150mm below bottom of excavation = 95%
e72bd9e3-0b27-5150-b20b-4239cac2d293 | note | Acceptance Criteria & Frequency (Project Specific) - Max Lot Size: each excavation, 1 per 50m2, 2 per lot
82e58849-338a-5cad-b05a-52ca1448873a | note | Check Item - Check Item
fa178717-b358-5536-91c1-a171bb2a31c1 | note | Reference - Table A2.1
| checkpoint | Geometrics: Profile
6bc94736-97c2-5685-80cf-b42a71fb170b | note | Acceptance Criteria & Frequency (Project Specific) - Max Lot Size: each excavation, 1 per 100m, 1 per lot
df56a5c1-6c79-5407-928c-86f0a9a446c2 | note | Check Item - Check Item
d1b9eff5-067c-58c7-831e-32ccfdd16e29 | note | Reference - Table A2.1
| checkpoint | Final Verification
823943f7-10e9-581a-91f0-e2457838ed34 | note | Project Manager Verify that the Above has been Constructed according to Specification
d4271d11-fd83-53d0-b7a9-9615efdf2dbe | textbox | Print Name:
685b1fca-7ce9-5560-9964-b6f1e5aab965 | date | Date:
ef89f335-1114-5a26-8cf0-1feac7e69da9 | note | Client Verify that the Above has been Constructed according to Specification
28f59d29-5f64-5e02-879c-169f8b2fcecf | textbox | Print Name:
0a1ebe56-005f-5d0a-b706-b7f4e37a3d4a | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 04.08 - Embankment | itp | 04.08 - Embankment |  | 93934d3b-407f-4c9d-ab8d-560aecffe761
| section | Details
| checkpoint | Prior to incorporating any Earth or Rock Fill Material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements.
5466883a-1512-5070-98de-905cdc9de154 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
fee4102c-e960-5d71-85b2-c0ca58060746 | note | Check Item - Hold Point 10
e70c7f95-027d-581d-b6c3-d0e84bea7845 | note | Reference - MRTS04 Cl14.2.1
| signoff | HOLD POINT
| checkpoint | Rock Fill shall be sourced from a TMR regsitered quarry or other suitable source and shall comply with the properties states in Table 14.2.3.
a3b746fd-d02c-57f9-ace7-c227816b08ee | note | Acceptance Criteria & Frequency (Project Specific) - Visual
bded237d-e3df-5a5c-8a05-def6458aaff8 | note | Check Item - Check Item
2eb8db37-ddcd-5bb2-a79f-320b41a2f00f | note | Reference - MRTS04 Cl14.2.3
| checkpoint | The foundation under rock fill shall be treated and shaped to maintain drainage and so erosion of the foundation will not occur.
c04fcd8e-df41-5879-bb55-e5e453f9d62a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
036b7f55-5c2c-5125-bfac-a9ea27ac4c9d | note | Check Item - Check Item
39209c65-59ea-5ea4-a2d7-d372f56bce49 | note | Reference - MRTS04 Cl14.2.3
| checkpoint | Rock fill shall be placed and spread in such a way to avoid segregation and contamination with foreign material. The uncompacted Rock Fill layer thickness must not exceed the thickness given in Table 15.4
6cf5eeea-99c2-52e1-bc5e-230e97c22cee | note | Acceptance Criteria & Frequency (Project Specific) - Visual
65dfe3ca-eb2d-529c-bf18-febc6c9737dc | note | Check Item - Check Item
11b21866-4b2b-5961-a9cc-802219d2bc94 | note | Reference - MRTS04 Cl14.2.3
| checkpoint | Compact the Rock Fill using the mechanical interlock method of construction as per Clause 15.4
bc92b06b-4e39-5491-add0-49fcea667e88 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
cb7b6811-fda6-57d0-a5ec-a691554a1ed0 | note | Check Item - Check Item
88bbfb62-48a4-5d57-8ed7-8587dc18df52 | note | Reference - MRTS04 Cl14.2.3
| checkpoint | Embankments constructed to the shapes, zones and other requirements shown on the drawings or as otherwise specified.
58f9054b-e48d-5bed-8ef1-62751bf03b2f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8e859910-7315-5922-8e1e-a9f058b5d075 | note | Check Item - Check Item
2b505295-1d6d-51ae-9be9-f06b5cc1dc6d | note | Reference - MRTS04 Cl14.3.1
| checkpoint | Geotextile placed at interchange between compaction methods
9a64e7dd-bca5-59cc-b42e-608292374198 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
10dfcf5e-dd10-578d-a0af-667311328c14 | note | Check Item - Check Item
9cae4a7c-06b9-5113-895c-aeb25f110e17 | note | Reference - MRTS04 Cl14.3.2
| checkpoint | The ground surface on which embankments are to be constructed shall be stepped in accordance with the requirements of Cl14.3.3
1bf8868e-2690-5118-861b-fa764bd647f0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0ef7bd89-7819-5925-a5fa-29fb12d485c6 | note | Check Item - Check Item
e0e60595-ce73-5fb8-b8b6-08634c22667b | note | Reference - MRTS04 Cl14.3.3
| checkpoint | The max thickness of an uncompacted layer shall be as per Table 15.4.
3be6f60a-c965-5ffd-917b-c19ca375db46 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c41d56a8-8782-5bfe-a072-693b2fa22912 | note | Check Item - Check Item
284dd5c1-e8cf-506a-8da0-107a12461156 | note | Reference - MRTS04 Cl15.4
| checkpoint | Each layer rolled until the rolled surfaces do not exhibit any permanent deformation, rutting, yielding, signs of distress or instability.
8b3c1dd2-b58a-53ef-afa1-9566d5bc32eb | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1f727234-6185-5cb9-a505-90e02d89d269 | note | Check Item - Witness Point 6
7624f324-03b9-5b43-92bf-7cc7f2f23b19 | note | Reference - MRTS04 Cl15.4
| checkpoint | Final Verification
5af75e70-acbe-506e-8ebe-1d2c15714a19 | note | Project Manager Verify that the Above has been Constructed according to Specification
3901a0e9-b767-5036-9e46-241d70f41390 | textbox | Print Name:
f444e2ca-3985-5c9d-bc70-f5099419d1e0 | date | Date:
efd6d36f-f763-5a1b-b374-5e79c5a1f72e | note | Client Verify that the Above has been Constructed according to Specification
74e1ee87-e77e-5ac3-8823-56ddb178cd04 | textbox | Print Name:
123c6b39-c0f8-500b-a3f2-4dad7ed96bba | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 04.09 - Subgrade | itp | 04.09 - Subgrade |  | 96bf7402-7b72-4bd4-9ee8-68964f5c61e4
| section | Details
| checkpoint | CUTTINGS: Tests conducted in accordance with MRTS04 Cl 18.3.3.2
19bd145b-c7d7-5133-b12b-cbbd33d1dabc | note | Acceptance Criteria & Frequency (Project Specific) - RDD
141dcb91-f52c-5d29-aa87-8072469e895a | note | Check Item - Check Item
603f4d6d-f4da-5e1c-bfbb-4ffa45c418fd | note | Reference - MRTS04 Cl 18.3.3.2
| checkpoint | Work stopped when excavation has reached sugrade level. Contractor shall carry out the requirements of the relevant provisions of Clause 13.3.2.1
3fe55482-0233-5032-9c91-21b0167ab220 | textbox | Specified Subgrade Treatement (A-K):
e1a5011f-9546-5137-aa0d-798ecce29b38 | note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 Table 15.3-A, Table 15.3-B
ca34f9fb-a911-56dd-978b-5ddec793522b | note | Check Item - Hold Point 8
ee931255-81fa-57ae-8737-3e86583e3c46 | note | Reference - MRTS04 Cl13.3.2.1 Cl18.3.3
| signoff | HOLD POINT
| checkpoint | General fill material used for construction of subgrade where embankment or cutting treatment using general fill, if used in road embankments must comply with Cl 14.2.4
29616f32-8814-5ccd-8962-bb97882ef7a3 | note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 (Embankment ITP or Related Lot)
99d16553-7aef-5472-85a3-51056aa70613 | note | Check Item - Check Item
ce8fb2f3-659b-5fde-9523-4658de9c282d | note | Reference - MRTS04 Cl 18.2.1
| checkpoint | Unbound pavement material shall conform with the requirements of MRTS05 Unbound Pavements and shall be at least of the subtype specified in Clause 12.1 of Annexure MRTS04.1, or where no such subtype is specified, at least subtype 2.4.
e76f8b86-c1d8-50fc-ac91-c19c7a748835 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4067c77a-bb48-5e94-99b2-6c665f099dfb | note | Check Item - Check Item
88a118a7-7da4-5f76-bbf4-7e2705714d2d | note | Reference - MRTS04 Cl 18.2.2
| checkpoint | Quarry Registration Certificate submitted to Administrator 7 days prior to sourcing high permeability drainage materials.
a9883265-59a6-50f7-8b75-7410c7699f6a | note | Acceptance Criteria & Frequency (Project Specific) - Written
da8f7f41-c505-57a2-a0a1-f52e307dc047 | note | Check Item - Milestone
66e223ff-0c0d-53c4-b63f-5e2504ece1ab | note | Reference - MRTS04 Cl18.2.4.1
| checkpoint | A mix design shall be submitted atleast 14 days prior to commencement of subgrade stabilisation
557cfc90-081f-5c07-9b84-04a11ada5841 | note | Acceptance Criteria & Frequency (Project Specific) - Written
77fdad23-38ce-51af-8205-85e91a9036b1 | note | Check Item - Hold Point 11
71f1e0ef-4748-50fd-89fd-e18609fa93c7 | note | Reference - Cl18.2.5.4
| signoff | HOLD POINT
| checkpoint | Subgrade and underlying work tested and conforming prior to placement of pavement.
0d6c4e77-81ee-51b0-9bf0-e2e18371f7d3 | note | Acceptance Criteria & Frequency (Project Specific) - ITP
1a652693-6024-5183-bd09-4fb8585e1ce9 | note | Check Item - Hold Point 12
872e0555-6650-5972-930c-1bfaf0224f1e | note | Reference - MRTS04 Cl18.3.1
| signoff | HOLD POINT
| checkpoint | Subgrade material provides a stable dense surface displaying no vertical movement under proof roll
df7df442-5413-59bb-896e-4ec5a15dc3b7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Delfection, Continuous
83c0e495-d4ec-5c9f-b8b3-83fd79c1d674 | note | Check Item - Witness Point 8
2064f7bb-e90a-5e65-a104-d4e28732dba7 | note | Reference - Cl18.3.2
| checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
51cf57ec-7a92-50c2-bb01-06302805dc2c | note | Acceptance Criteria & Frequency (Project Specific) - Visual, Tolerances: Table 6.3.1, Subgrade (individual results) = +25mm, Subgrade (average) = +10mm
478254b7-8113-5245-9448-ed559aa78d75 | note | Check Item - Check Item
d0658ca1-6912-5190-b639-b72cb466867f | note | Reference - Cl 18.3.3.1
| checkpoint | Quality Verification Requirements Test Method
ccf1a8d2-f1fe-5818-a121-ffd210f82a53 | note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
c0e1614b-15df-5b10-99c8-eb30b1112967 | note | Check Item - Check Item
f0146b64-38a8-5b7f-a042-ec1e1c1fc656 | note | Reference - Table A.2
| checkpoint | Compaction/Moisture Ratio: AS1289.5.4.1 or AS1289.5.7.1
00437d13-0f4d-5c3c-b1f0-19392a297c2e | note | Acceptance Criteria & Frequency (Project Specific) - 2000m2, 1 per 500m2 (per layer), 4 per lot
7229f78d-1e2b-5897-aa03-2bdf6ae386e1 | note | Check Item - Check Item
67c03909-22dd-58ec-a031-e9a4977feed7 | note | Reference - MRTS04 Table A.2 No. 2.11
| checkpoint | Grading (AS1289.3.6.1), PI (AS1289.3.3.1 or AS1289.3.3.2), WPI (Q252)
63708258-32bd-57e0-920d-38f8c88d4f17 | note | Acceptance Criteria & Frequency (Project Specific) - 2000m2, 1 per 1000m2 (per layer), 2 per lot
506b74a3-85d3-5e8b-9e97-e5cbbce34438 | note | Check Item - Check Item
1cbc3687-849e-5ee2-b4bb-84eb3e32e506 | note | Reference - MRTS04 Table A.2 No. 2.11
| checkpoint | Geometrics, Horizontal Position
2ad76394-3ada-5d99-aa57-0a965ca586c3 | note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
266a1b1f-fd2e-541e-ae8a-9a28c21346e2 | note | Check Item - Check Item
a3e9e289-b62b-5167-90b3-18bbdf653ab4 | note | Reference - MRTS04 Table A.2
| checkpoint | Geometrics, Vertical Level
e3fc6fcf-f556-56ab-abe5-aa0e208fd8de | note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
c0bd772f-f5c9-5f06-8ace-56cfb0b1c772 | note | Check Item - Check Item
b9a1a84a-48bb-51e3-82ba-c46783ea0cd8 | note | Reference - MRTS04 Table A.2
| checkpoint | Geometrics, Deviation from a straight edge < 25mm
1eb75ee9-d9d7-5c6f-86a1-84064c19535b | note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
b0c955e1-48b8-5935-9dbf-1bd7abd1e7c4 | note | Check Item - Check Item
766d459e-c2e1-5406-8669-0dcb9b8863a5 | note | Reference - MRTS04 Cl 6.3.2
| checkpoint | Final Verification
457757f1-b031-5023-9926-b7aa1431524b | note | Project Manager Verify that the Above has been Constructed according to Specification
e8121250-b810-5a59-b5df-8fe3dde7b1ec | textbox | Print Name:
134bba23-836b-5f05-b6df-fe3a76a93a4d | date | Date:
26506228-8c96-5866-a48a-0c58781674f4 | note | Client Verify that the Above has been Constructed according to Specification
c7d877ed-0a24-51dc-b067-f0fae6816bc8 | textbox | Print Name:
684354e9-ce31-55d9-b222-b894bc1c96c4 | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 05.01 - Placement of Unbound Pavement | itp | 05.01 - Placement of Unbound Pavement |  | fd0d82a7-67b5-444c-a1ef-4ab138b77c88
| section | Details
| checkpoint | Pavement layers shall be constructed by either using a paver or grader, unless spceific plant is specified within Clause 3.1.1. of MRTS05.1
deaa7210-bc3a-5312-b039-212226d26950 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b7ce9022-6884-5f65-b936-aebf2f49129e | note | Check Item - Check Item
b00ef6d6-97de-577b-84b7-2157adcd4a34 | note | Reference - MRTS05 Cl8.3.1.1.3
| checkpoint | If specified in Clause 3.1.2 of MRTS05.1, Intelligent Construction (IC) rollers shall be used to compact unbound material.
8a70888f-d92a-5eee-873d-595a5ec8648e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9f88df1e-0d95-5cbd-8f22-a57a1a3e9d37 | note | Check Item - Check Item
24035012-f8d6-5303-807d-a820b89e0dcb | note | Reference - MRTS05 Cl8.3.1.3
| checkpoint | Primary Geometric Tolerances, Layer Thickness between 75mm and 250mm
0d7db287-b7dd-575e-81da-4fb75be8978d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2ec4be13-c925-5b5f-845d-9f8f07bcc7c8 | note | Check Item - Check Item
2aac9f6a-9f2d-5bf9-bee0-70a6a0379a8e | note | Reference - MRTS05 Cl8.3.3
| checkpoint | Materials not incorporated into the works unless it conforms with the requirements of MRTS05.
1d0be8dd-d262-5765-82c7-c36046ee9ccf | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9610028d-67d4-50a3-b3d8-d7af8ea912d9 | note | Check Item - Hold Point 5
39a70ecf-72dc-54cf-87a3-632823833479 | note | Reference - MRTS05 Cl9.1
| signoff | HOLD POINT
| checkpoint | Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by construction equipment nominated
a8e199ea-535c-5a45-bd4e-e4673edd1cd5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
40d8e5da-d404-56da-bea0-c5aee4f5bd5a | note | Check Item - Witness Point 2
0f5926c0-bca5-55ae-8164-c52891604441 | note | Reference - MRTS05 Cl9.4.7
| checkpoint | No Layer of Pavement shall be covered by a subsequent layer of pavement or by surfacing until all testing has been completed and the layer has been presented to the administrator for permission to proceed
ca290218-d348-513b-b740-f752ed1d0c76 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
70b6c975-96ae-5f42-935c-ff951575d081 | note | Check Item - Hold Point 6
98eb0b6a-e358-5ce2-9229-b85f96897aaf | note | Reference - MRTS05 C9.5.1
| signoff | HOLD POINT
| checkpoint | Construction Testing Requirements: Test Method
f11a2938-7589-5bf6-9292-f6aa72f2315b | note | Acceptance Criteria & Frequency (Project Specific) - Min. Testing Frequency, Min. No. of Tests
1062a243-7f6c-5043-919d-987ee2f41eed | note | Check Item - MRTS05
6cd8bb2b-58f1-573c-b103-3cf0eead54bf | note | Reference - Table A3
| checkpoint | Segregation: Q103A
eaf42e0d-3e77-570b-b025-5f640a1f97a1 | note | Acceptance Criteria & Frequency (Project Specific) - 1 per lot
68a04b93-e33d-5e5b-b071-ab14c4ac2a3e | note | Check Item - Check Item
56c990eb-4b77-57ee-b334-08da24f9b5a5 | note | Reference - MRTS05 Cl. 8.3.4.1
| checkpoint | Degree of Saturation: Q146, Type 2: 65%
cf557ced-778d-5438-93f8-686a4961a136 | note | Acceptance Criteria & Frequency (Project Specific) - 1 per 500m2, 4 per lot
66848798-4e40-5394-b841-7b9dca14c197 | note | Check Item - Check Item
ec69d6c3-f0a9-5c21-b75d-3d18af009fa5 | note | Reference - MRTS05 Cl. 8.3.4.1
| checkpoint | Compaction: Q140A, C.V. of RDD >= 102% for all Type 1 Materials, C.V of RDD >= 100% for Type 2/3/4 Materials
d82ddf0f-43bc-5840-b149-8136924d85f7 | note | Acceptance Criteria & Frequency (Project Specific) - 1 per 500m2, 4 per lot
973b3662-780a-58ef-99f2-5c0faaf2df2e | note | Check Item - Check Item
a7abaef8-71cc-5dcc-9732-9e73a35be5b1 | note | Reference - MRTS05 Cl. 8.4.3
| checkpoint | Vertical Position: Survey +/- 15mm
752a945c-a385-55a5-b125-576947b96f9f | note | Acceptance Criteria & Frequency (Project Specific) - 1 per 20 linear meter
92466b47-dbf8-5411-b64d-1f92931dc66d | note | Check Item - Check Item
b5ed30d8-ebfa-5475-b1f0-cf044138e5c6 | note | Reference - MRTS05 Table 8.4.4.3
| checkpoint | Deviation from a Straight Edge: Q712, Types 2, 3 & 4 materials: 5mm
a4d06aae-faab-5132-bdee-3dd428e4b950 | note | Acceptance Criteria & Frequency (Project Specific) - 1 per 20 linear meter
f6e5528b-410a-5b01-a373-309c79897ac0 | note | Check Item - Check Item
4c6ff201-2359-544f-8943-49dbc0d1c7a8 | note | Reference - MRTS05 Table 8.4.5
| checkpoint | Road Roughness: Q708B, Q708C & Q708D, Rs max. value: 2.31 (m/km)
326b33be-669f-5b2d-8546-977e13aac1bf | note | Acceptance Criteria & Frequency (Project Specific) - As per Clause 9.4.10, Greater than 100m less than 500mm
5ce89724-0dbe-57cc-8bea-31fcd4bfc627 | note | Check Item - Check Item
07b14df6-0174-55f8-8eba-069035eaffc2 | note | Reference - MRTS05 Table 8.4.6
| checkpoint | For layers to be covered by a sprayed bituminous treatment, the surface shall have a maximum ball penetration of 3mm.
7b55c03c-5465-563c-9f9b-73a39836857f | note | Acceptance Criteria & Frequency (Project Specific) - 5 test chainages per lot
ed1c7847-bd42-5ffa-b8c9-fdb36290c447 | note | Check Item - Check Item
4d47e480-2ee8-558f-9f21-f1f649b166c6 | note | Reference - MRTS05 Table 8.4.7
| checkpoint | Final Verification
356a0f26-face-5f31-8fbc-69113b07d7cc | note | Project Manager Verify that the Above has been Constructed according to Specification
2f65dfc3-444c-51ce-8739-ecc83f0ac922 | textbox | Print Name:
098100ee-4ba1-5a97-99a4-35578004460c | date | Date:
fdcb0872-5e22-5a54-aa16-1ab6ba742773 | note | Client Verify that the Above has been Constructed according to Specification
9f0eed84-1589-5f27-9a96-74507b4db0aa | textbox | Print Name:
bc825b16-d396-5141-ba0c-5c0dea1f307e | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 05.02 - Supply of Unbound Material | itp | 05.02 - Supply of Unbound Material |  | e54a55de-9ec8-4148-956c-fb4fbc60a49e
| section | Details
| checkpoint | No unbound pavement works shall commence until all relevant construction procedures have been accepted by the Administrator.
0f3b3c4d-5371-57c3-8c5d-c20261c2d541 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3a2d7fd5-0c84-5258-a718-6e417aa5ac09 | note | Check Item - Hold Point 1
6718de12-5506-57c7-b445-f0a7324e1344 | note | Reference - MRTS05 Cl. 5.2.1
| signoff | HOLD POINT
| checkpoint | The aggregate production procedures shall be submitted to the Administrator at least 7 days prior to commencement of material production
bf404175-0e6e-587d-be47-064cb2566c36 | note | Check Item - Milestone
2b27f0f2-e995-5df6-9153-f7cab1d73cdb | note | Reference - MRTS05 Cl. 5.2.2
| checkpoint | The unbound pavement construction procedure shall be submitted to the Administrator at least 14 days prior to the commencement of unbound pavement works
db4d7364-a91d-5301-8b71-12f52879f444 | note | Check Item - Milestone
6a37b94a-0e1b-5b2a-afa8-16ee43aca23d | note | Reference - MRTS05 Cl. 5.2.3
| checkpoint | The current TMR Quarry Registration Certificates for Type 1, 2 and 3 materials, shall be submitted to the Administrator at least 7 days before a material's supply or use.
6de999da-4b8b-5173-811d-3dffe40d9bce | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0f71acbd-0abc-570b-9a44-cc8e8d5f80a1 | note | Check Item - Milestone
fbda2f9b-d1f8-57a3-a03a-56069389443a | note | Reference - MRTS05 Cl6
| checkpoint | Material from a quarry shall not be used until the quarry has been approved by the administrator.
64130b6d-f530-504a-8582-b1f7be225192 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1c63d2dc-d679-56a4-bc38-dcd44aba5dc5 | note | Check Item - Hold Point 2
53f851f4-1ec4-5162-8534-dd5a857b1c58 | note | Reference - MRTS05 Cl6.1
| signoff | HOLD POINT
| checkpoint | Type 1, Type 2, Type 3 and Type 4 materials to comply with the respective material properties from clauses 7.1 to 7.4.
b1d6f35d-f081-5fbb-a9aa-14e20079a357 | note | Check Item - Check Item
f12d49ae-0f43-524d-a32e-6033a311238d | note | Reference - MRTS05 Cl. 7.1 - Cl. 7.4
| checkpoint | All pavement material incorporated into the finished pavement shall be free from sticks, organic matter, clay lumps and other deleterious material or contamination.
d83330cd-2778-5318-9a3f-2b5db7680c7d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2ace1c9c-d29d-5b9c-b956-eb89f42d1c87 | note | Check Item - Check Item
7d3c2fee-8a8a-5ea0-b40e-aeab5c6cd2e1 | note | Reference - MRTS05 Cl7.5
| checkpoint | Stockpiles located as specified in MRTS05.01 Cl. 2.4 or if not specified, on clear, even, firm, well drained ground where it can be clearly identified with individual stockpiles separated by at least 2m.
647af14d-d7b6-5500-85f8-251567912145 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d3028e9d-2494-511b-85be-5695dc9fd135 | note | Check Item - Check Item
67970b36-7ffb-5d05-945b-1e2d233fd604 | note | Reference - MRTS05 Cl7.7
| checkpoint | Separate stockpiles for each production lot, or stockpiles incrementally created from a single material subtype with each added lot tested and approved prior to subsequent lots being added.
0ed821de-a892-5563-9e86-44caefd3b0bd | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2fbc264c-9e9c-5462-bfd9-c65ffde1f9be | note | Check Item - Check Item
aabc51dd-21cd-596c-87cd-f30885ab7918 | note | Reference - MRTS05 Cl7.7
| checkpoint | Final Verification
3396590e-dfa8-5044-a5b8-264c2b218cb1 | note | Project Manager Verify that the Above has been Constructed according to Specification
ed37e4bb-5d92-5b56-9121-00c91c09525a | textbox | Print Name:
642fbca5-09c6-5195-b252-782c16faadf2 | date | Date:
e694c48f-cab6-5778-9880-e8b2941a3fa2 | note | Client Verify that the Above has been Constructed according to Specification
ba39020a-88c1-5a2e-8a4e-4293230330f2 | textbox | Print Name:
a41ad978-90b2-5d01-8a85-20d516bd6f9c | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 11.00 - Sealing Works | itp | 11.00 - Sealing Works |  | 95008902-fbc1-48a4-8d94-4740a6bb591e
| section | Details
| checkpoint | Permission to use construction procedures
34c57bfb-c8eb-5f0d-bdb3-4be546da52d0 | note | Acceptance Criteria & Frequency (Project Specific) - Written
9b786937-6aa5-57cd-bae6-f7d2e1f2c4c5 | note | Check Item - Hold Point 1
9cff0ce1-14b4-54b0-987b-23562ed0ab05 | note | Reference - MRTS11 CL5.2
| signoff | HOLD POINT
| checkpoint | Construction procedures and ITP submitted to the Administrator seven days prior to use
cf902488-d638-522b-b9b8-2245244de187 | note | Acceptance Criteria & Frequency (Project Specific) - Written
8ac0da5c-c7df-555e-88f1-bd1e8856f70c | note | Check Item - Milestone
86e5772a-f71a-59a0-9a51-8e886f5d2c63 | note | Reference - MRTS11 CL5.2
| checkpoint | The Contractor shall notify the Administrator of the binder class substitution not less than 14 days prior to the commencement of spraying
3122d275-1059-5634-916a-11936ec59191 | note | Acceptance Criteria & Frequency (Project Specific) - Written
4700265e-16ab-5216-8588-1e523a1e4d97 | note | Check Item - Milestone
001979e9-304a-51f5-ad20-b8f5e9b0134b | note | Reference - MRTS11 CL6.1.2
| checkpoint | The Contractor shall submit the seal design report to the Administrator at least seven days prior to commencement of spraying operations.
57dd841b-7a58-5c0d-8592-84447d06627e | note | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Contractor
000ed381-9499-5012-b2bc-f71721684fb9 | note | Check Item - Milestone
e52e5579-beec-5cc1-a284-a14d664c3a4a | note | Reference - MRTS11 Cl. 6.3.2 & MRTS11.1 Cl. 3.2
| checkpoint | Spraying operations shall not commence until the Administrator has approved the seal design report
f9607cd4-bccc-5497-8729-bc4c42ef8e0f | note | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Contractor
9d3c7c22-50ea-5d39-a609-8aae9df0ea4f | note | Check Item - Hold Point 3
44181601-a93a-5f51-b6d5-6abc80eecb9e | note | Reference - MRTS11 Cl. 6.3.2
| signoff | HOLD POINT
| checkpoint | Cover aggregate is covered by a light plastic until it's implementation in the works
24456794-57a4-55af-892c-a68ba1c4f840 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
57eac0cc-274b-5934-ba24-8870e4b5bc16 | note | Check Item - Witness Point 1
e5bc9e29-06b2-5851-999a-aed31d8a421a | note | Reference - MRTS11 CL8.2
| checkpoint | Binder storage temperature measured and recordered at delivery to site
7df536f3-b1fc-571f-a2c6-c0a588ce8e63 | note | Acceptance Criteria & Frequency (Project Specific) - See Table 12.5 of MRTS11
679ffe94-dc7b-585a-8f90-3967ffa93a94 | note | Check Item - Witness Point 2
5899d001-029d-5ecb-ae6f-4fac20d612d8 | note | Reference - MRTS11 CL8.3.1
| checkpoint | If binder temperature low, raise to within the spraying temperature range as per Table 12.5. Heating shall be strictly observed.
fbdfaddf-cc34-56af-9da6-703a7ecff6c2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2b181acf-6106-5411-a4c8-96d7e5466c62 | note | Check Item - Witness Point 3
cf09f6a2-3333-5e18-af1f-d49e86e9774e | note | Reference - MRTS11 CL8.3.2
| checkpoint | Three days prior to sealing operation, the Contractor shall submit details of all plant to be used.
d6329ad4-a82e-541b-b76c-46ecff17f235 | note | Acceptance Criteria & Frequency (Project Specific) - As per MRTS11.1 Annexure
432eee18-bd37-5029-ac45-bb3faa954664 | note | Check Item - Hold Point 4
28d4d837-770a-5c2f-a27a-8cec664c3bdf | note | Reference - MRTS11 CL9.0
| signoff | HOLD POINT
| checkpoint | Ball penetration test results < 3mm unless approved by the administrator
4c99736e-0e5f-59b5-92cf-2c28d1cb64d3 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9ec58de8-cfed-5051-80dd-19fb37d1ef74 | note | Check Item - Hold Point 5
66150adf-5623-5075-a930-3fc25682e8d1 | note | Reference - MRTS11 CL10.1.2
| signoff | HOLD POINT
| checkpoint | Ensure enough cover aggregate available on site to complete works
b7ac9534-1f4e-5060-9c81-9537b17d0550 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3a6ce161-83e6-5a7b-816f-cc6e7cc4701f | note | Check Item - Hold Point 6
3af36c27-9f9d-5b0c-a95b-5544eff07c3d | note | Reference - MRTS11 CL11.1
| signoff | HOLD POINT
| checkpoint | Pavement Temperature above minimum specified
4af99205-2d0b-5b29-8787-5c4e44a93230 | note | Acceptance Criteria & Frequency (Project Specific) - Primes: >/=10 degrees
885d3700-6a72-5737-828a-f95fd92b0248 | note | ○ AMC4 to AMC6 Cutback Bitumen: >/=15
429d1fe3-a91e-52a3-ac45-73a0fd3d738f | note | ○ AMC7 Cutback Bitumen, Bitumen Class 170, 240 & 320, multigrade bitumen, crumb rubber binders : >/=20
b398f72b-7550-5a77-bf82-43f4fe54d31d | note | ○ Polymer binder: >/=25
000bd06e-e4f3-54a5-8bf4-31c9888027e7 | note | Check Item - Witness Point 4
eae0ade8-578e-5af0-aa44-9e458e3800df | note | Reference - MRTS11 CL11.2
| checkpoint | Spraying shall only take place under the weather conditions permitted as per clause 11.3 and clause 6.3 of MRTS11.1. Where additional measures are required to minimise the risk of early life stripping, the Contractor shall submit procedures to the Administrator for review 14 days prior to commencement of spraying. Spraying shall not commence until these procedures have been deemed suitable.
73264055-1f62-5907-9416-4d45f6361c8e | note | Acceptance Criteria & Frequency (Project Specific) - Written
736a5c08-ecc3-5d6f-b49c-b1fd0fd7e1dd | note | Check Item - Hold Point 7
69a0dbdc-504b-52de-bae1-e873636d6575 | note | Reference - MRTS11 CL11.3
| signoff | HOLD POINT
| checkpoint | Current QLD sprayer certificate to be sighted
31fc5ffd-1a30-50e6-88a0-15d472213ab9 | note | Acceptance Criteria & Frequency (Project Specific) - Current Certificate
b3e8b93f-acf2-5b5e-a400-df2b4615045d | note | Check Item - Witness Point 5
d5edde54-c0b0-581e-ac3b-c477d425d6a4 | note | Reference - MRTS11 CL12.4
| checkpoint | Nomination and recording of cutting requirements where required
cee116dd-0d82-550c-a7db-c115f2c5a6dd | note | Acceptance Criteria & Frequency (Project Specific) - Visual
733a4212-9f90-5302-ada9-6012f7056322 | note | Check Item - Witness Point 6
2147f911-b746-5677-901b-55640ef832b9 | note | Reference - MRTS11 CL12.7
| checkpoint | Wet cover aggregate containing free surface water shall not be loaded in the aggregate spreader
268095b2-957f-58f7-ab3f-d3b35a6faaa4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e69bbfef-de22-5020-8f51-d7b33fd70147 | note | Check Item - Witness Point 7
198f0d08-e69b-5005-a35d-bdbcce00f5f1 | note | Reference - MRTS11 CL14.1
| checkpoint | Prior to opening to traffic the requirements of Clause 14.8 shall be met.
9ac67d18-80bd-567a-be54-dccb3dbfb20b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
06e68cdd-8bdd-5bdb-9f88-31ff67f91807 | note | Check Item - Hold Point 8
98c1b84f-d8d3-5db2-9ff4-9ec1756fc70c | note | Reference - MRTS11 CL14.8
| signoff | HOLD POINT
| checkpoint | Quality Verification Requirements
2e2b9afd-9c58-5dd8-8386-bcfa17441e9d | note | Acceptance Criteria & Frequency (Project Specific) - Testing Frequency
85eb2007-09a8-5e79-a9ce-4a6713d3a4a1 | note | Check Item - MRTS11
ff5357f0-585a-5665-866a-c8cc52e4d679 | note | Reference - Table 6.2
| checkpoint | Particle Size Distribution, Flakiness Index, Avg. Least Dimension
83985b0d-9a55-554a-b66d-d2a077c10201 | note | Acceptance Criteria & Frequency (Project Specific) - One test per aggregate type, nominal size & source
d9b36e84-009d-52d2-8bde-c2d64a2b2b49 | note | ○ Repeat tests every 1000t
5e286b98-8881-570e-8bdc-1776a926a639 | note | Check Item - Check Item
d780eccd-ca72-5929-b13c-718771a3d8d6 | note | Reference - MRTS11 Table 6.2
| checkpoint | Texture Depth: In and between the wheelpaths - that is, 3 tests at each test chainage per direction
81ceaa65-cb98-512c-9c03-a2e0ce978fe7 | note | Acceptance Criteria & Frequency (Project Specific) - Lesser of:
3dd0a766-d1a7-59a7-a4f5-926554240f21 | note | ○ Every 400m
c4517a21-ffbe-5b2d-afe1-6a05bb257f88 | note | ○ 3 test chainages per homogenous section
3ae05ec2-f2c8-519a-bc74-64664c650374 | note | Check Item - Check Item
eee66d56-6078-5a1d-8bfa-c529a342a27f | note | Reference - MRTS11 Table 6.2
| checkpoint | Ball Penetration: Inner and outer wheelpaths - 2 tests at each test chainage per direction
aa45023d-26a3-5e8a-9b1b-c8bcda86d5e1 | note | Acceptance Criteria & Frequency (Project Specific) - 5 test chainages per homogenous section
6fbe76d5-d709-5307-9821-97a523df2e27 | note | Check Item - Check Item
c2281311-962f-56a4-9f52-1af2e0820b82 | note | Reference - MRTS11 Table 6.2
| checkpoint | Spreading: Each spreader shall be tested in accordance with the Field Spread Rate Cover Aggregate Test (Q711A)
e8773050-2034-55d9-8ae5-73f43fdad997 | note | Acceptance Criteria & Frequency (Project Specific) - One test per spreader per day, Tolerance: ±10%
38549940-0e61-5a1a-939b-5b6ee424c873 | note | Check Item - Check Item
19439f37-0ebb-53ee-9970-4f8399d3dc66 | note | Reference - MRTS11 Cl. 14.4
| checkpoint | Sampling of Bitumen (two x 1L samples) shall be undertaken before or during transfer of bitumen to sprayers.
ab842bce-c637-594d-bed0-54977e5ed9fd | note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size
770d2e12-817c-5a6a-81b3-82c1fc19d28b | note | ○ Asphalt = Each new tank
dbf01036-fff1-541f-83bb-8f036fd4e204 | note | ○ Sealing = 150 tonnes
5a82d081-c1b9-5d53-b3cf-5c187e3ab263 | note | Check Item - Witness Point
4fb7d805-e487-5d83-b3db-482a0a9d8c26 | note | Reference - MRTS17 Cl. 9.3.1
| checkpoint | The minimum frequencies for sampling and testings in regards to the cutter oil and flux oil shall be in accordance with Table 9.2 of MRTS19
a38d2d5c-28d5-5adc-8e5a-b28f5c06418b | note | Acceptance Criteria & Frequency (Project Specific) - Refer to Table 9.2
5ff3411f-d3f3-53c8-b413-a4356d7f5318 | note | Check Item - Check Item
c6a6f6ae-7518-53dd-9620-11a4b487e0bb | note | Reference - MRTS19 Cl. 9.2
| checkpoint | The minimum frequencies for sampling and testings in regards to cutback bitumen shall be in accordance with Table 9.3 of MRTS20
ba5788cd-6c57-5b38-99ef-2b46dc36762a | note | Acceptance Criteria & Frequency (Project Specific) - Refer to Table 9.3
cd33ee5f-4616-52a7-8d74-1ad1a9569f34 | note | Check Item - Check Item
8a2a65d6-c724-5cf1-a9a9-1f1e6ff627a3 | note | Reference - MRTS20 Cl. 9.3
| checkpoint | Final Verification
0765fe03-4344-574c-87bd-d2772a31f25d | note | Project Manager Verify that the Above has been Constructed according to Specification
f6f416c7-c98e-5d5d-8e23-6e5110ad44b2 | textbox | Print Name:
92c7e75a-d225-50f1-a4d1-f20e518de760 | date | Date:
8d12867b-d937-5e78-aba7-cbd36b9a9883 | note | Client Verify that the Above has been Constructed according to Specification
4c1f7117-229e-58ff-bdf4-ff74a00839d3 | textbox | Print Name:
71dea2a9-0807-5c10-b84a-56f75229a843 | date | Date:
| signoff | Sign ITP
| checklist | 14.08 - Demolition, Removal, Salvage & Re-erection of Road Furniture | itp | 14.08 - Demolition, Removal, Salvage & Re-erection of Road Furniture |  | 23fb40a4-43f8-47b3-8153-a69b54a4cdc5
| section | Details
| checkpoint | The items of road furniture to be demolished and disposed of are listed in Clause 3 of MRTS14.1
934d5927-2f1a-5bdd-98ee-18ec02e0da53 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f740b2d5-7e95-5077-82ab-eb3a6757e470 | note | Check Item - Check Item
0ec4eaaf-6674-5e64-afed-7144ec3b1019 | note | Reference - MRTS14 Cl 7.2
| checkpoint | Seven days prior to commencement, the Contractor shall submit a schedule of items to be salvaged in accordance with the design documentation.
5d0350cb-64a4-51c9-a69b-3c5a7540c5af | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3eb1173b-ff7b-536f-b9e6-6a0985f296ab | note | Check Item - Milestone
d7af47ff-f395-5cef-843d-c823da13d311 | note | Reference - MRTS14 Cl 8.2
| checkpoint | Dismantling and removal shall not commence until expiration of the seven day period.
0eabb5ef-3cdb-5452-929e-9466bd85be03 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7f40a797-52b3-532e-951f-34513889bc69 | note | Check Item - Hold Point 1
95c906f3-668e-5d75-a344-d43239025f49 | note | Reference - MRTS14 Cl 8.2
| signoff | HOLD POINT
| checkpoint | Salvaged materials shall be transported and stored in accordance with Cluase 1.2 of MRTS14.1
ab5e612f-b8ab-52dc-aeee-1f95e54061b8 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
fdee87da-4576-57fd-8a63-c8571ae202c1 | note | Check Item - Check Item
14cd4c2c-1221-59f5-8bfb-62e4d953a225 | note | Reference - MRTS14 Cl 8.4
| checkpoint | Seven days prior to commencement, the Contractor shall submit a schedule of items to be dismantled for re-erection in accordance with the design documentation.
10857995-b379-5e16-8480-2a4a470da024 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
bff28009-c84a-5d85-8f13-6aee8da96447 | note | Check Item - Milestone
d3612d6a-9fee-5bf1-ab36-b19286a6500b | note | Reference - MRTS14 Cl 9.2
| checkpoint | Dismantling and removal shall not commence until expiration of the seven day period.
b85ee328-1231-5e32-8110-38dd071e6fb7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e6d3e831-0466-511e-8dd1-5c414290c972 | note | Check Item - Hold Point 2
0e5f53dd-299e-5800-969d-4ce11c7e1044 | note | Reference - MRTS14 Cl 9.2
| signoff | HOLD POINT
| checkpoint | Final Verification
a8102be3-4045-5dfa-8a66-d19ac221fa68 | note | Project Manager Verify that the Above has been Constructed according to Specification
eabc9c22-f8b3-58ea-bb09-0e65650f4d68 | textbox | Print Name:
01695b02-01f6-5cb7-b18a-ecb899d19055 | date | Date:
a68ed5b8-ed8a-5333-ad9a-2f36bcd0095e | note | Client Verify that the Above has been Constructed according to Specification
32d0784f-386e-5443-9cb0-db76ba0cab40 | textbox | Print Name:
0b67fd61-5871-5b0d-abe9-6c9f379a40e2 | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 14.20 - Installation of Steel beam Guardrail and End Treatments (Public Domain) | itp | 14.20 - Installation of Steel beam Guardrail and End Treatments (Public Domain) |  | e337bef9-4f73-4c16-850a-95b9b5d6ee8f
| section | Details
| checkpoint | Manufacture of steel beam guardrail post, panel components and end treatments are maufactured by an approved manufacturer
f6b610f9-0966-5f5a-ae99-42e8c1a64f83 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
63044201-a903-5369-9f3a-2496410c6092 | note | Check Item - Check Item
3dc792a8-082d-5391-aec9-2e71dfa07a4c | note | Reference - MRTS14 Cl20.2.1
| checkpoint | Supply of steel beam guardrail post, panel components and end treatments are supplied by an approved supplier
f48ccd54-f2ef-5689-bd6c-3050698b5e6a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f1548cb0-3d57-5926-98c1-c0681489fb3f | note | Check Item - Check Item
49b8e9b7-e3df-5877-b4e6-46dd271bc918 | note | Reference - MRTS14 Cl20.3.1
| checkpoint | All the steel manufacturer test certificates shall be supplied to the Administrator. The Administrator shall review and approve the certificates.
fe51a499-dc13-56e6-b225-40b9378bee65 | note | Acceptance Criteria & Frequency (Project Specific) - Written
fc611fca-bd26-5b6a-b04e-051b65cd8953 | note | Check Item - Hold Point 7
033ae46e-2d32-5c6b-8260-a088ae99ca32 | note | Reference - MRTS14 Cl. 20.4.5
| signoff | HOLD POINT
| checkpoint | If test certificates are not available, the Contractor shall submit to the Administrator for approval a proposal for selecting samples for testing.
437ae8fd-5dce-5d13-855b-bfca45043204 | note | Acceptance Criteria & Frequency (Project Specific) - Written
1278ade6-a26a-5498-9d94-4b0d965646b5 | note | Check Item - Witness Point 2
44fd806b-3a56-5d7e-80f8-bd26e8c1d894 | note | Reference - MRTS14 Cl. 20.4.5
| checkpoint | All projects are to be supplied with a min. two extra posts and panels from each batch. The Administrator shall randomly select from each batch two post and two panels for Audit testing.
30db1eed-89e9-56b0-b906-40d464dbec8f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4e7336c2-55ec-56d7-a3c0-11656b2ae53b | note | Check Item - Witness Point 3
39fdd05e-9e35-554e-aab9-1ab6d219c645 | note | Reference - MRTS14 Cl. 20.4.6.1
| checkpoint | Installation shall not commence until the Administrator has confirmed the materials tested match the material test certificates supplied.
47e0ff79-417a-51f1-9880-397f06f56b4f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9dffb41a-fbe9-5167-8f3d-9d18fb712da1 | note | Check Item - Hold Point 8
8eb9f6af-09a9-51fa-bcbb-e75876f44867 | note | Reference - MRTS14 Cl. 20.4.6.3
| signoff | HOLD POINT
| checkpoint | All welders must comply with the requirements of Clause 20.5.2 otherwise a TMR representative shall be present when macro samples are prepared to show conformorance
4094acad-6142-5c35-8b4f-8321f693ca7a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ee9323ed-ce18-5308-82db-494b2e5d4f2e | note | Check Item - Hold Point 9
ee7d930a-95e6-5f9a-aad1-c75d9ec85ad6 | note | Reference - MRTS14 Cl. 20.5.2
| signoff | HOLD POINT
| checkpoint | Steel Beam guardrail installed in the locations shown in the design documentation and in accordance with the Standard Drawings
50a00f52-61b6-586c-b801-e316563d3f39 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
62b9225e-6690-54ec-a2bf-f21ddfee24bb | note | Check Item - Check Item
205248b0-9220-5173-ac92-913ed38a1d6d | note | Reference - MRTS14 Cl20.6.1
| checkpoint | Steel Posts driven into ground except where posts are to be driven into asphalt, concrete or rock.
6b81d377-9465-5e06-a885-3c1ecceb6b11 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
665acc74-1eec-5ef7-8745-cbe0e26ddbbb | note | Check Item - Check Item
660b890b-0faa-5f6e-8cd2-4cabbbd1e98d | note | Reference - MRTS14 Cl20.6.2
| checkpoint | Where ground is asphalt, concrete or rock, a hole shall be excavated in accordane with Cl 20.6.2
9b35e87c-0627-5f1b-99b4-58d3a81d1d06 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
445aea16-59a4-58fd-bc73-718f862ee76b | note | Check Item - Check Item
60c65a37-263c-5ad4-9631-520abc121575 | note | Reference - MRTS14 Cl20.6.2
| checkpoint | Terminals installed as per the design documentation
c820ade2-485c-5edc-9b64-18831a4329d4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
06816669-cd80-5f09-8bfc-cf32a7bacafc | note | Check Item - Check Item
3dbb9325-b1a0-5e76-bbdc-29ffbfdf32cb | note | Reference - MRTS14 Cl20.6.3
| checkpoint | Delinerators installed on steel beam guardrail in accordance with the MUTCD Part 2
6ac7d116-196a-56c9-abc7-54b1217f745d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8225a87a-2c85-56ef-a05a-88b850081a35 | note | Check Item - Check Item
fad61ab9-b3e4-5647-a8e7-a603e3ec50f5 | note | Reference - MRTS14 Cl20.6.5
| checkpoint | Installed within Geometric Tolerances
5f847678-5f5c-584b-bf66-855806a08287 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c1c0695b-bbb0-520e-9884-c3128c573155 | note | Check Item - Check Item
91fa1dec-7f39-5047-a8c4-a44b26c79760 | note | Reference - MRTS14 Cl20.6.6
| checkpoint | Adminstrator accepts guardrail installation as per the design documentation
614a3ce5-5141-5558-9991-c1084e2e3af7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7ad4b991-8442-5b0b-adab-eeaa71ac9d81 | note | Check Item - Hold Point 10
4d9491b9-0426-5787-9cef-b6226fa029c3 | note | Reference - MRTS14 Cl 20.6.7
| signoff | HOLD POINT
| checkpoint | Final Verification
c73fcb8e-e1f9-5c10-a584-530ce48241dd | note | Project Manager Verify that the Above has been Constructed according to Specification
0091c788-f5f0-554c-9b60-324c5ab795ea | textbox | Print Name:
33202076-41ca-5d83-bfd2-7f32293f2bf0 | date | Date:
09ebb62a-56f6-5b77-bc58-6a86d95e2215 | note | Client Verify that the Above has been Constructed according to Specification
8d18e718-f5f0-5a13-aedd-793a3a7d346c | textbox | Print Name:
2c6ed2c0-ab5a-5a76-b784-a32bcd80d965 | date | Date:
| signoff | Sign ITP
| checklist | 14.21 - Installation of Steel beam Guardrail and End Treatments (Proprietary Systems) | itp | 14.21 - Installation of Steel beam Guardrail and End Treatments (Proprietary Systems) |  | f22d5cf1-2f5b-4d09-9c4c-8b336526789e
| section | Details
| checkpoint | Proprietary road safety barrier systems and/or end treatment shall be manufactured, fabricated and assembled in accordance with the design and specifications provided by the system and/or device designer.
20df078c-6d2e-5c55-a69d-5bdbc0f6deb0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0ef18643-4bb0-571a-9d9b-a39ea73bb898 | note | Check Item - Check Item
13e5b209-2ed2-5238-b8d7-f802ad27113a | note | Reference - MRTS14 Cl21.2
| checkpoint | The installer of proprietary road safety systems shall provide the required quality documentation in accordance with clause 21.2 to the Administrator.
2d281c8e-cb93-5042-b979-95a9dd7c652c | note | Acceptance Criteria & Frequency (Project Specific) - Written
d40a747b-2e62-5b80-802f-96736bcd0ee4 | note | Check Item - Hold Point
69332ffc-d05f-56d7-9191-994ae1dc424c | note | Reference - MRTS14 Cl21.2
| checkpoint | Proprietary barrier systems shall be installed as shown in and required by the design documentation and in accordance with the requirements of the installation manual.
350e214b-c57f-540a-bcf9-76c411812910 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
bdfb04be-78fb-565b-afdb-d3971d1dffc1 | note | Check Item - Check Item
b87999a3-1bd5-5e32-904e-7a365e451057 | note | Reference - MRTS14 Cl. 21.4.1
| checkpoint | Where the design of the system is provided by the Contractor, the design, installation drawings, specifications and evidence and conditions of acceptance for use on state-controlled roads in Queensland shall be provided to the Administrator prior to commencement of installation.
0e164b0f-bd40-5fca-ae73-9bdfef16929a | note | Acceptance Criteria & Frequency (Project Specific) - Written
1c33e034-3fd3-507b-a4a8-635f1c7cc4a0 | note | Check Item - Hold Point 12
72ffa523-723c-5f71-bf97-0ff37a05fec6 | note | Reference - MRTS14 Cl. 21.4.1
| signoff | HOLD POINT
| checkpoint | Delineation shall conform to the requirements of Clause 10.2.4 of MRTS14 and shall be installed in accordance with Part 2 of the MUTCD.
1e163d13-0bde-55ad-a7c6-60d2ad3a20a7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ae343970-3db5-5b42-a8cb-c35e2d50880c | note | Check Item - Check Item
bf295a62-641f-5e7b-a9da-627d278921f2 | note | Reference - MRTS14 Cl. 21.4.5
| checkpoint | Proprietary systems shall be installed in accordance with the tolerances specified by the supplier. Where not specified, the alignment shall not deviate from the design by more than 20mm and the height shall not deviate by more than 10mm from the design.
e238c433-be5c-5ba8-859a-682791371156 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8dd2ace8-b800-5bc7-9b50-adb6cf04ad57 | note | Check Item - Check Item
d845b0ca-3e70-51d5-926d-0f200589a700 | note | Reference - MRTS14 Cl. 21.4.6.2
| checkpoint | The quality records of proprietary systems shall include: - Evidence and conditions of acceptance for use on state-controlled roads in Queensland - Supplier's instructions or procedures for the installation and ongoing maintenance and repair - Details of the country of manufacture of all components - Quality documentation showing the supplied components are in accordance with the supplier's specification - A copy of the detailed design (where not provided by the Principal)
5d12ff49-0dfc-5c1f-8202-1debe94845e5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
812f3d44-1da2-51dc-bbee-4b00c08cf88c | note | Check Item - Check Item
363008db-b5c6-542e-be8f-eece9e94a33d | note | Reference - MRTS14 Cl. 21.4.7
| checkpoint | Final Verification
e5135aad-34c3-5dbf-bf36-8c5bdc617ab1 | note | Project Manager Verify that the Above has been Constructed according to Specification
15052c69-27a8-5fd1-b6b6-d76552de53e4 | textbox | Print Name:
4faf334c-6493-546b-8a72-9d0f4fed752e | date | Date:
0144f8aa-6a83-59a8-aa61-3863d5d00579 | note | Client Verify that the Above has been Constructed according to Specification
a4e1fca1-4f87-5b76-ac6b-4a72eecc9c1f | textbox | Print Name:
0366c016-46ff-51da-a787-5b576f36b6de | date | Date:
| signoff | Sign ITP
| checklist | 16.01 - Landscape and Revegetation | itp | 16.01 - Landscape and Revegetation |  | ce369170-ed86-41d4-8492-d1e7538ddfb8
| section | Soil Management Plan
| checkpoint | Soil Management Plan - assessed for suitability by the Administrator in accordance with the conditions of Clause 5.2.1 of MRTS16
edaaf223-a250-5309-859e-65cd584c99e9 | note | Acceptance Criteria & Frequency (Project Specific) - Written Acceptance
78dfd6ef-f24f-5f12-aa30-20bcb25ae95c | note | Check Item - Hold Point 1
2a655939-c3d0-5333-a745-5bdce33c2e6c | note | Reference - MRTS16 Cl 5.2.1
| signoff | HOLD POINT
| checkpoint | Where a Contractor proposes to water vegetation works with non-potable water a Non-Potable Water Management Plans shall be submmited and assessed for suitability by the Administrator.
48d9da6c-4de6-5616-b3cb-09fb650fee4e | note | Acceptance Criteria & Frequency (Project Specific) - Written Acceptance
9c9a8215-c9b1-572d-8dba-dbd601685c8c | note | Check Item - Hold Point 2
90806483-d530-5c9a-9ee5-2248d1e484e7 | note | Reference - MRTS16 Cl 5.2.2
| signoff | HOLD POINT
| checkpoint | Seed Supply Proposal submitted for determination as to its suitability by the Administrator, within 30 days of the date of Possession of Site.
acf9fbc3-ee8d-5ae4-b2db-72d74cb75483 | note | Acceptance Criteria & Frequency (Project Specific) - Written Acceptance
c4255825-ac52-5614-9c54-d3b3f5b2c468 | note | Check Item - Hold Point 3
c3225331-5d56-5072-af11-6e53a2b9fa3b | note | Reference - MRTS16 Cl 5.3.1
| signoff | HOLD POINT
| section | Materials
| checkpoint | Materials imported to site shall be free of prohibited or restricted biosecurity matter.
5d7dd4a6-be4c-5ef7-a81e-a57ffb2ad064 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
711714a2-eaa9-5be1-919d-f8d01ff390a1 | note | Check Item - Check Item
e225d669-506c-5847-a2d4-537e49799a1e | note | Reference - MRTS16 Cl 7
| checkpoint | Materials are stored to ensure no deterioration or contamination occurs
0acd1ce1-4a99-5b3c-bbb4-94692c2ff945 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b70f11e5-073f-51a3-9e72-66ec1c8f0e03 | note | Check Item - Check Item
af3466d6-e7d2-5fc3-8b91-7a777cdc9e8a | note | Reference - MRTS16 Cl 7
| checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
16238685-4255-5fa5-9d3a-f299fb3b4277 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
39f5e58e-0f07-5339-bb83-6c95df92d214 | note | Check Item - Check Item
9cb3b03d-fe2e-515a-a9e6-4c0a980576f9 | note | Reference - MRTS16 Cl 7
| checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
d2dd21e2-cb5f-57ca-b888-6849e3be9404 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
98397934-e652-54fc-abed-8e50ca474761 | note | Check Item - Check Item
c127f54c-b4ab-58a1-a06b-b10651559313 | note | Reference - MRTS16 Cl 8
| section | Weed Control
| checkpoint | Routine inspections of the site shall be undertaken to treat weeds as appropriate for their destruction prior to flowering/seeding. Weeds manually removed shall be disposed of off-site
3d1199e4-0056-5f2f-9c20-d205eeaabcc0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
494158f6-8481-5e11-b21c-cd4a4ff0ea3d | note | Check Item - Check Item
1553fa31-75dc-5f2c-a45a-81bb69049c50 | note | Reference - MRTS16.1 Cl 3.1.1
| section | Subsoil and Topsoil Amelioration
| checkpoint | Ground preparation works carried out within the drip line of retained vegetation, 300mm of paths, kerbs, road furniture or structures and in accordance with TMR Standard Drawings 1644 and 1646
197969fa-89a7-51c4-98ca-9533f6af1982 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9f867fae-7804-51fd-bd5f-c4eb5de279d3 | note | Check Item - Check Item
16940c9d-60d1-5989-8d3c-53ec4d39a598 | note | Reference - MRTS16 Cl 8.1 TMR SD 1644, TMR SD 1646
| checkpoint | Site is weed free prior to ground preparation operations
c9e7b00b-d308-5bbb-8063-8531e9bf8942 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c7b663df-f6f9-57bc-8a54-1bc1fc6b8e53 | note | Check Item - Witness Point
788b5ea1-2a43-530e-92d5-c6fa46c66c23 | note | Reference - MRTS16 Cl 8.1.1.2
| checkpoint | Administrator notified at least 3 days before each of the following:
c866843a-00ab-5e3e-9107-15155436b2fa | note | ○ Application and incorporation of amelioration agents
8f8d0920-bb7a-5ebf-997e-75cd0a305b8b | note | ○ Ripping
b47c13d2-2f21-5644-a7b1-99c07d9481b2 | note | ○ Cultivation
5df9e7a8-f600-5f11-b8b1-42bdc3ee3f23 | note | ○ Roughening
82cb4919-5cd9-5691-b2dc-169c25c650e9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
42b95e04-b0c3-5a3e-a7bc-86a8913cfd37 | note | Check Item - Witness Point
17c0bae6-fe25-5659-bdd0-bba85aa30585 | note | Reference - MRTS16 Cl 8.1.1.3 Cl 8.1.1.4 Cl 8.1.1.5 Cl 8.1.1.6 Cl 8.1.2.4
| checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
443bd23f-8780-5ad8-a03b-3f906589bdd2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
fefff5b2-a154-5908-bb27-ed53d6be5713 | note | Check Item - Hold Point 6
8591867b-e40b-5356-a300-71f04a30718f | note | Reference - MRTS16 Cl 8.1.2.3
| signoff | HOLD POINT
| checkpoint | Topsoil installed evenly over the surface, within 5 days of subsoil preparation and at the required minimum depth
afbcbde1-38b7-5e7c-8666-3bfbaf04366e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
406a7bad-3b21-5e2a-96cb-fd6025be1944 | note | Check Item - Check Item
a19699ff-2a0a-5052-b6ba-5351abaefd8b | note | Reference - MRTS16 Cl 8.1.2.4
| section | Grass seeding, Hydromulching and Turfing
| checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
17f2d4d0-b252-5a19-b9e4-ae008b737794 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
03793129-4ad5-5462-9580-3028a89b2b50 | note | Check Item - Check Item
5337388f-59a4-5a59-9267-636303dafc18 | note | Reference - MRTS16 Cl 8.2.2
| checkpoint | Application rate of hydro-compost, seeding mix and timing shall be submitted to the Administrator prior to application for approval.
b3cb4a67-9b1f-5019-bbf2-89f1d0dff3f5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c1a44d38-0d99-5c43-a44c-2a01a604c609 | note | Check Item - Check Item
7967107a-2b65-56ae-8f03-6fe8d77c7eb4 | note | Reference - MRTS16.1 Cl. 3.6
| signoff | HOLD POINT
| checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.2.2 with initial watering on the day of installation and at least 10L/m2
d3128f8c-44c1-55d4-a651-86b38bf1b046 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
918587c3-e136-507e-a33a-fe49ae7d5420 | note | Check Item - Check Item
7313bca0-7b7d-549e-b6fd-61e4c54265a6 | note | Reference - MRTS16 Cl 8.2.2
| section | Establishment, Monitoring and Finalisation
| checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
8d1c3897-bc4f-595f-9d01-edc530445756 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8466a8e1-1ab6-5180-ba50-4cd13baea4fc | note | Check Item - Milestone
675ac15a-c373-5267-837e-0f320cbde107 | note | Reference - MRTS16 Cl 9.1
| checkpoint | All Establishment operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.1.1
cc3be1b3-4846-538f-a023-bfb90899af0e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
936211e1-5e4c-539c-8a15-afd58ea938fa | note | Check Item - Check Item
11f9a565-8480-58c9-b783-13ea778ab768 | note | Reference - MRTS16 Cl 9.1.1
| checkpoint | If a plant failure is determine to relate to the species, a substitute species has been proposed and submitted to the administrator for suitability
c85b9f64-d568-5d64-b913-e6cbdce2226c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
94705ce5-4e42-5610-8819-d1e5867f3256 | note | Check Item - Hold Point 10
e9fbfe5f-b0c7-5ca6-b0de-083039aae56b | note | Reference - MRTS16 Cl 9.1.1.5 Cl 9.2.1.5
| signoff | HOLD POINT
| checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified
fa435f69-a090-5b9f-908f-11a90c1cfd36 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c74e5a9e-a85f-5864-bd79-167167d6e9b8 | note | Check Item - Milestone
9c771c13-eeeb-5d13-875c-2f291047d1eb | note | Reference - MRTS16 Cl 9.2
| checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
877b7cdf-08bf-5ee7-8676-1f07539dd73a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3aeb312c-3477-580e-846d-c5e37507e7e5 | note | Check Item - Check Item
296b3049-20fc-5644-a59a-0388c78a7c95 | note | Reference - MRTS16 Cl 9.2.1
| checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
fdd21fe9-a279-5a3d-bfb6-47df5e51cd27 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9b71ed9f-1b2e-5d91-bbed-b5b5294d3128 | note | Check Item - Milestone
4f87f377-1ab0-58ad-9c99-655ef821f8c2 | note | Reference - MRTS16 Cl 9.2
| checkpoint | Final Verification
faf92237-e720-5066-8545-43ac92410f54 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
c27aafd0-7e70-59ec-8e38-c56f6cd0df92 | textbox | Print Name:
fbbf7c84-7dd7-5a64-9e95-f1256a7b27ca | date | Date:
4eaeb734-2977-5add-943a-dc3fbc81f59f | note | Project Manager Verify that the Above has been Constructed according to Specification
d6d7a0fa-9649-5214-9a61-d28a025fe966 | textbox | Print Name:
d7d20118-a96e-5747-83e6-ab16259f4f80 | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 22.01 - Supply of Cover Aggregate | itp | 22.01 - Supply of Cover Aggregate |  | be0094cc-89b4-450c-9c27-2f5d1fc37d03
| section | Details
| checkpoint | Cover aggregate supplied by a quarry registered and operated in accordance with DTMR's Quarry Registration System requirements. Submitted to Administrator 7 days prior to supply
c5feb943-0e1b-5aab-8c0b-4929915b8d6c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6d85a94d-5e92-56d1-bff0-568616dc72b2 | note | Check Item - Milestone
c8be1b9e-ab3b-57c0-a213-92d135a0172f | note | Reference - MRTS22 Cl. 6
| checkpoint | Material from a quarry shall not be supplid or used without written permission from the Administrator
dc58e5bb-587a-500e-b8fc-4a88bd7b2457 | note | Acceptance Criteria & Frequency (Project Specific) - Written
753e85c5-1803-5748-a57c-e237dc0d9057 | note | Check Item - Hold Point 1
f0c8dca1-af73-56aa-a5b5-7bea83e021fe | note | Reference - MRTS22 Cl. 6
| signoff | HOLD POINT
| checkpoint | Construction procedure shall be submited to the administrator atleast 7 days prior to the commencement of aggregate production for the works
4053e401-77a7-5469-9457-ce3affc4903b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b4ba665c-06e8-5e2c-b0c2-b8dadbe3ac83 | note | Check Item - Milestone
1e918572-807f-5bfb-a2aa-be481014ed00 | note | Reference - MRTS22 Cl. 6
| checkpoint | The cover aggregate particles shall comply with the requirements of Table 7.1.3 of MRTS22
458e773a-483f-5ec5-ab4f-92518b292797 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
060c676d-d8c6-501c-b2a9-bef74e0b4a9e | note | Check Item - Check Item
faf8edaf-1b31-5bee-b0ec-4ad2c868aeb7 | note | Reference - MRTS22 Cl. 7.1.3
| checkpoint | Where precoated cover aggregate is specified the Contractor shall submit to the Administrator 7 days prior, the procedure to be used for application of the precoating agent
04c7c2b1-5853-582b-bf5f-1201af8bf1a0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
fe0e3e31-ecad-5d88-94d9-42185f7c49f1 | note | Check Item - Milestone
24001c79-8687-5bc5-8210-1cd09620aad3 | note | Reference - MRTS22 Cl. 7.1.4
| checkpoint | If stated in Clause 3 of MRTS22.1, a sample of 40kg of each type of aggregate to be used shall be supplied to the Administrator 14 days prior to use.
09770a8a-69a1-5ed2-9f80-78e69b208ff3 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2be4e79d-fd4a-5698-b49f-649cbbebe4e4 | note | Check Item - Milestone
4ea88a76-8321-5427-838e-4bdf6f3a8c7e | note | Reference - MRTS22 Cl 8.1
| checkpoint | Prior to commencement of delivery of aggregate to any stockpile, the Contractor shall obtain the Administrators authorisation
76674e3c-afb2-5459-b9b3-79d216b32668 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6913b120-8ae6-506b-945c-52b396564d09 | note | Check Item - Hold Point 2
2dd8f9ce-3502-513f-ae93-e4d8d0eb4046 | note | Reference - MRTS22 Cl. 10
| signoff | HOLD POINT
| checkpoint | Except for prime cover materials, all cover aggregate stockpiles shall be protected with a light plastic material
1fdccfe5-de74-5895-b7ed-d52b04b4b97d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
71e5191b-49ed-5df2-b950-68b9e8367a5b | note | Check Item - Witness Point
49d519fb-34d4-56df-b7b5-b765827be2a6 | note | Reference - MRTS22 Cl. 10
| checkpoint | Quality Verification Requirements
b3655672-453f-53c5-ab01-f9254a48dbbb | note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
8dbdfd9e-2a83-5226-b2a0-64f9ad75b18f | note | Check Item - MRTS22
85557378-5903-552a-b7de-bba123bc6181 | note | Reference - Clause 8.3
| checkpoint | Material compliance testing shall be conducted in accordance with the requirements of MRTS22 Cl. 8.3
6da2b042-9985-5741-a961-d1bfdf0a4209 | note | Acceptance Criteria & Frequency (Project Specific) - Refer to Table 8.3.2(a) and 8.3.2(b)
647a3022-633d-5895-905a-43cf701ef99b | note | Check Item - Check Item
7648383e-3921-5dce-80aa-37c752b751c8 | note | Reference - Clause 8.3
| checkpoint | Final Verification
5538a623-7052-526a-bc64-cc7456eea2fb | note | Project Manager Verify that the Above has been Constructed according to Specification
77ac56b1-d298-5db0-a345-7b0959b0f007 | textbox | Print Name:
cc298084-06fb-5f34-b10e-0cf2cb329b66 | date | Date:
bedef31a-5787-5add-8f0a-14ec4305332d | note | Client Verify that the Above has been Constructed according to Specification
e4c9d3c8-d3aa-5628-bd9b-675e6483eb16 | textbox | Print Name:
486a7b1c-3276-5fb8-8bdb-f74078dc99c2 | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 27.01 - Geotextile | itp | 27.01 - Geotextile |  | c0b1d545-a9d3-4527-87a5-27d65a72fd83
| section | Details
| checkpoint | Geotextile strength and filtration classes as specified on drawings or within MRTS27
ea22728d-8577-5457-8630-d5809d9c8511 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7c01eb07-d08b-5dc4-8197-8929bf78b7c1 | note | Check Item - Check Item
dfe432e9-35e0-5992-9910-5975aac99f50 | note | Reference - MRTS27 Cl6
| checkpoint | Geotextile stored on site under protective covers, off the ground and in a manner unaffected by heat. Rolls clearly marked with manufacturer, type and batch.
70cc3f6c-ca05-5fce-9858-9f4b2807d439 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
649f6f03-0118-54a3-8cd0-b28f5a588111 | note | Check Item - Check Item
daa179c5-f693-5584-aa94-e9d289be7375 | note | Reference - MRTS27 Cl7
| checkpoint | Proposed Geotextile submitted to and accepted by Adminstrator for acceptability to Cl6.
88eab5da-61cd-544f-80e6-6e951616b4e0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
60ece281-b1d7-5782-ae1f-48fba7655976 | note | Check Item - Hold Point 1
014108ce-54cf-5cd2-a866-260792585855 | note | Reference - MRTS27 Cl8.1
| signoff | HOLD POINT
| checkpoint | Geotextiles installed as specified in the contract
2c4172bf-8c72-543a-a3f1-3240403b9a02 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
40e71f73-7d0d-501b-95f6-5397efe90124 | note | Check Item - Check Item
4c550b25-ec15-586f-90f6-6a5840873cd7 | note | Reference - MRTS27 Cl9.1
| checkpoint | Area cleared and graded with all sharp objects and large stones removed and covered within 48hours of being placed
22fe99fc-4d79-5fb8-8d11-0c1a02687e21 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6933daef-fc39-52ee-b35b-1f198617cb22 | note | Check Item - Check Item
e4a58b1d-07b9-5f83-a98a-baa839c5ad4b | note | Reference - MRTS27 Cl9.1
| checkpoint | Initial uncompacted layer thickness for fill material placed over the geotextile shall be not less than 200mm of D85 of the fill material, whichever is greater.
b3eb5fe2-30fd-51a3-bba9-26be210c318f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e8b15e26-fdbd-5759-ab57-4f4d424e25c2 | note | Check Item - Check Item
cd7762c0-bc84-5271-9689-896e95dd9864 | note | Reference - MRTS27 Cl9.2
| checkpoint | Jointing of geotextiles in accordance with clause 9.3. If overlap is not specified, it shall be a minimum of 500mm. If used to line subsoil drainage trenches, the geotextile shall fully envelop the drainage material with a minimum 300mm overlap at the top of the trench.
95d14be5-012a-5415-a801-2a515c3df31e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b880e008-2a5e-5d5b-a2a1-abb182520b73 | note | Check Item - Check Item
fe84953b-ed7e-5554-b6dd-228ce85e9c23 | note | Reference - MRTS27 Cl9.3
| checkpoint | Filling over installed geotextile shall be in accordance with clause 9.4. No construction equipment shall stand or travel directly on the laid geotextile. Rock placed directly on geotextile shall be placed with a drop height not exceeding 1.5m.
b6ef0d32-77a0-5d67-812c-e4a597d1c3cd | note | Acceptance Criteria & Frequency (Project Specific) - Visual
db388585-6ee0-558b-b4a4-b361095dbc24 | note | Check Item - Check Item
8fd1a42a-9213-5201-b090-c6080c3212be | note | Reference - MRTS27 Cl9.4
| checkpoint | Where batch size is <5000m2, sampling and testing need not be undertaken, provided the nominal strength of the material supplied is 20% higher than the requirements and the filtration properties are 20% lower than the requirements stated.
5d604049-40fd-5100-ad07-c8f1d19d40c8 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
bee9e16f-2be9-500f-9fa7-2915e0216502 | note | Check Item - Check Item
ad66308f-eb09-50cc-8be4-b9952f100694 | note | Reference - MRTS27 Cl10.2
| checkpoint | Where directed, a testing sample shall be cut and provided to the administrator
190b7871-6438-5c06-81ce-cb56c4b9da7c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4726e54b-a656-56a7-9b8e-8c66433d32d7 | note | Check Item - Witness Point
ff2334ab-f82b-5946-b174-d98e5efdbf63 | note | Reference - MRTS27 Cl10.2
| checkpoint | Sampled geotextile shall be tested by the Contractor for the range of properties specified in Table 6.2 and Table 6.3 in accordance with the requirements of Clause 10.3.
88968ab2-b3fb-537e-a5e8-15d3e4ce239c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c380cb32-d86c-5e61-94dc-0c1db5ee198e | note | Check Item - Check Item
69f2b47f-d347-500b-9a43-7299eb1672de | note | Reference - MRTS27 Cl10.3
| checkpoint | Geotextile not placed until administrator accepts test results
e7cc4606-13d2-5ffe-88ff-4b9a09a4e310 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3d5fe794-0874-57ef-8887-79301e6961a7 | note | Check Item - Hold Point 2
94544af2-2e82-55e4-ae7a-a6f1a1205033 | note | Reference - MRTS27 Cl10.4
| signoff | HOLD POINT
| checkpoint | The administrator may select samples from the site for audit testing.
94a87b19-5966-536c-958d-57b0b60fc2b1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8217d5c2-e22f-5f2d-8bf1-ed9724c65eb5 | note | Check Item - Check Item
5246baab-5940-5eb3-b9a6-bb48e20a91e0 | note | Reference - MRTS27 Cl10.5
| checkpoint | Final Verification
9443414b-b88c-5636-884e-09c90845da41 | note | Project Manager Verify that the Above has been Constructed according to Specification
2935de67-4305-54f7-81be-e8fd131f9da2 | textbox | Print Name:
aba0fd33-c267-5cab-bce7-b721e832fca3 | date | Date:
5fe84082-02be-5bc7-87ae-577a0fa48b92 | note | Client Verify that the Above has been Constructed according to Specification
9d36177e-cd3e-5309-839c-744e0dad1a4a | textbox | Print Name:
ae7596e8-0624-51e8-894e-42790bc89fca | date | Date:
| signoff | Sign ITP
| checklist | 28.01 - Contractor's Camp and Site Facilities | itp | 28.01 - Contractor's Camp and Site Facilities |  | bb2f095c-aece-49bf-87b3-6f899017298e
| section | Details
| checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
973734b7-ea3d-5a8b-a1ae-8075bdad35d4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c9621a30-4189-5052-9e62-1dffea50cbbc | note | Check Item - Check Item
0074fa48-2c55-5adf-83d5-07f8948a5efb | note | Reference - MRTS28 Cl 4.2
| checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided.
70ffe19a-30c6-5a3a-9629-bf311f68a42a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1cdd386d-8f44-5309-b338-be91f78af8a8 | note | Check Item - Check Item
d4e88d54-604b-5b96-a3f9-ceb0ca6035b2 | note | Reference - MRTS28 Cl 4.3
| checkpoint | If stated in Clause 2 of MRTS28.1, a separate room shall be provided for the use of auditing, QA documentation and private meetings with the Administrator and Principal. The requirements of the room shall be as stated in Clause 4.4.1 of MRTS28.
f0600b12-4719-5fed-bc75-1e2f5ab8e425 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b829163a-07dc-52d1-bbc7-bfe132837233 | note | Check Item - Check Item
b49671ee-80fe-540f-944b-45f0dfe196b8 | note | Reference - MRTS28 Cl 4.4.1
| checkpoint | If stated in Clause 3 of MRTS28.1, a separate room shall be provided for the exclusive use of the administrator during Work Under the Contract. The requirements of the room shall be as stated in Clause 3 of MRTS28.1
f6e2d52f-9d1b-56cb-a516-4df3c2479e3f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
21a4279d-052d-5a0a-939b-e8c4ba6552b1 | note | Check Item - Check Item
9dbf0d21-093f-51fe-9f82-6fc09e9ae724 | note | Reference - MRTS28 Cl 4.4.2
| checkpoint | If stated in Clause 4 of MRTS28.1, documentation of the Contractor's site facilities shall be provided to the Administrator for approval.
1ceb748b-5d6c-5227-86ec-42a9febd7600 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c09dcd98-e5d0-57d7-a4eb-62dca03ab3b2 | note | Check Item - Check Item
e6a1fcdb-fd78-525d-9715-3f9c182fbded | note | Reference - MRTS28 Cl 4.5.1
| checkpoint | If stated in Clause 5 of MRTS28.1, the Contractor's site facilities shall be screened from public view.
caef25ce-34b7-5588-aa5f-4ed287c64bcf | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9a921a00-435e-5b62-97aa-1b226cba2481 | note | Check Item - Check Item
25d1bb17-bfda-5d64-bd9e-3bb2ff11d425 | note | Reference - MRTS28 Cl 4.5.2
| checkpoint | Camp and facilities provide safe egress and ingress and do not impact on existing through traffic.
291660c5-0e4f-5137-ac09-385c95b27222 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
66f9dab4-002b-5a9a-9196-8f0808ffb17c | note | Check Item - Check Item
6cc1e487-d1fb-508e-aec0-c6089a1f66cf | note | Reference - MRTS28 Cl 4.5.6
| checkpoint | If no area's are included in Cl6 MRTS 28.1 the contractor shall be responsible for obtaining any necessary area's for the establishment of a camp.
e5bdeee2-97c8-54db-ae99-1e0b28b96bd7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
394f1772-dc6e-53d3-aa78-b2c10f8b0ed8 | note | Check Item - Check Item
b2469ffc-c18e-5632-9c4d-ce97816449c2 | note | Reference - MRTS28 Cl 5.2
| checkpoint | Contractors camp complies with all requirements of MRTS28 annexure, including any supplementary requirements.
c204aa4b-cce1-5182-b2d4-6933bb8b8d77 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
78986c76-795d-5a4c-a24e-7b0f92513010 | note | Check Item - Check Item
1ad7c173-1bd7-5e0a-aeb1-a22966340c82 | note | Reference - MRTS28.1
| checkpoint | If private property is to be used for the Contractor's facilities, written approval must be sought from the property owner and provided to the Administrator for approval. Restoration of these areas shall be in accordance with MRTS16, MRTS28 and MRTS51 and a plan shall be submitted to the Administrator for approval prior to commencement.
898d1d79-44e7-5abe-99a8-24334f97161d | note | Acceptance Criteria & Frequency (Project Specific) - Written
3b476c27-9345-5d80-9876-d8ced61cba76 | note | Check Item - Hold Point
df78ea9e-4cf4-5ee3-88e5-a2b34b57fbb3 | note | Reference - MRTS28.1 Clause 8
| signoff | HOLD POINT
| checkpoint | Final Verification
81c30a1c-bd35-5e48-8fba-3ea678d5e0c0 | note | Project Manager Verify that the Above has been Constructed according to Specification
449ca558-0ec0-5b31-99de-a765b69e209f | textbox | Print Name:
f7037929-bf58-5759-8dbb-fc476590b83b | date | Date:
b53486e6-56ee-5432-9895-4ee582930812 | note | Client Verify that the Above has been Constructed according to Specification
2362c2fb-019d-5f03-9697-bc3bf7a19604 | textbox | Print Name:
38d19a88-df40-52d6-8bc9-de01d9bedb0b | date | Date:
| signoff | Sign ITP
| checklist | 51.01 - Environmental Management Systems | itp | 51.01 - Environmental Management Systems |  | 018249db-74c8-427a-95fc-5857f6039bc6
| section | Details
| checkpoint | Environmental Management Plan (Construction) submitted in accordance with Conditions of Contract.
ac848252-5001-5b3e-bf3b-d274dda84db3 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
03dae743-d32a-5039-8f18-50e12c2d0611 | note | Check Item - Milestone
ab71ef56-67ea-5604-9f93-0ceaa23236fb | note | Reference - MRTS51 Cl 6.3
| checkpoint | Works shall not commence until the Environmental Management Plan (Construction) has been assessed for suitability by the Administrator and approved.
947db946-2a75-5bce-9911-de710f50a074 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
98187155-0913-554e-b47a-35b0b37b01e8 | note | Check Item - Hold Point 1
7df56cf2-d118-50e8-8f09-7f829d6fdee2 | note | Reference - MRTS51 Cl 6.3
| signoff | HOLD POINT
| checkpoint | Amendments to the Environmental Management Plan (Construction) to be submitted on a monthly bases for assessment of suitability by the Administrator.
778a24ab-5ec1-5ca7-ac14-58718c5dc85a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
808946ed-c437-5793-8f74-a8fd988cff61 | note | Check Item - Hold Point 2
43bbaa07-3dc5-55da-8e1f-7ade371b92ce | note | Reference - MRTS51 Cl 6.4
| signoff | HOLD POINT
| checkpoint | Enviromental site inspections to be conducted daily against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Superintendent on a monthly basis.
81aa9eb5-0e14-5544-a7d6-1fadc70305bd | note | Acceptance Criteria & Frequency (Project Specific) - Visual
66d1f2e8-1818-5daf-ad1c-2b56d4e25c0b | note | Check Item - Check Item
57ff063a-c590-5b3e-a4c0-bd3cebd8cc7b | note | Reference - MRTS51 Cl 7
| checkpoint | Environmental records are to be included in the Quality Records under the Contract. Records and registers shall be made available to the Administrator upon request.
1142f195-d9b0-5c3c-a628-50921608a9bd | note | Acceptance Criteria & Frequency (Project Specific) - Written
b272e5db-dd67-5a2a-83d1-5dd6d2d4c04c | note | Check Item - Check Item
4dbbdc88-5ded-5853-b2b8-0a0bb8f6e444 | note | Reference - MRTS51 Cl 7.3
| signoff | HOLD POINT
| checkpoint | Water quality monitoring undertaken as per requirements in MRTS52 and Annexure
4728a1f3-87e7-5c5b-88a7-f037ac4ce21c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
18a6e453-4cbf-532e-9955-4f11a52c8011 | note | Check Item - Check Item
dc9119b6-fab6-5ea7-b0fc-48c8a5e191c3 | note | Reference - MRTS51 Cl 8.2.1
| checkpoint | Requirements relating to Erosion and Sediment Control are contained within MRTS52
ffed64cc-a440-5bbd-93bd-2e2a5d5cf497 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c1e6be39-cab6-53dd-abf9-69d2fb9fc1bb | note | Check Item - Check Item
e89d29a9-1432-575a-9d3e-6ff9c0414e7d | note | Reference - MRTS51 Cl 8.3
| checkpoint | Construction activities have not resulted in air quality impacts that cause environmental nuisance or harm. Visual monitoring shall be conducted in accordance with Clause 6.3.1 of MRTS51.1 and recorded in the site diary.
b7f8472b-2415-53ac-9cc6-0058dd1a69b4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7dd1e2cb-d1ac-5241-a691-d30fda586561 | note | Check Item - Check Item
0f905643-5b31-53c9-893b-c72a0c69dd20 | note | Reference - MRTS51 Cl 8.7
| checkpoint | No harm caused to native fauna. Areas of significance and related management requirements are stated in Cl 7 of Annexure MRTS51.1.
2a350a83-2169-55d8-89f1-38ded6eb72e0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4838efb1-3155-53bb-8fe3-50e7dc5ea2da | note | Check Item - Check Item
641041a8-233b-5576-a6f8-ef64191c063d | note | Reference - MRTS51 Cl 8.10
| checkpoint | Where stated in Cl 7.2 of Annexure MRTS51.1 the contractor shall engage persons authorised by Queensland Parks and Wildlife Service to attend the site to carry out an inspection of the site and subsequent capture or relocation of any fauna. Injury or death of fauna know as rare, endangered, or vulnerble shall be reported immediately to the Administrator and reported in the monthly report
c5aeedaa-6baf-539c-8238-16fa74eb323d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4e4b33b0-530f-595e-9721-2a54353c628e | note | Check Item - Check Item
eb3778d5-2e01-520e-83ec-a8513fdb49e7 | note | Reference - MRTS51 Cl 8.10
| checkpoint | Management of vegetation within the worksite. The daily site inspections shall include visual assessments of vegetation management measures.
46c51779-7317-5998-8b02-74d2625fc4a7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
02424173-d54d-5d49-9351-b3b609d50345 | note | Check Item - Check Item
f9717ff7-66e5-5cc3-9a9f-1f38126a2969 | note | Reference - MRTS51 Cl 8.11
| checkpoint | Clearing extents to be clearly defined by the Contractor and approved by the Contract Administrator. Should any clearing outside the defined clearing extents be required, the Contractor must notify the Contract Administrator and may only proceed with the written approval.
4b0fdf90-8551-59f2-b3d9-6bc09c8050ad | note | Acceptance Criteria & Frequency (Project Specific) - Written
7ea9099a-53ae-59e1-b6e3-91c297f7d702 | note | Check Item - Hold Point
59e2417e-3dda-5277-8554-2f0d15ee8e77 | note | Reference - MRTS51.1 Cl 9.1.3
| signoff | HOLD POINT
| checkpoint | The Contractor shall undertake a pre-clearing weed and pest survey to document areas of existing prohibited and restricted invasive plants, and identify treatment and management requirements. Weekly inspections shall be carried out once clearing is complete to determine the success of the pest management procedures.
46057d8a-e480-5f85-9a59-2da09a3499e6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e6000fdf-ae45-5b75-899a-8725abdb9685 | note | Check Item - Check Item
de295d7e-75a7-5609-be2f-1083ea01cd3d | note | Reference - MRTS51.1 Cl 10.1
| checkpoint | All chemicals and fuels within the worksite are contained so as not to cause environmental nuisance or harm. Spill kits response equipment are available on site for use in emergency.
7184773a-61f4-5575-8c51-f3e243f3b14c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
613608c5-3d90-5dcd-b6fd-cd00badc3862 | note | Check Item - Check Item
1bfb6f8e-e557-579c-8d65-920bcdb433a0 | note | Reference - MRTS51 8.14
| checkpoint | Final Verification
f20adcb4-aebf-5722-8fa3-7f5e9027b838 | note | Project Manager Verify that the Above has been Constructed according to Specification
c389d92f-7f72-5079-b2f2-21c6615f667d | textbox | Print Name:
b8c2e814-06d2-5bcb-b7a3-5a93d01c57b0 | date | Date:
588c6f33-3e11-5ca5-ac29-352b24a3e382 | note | Client Verify that the Above has been Constructed according to Specification
57b87a99-1f05-5477-8be4-0f02783e7630 | textbox | Print Name:
4353945a-8536-5f3a-856d-8b19ca9ca0c9 | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 52.01 - Erosion and Sediment Control | itp | 52.01 - Erosion and Sediment Control |  | 52464860-079a-48ea-bc70-067891b0dc63
| section | Details
| checkpoint | Submit an Erosion and Sediment Control Plan (ESCP) for that section
0156f7c4-e47c-556e-a59d-730188f12737 | note | Acceptance Criteria & Frequency (Project Specific) - 14 days prior to tree removal as per Annexure 52.1
692a232e-7b7f-55d1-9acd-5a0c31357e6f | note | Check Item - Check Item
284b9a64-60ee-5ee9-b18e-4692b8c2b4b0 | note | Reference - MRTS52 Cl 6.1
| checkpoint | Administrator assessed suitability of Erosion and Sediment Control Plan for each stage and/or section of the works where required
d0885505-8a73-5b12-ab71-bed4cc85b7f4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
dd66b865-788b-5768-818c-a3bb77c7c41e | note | Check Item - Hold Point 1
7d422d35-34b2-57ea-abd3-85d1663a228e | note | Reference - MRTS52 Cl 6.1
| signoff | HOLD POINT
| checkpoint | Installation of appropriate erosion and sediment controls in each section of the works
14311230-79eb-51c3-96e6-22743c052fe5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
15addf54-924c-5632-855a-fdfd51888183 | note | Check Item - Hold Point 2
68e06833-0f1a-5b22-90b5-0d30e83b578f | note | Reference - MRTS52 Cl 7.1
| signoff | HOLD POINT
| checkpoint | Any clearing required to be able to install sediment control must be discussed and approved by Administrator
e9af761d-ae26-56f6-ad5f-a293b4917a28 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d0e42ff2-e5a9-501f-ac8e-6f77b9fb9f22 | note | Check Item - Check Item
c1cd1f49-a5a0-5799-9886-b0ea3d1a2b13 | note | Reference - MRTS52 Cl 7.1
| checkpoint | Erosion and sediment controls maintained and reconfigured throughout the stages of the project
a94b9b53-c36e-5aba-8e4b-a835e18c767d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
41773e54-203f-5c66-a548-db5af8a4413c | note | Check Item - Check Item
680d1bd8-0d94-55e7-ad0a-379fea58cf48 | note | Reference - MRTS52 Cl 7.2
| checkpoint | Remove temporary controls when permanent measures in place and/or site stabilisation occurred
582f2afa-696c-5a28-bb8c-99d6509d74fe | note | Acceptance Criteria & Frequency (Project Specific) - Visual
fbfe8e0b-a9f3-5d0e-ad07-19ec1cd49811 | note | Check Item - Check Item
e2483af6-4e0e-5960-bae9-c8a280e0e07e | note | Reference - MRTS52 Cl 7.3
| checkpoint | Install a proprietary rain gauge and monitor/record rainfall in spreadsheet (mm)
327e35e9-0e25-5f12-b4cb-5ddf4e6b3103 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
61a84cc7-f718-5e2b-8980-0618474da8c7 | note | Check Item - Check Item
eb59c327-171b-51da-a99f-b4f00adefea0 | note | Reference - MRTS52 Cl 8.2.1
| checkpoint | There shall be no erosion resulting from construction practices unless there are provisions within the worksite to manage resultant sediment. Releases from site must not cause scour at the area of discharge. Implemented controls shall be sufficient to achieve the water quality investigation criteria as per Clause 8.2.2 of MRTS51.1
f29bf1a9-35c5-5024-8978-a58ffe5693e5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a0bddbc5-039f-5525-9165-f9c95780b9aa | note | Check Item - Check Item
f8fa9360-bc75-52a4-b3b8-cf4c6eb60de4 | note | Reference - MRTS52 Cl 8.1
| checkpoint | Final Verification
fa14e851-6f3a-565b-ab8f-ddbb30ec947d | note | Project Manager Verify that the Above has been Constructed according to Specification
e9b97401-405e-50b2-a422-c6fa4cf8543c | textbox | Print Name:
b4c6e822-8bc7-54fb-9707-a49f5f1e76f2 | date | Date:
40bcedbb-f537-5266-883d-1dab2909a810 | note | Client Verify that the Above has been Constructed according to Specification
80943052-14f0-5758-b6ba-398291529013 | textbox | Print Name:
528b82f6-d493-5581-a230-38dc9fe99c65 | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 70.01 - Placement of Concrete | itp | 70.01 - Placement of Concrete |  | 819e1863-d8a0-4092-8077-ffdfff3418e1
| section | Details
| checkpoint | Concrete placed within 1 hour (conc. Temp<=32 degrees) or 45 mins (32>conc. temp < 35 degrees) from the time of charging the mixer unless a retardant is used and approved by the Administrator.
76f3b3c3-050a-54b3-bd3b-bdb2c3ee3924 | note | Acceptance Criteria & Frequency (Project Specific) - Temp <35 Continuous
7c467c11-4847-5840-b0f2-533732698636 | note | Check Item - Check Item
b0e2307b-efd1-58e1-80d3-fe7ffb86a131 | note | Reference - MRTS70 Cl 10.5
| checkpoint | The Contractor shall supply the Administrator with detailed drawings of falsework at least four weeks prior to the commencement of erection
35d03873-d952-5e4e-aafc-144dd4a909eb | note | Acceptance Criteria & Frequency (Project Specific) - Written
0d02dd34-5829-56f9-9bde-3e9711be0e22 | note | Check Item - Milestone
273b8300-421c-5ba9-b2ad-7b9d1b79c2ad | note | Reference - MRTS70 Cl 15.3
| checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
142b2d5a-09ff-5128-bf8c-955b913e78a1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1b909f61-2344-59c0-b983-b63aa8da33d9 | note | Check Item - Hold Point 2
a6879be8-9e2d-52c4-b1bc-ec1a0d5d4f60 | note | Reference - MRTS70 Cl 15.3
| signoff | HOLD POINT
| checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
266ddda8-dcc6-5bac-8265-29fe34067c8f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
626af846-1bb8-50ff-ac9c-b6e2f44178f0 | note | Check Item - Milestone
42a2d377-6374-5390-948c-ca03a3057c77 | note | Reference - MRTS70 Cl 15.3
| checkpoint | Procedure for underwater concreting submitted to Administrator 2 weeks prior to first pour
d25d97ad-1525-56fe-b590-954783f4a546 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b26dade6-d5d7-5aa4-a1ea-d506ac9f48f3 | note | Check Item - Milestone
4a398a78-7603-515d-8225-de00a43d5d07 | note | Reference - MRTS70 Cl 15.6.3
| checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
5d77aa8d-4f65-562d-9630-45f1055715b2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
19467aee-c690-5d51-9705-61e4d06131a3 | note | Check Item - Milestone
a7b9e1b2-6c4d-5673-9405-2acf0172e5ab | note | Reference - MRTS70 Cl 15.11.1
| checkpoint | All formwork shall be subject to inspection and approval by the Administrator
4c6ad9bc-1bb6-5c75-8807-b9f595c9750a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3649db4f-26d5-5115-abf4-08d239171de3 | note | Check Item - Hold Point 3/5
29a7a3ee-93f5-5bf1-8ddc-41ae26343036 | note | Reference - MRTS70 Cl 15.4.1
| signoff | HOLD POINT
| checkpoint | Concrete operations shall not commence until all relevant procedures have been approved by the Administrator
0ae5052b-0fec-565f-a7fe-3c4e06d16c54 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
62477441-25bc-598f-ba25-33e8feaf5f27 | note | Check Item - Hold Point 4
765aaf7b-d06d-50da-933e-b2ea258c0a61 | note | Reference - MRTS70 Cl 15.6
| signoff | HOLD POINT
| checkpoint | No concrete placed until formwork, reinforcement and stressing materials inspected, foreign material removed from forms and equipment and placement procedures approved.
8f040dd4-0fd0-59f1-a779-404302c2a723 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
14290144-1b8d-5d7d-94fe-45cb32baacb2 | note | Check Item - Hold Point 3/5
c059b936-e0b3-5e42-ac05-27251a1b7eb7 | note | Reference - MRTS70 Cl 15.6.1
| signoff | HOLD POINT
| checkpoint | Administrator to be present for placement of concrete, with 24 hours notice.
1f6f642b-ef00-5946-a708-95e40d3335b5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4110bc48-23d5-558e-9f60-86a54e253adc | note | Check Item - Witness Point
b0e5978c-00cf-56eb-b722-107da1ef1c9d | note | Reference - MRTS70 Cl 15.6.1
| checkpoint | The placement of concrete underwater shall be carried out in the presence of the Administrator and shall comply with the requirements of Clause 19.2
e0fdde00-9092-5418-ac37-fe7048dfe43c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
39bb27c4-3ac0-5ed2-9fb3-d8be6a285698 | note | Check Item - Witness Point
f515f661-0330-59f4-829c-50ed255e29a0 | note | Reference - MRTS70 Cl 15.6.3
| checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
f83d207a-6dc9-5bbf-91fe-e1becc06fed2 | note | Acceptance Criteria & Frequency (Project Specific) - Slump Test:
aadba958-da2f-5264-92ca-65e442a48c2f | note | ○ <60 - ±10
e7b93b83-033f-5f54-899e-2ed8144ec8ba | note | ○ 60<80 - ±15
60c3c824-3f13-53f8-b25c-b0c661a9a59d | note | ○ 80<110 - ±20
78aecf26-9cea-5397-bcf6-d6b86f105493 | note | ○ 110<150 - ±30
f16528cd-ca7a-5f93-9b9e-4b5241031beb | note | ○ 150< - ±40
b5e3e6e3-9a9e-54a8-8809-6da730e68262 | note | ○ Every Load
07b09918-295a-57b8-a6c1-693f3b4a9de2 | note | Check Item - Check Item
d82228a7-2dae-5fa8-aed3-640f7219b488 | note | Reference - MRTS70 Cl 11.3 AS1379
| checkpoint | Samples for testing taken as required - min 2 cylinders/sample
8cf0a871-a043-51ae-8ed3-53e34760a969 | note | Acceptance Criteria & Frequency (Project Specific) - 1-3 Loads - Every Load
f93119e3-36c3-5b8a-8a81-f0ed53dfaff6 | note | ○ 4-10 Loads - 4 Samples
ceb3533f-53c7-517a-8940-503398534807 | note | ○ 11-23 Loads - 5 Samples
6a89e25c-79c1-5c17-b19b-e0e0d50aeb2e | note | ○ >24 Loads - 1 per 4 loads
d5537c9e-fe63-5387-aef3-46c635e177e0 | note | Check Item - Check Item
bcbd9639-97f7-565a-aac6-4ba8de76be9a | note | Reference - MRTS70 Cl 15.2.2
| checkpoint | Compressive Strength Testing
942b80e7-fb36-5b79-81cd-e45dd3128bd6 | note | Acceptance Criteria & Frequency (Project Specific) - f'c
274a39a9-64e2-5a5c-bdcb-02930a59e068 | note | ○ <2Mpa Difference/2 Cylinders
9f929d60-9341-559b-84e5-817349966d44 | note | ○ <3Mpa Difference/2 Cylinders
37a276a5-6686-5983-bfae-b04206ae6770 | note | Check Item - Check Item
9a60a364-9055-5eb5-b0e8-66ff3d6561af | note | Reference - MRTS70 Cl 12.3
| checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - minimum of two vibrators used with at least one per 4m3 of concrete placed per hour.
fa42f3f6-d433-5711-963b-7d23d807fcbb | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e0a12004-4ce4-5008-8c35-89cfadaa1969 | note | Check Item - Check Item
a3ef65f2-c885-5e5f-9887-2bc63293a850 | note | Reference - MRTS70 Cl 15.6
| checkpoint | Additional construction joints approved by the Designer.
c73af011-ab32-5233-8210-e5d7787db3dc | note | Acceptance Criteria & Frequency (Project Specific) - Visual
57454a87-b60b-5111-8002-8257c351308f | note | Check Item - Hold Point 7
3ccc9620-7a18-54ec-84ca-65c0d53a4005 | note | Reference - MRTS70 Cl 15.13
| signoff | HOLD POINT
| checkpoint | Forms and Falsework not removed early unless approved by the Administrator.
2e89f0d0-09a7-5a97-b048-3ed678056a48 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
fe2a7b07-b5ed-5c35-9a31-98fe9e9bdd33 | note | Check Item - Hold Point 6
c015bc0d-bf5f-5b04-8ba3-9174c0b27cf4 | note | Reference - MRTS70 Cl 15.8
| signoff | HOLD POINT
| checkpoint | Forms not removed until
1bb9ff2f-f854-5b14-8324-ed4ea6fa55dc | note | ○ Non-structural - min(50% of 28 day strength or 3 days)
4f493cfd-e99f-5987-8932-2a99e8a3d29e | note | ○ Soffits of slabs, headstock and diaphragms - 7 days
f532c0c4-f9ef-5371-93ac-907ba647b33e | note | ○ Side forms of structural concrete - 2 days (Exposure class A), 3 days (B1, B2) or 5 days (Exposure class C)
3032f6cf-9d28-53dc-b130-a2f321d364e3 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
52191b1a-9b7f-5cd0-b4b6-d800b708f40b | note | Check Item - Check Item
0a12fd32-da33-5e52-af51-51c4a87546f1 | note | Reference - MRTS70 Cl 15.8
| checkpoint | Forms removed with care and curing commence upon completion of finishing operations to approved procedures. If forms removed in under 7 days, curing commences within 1 hour
1dc8ade8-9e93-51cb-a092-30199b556405 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
514b7494-ca13-5460-af25-c5979255619e | note | Check Item - Witness Point
36c13d53-9c86-5dc9-a6e4-08260aa35ad8 | note | Reference - MRTS70 Cl 15.8
| checkpoint | Following removal of forms
a352a2cc-bae8-5480-a819-8239fd3932f8 | note | ○ Fins and unwanted projections are ground off
02af2874-07c1-56c3-900a-3290c9609561 | note | ○ Pockets and honeycombed areas repaired using approved methods
bec81140-11da-58cf-9311-a501e8910c1d | note | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
8b8eecb9-67f7-5389-a233-b0029fae07d1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7cfcec89-c46b-5952-9095-659a6fb419b8 | note | Check Item - Check Item
09fcca21-1661-5c6e-acbc-289fa799aea3 | note | Reference - MRTS70 Cl 15.12
| checkpoint | Concrete installed to within positional, dimensional and relative tolerances. Should a specified tolerance be exceeded, the work shall be liable to rejection.
b2117430-5ab9-52b0-822e-21b61c774615 | note | Acceptance Criteria & Frequency (Project Specific) - Visual <Specified MRTS70 Cl22 QR-CTS-Part 7
b3d4db21-2b41-5864-8ea6-cf3750e56db0 | note | Check Item - Check Item
fd153d41-02c6-509d-a802-ec167a938943 | note | Reference - MRTS70 Cl 15.7.2
| checkpoint | Acceptance or Rejection of Hardened Concrete
ac596b57-acb3-5a6e-b5aa-b8f6bf7da81d | note | a) < 0.9 Fc (Any sample)
9032c71f-50dd-5803-ae64-48d5b3bd01e4 | note | b) < Fc (Ave 3 consecutive samples from Lot)
59aea6c7-b5dc-51d0-9491-6e9ad14ad172 | note | c) > 1.4 Fc (Ave 3 consecutive samples from Lot)
d8e2a0a6-999e-53dc-bf33-1b65a1b1fdf9 | note | In addition
08d534ff-fe0d-55eb-92dc-026d0a3d0e7c | note | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consecutive weeks)
ed67ffea-8245-57e2-9983-dd0662405f58 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8f55ce88-8fec-552e-a715-62069cf73f69 | note | Check Item - Check Item
36e8b4b0-d67d-5c27-a7e8-cab29ac4f3e0 | note | Reference - MRTS70 Cl 12.5
| checkpoint | Final Verification
d8296ae3-167e-54cb-a074-96da7068dd6b | note | Project Manager Verify that the Above has been Constructed according to Specification
0e6a09e3-dde4-5495-a32e-8c492ec8d384 | textbox | Print Name:
ebd1b53a-8a70-5e1a-b01c-845d14a1de0a | date | Date:
b7be7999-8868-55f4-82a0-f68b57d6b3f2 | note | Client Verify that the Above has been Constructed according to Specification
b5bafb90-d043-545b-8fe4-6bc95cdb9514 | textbox | Print Name:
02cce558-754c-5c2d-b520-baeeb22d65c9 | date | Date:
| signoff | Sign ITP
| section | 70.02 - Concrete Record
| checkpoint | Truck 1
fc2eae6c-3817-5a0e-8324-285f0a791b67 | date | Date
eb1e5e6e-a4fd-5ea4-b649-07679f6b9fae | textbox | Docket
65130029-08ad-5a8d-8b87-bd865c1dd80f | textbox | Time Batched
582531e6-117f-5f57-9e18-0b03b48609ea | textbox | Truck Arrival Time
7b55aa52-be85-5f74-8ca3-0270dfb54d04 | textbox | Load Size
0a3ebaaf-8e95-5108-9ba6-9700f6e5015f | textbox | Slump
8a00bdba-f08c-58e4-b192-1ac5ca7d1a5b | textbox | Slump Time
bc13ebf8-3448-56a3-bb2f-dde41e9650da | textbox | Concrete Arrival Temperature
660dbbfd-a871-5541-90c1-7a4882edb485 | textbox | Ambient Temperature at time of slump
a26dd4b9-d97c-5653-be4a-301feea3a679 | textbox | Time Start delivery
f0e13c11-bebb-5fdd-b0ce-8cbf7313c75f | textbox | Time Finish delivery
| checkpoint | Truck 2
ce9d7a2b-f3c4-598b-b651-a4cb06ffd049 | date | Date
ccfe373b-26ec-5997-ae91-bc9dc67bec9a | textbox | Docket
2209c1ed-e55e-5fc4-a671-39830faa87c9 | textbox | Time Batched
168741a7-3bc9-5fad-873f-b4703da1eb28 | textbox | Truck Arrival Time
bcfcdd17-3c86-5eb9-96d6-aad60e9bcce7 | textbox | Load Size
6fe5b1b9-87a4-579d-aef0-d1a255baea70 | textbox | Slump
b60c711b-f395-50dc-8e0c-1c9e918ead29 | textbox | Slump Time
df81d6e2-2213-5937-9935-b069b21e9aaa | textbox | Concrete Arrival Temperature
3fc4964c-7ad7-55eb-ac27-7f6030708d7a | textbox | Ambient Temperature at time of slump
0abd3119-41fe-5beb-8d24-4033458e0fe9 | textbox | Time Start delivery
296a14bc-88ed-51bf-95b0-1d85854cee40 | textbox | Time Finish delivery
| checkpoint | Truck 3
39179c96-22e7-583a-b993-970f3a450dab | date | Date
31d61f20-9f41-553f-b1c4-f0936847c1c1 | textbox | Docket
53ea99ce-9e45-5126-8dd6-f657fa0bf24c | textbox | Time Batched
5092f566-7b70-58b2-9e1b-db5d311b884b | textbox | Truck Arrival Time
4afb59e6-6be2-5f12-a85f-cc891723915b | textbox | Load Size
c688301b-beee-5005-8420-1a0309f8ad0f | textbox | Slump
11cf7697-3793-55c6-8f37-846592529e6f | textbox | Slump Time
7e2fc2f4-2bec-5b72-8dcb-79f5d4ff8b6f | textbox | Concrete Arrival Temperature
fc2d6a4f-2bb2-5d3c-b350-dec69e48b334 | textbox | Ambient Temperature at time of slump
147e29d5-f066-5121-ba05-6a7870e51035 | textbox | Time Start delivery
5ff987f4-0647-53b1-88d9-4fa58dc2bf4b | textbox | Time Finish delivery
| checkpoint | Truck 4
56ec46d8-6704-5efe-bf95-88a21143fe8c | date | Date
adea7e86-5e71-5fb5-9876-c1bcca9facdc | textbox | Docket
acff2faf-5c46-55b1-94cf-cf717b338bf0 | textbox | Time Batched
3ff2b7ae-3474-5fa9-ac86-de65eb088e7f | textbox | Truck Arrival Time
6e7c1744-183c-57fe-971a-113c15f165ca | textbox | Load Size
911e5b30-1299-58b7-8358-e74301f66f02 | textbox | Slump
482620ad-2474-54dd-88b9-bdad58549205 | textbox | Slump Time
f8307dee-58e1-522c-8353-df25259f5f8e | textbox | Concrete Arrival Temperature
4b4a14c6-6076-5866-9669-aa4267d32c0d | textbox | Ambient Temperature at time of slump
cc3bbcf1-43e2-5181-beed-b9f66b1f9547 | textbox | Time Start delivery
1986ad3c-a459-5e5c-83c0-2840bed94c3e | textbox | Time Finish delivery
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off
| checklist | 70.02 - Concrete Record |  | 70.02 - Concrete Record |  | 0ef25b1d-63e3-4634-9711-3b573a52f48f
| section | Details
| checkpoint | 1 - Date
e31ddbd0-fc6e-5123-b927-52470c964a93 | date | Truck 1:
b1954871-76b1-5d46-bba8-9a60138abcfa | date | Truck 2:
7d82a3cc-3b28-5c62-8e4d-01f0a82b3986 | date | Truck 3:
c9c1a8da-87e8-5c67-876b-5fd03ce7373d | date | Truck 4:
| checkpoint | 2 - Docket
05bd2138-8a04-531c-8cd2-fe3f0a0ef3ca | textbox | Truck 1:
78af93e8-9b28-5257-b43d-791089993591 | textbox | Truck 2:
123e71e4-3d9b-554a-8024-a59ef252a33d | textbox | Truck 3:
e3163221-9a98-5a4d-ac14-febf58a385e2 | textbox | Truck 4:
| checkpoint | 3 - Time Batched
1e82fb86-d20b-587c-a064-b7a50d467a2c | textbox | Truck 1:
3b4c39a7-75dd-544c-84a3-f8566914cb76 | textbox | Truck 2:
8d4a9dde-dc44-5042-a894-95c4c6a7e6ef | textbox | Truck 3:
6e850f31-6990-53c4-a3aa-e1378ae23588 | textbox | Truck 4:
| checkpoint | 4 - Truck Arrival Time
6fee1edc-b82e-526c-96ba-5cfba93a8930 | textbox | Truck 1:
7c80a2d7-1bc0-5acd-9c10-a00aad79ba8a | textbox | Truck 2:
270fb6fc-7906-5e08-9c00-78a17fca95e4 | textbox | Truck 3:
1ad8540a-4826-5a46-b081-d49c94189eb3 | textbox | Truck 4:
| checkpoint | 5 - Load Size (m3)
04694081-eed2-5eef-9e87-473bcc299a67 | textbox | Truck 1: |  |  | m3
3b164171-5a09-5b4b-b583-9a8644f33763 | textbox | Truck 2: |  |  | m3
01b68ffe-b6e2-576f-8165-8bd4ab16b1fb | textbox | Truck 3: |  |  | m3
ebe21f5c-798a-58f4-9a5d-1f1f600d36cc | textbox | Truck 4: |  |  | m3
| checkpoint | 6 - Mix
| checkpoint | 7 - Slump (mm)
590a7e63-90f9-5810-b79c-6b73c00f3f27 | textbox | Truck 1: |  |  | mm
a5449662-2326-5cde-be9c-2f65ae43d66d | textbox | Truck 2: |  |  | mm
a5258d02-860c-5349-aa9f-f89ee63dcc9a | textbox | Truck 3: |  |  | mm
47e4c109-b5a9-5ab1-a249-bffcf24bab55 | textbox | Truck 4: |  |  | mm
| checkpoint | 8 - Slump Time
80dcf172-cf05-5f2d-b9ee-ce4b56301eb1 | textbox | Truck 1:
50885b53-ddbe-5fb2-8157-fcb4d8a7adab | textbox | Truck 2:
ed1dc5ec-bde6-5e94-b3e1-46f9f72bb26e | textbox | Truck 3:
9eb2dfd9-85a3-5b2a-ac07-4263f90a731b | textbox | Truck 4:
| checkpoint | 9 - Concrete Arrival Temperature (˚C)
ad3901d6-17ed-52d6-9614-a9986501c4fd | textbox | Truck 1: |  |  | ˚C
0abc09d8-bcb0-5458-96d0-2495a9febcb5 | textbox | Truck 2: |  |  | ˚C
c334e5f4-e3c0-5ad3-a218-a8dc5ad5f898 | textbox | Truck 3: |  |  | ˚C
75503d25-5a06-5a63-a55c-c5b3af7c7296 | textbox | Truck 4: |  |  | ˚C
| checkpoint | 10 - Ambient Temperature at time of slump (˚C)
1fac6e62-4210-55fa-a501-623924933376 | textbox | Truck 1: |  |  | ˚C
40a20a8a-fd4a-5b0f-8c7f-d9c462f46b68 | textbox | Truck 2: |  |  | ˚C
cf6e8141-2188-5278-8582-65755f06c03f | textbox | Truck 3: |  |  | ˚C
0d3834ba-ca26-5f35-b921-202ab038fb59 | textbox | Truck 4: |  |  | ˚C
| checkpoint | 11 - Time Start delivery
1bc3be20-dca1-5f55-8b2b-9b432663dd6f | textbox | Truck 1:
88ffc339-523c-50a2-84b3-707676524921 | textbox | Truck 2:
a7531d34-d2d3-5e4c-a555-55df68e37dc5 | textbox | Truck 3:
f1cf18ae-5df0-5ad3-befe-4f42963a6316 | textbox | Truck 4:
| checkpoint | 12 - Time Finish Delivery
eed787ad-7ff8-5af7-a058-5a80f9f670f5 | textbox | Truck 1:
4c1c6a89-ac0d-5578-bee5-5642ab4b5710 | textbox | Truck 2:
ceaadd30-96bf-532d-96e8-03e4f11d49aa | textbox | Truck 3:
1beac623-f51a-5ad6-a383-8636aa3e8d71 | textbox | Truck 4:
| checklist | 70.03 - Supply of Concrete | itp | 70.03 - Supply of Concrete |  | fb9d88e0-76c9-4cd2-95f4-33e170772ef2
| section | Details
| checkpoint | Mix designs for each class of concrete forwarded to Administrator at least 4 weeks prior to first delivery
dd6bd8a3-d993-5a1a-8ddc-b828c9de2c95 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9af0f4c5-0dae-59ba-a6df-f62f4a66d6e3 | note | Check Item - Milestone
0cb0abc3-ee65-513a-9be2-0634a18d13bd | note | Reference - MRTS70 Cl 9.2
| checkpoint | Where travel or placement times are, by neccessity, longer than those listed in Table 10.4 a procedure shall be submitted to the Adminstrator for approval.
7761004a-1b55-5bee-8630-e8efe12f6a8a | note | Acceptance Criteria & Frequency (Project Specific) - Written, 6 weeks notice
5f0f694d-5119-5bfa-87d0-aafcfd70db84 | note | Check Item - Milestone
decb691c-c49a-5114-883b-ecf8dae9680b | note | Reference - MRTS70 Cl 10.5.1, 15.1.1 & Cl 17.6.1
| checkpoint | All mixes >20MPa have a trial mix complete and Administrator given 3 days notice.
ce2ef4f0-20db-5d39-b50e-ac6f4d1abf65 | note | Acceptance Criteria & Frequency (Project Specific) - f'c, Each Mix
f3b325a7-d0d9-5d54-aa91-21ca04f3c5fb | note | Check Item - Witness Point 1
9382b51e-ab07-5805-8f1b-50484f939343 | note | Reference - MRTS70 Cl 15.1.1
| checkpoint | Concrete not incorporated into works until trial mix completed or ready mixed concrete supplier is approved.
2227937f-898b-5bb3-ae50-6c6419648df5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4f324759-72b9-5cb4-b150-0df5617b4601 | note | Check Item - Hold Point 1
d8c9032b-f3e6-5117-9baa-6845fe92d422 | note | Reference - MRTS70 Cl 15.1
| signoff | HOLD POINT
| checkpoint | All aggregate shall be sampled in accordance with AS 2758.1 during concrete production and tested for conformance to the aggregate requirements in MRTS70 clause 7.8 or Quarry assessment and certification approved
eb25c73a-295f-5420-a4c6-4dd15f413cea | note | Acceptance Criteria & Frequency (Project Specific) - Visual
daecfef5-e093-5c4a-ba79-5b6fb4c3821d | note | Check Item - Check Item
be1c3e65-9555-58bb-b4c4-7fe36ed94cf2 | note | Reference - MRTS70 Cl 7.5
| checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
d896bde3-042e-57e6-8495-5ed41bdb0d2a | note | Acceptance Criteria & Frequency (Project Specific) - Visual, Ambient temp. > 35 degrees
c7a1b771-ca4c-586b-96df-d3526779a9df | note | Check Item - Milestone
8eb63850-8325-5ea6-acd3-8e5b7854cb8b | note | Reference - MRTS70 Cl 13.1
| checkpoint | Final Verification
ae17b77d-6efb-58f4-b5cd-3b9b08164318 | note | Project Manager Verify that the Above has been Constructed according to Specification
ccb1fd6d-f21a-5f90-ad89-f254cd7f448a | textbox | Print Name:
1a6e38b3-5c0a-5b42-bf63-0409bb14b5c9 | date | Date:
64e5ce35-deff-51b4-b371-045f1b073751 | note | Client Verify that the Above has been Constructed according to Specification
77ebed6e-e6b6-599b-b29d-0d433ae1f06a | textbox | Print Name:
af9356b1-4fc9-522e-b7cd-0502f3365156 | date | Date:
| signoff | Sign ITP
| section | Final Sign Offs (to be completed at closure of Lot)
| checkpoint | Agreed Quantities
| signoff | Agreed Quantities Sign Off
| checkpoint | Closure of Lot
| signoff | Closure of Lot Sign Off