## 1. Clearing & Grubbing
Closed |  | Open |  | Lot Requirements
# | Lot No | Title | Symal ITP | Lot Map | Signed Hold Points | Enviromental Permit | NCR | Lot Status | Lot Opened On | Lot Opened By | Comments
1 | 1630-SYM-EAL-0001 | Tree Clearing - McGregor South 220112 | 1630-P200-SYM-QAC-ITP-0001 | Yes | Yes | Yes | N/A | Closed | 2023-01-12 | Courtney Brighton
2 | 1630-SYM-EAL-0015 | Topsoil Strip - McGregor Road (North) - EB On Ramp | 1630-P200-SYM-QAC-ITP-0001 | Yes | Yes | Yes | N/A | Closed | 2023-02-13 | Brad Pfitzner
3 | 1630-SYM-EAL-0003 | Tree Clearing - Healesville-Koo Wee Rup Rd - NW Diamond | 1630-P200-SYM-QAC-ITP-0001 | Yes | Yes | yes | N/A | Awaiting verification | 2023-01-16 | Zachary Gilbert
4 | 1630-SYM-EAL-0004 | Tree Clearing - Healesville-Koo Wee Rup Rd - SW Diamond | 1630-P200-SYM-QAC-ITP-0001 | Yes | Yes | Yes | N/A | Closed | 2023-01-16 | Zachary Gilbert
5 | 1630-SYM-EAL-0011 | Tree Clearing - McGregor Road North | 1630-P200-SYM-QAC-ITP-0001 | Yes | Yes | Yes | N/A | Closed | 2023-02-09 | Zachary Gilbert
6 | 1630-SYM-EAL-0017 | Tree Clearing - Compound | 1630-P200-SYM-QAC-ITP-0001
7 | 1630-SYM-EAL-0051 | Tree Clearing - Commercial Drive | 1630-P200-SYM-QAC-ITP-0001
8 | 1630-SYM-EAL-0094 | Existing Sed Basin - Clearing and Grubbing | 1630-P200-SYM-QAC-ITP-0001 | Yes | Yes | Yes | N/A | Awaiting verification
9 | 1630-SYM-EAL-0002 | Topsoil Strip - McGregor Road (South) - WB Exit Ramp | 1630-P200-SYM-QAC-ITP-0001 | Yes | Yes | Yes | N/A | Awaiting verification |  | Nicholas Dimopoulos
10 | 1630-SYM-EAL-0107 | Top soil strrpping - Princes Freeway South | 1630-P200-SYM-QAC-ITP-0001 |  | No |  | N/A | Work in Progress |  | Nicholas Dimopoulos
11 | 1630-SYM-EAL-0127 | Tree Clearing - Healesville-Koo Wee Rup Rd - South Gate 7 | 1630-P200-SYM-QAC-ITP-0001 | Yes | Yes | Yes | N/A | Awaiting verification |  | Zachary Gilbert

## 2. Cut Floor
|  |  | Link - | Subgrade
Closed | 0 | Open | 0 | Lot Requirements |  |  | Lot Requirements
# | Lot No | Title | ITP | Lot Map | CHAINAGE FROM | CHAINAGE TO | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compaction Test Result | Proof Roll | CBR Test Result | NCR | Lot Status | Lot Opened On | Lot Opened By | Comments
1 | 1630-SYM-EAL-0010 | Cut Floor Gorund Improvement - Lime/Cement Stabilisation - McGregor Road (South) WB Exit Ramp | 1630-P200-SYM-QAC-ITP-0002 | Yes | 3420.00 | 3600.00 | N/A, Refer Layer 1 Type B Fill | Yes | Yes | Yes | Yes | Yes |  | Awaiting Verification | 2023-09-02 | Nicholas Dimopoulos
2 | 1630-SYM-EAL-0006 | Cut Floor Ground Improvement - McGregor Road (South) WB Exit Ramp - Blend of In Situ and Type B | 1630-P200-SYM-QAC-ITP-0002 | Yes | 3600.00 | 3680.00 | N/A, Refer Layer 1 Type B Fill | Yes | N/A | Yes | Yes | Yes |  | Awaiting Verification | 23/01/2023 | Nicholas Dimopoulos
3 | 1630-SYM-EAL-0005 | Cut Floor Ground Improvement - McGregor Road (South) WB Exit Ramp - Rip & Re-Compact | 1630-P200-SYM-QAC-ITP-0002 | Yes | 3680.00 | 3700.00 | N/A, Refer Layer 1 Type B Fill | Yes | N.A | N/A | Yes | N/A |  | Awaiting Verification | 23/01/2023 | Nicholas Dimopoulos
4 | 1630-SYM-EAL-0012 | Cut Floor Ground Improvement - McGregor Road (South) WB Exit Ramp - Remove and Replace | 1630-P200-SYM-QAC-ITP-0002 | Yes | 3710.00 | 3750.00 | No | No | N.A | N/A | Yes | N/A |  | Awaiting Test Results | 2023-11-02 | Nicholas Dimopoulos | Dependent on water main / Drainage line completion
5 | 1630-SYM-CIL-0001 | Cut Floor Ground Improvement - McGregor Road (North - Rip & Re-Compact | 1630-P200-SYM-QAC-ITP-0002 | Yes | 2100.00 | 2300.00 | N/A, Refer Layer 1 Type B Fill | Yes | N/A | Yes | No | Yes |  | Awaiting Verification | 24/02/2023 | Nicholas Dimopoulos
6 | 1630-SYM-EAL-0074 | Cut Floor Ground Improvement - McGregor Road (South) and Freeway South | 1630-P200-SYM-QAC-ITP-0002 | Yes | 3000 | 3400 | N/A, Refer Layer 1 Type B Fill | Yes | N/A | Yes | Yes | Yes |  | Awaiting Verification | 2023-03-22 | Nicholas Dimopoulos
7 | 1630-SYM-EAL-0106 | Cut Floor Ground Improvement - McGregor Road (South) and Freeway South | 1630-P200-SYM-QAC-ITP-0002 | Yes | 3040 | 3400 | N/A, Refer Layer 1 Type B Fill | No | N/A | Yes | No | No |  | Awaiting Test Results |  | Nicholas Dimopoulos
8 | 1630-SYM-EAL-0110 | Cut Floor Ground Improvement - McGregor Road (South) and Freeway South | 1630-P200-SYM-QAC-ITP-0002 | Yes | 3040 | 3400 | N/A, Refer Layer 1 Type B Fill | No | N/A | Yes | Yes | Yes |  | Awaiting Test Results |  | Nicholas Dimopoulos
9 | 1630-SYM-EAL-0083 | Cut Floor / existing sed basin group improvement - South HKWRR | 1630-P200-SYM-QAC-ITP-0002
10
11
12
13
14
15
16
17
18
19
20

## 3. Type B
Closed | 0 | Open | 0 | Lot Requirements
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compaction Test Result | CBR Test Result | Proof Roll | Comments | Lot Status | Lot Opened On | Lot Opened By | Comments
1 | 1630-SYM-EAL-0007 | Type B Capping Layer - McGregor Road (South) WB Exit Ramp | 1630-P200-SYM-QAC-ITP-0007 | [8 empty] | CANCELLED | 2023-01-25 | Brad Pfitzner
2 | 1630-SYM-EAL-0016 | Type B Fill - Layer 1 - McGregor Road South | 1630-P200-SYM-QAC-ITP-0007 | Yes | Yes | Yes | No | Yes | Yes | Yes | Swell = 2.5% | Awaiting survey | 15/02/2023 | Nicholas Dimopoulos
3 | 1630-SYM-EAL-0014 | Type B Fill - Layer 1 - McGregor Road South | 1630-P200-SYM-QAC-ITP-0007 | Yes | Yes | Yes | No | Yes | Yes | Yes |  | Awaiting survey | 13/02/2023 | Nicholas Dimopoulos
4 | 1630-SYM-EAL-0026 | Type B Fill - Layer 2 - McGregor Road South | 1630-P200-SYM-QAC-ITP-0007 | Yes | Yes | Yes | No | Yes | No | Yes |  | Awaiting Test Results | 2023-01-03 | Nicholas Dimopoulos
5 | 1630-SYM-EAL-0029 | Type B Fill - Layer 3 - McGregor Road South | 1630-P200-SYM-QAC-ITP-0007 | Yes | Yes | No | No | Yes | Yes | No | CBR = 2.0% | Awaiting Test Results | 2023-03-03 | Nicholas Dimopoulos
6 | 1630-SYM-EAL-0034 | Type B Fill - Layer 4 - McGregor Road South | 1630-P200-SYM-QAC-ITP-0007 | Yes | Yes | Yes | No | Yes | Yes | Yes |  | Awaiting survey | 2023-04-03 | Nicholas Dimopoulos
7 | 1630-SYM-EAL-0036 | Type B Fill - Layer 5 - McGregor Road South | 1630-P200-SYM-QAC-ITP-0007 | Yes | Yes | Yes | No | Yes | Yes | Yes | Swell = 2.5% | Awaiting survey | 2023-06-03 | Nicholas Dimopoulos
8 | 1630-SYM-EAL-0035 | Type B Fill - Layer 6 - McGregor Road South | 1630-P200-SYM-QAC-ITP-0007 | Yes | Yes | No | No | Yes | Yes | No |  | Awaiting Test Results | 2023-07-03 | Nicholas Dimopoulos
9 | 1630-SYM-EAL-0070 | Type B Fill - Layer 1 - McGregor Road North | 1630-P200-SYM-QAC-ITP-0007 | Yes | Yes | Yes | No | Yes | No | Yes |  | Awaiting Test Results | 2023-03-21 | Nicholas Dimopoulos
10 | 1630-SYM-EAL-0071 | Type B Fill - Layer 2 - McGregor Road North | 1630-P200-SYM-QAC-ITP-0007 | Yes | Yes | No | No | Yes | Yes | No |  | Awaiting survey | 2023-03-21 | Nicholas Dimopoulos | CONQA
11 | 1630-SYM-EAL-0072 | Type B Fill - Layer 2 - McGregor Road North | 1630-P200-SYM-QAC-ITP-0007 | Yes | No | Yes | No | Yes | Yes | Yes |  | Awaiting survey | 2023-03-22 | Nicholas Dimopoulos | CONQA
12 | 1630-SYM-EAL-0073 | Type B Fill - Layer 3 - McGregor Road North | 1630-P200-SYM-QAC-ITP-0007 | Yes | No | Yes | No | Yes | Yes | Yes |  | Awaiting survey | 2023-03-24 | Nicholas Dimopoulos | CONQA
13 | 1630-SYM-EAL-0076 | Type B Fill - Layer 4 - McGregor Road North | 1630-P200-SYM-QAC-ITP-0007 | Yes | No | Yes | No | Yes | Yes | Yes |  | Awaiting survey | 2023-03-28 | Nicholas Dimopoulos | CONQA
14 | 1630-SYM-EAL-0078 | Type B Fill - Layer 5 - McGregor Road North | 1630-P200-SYM-QAC-ITP-0007 | Yes | No | No | No | No | No | No | TR-040 not recieved | Awaiting Test Results, Proof Roll, Survey | 2023-03-29 | Nicholas Dimopoulos | CONQA
14 | 1630-SYM-EAL-0077 | Type B Fill - Layer 1 - Freeway South | 1630-P200-SYM-QAC-ITP-0007 | Yes | No | No | No | Yes | No |  |  | Awaiting Test Results, Proof Roll, Survey |  | Nicholas Dimopoulos
| 1630-SYM-EAL-0021 | Type B Fill Layer 1 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean & Std Dev Survey
| 1630-SYM-EAL-0028 | Type B Fill Layer 2 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Std Dev Survey
| 1630-SYM-EAL-0031 | Type B Fill Layer 3 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes
| 1630-SYM-EAL-0032 | Type B Fill Layer 4 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean & Std Dev Survey
| 1630-SYM-EAL-0041 | Type B Fill Layer 5 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Std Dev Survey
| 1630-SYM-EAL-0042 | Type B Fill Layer 6 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes
| 1630-SYM-EAL-0044 | Type B Fill Layer 7 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes
| 1630-SYM-EAL-0046 | Type B Fill Layer 8 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean & Std Dev Survey
| 1630-SYM-EAL-0047 | Type B Fill Layer 9 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | No | Yes | Std Dev Survey
| 1630-SYM-EAL-0075 | Type B Fill Layer 10 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | Yes | No | Yes
| 1630-SYM-EAL-0081 | Type B Fill Layer 11 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | No | No | Yes
| 1630-SYM-EAL-0084 | Type B Fill Layer 12 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0089 | Type B Fill Layer 13 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0090 | Type B Fill Layer 14 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | Yes | No | Yes
| 1630-SYM-EAL-0095 | Type B Fill Layer 15 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0096 | Type B Fill Layer 16 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0099 | Type B Fill Layer 17 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | No | No | Yes
| 1630-SYM-EAL-0108 | Type B Fill Layer 18 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0114 | Type B Fill Layer 19 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0115 | Type B Fill Layer 20 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | No | No | Yes
| 1630-SYM-EAL-0116 | Type B Fill Layer 21 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0119 | Type B Fill Layer 22 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0033 | Type B Fill Layer 1 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Std Dev Survey
| 1630-SYM-EAL-0037 | Type B Fill Layer 2 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean & Std Dev Survey
| 1630-SYM-EAL-0038 | Type B Fill Layer 3 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean, Std Dev, # Points Survey
| 1630-SYM-EAL-0039 | Type B Fill Layer 4 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean & Std Dev Survey
| 1630-SYM-EAL-0040 | Type B Fill Layer 5 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean & Std Dev Survey
| 1630-SYM-EAL-0045 | Type B Fill Layer 6 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean, Std Dev, # Points Survey
| 1630-SYM-EAL-0048 | Type B Fill Layer 7 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | No | Yes | Std Dev Survey
| 1630-SYM-EAL-0049 | Type B Fill Layer 8 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | No | Yes | Std Dev Survey
| 1630-SYM-EAL-0082 | Type B Fill Layer 9 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | Yes | No | Yes
| 1630-SYM-EAL-0086 | Type B Fill Layer 10 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0087 | Type B Fill Layer 11 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0088 | Type B Fill Layer 12 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | No | No | Yes
| 1630-SYM-EAL-0098 | Type B Fill Layer 13 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0101 | Type B Fill Layer 14 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | No | No | Yes
| 1630-SYM-EAL-0111 | Type B Fill Layer 15 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | No | No | Yes
| 1630-SYM-EAL-0112 | Type B Fill Layer 16 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0113 | Type B Fill Layer 17 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0120 | Type B Fill Layer 18 - HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | No | No | Yes
| 1630-SYM-EAL-0103 | Type B Fill - Layer 2 - Freeway South | 1630-P200-SYM-QAC-ITP-0008 | Yes | [5 empty] | Yes |  | Awaiting Test Results |  | Nicholas Dimopoulos
| 1630-SYM-EAL-0104 | Type B Fill - Layer 3 - Freeway South | 1630-P200-SYM-QAC-ITP-0008 | Yes | [5 empty] | No |  | Awaiting Test Results |  | Nicholas Dimopoulos
15 | 1630-SYM-EAL-0077 | Type B Fill - Layer 1 - Freeway South | 1630-P200-SYM-QAC-ITP-0007 | Yes | No | No | No | Yes | Yes |  | Same as 1630-SYM-EAL-0079, test results for 0079 | Awaiting Test Results | 2023-03-28 | Nicholas Dimopoulos
16 | 1630-SYM-EAL-0103 | Type B Fill - Layer 2 - Freeway South | 1630-P200-SYM-QAC-ITP-0007 | Yes | No | No | No | Yes | Yes |  |  | Awaiting survey | 2023-04-18 | Nicholas Dimopoulos
17 | 1630-SYM-EAL-0104 | Type B Fill - Layer 3 - Freeway South | 1630-P200-SYM-QAC-ITP-0007 | Yes | No | No | No | Yes | Yes |  | 98.7% CDR | Awaiting survey | 2023-03-24 | Nicholas Dimopoulos
18 | 1630-SYM-EAL-0126 | Type B Fill - Layer 4 - Freeway South | 1630-P200-SYM-QAC-ITP-0007 | Yes | No | No | No | No | No |  |  |  | 2023-05-05 | Nicholas Dimopoulos
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Internal proof roll correspondence
Note on K11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Internal proof roll correspondence

## 4. Type A
Closed | 0 | Open | 0 | Lot Requirements
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compaction Test Result | CBR Test Result | Proof Roll | Comments | Lot Status | Lot Opened On | Work Started | Work Completed | Lot Opened By | Comments
1 | 1630-SYM-EAL-0018 | Type A Fill Layer 1 - HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Mean & Std Dev Survey | Work in Progress | 2023-02-14 | 2023-02-22 | 2023-02-24 | Zachary Gilbert
2 | 1630-SYM-EAL-0020 | Type A Fill - Layer 2 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean & Std Dev Survey |  | 2023-02-22 | 2023-02-23 | 2023-02-27 | Zachary Gilbert
| 1630-SYM-EAL-0022 | Type A Fill - Layer 3 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean & Std Dev Survey |  | 2023-02-22 | 2023-02-27 | 2023-02-27 | Zachary Gilbert
| 1630-SYM-EAL-0023 | Type A Fill - Layer 4 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean & Std Dev Survey |  | 2023-02-27 | 2023-02-27 | 2023-02-28 | Alexandra Holman
| 1630-SYM-EAL-0024 | Type A Fill - Layer 5 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean & Std Dev Survey Grading |  | 2023-02-28 | 2023-02-28 |  | Alexandra Holman
| 1630-SYM-EAL-0025 | Type A Fill - Layer 6 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Std Dev Survey |  | 2023-03-01 |  |  | Alexandra Holman
| 1630-SYM-EAL-0027 | Type A Fill - Layer 7 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes | Grading |  | 2023-03-02 |  |  | Alexandra Holman
| 1630-SYM-EAL-0043 | Type A Fill - Layer 8 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes |  |  | 2023-03-09 |  |  | Alex Redman
| 1630-SYM-EAL-0052 | Type A Fill - Layer 9 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes |  |  | 2023-03-09
| 1630-SYM-EAL-0053 | Type A Fill - Layer 10 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes | Grading
| 1630-SYM-EAL-0054 | Type A Fill - Layer 11 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | No | Yes
| 1630-SYM-EAL-0058 | Type A Fill - Layer 12 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes
| 1630-SYM-EAL-0059 | Type A Fill - Layer 13 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes
| 1630-SYM-EAL-0060 | Type A Fill - Layer 14 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | No | Yes
| 1630-SYM-EAL-0066 | Type A Fill - Layer 15 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | No | Yes
| 1630-SYM-EAL-0067 | Type A Fill - Layer 16 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | No | Yes
| 1630-SYM-EAL-0068 | Type A Fill - Layer 17 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | No | Yes
| 1630-SYM-EAL-0085 | Type A Fill - Layer 18 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0091 | Type A Fill - Layer 19 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | No | No | Yes
| 1630-SYM-EAL-0097 | Type A Fill - Layer 20 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0100 | Type A Fill - Layer 21 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | No | No | No
| 1630-SYM-EAL-0105 | Type A Fill - Layer 22 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | No | No | No
| 1630-SYM-EAL-0117 | Type A Fill - Layer 23 HKWRR North Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | No | No | No
| 1630-SYM-EAL-0050 | Type A Fill - Layer 1 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes
| 1630-SYM-EAL-0055 | Type A Fill - Layer 2 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes | Grading
| 1630-SYM-EAL-0056 | Type A Fill - Layer 3 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes
| 1630-SYM-EAL-0057 | Type A Fill - Layer 4 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | No | Yes
| 1630-SYM-EAL-0061 | Type A Fill - Layer 5 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | No | Yes
| 1630-SYM-EAL-0062 | Type A Fill - Layer 6 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | Yes | Yes
| 1630-SYM-EAL-0063 | Type A Fill - Layer 7 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | Yes | No | Yes | No | Yes
| 1630-SYM-EAL-0064 | Type A Fill - Layer 8 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | Yes | Yes | No | Yes | Yes | Yes | Mean & Std Dev Survey
| 1630-SYM-EAL-0065 | Type A Fill - Layer 9 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | Yes | Yes | Yes
| 1630-SYM-EAL-0069 | Type A Fill - Layer 10 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0092 | Type A Fill - Layer 11 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | No | No | Yes
| 1630-SYM-EAL-0093 | Type A Fill - Layer 12 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | Yes | No | No | No | N/A | N/A | Yes
| 1630-SYM-EAL-0102 | Type A Fill - Layer 13 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | No | No | No
| 1630-SYM-EAL-0109 | Type A Fill - Layer 14 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | No | No | No
| 1630-SYM-EAL-0118 | Type A Fill - Layer 15 HKWRR South Embankment | 1630-P200-SYM-QAC-ITP-0008 | No | No | No | No | No | No | No
| 1630-SYM-CIL-0002 | Verge (RHS) - Layer 1 - McGregor Road | 1630-P200-SYM-QAC-ITP-0009 | Yes | No | No | No | Yes | Yes |  | CBR = 3% | Awaiting Test Results
| 1630-SYM-CIL-0003 | Verge (RHS) - Layer 2 - McGregor Road | 1630-P200-SYM-QAC-ITP-0012 | Yes | No | No | No | Yes |  |  |  | Awaiting Test Results
| 1630-SYM-CIL-0004 | Verge (LHS) - Layer 1 - McGregor Road | 1630-P200-SYM-QAC-ITP-0012 | Yes | No | No | No | No |  |  |  | Work in Progress

## 5. Drainage Pits
Link to folder
Closed | 0 | Open |  | Lot Requirements
# | Lot No | Title | Lot Map | ITP | Compliance Certificate | Approved Mix Design | Delivery Docket / Invoice | Concrete Mix Registration | Grading Report | Incoming Material Docket | Step Iron Compliance | Shop Card | Survey Report | Lot Status | Lot Opened On | Lot Opened By | Comments
| 1630-SYM-DRL-0001 | Drainage Install - A-03-2 to A-03-1 AND A-04-2 to A-04-1 | [11 empty] | Work In Progress | 27/04/2023 | Nicholas Dimopoulos

## 6. Stormwater Drainage Run
[5 empty] | Links - | Lot Folder | Testing
Closed | 0 |  | Open |  | 0 | Lot Requirements
Lot No. | Description of Work | Location | Pipe Size/Class | Length | ITP | Lot Map | Surveyor Report Reference | Delivery Docket | Vic Roads Mix Design | Bedding Material Docket | D.O.T Mix Registration | Quarry Grading | Certificate of Conformance | Test Report | CCTV Report | NCR | Lot Status | Lot Opened On | Lot Opened By | Comments
| A-01-1 to A-01-2 | McGregor Ramp | ᶲ150 HDPE | 3.812
| A-02-1 to A-02-2 | McGregor Ramp | 2 x ᶲ150 PVC | 6.178
1630-SYM-DRL-0001 | A-03-1 to A-03-2 | McGregor Ramp | ᶲ375 RCP CL 3 | 32.296 | 1630-SYM-QAC-ITP-0011 | Yes | No | No | No | No | No | No | No | No | No
1630-SYM-DRL-0001 | A-04-1 to A-04-2 | McGregor Ramp | ᶲ375 RCP CL 3 | 32.579 | 1630-SYM-QAC-ITP-0011 | Yes | No | No | No | No | No | No | No | No | No
| A-05-1 to A-05-2 | McGregor Ramp | ᶲ375 HDPE | 17.451
| C-01-1 to C-01-2 | Princes Freeway | ᶲ375 HDPE | 6.365
| C-02-1 to C-02-2 | Princes Freeway | 2 x ᶲ150 PVC | 9.765
| C-03-1 to C-03-2 | Princes Freeway | ᶲ375 RCP CL 4 | 16.421
| C-04-1 to C-04-2 | Princes Freeway | ᶲ450x300 RCBC | 15.284
| EX-17-4 to D-01-1 | HKWRR | ᶲ375 HDPE | 18.953
| D-01-1 to D-01-2 | HKWRR | ᶲ375 HDPE | 38.025
| D-01-2 to D-01-3 | HKWRR | ᶲ375 HDPE | 79.007
| D-01-3 to D-01-4 | HKWRR | ᶲ375 RCP CL 3 | 57.387
| D-01-4 to D-01-5 | HKWRR | ᶲ150 PVC | 1.36
| D-02-1 to D-02-2 | HKWRR | 2 x ᶲ150 PVC | 3.851
| D-01-1 to D-03-1 | HKWRR | ᶲ375 RCP CL 3 | 28.448
| D-03-1 to D-03-2 | HKWRR | ᶲ375 HDPE | 38.991
| D-03-2 to D-03-3 | HKWRR | ᶲ375 HDPE | 62.713
| D-03-3 to D-03-4 | HKWRR | ᶲ375 HDPE | 38.232
| D-03-4 to D-03-5 | HKWRR | ᶲ375 HDPE | 20.991
| D-03-5 to D-03-6 | HKWRR | ᶲ375 RCP CL 3 | 11.137
| D-06-2 to D-04-1 | HKWRR | ᶲ375 HDPE | 22.949
| D-04-1 to D-04-2 | HKWRR | ᶲ375 RCP CL 3 | 7.954
| D-06-2 to D-05-1 | HKWRR | ᶲ375 RCP CL 3 | 30.228
| D-05-1 to D-05-2 | HKWRR | ᶲ375 HDPE | 10.524
| D-06-1 to D-06-2 | HKWRR | ᶲ375 HDPE | 37.286
| D-09-1 to D-09-2 | HKWRR | ᶲ375 RCP CL 3 | 13.66
| D-10-1 to D-10-2 | HKWRR | ᶲ375 RCP CL 4 | 25.457
| EX-03-2 to D-11-1 | HKWRR | ᶲ525 HDPE | 12.884
| D-11-1 to D-11-2 | HKWRR | ᶲ525 HDPE | 47.876
| D-11-2 to D-11-3 | HKWRR | ᶲ525 HDPE | 62.235
| D-11-3 to D-11-4 | HKWRR | ᶲ525 HDPE | 48.234
| D-11-4 to D-11-5 | HKWRR | ᶲ525 HDPE | 40.188
| D-11-5 to D-11-6 | HKWRR | ᶲ375 HDPE | 32.029
| D-11-5 to D-12-1 | HKWRR | ᶲ525 RCP CL 3 | 27.407
| D-12-1 to D-12-2 | HKWRR | ᶲ525 RCP CL 3 | 38.356
| D-12-2 to D-12-3 | HKWRR | ᶲ375 HDPE | 5.059
| D-13-1 to D-13-2 | HKWRR | 2 x ᶲ150 PVC | 5.308
| D-14-1 to D-14-2 | Princes Freeway | 2 x ᶲ150 PVC | 4.927
| D-16-2 to D-15-1 | HKWRR | ᶲ375 HDPE | 38.042
| D-15-1 to D-15-2 | HKWRR | ᶲ375 HDPE | 105.47
| D-15-2 to D-15-3 | HKWRR | ᶲ150 PVC | 2.186
| D-16-1 to D-16-2 | HKWRR | ᶲ375 HDPE | 15.32
| D-16-2 to D-16-3 | HKWRR | ᶲ375 RCP CL 3 | 26.75
| D-16-3 to D-16-4 | HKWRR | ᶲ375 HDPE | 60.04
| D-16-4 to D-16-5 | HKWRR | ᶲ375 HDPE | 31.608
| D-16-5 to D-16-6 | HKWRR | ᶲ375 RCP CL 3 | 10.088
| D-17-1 to D-17-2 | HKWRR | ᶲ375 RCP CL 3 | 19.46
| D-17-2 to D-17-3 | HKWRR | ᶲ375 HDPE | 30.008
| D-20-1 to D-20-2 | HKWRR | ᶲ375 HDPE | 16.611
| D-21-1 to D-21-2 | HKWRR | ᶲ1200 RCP CL 2 | 31.678
| D-21-2 to D-21-3 | HKWRR | ᶲ1200 RCP CL 2 | 95.11
| D-21-3 to D-21-4 | HKWRR | ᶲ1200 RCP CL 2 | 22.012
| D-21-4 to D-21-5 | HKWRR | ᶲ1200 RCP CL 3 | 24.407
| D-21-5 to D-21-6 | HKWRR | ᶲ1200 RCP CL 3 | 37.009
| D-21-6 to D-21-7 | HKWRR | ᶲ1200 RCP CL 3 | 36.506
| D-21-7 to D-21-8 | HKWRR | ᶲ1200 RCP CL 3 | 53.857
| D-21-8 to D-21-9 | HKWRR | ᶲ1200 RCP CL 2 | 15.125
| D-22-1 to D-22-2 | HKWRR | ᶲ675 HDPE | 7.5
| D-21-8 to D-23-1 | HKWRR | ᶲ525 HDPE | 6.911
| D-23-1 to D-23-2 | HKWRR | ᶲ375 HDPE | 1.238
| D-21-5 to D-24-1 | HKWRR | ᶲ375 HDPE | 8.649
| D-25-1 to D-25-2 | HKWRR | ᶲ300 HDPE | 17.395
| D-26-1 to D-26-2 | HKWRR | 2 x ᶲ150 PVC | 11.206
| D-27-1 to D-27-2 | HKWRR | ᶲ375 HDPE | 9.623
| D-28-1 to D-28-2 | HKWRR | 2 x ᶲ150 PVC | 10.22
| D-21-3 to D-30-1 | HKWRR | ᶲ375 HDPE | 9.698
| D-30-1 to D-30-2 | HKWRR | ᶲ375 HDPE | 21.006
| D-30-2 to D-30-3 | HKWRR | ᶲ375 HDPE | 1.306
| D-30-3 to D-30-4 | HKWRR | ᶲ375 HDPE | 25.809
| D-30-4 to D-30-5 | HKWRR | ᶲ375 HDPE | 28.099
| D-30-5 to D-30-6 | HKWRR | ᶲ375 RCP CL 4 | 29.519
| D-15-1 to D-31-1 | HKWRR | ᶲ375 RCP CL 3 | 16.141
| D-32-1 to D-32-2 | HKWRR | ᶲ375 HDPE | 4.064
| DG-02-1 to DG-02-2 |  | 2 x ᶲ150 PVC | 4.176
| EX-E-02-8 to E-01-1 |  | ᶲ375 HDPE | 18.139

## 7. Subsoil Drainage
|  |  | Link - | SSD
Closed | 0 | Open | 0 | Lot Requirements
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Agi Compliance | Agi delivery | Vic Roads Rock Compliance | No Fines Docket | Sand Docket | CCTV Footage | CCTV Report | Rock Grading Report | Hold Points Signed Off | NCR | Lot Status | Lot Opened On | Lot Opened By | Comments

## 8. Lower Subbase
|  |  | Link - | Lower Subbase
Closed | 0 | Open | 0 | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Approved Mix Designs | Monthly Quarry Grading | Proof Roll | Test Result | Delivery Dockets | NCR | Lot Status | Lot Opened On | Lot Opened By | Comments

## 9. Upper Subbase
|  |  | Link - | Cementitious Treated
Closed | 0 | Open | 0 | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Approved Mix Designs | Monthly Quarry Grading | Test Result | Delivery Dockets | NCR | Lot Status | Lot Opened On | Lot Opened By

## 10. Kerb
Closed | 0 | Open | 0 | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Concrete Mix Designs | Delivery Dockets | NCR | Lot Status | Lot Opened On | Lot Opened By | Comments
99 | 1120-SYM-CIL-0107 | United Driveway - Kerb In-suti - 18.01.22 | No | No | No | No | No | No | No | CANCELLED | 2022-01-17 | Bradley Pfitzner (SYMAL)
263 | 1120-SYM-CIL-0271 | Zone 3 EB Kerb | No | No | No | No | No | No | No | CANCELLED | 2022-07-31 | Christian Figueroa (SYMAL)

## 11. Asphalt
Closed | 0 | Open | 0 | Lot Requirments
# | Lot No | Title | Lot Type | Lot Map | ITP | Signed Hold Points | Vicroads Approval Certificate | Quality Records From batch Plants | Asphalt Placement Plan | Delivery Dockets | NATA Test Reports | Conformance Report | Closed Out NCR | Closed Out RFI | Lot Status | Lot Opened On | Lot Opened By | Comments

## 12. General Concrete Paving
Closed | 0 | Open | 0 | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compliance Certificate for Mix | Certificate of Compliance for Reinformcement | Concrete Testing Results | Concrete Checklist | Pour Record | NCR | Lot Status | Lot Opened On | Lot Opened By | Symal Comments

## 13. TS & PL Conduit
Closed | 0 | Open | 0 | Lot Requirments
# | Lot No | Title | DM Roads ITP/Symal ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compliance Certification | Compaction Test Result | Incomign Material Grading | NCR | Lot Status | Lot Opened On | Lot Opened By | Comments

## 14.Guard Rail
Closed | #REF! | Open | #REF! | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compliance Certificate for Material | Certificate of Compliance for Install | NCR | Lot Status | Lot Opened On | Lot Opened By | Symal Comments

## 15.Utilities NCW
Closed | 0 | Open | 0 | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compliance Certificate for Material | Certificate of Compliance for Install | NCR | Lot Status | Lot Opened On | Lot Opened By | Symal Comments

## 16. Fencing
Closed | #REF! | Open | #REF! | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compliance Certificate for Material | Certificate of Compliance for Install | NCR | Lot Status | Lot Opened On | Lot Opened By | Symal Comments

## 17. SUP
Closed | #REF! | Open | #REF! | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compliance Certificate for Material | Compliance Certificate for Mix | Certificate of Compliance for Reinformcement | Concrete Testing Results | Concrete Checklist | Pour Record | NCR | Lot Status | Lot Opened On | Lot Opened By | Symal Comments

## 18. Structural Concrete
Closed | #REF! | Open | #REF! | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compliance Certificate for Mix | Certificate of Compliance for Reinformcement | Concrete Testing Results | Concrete Checklist | Pour Record | NCR | Lot Status | Lot Opened On | Lot Opened By | Symal Comments
556 | 1120-SYM-DRL-0255 | Rock Beaching outside Headwall C-09-01 | 1120 | DRL | WORK IN PROGRESS | 44748 | [6 empty] | Adam Aladin (SYMAL)
656 | 1120-SYM-EAL-0026 | HNRU_EVN_PMT_CLV_020 | 1120 | EAL | CANCELLED | 44595 | [6 empty] | Ahmed Kandash (SYMAL)
687 | 1120-SYM-STL-0001 | RW04 | 1120 | STL | OUTSTANDING | 44379 |  |  |  |  | 44379 |  | Zachary Gilbert (SYMAL)
688 | 1120-SYM-STL-0002 | RW01 | 1120 | STL | WORK IN PROGRESS | 44393 | [6 empty] | Zachary Gilbert (SYMAL)
689 | 1120-SYM-STL-0003 | RW02 - Soil Nails | 1120 | STL | CLOSED-OUT | 44455 | 44628 |  |  |  | 44490 | 44565 | Grant Mcinerney (SYMAL)
690 | 1120-SYM-STL-0003.S01 | RW02 - Soil Nails Row 1 | 1120 | STL | CLOSED-OUT | 44455 | 44628 |  |  |  | 44487 | 44621 | Grant Mcinerney (SYMAL)
691 | 1120-SYM-STL-0003.S02 | RW02 - Soil Nail Row 2(A) | 1120 | STL | CLOSED-OUT | 44455 | 44609 |  |  |  | 44575 | 44609 | Grant Mcinerney (SYMAL)
692 | 1120-SYM-STL-0003.S03 | RW02 - Soil Nail Row 2(B) | 1120 | STL | CLOSED-OUT | 44602 | 44721 |  |  |  | 44607 | 44721 | Grant Mcinerney (SYMAL)
693 | 1120-SYM-STL-0003.S04 | RW02 - Soil Nails Row 3 | 1120 | STL | CLOSED-OUT | 44642 | 44690 |  |  |  | 44640 | 44691 | Grant Mcinerney (SYMAL)
694 | 1120-SYM-STL-0004 | RW02 Shotcrete Master Lot | 1120 | STL | CLOSED-OUT | 44479 | 44628 |  |  |  | 44501 | 44596 | Grant Mcinerney (SYMAL)
695 | 1120-SYM-STL-0004.S01 | RW02 Shotcrete - Row 1 | 1120 | STL | CLOSED-OUT | 44479 | 44628 |  |  |  | 44501 | 44595 | Grant Mcinerney (SYMAL)
696 | 1120-SYM-STL-0004.S02 | RW02 Shotcrete Row2 (A) | 1120 | STL | CLOSED-OUT | 44571 | 44685 |  |  |  | 44594 | 44655 | Grant Mcinerney (SYMAL)
697 | 1120-SYM-STL-0004.S03 | RW02 Shotcrete Row 2(B) | 1120 | STL | CLOSED-OUT | 44609 | 44726 |  |  |  | 44609 | 44677 | Grant Mcinerney (SYMAL)
698 | 1120-SYM-STL-0004.S04 | RW02 Shotcrete Row 3 | 1120 | STL | CLOSED-OUT | 44642 | 44726 |  |  |  | 44501 | 44718 | Grant Mcinerney (SYMAL)
699 | 1120-SYM-STL-0004.S05 | RW02 Shotcrete Row 3(2) - Northern Section | 1120 | STL | AWAITING TEST RESULT | 44643 |  |  |  |  | 44664 | 44694 | Grant Mcinerney (SYMAL)
700 | 1120-SYM-STL-0005 | RW06 | 1120 | STL | CLOSED-OUT | 44439 | 44776 |  |  |  | 44456 | 44537 | Zachary Gilbert (SYMAL)
701 | 1120-SYM-STL-0006 | RW07 Post and panel | 1120 | STL | CLOSED-OUT | 44494 | 44748 |  |  |  | 44530 | 44223 | Zachary Gilbert (SYMAL)
702 | 1120-SYM-STL-0006.S01 | RW07 capping beam | 1120 | STL | CLOSED-OUT | 44494 | 44733 |  |  |  | 44546 | 44572 | Bradley Pfitzner (SYMAL)
703 | 1120-SYM-STL-0007 | RW08 Post and panel | 1120 | STL | CLOSED-OUT | 44474 | 44775 |  |  |  | 44518 | 44718 | Zachary Gilbert (SYMAL)
704 | 1120-SYM-STL-0007.S01 | RW08 Capping beam P1-P2 | 1120 | STL | CLOSED-OUT | 44474 | 44732 |  |  |  | 44687 | 44683 | Bradley Pfitzner (SYMAL)
705 | 1120-SYM-STL-0007.S02 | RW08 Capping beam P3-P4 | 1120 | STL | CLOSED-OUT | 44670 | 44775 |  |  |  | 44671 | 44684 | Bradley Pfitzner (SYMAL)
706 | 1120-SYM-STL-0008 | RW05 Post and panel | 1120 | STL | CLOSED-OUT | 44586 | 44713 |  |  |  | 44615 | 44698 | Zachary Gilbert (SYMAL)
707 | 1120-SYM-STL-0009 | MW-06-02 - Base Slab Pour | 1120 | STL | CANCELLED | 44602 |  |  |  |  | 44602 |  | Grant Mcinerney (SYMAL)
711 | 1120-SYM-STL-0013 | MW-06-02 - 1200 Wall Pour | 1120 | STL | CLOSED-OUT | 44602 | 44791 |  |  |  | 44602 | 44644 | Grant Mcinerney (SYMAL)
712 | 1120-SYM-STL-0014 | MW-06-02 - Walls | 1120 | STL | CLOSED-OUT | 44602 | 44801 |  |  |  | 44602 | 44645 | Grant Mcinerney (SYMAL)
713 | 1120-SYM-STL-0015 | MW-06-01 - Base Slab Pour | 1120 | STL | CLOSED-OUT | 44602 | 44657 |  |  |  | 44602 | 44657 | Grant Mcinerney (SYMAL)
714 | 1120-SYM-STL-0016 | MW-06-01 - Wall Pour 1 | 1120 | STL | CLOSED-OUT | 44602 | 44715 |  |  |  | 44602 | 44657 | Grant Mcinerney (SYMAL)
715 | 1120-SYM-STL-0017 | Pedestrian staircase 1 base slab | 1120 | STL | WORK IN PROGRESS | 44572 |  |  |  |  | 44636 | 44636 | Bradley Pfitzner (SYMAL)
716 | 1120-SYM-STL-0018 | Pedestrian staircase 1 walls | 1120 | STL | WORK IN PROGRESS | 44641 |  |  |  |  | 44644 |  | Bradley Pfitzner (SYMAL)
717 | 1120-SYM-STL-0019 | MW-06-01 - Wall Pour 2 | 1120 | STL | CLOSED-OUT | 44641 | 44715 |  |  |  | 44602 | 44657 | Grant Mcinerney (SYMAL)
718 | 1120-SYM-STL-0020 | MW-06-01 - Roof Pour | 1120 | STL | CLOSED-OUT | 44641 | 44720 |  |  |  | 44602 | 44659 | Grant Mcinerney (SYMAL)
719 | 1120-SYM-STL-0021 | MW02 - RW10 Headwall Grout | 1120 | STL | CANCELLED | 44651 |  |  |  |  | 44652 |  | Grant Mcinerney (SYMAL)
720 | 1120-SYM-STL-0022 | RW12 Post and panel | 1120 | STL | CLOSED-OUT | 44652 | 44748 |  |  |  | 44664 | 44698 | Bradley Pfitzner (SYMAL)
721 | 1120-SYM-STL-0023 | Pedestrian staircase 2 base slab | 1120 | STL | WORK IN PROGRESS | 44683 |  |  |  |  | 44683 | 44686 | Bradley Pfitzner (SYMAL)
722 | 1120-SYM-STL-0024 | Pedestrian staircase 2 upstand | 1120 | STL | WORK IN PROGRESS | 44683 |  |  |  |  | 44690 | 44692 | Bradley Pfitzner (SYMAL)
723 | 1120-SYM-STL-0025 | RW10 Post and panel wall piles 11-33 | 1120 | STL | CLOSED-OUT | 44694 | 44771 |  |  |  | 44715 | 44750 | Bradley Pfitzner (SYMAL)
724 | 1120-SYM-STL-0026 | RW13 Post and panel wall | 1120 | STL | CLOSED-OUT | 44694 | 44768 |  |  |  | 44712 | 44735 | Bradley Pfitzner (SYMAL)
725 | 1120-SYM-STL-0027 | RW11 post and panel wall | 1120 | STL | WORK IN PROGRESS | 44732 |  |  |  |  | 44784 |  | Bradley Pfitzner (SYMAL)
726 | 1120-SYM-STL-0028 | RW07 Painting panels (all panels) | 1120 | STL | WORK IN PROGRESS | 44747 |  |  |  |  | 44747 |  | Bradley Pfitzner (SYMAL)
727 | 1120-SYM-STL-0029 | RW06 painting (all panels) | 1120 | STL | WORK IN PROGRESS | 44748 |  |  |  |  | 44749 |  | Bradley Pfitzner (SYMAL)
728 | 1120-SYM-STL-0030 | RW10 Capping Beam Piles | 1120 | STL | AWAITING TEST RESULT | 44778 | [6 empty] | Bradley Pfitzner (SYMAL)
729 | 1120-SYM-STL-0031 | MW-06-03 - Base Slab | 1120 | STL | OUTSTANDING | 44784 | [6 empty] | Grant Mcinerney (SYMAL)
730 | 1120-SYM-STL-0032 | MW-06-03 - Walls | 1120 | STL | OUTSTANDING | 44784 | [6 empty] | Grant Mcinerney (SYMAL)
731 | 1120-SYM-STL-0033 | MW-06-02 - Baseslab | 1120 | STL | CLOSED-OUT | 44571 | 44701 |  |  |  | 44602 | 44644 | Grant Mcinerney (SYMAL)
732 | 1120-SYM-STL-0034 | RW10 Capping Beam 1 | 1120 | STL | AWAITING TEST RESULT | 44798 |  |  |  |  | 44802 |  | Bradley Pfitzner (SYMAL)
733 | 1120-SYM-STL-0035 | RW10 Capping Beam 2 | 1120 | STL | AWAITING TEST RESULT | 44798 |  |  |  |  | 44802 |  | Bradley Pfitzner (SYMAL)

## 19. RW Painting
Closed | #REF! | Open | #REF! | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compliance Certificate for Material | Certificate of Compliance for Install | NCR | Lot Status | Lot Opened On | Lot Opened By | Symal Comments

## 20. Traffic Signal Foundation
Closed |  | Open |  | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compliance Certificate for Material | Certificate of Compliance for Install | NCR | Lot Status | Lot Opened On | Lot Opened By | Symal Comments

## 21. Landscaping
Closed |  | Open |  | Lot Requirments
# | Lot No | Title | ITP | Lot Map | Surveyor Report Reference | Signed Hold Points | Incoming Material Docket | Compliance Certificate for Material | Certificate of Compliance for Install | NCR | Lot Status | Lot Opened On | Lot Opened By | Symal Comments