## Table 1
Abbreviations
Third Party |  |  |  | TP |  |  | RSA Contractors |  |  | RSA |  | Nominated Project Personnel |  |  |  |  | NPP |  | Principle Contractor |  |  |  | PC
Surveyor |  |  |  | SUR |  |  | RPEQ |  |  | RPEQ |  | Supervisor |  |  |  |  | SUP |  | Inspect |  |  |  | INS
Test |  |  |  | TST |  |  | Project Engineer |  |  | PE |  | Witness Point |  |  |  |  | WP |  | Hold Point |  |  |  | HP
Visual |  |  |  | VIS |  |  | Check |  |  | CHK |  | Written |  |  |  |  | WRI |  | Monitor |  |  |  | M
Milestone |  |  |  | MST |  |  | Review |  |  | R
| Inspection and Test Plan Details | [17 empty] | Contractor |  |  |  | Client
| Item | Inspection Activity |  |  | Work By |  |  | Standard / Spec |  |  | Criteria |  |  |  | Frequency |  |  | Record | Resp |  | Type | Signoff | Resp | Type | Signoff
| 1 | Lot Identification |  |  | Contractor |  |  | Technical Specification |  |  | Location of Works identified in accordance with project technical specification |  |  |  | 1/Lot |  |  | ITP Verification Checklist/Lot Map | RSA |  | CHK |  | Senex | CHK
| 2 | Material Approval |  |  | Contractor |  |  | Technical Specification |  |  | Material shall meet the requirements under Queensland Department of Main Roads Technical Specification MRTS05 Type 2.5. |  |  |  | 3 prior to import |  |  | Laboratory test Certificate | RSA |  | CHK |  | Senex | CHK
| 3 | Subgrade Testing |  |  | Contractor |  |  | Technical Specification |  |  | Subgrade shall be tested for material characteristics, moisture, and compaction. >96% SDDR -2% dry to +2% wet OMC |  |  |  | 1/2500m3 |  |  | Laboratory test Certificate | RSA |  | HP |  | Senex | HP
| 4 | Proof Rolling Subgrade acceptance |  |  | Contractor |  |  | Technical Specification |  |  | Subgrade shall be Proof Rolled in accordance with Queensland Department of Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client. Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone |  |  |  | 1/Lot |  |  | ITP Verification Checklist/Lot Map | RSA |  | WP |  | Senex | WP
| 5 | Placement of material |  |  | Contractor |  |  | Technical Specification |  |  | Access track and ring road capped with 200 mm depth gravel. Placed in continuous, approximately horizontal layers having a mi compacted thickness of 150 mm and not more than 300 mm. |  |  |  | 1/Lot |  |  | ITP Verification Checklist/Lot Map | RSA |  | CHK |  | Senex | CHK
| 6 | Material Testing |  |  | Contractor |  |  | Technical Specification |  |  | Capping Material shall be tested for material characteristics, moisture, and compaction. >100% SDDR -2% dry to +2% wet OMC |  |  |  | 1/500m3 |  |  | Laboratory test Certificate | RSA |  | HP |  | Senex | HP
| 7 | As built Survey |  |  | Contractor |  |  | Technical Specification |  |  | Finished levels checked for Vertical and horizontal tolerances as required. Refer to TS section 3.4 |  |  |  | 1/Lot |  |  | Survey as Built | RSA |  | HP |  | Senex | HP
| Test Details | [9 empty] | Normal Testing Level | [8 empty] | Required Result(s)
| Item | Test |  |  |  | Description |  |  |  |  | Max Lot Size |  | Min Test Frequency |  |  | Min No of tests |  |  |  | Criteria
| 1 | AS 1289.2.1.1, AS 1289 5.1.1, AS1289.5.4.1, AS1289.5.8.1 |  |  |  | Standard Dry density ratio, Moisture Content |  |  |  |  | 1005 m3 |  | 1/ 500 m3 |  |  | 2 |  |  |  | -2% dry to +2% wet OMC SDDR 100%
| 2 | AS 1289.3.6.1, AS1289.3.3.1, AS1289.3.2.2 |  |  |  | PSD and Atterberg limits |  |  |  |  | 1005 m3 |  | 1/ 500 m3 |  |  | 2 |  |  |  | Table 8 Technical Specification
| 3 | AS 1289.6.1.1 |  |  |  | 4 days soaked CBR value |  |  |  |  | 1005 m3 |  | 1/ 500 m3 |  |  | 2 |  |  |  | >=15
Contractor Construction Manager:
[9 empty] | (Print Name) |  |  |  |  | (Signature) | [6 empty] | (Date)
Client Superintendent:
[9 empty] | (Print Name) |  |  |  |  | (Signature) | [6 empty] | (Date)
Document Status
Revision Status |  |  | Responsible Person |  |  |  | Signed |  |  | Dated |  | Revision
Draft By: Reviewed By: Submitted By: Approved By: |  |  | Madhu Achana | [8 empty] | Rev1