## Table 1
Abbreviations
Third Party |  |  |  | TP |  | RSA Contractors |  | RSA |  | Nominated Project Personnel |  |  |  |  | NPP | Principle Contractor |  |  |  | PC
Surveyor |  |  |  | SUR |  | RPEQ |  | RPEQ |  | Supervisor |  |  |  |  | SUP | Inspect |  |  |  | INS
Test |  |  |  | TST |  | Project Engineer |  | PE |  | Witness Point |  |  |  |  | WP | Hold Point |  |  |  | HP
Visual |  |  |  | VIS |  | Check |  | CHK |  | Written |  |  |  |  | WRI | Monitor |  |  |  | M
Milestone |  |  |  | MST |  | Review |  | R
| Inspection and Test Plan Details | [14 empty] | Contractor |  |  |  | Client
| Item | Inspection Activity |  | Work By |  | Standard / Spec |  | Criteria |  |  |  |  | Frequency |  | Record | Resp |  | Type |  | Resp | Type
| 1 | Lot Identification |  | Contractor |  | Technical Specification |  | Location of works identify as per IFC drawings |  |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot drawing | RSA |  | CHK |  | Senex | CHK
| 2 | Subgrade Preparation |  | Contractor |  | Technical Specification |  | Scarify subsoil to a minimum depth of 150 mm |  |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot drawing | RSA |  | CHK |  | Senex | CHK
| 3 | Gypsum Application |  | Contractor |  | Technical Specification |  | Apply gypsum to batters and table drains at rate of 5t/ha, and apply water at 10mm/m2 to create adequate topsoil bond with the subgrade |  |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot drawing | RSA |  | CHK |  | Senex | CHK
| 4 | Respreading of Topsoil |  | Contractor |  | Technical Specification |  | Topsoil is to be placed 300mm thick and trim with grader and scarify to a depth of 100mm. |  |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot drawing | RSA |  | CHK |  | Senex | CHK
| 5 | Hydro mulch and Grass Seeding |  | Contractor |  | Technical Specification |  | Topsoil shall be hydro-mulched using the client-specified seed mix, approved mulch, and fertilizer applied at a rate of 150 kg per hectare. |  |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot drawing | RSA |  | HP |  | Senex | HP
| 6 | Watering of Topsoil |  | Contractor |  | Technical Specification |  | Watering 10mm/m2 every day for first 8 days, then every second day to get to a total of 14 irrigation days. |  |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot drawing | RSA |  | WP |  | Senex | WP
| 7 | Topsoil Testing |  | Contractor |  | Technical Specification |  | The PH of the topsoil shall be tested to confirm applicability of gypsum |  |  |  |  | 1/Lot |  | Test Certificate | RSA |  | WP |  | Senex | WP
| 8 | Survey |  | Contractor |  | Technical Specification |  | As-constructed survey has been completed to record the surface levels on completion. Refer to TS section 3.4 The Contractor shall submit results of each survey to the superintendent within 48hours of undertaking the Survey. |  |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot drawing | RSA |  | HP |  | Senex | HP
| Test Details | [7 empty] | Normal Testing Level | [7 empty] | Required Result(s)
| Item | Test |  |  | Description |  |  |  | Max Lot Size |  | Min Test Frequency |  |  | Min No of tests |  |  | Criteria
| 1 |  |  |  | Topsoil PH | [5 empty] | TBC |  |  | TBC
Contractor Construction Manager:
[7 empty] | (Print Name) |  |  |  |  | (Signature) | [6 empty] | (Date)
Client Superintendent:
[7 empty] | (Print Name) |  |  |  |  | (Signature) | [6 empty] | (Date)
Document Status
Revision Status |  |  | Responsible Person |  |  | Signed |  | Dated |  | Revision
Draft By: Reviewed By: Submitted By: Approved By: |  |  | Madhu Achana | [6 empty] | Rev1