## Table 1
Abbreviations
Third Party |  |  |  | TP |  | RSA Contractors |  | RSA | Nominated Project Personnel |  |  |  |  | NPP | Principle Contractor |  |  | PC
Surveyor |  |  |  | SUR |  | RPEQ |  | RPEQ | Supervisor |  |  |  |  | SUP | Inspect |  |  | INS
Test |  |  |  | TST |  | Project Engineer |  | PE | Witness Point |  |  |  |  | WP | Hold Point |  |  | HP
Visual |  |  |  | VIS |  | Check |  | CHK | Written |  |  |  |  | WRI | Monitor |  |  | M
Milestone |  |  |  | MST |  | Review |  | R
Inspection and Test Plan Details | [14 empty] | Contractor |  |  | Client
Item |  | Inspection Activity |  | Work By |  | Standard / Spec |  | Criteria |  |  |  | Frequency |  | Record | Resp | Type | Signoff | Resp | Type | Signoff
1 |  | Lot Identification |  | Contractor |  | Technical Specification/IFC Drawings |  | Location of works identified as per IFC drawings |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot drawing | RSA | CHK |  | Senex | CHK
Temporary Sediment and Erosion Control
2 |  | Clear identification and demarcation of ‘no go zones’ (where required) |  | Contractor |  | Technical Specification/IFC Drawings |  | Remove vegetation and disturb soil only in those areas approved for construction work to occur |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | CHK |  | Senex | CHK
3 |  | Installation of temporary sediment and erosion control devices |  | Contractor |  | Technical Specification/IFC Drawings |  |  Construction of diversion bunds  Excavation of sediment catch sumps and Rumble pad  Temporary approved construction tracks  Installation of Silt Fence |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | HP |  | Senex | HP
4 |  | Sediment and erosion control device ongoing inspections |  | Contractor |  | Technical Specification/IFC Drawings |  | Inspection of sediment and erosion control devices completed to be completed at the below frequencies Rain: >50mm in on day or >100mm over 4 days Prior to shift breaks |  |  |  | Ongoing |  | Environmental Routine Checklist | RSA | WP |  | Senex | WP
Permanent Sediment and Erosion Control – Rip Rap (Rock Protection)
5 |  | Underlying Lot conformance - Subgrade |  | Contractor |  | Technical Specification/IFC Drawings |  | The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile. |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | HP |  | Senex | HP
6 |  | Conformance Separation Geotextile Material |  | Contractor |  | Technical Specification/IFC Drawings |  | The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data Certificates. |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | HP |  | Senex | HP
7 |  | Conformance Rip Rap |  | Contractor |  | Technical Specification/IFC Drawings |  | The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates. |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | HP |  | Senex | HP
8 |  | Separation geotextile placement |  | Contractor |  | Technical Specification/IFC Drawings |  | Installation method complies with the requirements of the technical specification and the IFC drawings. Laps to geotextiles shall be a minimum 0.6m. The Superintendent shall inspect subgrade and the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers. |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | HP |  | Senex | HP
9 |  | Rip Rap Placement |  | Contractor |  | Technical Specification/IFC Drawings |  | The contractor shall provide a Work Method Statement for the placement of Rip Rap. Rip rap shall be place in a manner which does not damage the underlying geotextile Rock finished smoothed to the final lines and levels. |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | CHK |  | Senex | HP
10 |  | Acceptance of works (Rip rap) |  | Contractor |  | Technical Specification/IFC Drawings |  | The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works. |  |  |  | 1/Lot |  | ITP Verification Checklist / MDR | RSA | CHK |  | Senex | HP
Permanent Sediment and Erosion Control – CMP and Headwall
11 |  | CMP Installation Contractor |  | Contractor |  | Technical Specification/IFC Drawings |  | Contractor shall provide a culvert installation methodology to the superintendent for approval Excavation to design invert levels allowing for 175 mm bedding sand beneath culverts up to haunch. Select Fill around culverts 300 mm min thickness above Foundation to be tested for bearing capacity of 100kPa |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | CHK |  | Senex | CHK
12 |  | Backfilling |  | Contractor |  | Technical Specification/IFC Drawings |  | Trench backfilled and tested in line with requirements for Fill 96% +/ -2% moisture |  |  |  | Min 2 tests |  | ITP Verification Checklist | RSA | CHK |  | Senex | CHK
13 |  | Headwall Installation |  | Contractor |  | Technical Specification/IFC Drawings |  | 2 x 600DN Headwalls installed on 100 -250mm sand bedding (or equivalent) to required invert levels Headwall installed flush with CMP pipe and grouted neat. |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | CHK |  | Senex | CHK
14 |  | Acceptance of works |  | Contractor |  | Technical Specification/IFC Drawings |  | Conformance certificates supplied by manufacturer All required test reports provided to client |  |  |  | 1/Lot |  | As-constructed survey data obtained | RSA | CHK |  | Senex | HP
Test Details | [7 empty] | Normal Testing Level | [6 empty] | Required Result(s)
Item |  | Test |  |  | Description |  |  | Max Lot Size |  | Min Test Frequency |  |  | Min No of tests |  | Criteria
1 |  | 01 AS 1289 .2.22, AS1289.5.1.1, AS 1289.5.4.1, AS1289.5.8.1 |  |  | General Fill Standard Dry density ratio, Moisture Content |  |  |  |  | 2 per lot |  |  | 2 |  | -2% dry to +2% wet OMC SDDR 96%
2 |  | AS 1289.3.6.1, AS1289.3.3.1, AS1289.3.2.2 |  |  | PSD and Atterberg limits |  |  |  |  | 2 per lot |  |  | 2 |  | Table 15 Technical Specification
3 |  | AS1289.6 .3.2 |  |  | DCP |  |  |  |  | 1 |  |  | 1 |  | 100 KPA (3 blows per 100 mm)
4 |  | AS1289.5.7.1 AS 1289.3.6.1, AS1289.3.3.1, AS1289.3.2.2 |  |  | Bedding Material PSD and Atterberg limits |  |  |  |  | 2 test per culvert |  |  | 2 OMC and SDR 2 PSD and Atterberg limits |  | -2% dry to +2% wet OMC 96% STD or 60-80% DI
5 |  | AS1289.3.6.1/ Visual Classification |  |  | RIP RAP PSD |  |  |  |  | 1 test per tank pad
Contractor Construction Manager:
[7 empty] | (Print Name) |  |  |  | (Signature) |  |  |  |  | (Date)
Client Superintendent:
[7 empty] | (Print Name) |  |  |  | (Signature) |  |  |  |  | (Date)
Document Status
Revision Status |  |  | Responsible Person |  |  | Signed |  | Dated | Revision
Draft By: Reviewed By: Submitted By: Approved By: |  |  | Madhu Achana | [5 empty] | Rev1