## Table 1
Abbreviations
Third Party |  |  |  | TP |  | RSA Contractors |  | RSA | Nominated Project Personnel |  |  |  |  | NPP | Principle Contractor |  |  | PC
Surveyor |  |  |  | SUR |  | RPEQ |  | RPEQ | Supervisor |  |  |  |  | SUP | Inspect |  |  | INS
Test |  |  |  | TST |  | Project Engineer |  | PE | Witness Point |  |  |  |  | WP | Hold Point |  |  | HP
Visual |  |  |  | VIS |  | Check |  | CHK | Written |  |  |  |  | WRI | Monitor |  |  | M
Milestone |  |  |  | MST |  | Review |  | R
Inspection and Test Plan Details | [14 empty] | Contractor |  |  | Client
Item |  | Inspection Activity |  | Work By |  | Standard / Spec |  | Criteria |  |  |  | Frequency |  | Record | Resp | Type | Signoff | Resp | Type | Signoff
1 |  | Lot Identification |  | Contractor |  | Technical Specification/IFC Drawings |  | Location of works identified as per IFC drawings |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot drawing | RSA | CHK |  | Senex | CHK
Temporary Sediment and Erosion Control
2 |  | Clear identification and demarcation of ‘no go zones’ (where required) |  | Contractor |  | Technical Specification/IFC Drawings |  | Remove vegetation and disturb soil only in those areas approved for construction work to occur |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | CHK |  | Senex | CHK
3 |  | Installation of temporary sediment and erosion control devices |  | Contractor |  | Technical Specification/IFC Drawings |  |  Construction of diversion bunds  Excavation of sediment catch sumps and Rumble pad  Temporary approved construction tracks  Installation of Silt Fence |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | HP |  | Senex | HP
4 |  | Sediment and erosion control device ongoing inspections |  | Contractor |  | Technical Specification/IFC Drawings |  | Inspection of sediment and erosion control devices completed to be completed at the below frequencies Rain: >50mm in on day or >100mm over 4 days Prior to shift breaks |  |  |  | Ongoing |  | Environmental Routine Checklist | RSA | WP |  | Senex | WP
Permanent Sediment and Erosion Control – Rip Rap (Rock Protection)
5 |  | Underlying Lot conformance - Subgrade |  | Contractor |  | Technical Specification/IFC Drawings |  | The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile. |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | HP |  | Senex | HP
6 |  | Conformance Separation Geotextile Material |  | Contractor |  | Technical Specification/IFC Drawings |  | The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data Certificates. |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | HP |  | Senex | HP
7 |  | Conformance Rip Rap |  | Contractor |  | Technical Specification/IFC Drawings |  | The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates. |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | HP |  | Senex | HP
8 |  | Separation geotextile placement |  | Contractor |  | Technical Specification/IFC Drawings |  | Installation method complies with the requirements of the technical specification and the IFC drawings. Laps to geotextiles shall be a minimum 0.6m. The Superintendent shall inspect subgrade and the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers. |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | HP |  | Senex | HP
9 |  | Rip Rap Placement |  | Contractor |  | Technical Specification/IFC Drawings |  | The contractor shall provide a Work Method Statement for the placement of Rip Rap. Rip rap shall be place in a manner which does not damage the underlying geotextile Rock finished smoothed to the final lines and levels. |  |  |  | 1/Lot |  | ITP Verification Checklist | RSA | CHK |  | Senex | HP
10 |  | Acceptance of works (Rip rap) |  | Contractor |  | Technical Specification/IFC Drawings |  | The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works. |  |  |  | 1/Lot |  | ITP Verification Checklist / MDR | RSA | CHK |  | Senex | HP
Test Details | [7 empty] | Normal Testing Level | [6 empty] | Required Result(s)
Item |  | Test |  |  | Description |  |  | Max Lot Size |  | Min Test Frequency |  |  | Min No of tests |  | Criteria
|  | AS1289.3.6.1/Visual Classification |  |  | PSD |  |  |  |  | 1 per tank pad |  |  | 1
Contractor Construction Manager:
[7 empty] | (Print Name) |  |  |  | (Signature) |  |  |  |  | (Date)
Client Superintendent:
[7 empty] | (Print Name) |  |  |  | (Signature) |  |  |  |  | (Date)
Document Status
Revision Status |  |  | Responsible Person |  |  | Signed |  | Dated | Revision
Draft By: Reviewed By: Submitted By: Approved By: |  |  | Madhu Achana | [5 empty] | Rev1