## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP001 - Clear Grub & Topsoil Stripping | itp |  |  |  |  | Tank 1 - ITP001 - Clear Grub & Topsoil Stripping - Rev1
section | CLEARING & GRUBBING
checkpoint | 01 - Survey Set Out
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works
label | Frequency - Prior to commencement
label | Record - ITP Verification Checklist/Site Survey
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - SENEX
label | Client: Type - WP
checkpoint | 02 - Site Services
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Contractor shall take reasonable steps to locate all existing service on the site. Where existing services are identified they shall be clearly marked for the duration of the works.
label | Frequency - Prior to commencement
label | Record - Site general layout drawing
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - SENEX
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 03 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Location of works identified in accordance with the Project Technical Specifications.
label | Frequency - 1/Lot
label | Record - Attached Drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - SENEX
label | Client: Type - CHK
checkpoint | 04 - Clearing& Grubbing
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Clearing shall be performed within the limits of the works indicated on the drawings.
label | ○ Trees, shrubs, logs, debris, perishable material, organic matter, fallen trees, overhanging branches and surface obstructions shall be removed from the stripping area.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - SENEX
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - Stockpile of Materials
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Cleared and grubbed materials shall be stockpiled or disposed of as directed by the superintendent
label | Frequency - 1/lot
label | Record - ITP, Verification Checklist/ Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - SENEX
label | Client: Type - WP
section | TOPSOIL STRIPPING
checkpoint | 07 - Topsoil Stripping
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Topsoil shall be stripped such that all organic rich soil and roots/rootlets has been removed from the foundation of the embankment and internal borrow areas
label | ○ Topsoil shall be stripped to the nominal depth of 300mm+10%. Any areas with depth greater should be notified to the superintendent.
label | Frequency - Confirm with survey
label | Record - ITP, Verification Checklist/Site Survey
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - SENEX
label | Client: Type - WP
checkpoint | 06 - Stockpile of Materials
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Stripped topsoil shall be stockpiled where directed by the Superintendent, for reuse.
label | ○ Topsoil is to be placed in a loose, non-compacted state, to a maximum height as directed by superintendent.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/ Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - SENEX
label | Client: Type - WP
checkpoint | 07 - Topsoil Strip Survey
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - As-constructed survey has been to be completed to record the surface levels on completion of topsoil stripping.
label | ○ The Contractor shall submit a topsoil strip survey to the superintendent prior to excavation and/or placement of fill material
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - SENEX
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Superintendent:
signoff | (Signature)
checklist | ITP002 - Foundation Preparation | itp |  |  |  |  | Tank 1 - ITP002 - Foundation Preparation - Rev1
section | FOUNDATION PREPARATION
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Location of Works identified in accordance with project technical specification
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 02 - Foundation Preparation
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Foundation preparation of Lot will be visually inspected for material type, moisture and organic material prior to foundation preparation works.
label | ○ The Subgrade shall be trimmed with a grader, smooth bladed scraper to assist with the inspection process.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - VIS
label | Client: Resp - Senex
label | Client: Type - VIS
checkpoint | 03 - Foundation Preparation – Proof Rolling
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Subgrade shall be Proof Rolled in accordance with Queensland Department of Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client.
label | ○ Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 04 - Dynamic Cone Penetrometer (DCP)
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - DCP testing shall the undertaken in accordance with AS1289.6.3.2 by the superintendent to assess the consistency of the subgrade. DCP test Shall extend to a depth of 1m and achieve a min of 3 blows per 100mm penetration
label | Frequency - 1/2500m2
label | Record - NATA certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 05 - Foundation Preparation – Ground Surface Treatment
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Scarify minimum 200mm, moisture condition and compact.
label | ○ The Superintend shall inspect the subgrade for conformance with the specification prior to placement of overlying fill.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - Ground Surface Treatment Testing
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Tank Pad foundations surface level shall be scarified, watered and compacted to a density ratio of no less than 96% of standard MDD and -+2 % of OMC.
label | Frequency - 1/2500m2
label | Record - NATA certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 07 - As built Survey
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Finished levels checked for Vertical and horizontal tolerances as required. Refer to TS section 3.4
label | Frequency - 1/Lot
label | Record - Survey as Built
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Client Superintendent:
signoff | (Signature)
checklist | ITP003 - Embankment Construction | itp |  |  |  |  | Tank 1 - ITP003 - Embankment Construction - Rev1
section | EMBANKMENT CONSTRUCTION
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Location of Works identified in accordance with project technical specification
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 02 - Underlying Lot Conforms
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Foundation preparation works completed in underlying lot.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 03 - General Fill Material Requirement
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Grading Requirements
label | ○ 75mm sieve – 100% passing
label | ○ 37.5mm Sieve – 90 to 100% passing 19mm Sieve – 80 to 100% passing
label | ○ 4.75mm Sieve – 60 to 100% passing
label | ○ 2.36mm sieve – 40 to 95 % passing 0.075mm Sieve –15 to 90% passing Indicator requirements
label | ○ Plasticity Index – 10 to 40%
label | ○ Liquid Limit – 20 to 60% Emerson Class 2 (minimum) Organic content 2% (maximum)
label | Frequency - Refer to TS Table 11
label | Record - Laboratory test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 04 - Fill placement
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - General Fill
label | ○ Placed in continuous, approximately horizontal layers for the full width of the area, having a compacted thickness of not more than 300 mm or less than 75 mm. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm prior to the placement of the next layer.
label | Frequency - Each Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 05 - General Fill Testing
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - ≥ 96 % standard MDD.
label | ○ NOTE: ≥ 98% standard MDD for the Earthen Ring Beam General Fill Section.
label | ○ -2% to +2% of OMC
label | Frequency - Table 10 Technical specification
label | Record - Laboratory test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - ERB Inspection
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Verification of RLs/Elevations filed controls for the ERB
label | Frequency - Progressive During Fill Placement
label | Record - Survey Data
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 07 - Survey
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - RSA shall submit 25%, 50%, 75%, 100% tank pad foundation fill placement completion survey to the superintendent within 48 hours of each milestone achievement. Refer to TS section 3.4
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Client Superintendent:
signoff | (Signature)
checklist | ITP004 - Capping Layer | itp |  |  |  |  | Tank 1 - ITP004 - Capping Layer - Rev1
section | CAPPING LAYER
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Location of Works identified in accordance with project technical specification
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 02 - Material Approval
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Material shall meet the requirements under Queensland Department of Main Roads Technical Specification MRTS05 Type 2.5.
label | Frequency - 3 prior to import
label | Record - Laboratory test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 03 - Subgrade Testing
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Subgrade shall be tested for material characteristics, moisture, and compaction.
label | ○ >96% SDDR
label | ○ -2% dry to +2% wet OMC
label | Frequency - 1/2500m3
label | Record - Laboratory test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 04 - Proof Rolling Subgrade acceptance
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Subgrade shall be Proof Rolled in accordance with Queensland Department of Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client.
label | ○ Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 05 - Placement of material
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Access track and ring road capped with 200 mm depth gravel. Placed in continuous, approximately horizontal layers having a mi compacted thickness of 150 mm and not more than 300 mm.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 06 - Material Testing
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Capping Material shall be tested for material characteristics, moisture, and compaction.
label | ○ >100% SDDR
label | ○ -2% dry to +2% wet OMC
label | Frequency - 1/500m3
label | Record - Laboratory test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 07 - As built Survey
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Finished levels checked for Vertical and horizontal tolerances as required. Refer to TS section 3.4
label | Frequency - 1/Lot
label | Record - Survey as Built
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Client Superintendent:
signoff | (Signature)
checklist | ITP005 - Surface Water Runoff Management | itp |  |  |  |  | Tank 1 - ITP005 - Surface Water Runoff Management - Rev1
section | CAPPING LAYER
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Location of works identify as per IFC drawings
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 02 - Subgrade Preparation
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Scarify subsoil to a minimum depth of 150 mm
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 03 - Gypsum Application
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Apply gypsum to batters and table drains at rate of 5t/ha, and apply water at 10mm/m2 to create adequate topsoil bond with the subgrade
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 04 - Respreading of Topsoil
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Topsoil is to be placed 300mm thick and trim with grader and scarify to a depth of 100mm.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 05 - Hydro mulch and Grass Seeding
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Topsoil shall be hydro-mulched using the client-specified seed mix, approved mulch, and fertilizer applied at a rate of 150 kg per hectare.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - Watering of Topsoil
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Watering 10mm/m2 every day for first 8 days, then every second day to get to a total of 14 irrigation days.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 07 - Topsoil Testing
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - The PH of the topsoil shall be tested to confirm applicability of gypsum
label | Frequency - 1/Lot
label | Record - Test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 08 - Survey
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - As-constructed survey has been completed to record the surface levels on completion. Refer to TS section 3.4
label | ○ The Contractor shall submit results of each survey to the superintendent within 48hours of undertaking the Survey.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Client Superintendent:
signoff | (Signature)
checklist | ITP006 - Erosion and Sediment Control | itp |  |  |  |  | Tank 1 - ITP006 - Erosion and Sediment Control - Rev1
section | LOT IDENTIFICATION
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Location of works identified as per IFC drawings
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
section | TEMPORARY SEDIMENT AND EROSION CONTROL
checkpoint | 02 - Clear identification and demarcation of ‘no go zones’ (where required)
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Remove vegetation and disturb soil only in those areas approved for construction work to occur
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 03 - Installation of temporary sediment and erosion control devices
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Construction of diversion bunds
label | ○ Excavation of sediment catch sumps and Rumble pad
label | ○ Temporary approved construction tracks
label | ○ Installation of Silt Fence
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
section | PERMANENT SEDIMENT AND EROSION CONTROL – RIP RAP (ROCK PROTECTION)
checkpoint | 04 - Sediment and erosion control device ongoing inspections
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Inspection of sediment and erosion control devices completed to be completed at the below frequencies
label | ○ Rain: >50mm in on day or >100mm over 4 days Prior to shift breaks
label | Frequency - Ongoing
label | Record - Environmental Routine Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 05 - Underlying Lot conformance - Subgrade
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - Conformance Separation Geotextile Material
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data Certificates.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 07 - Conformance Rip Rap
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 08 - Separation geotextile placement
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Installation method complies with the requirements of the technical specification and the IFC drawings. Laps to geotextiles shall be a minimum 0.6m. The Superintendent shall inspect subgrade and the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 09 - Rip Rap Placement
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - The contractor shall provide a Work Method Statement for the placement of Rip Rap.
label | ○ Rip rap shall be place in a manner which does not damage the underlying geotextile
label | ○ Rock finished smoothed to the final lines and levels.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 10 - Acceptance of works (Rip rap)
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist / MDR
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
section | PERMANENT SEDIMENT AND EROSION CONTROL – CMP AND HEADWALL
checkpoint | 11 - CMP Installation Contractor
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Contractor shall provide a culvert installation methodology to the superintendent for approval Excavation to design invert levels allowing for 175 mm bedding sand beneath culverts up to haunch.
label | ○ Select Fill around culverts 300 mm min thickness above
label | ○ Foundation to be tested for bearing capacity of 100kPa
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 12 - Backfilling
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Trench backfilled and tested in line with requirements for Fill 96% +/ -2% moisture
label | Frequency - Min 2 tests
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 13 - Headwall Installation
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - 2 x 600DN Headwalls installed on 100 -250mm sand bedding (or equivalent) to required invert levels
label | ○ Headwall installed flush with CMP pipe and grouted neat.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 14 - Acceptance of works
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Conformance certificates supplied by manufacturer
label | ○ All required test reports provided to client
label | Frequency - 1/Lot
label | Record - As-constructed survey data obtained
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Client Superintendent:
signoff | (Signature)
checklist | ITP007 - Leak Detection System | itp |  |  |  |  | Tank 1 - ITP007 - Leak Detection System - Rev0
section | LEAK DETECTION SYSTEM
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Location of works identified as per IFC drawings
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 02 - Survey control and Setout
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Confirm centres of both sump and tank locations
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 03 - Excavation of sump
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Located at 3m outside from the hinge point of the tank pad. To be trenched to a depth of 3.17 m (to be confirmed on site)
label | ○ Sump excavated to correct dimensions in line with Concept Tanks 0.8m diameter excavation to design depth. Sump pit depth to be determined onsite ensuring sufficient fall from tank centre to sump
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 04 - Installation of HDPE sump base and chamber at correct height and level
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Poly sump base to be installed at 200mm below leak detection pipe.
label | ○ Sump chamber installed plumb to correct height minimum 150mm above top of tank
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 05 - Backfill - Sump
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Backfill in accordance with CT requirements. Compaction testing in line with Earthworks specification
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist / Test
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - Leakage pipe trench excavation
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Trench excavated to correct lines and levels in line with CES drawings.
label | ○ 1:100 fall to sump
label | ○ Sufficient excavation width to facilitate installation.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 07 - Installation of 50mm HDPE leakage pipe
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - 50mm HDPE pipe and bends installed in accordance with CT and manufacturer requirements.
label | ○ Minimum 150mm cover at centre of tank Pipe installed on 50mm sand bedding (optional) as per CT recommendations
label | ○ HDPE pipe riser installed 300mm above FSL at centre of tank, temporary seal to prevent sediment ingress.
label | ○ Pipe to be left exposed at centre of sump pit
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 08 - Surface Water Runoff
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - DN110 HDPE pipe for construction surface water runoff to be installed 1:100 fall to swale drain
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 09 - Backfill - Trench
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Backfill in accordance with CES requirements and general earthworks specifications
label | ○ 98% +/-2% moisture (Ring beam area) 96% +/-2% moisture (All other areas)
label | Frequency - Min 2 tests per lot
label | Record - ITP, Verification Checklist / Test Report
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 10 - Acceptance of work
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Work completed in accordance with CES requirements.
label | ○ Compaction reports received and meeting specification
label | ○ As-constructed survey data obtained
label | Frequency - Once per lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Client Superintendent:
signoff | (Signature)
checklist | ITP001 - Clear Grub & Topsoil Stripping | itp |  |  |  |  | Tank 2 - ITP001 - Clear Grub & Topsoil Stripping - Rev1
section | CLEARING & GRUBBING
checkpoint | 01 - Survey Set Out
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works
label | Frequency - Prior to commencement
label | Record - ITP Verification Checklist/Site Survey
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - SENEX
label | Client: Type - WP
checkpoint | 02 - Site Services
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Contractor shall take reasonable steps to locate all existing service on the site. Where existing services are identified they shall be clearly marked for the duration of the works.
label | Frequency - Prior to commencement
label | Record - Site general layout drawing
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - SENEX
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 03 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Location of works identified in accordance with the Project Technical Specifications.
label | Frequency - 1/Lot
label | Record - Attached Drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - SENEX
label | Client: Type - CHK
checkpoint | 04 - Clearing& Grubbing
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Clearing shall be performed within the limits of the works indicated on the drawings.
label | ○ Trees, shrubs, logs, debris, perishable material, organic matter, fallen trees, overhanging branches and surface obstructions shall be removed from the stripping area.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - SENEX
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - Stockpile of Materials
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Cleared and grubbed materials shall be stockpiled or disposed of as directed by the superintendent
label | Frequency - 1/lot
label | Record - ITP, Verification Checklist/ Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - SENEX
label | Client: Type - WP
section | TOPSOIL STRIPPING
checkpoint | 07 - Topsoil Stripping
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Topsoil shall be stripped such that all organic rich soil and roots/rootlets has been removed from the foundation of the embankment and internal borrow areas
label | ○ Topsoil shall be stripped to the nominal depth of 300mm+10%. Any areas with depth greater should be notified to the superintendent.
label | Frequency - Confirm with survey
label | Record - ITP, Verification Checklist/Site Survey
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - SENEX
label | Client: Type - WP
checkpoint | 06 - Stockpile of Materials
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Stripped topsoil shall be stockpiled where directed by the Superintendent, for reuse.
label | ○ Topsoil is to be placed in a loose, non-compacted state, to a maximum height as directed by superintendent.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/ Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - SENEX
label | Client: Type - WP
checkpoint | 07 - Topsoil Strip Survey
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - As-constructed survey has been to be completed to record the surface levels on completion of topsoil stripping.
label | ○ The Contractor shall submit a topsoil strip survey to the superintendent prior to excavation and/or placement of fill material
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - SENEX
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Superintendent:
signoff | (Signature)
checklist | ITP002 - Foundation Preparation | itp |  |  |  |  | Tank 2 - ITP002 - Foundation Preparation - Rev1
section | FOUNDATION PREPARATION
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Location of Works identified in accordance with project technical specification
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 02 - Foundation Preparation
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Foundation preparation of Lot will be visually inspected for material type, moisture and organic material prior to foundation preparation works.
label | ○ The Subgrade shall be trimmed with a grader, smooth bladed scraper to assist with the inspection process.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 03 - Foundation Preparation – Proof Rolling
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Subgrade shall be Proof Rolled in accordance with Queensland Department of Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client.
label | ○ Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 04 - Dynamic Cone Penetrometer (DCP)
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - DCP testing shall the undertaken in accordance with AS1289.6.3.2 by the superintendent to assess the consistency of the subgrade. DCP test Shall extend to a depth of 1m and achieve a min of 3 blows per 100mm penetration
label | Frequency - 1/2500m2
label | Record - NATA certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 05 - Foundation Preparation – Ground Surface Treatment
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Scarify minimum 200mm, moisture condition and compact.
label | ○ The Superintend shall inspect the subgrade for conformance with the specification prior to placement of overlying fill.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - Ground Surface Treatment Testing
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Tank Pad foundations surface level shall be scarified, watered and compacted to a density ratio of no less than 96% of standard MDD and -+2 % of OMC.
label | Frequency - 1/2500m2
label | Record - NATA certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 07 - As built Survey
label | Work By - Contractor
label | Standard / Spec - OPS-TETW-CS- SPE-002
label | Criteria - Finished levels checked for Vertical and horizontal tolerances as required.
label | Frequency - 1/Lot
label | Record - Survey as Built
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Superintendent:
signoff | (Signature)
checklist | ITP003 - Embankment Construction | itp |  |  |  |  | Tank 2 - ITP003 - Embankment Construction - Rev1
section | EMBANKMENT CONSTRUCTION
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Location of Works identified in accordance with project technical specification
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 02 - Underlying Lot Conforms
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Foundation preparation works completed in underlying lot.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 03 - General Fill Material Requirement
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Grading Requirements
label | ○ 75mm sieve – 100% passing
label | ○ 37.5mm Sieve – 90 to 100% passing 19mm Sieve – 80 to 100% passing
label | ○ 4.75mm Sieve – 60 to 100% passing
label | ○ 2.36mm sieve – 40 to 95 % passing 0.075mm Sieve –15 to 90% passing Indicator requirements
label | ○ Plasticity Index – 10 to 40%
label | ○ Liquid Limit – 20 to 60% Emerson Class 2 (minimum) Organic content 2% (maximum)
label | Frequency - Refer to Table 11 SPE
label | Record - Laboratory test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 04 - Fill placement
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - General Fill
label | ○ Placed in continuous, approximately horizontal layers for the full width of the area, having a compacted thickness of not more than 300 mm or less than 75 mm. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm prior to the placement of the next layer.
label | Frequency - Each Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 05 - General Fill Testing
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - ≥ 96 % standard MDD.
label | ○ NOTE: ≥ 98% standard MDD for the Earthen Ring Beam General Fill Section.
label | ○ -2% to +2% of OMC
label | Frequency - Table 10 Technical specification
label | Record - Laboratory test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - ERB Inspection
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Verification of RLs/Elevations filed controls for the ERB
label | Frequency - Progressive During Fill Placement
label | Record - Survey Data
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 07 - Survey
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - RSA shall submit 25%, 50%, 75%, 100% tank pad foundation fill placement completion survey to the superintendent within 48 hours of each milestone achievement
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Superintendent:
signoff | (Signature)
checklist | ITP004 - Capping Layer | itp |  |  |  |  | Tank 2 - ITP004 - Capping Layer - Rev1
section | CAPPING LAYER
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Location of Works identified in accordance with project technical specification
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 02 - Material Approval
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Material shall meet the requirements under Queensland Department of Main Roads Technical Specification MRTS05 Type 2.5.
label | Frequency - 3 tests prior to import
label | Record - Laboratory test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 03 - Subgrade Testing
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Subgrade shall be tested for material characteristics, moisture, and compaction.
label | ○ >96% SDDR
label | ○ -2% dry to +2% wet OMC
label | Frequency - 1/2500m3
label | Record - Laboratory test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 04 - Proof Rolling Subgrade acceptance
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Subgrade shall be Proof Rolled in accordance with Queensland Department of Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client.
label | ○ Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 05 - Placement of material
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Access track and ring road capped with 200 mm depth gravel. Placed in continuous, approximately horizontal layers having a mi compacted thickness of 150 mm and not more than 300 mm.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 06 - Material Testing
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Capping Material shall be tested for material characteristics, moisture, and compaction.
label | ○ >100% SDDR
label | ○ -2% dry to +2% wet OMC
label | Frequency - 1/500m3
label | Record - Laboratory test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 07 - As built Survey
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Finished levels checked for Vertical and horizontal tolerances as required. Refer to section 3.4 SPE
label | Frequency - 1/Lot
label | Record - Survey as Built
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Superintendent:
signoff | (Signature)
checklist | ITP005 - Surface Water Runoff Management | itp |  |  |  |  | Tank 2 - ITP005 - Surface Water Runoff Management - Rev1
section | CAPPING LAYER
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Location of works identify as per IFC drawings
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 02 - Subgrade Preparation
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Scarify subsoil to a minimum depth of 150 mm
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 03 - Gypsum Application
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Apply gypsum to batters and table drains at rate of 5t/ha, and apply water at 10mm/m2 to create adequate topsoil bond with the subgrade
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 04 - Respreading of Topsoil
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Topsoil is to be placed 300mm thick and trim with grader and scarify to a depth of 100mm.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 05 - Hydro mulch and Grass Seeding
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Topsoil shall be hydro-mulched using the client-specified seed mix, approved mulch, and fertilizer applied at a rate of 150 kg per hectare.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - Watering of Topsoil
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Watering 10mm/m2 every day for first 8 days, then every second day to get to a total of 14 irrigation days.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 07 - Topsoil Testing
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - The PH of the topsoil shall be tested to confirm applicability of gypsum
label | Frequency - 1/Lot
label | Record - Test Certificate
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 08 - Survey
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - As-constructed survey has been completed to record the surface levels on completion. Refer to TS section 3.4
label | ○ The Contractor shall submit results of each survey to the superintendent within 48hours of undertaking the Survey.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Client Superintendent:
signoff | (Signature)
checklist | ITP006 - Erosion and Sediment Control | itp |  |  |  |  | Tank 2 - ITP006 - Erosion and Sediment Control - Rev1
section | LOT IDENTIFICATION
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Location of works identified as per IFC drawings
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
section | TEMPORARY SEDIMENT AND EROSION CONTROL
checkpoint | 02 - Clear identification and demarcation of ‘no go zones’ (where required)
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Remove vegetation and disturb soil only in those areas approved for construction work to occur
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 03 - Installation of temporary sediment and erosion control devices
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Construction of diversion bunds
label | ○ Excavation of sediment catch sumps and Rumble pad
label | ○ Temporary approved construction tracks
label | ○ Installation of Silt Fence
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 04 - Sediment and erosion control device ongoing inspections
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Inspection of sediment and erosion control devices completed to be completed at the below frequencies
label | ○ Rain: >50mm in on day or >100mm over 4 days Prior to shift breaks
label | Frequency - Ongoing
label | Record - Environmental Routine Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - Senex
label | Client: Type - WP
section | PERMANENT SEDIMENT AND EROSION CONTROL – RIP RAP (ROCK PROTECTION)
checkpoint | 05 - Underlying Lot conformance - Subgrade
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - Conformance Separation Geotextile Material
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data Certificates.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 07 - Conformance Rip Rap
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 08 - Separation geotextile placement
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Installation method complies with the requirements of the technical specification and the IFC drawings. Laps to geotextiles shall be a minimum 0.6m. The Superintendent shall inspect subgrade and the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 09 - Rip Rap Placement
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - The contractor shall provide a Work Method Statement for the placement of Rip Rap.
label | ○ Rip rap shall be place in a manner which does not damage the underlying geotextile
label | ○ Rock finished smoothed to the final lines and levels.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 10 - Acceptance of works (Rip rap)
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist / MDR
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Client Superintendent:
signoff | (Signature)
checklist | ITP007 - Leak Detection System | itp |  |  |  |  | Tank 2 - ITP007 - Leak Detection System - Rev0
section | LEAK DETECTION SYSTEM
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Location of works identified as per IFC drawings
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist/Lot drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - CHK
checkpoint | 02 - Survey control and Setout
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Confirm centres of both sump and tank locations
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 03 - Excavation of sump
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Located at 3m outside from the hinge point of the tank pad. To be trenched to a depth of 3.17 m (to be confirmed on site)
label | ○ Sump excavated to correct dimensions in line with Concept Tanks 0.8m diameter excavation to design depth. Sump pit depth to be determined onsite ensuring sufficient fall from tank centre to sump
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 04 - Installation of HDPE sump base and chamber at correct height and level
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Poly sump base to be installed at 200mm below leak detection pipe.
label | ○ Sump chamber installed plumb to correct height minimum 150mm above top of tank
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 05 - Backfill - Sump
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Backfill in accordance with CT requirements. Compaction testing in line with Earthworks specification
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist / Test
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - Leakage pipe trench excavation
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Trench excavated to correct lines and levels in line with CES drawings.
label | ○ 1:100 fall to sump
label | ○ Sufficient excavation width to facilitate installation.
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 07 - Installation of 50mm HDPE leakage pipe
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - 50mm HDPE pipe and bends installed in accordance with CT and manufacturer requirements.
label | ○ Minimum 150mm cover at centre of tank Pipe installed on 50mm sand bedding (optional) as per CT recommendations
label | ○ HDPE pipe riser installed 300mm above FSL at centre of tank, temporary seal to prevent sediment ingress.
label | ○ Pipe to be left exposed at centre of sump pit
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 08 - Surface Water Runoff
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - DN110 HDPE pipe for construction surface water runoff to be installed 1:100 fall to swale drain
label | Frequency - 1/Lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 09 - Backfill - Trench
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Backfill in accordance with CES requirements and general earthworks specifications
label | ○ 98% +/-2% moisture (Ring beam area) 96% +/-2% moisture (All other areas)
label | Frequency - Min 2 tests per lot
label | Record - ITP, Verification Checklist / Test Report
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - WP
checkpoint | 10 - Acceptance of work
label | Work By - Contractor
label | Standard / Spec - Technical Specification/IFC Drawings
label | Criteria - Work completed in accordance with CES requirements.
label | ○ Compaction reports received and meeting specification
label | ○ As-constructed survey data obtained
label | Frequency - Once per lot
label | Record - ITP, Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - Senex
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | Contractor Construction Manager:
signoff | (Signature)
checkpoint | Client Superintendent:
signoff | (Signature)