## Master List Templates
Id | Type | Name | Values | Prompting Name
86ae3961-60d5-45f1-932f-d3e37caaebb8 | checklist | ITP006 - EC - Embankment Construction - Rev0 | itp | ITP006 - EC - Embankment Construction
13b0701b-437d-4439-8589-e352aa4d6a77 | section | Inspection and Test Plan Details
f8e1fda0-37f2-4f14-9b63-6f39648a3f6a | checkpoint | 01 - Lot Identification
2d96dbf8-4f30-58b1-815e-a071a9bc0309 | note | Work By - Contractor
36696be1-f395-597e-b498-6eee8d38cc40 | note | Standard / Spec - Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0
c55d72e4-5b6c-5270-874b-60c28b9f48be | note | Criteria - Location of Works identified in accordance with project technical specification
15b5283f-f48b-5a6a-bd64-a589b1e40b17 | note | Frequency - 1/Lot
9ff5af48-147c-5aec-a4f5-10858abb8b59 | note | Record - ITP Verification Checklist / Lot Map
3d30033f-2363-5065-b134-400e8f55762c | note | Contractor: Resp - RSA
5ec84754-cc14-5a42-a8f1-46c6a29195e5 | note | Contractor: Type - Check
c0f12560-9579-550e-85b2-47bb4dbd9668 | note | Client: Resp - Senex
ed915557-5d6e-5886-840d-5c1b90b14564 | note | Client: Type - Check
b32dbc0f-bf42-453a-9eeb-65f313b37f15 | checkpoint | 02 - Lot Identification – Lot Plan
56803441-113a-5671-b36e-9f746b84823e | note | Work By - Contractor
4d430989-0ff9-551a-9578-07935b45256f | note | Standard / Spec - Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0
5ddd7d35-5d07-57cf-be14-3d5ca7e64bad | note | Criteria - Lot Plan submitted to the Superintendent 5 days prior to the commencement of the Work (if required)
523170be-e24b-5ddb-adb9-96736f53c960 | note | Frequency - Prior to commencement
30dd0259-c1e9-5e9b-aa46-404149951d18 | note | Record - ITP Verification Checklist / Lot Plan
86d70440-12ad-5979-8c77-e353758273e9 | note | Contractor: Resp - RSA
8ed29f3f-58d6-5479-bd39-6d8c1f7537e6 | note | Contractor: Type - Hold Point
8a689619-fe4e-5a03-ab20-65efc1d0f017 | note | Client: Resp - Senex
fd0734df-6ad9-57e3-84db-e6d92927f312 | note | Client: Type - Hold Point
7c444921-baa6-437a-b82e-9da65e716e63 | signoff | HOLD POINT
5396f34d-8efc-4d6e-97b8-641a59752120 | checkpoint | 03 - Underlying Lot Conforms
0a83394b-e86b-5704-93bb-08b44b4fce8a | note | Work By - Contractor
fac80fa7-9a95-5ade-8219-df34de37cd23 | note | Standard / Spec - Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
44badee9-1d7c-5f35-b1f4-a8960ea6f1c7 | note | Criteria - The Superintendent shall inspect the results of the testing of each layer in each lot of material for conformance with the Specification.
fba09278-967a-538c-a01a-f00361aaf933 | note | Frequency - 1/Lot
419ecc15-bced-5063-97bf-b66f68300de5 | note | Record - ITP Verification Checklist / Lot Map
a87f1507-1ba4-5594-ba88-a5bac673f9fa | note | Contractor: Resp - RSA
d6ddf9c4-3cd6-57a2-a7e6-da4921eaae63 | note | Contractor: Type - Hold Point
78cf7ae4-c879-5b8f-985f-b50609e2abdf | note | Client: Resp - Senex
3aa2062d-ac6f-537a-a3a8-66bf02db35e4 | note | Client: Type - Hold Point
051b6aa3-d1c0-4983-989b-b4953ffda876 | signoff | HOLD POINT
8576ce32-5e55-4c23-928e-dcbd90595d34 | checkpoint | 04 - Placement of General Fill – Outer Zone and Inner Zone
8ba1a045-a2c1-5856-a832-b72e870efa68 | note | Work By - Contractor
4fcee5b6-0357-5eba-8034-ab73a7b70798 | note | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0, Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
09b6b0bc-487a-5e9b-82e9-bc6152570c4b | note | Criteria - Outer Zone and Inner zone earth fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness in line with RSA construction methodology.
e3da42e6-dc39-5602-87da-bf9e93ef5ac8 | note | ○ Any existing surfaces to be lightly scarified and moisture conditioned prior to placement of subsequent layer to provide sufficient bond and prevent lamination.
0de455a3-9eae-524a-9989-95650d22f86b | note | ○ Overfill to outer edges of embankment to allow for trim back to design surface
3ee59b50-a41b-5c35-8fb2-542b906a93f5 | note | ○ Completed under Level 2 Testing
e143fa1f-076e-5a42-8b33-cd5ef118dd47 | note | Frequency - Each Lot
3ee9334e-efd4-5787-919a-5f48fd96ef56 | note | Record - ITP Verification Checklist / Lot Map
3fdd6701-73ce-5a1f-a55f-b97bf27fe676 | note | Contractor: Resp - RSA
57cdfb22-157c-5cdc-a9c0-30dbfdd5ab93 | note | Contractor: Type - Check
970144f1-03ef-5a9c-bd8a-4767cbf9abdd | note | Client: Resp - Senex
17816d18-b5f1-5973-aa67-ce007013c896 | note | Client: Type - Witness Point
c0c3680a-710b-4c04-bd6c-0ab5b663e806 | checkpoint | 05 - Placement of Select Fill (if required)
de02f8f1-cf4d-55d1-a9ec-de270cf90eba | note | Work By - Contractor
94118cc9-0c5b-5d8c-b453-40e8a07d3cb0 | note | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0, Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
5728a1a9-2b4d-5eea-8611-51da7bc34109 | note | Criteria - Select Fill shall comprise clay-rich soils sourced from the excavation of the dam and onsite borrow areas that conform to the geotechnical properties specified in Table 8 of OPS-TETW-CS-SPE-001 IFC Rev 0
e1357788-b3ac-5caf-8bf0-a688cc9f2003 | note | ○ Select fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness.
a19f3098-d5ed-5efc-85e1-8716ba270ebc | note | ○ The final surface shall be prepared with a smooth drum roller to create a smooth surface immediately prior to the deployment of the geomembrane material
847e5261-6c6f-539b-be48-87e4cb543f70 | note | ○ Finished surface to be free of all stones or other objects with potential to puncture liner.
ad45f216-b2a2-54ac-acb2-600be26d5a02 | note | ○ Completed under Level 2 Testing
218bb607-4d86-5ac8-bbc2-caa6add808dd | note | Frequency - 1 / Lot
3cbb926b-588f-5217-b398-8918527b37c0 | note | Record - ITP Verification Checklist / Lot Map
c297ebcf-5ae4-500b-947f-98064b8837f8 | note | Contractor: Resp - RSA
2b65c637-b850-5140-89b4-f17d4e2980bd | note | Contractor: Type - Check
3654b183-420e-58b1-89d5-9033bd4408bb | note | Client: Resp - Senex
d11fc013-e2a4-5872-81f5-b585d69c737a | note | Client: Type - Witness Point
83277ca0-c5a9-41c3-ad26-d38093f91174 | checkpoint | 06 - Testing – Outler Layer Density and Moisture
ff6d8179-c182-5671-b5bb-a2c35b2c9da1 | note | Work By - Contractor
36f07909-181a-5ab8-b9bf-7c4d045ed5db | note | Standard / Spec - Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
34bc7774-2d6e-5383-897f-de1bb6a6b007 | note | Criteria - Testing in line with Table 10 & 11 of OPS-TETW-CS-SPE-001 IFC Rev 0 (See below)
5d90cb6e-6f92-5d61-a0cf-6ba7a83188c9 | note | Frequency - 1 / 500m3
3ab4b78e-f882-5b8e-a83b-86b5264a0d3c | note | Record - ITP Verification Checklist / Report
e7187b55-4eaf-5e61-8569-b93fd5af556e | note | Contractor: Resp - RSA
1d10818d-8c94-56d7-898c-5cdcaf2c34d9 | note | Contractor: Type - Check
ca1094c1-2080-5523-9ebf-3fb8cfd6c42c | note | Client: Resp - Senex
8527d499-f472-50de-98cc-3087c0a1fb2a | note | Client: Type - Witness Point
fcf5e1e1-146f-4ffc-9926-51c076c6e80e | checkpoint | 07 - Testing – Outler Layer Material Quality
82a59712-4e7c-5b5f-a9ab-16c11a434210 | note | Work By - Contractor
5d7dc1c9-3d40-5947-abe0-ab4d21317d5f | note | Standard / Spec - Table 6 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
1cb2743f-8e15-5f45-b983-2a02cf55edfa | note | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Outer Zone Conforming to properties provided in Table 6 (See below)
d56416db-108b-50a8-9acf-d73929738d1c | note | Frequency - See Criteria
38490ca5-a55d-5389-be78-b34104defdf0 | note | Record - ITP Verification Checklist / Report
bfce86a0-a50d-5dd7-807a-97c9bf8ed4a5 | note | Contractor: Resp - RSA
6d19f863-dab6-5762-b02a-1be8b2a2fcf4 | note | Contractor: Type - Check
56c69313-4f04-53a7-b0bd-989238014a53 | note | Client: Resp - Senex
335e4ef7-92b6-539f-a8d3-7f20c4becf09 | note | Client: Type - Witness Point
0c5137cd-626a-4cc5-bf89-3018505ad269 | checkpoint | 08 - Testing – Inner Layer Density and Moisture
91f1185a-5f03-568f-96c8-fef9df0712ca | note | Work By - Contractor
b19c1c8e-7974-5812-bb14-44b52bbf5403 | note | Standard / Spec - Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
74b68c8c-c84e-5a9e-80fc-9c373cd7ea76 | note | Criteria - Testing in line with Table 10 & 11 of OPS-TETW-CS-SPE-001 IFC Rev 0 (See below)
dc7a18ce-ef23-54f8-8f19-8db501654510 | note | Frequency - 1 / 500m3
faa6b0e1-fa73-5cd2-8151-4826739883a4 | note | Record - ITP Verification Checklist / Report
1620a0f5-841a-5883-8b50-46c6fdc337f8 | note | Contractor: Resp - RSA
7beb19b0-8618-5216-8ef3-1ba82a544fa4 | note | Contractor: Type - Check
d7412273-6770-5841-acbd-4a2b4f611d29 | note | Client: Resp - Senex
39d8a134-5c08-5138-b07e-be26fde8752f | note | Client: Type - Witness Point
93e47e23-951f-47e4-b8e2-6c9188af0431 | checkpoint | 09 - Testing – Inner Layer Material Quality
c15d2f19-2e05-5429-895d-8d791399ff67 | note | Work By - Contractor
e3eea868-4926-5bde-9898-227ceac83b93 | note | Standard / Spec - Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
ce81274e-2502-5918-8855-ef2ecde2c695 | note | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 7 (See below)
c6685d8b-22e3-55e6-93ee-0163fab2471e | note | Frequency - See Criteria
797e5c43-797d-53d2-82f8-f1d07f8c0d61 | note | Record - ITP Verification Checklist / Report
b164d12c-76dd-57c1-984e-74fa91cea3fa | note | Contractor: Resp - RSA
413b1e6f-4247-5f8b-b66d-af67e04ec0d2 | note | Contractor: Type - Check
320d6364-dd71-53b2-978a-52a96ca4ee03 | note | Client: Resp - Senex
892581f5-804b-536c-8833-f8bc6bb15879 | note | Client: Type - Witness Point
8eb47570-cf7a-4016-86a2-ac89642aea3a | checkpoint | 10 - Testing – Select Fill Density and Moisture
b2d38b55-0001-5687-9fa7-d1a9ab6b0088 | note | Work By - Contractor
385e5cd7-528b-5247-9b42-7059c359cc50 | note | Standard / Spec - Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
1eb88e6a-a032-5a81-8d12-ab399599727f | note | Criteria - Testing in line with Table 10 & 11 of OPS-TETW-CS-SPE-001 IFC Rev 0 (See below)
1acf80db-ab35-5a77-a89e-25a651f2c360 | note | Frequency - 1 / 500m3
5acf81cf-cfb3-55da-a33a-eff8a4c337bc | note | Record - ITP Verification Checklist / Report
82152375-9425-5636-8053-a65605de645b | note | Contractor: Resp - RSA
3212cfe2-3a37-5c37-936d-e61ccfa7737d | note | Contractor: Type - Check
e8535253-97c8-5a67-b72e-ff2e2795a1f8 | note | Client: Resp - Senex
7514de69-4a84-5bd1-b3e8-e36e568ac1e9 | note | Client: Type - Witness Point
8cf70ad0-ba18-4291-ae53-68c8d161cb41 | checkpoint | 11 - Testing – Select Fill Material Quality
07dc1dd6-0a02-56be-a48c-1b58e86c5e0c | note | Work By - Contractor
bdadaf8a-ba2a-5d5d-9400-99ccef7e2fba | note | Standard / Spec - Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
5f600a08-cdc4-5633-b784-0a93e4b9c7e8 | note | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 8 (See below)
5235e562-bc49-5052-a9d8-8a5a60c5c494 | note | Frequency - See Criteria
197ec230-26f4-5067-b0ea-6d48d5aa0725 | note | Record - ITP Verification Checklist / Report
f25668f1-d389-536b-9b3d-408ef2275aef | note | Contractor: Resp - RSA
5436c51c-6fc9-54a6-9981-c11fe8a2e5e5 | note | Contractor: Type - Check
028f0485-d030-5639-8e03-21749228af11 | note | Client: Resp - Senex
2b089aed-158a-5ed5-8dca-ec85dce15ae2 | note | Client: Type - Witness Point
1ad5445f-dd2b-4a2c-a7a3-618017ace181 | checkpoint | 12 - Rework / Repairs to fill (if required)
a880af30-af1c-5c70-8ca4-46959305577a | note | Work By - Contractor
643dbef4-6a05-5c3f-a27c-5fac202ab2d3 | note | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0
bd84bd46-e9cf-5c48-b400-4abd1fb3f0c9 | note | Criteria - The Superintendent shall approve the extent of all repairs to damage, eroded, cracked or otherwise non-conforming materials and also the finish product of the repairs.
747550ab-e4ea-58ae-8496-5e3110c760f2 | note | ○ If the moisture content is within plus or minus 1% of the range, the Contractor may scarify that layer or area and add moisture, or work the clay to dry out as appropriate, re-compact, and present for retesting.
f8468fe8-9c47-5a82-994e-795602f84a35 | note | ○ If the moisture content is drier than 1% of the specified range, the layer shall be removed and reworked to a satisfactory condition before it is reused.
be3cf073-57d3-5ba7-a6b5-689485d9e87a | note | ○ If the dry density ratio is within 3% of the specified requirement additional compaction using a roller may be performed to increase the density and the layer, then presented for re-testing.
48f6aa7d-fde8-5070-a7a9-e21a6830a2ed | note | ○ If the dry density ratio is more than 3% below the specified requirement, the layer shall be removed and be replaced to achieve specification.
b4bf948d-160d-5dc2-b38b-72ef3e0a171b | note | ○ Retesting (if required) in line with requirements of the Zone being repaired.
c815c0fe-b174-5fa7-ae82-9f685fbe6a69 | note | Frequency - As required
70093ae5-7cc2-53da-8509-e7caa9050615 | note | Record - ITP Verification Checklist / Lot Map
6904bd0a-88a8-5eb4-a093-e94f8eb83ca4 | note | Contractor: Resp - RSA
f7222743-5b86-57d6-ba37-bdbb61384796 | note | Contractor: Type - Hold Point
97226475-a5d0-56bc-bdb9-b6190998ab0a | note | Client: Resp - Senex
2abc2bf1-f69d-5833-8480-813fea910bbd | note | Client: Type - Hold Point
e0165a58-08cc-416c-b82a-3f76b3ceef25 | signoff | HOLD POINT
f318ea0c-be0e-4c66-99ec-caf1e282e9d9 | checkpoint | 13 - Survey – Progress
fab901f6-b9f3-5ca6-bff6-9bbefa2281b9 | note | Work By - Contractor
1c8c0d5a-a095-5c5f-8a07-cc6ba10e738a | note | Standard / Spec - Clause 3.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
15cf62a6-b21b-5c13-bdfd-5cdaa81b8402 | note | Criteria - The Contractor shall submit to the Superintendent 25%, 50% and 75% embankment fill placement completion surveys within 48 hours days of each milestone achievement.
ab1d14ef-5043-5d19-b969-def7fc6b097d | note | Frequency - 25%, 50%, 75%
db34ea0b-bb6c-5d24-8324-21ddbac9a958 | note | Record - Survey
99cd1498-e62d-55d5-8cab-7a4c7f3c2cc6 | note | Contractor: Resp - RSA
4775b183-5f35-56ea-aee7-dc7acf694c32 | note | Contractor: Type - Check
9b14a90e-7185-5a6c-ac35-cc0a558889b9 | note | Client: Resp - Senex
7bafec6e-5a47-5c46-95b4-521fb3dd8c49 | note | Client: Type - Hold Point
d2286d55-02f8-4776-8cb4-b563cb2477f7 | signoff | HOLD POINT
781e3580-5153-4a98-b686-b7d88ac21d1c | checkpoint | 13 - As-constructed Survey
ff13b901-028a-5943-a6b5-d738171d5584 | note | Work By - Contractor
09e072db-b5bb-538a-8cc8-f6beb251ba94 | note | Standard / Spec - Clause 3.4 of OPS- TETW-CS-SPE-001 IFC Rev 0, Clause 20.2.4 of OPS-TETW-CS- SPE-001 IFC Rev 0
0df5c2ba-711b-5528-a710-74df68edc044 | note | Criteria - After all work, or parts of work requiring survey acceptance has been completed, a final survey of all elements of the work shall be performed and submitted to the CQA Engineer for review and acceptance.
007f52d5-469a-56c4-b427-750f96a73305 | note | Tolerances:
e84cf095-b07c-565c-8323-bcb66f51c217 | note | — Embankment Crest
549fa817-082a-5f2d-a12d-f94bd5b3b290 | note | ○ -0 / +200mm
de50c36c-1301-5a8a-acfd-a2d422e600a2 | note | — Liner Subgrade
ec4325bf-99a7-52e1-891b-471344290e94 | note | ○ -20 / +50mm
1cd2eeab-c4e7-5ea8-a988-fc5f2e5907da | note | — Final Liner Subgrade Grader
9c5cfd0e-e26d-5170-9549-133beeafb70d | note | ○ Within 1/20th specified grade
345805ae-cec2-543b-9666-06628aafaef6 | note | — Emergency Spillway (invert)
a3e3c94a-2c97-53a0-8719-468f556c36e2 | note | ○ -20 / +20mm
c457717c-013d-5b1b-87f2-38013a733d1b | note | — Extraction Pipework
5141e39e-72cb-59c5-8147-4a2f1afb9766 | note | ○ ±50mm
13cfda93-ae90-5946-9b33-ccf8681375e7 | note | Frequency - 1/Lot
960067b8-37f3-50f4-a576-75344ece6720 | note | Record - Survey
7774c2ed-c775-57a4-9e7f-a54514696cfc | note | Contractor: Resp - RSA
26bf3980-ae47-5bbf-bc26-3e627cae4d75 | note | Contractor: Type - Hold Point
33b944ad-1803-598d-999b-af4f535fbbf2 | note | Client: Resp - Senex
3a585093-5beb-563c-807e-23c3ba53f6ea | note | Client: Type - Hold Point
e719a76d-f178-4537-9fc4-0bbbc17f2692 | signoff | HOLD POINT
b8bc743e-da4a-494c-9b64-057d4565ecb2 | checkpoint | Built in accordance with this document:
6df4b410-d793-5b1e-8f33-23a007977c7f | date | Date
bce0c0f6-fc0f-4baa-9abd-83a26a092bd3 | signoff | Signed
fb7d262f-3c1e-4767-b67e-79e0531b45b7 | checkpoint | Test results received. Lot conforms to Specification:
642b7ac2-f173-552e-8efa-5d2e7b4e63c9 | date | Date
1fe97b86-e7f0-40c1-8665-19032be111cd | signoff | Signed
6824d8e7-41a9-4dca-bef7-b072ac9b82c0 | checklist | RSA.WP28.FIC - ACCESS TRACK - Rev2.0 | itp | RSA.WP28.FIC - ACCESS TRACK
69387c76-6a81-4cd5-b6a1-5fb8b21f99b2 | section | FIELD INSPECTION CHECKLIST ACCESS TRACK
022fd95d-5237-41be-947f-5d65485e7d37 | checkpoint | CH and FDM clearance
ecd64d70-71b0-4c45-b19d-ef348573705d | signoff | HOLD POINT
fa656ecc-8a11-4fd3-8b48-e85d2de166a8 | checkpoint | Identify extent of work area, clearance boundaries and any required surveying works
9cd406a0-7916-4cf2-84aa-1cd3ef7f23f8 | checkpoint | Measure access road dimensions as per IFC
39d8127c-4df2-42da-8a43-20634c7914c7 | checkpoint | Clear & Grub
62d483f9-9717-459b-8507-3c390f3b7ae2 | checkpoint | Form track profile
9d0dbe2b-ba18-4b5d-9190-d8dc61793978 | checkpoint | Construct erosion and sediment controls
db5541c9-66d7-4b26-be35-507e91222438 | checkpoint | Construct water way barriers crossings
8ef879d7-2257-4f9d-8429-40efeb51cab3 | checkpoint | Gravel cap access track (if applicable)
d5e14f03-a3cf-4b9e-8d46-0b9588da4993 | checkpoint | As Built Completed
e5960946-98c8-450c-9374-3a9adb1efd53 | checkpoint | RSA QA Inspection
29102593-1758-4123-b5b7-25627eede0c1 | signoff | HOLD POINT
81ac979c-6389-4763-b9a5-182d12096eed | checklist | RSA.WP28.FIC - FENCING & GRIDS - Rev2.0 | itp | RSA.WP28.FIC - FENCING & GRIDS
fe3b6b3a-395c-4e1f-8cd6-8457c3d37cfd | section | FIELD INSPECTION CHECKLIST FENCING & GRIDS
c5e2fbfd-517c-47a7-8dd3-585197f53867 | checkpoint | CH & FDM Clearance
1d86cd3c-1c45-4588-b040-928cd6bc756d | signoff | HOLD POINT
91f45ff0-2a78-47a0-b18c-cc897ff200b9 | checkpoint | Identify Work Area, boundaries of Fencing
e43dae43-2af4-4f3f-a2ab-44e7d07ffb44 | checkpoint | Inspect fencing materials
83ff1169-bd15-4472-afda-be13ec4fa6fc | checkpoint | Installation of fencing
c399b626-d3e9-432e-bcb7-a2cef7acefed | checkpoint | Concrete for base of fencing
9050c22d-0cdb-4f8d-9d98-38e9efb6d067 | checkpoint | Fence posts caps
ec952728-95a9-4d3d-a797-3adfa2b5b196 | checkpoint | Welding
b242b80f-c61d-43c0-8377-a8fa2db5acbb | checkpoint | Welds Galvanized Painting
15c7992f-55d2-4ca0-84bb-369113072faa | checkpoint | Gate Chain and Carabiner clips
b187d229-1ef3-4c62-b0a7-f8af9f2b6f85 | checkpoint | Box Out Grid Footings and Prep Site
41b71f21-327e-4afc-98df-9bb78afd6bcc | checkpoint | Inspect grid materials
9a7e08f6-af83-4ec6-bee7-06a88c9d9d64 | checkpoint | Compaction for Grid base
1d1e0818-68eb-45c6-a7b3-bac784e6d73b | checkpoint | Concrete Abutment / Install Base Slab (if required)
0465663b-a0b6-4e62-8519-809113177a84 | checkpoint | Position and Install Grid
25579f57-9e69-48df-ba45-9be41f42cdda | checkpoint | Install and Compact Gravel Ramps
95318c65-425c-4f30-a7bf-e01cabbed195 | checkpoint | Attach Fence to Box Assembly
99485ed6-e7ff-4695-afb1-f454172a9332 | checkpoint | RSA QA inspection
6f4cfae8-0531-44f8-814c-049e6334ab2a | signoff | HOLD POINT
a2f28301-ad52-4600-adf7-85ceaf790734 | checklist | RSA.WP28.FIC - LEASE PADS - Rev2.0 | itp | RSA.WP28.FIC - LEASE PADS
f51fedc0-fa6b-44cd-8b0c-d780ffaae9f9 | section | FIELD INSPECTION CHECKLIST LEASE PADS
cb8b0a99-5fd0-425a-873d-86dc491fb502 | checkpoint | CH and FDM clearance
1e094529-19b3-411a-991b-ac1018ed126a | signoff | HOLD POINT
f6a6b65f-46f3-4688-ab37-57a92dfdcbaf | checkpoint | Identify work area, boundaries and survey requirement
8f18f6f6-44ad-42d2-92a1-800791b3005d | checkpoint | Clear & Grub Topsoil and stack timber
072d34b6-613b-42ce-ab8e-f599f3531cfc | checkpoint | Lease Entry Construction
ed51c11b-1006-4c98-afed-520a9534beee | checkpoint | Lease construction
a2365bd3-d844-4786-83a5-b0ac4ce0e38a | checkpoint | Compaction of layers in 300mm layers
bac5b8eb-e813-4801-b37f-1ea055a7e56a | checkpoint | Proof roll
4417cd67-86a5-4a89-864a-b89288a0154a | checkpoint | Verification of cross falls/laser set ups
d46dac32-34bb-4c41-8565-14db0cbb69cb | checkpoint | Final Trim
3b5097b0-2749-47cb-b951-529fd87b3445 | signoff | HOLD POINT
11e7a05b-3b5e-4256-b29f-fe3bdebdc116 | checkpoint | DCP Testing
09866dc9-38ea-445d-b786-c575f4420528 | signoff | WITNESS POINT
a14f9901-271b-47fa-9a7a-69026aa125c9 | checkpoint | Gravel Cap (as required)
b26012a9-9c09-4e9e-9c05-edecfd3751de | checkpoint | Install ESC
5ad1a4c9-4620-4f50-8b61-85c29a8338ca | checkpoint | Cellar Installation
7bd2a227-6be0-425a-9790-f512d0f7cc09 | checkpoint | Conductor Installation – Record plumb
366fb9b2-36ce-410c-b910-bf5811ebfcd2 | checkpoint | Conductor cemented in place
54f716c1-ada9-41ef-88aa-52dfd809f0ca | checkpoint | 4 x cattle panels to be installed
2e30158d-48d1-403f-8c98-fe7eb452d3db | checkpoint | Well signage and Pipeline entry mark completed
be858ad0-ac49-4b59-b219-f5d25fe7793e | checkpoint | As Built Completed
df28eb7c-e3c4-48ba-87b1-76f9672bb41e | checkpoint | RSA supervisor inspection
8bedfbdd-7ac2-42bd-9c27-ec20351f38ec | signoff | HOLD POINT
cf576cdc-3ae5-41af-bd9b-2d78c5d476d2 | checklist | RSA.WP28.FIC - PRELIMINARY - Rev2.0 | itp | RSA.WP28.FIC - PRELIMINARY
113ae58b-3e03-4a2d-941d-8b9bceb8d1a9 | section | FIELD INSPECTION CHECKLIST LEASE PADS
93e363bd-3c35-4235-9930-675bbefbd32d | checkpoint | Access documentation of relevant ATW, LARs/PTA, Cultural Heritage, Clearance Request
e9bc2d2f-7b2e-432f-aaa8-91b07b26a2cf | signoff | HOLD POINT
25c23025-b9a2-4229-9c53-72be2794cffb | checkpoint | Mobilisation of Machinery & Fit for Purpose inspection
141eb26d-6031-4789-9d7f-2588c2ddf3d1 | signoff | HOLD POINT
0fd53f78-656e-40d9-aed1-433c179fa64f | checkpoint | Gravel Compliance
db9e68e9-2210-4718-b706-26a3fef98fa7 | checklist | RSA.WP28.ITP | itp | RSA.WP28.ITP
3b25b908-a6c8-48de-bf4b-65181a189d03 | section | 1 - Preliminary
850f0d2d-e837-45e1-957a-2c0c2bea1604 | checkpoint | 1.1 - Access Documentation
71c2652f-7ab6-5b8e-afd5-0999f1ee4481 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Relevant ATW
97ae41d2-6732-56ca-9fb9-64ea2941a8d4 | note | ○ LARS / PTA
6a0359e9-cc47-5927-a9b2-ed9b4a787f82 | note | ○ Cultural Heritage Clearance Request (Works Notice)
d604ac57-73cc-5b5f-afb5-440d174be5f0 | note | Frequency - Prior to Start
a800cf7d-c606-50ae-bacc-65efa86b9387 | note | Test Method - Review
7ff3cadf-d9f2-57b3-9200-a0a6909f0805 | note | Acceptance Criteria - All documents in place and correct.
0150894b-d52f-5631-843d-2ee874db1a54 | note | Verifying Documents - LARS / PTA
75400374-4aef-59a7-9fd6-d101805f10b0 | note | ○ Landholder Notification
588b7862-2838-583b-a2aa-f3eb6a7f436c | note | ○ Weed Washdown Cert.
122e8c07-037c-5d44-9453-3f33288412e8 | note | ○ Species and Fauna Management
3d6d9a8f-a1d6-5ee0-aae3-5ed7ff8a237e | note | ○ Cultural Heritage Induction Attendance Register
a1557186-6986-583d-a255-dee2bc65ba71 | note | ○ Cultural Heritage Clearance Report / Form
d8dd3f3b-5552-5f65-bc70-2b66681032fd | note | Responsibility: RSA - H
9a85cf4c-a1e4-584a-8f63-bf382649b517 | note | Responsibility: Senex - H
6714bc34-c61a-4e96-88cc-4323e4cde7a5 | signoff | HOLD POINT
19b16ff4-7eef-4840-a386-028e5d20bc96 | checkpoint | 1.2 - Mobilise Machinery & Fit For Purpose (FFP) Inspection
381c782b-00ca-5ca8-9c5c-4382d4c9d6bf | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Permit To Access (PTA), Land Access Rules (LARs), and Construction Management Plan (CMP)
065bd560-768b-5cb9-841d-a84d4043fa81 | note | Frequency - Prior to Start
18f47546-90e5-54e6-af8e-d3c69fcdfa8a | note | Test Method - Review
eae80768-863c-5915-beb3-671f35b3d196 | note | Acceptance Criteria - Valid Weed Hygiene Certification for all vehicles and plant.
211967ee-ba0d-541b-9ee4-03158a196dd9 | note | Verifying Documents - Weed Declaration Certificate.
e12e18f0-78ca-51f0-89c9-a93ce4c77fff | note | ○ Appenate FFP Form
8c4945ca-d2cf-5cf6-8a42-87bae3f60b96 | note | Responsibility: RSA - H
4dd3db65-480c-5365-9730-f2b736ccec03 | note | Responsibility: Senex - W
a6fba66c-3e3c-4f01-9799-288ac753c774 | signoff | HOLD POINT
8229142c-0706-4362-9241-0bd14005ecc6 | checkpoint | 1.3 - Gravel Compliance
385afd1d-df84-575e-af4f-af410405c9fc | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 6
c76360b0-71ba-5e28-8c3b-538f04689c68 | note | Frequency - Each Quarry
e2bc2527-6b8a-5ab2-810b-f252894cae43 | note | Test Method - Lab Testing
ed741200-ce4a-5f2b-9775-8b07097075b0 | note | Acceptance Criteria - Grading C
2e089bff-de73-5253-91c0-d9b81a026d66 | note | Verifying Documents - NATA Test Report
bb87964a-eb52-58e6-b550-0871125d05a3 | note | Responsibility: RSA - R
9af022e6-a69e-5ac8-8524-c5679a55f3f0 | note | Responsibility: Senex - W
9a667e0f-dc3b-424b-83b1-8497bcd09dbb | section | 2 - Access Tracks
a3291f52-3917-4123-8864-3e08c9e1a4dc | checkpoint | 2.1 - RSA QA inspection
42cb65bf-b111-5a54-9e12-d023367d0056 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
a5fb43a7-60e2-59a2-80fd-7de67421d4d0 | note | Frequency - Each Track
f0e6481a-cf1b-569d-9463-a83cd1da767b | note | Test Method - Visual Inspection
9121480d-2407-559a-8bf1-b9c9f13ddd01 | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
32c2b27f-7e05-59f6-bcc3-17253cec4dee | note | Verifying Documents - Access Track FIC
22ce588f-7126-50c2-a198-7dfb5d8d4ada | note | Responsibility: RSA - H
346b5b1d-0537-5430-a530-106858ac772d | note | Responsibility: Senex - N/A
b2cc6697-593d-4085-9e7e-1956e09bf93d | signoff | HOLD POINT
f479ab23-723e-4f5e-819a-15ef56e38d9e | checkpoint | 2.2 - Client Signoff
4219a84c-6515-54e9-807a-b7eaf042211b | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
aa1e469f-600a-50f3-a12e-d67ea71254c7 | note | Frequency - Each Track
7bacc9ff-be70-5434-9243-1d327a5c1360 | note | Test Method - Visual Inspection
27ce9cd6-7a35-5aff-adfc-4fa7f95b1d6d | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve access road is fit for purpose prior to machinery being demobilised.
662a3ebc-87f1-5885-a949-fe8da499983d | note | Verifying Documents - Access Track FIC
6a7fb81d-d50b-5272-9319-b6206065559f | note | Responsibility: RSA - N/A
9cd8c4d0-ca51-5faf-bf9a-d14173d90998 | note | Responsibility: Senex - H
48512afa-dd59-43da-bd3d-2b72143fd68a | signoff | HOLD POINT
0f3e0f6b-895d-48d6-9211-041617e0cb24 | section | 3 - In Field, Property Fencing and Grid (Fencing)
6338b478-60e3-4d55-9bd2-e1ca0fa199a8 | checkpoint | 3.1 - RSA QA inspection
56315118-5a29-5e84-9bd2-88ef1f7c930d | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
9eee845a-5b64-5c36-8f4d-d3f5a3fa2d30 | note | Frequency - Each Grid
28d75ef2-bf0a-51f2-97d2-caec73f52535 | note | Test Method - Visual Inspection
709f73e5-5ed6-5bfa-8f9c-0754c64a268f | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
eae51c37-ff80-5163-8230-41d1557a0c2b | note | Verifying Documents - Grid &Fence Installation FIC
b596122e-8d39-5884-9a03-f1a684141ed7 | note | Responsibility: RSA - H
ee404a61-27a2-5ef5-8b4e-521351410070 | note | Responsibility: Senex - N/A
73b830a9-79f6-4513-960f-e638094163fb | signoff | HOLD POINT
a16c5e69-7d9e-43bd-b97c-01bbbe101c85 | checkpoint | 3.2 - Client Signoff
6a7cf3e6-3ed5-5c55-8705-dc44201f45e8 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
13d3f1b0-c976-5230-b04a-ed0f42cc97aa | note | Frequency - Each Grid
f21911c7-8756-5f97-bb7a-bb894e684879 | note | Test Method - Visual Inspection
5f43cbe5-5342-5944-b9b2-e4319ba05cc1 | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
a33a9079-484e-5a64-bd18-766210d3da69 | note | Verifying Documents - Grid &Fence Installation FIC
ac71f739-5a26-5541-a671-d593c1b00c23 | note | Responsibility: RSA - N/A
3e74f123-d7fc-5b78-a196-3be2f982dd2b | note | Responsibility: Senex - H
8aaf4bb8-1163-4b9b-bae2-183bded972b4 | signoff | HOLD POINT
0f33aece-7d30-4cd1-b16f-902899fdc216 | section | 4 - Lease Pads
d0aa8a66-adb2-4dd7-9eba-be0da54aeef1 | checkpoint | 4.1 - RSA Supervispr inspection
4ee7d60d-e2c5-59f0-8e3b-05c4ca55c924 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 & OPS-QLDS-CI-SPE-002
00575f72-aa66-5277-8117-554ee62e5478 | note | Frequency - Each Pad
f5f49b26-7082-5a7a-b866-42e9036127f8 | note | Test Method - Visual Inspection
d24190e2-c105-531d-b793-bb998067e882 | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
4f395cd1-bfb3-5d4c-befc-daf2a66a69c0 | note | Verifying Documents - Lease Pad FIC
756f6fdc-b986-53af-8bb1-d3ecea6f6ad4 | note | Responsibility: RSA - H
cdd81c8b-ced8-5dd7-b1c0-d50eb79d9493 | note | Responsibility: Senex - N/A
2b320a1c-8a4b-4c86-bbc6-b9667ad8fd31 | signoff | HOLD POINT
0c74c43e-afea-40e4-8428-5e1f82948ea1 | checkpoint | 4.2 - Client Signoff
88adf751-88f7-5499-a75a-2e36121818e2 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 &OPS-QLDS-CI-SPE-002
faa9f5ef-0a27-50d6-8cc9-215865a2dacc | note | Frequency - Each Pad
1a19e18e-9b90-5df5-a56a-7deac1e079ea | note | Test Method - Visual Inspection
54502229-c3d2-5db9-8c46-4e8887db476f | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
945a166e-e965-5f6b-a45e-79ff36c32594 | note | Verifying Documents - Lease Pad FIC
2505f2c3-85cf-54a4-9d71-58b8af01ee35 | note | Responsibility: RSA - N/A
9e8deef2-a7a5-520b-b5f8-be931d629273 | note | Responsibility: Senex - H
3c4a1e69-50c3-46aa-b2e6-419eb29659ac | signoff | HOLD POINT
2f0e9f06-b599-40c2-a349-b81952e15585 | section | Reference Documents
cd4bac6c-b1fe-408a-9f3c-40a6ca6ee8b2 | checkpoint-no-value | Reference Documents:
3ee55128-e638-55c7-9e0a-edd08bd54646 | note | SENEX-QLDS-EN-PRC-003 rev 1 (Queensland Erosion and Sediment Control Procedure)
f5931ffb-1737-5e76-ba25-8703364e0121 | note | OPS-QLDS-CI-SPE-003 REV 0 (Fencing, Grids and Gateways Civil Specification)
bbfb6c57-357c-50a4-a756-77ed7aac2e62 | note | OPS-QLDS-CI-SPE-002 Rev 0 (Lease Pads, Hardstands, Access Roads Civil Specification)
7df7496a-a078-50fd-8964-3bf189030bfb | note | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
1cc94b81-18d8-5fc7-af30-e21707fbd93e | note | SENEX-QLDS-CI-GDL-001 Rev D (Whoa-Boy Construction Guidelines)
1871146a-0de5-5b5d-bd4f-3e2b4a5af22c | note | SENEX-QLDS-DR-SPE-001 Rev 4 (Conductor and Cellar Installation Specification)
e0800e5c-727d-5637-8ad4-114f4d2cce0d | note | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
587ac5ea-06b4-57ce-8c29-1d7eb5192a15 | note | OPS-QLDS-CI-GAR-001 Rev 1A (Well Lease Layout Standard Drill Rig Civil General Arrangement)
7ec76482-c08a-457a-a805-27986355c9d2 | section | To be completed upon completion of all work activities
cf62cb0b-e4c6-4298-b0e1-4d0e8730e64f | checkpoint | This is to confirm that the above ITP has been completely signed off. All necessary inspections have been completed, the verifying documents have been provided, and the works conform to the contract specification
5f584e7a-a84f-53b7-909c-18ae703aa8c5 | note | Completed By:
8ad45b02-c269-529a-bcc1-de4a886cdb7f | textbox | Contractor Representative - Name:
32a5bead-bd3e-5e5a-825c-2b50efd28c74 | textbox | Contractor Representative - Position:
179cf659-e8c0-5fdc-adf7-3575bd95f808 | textbox | Senex Construction Representative - Name:
2b59d25d-8fe3-5658-9beb-6456c0232a50 | textbox | Senex Construction Representative - Position:
b559f123-c776-59b3-9f83-bccacbc9cc0f | note | Approved By:
282912a7-00bb-5ab8-9f41-44fcb38d7107 | textbox | Client Representative - Name:
5c80d40c-d465-54ca-b9d0-8291c6abb015 | textbox | Client Representative - Position:
db995536-f190-5a12-a959-de32801538fd | date | Date:
96a60e51-6445-4c84-b9e5-dceb1db5722f | signoff | Add Signature

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
53c4ae4a-9f7b-4590-aec1-4e4b10ebeea7 | checklist | Tank 1 - ITP001 - Clear Grub & Topsoil Stripping - Rev1 | itp | ITP001 - Clear Grub & Topsoil Stripping
93c3a332-0ef4-456c-8d2f-b63804de29c3 | section | CLEARING & GRUBBING
b0fd0254-cad8-4739-a0f2-c6b9472e32b0 | checkpoint | 01 - Survey Set Out
e7bba3ae-d963-5b7d-b72a-e00d6db6d866 | note | Work By - Contractor
a97ba3d4-3474-5815-bb15-4ef12b29616e | note | Standard / Spec - OPS-TETW-CS- SPE-002
1cb1d3cb-7c29-5614-8308-024049d559e7 | note | Criteria - The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works
227aadef-9b36-5be6-b605-ca85bdb7a2af | note | Frequency - Prior to commencement
da0e4a91-987b-5650-8ca5-8cb1afb5a9f0 | note | Record - ITP Verification Checklist/Site Survey
3d11b507-0f98-5033-a0dc-cbd75554eae2 | note | Contractor: Resp - RSA
be68a9e4-5084-5986-8ae2-47f7d3b114b8 | note | Contractor: Type - WP
1d2858e2-aeff-5282-a9e0-0bedda738a16 | note | Client: Resp - SENEX
50764931-0c2b-5452-8451-b8c6e81a9636 | note | Client: Type - WP
3750afad-12c0-4546-ad78-382670268bb0 | checkpoint | 02 - Site Services
51d01ef4-f3bb-5b13-8f06-f2df2a34102a | note | Work By - Contractor
364cc07f-af62-553e-b218-f161642fbeb6 | note | Standard / Spec - OPS-TETW-CS- SPE-002
03b635fe-969d-5df8-a0c5-56cd37bc7f53 | note | Criteria - Contractor shall take reasonable steps to locate all existing service on the site. Where existing services are identified they shall be clearly marked for the duration of the works.
605ca2ee-ed4d-578e-8ab7-db0ff632910d | note | Frequency - Prior to commencement
dde1a85b-6155-5ed7-8463-93c3525de96c | note | Record - Site general layout drawing
525708a3-e448-5506-9656-85d36189375e | note | Contractor: Resp - RSA
7eb4828a-15dd-53fe-8993-3e624988242d | note | Contractor: Type - HP
8e5df944-37d5-541a-8678-c2a8580ad0ca | note | Client: Resp - SENEX
abf98ad6-6a34-5d79-aec1-7fed872f692f | note | Client: Type - HP
c64de127-0f16-4893-a0f0-b47e949098b8 | signoff | HOLD POINT
9c3716ee-8e17-4a8c-bbef-19988818c25e | checkpoint | 03 - Lot Identification
d2cd70e8-850e-5e9b-9716-589c0d7bdf5c | note | Work By - Contractor
06be045e-6952-592f-adfc-33c6f705d9ea | note | Standard / Spec - OPS-TETW-CS- SPE-002
52798d97-3731-5d48-ae11-46381d281bdc | note | Criteria - Location of works identified in accordance with the Project Technical Specifications.
f5636814-6b98-53c0-85e4-07de7b17c853 | note | Frequency - 1/Lot
5dfe5117-9b8d-5893-a17f-056537a9eec9 | note | Record - Attached Drawing
2034a032-bec4-514a-95f5-3f4fec4ead78 | note | Contractor: Resp - RSA
caaea6bd-d781-5998-90e3-95528c9714b2 | note | Contractor: Type - CHK
25f64962-0284-5929-8aa1-5369de848c22 | note | Client: Resp - SENEX
8a95e962-b4ec-50e3-bf80-ce2ffa330bc0 | note | Client: Type - CHK
f99913e0-c1a5-4091-ad39-4208629843df | checkpoint | 04 - Clearing& Grubbing
002f6e66-1864-508d-b51f-e8a9804d8c12 | note | Work By - Contractor
339c31cb-c387-5d1e-bc30-5c50a63ac47c | note | Standard / Spec - OPS-TETW-CS- SPE-002
f20f81b6-b171-5c4f-aabf-633ff1297369 | note | Criteria - Clearing shall be performed within the limits of the works indicated on the drawings.
899f627b-4a39-5cee-8d05-6e8e6815a538 | note | ○ Trees, shrubs, logs, debris, perishable material, organic matter, fallen trees, overhanging branches and surface obstructions shall be removed from the stripping area.
b2d129df-6ef1-58b9-97f6-df4da71744d7 | note | Frequency - 1/Lot
dec6e55c-3dff-59b7-82d9-0c319b125baa | note | Record - ITP, Verification Checklist
859c8143-4a93-51dd-a8ef-cf1ee7900c2d | note | Contractor: Resp - RSA
5d7e6470-d8e3-5446-b644-f053d370f460 | note | Contractor: Type - HP
cfcbc859-2134-55ff-8f8d-44c2454d1bc8 | note | Client: Resp - SENEX
cc377ba5-6bbb-5009-a7ed-27de7f4085d5 | note | Client: Type - HP
142c3494-b9bf-4bb7-bf0c-5117798e9a90 | signoff | HOLD POINT
e482c6bf-a38a-4dc1-ae1c-35fef339a301 | checkpoint | 06 - Stockpile of Materials
da4aa5e9-97bf-5cf6-910f-8e1254748dac | note | Work By - Contractor
753254d8-25f2-56ec-8db9-a624020e67e8 | note | Standard / Spec - OPS-TETW-CS- SPE-002
c5e5d2cf-846d-575b-8c5c-836948165f6d | note | Criteria - Cleared and grubbed materials shall be stockpiled or disposed of as directed by the superintendent
3d5b916a-85ba-5dbf-8e0f-91ea19befc9f | note | Frequency - 1/lot
e21692af-580a-5723-b7c2-23b617bd2ce8 | note | Record - ITP, Verification Checklist/ Lot Map
fefe0304-d4b4-58cf-a24d-15adfe9fae68 | note | Contractor: Resp - RSA
8a2969b9-7090-5679-aba5-5ef3e7d6a47d | note | Contractor: Type - WP
78e97675-fb63-5329-b487-a35960e404e3 | note | Client: Resp - SENEX
2179f778-3c74-51b6-bf7e-194109e5d862 | note | Client: Type - WP
4cccf8ff-c6f2-4fac-8906-ab1a81e695c1 | section | TOPSOIL STRIPPING
788ec31f-7937-415d-94c2-2b8f606d58eb | checkpoint | 07 - Topsoil Stripping
0321b271-92e5-5324-83fe-7d88bcedcf52 | note | Work By - Contractor
1da4e556-9084-5744-983f-8c4891bb7a9c | note | Standard / Spec - OPS-TETW-CS- SPE-002
ac5ac184-1df8-5501-a3dd-711e1b2fc3f1 | note | Criteria - Topsoil shall be stripped such that all organic rich soil and roots/rootlets has been removed from the foundation of the embankment and internal borrow areas
cb9d451b-6961-5986-b3d7-db8f421355e1 | note | ○ Topsoil shall be stripped to the nominal depth of 300mm+10%. Any areas with depth greater should be notified to the superintendent.
e27fc0e4-9b58-5acb-af6b-34138a07c425 | note | Frequency - Confirm with survey
2007e523-bb9c-5480-9b3d-c38d9384dea8 | note | Record - ITP, Verification Checklist/Site Survey
8fbcec8b-e326-5d1d-9ab5-777d1a1e595d | note | Contractor: Resp - RSA
e9135059-95b0-5fd8-937d-de356a5f8059 | note | Contractor: Type - WP
534230a6-114a-5af2-807a-142a3c3b54f2 | note | Client: Resp - SENEX
2491e05f-40d4-5e6d-9f09-717e9f49dc75 | note | Client: Type - WP
f847b2da-5ad4-429b-b451-3fc98735c558 | checkpoint | 06 - Stockpile of Materials
f60ee3cd-6ee4-551e-b842-d6c153a1d8b8 | note | Work By - Contractor
a979b01b-7c12-5d2d-94db-e9c21d775e72 | note | Standard / Spec - OPS-TETW-CS- SPE-002
ff35f736-487d-52f7-b0ba-22c508451c85 | note | Criteria - Stripped topsoil shall be stockpiled where directed by the Superintendent, for reuse.
e302cca1-8ea7-5981-aed5-e66dfd2e1a99 | note | ○ Topsoil is to be placed in a loose, non-compacted state, to a maximum height as directed by superintendent.
d7ce26ca-ebb3-54c8-9396-ddf2e244c688 | note | Frequency - 1/Lot
4a890c4a-dc95-5bd6-9161-e5464dd008fd | note | Record - ITP, Verification Checklist/ Lot Map
b215c489-e5e9-565d-9f4c-14f4a2340ded | note | Contractor: Resp - RSA
4b11b2e5-bacf-5b77-ae8a-483f1e38215a | note | Contractor: Type - WP
d4236d9d-ec49-5ce6-b34e-69e37b22abfc | note | Client: Resp - SENEX
1590d5e0-c3dc-53ca-a1bb-5f7861669b1b | note | Client: Type - WP
d990542c-29f3-49d0-9121-f28f4287e7b0 | checkpoint | 07 - Topsoil Strip Survey
56d83321-e818-59bc-a124-9ca97e5981d9 | note | Work By - Contractor
9725fc5a-4d19-5af7-97f2-b6105376594f | note | Standard / Spec - OPS-TETW-CS- SPE-002
95f74c92-dd8d-5eb7-a8c0-b16382953ca1 | note | Criteria - As-constructed survey has been to be completed to record the surface levels on completion of topsoil stripping.
e8587ba9-2129-5554-8741-12ac063b494e | note | ○ The Contractor shall submit a topsoil strip survey to the superintendent prior to excavation and/or placement of fill material
1ddc5582-42ac-5bb8-9975-3dd073447b99 | note | Frequency - 1/Lot
f5bc6b1f-9b57-58e9-ad86-ce48f3ec4e48 | note | Record - ITP, Verification Checklist/Lot Map
5c04cd98-aeff-59f2-9d33-c38d240da9bb | note | Contractor: Resp - RSA
93082e0a-57cc-520b-b70e-4df11826de02 | note | Contractor: Type - HP
1f164e76-9c77-5a4b-90b8-3836c1a4abe0 | note | Client: Resp - SENEX
eb3524de-abc4-5fdd-bf79-d46e73b44758 | note | Client: Type - HP
e85f53f4-d2c3-41a3-8b30-7ec24b4155f9 | signoff | HOLD POINT
6c1244d2-9597-4913-b5c3-fddeae2999c7 | checkpoint | Contractor Construction Manager:
6c425e62-7bdf-4404-b838-2f7612735c6e | signoff | (Signature)
355a8170-91a1-4112-b160-55bd2f3c9c46 | checkpoint | Superintendent:
7e5aacd9-3667-4328-a4cb-d3ab5b29946a | signoff | (Signature)
179174af-2596-4a70-9c30-38525e59c7f2 | checklist | Tank 1 - ITP002 - Foundation Preparation - Rev1 | itp | ITP002 - Foundation Preparation
3d307aa6-f4cf-466a-9ae5-f987c0cef180 | section | FOUNDATION PREPARATION
16782f03-e781-403a-bab7-331f7ccd2916 | checkpoint | 01 - Lot Identification
98dc8a51-64c4-5053-8e25-28b50e5653ee | note | Work By - Contractor
616352c7-ae48-51ee-863f-cc00aacac528 | note | Standard / Spec - OPS-TETW-CS- SPE-002
840f4d6b-a2fc-5075-ad3f-80d1c1bb993f | note | Criteria - Location of Works identified in accordance with project technical specification
7a32ce29-9016-50b4-a18e-0ab5bf25740e | note | Frequency - 1/Lot
e242d504-225f-59f5-bae6-9b22f5ca1f9c | note | Record - ITP Verification Checklist/Lot Map
22e4f751-0596-5cbe-b0d8-dca81441929f | note | Contractor: Resp - RSA
d9336a86-b0b0-53cf-b49b-dd80e2e73d14 | note | Contractor: Type - CHK
7f276d90-1606-53bf-a2a4-9b806b34d9e0 | note | Client: Resp - Senex
cef3e88d-8c6b-54e7-ad92-c2a57854d708 | note | Client: Type - CHK
ed576f17-0ce8-4930-8e46-adc78f97ba3b | checkpoint | 02 - Foundation Preparation
5e5f1019-586f-59ac-8b98-b5c7cf1fcdc7 | note | Work By - Contractor
d6051101-6715-5341-93b9-d9a8ba1e1c34 | note | Standard / Spec - OPS-TETW-CS- SPE-002
9048c553-ef68-5fe9-bfbd-80bf172c1417 | note | Criteria - Foundation preparation of Lot will be visually inspected for material type, moisture and organic material prior to foundation preparation works.
b1ffb197-ed2f-510d-9874-255019b700e4 | note | ○ The Subgrade shall be trimmed with a grader, smooth bladed scraper to assist with the inspection process.
0646fb0d-8fe3-5eeb-bcc6-1b457ecbb98b | note | Frequency - 1/Lot
319a9ff0-9d40-525c-9611-f4a991696e63 | note | Record - ITP Verification Checklist/Lot Map
78efc3ee-72a6-5491-89c7-94e3c5fc0823 | note | Contractor: Resp - RSA
2caf6a8f-af1f-5863-a1c4-7eb7fed0913a | note | Contractor: Type - VIS
057e022e-97e4-5e88-b903-84a3ed746dbe | note | Client: Resp - Senex
e005341b-5d3a-50b5-a11e-43b8c49f7427 | note | Client: Type - VIS
fd0d7142-8323-4b25-8fb7-3fda93e895b4 | checkpoint | 03 - Foundation Preparation – Proof Rolling
e1f38ccf-f280-55c9-8191-447ab3cc015c | note | Work By - Contractor
92bd2124-3f6a-5d7f-8767-984183aac752 | note | Standard / Spec - OPS-TETW-CS- SPE-002
7c1f71ee-321e-5430-855e-4277d0e7f79d | note | Criteria - Subgrade shall be Proof Rolled in accordance with Queensland Department of Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client.
1d1867c8-28f7-583f-952c-5113c6009111 | note | ○ Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
7510a448-148c-55ea-86ce-9b64231a48e2 | note | Frequency - 1/Lot
9230a477-edd3-5a59-88ec-ded1cb331e84 | note | Record - ITP Verification Checklist/Lot Map
1d56bd14-de34-58ab-8819-544c1229c2e0 | note | Contractor: Resp - RSA
fcbea538-d4d0-584c-bb41-576d69d75d41 | note | Contractor: Type - WP
0a0f7f71-c9e2-5774-94e7-57efd482dc4a | note | Client: Resp - Senex
1cbc4f40-544f-526a-bcb3-f6501f8d55f2 | note | Client: Type - WP
7cda2e50-bb5a-4707-b377-d6d8801b662b | checkpoint | 04 - Dynamic Cone Penetrometer (DCP)
08a5a9a4-6ba8-5c0c-ba14-8682d0da61e0 | note | Work By - Contractor
9e95c9fc-e85e-5f31-84df-9e1427429800 | note | Standard / Spec - OPS-TETW-CS- SPE-002
b31000a0-be99-583a-a7db-e6bcab8405d3 | note | Criteria - DCP testing shall the undertaken in accordance with AS1289.6.3.2 by the superintendent to assess the consistency of the subgrade. DCP test Shall extend to a depth of 1m and achieve a min of 3 blows per 100mm penetration
0537e0fe-1b6e-5939-9e30-3c62f4a09419 | note | Frequency - 1/2500m2
3ebc36af-7f4e-5454-9458-c7390eeb5b47 | note | Record - NATA certificate
354d17e9-7fb7-5c43-b1ae-0399c4dfb298 | note | Contractor: Resp - RSA
e164ca64-24c3-58dd-8eae-449a09753bfe | note | Contractor: Type - HP
a614ff5e-09dd-5312-9a75-e8629e411b4b | note | Client: Resp - Senex
ff5f4b93-e5a4-5f53-8d47-1800b8d84c86 | note | Client: Type - HP
ea30fcab-2e4f-4c37-a778-7e252fbb40ae | signoff | HOLD POINT
26bd87f9-5d06-4405-bba2-4bb7140b954f | checkpoint | 05 - Foundation Preparation – Ground Surface Treatment
ffc049f8-e140-5511-9708-6201832f60ae | note | Work By - Contractor
0ffb7e82-e858-526d-b733-ca2e7f081cf8 | note | Standard / Spec - OPS-TETW-CS- SPE-002
8dd34832-919a-555e-9213-c5c240506c48 | note | Criteria - Scarify minimum 200mm, moisture condition and compact.
9e503a1e-b0b9-54be-ba57-3d74fec24ba9 | note | ○ The Superintend shall inspect the subgrade for conformance with the specification prior to placement of overlying fill.
fe6ea514-059e-5a24-af47-0c891273b49c | note | Frequency - 1/Lot
65e8f093-e144-55b7-9be4-66a6e8ca589b | note | Record - ITP Verification Checklist/Lot Map
9e76c4d8-f174-50f3-8924-2e7c53fce3c0 | note | Contractor: Resp - RSA
94a7f5c6-998d-5afb-82a6-efd18520618e | note | Contractor: Type - HP
c55480dd-08b3-56e5-a96f-654761984d55 | note | Client: Resp - Senex
aa64a3a2-8a6c-598d-bdf2-0e56021488a7 | note | Client: Type - HP
d9d4f61b-b50f-420a-a004-dcb8f0eaa473 | signoff | HOLD POINT
81398351-d6d2-4890-bba1-a2c3ee0bb7a0 | checkpoint | 06 - Ground Surface Treatment Testing
5bd04205-3594-522b-8027-0cb39ca37a1a | note | Work By - Contractor
e23e9b54-3b44-57d4-9f3d-464389f307d8 | note | Standard / Spec - OPS-TETW-CS- SPE-002
a5fc32b1-48b7-5faa-8c28-6766ff54df32 | note | Criteria - Tank Pad foundations surface level shall be scarified, watered and compacted to a density ratio of no less than 96% of standard MDD and -+2 % of OMC.
e50585fd-5788-5a1a-9609-8479d2b0875b | note | Frequency - 1/2500m2
caea5fab-4e8e-5768-9532-979fb5d7c4ca | note | Record - NATA certificate
24f926ae-3be9-55fc-bc69-e783b8df7f84 | note | Contractor: Resp - RSA
26c468b3-d058-55c3-8be3-63a6472279a1 | note | Contractor: Type - HP
dfe4f221-81df-525f-a489-25e2ddde0954 | note | Client: Resp - Senex
4e20ae41-892f-5a3a-8503-bb26ef5743b0 | note | Client: Type - HP
0b26e828-153f-4d86-a439-b89fdde504c9 | signoff | HOLD POINT
5f774825-8604-4a3e-904a-e6ef983c6d35 | checkpoint | 07 - As built Survey
5591abbf-2e27-5d3b-b434-8f564a090c7c | note | Work By - Contractor
5e19dbc8-3552-5359-9ec2-afd4ea05d6b8 | note | Standard / Spec - OPS-TETW-CS- SPE-002
51d2cec4-375f-53db-8f7b-ccc217c96a7e | note | Criteria - Finished levels checked for Vertical and horizontal tolerances as required. Refer to TS section 3.4
a584e67a-cbba-5bae-a427-1d131ba26bc2 | note | Frequency - 1/Lot
ce17288b-b6c4-566e-92f9-000f4100530d | note | Record - Survey as Built
7b0c5c4a-0678-5691-b909-ea929ac3ce14 | note | Contractor: Resp - RSA
c7b799db-e5c5-5aa0-bb73-455ba2af176f | note | Contractor: Type - HP
76fbabb1-6e48-5f19-a484-36f9676d2b31 | note | Client: Resp - Senex
0cf14b67-51e3-579a-962e-add31d3dfa1d | note | Client: Type - HP
1034d2c2-61b3-4eed-915f-d28efc068191 | signoff | HOLD POINT
bedc3a13-e44b-4a97-aa22-07d0c0610225 | checkpoint | Contractor Construction Manager:
f1ff0aef-9de6-485c-bfae-65571ffd6cc6 | signoff | (Signature)
7c30208d-ac9a-4478-86fd-79be511e6eab | checkpoint | Client Superintendent:
4d24ad31-7fec-4bb6-a40b-6c61eb6e935b | signoff | (Signature)
2d559604-216b-46b0-b1ec-0ae65de22a6a | checklist | Tank 1 - ITP003 - Embankment Construction - Rev1 | itp | ITP003 - Embankment Construction
8946a8e4-e75a-4d88-b396-a23419eef642 | section | EMBANKMENT CONSTRUCTION
c28df1e1-b646-4549-b127-d66dcb270a3e | checkpoint | 01 - Lot Identification
6caadfd5-c3ec-596d-bbb5-8eb1a105484e | note | Work By - Contractor
3e6f60ca-02b0-5422-a3b0-b4ed1c2df1bf | note | Standard / Spec - Technical Specification
b1139fcc-3b5d-528c-928f-139cceaeb722 | note | Criteria - Location of Works identified in accordance with project technical specification
f4839f70-afdb-5cb5-954c-f7be258ab12a | note | Frequency - 1/Lot
67cf919b-8194-58d9-ae86-c95e2388158d | note | Record - ITP, Verification Checklist/Lot Map
aa57677e-5a6c-5701-91a0-573e36c46dad | note | Contractor: Resp - RSA
e7777f0b-f348-579e-8c78-f4f5ccc48e88 | note | Contractor: Type - CHK
af4a1edb-2d85-52ae-a0d6-46643b000595 | note | Client: Resp - Senex
2994f650-c773-5dda-ac63-b9e2571f297e | note | Client: Type - CHK
fddc64b0-4094-4795-9030-ca3bdbfcb0c6 | checkpoint | 02 - Underlying Lot Conforms
f3458dbf-ee17-5e21-9ff2-2b22460ba80c | note | Work By - Contractor
32c4f0f7-cdba-57b7-86b3-3d83936a5dae | note | Standard / Spec - Technical Specification
0f7e69dd-f3e1-5ac4-9904-d4da7bb98e91 | note | Criteria - Foundation preparation works completed in underlying lot.
6272c84e-ad3a-51f4-9424-178b903f70ed | note | Frequency - 1/Lot
3c9794ca-dcfe-53f3-a1dd-3f21080ecf98 | note | Record - ITP, Verification Checklist/Lot Map
78085e18-2f61-5885-a741-23b5daebff3f | note | Contractor: Resp - RSA
be045e54-5cf3-5af5-ae79-a1d01ccd3584 | note | Contractor: Type - CHK
923d33a9-4ca3-5e83-9c06-f586b4e0691f | note | Client: Resp - Senex
27d3e3c6-3c1f-5b92-bc60-020209ae698f | note | Client: Type - CHK
0d74a3b1-dc7e-47c8-b0ae-ad73993ec3db | checkpoint | 03 - General Fill Material Requirement
4ee10846-5532-578e-8459-9a9c53d12ce4 | note | Work By - Contractor
50bff719-6829-5367-a766-7a1f95d07da7 | note | Standard / Spec - Technical Specification
2fe98834-0476-5d1d-acfc-1e6c2022f2af | note | Criteria - Grading Requirements
ad696cb2-21d2-57be-bcb6-02f86ff8eb9a | note | ○ 75mm sieve – 100% passing
459164c7-0cc9-56fd-84ec-87d8c263ef03 | note | ○ 37.5mm Sieve – 90 to 100% passing 19mm Sieve – 80 to 100% passing
febfb33f-c4b1-5ada-997e-eac716da445c | note | ○ 4.75mm Sieve – 60 to 100% passing
e3c8d71f-ba08-5e1d-876e-cd5ae1cb965e | note | ○ 2.36mm sieve – 40 to 95 % passing 0.075mm Sieve –15 to 90% passing Indicator requirements
f2800d1a-f893-57a8-a4ef-a0014e241176 | note | ○ Plasticity Index – 10 to 40%
34a67a51-1703-5755-b251-b80b267cfbd8 | note | ○ Liquid Limit – 20 to 60% Emerson Class 2 (minimum) Organic content 2% (maximum)
c542e626-aa58-56f2-bdc2-c3aa360ccb5e | note | Frequency - Refer to TS Table 11
969db017-e043-5560-b045-34116bc680ee | note | Record - Laboratory test Certificate
7da4835b-a1a8-5003-9edb-d74fe09c02d0 | note | Contractor: Resp - RSA
881c56dc-7548-5629-a204-1a32d7d459e3 | note | Contractor: Type - HP
553c95b1-e79b-5f97-a399-e4817cbb549f | note | Client: Resp - Senex
da947d53-bcda-57b3-abcd-55d7fd797142 | note | Client: Type - HP
80d19fc4-62da-46e5-a949-57e3da6bbf72 | signoff | HOLD POINT
c5d88acf-e0be-49d1-9511-a924ee8d0044 | checkpoint | 04 - Fill placement
23961720-b996-500b-b4c3-66fe3ecbcf6f | note | Work By - Contractor
c026e037-10f9-5a74-a683-13cb09a64688 | note | Standard / Spec - Technical Specification
c6e0cfe0-6909-52d9-8b16-133f0aed3309 | note | Criteria - General Fill
fb5e25d9-f951-504f-99e7-c4224c1973de | note | ○ Placed in continuous, approximately horizontal layers for the full width of the area, having a compacted thickness of not more than 300 mm or less than 75 mm. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm prior to the placement of the next layer.
03316d91-2be8-5a3a-9ab9-77b45da83b13 | note | Frequency - Each Lot
5ca337cf-90f3-50b9-8b83-9056954a9f60 | note | Record - ITP, Verification Checklist/Lot Map
7340c9ae-7964-5407-bc34-c02da777721b | note | Contractor: Resp - RSA
a0a31052-e0f8-5faf-9923-6197f5a38f21 | note | Contractor: Type - WP
fdd7fc26-6780-5076-b869-d23b10e57bd5 | note | Client: Resp - Senex
5d34dd80-e9ba-5cab-a983-dc9e38bf454e | note | Client: Type - WP
0a106e51-a6c1-4f62-ba2f-395dee31ccbe | checkpoint | 05 - General Fill Testing
30cdc10b-f87f-50d4-9b8a-3d8221e495bf | note | Work By - Contractor
f0bb2bf1-9d63-5e1f-a5d9-ef274173e652 | note | Standard / Spec - Technical Specification
7182dc74-a5fd-5a97-a8f4-644cbac6e62b | note | Criteria - ≥ 96 % standard MDD.
33e8294c-b4fb-57c9-95c4-96df0826b6fc | note | ○ NOTE: ≥ 98% standard MDD for the Earthen Ring Beam General Fill Section.
0e1fe3b8-3312-5cc0-8eda-0d6a1c3c3b5b | note | ○ -2% to +2% of OMC
809fc79c-60d6-55f6-8463-f30b68f1a8e7 | note | Frequency - Table 10 Technical specification
ae2c871e-38e6-5a9d-935e-47657fcc78d0 | note | Record - Laboratory test Certificate
9c5d44ec-5f98-57a8-8c03-1dae615af3a5 | note | Contractor: Resp - RSA
837ea2df-2b1b-541c-852a-9e784dd0d5ce | note | Contractor: Type - HP
18405475-6e6f-5e04-bb16-c5e7eef3cfac | note | Client: Resp - Senex
84f6d9b7-4807-57b0-81a1-1e9237f9f591 | note | Client: Type - HP
e3d12bcf-6585-4765-8abf-1d6cfc674618 | signoff | HOLD POINT
7276a488-2ff7-4c62-8fc6-2170b4bdeeee | checkpoint | 06 - ERB Inspection
e8aa2823-aa93-5f4c-b718-9aadd1284c26 | note | Work By - Contractor
40bb3efe-47e8-5f59-b43c-fff0a6ecabaf | note | Standard / Spec - Technical Specification
daee5605-573a-56ba-b134-93f34936fae6 | note | Criteria - Verification of RLs/Elevations filed controls for the ERB
e9a1c6fb-5849-5c40-9c58-aa51bfa545a2 | note | Frequency - Progressive During Fill Placement
36fba996-b3bd-567c-95e1-f695286cbe52 | note | Record - Survey Data
6cdd99ec-fc09-5f96-8620-9c64726c231d | note | Contractor: Resp - RSA
cd57bbdd-c76a-5f37-946b-dc9e23935543 | note | Contractor: Type - CHK
0fa62e60-ef35-5e8e-9ff2-611892311998 | note | Client: Resp - Senex
dd5e756d-0e54-510d-bbbf-0007d9163dcd | note | Client: Type - CHK
54feccfe-844d-4a1d-9f9a-a6367959beb9 | checkpoint | 07 - Survey
afd9bccc-7f72-53c8-afaf-0570b5341278 | note | Work By - Contractor
c136e9b9-9e2c-58c6-af38-baeb0071b240 | note | Standard / Spec - Technical Specification
449d78e4-4cbe-569f-b275-8f5c9b222cd1 | note | Criteria - RSA shall submit 25%, 50%, 75%, 100% tank pad foundation fill placement completion survey to the superintendent within 48 hours of each milestone achievement. Refer to TS section 3.4
4b2f4bb1-d441-5b5a-a423-ccfb7140d9e9 | note | Frequency - 1/Lot
8431d4fe-1065-550a-8a94-c13ee7d6e2fe | note | Record - ITP, Verification Checklist/Lot Map
b7ebc151-0bcd-57fc-8634-a8f707fc517c | note | Contractor: Resp - RSA
2a974f03-5f37-5f7c-98d1-7ab6abe41f22 | note | Contractor: Type - HP
f362fbef-843d-5917-b2be-bd3b6240ed64 | note | Client: Resp - Senex
3d0fa447-e8d5-5b17-9e86-bcf09e8f6094 | note | Client: Type - HP
054e89bf-14ca-4f7f-99ed-f9bc13adb10c | signoff | HOLD POINT
67b73fd9-e001-4e62-aa35-d02bc4b54545 | checkpoint | Contractor Construction Manager:
f5e571c9-a421-43c5-abf2-9cf9b4966388 | signoff | (Signature)
6ed56dab-3ae4-4ffa-9c97-9d5e8054ac68 | checkpoint | Client Superintendent:
a28fdac5-5c70-40d5-96e4-1028efca0e3a | signoff | (Signature)
f502816f-4cee-46bb-b187-ffc16acf94d9 | checklist | Tank 1 - ITP004 - Capping Layer - Rev1 | itp | ITP004 - Capping Layer
91f397e8-fca4-4b03-b8f6-f5756705693d | section | CAPPING LAYER
e3832fca-7ed1-40bc-912e-064b441afa8f | checkpoint | 01 - Lot Identification
981f5369-8626-563e-8454-b9de14f265bf | note | Work By - Contractor
180c065f-c417-58fb-a213-7e30ad540320 | note | Standard / Spec - Technical Specification
0d7ebea9-40b1-52be-ba64-249ba493207b | note | Criteria - Location of Works identified in accordance with project technical specification
20841f40-e15f-5384-a1e0-5e173883affa | note | Frequency - 1/Lot
0d927eb6-8aba-5a39-92ab-046abb5446e1 | note | Record - ITP, Verification Checklist/Lot Map
b1a6f612-f813-5580-af0f-4f1819032418 | note | Contractor: Resp - RSA
3f817695-8363-5519-aac6-2eb02cd5c1a6 | note | Contractor: Type - CHK
c45dd4b5-7791-5e64-9107-3318b26c2f7f | note | Client: Resp - Senex
c515014d-4d8c-5d49-a46f-bc90c5642207 | note | Client: Type - CHK
ee3dcdd6-d80f-474c-aa57-dcc2d31feb05 | checkpoint | 02 - Material Approval
0ea509e5-0b64-547a-92f0-955a4641d369 | note | Work By - Contractor
2946076c-d283-57b1-a886-df914231a0f3 | note | Standard / Spec - Technical Specification
039fd8cd-f913-5974-99e5-bffff43468b6 | note | Criteria - Material shall meet the requirements under Queensland Department of Main Roads Technical Specification MRTS05 Type 2.5.
d461dbf0-a8c5-5809-a4eb-5abcce15c8f7 | note | Frequency - 3 prior to import
ad6b3adf-7481-527d-adb0-7c5271801b67 | note | Record - Laboratory test Certificate
2cf46f74-901c-5eb6-b13c-2de4b0016cb3 | note | Contractor: Resp - RSA
e0480b01-8522-5211-9478-472de94c9120 | note | Contractor: Type - CHK
f8ce1c28-0270-5e16-b957-c8e75ec65407 | note | Client: Resp - Senex
ff64ce5a-dcf9-5cac-b993-21a90d4dace4 | note | Client: Type - CHK
65324c75-0215-4257-a4fd-1da1c6a2c5b6 | checkpoint | 03 - Subgrade Testing
b574c1ef-9194-5a4b-9cf6-d1250505a804 | note | Work By - Contractor
87ecf937-96cd-5ed7-bf8e-2f2935b48e78 | note | Standard / Spec - Technical Specification
03517d1d-be8c-5108-9edc-2526bd272718 | note | Criteria - Subgrade shall be tested for material characteristics, moisture, and compaction.
aa2ea824-0f9c-5fb2-8d01-3bf88b3cbcde | note | ○ >96% SDDR
ab65e1b0-910a-5168-911d-e7c213fec141 | note | ○ -2% dry to +2% wet OMC
ea570073-2af7-5b1a-96c6-d4799bb19141 | note | Frequency - 1/2500m3
1aa55a8b-a31d-5550-a8ed-47ffe782b83b | note | Record - Laboratory test Certificate
4f91e7e8-605e-5f7d-affb-7f78f332ecef | note | Contractor: Resp - RSA
0b244d15-fa7f-54da-b052-55f5cc1202d4 | note | Contractor: Type - HP
98068eef-a0bf-5731-8257-12ea7d1a6772 | note | Client: Resp - Senex
9993aced-6b5e-5b50-9ba2-8929ce7bda75 | note | Client: Type - HP
4f0517c5-22aa-4307-9d7f-703672e6619d | signoff | HOLD POINT
ec9dddde-0686-4a77-8613-80bb09b13861 | checkpoint | 04 - Proof Rolling Subgrade acceptance
597f07c8-9a07-53f7-bef8-dde31004d1c1 | note | Work By - Contractor
765b7067-c102-551e-b715-38139bda3ba6 | note | Standard / Spec - Technical Specification
58fcfdd8-78b2-562b-a45f-d1606f5cb4b5 | note | Criteria - Subgrade shall be Proof Rolled in accordance with Queensland Department of Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client.
f289ea87-8ee5-5212-a581-f311d8e5ec19 | note | ○ Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
7450b11e-c02e-5aca-b3f7-8bbaecba380a | note | Frequency - 1/Lot
810c362c-3db9-531f-83b2-f28bf9bffff0 | note | Record - ITP, Verification Checklist/Lot Map
33be45cc-4c47-5eef-a76b-76a129a8dff6 | note | Contractor: Resp - RSA
0807bb55-1ad3-50a3-ad11-64c7a564b3ac | note | Contractor: Type - WP
56e95ac8-c811-5c04-a0dc-dd3222e8038f | note | Client: Resp - Senex
de83ca5d-6675-5d12-aad9-4880d3b1e538 | note | Client: Type - WP
bd413ef8-c2e1-4717-bf3c-409133b54870 | checkpoint | 05 - Placement of material
8721b21b-4474-559a-b409-eb51b4974e5d | note | Work By - Contractor
59113265-1fe6-5a89-98ef-8a6ba03c1a02 | note | Standard / Spec - Technical Specification
bef23a1c-3d8a-5fc0-9751-09899cbcb6a4 | note | Criteria - Access track and ring road capped with 200 mm depth gravel. Placed in continuous, approximately horizontal layers having a mi compacted thickness of 150 mm and not more than 300 mm.
3ab1fa91-b1af-51c7-8ec1-d4f6527f01c6 | note | Frequency - 1/Lot
6d25a3dd-7afd-57d3-8cdf-4d857d13f08b | note | Record - ITP, Verification Checklist/Lot Map
83c3b4c3-d604-5ba8-bb9f-f074cc942cdf | note | Contractor: Resp - RSA
b45ce0c4-5896-5a95-b90d-761c5b2b3a43 | note | Contractor: Type - CHK
3bab66de-c44b-5831-9547-ba5b7d9986be | note | Client: Resp - Senex
bf5462e4-0136-564a-a1f5-fb05014e2baa | note | Client: Type - CHK
2f527a94-a332-45e6-90c0-19f0c53a4a1c | checkpoint | 06 - Material Testing
ebd97a90-048c-5674-818e-9a1dea5798a2 | note | Work By - Contractor
d4e5ea53-a469-51f7-b111-57dc0cd4d156 | note | Standard / Spec - Technical Specification
043122ed-d7a0-5049-9b4e-c87a9ff3c484 | note | Criteria - Capping Material shall be tested for material characteristics, moisture, and compaction.
3ad2d755-a292-518d-89f7-371e826c3fb6 | note | ○ >100% SDDR
4bda9bea-90e2-50bb-90d1-b1843dcc8395 | note | ○ -2% dry to +2% wet OMC
aa4d687a-3a43-5c18-8d40-a05b836f217d | note | Frequency - 1/500m3
22488a2c-c864-5f3d-8067-06d551456619 | note | Record - Laboratory test Certificate
4cb51bb6-50ea-5637-9b77-487f5034e996 | note | Contractor: Resp - RSA
e4b2bc27-e62c-57c7-9d61-4daf7b3e3523 | note | Contractor: Type - HP
92c6b753-9db4-5437-a524-f50b8236cb71 | note | Client: Resp - Senex
4737c660-f5cc-5206-9ee6-9b1a6db9d94a | note | Client: Type - HP
52898ca6-f945-4acd-b9e6-4c16af887ea4 | signoff | HOLD POINT
4744ffc5-1056-4faa-9ec0-e9d7442559bb | checkpoint | 07 - As built Survey
27689248-20c1-578f-b67d-f5b70545ad36 | note | Work By - Contractor
8366833f-c792-5104-9bc6-0cebd60a09d6 | note | Standard / Spec - Technical Specification
04390bdc-54a9-594f-bf9f-8d3d66a2ec35 | note | Criteria - Finished levels checked for Vertical and horizontal tolerances as required. Refer to TS section 3.4
bcbf0faa-32c1-57ea-b78e-f7ce4a2aa8e3 | note | Frequency - 1/Lot
5b1ed561-41e6-5d83-984e-cbe7eda916fe | note | Record - Survey as Built
6bb86c6e-19ee-5d9f-a9f5-ef51ba8172a1 | note | Contractor: Resp - RSA
4cc116a5-3373-557d-909f-d6f69c82f85a | note | Contractor: Type - HP
6664b4f0-1e3b-5c0e-a304-ddf34c1a5403 | note | Client: Resp - Senex
2d92533b-3969-5b76-9994-32dbb982093b | note | Client: Type - HP
b13726ed-395f-42c5-b400-e62ee9830678 | signoff | HOLD POINT
a02e31a5-6078-4700-908e-203ce5c26290 | checkpoint | Contractor Construction Manager:
15f9c914-e5a9-4e33-b1b8-e193d2f2e5bb | signoff | (Signature)
719c9acd-5532-44e9-a40b-a8a9b2df480b | checkpoint | Client Superintendent:
a8dee8df-af2c-4734-9a1e-4f5e077a4e28 | signoff | (Signature)
03b69e66-e3b8-4dd8-90b4-537395c8d6ce | checklist | Tank 1 - ITP005 - Surface Water Runoff Management - Rev1 | itp | ITP005 - Surface Water Runoff Management
c08797f1-0842-4fb6-9c9d-c947f886e214 | section | CAPPING LAYER
cd052391-8c65-4a49-9504-ab01e45a12ff | checkpoint | 01 - Lot Identification
f3957abe-bfbd-58cf-828e-237c8ff2df11 | note | Work By - Contractor
dc5803ff-7966-515e-8a8d-23c5221a827f | note | Standard / Spec - Technical Specification
894cd608-3838-58a0-a9f5-d3ab9c9ceae9 | note | Criteria - Location of works identify as per IFC drawings
edde7137-533e-5250-bad6-832de023e318 | note | Frequency - 1/Lot
dc960cc5-e928-5f9b-bcdb-a0dda413924a | note | Record - ITP Verification Checklist/Lot drawing
d7fdc635-2525-5a23-8213-90c544125d7d | note | Contractor: Resp - RSA
595ea0e5-5890-5f22-94d8-024e4a3e368b | note | Contractor: Type - CHK
c33d9e38-9b17-519d-a534-bd2617f2875d | note | Client: Resp - Senex
6f75c107-be93-50d3-9ca7-105fab3a00ac | note | Client: Type - CHK
1697cd91-5c0e-43f3-9a27-5bd7fd1e6b1f | checkpoint | 02 - Subgrade Preparation
80f7d0b9-76df-59af-aea1-a9c5608ecf8b | note | Work By - Contractor
d590cb46-b159-5375-be77-541c4608b252 | note | Standard / Spec - Technical Specification
4253d60a-bd3a-516d-b3f4-23859491363d | note | Criteria - Scarify subsoil to a minimum depth of 150 mm
5cb5cb76-ee27-59e6-b876-782eba112ab4 | note | Frequency - 1/Lot
f84f8a59-cdc6-5476-b2dc-12cf9643e815 | note | Record - ITP Verification Checklist/Lot drawing
dc599be3-a335-5b0e-b1a3-9330c587bdfe | note | Contractor: Resp - RSA
aaeb22dc-aea4-57cb-a96b-314c248c508a | note | Contractor: Type - CHK
c66be897-e7c2-5a06-ab77-824610ab9ac4 | note | Client: Resp - Senex
f74fb016-8d97-5c13-a333-4d5a87e55f02 | note | Client: Type - CHK
7ecea102-0b52-4bc5-a160-8e2e4abf59b9 | checkpoint | 03 - Gypsum Application
3ae0b1e3-a9c7-5209-9048-98292b378b26 | note | Work By - Contractor
576b1f0a-9d5e-52bc-80e6-760ef7924f55 | note | Standard / Spec - Technical Specification
f23f7ff2-7206-5de5-99d1-b7e9b6aa2692 | note | Criteria - Apply gypsum to batters and table drains at rate of 5t/ha, and apply water at 10mm/m2 to create adequate topsoil bond with the subgrade
efe64cb0-3331-5ff2-9f89-0446115207e8 | note | Frequency - 1/Lot
3e5006e1-b3dd-5956-8ec6-683cf791805f | note | Record - ITP Verification Checklist/Lot drawing
e9ae0537-2c2c-5517-9cc8-2bac5586cb31 | note | Contractor: Resp - RSA
ae94650e-f06e-575e-be8c-bbad56004d9e | note | Contractor: Type - CHK
47645b0f-4b1f-583b-a82f-f5e4fd2946df | note | Client: Resp - Senex
e52a4382-b598-539c-91e9-34ee3c1340b1 | note | Client: Type - CHK
873d8b0f-3816-49e9-9ae3-7aec00b048b0 | checkpoint | 04 - Respreading of Topsoil
abf4e6bf-81bf-5d95-bd00-cc30742af5c2 | note | Work By - Contractor
fab5f21f-868e-51b7-a5aa-699660f5fd79 | note | Standard / Spec - Technical Specification
0d46c26a-030e-5977-9488-948b85038df6 | note | Criteria - Topsoil is to be placed 300mm thick and trim with grader and scarify to a depth of 100mm.
fb4de729-70e2-5f03-9e11-60b2324893b9 | note | Frequency - 1/Lot
0689250e-451e-58b1-a051-bc3244cb29f2 | note | Record - ITP, Verification Checklist/Lot drawing
fe07a956-94a7-598e-a557-cdfc9e41677f | note | Contractor: Resp - RSA
582826e9-77f5-55e7-8dc5-b9dda2ec838e | note | Contractor: Type - CHK
0eadc055-c3db-5e86-91f6-ae0e630f5c2a | note | Client: Resp - Senex
591ff971-1ee6-5067-89bb-afb91780e867 | note | Client: Type - CHK
ef259a90-c0fe-40cf-90c6-5fe6fc2dbbcb | checkpoint | 05 - Hydro mulch and Grass Seeding
0a58a827-a926-51a6-89fd-51410449d129 | note | Work By - Contractor
64030eb3-2b27-538c-9555-8a4fc651f164 | note | Standard / Spec - Technical Specification
bc4186eb-21b3-5467-b97f-0c76634c2dc6 | note | Criteria - Topsoil shall be hydro-mulched using the client-specified seed mix, approved mulch, and fertilizer applied at a rate of 150 kg per hectare.
eeb802ae-b763-50a5-ab0e-c53dee786a78 | note | Frequency - 1/Lot
e4610aab-d732-59bc-92ed-0dfecd1ca23a | note | Record - ITP, Verification Checklist/Lot drawing
5eb422b8-a0e3-5c5b-937d-6054bb96bc65 | note | Contractor: Resp - RSA
6cdbb1ac-b155-510f-b7d0-edb319d3aa7e | note | Contractor: Type - HP
7139291d-c3b4-522f-8b7a-8ee43a2b08a4 | note | Client: Resp - Senex
85ceabcf-cc14-518e-a028-efdeb7216a11 | note | Client: Type - HP
1db2fb27-c707-4103-9e48-35c7dbae6cc6 | signoff | HOLD POINT
f7388fa9-cd3e-430c-9b0a-67052ea61927 | checkpoint | 06 - Watering of Topsoil
488512b8-23f7-5a11-9fab-0a5bf00124db | note | Work By - Contractor
51828d5f-06ae-57b3-a149-4898bfec2e7c | note | Standard / Spec - Technical Specification
0d56c15f-e23e-5efa-97d4-7de6f1d1bba8 | note | Criteria - Watering 10mm/m2 every day for first 8 days, then every second day to get to a total of 14 irrigation days.
618ecf30-ad91-585e-ab88-8504cd29ccc3 | note | Frequency - 1/Lot
6dfd03b2-4645-57c6-9629-8000d2929a83 | note | Record - ITP, Verification Checklist/Lot drawing
33d303cf-682f-571b-946a-9b88bdaee03c | note | Contractor: Resp - RSA
804498a4-d672-5586-939d-14f593d47c9e | note | Contractor: Type - WP
7cd9ab17-9f08-5849-8728-43a10a709658 | note | Client: Resp - Senex
f9013f00-0ba1-5f0d-b4c1-27149e3328d2 | note | Client: Type - WP
9c95be80-607b-4a97-b194-5d61e4cd9c9e | checkpoint | 07 - Topsoil Testing
54740992-8ea3-5e69-86ee-f37275a6764e | note | Work By - Contractor
0cf979c3-fcca-57ba-8f95-0fba0476a0f2 | note | Standard / Spec - Technical Specification
10127a18-300d-5860-9cd4-e157e8a2bc2a | note | Criteria - The PH of the topsoil shall be tested to confirm applicability of gypsum
bebbb61f-6515-58e8-9422-9954d975f291 | note | Frequency - 1/Lot
35bec17d-b428-50ec-91c8-a547908569a0 | note | Record - Test Certificate
a014e365-b790-5e2e-b625-a13bdd688224 | note | Contractor: Resp - RSA
18f2ecf3-01b8-51b1-af17-a4d92cec9b2b | note | Contractor: Type - WP
c8d92273-c104-5b16-b4b7-f26026bfaba7 | note | Client: Resp - Senex
5dc769ce-9a77-5431-b825-35110c2ca2c7 | note | Client: Type - WP
8499c702-c719-4a77-8376-c69671b7379a | checkpoint | 08 - Survey
8ab3363e-d464-5898-9846-c09e733aa8a3 | note | Work By - Contractor
328003df-8925-56b8-9cac-6e0ed7126ee4 | note | Standard / Spec - Technical Specification
e31e1bb8-d8bf-5061-bafb-73a92d197740 | note | Criteria - As-constructed survey has been completed to record the surface levels on completion. Refer to TS section 3.4
33748978-a931-5b47-a336-18e595719259 | note | ○ The Contractor shall submit results of each survey to the superintendent within 48hours of undertaking the Survey.
a369033e-eedf-598b-9517-513b49a4c5ca | note | Frequency - 1/Lot
74feb68c-0301-51aa-bb41-e5bfd3fb76a5 | note | Record - ITP, Verification Checklist/Lot drawing
85f3d83c-9a45-536e-9c2d-32480a0733db | note | Contractor: Resp - RSA
84904434-656c-53ca-883e-6da8d010de2d | note | Contractor: Type - HP
c3aae88e-f7d3-54ac-83fe-7dadb62eb715 | note | Client: Resp - Senex
78bc45d5-dfca-5a44-8527-2c5f922b90ee | note | Client: Type - HP
b05a70b2-af59-4943-badb-cfdb57e0e2fc | signoff | HOLD POINT
456b2b50-909e-49e4-8612-9242481b1bdf | checkpoint | Contractor Construction Manager:
9c458f5a-1cd5-4c55-a713-41778ef37716 | signoff | (Signature)
5d3d2f08-7602-486c-ba7b-a2411d3aa511 | checkpoint | Client Superintendent:
f062b04f-2a19-4049-8440-420f9e854398 | signoff | (Signature)
9ae2f3f6-b4c5-4ed7-9642-a371566251e8 | checklist | Tank 1 - ITP006 - Erosion and Sediment Control - Rev1 | itp | ITP006 - Erosion and Sediment Control
78e6cc49-2475-463e-b3e3-7069434c364c | section | LOT IDENTIFICATION
2de5dbfc-0f97-4500-8d17-31d12121c7e2 | checkpoint | 01 - Lot Identification
2559ef4b-3618-5ce4-8ab8-643b811f1490 | note | Work By - Contractor
9565e6db-bbd1-58a4-ab2a-4734cc86c037 | note | Standard / Spec - Technical Specification/IFC Drawings
0b0b1f20-d35b-53dc-956d-f0cb1d629528 | note | Criteria - Location of works identified as per IFC drawings
d6ab3eb1-04dd-5d62-9e0d-e5e2265dab14 | note | Frequency - 1/Lot
2cac8eb6-5a9f-57f9-9bff-af155cd53d74 | note | Record - ITP Verification Checklist/Lot drawing
0fd45868-229f-5f40-a1e1-c538bf88959b | note | Contractor: Resp - RSA
a823ed04-917c-5362-8dc3-480a702bc972 | note | Contractor: Type - CHK
180a94e7-f88a-584e-ae15-b477ddbff17c | note | Client: Resp - Senex
7ae63f6a-e9e1-5905-81e7-be1b1459ae00 | note | Client: Type - CHK
b8b565dc-46c1-4291-aef5-f4dcbef2fd1f | section | TEMPORARY SEDIMENT AND EROSION CONTROL
c00d77b5-8a83-4776-a400-c88cba5a990a | checkpoint | 02 - Clear identification and demarcation of ‘no go zones’ (where required)
25115771-6e8b-53d2-888b-066042ee75f7 | note | Work By - Contractor
55922af5-7019-584f-bb54-372ab13388fb | note | Standard / Spec - Technical Specification/IFC Drawings
6cb42b3d-a65d-5dde-bf2f-482ab472ddde | note | Criteria - Remove vegetation and disturb soil only in those areas approved for construction work to occur
88de61a2-733f-5bcb-871f-7b28a2a027a4 | note | Frequency - 1/Lot
94bed0d6-9351-578b-a430-16bbb873777b | note | Record - ITP Verification Checklist
09419628-2714-52d0-83df-742eac0548ff | note | Contractor: Resp - RSA
6c98782e-7e23-56aa-a6e0-5e05f0cbb564 | note | Contractor: Type - CHK
05372f0d-d8fb-5015-903c-a4e0dfb82480 | note | Client: Resp - Senex
1963bcf1-2f22-52ff-b9e3-9bbe24b15bf1 | note | Client: Type - CHK
12d88852-d81d-4745-b943-948ae0641de4 | checkpoint | 03 - Installation of temporary sediment and erosion control devices
8a19169e-1aea-5efb-98b1-c64dbc4884fe | note | Work By - Contractor
f38a1a2a-6918-5bd1-9a2e-cdfa16cceadc | note | Standard / Spec - Technical Specification/IFC Drawings
90de77e4-77d3-59ed-a345-b631ef551180 | note | Criteria - Construction of diversion bunds
b86aeadc-3e37-5f07-979a-b5466cc328ec | note | ○ Excavation of sediment catch sumps and Rumble pad
060833ee-4d6a-52ed-b0c6-c16569587cd2 | note | ○ Temporary approved construction tracks
40515d15-4f12-5dc6-9c57-f070df7f646c | note | ○ Installation of Silt Fence
ec888ede-7a9d-5402-b6bc-41f159ae046b | note | Frequency - 1/Lot
e0f40259-35ad-57a4-923a-35b055667211 | note | Record - ITP Verification Checklist
f8db8da3-c798-5b3d-8ed1-688e0e7c3de6 | note | Contractor: Resp - RSA
00cfb470-0ab2-54b2-a982-869fa83d3af2 | note | Contractor: Type - HP
996e9f06-d8ac-5bbc-a5ff-46e35c0d4105 | note | Client: Resp - Senex
5b6c4833-525d-5a9c-af54-6bc7e6e61906 | note | Client: Type - HP
b06ae4a6-e5ba-4db7-a3d6-78a20224a014 | signoff | HOLD POINT
57483478-e9de-439d-922a-0acf7a01b209 | section | PERMANENT SEDIMENT AND EROSION CONTROL – RIP RAP (ROCK PROTECTION)
7706ff3f-7390-4799-aee9-02d482a230d2 | checkpoint | 04 - Sediment and erosion control device ongoing inspections
cdbde973-60aa-57c8-a721-d68792b75509 | note | Work By - Contractor
635a00e8-6140-5d2b-be02-c2beecafb78c | note | Standard / Spec - Technical Specification/IFC Drawings
3f5fe1b2-e973-5dd9-96bb-44402a5c2a49 | note | Criteria - Inspection of sediment and erosion control devices completed to be completed at the below frequencies
e2d0a68c-a45e-5479-a00c-0222a1f3b98c | note | ○ Rain: >50mm in on day or >100mm over 4 days Prior to shift breaks
7f4bc024-f7d5-5d7b-aff0-20f73f03a020 | note | Frequency - Ongoing
9e0cf20d-e2a9-5f66-9f43-d66388933036 | note | Record - Environmental Routine Checklist
c63cefb6-4221-5ec8-b7f9-9b85f56bd9b7 | note | Contractor: Resp - RSA
25ddbdd8-77d9-5ec5-ad38-9c0cf6e17518 | note | Contractor: Type - WP
b869b13f-526f-57fb-b2fa-c7056a01016c | note | Client: Resp - Senex
f1ea30e7-971d-5027-b754-8848c2e1d8dd | note | Client: Type - WP
73c2d2df-1b91-4fd6-8031-b5166ff20135 | checkpoint | 05 - Underlying Lot conformance - Subgrade
1debdc94-6053-501e-acf1-0ee2595c7360 | note | Work By - Contractor
702d7b8d-bae3-5a16-9d8e-952cba405687 | note | Standard / Spec - Technical Specification/IFC Drawings
2dfc100b-702a-51af-b6ab-3015f9b6b9da | note | Criteria - The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile.
c970e47e-319f-52db-aa9d-eb4b6a423c99 | note | Frequency - 1/Lot
58456c18-77e1-5e1a-9bd6-871264ab1a41 | note | Record - ITP Verification Checklist
7e71deb9-e4e9-5b93-8762-364b0481e873 | note | Contractor: Resp - RSA
ca816e38-2852-5329-8f18-4bab48edce38 | note | Contractor: Type - HP
8c9de8f8-6206-505b-83c1-64bff6fe8985 | note | Client: Resp - Senex
ee9f75d8-f133-5fa0-bdb3-dd673dbd628d | note | Client: Type - HP
ebf335d8-4ac5-4f3f-a7a1-e609392be9bb | signoff | HOLD POINT
e73b9b13-4b38-4e24-aef5-ef2078587e94 | checkpoint | 06 - Conformance Separation Geotextile Material
47a20d7c-1897-57de-a092-29fcac87e121 | note | Work By - Contractor
5e4350ab-6ae8-53e4-995b-6bbf83545882 | note | Standard / Spec - Technical Specification/IFC Drawings
561ed810-6fb6-5df9-9921-0812344088a0 | note | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data Certificates.
c7b5f473-9a0f-5482-b44b-52fc1f880931 | note | Frequency - 1/Lot
c67e9a8e-7c53-531b-a619-1affbc44999e | note | Record - ITP Verification Checklist
5a161b05-8f5b-5447-baba-5e73c7b573eb | note | Contractor: Resp - RSA
79d713dc-8147-5b09-b087-1dac8104fbff | note | Contractor: Type - HP
08a7ba57-700f-53db-b4c4-84345c5b1deb | note | Client: Resp - Senex
049ab1b2-8db3-5a00-b0b5-ac0924576042 | note | Client: Type - HP
9cde3f76-d1af-4b6c-abb7-e92c4a5a9d35 | signoff | HOLD POINT
ee9308a2-109f-4d16-9d59-9a89af93bff2 | checkpoint | 07 - Conformance Rip Rap
f3362e94-fc4b-5608-a06d-44802edd27a6 | note | Work By - Contractor
c453109d-c59a-5d6c-a3c7-f7499fc999e5 | note | Standard / Spec - Technical Specification/IFC Drawings
ce2785a8-4996-5e99-8510-d70db74e7089 | note | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates.
c9cebe35-1134-5786-8f06-1b0bc0f42838 | note | Frequency - 1/Lot
52a7c972-3f8a-5f58-80d2-1f8d26831eba | note | Record - ITP Verification Checklist
7aaf9b54-6843-5eb4-b9b3-2df4c4f624ea | note | Contractor: Resp - RSA
3d9335e3-5434-5394-8f14-6f5063905dbd | note | Contractor: Type - HP
bcb60cc4-ff01-5396-bdb6-88bef60dca38 | note | Client: Resp - Senex
551af994-53bf-5736-a306-32c6fccd2814 | note | Client: Type - HP
2ae902a8-169d-4937-ba9e-930bccc549a2 | signoff | HOLD POINT
7fbb9e01-58e5-40cc-86c7-9e8128c7db68 | checkpoint | 08 - Separation geotextile placement
37868b8c-ebf5-57de-8e2d-367eb3e7b876 | note | Work By - Contractor
a0db9390-409e-50bf-bed9-4018d56dc0f5 | note | Standard / Spec - Technical Specification/IFC Drawings
9c5197cc-4f4f-5d44-bfa1-4bc52dbc175a | note | Criteria - Installation method complies with the requirements of the technical specification and the IFC drawings. Laps to geotextiles shall be a minimum 0.6m. The Superintendent shall inspect subgrade and the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers.
17d60319-4fe5-5c2b-bfe1-b4fccfebc305 | note | Frequency - 1/Lot
ab67f7f5-5630-569b-af37-56fa113a293f | note | Record - ITP Verification Checklist
03cbebc6-8a4a-5336-b072-8ee3bbc6e36e | note | Contractor: Resp - RSA
7ad67494-8425-5268-85b0-acd7f47af0e1 | note | Contractor: Type - HP
911a9d9e-289a-5dba-8574-1024636650c9 | note | Client: Resp - Senex
aa2be9b3-2f4a-5f5b-88cd-52d3f5f79da1 | note | Client: Type - HP
835e40f4-4af7-4087-b808-c329daad3e4b | signoff | HOLD POINT
671df8a9-8230-401d-9efa-3662926d3320 | checkpoint | 09 - Rip Rap Placement
a624eb23-b059-5def-b905-ab5aab9fc6ea | note | Work By - Contractor
59af2014-70bc-5a6b-bc35-c08fc97c73f6 | note | Standard / Spec - Technical Specification/IFC Drawings
c0809294-f24a-5cdc-a305-d386f619ae24 | note | Criteria - The contractor shall provide a Work Method Statement for the placement of Rip Rap.
e405b4b3-7eb8-594d-bab2-d45ce9b885c1 | note | ○ Rip rap shall be place in a manner which does not damage the underlying geotextile
52c52cb8-3377-560e-9bf9-e996a03e5360 | note | ○ Rock finished smoothed to the final lines and levels.
ed593970-556e-5aaf-842e-d1f6cb0bbdc5 | note | Frequency - 1/Lot
ed69aff4-e895-564a-a49a-fe5743c2b545 | note | Record - ITP Verification Checklist
31620dd2-b7ef-5cbe-9b0e-d60878e389a4 | note | Contractor: Resp - RSA
c2a6763e-57b4-5b93-802d-b8280058cb36 | note | Contractor: Type - CHK
07519602-d323-56b8-b9e1-517f531dc0c8 | note | Client: Resp - Senex
c0683d9e-e6ca-5905-bbd4-b22869f03d83 | note | Client: Type - HP
74832bbb-be04-4f0d-86ef-d3200a8032a4 | signoff | HOLD POINT
349d0e7d-3c48-4102-9f0b-8cc69e339542 | checkpoint | 10 - Acceptance of works (Rip rap)
2fc20895-b28a-5b13-a5fb-6284f46d7836 | note | Work By - Contractor
4da27bc7-140a-5a9f-a06d-73684dc0816e | note | Standard / Spec - Technical Specification/IFC Drawings
5880838d-190f-5ed6-a2b7-674551e97157 | note | Criteria - The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works.
45a4423b-65d6-59ba-9f1e-5d79b0e86ea9 | note | Frequency - 1/Lot
35704f7a-452c-5eec-9d05-a62a9f012ce6 | note | Record - ITP Verification Checklist / MDR
3d573e92-ca16-5d1f-85d5-f5b93c8af3bb | note | Contractor: Resp - RSA
151f69f7-bd74-54b3-b0fe-625c9fcb1bd0 | note | Contractor: Type - CHK
137dc1c1-f8e0-5994-aa53-413db8c45cb9 | note | Client: Resp - Senex
86a6212b-b280-55d9-b4ae-6d85e32a36e0 | note | Client: Type - HP
fdcf1f6f-f1e7-44e1-ad7a-434dce69f786 | signoff | HOLD POINT
0537ea92-69d4-4dc8-bb67-17a9d1dfd60f | section | PERMANENT SEDIMENT AND EROSION CONTROL – CMP AND HEADWALL
d071016e-1d99-46b2-8f2f-6ccaa46e8715 | checkpoint | 11 - CMP Installation Contractor
9d6056fe-4a70-5614-8f81-8db5bf5870f0 | note | Work By - Contractor
a87e9684-6074-5d42-a897-c5427c635dcf | note | Standard / Spec - Technical Specification/IFC Drawings
523f8baa-19e5-5d27-a68a-dffe295e1a1b | note | Criteria - Contractor shall provide a culvert installation methodology to the superintendent for approval Excavation to design invert levels allowing for 175 mm bedding sand beneath culverts up to haunch.
03ce0ce6-01eb-59fe-b8a8-2fa058a33e23 | note | ○ Select Fill around culverts 300 mm min thickness above
ff5980e7-89e1-52f7-a89e-0cb3440eb781 | note | ○ Foundation to be tested for bearing capacity of 100kPa
db49dc7d-4a28-5e25-92c0-9c14d897e2fa | note | Frequency - 1/Lot
6603f75a-07c6-5721-8d05-20bb93c04593 | note | Record - ITP Verification Checklist
56145a3a-2f72-54c4-9047-e61f7a53335d | note | Contractor: Resp - RSA
b148f9fd-69c4-53bd-834f-676799b34866 | note | Contractor: Type - CHK
7a575003-9ed9-50f2-87ff-2820271a37fd | note | Client: Resp - Senex
c6f21b50-874f-5349-b2d7-0cb146a683fc | note | Client: Type - CHK
c933f21a-ce1c-4031-8c46-ebf89916565e | checkpoint | 12 - Backfilling
55ff7f59-9a45-5d34-bcc4-1923fd72dc04 | note | Work By - Contractor
22ffee6e-2360-5b0e-8532-98910f2ee65e | note | Standard / Spec - Technical Specification/IFC Drawings
fbdf97a2-d676-5383-b732-1b332a5002ff | note | Criteria - Trench backfilled and tested in line with requirements for Fill 96% +/ -2% moisture
771b339b-7cf9-5a2b-bede-d97e9b202035 | note | Frequency - Min 2 tests
ff834d39-a653-519a-870a-e9269f2910ec | note | Record - ITP Verification Checklist
fa09a570-3fe2-54ab-bc32-3d288c49bef8 | note | Contractor: Resp - RSA
38c17b7a-0162-5b56-8d61-fb13027697bb | note | Contractor: Type - CHK
1e547cdb-52a1-5422-9e03-28331beb96a4 | note | Client: Resp - Senex
474e1599-0fdf-537e-8ee3-b4c03d93089c | note | Client: Type - CHK
634362d3-7334-49ad-bea7-5cb81fe10810 | checkpoint | 13 - Headwall Installation
5bb1e348-a831-5246-9138-4d9996b1c6d0 | note | Work By - Contractor
ca74da5f-5625-52a3-ba7d-cf2e7521cc97 | note | Standard / Spec - Technical Specification/IFC Drawings
56368b41-9733-576f-a212-b56e4824f90b | note | Criteria - 2 x 600DN Headwalls installed on 100 -250mm sand bedding (or equivalent) to required invert levels
da5fd8cd-be08-5ea4-9409-4e640e9f2399 | note | ○ Headwall installed flush with CMP pipe and grouted neat.
73b3ccb4-ae79-5f59-94fc-d149c05ea9f4 | note | Frequency - 1/Lot
3898a300-111d-5c94-9e1a-87760fd4f52b | note | Record - ITP Verification Checklist
bfbdf53f-94fa-5d4a-8774-259979eccb85 | note | Contractor: Resp - RSA
c2b48aef-5ea5-5862-9e51-8b4acec337df | note | Contractor: Type - CHK
0022685f-af75-590e-8c7b-b572d47366c6 | note | Client: Resp - Senex
459e14ff-17e5-5203-b249-321b10d404ab | note | Client: Type - CHK
e701792f-871e-4b9d-945a-72469c673885 | checkpoint | 14 - Acceptance of works
d46cdc90-cbca-5e6d-92f7-ffcfabf16ede | note | Work By - Contractor
3bb1372d-a243-5f9d-bfb9-38e3c5ce1113 | note | Standard / Spec - Technical Specification/IFC Drawings
e01d67a4-786d-5e69-9adf-6fd8b766f825 | note | Criteria - Conformance certificates supplied by manufacturer
a4b650ec-cb8f-593b-97f9-3819dd841e01 | note | ○ All required test reports provided to client
a78dd107-14d5-57a9-9cc8-9742a57984ea | note | Frequency - 1/Lot
a1c5810b-379a-58e5-b4df-c810a5b912f4 | note | Record - As-constructed survey data obtained
c1b20794-6b59-5fdf-a88c-29848d912293 | note | Contractor: Resp - RSA
45c255eb-4d5b-5063-98c7-c56b3468d7c8 | note | Contractor: Type - CHK
6fc69db1-d560-5ee2-b21e-1facd40e38a0 | note | Client: Resp - Senex
dcb97bd6-62ab-5ad0-9b1e-29a2ec013807 | note | Client: Type - HP
c0d07be9-abf4-4dd7-93ed-d195a5abb5cb | signoff | HOLD POINT
c1b2cb27-8afc-426d-9731-66b19d23eac4 | checkpoint | Contractor Construction Manager:
3c0cd72b-5b2e-4afc-a5fd-d5c99ce509ef | signoff | (Signature)
a8fd4a28-0e6b-4d72-b18c-e0c87fda3988 | checkpoint | Client Superintendent:
4d4309ef-7eab-47f1-a1d8-ca7bafe7fccd | signoff | (Signature)
9f50b0bd-932b-4eac-816f-9a0d7e4aab8a | checklist | Tank 1 - ITP007 - Leak Detection System - Rev0 | itp | ITP007 - Leak Detection System
46777835-b6d6-42a8-a2cc-e371d4906c7c | section | LEAK DETECTION SYSTEM
bed7873d-8eaf-4ca3-8d3c-1487abd34171 | checkpoint | 01 - Lot Identification
415c708a-0898-5f58-b26a-28212d94bba2 | note | Work By - Contractor
e18162a6-2ea0-5aa7-b567-d2fcfe2918eb | note | Standard / Spec - Technical Specification/IFC Drawings
63f8489c-de7b-5538-8f6d-98c08cf81da2 | note | Criteria - Location of works identified as per IFC drawings
3cf107b0-74fa-5a93-8965-a3ed3dde8abd | note | Frequency - 1/Lot
06d39fee-e06a-5b9e-9e5d-019479955ec5 | note | Record - ITP, Verification Checklist/Lot drawing
d36bafb9-07b8-50d5-8ce3-0b34972eee42 | note | Contractor: Resp - RSA
43e1daca-5177-5c6d-9831-e8d1a969eea2 | note | Contractor: Type - CHK
b4d6c011-f213-5914-99a1-488f6434e8dc | note | Client: Resp - Senex
d04409f8-68e1-5851-ba5d-3d85fd8e0982 | note | Client: Type - CHK
cd58f0f7-cd3d-45e8-86c5-38260ba5ec77 | checkpoint | 02 - Survey control and Setout
1a4de101-5c84-51b8-b2f6-c6f2e9a007f5 | note | Work By - Contractor
f0077bca-abf0-5a64-9e66-a4e6da68cc2f | note | Standard / Spec - Technical Specification/IFC Drawings
a33e4687-8350-51a9-bc06-a0ee00d0b114 | note | Criteria - Confirm centres of both sump and tank locations
ae400d84-2b1b-5670-8761-224b28775d51 | note | Frequency - 1/Lot
1d1edd12-c6dd-5724-a2ba-2ab11ae05fe1 | note | Record - ITP, Verification Checklist
cb9752a3-b27b-5a7c-bce7-9d8a9aa98fa8 | note | Contractor: Resp - RSA
b7c32938-9545-5d47-9588-c7c93e124599 | note | Contractor: Type - HP
b00f098a-f31a-5495-b5fb-e8e4aade0050 | note | Client: Resp - Senex
092aba77-1c49-58b5-8f17-78451a890ddc | note | Client: Type - HP
48e5e9ac-67f6-4789-9639-f78710e71f8b | signoff | HOLD POINT
1c77f021-75d1-4715-884f-b5ee5fc1d690 | checkpoint | 03 - Excavation of sump
6a070a51-281f-583a-a2c1-5e152924bd6e | note | Work By - Contractor
9034d764-0217-5393-ba37-dd238c63205b | note | Standard / Spec - Technical Specification/IFC Drawings
7363c2a3-1127-5f7f-92ee-12f62e2c86bd | note | Criteria - Located at 3m outside from the hinge point of the tank pad. To be trenched to a depth of 3.17 m (to be confirmed on site)
c31709b1-68a9-5c7d-a56a-9821f73f8454 | note | ○ Sump excavated to correct dimensions in line with Concept Tanks 0.8m diameter excavation to design depth. Sump pit depth to be determined onsite ensuring sufficient fall from tank centre to sump
8ef66e20-f414-59ad-b4b9-6b213fcaf564 | note | Frequency - 1/Lot
cf0e37fc-6f90-551a-903c-12a725c2c1e1 | note | Record - ITP, Verification Checklist
7329000a-77fd-5c38-9afb-972c22d6cf26 | note | Contractor: Resp - RSA
0abe3015-7651-5716-92c4-2d69f3beccbb | note | Contractor: Type - CHK
e0240f6d-3ca1-5ba7-86dd-a4217916d8bb | note | Client: Resp - Senex
31b7f959-5d2e-5ace-8c48-0f45c6a37eda | note | Client: Type - WP
98465af6-ea69-447c-aa37-740cb22699d9 | checkpoint | 04 - Installation of HDPE sump base and chamber at correct height and level
88b00b50-626f-5086-b03d-c2cfedcc8e1f | note | Work By - Contractor
8ab346ba-25ef-57e3-ac23-513a0848de65 | note | Standard / Spec - Technical Specification/IFC Drawings
ee06bf74-940a-5b0e-9420-0f60dea8cd0c | note | Criteria - Poly sump base to be installed at 200mm below leak detection pipe.
b885d000-0397-5b2a-a787-2353ee0996a7 | note | ○ Sump chamber installed plumb to correct height minimum 150mm above top of tank
a7fc42b5-d570-588e-9b32-6c5141fb71d3 | note | Frequency - 1/Lot
e7b290fe-c71f-5075-b53c-553a388bc17c | note | Record - ITP, Verification Checklist
23702b7b-a146-51a5-bff8-33ef1ab10ef2 | note | Contractor: Resp - RSA
05d76080-589b-5bdd-ac35-0b19e2ab23f9 | note | Contractor: Type - CHK
4364e10c-f0f7-522f-84b6-8164fcc8cdbf | note | Client: Resp - Senex
f4eb5106-1977-57f4-96de-ddb63ba015e3 | note | Client: Type - WP
0f541be0-f52c-4e43-b82d-22c08934e6fc | checkpoint | 05 - Backfill - Sump
ad7e3bab-0a85-5b6d-98ad-41741d1b09af | note | Work By - Contractor
e11e1f95-99b9-55b0-979b-1191496c30da | note | Standard / Spec - Technical Specification/IFC Drawings
b24ebdb6-c1bd-5532-9454-8691736a44f5 | note | Criteria - Backfill in accordance with CT requirements. Compaction testing in line with Earthworks specification
264687fc-d3c2-5fc4-97df-011fcb52a3f4 | note | Frequency - 1/Lot
74b5844f-ad17-5526-8e7a-0bab34129e3c | note | Record - ITP, Verification Checklist / Test
7875630c-6206-55af-87d9-795026dd894d | note | Contractor: Resp - RSA
a330123f-4d28-5c0b-ad4d-92e398282c23 | note | Contractor: Type - CHK
d9eb6d1f-82df-5f46-921f-f7d33b061d5a | note | Client: Resp - Senex
3040d557-5cf0-57fc-a8de-4f9767c2282f | note | Client: Type - HP
ef0d5af1-7e1e-4ad0-82c4-73eb5c66b7a7 | signoff | HOLD POINT
a37b5efe-f7f3-497f-a423-7bc408a82630 | checkpoint | 06 - Leakage pipe trench excavation
500049c5-f458-5904-bd35-139ec0344dbc | note | Work By - Contractor
c0d4b44d-23fb-5225-86f4-7165f2d90f08 | note | Standard / Spec - Technical Specification/IFC Drawings
6edd65ba-43f3-5e2b-8c94-a0a6267391d6 | note | Criteria - Trench excavated to correct lines and levels in line with CES drawings.
ec0a7139-9fa3-5c14-af7e-a1b2dc14f2bd | note | ○ 1:100 fall to sump
549fd0c9-ed23-5be8-96d6-4b65ad4c55e0 | note | ○ Sufficient excavation width to facilitate installation.
80ddd514-e6cd-5abb-a426-b5d834539421 | note | Frequency - 1/Lot
3c98cd91-4901-50ab-8f96-34711222f49a | note | Record - ITP, Verification Checklist
c5bc126f-1f65-5ea6-846b-7baaabc08844 | note | Contractor: Resp - RSA
f5504861-b098-54e5-85e7-5e62ed6d7555 | note | Contractor: Type - CHK
6e878c10-abc2-5105-ab5d-b05595617ab1 | note | Client: Resp - Senex
14fd081c-4044-51c9-b024-b84d5716a75e | note | Client: Type - WP
bfa76815-c28e-4109-bff2-5044b639e4df | checkpoint | 07 - Installation of 50mm HDPE leakage pipe
1ea4b20a-082e-5f07-a9f8-f54f3ab58095 | note | Work By - Contractor
bd304419-26f5-5ce9-bb0f-b8fc2c2cd7d1 | note | Standard / Spec - Technical Specification/IFC Drawings
6e4b8f93-0c2f-5ed9-8fed-3bc275b2d23a | note | Criteria - 50mm HDPE pipe and bends installed in accordance with CT and manufacturer requirements.
e172205e-236c-5fe6-b849-6cab26c0266c | note | ○ Minimum 150mm cover at centre of tank Pipe installed on 50mm sand bedding (optional) as per CT recommendations
183b1f9d-3f9d-5f6d-a407-48aaffcff91a | note | ○ HDPE pipe riser installed 300mm above FSL at centre of tank, temporary seal to prevent sediment ingress.
c798d651-b59c-5523-8329-4541c0e40ec2 | note | ○ Pipe to be left exposed at centre of sump pit
39e54f17-6762-5c85-8545-279266f9fceb | note | Frequency - 1/Lot
5b0903e8-2fbc-5c99-94ca-72ee92830088 | note | Record - ITP, Verification Checklist
b2dae358-f788-5ab3-93ac-63193f69e9f0 | note | Contractor: Resp - RSA
039fbe4b-8f5a-505f-8b4d-247b6e45cc2d | note | Contractor: Type - CHK
7afb0a39-5df7-5249-9d9a-b0d86e395636 | note | Client: Resp - Senex
9920e105-bfe4-5625-9985-417518d60677 | note | Client: Type - WP
268f4608-7bb7-4c59-b248-a949fded6ebe | checkpoint | 08 - Surface Water Runoff
dca545a4-8588-5aae-ab6f-eaaace1fbce9 | note | Work By - Contractor
5dd6ad54-6931-5193-9fe2-855b38d6a14f | note | Standard / Spec - Technical Specification/IFC Drawings
4a71c947-e71a-51c5-b5eb-149faf5628cb | note | Criteria - DN110 HDPE pipe for construction surface water runoff to be installed 1:100 fall to swale drain
98c6db6b-5f12-5e66-bb6a-7d051607aee8 | note | Frequency - 1/Lot
722ef405-5caf-5643-8091-9f72b8f55fdd | note | Record - ITP, Verification Checklist
60aec8bb-cd04-5b3d-abe7-d6109f6d9e8d | note | Contractor: Resp - RSA
7dcf0ba9-dbc6-5999-a2d4-871af110093c | note | Contractor: Type - CHK
a7c7fd24-c613-5701-8d6a-2bb0a6905be7 | note | Client: Resp - Senex
bd9ab4e3-5c17-5b89-baec-46b7efd4975a | note | Client: Type - WP
d41db160-9c30-4919-b1bb-70cc412e5e3b | checkpoint | 09 - Backfill - Trench
c3ee29f7-afad-5e51-af7c-3b7cb5d8fb57 | note | Work By - Contractor
07a82f9a-de7d-5e49-8ac6-f7d9f19e6d1e | note | Standard / Spec - Technical Specification/IFC Drawings
09c74f27-35d1-59ce-be30-3fd2d8c10664 | note | Criteria - Backfill in accordance with CES requirements and general earthworks specifications
7befe9d2-acde-500e-ae6a-faaa6c93b260 | note | ○ 98% +/-2% moisture (Ring beam area) 96% +/-2% moisture (All other areas)
774b3116-9a30-5f47-906b-9fb0afba3bd2 | note | Frequency - Min 2 tests per lot
a9392204-3e17-5675-ae2e-59abcf22ca3f | note | Record - ITP, Verification Checklist / Test Report
5cad704c-1606-5c28-b12f-ba098887827c | note | Contractor: Resp - RSA
acf98368-d1d9-55e5-b16a-915ed1fa6f8d | note | Contractor: Type - CHK
be35a74d-6ecf-5248-a55f-ee1f3e4d9491 | note | Client: Resp - Senex
9f4fcda3-2024-57c1-b1fc-915b08f0f773 | note | Client: Type - WP
a051064b-83ec-4dc4-9e95-9a5f7f00ca05 | checkpoint | 10 - Acceptance of work
019d8a45-c62d-536d-baa6-3c14215e6770 | note | Work By - Contractor
098cd4b1-5185-59b1-91fc-b1fe0963c4ca | note | Standard / Spec - Technical Specification/IFC Drawings
e0ce0a17-608f-5f0f-9da2-98044a4a462b | note | Criteria - Work completed in accordance with CES requirements.
dc3c6efe-4d2c-5e0a-8959-3a93f4f98fc3 | note | ○ Compaction reports received and meeting specification
3a2dede7-6a58-5443-8fe9-c809c7120b6b | note | ○ As-constructed survey data obtained
2e53d89d-ccf3-55a5-aef9-7db0be70b5d9 | note | Frequency - Once per lot
5e42e62c-f534-578e-b9ef-e52741c26017 | note | Record - ITP, Verification Checklist
eb02bb7f-4839-5dfb-b561-7b19eb990c60 | note | Contractor: Resp - RSA
1881179a-51d8-5564-a8ee-fc9aaa740243 | note | Contractor: Type - CHK
45fc730b-e43d-52c8-a397-3a3823a3c2d9 | note | Client: Resp - Senex
4a370660-e9c0-5c41-a344-d0c282e19ed7 | note | Client: Type - HP
1dbe9560-09b8-4af3-b1a6-092e0e6a8921 | signoff | HOLD POINT
c41d0fa0-c4a8-43fc-b20f-28740d35390d | checkpoint | Contractor Construction Manager:
2b559c92-391b-401f-943d-0276885642c7 | signoff | (Signature)
d6952089-1ffa-4d46-b69a-aa8be8498634 | checkpoint | Client Superintendent:
d3e5d1d5-eddc-46c8-827e-124fbc571a91 | signoff | (Signature)
6398407e-361b-4fe3-8dab-e14b2edf0f49 | checklist | Tank 2 - ITP001 - Clear Grub & Topsoil Stripping - Rev1 | itp | ITP001 - Clear Grub & Topsoil Stripping
905ba5b8-464b-4775-887d-620a5b437d06 | section | CLEARING & GRUBBING
1750e263-ae7c-472d-a129-20f46261e0b4 | checkpoint | 01 - Survey Set Out
adab1a11-a394-5175-b270-bfe3b61fd065 | note | Work By - Contractor
fd8009ad-9c26-574b-804f-429870c9b8b6 | note | Standard / Spec - OPS-TETW-CS- SPE-002
890ee767-167c-50f0-99ae-0cef027d16e2 | note | Criteria - The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works
a437bfe4-1c41-5cd5-8b45-17ca5bee5ca9 | note | Frequency - Prior to commencement
18d15788-4612-5a67-af26-5b4a780ab0f7 | note | Record - ITP Verification Checklist/Site Survey
5d327b85-93a6-51d3-889e-1c0944e5c486 | note | Contractor: Resp - RSA
7652c47b-3504-57f2-b282-3feaa1dcf502 | note | Contractor: Type - WP
3f6d367b-ba1e-55e3-a922-32de4e5535ef | note | Client: Resp - SENEX
bd22edac-8c08-5062-baa7-8415934051f8 | note | Client: Type - WP
5885f26f-6a2d-4174-9eac-0227ff828312 | checkpoint | 02 - Site Services
5cbf7817-5054-5334-8b9d-d041a9486e72 | note | Work By - Contractor
f7d21e1c-7ce2-57bd-9081-734dc8634717 | note | Standard / Spec - OPS-TETW-CS- SPE-002
6f506b03-d00b-51b5-9a8a-b8fc71507033 | note | Criteria - Contractor shall take reasonable steps to locate all existing service on the site. Where existing services are identified they shall be clearly marked for the duration of the works.
bda2192c-53cc-5623-b598-a0b70fc9a98c | note | Frequency - Prior to commencement
48849483-8f54-5436-9f10-a142e6ac0978 | note | Record - Site general layout drawing
83ae7a18-01a5-55e7-a04a-576b711b1a01 | note | Contractor: Resp - RSA
1f8e97a2-5fcf-5dc4-bbd3-3133db9f8b72 | note | Contractor: Type - HP
5a0639d2-e622-5b95-9742-c788243652fd | note | Client: Resp - SENEX
f8bcac85-03d5-5710-903d-f2ba1f775239 | note | Client: Type - HP
a03253ea-2558-4025-a0cc-f1a960743ada | signoff | HOLD POINT
633e67bd-1dbf-407d-aa97-3a03356f9606 | checkpoint | 03 - Lot Identification
cee0c88e-ba33-56ba-9fd8-4807d54dbebc | note | Work By - Contractor
f403dacf-125f-5bb2-ab97-2dcdf45b2717 | note | Standard / Spec - OPS-TETW-CS- SPE-002
3e63d9a3-a96a-59cd-9354-14c8ea2eb4dd | note | Criteria - Location of works identified in accordance with the Project Technical Specifications.
d7e08dd9-6b9b-534e-b043-2381b3e1724c | note | Frequency - 1/Lot
0331cc5a-eeff-5ed3-a5b1-46eba091339f | note | Record - Attached Drawing
161216f7-ea30-5aac-a628-5f691151792d | note | Contractor: Resp - RSA
12ccad69-e505-5799-bf16-c437d820c6bc | note | Contractor: Type - CHK
34d077f3-1ac3-5637-8ff8-a0d506521c3f | note | Client: Resp - SENEX
b9cb03a6-3a95-5bfd-a307-8bb7dc1f5553 | note | Client: Type - CHK
41e7cb87-3838-40fa-bb83-d8186a535003 | checkpoint | 04 - Clearing& Grubbing
86cb13a1-c67a-5185-bca9-8a7650b6e2b9 | note | Work By - Contractor
0c712e1e-aadf-5d64-b94e-5ff4ff30457c | note | Standard / Spec - OPS-TETW-CS- SPE-002
27e37287-0027-5d9c-b391-a658d1967061 | note | Criteria - Clearing shall be performed within the limits of the works indicated on the drawings.
ee2ddffc-4fa8-59da-8f95-b34a41c6c4ba | note | ○ Trees, shrubs, logs, debris, perishable material, organic matter, fallen trees, overhanging branches and surface obstructions shall be removed from the stripping area.
f13fd064-5121-5ae7-b858-de8ac5ab9758 | note | Frequency - 1/Lot
f2d7bd56-e604-5020-bbdd-a31ee8c763e7 | note | Record - ITP, Verification Checklist
8ebd9f0b-d38b-52a9-bc80-0de76e4d6508 | note | Contractor: Resp - RSA
2fc4ddd3-de76-5fab-b564-5e68d213ea58 | note | Contractor: Type - HP
74775c2c-1b6b-5144-92e9-9a85a49ed46a | note | Client: Resp - SENEX
b7385cf9-27bb-5c4f-a035-9c54aa7b7711 | note | Client: Type - HP
0d3fcd9d-61da-4339-b108-60b75895b9f8 | signoff | HOLD POINT
fef42004-bc7b-41b9-9c9b-23d9446889ea | checkpoint | 06 - Stockpile of Materials
a0d308b2-9dd4-5b76-91da-40bbfb4abb1d | note | Work By - Contractor
a7c37471-c5bc-5961-a59f-f6c192d07be3 | note | Standard / Spec - OPS-TETW-CS- SPE-002
d317f425-78f1-5e8e-968e-322eb2fc635c | note | Criteria - Cleared and grubbed materials shall be stockpiled or disposed of as directed by the superintendent
35b134d4-662b-5530-81e1-23526475a366 | note | Frequency - 1/lot
92a1e762-fc75-5335-a8fd-fe2ca35c47e1 | note | Record - ITP, Verification Checklist/ Lot Map
4075f575-3531-58a9-b6fe-7cef3f6e87e1 | note | Contractor: Resp - RSA
91febc9f-9285-5ca1-8155-5bca15bb9784 | note | Contractor: Type - WP
ab310ff0-e64e-53d6-ad98-c9e39b64f3b2 | note | Client: Resp - SENEX
161eff11-ce43-5c5f-8c87-12f26ababf34 | note | Client: Type - WP
613064fd-d3a4-41f2-9837-0ef58475e32c | section | TOPSOIL STRIPPING
52ac0253-3d4a-408b-b969-8bb93a224710 | checkpoint | 07 - Topsoil Stripping
d187482d-5b8e-50e3-9c4a-37c71dc7ceb3 | note | Work By - Contractor
344e70ee-c6d7-5b13-8a16-3b353918560f | note | Standard / Spec - OPS-TETW-CS- SPE-002
249a205d-7e92-58f7-9ba1-dad200fc2722 | note | Criteria - Topsoil shall be stripped such that all organic rich soil and roots/rootlets has been removed from the foundation of the embankment and internal borrow areas
edb78d32-d0e4-5954-bb4d-56418cd1092b | note | ○ Topsoil shall be stripped to the nominal depth of 300mm+10%. Any areas with depth greater should be notified to the superintendent.
01064c12-d2f1-530b-9aac-950f9647e4c6 | note | Frequency - Confirm with survey
658937a4-efc6-52dd-8cda-6b073087a0a1 | note | Record - ITP, Verification Checklist/Site Survey
ef8a5392-f6af-5ff8-a9a4-d5e86daf3b50 | note | Contractor: Resp - RSA
8efb0221-0e7e-5382-ba24-f4c7f5f65874 | note | Contractor: Type - WP
142508b8-4996-5204-99e9-6705cff7e435 | note | Client: Resp - SENEX
5cc8f6b2-50cc-5119-8e2b-d4306a238756 | note | Client: Type - WP
71cf02b5-8253-4cf2-b3c0-7d4717f83610 | checkpoint | 06 - Stockpile of Materials
0b6352dd-b138-57d1-b2dc-6dfe08bfece0 | note | Work By - Contractor
def35b3b-a924-54df-9aa2-9b6f8b3abff1 | note | Standard / Spec - OPS-TETW-CS- SPE-002
3eecf9bd-0aeb-55df-bfe7-43062baa1612 | note | Criteria - Stripped topsoil shall be stockpiled where directed by the Superintendent, for reuse.
30f9a7da-20f5-5708-afd5-bb68370d7122 | note | ○ Topsoil is to be placed in a loose, non-compacted state, to a maximum height as directed by superintendent.
8a804eb0-244c-56c7-bc1a-94f0e2f89bd8 | note | Frequency - 1/Lot
65905142-01c0-516c-8422-363a7df8fd8e | note | Record - ITP, Verification Checklist/ Lot Map
8853eb17-878f-5f27-baf7-ec113a86c5ca | note | Contractor: Resp - RSA
460ce08b-0c29-5bf8-bf8b-cdb8a5448b63 | note | Contractor: Type - WP
2cc836cb-b2ca-5997-aa1a-8e90456fa44c | note | Client: Resp - SENEX
ad3c33e5-fa19-59cf-97e0-e21d7db0be27 | note | Client: Type - WP
d201b758-368b-42dc-845c-0b1cf0bc22ec | checkpoint | 07 - Topsoil Strip Survey
2b56fb9b-ede6-5888-8cbf-04a4af22555e | note | Work By - Contractor
cf8a06c6-746e-5f83-9f53-e148a0f8c7a3 | note | Standard / Spec - OPS-TETW-CS- SPE-002
cd325c77-102a-5281-8c69-23c589d43553 | note | Criteria - As-constructed survey has been to be completed to record the surface levels on completion of topsoil stripping.
3cf8ddd6-431b-544a-b284-7f398f49216f | note | ○ The Contractor shall submit a topsoil strip survey to the superintendent prior to excavation and/or placement of fill material
14950e1b-ea52-5fd0-8143-ef7930ad700e | note | Frequency - 1/Lot
a8398758-a02b-5b75-b9ff-ef7816ac634e | note | Record - ITP, Verification Checklist/Lot Map
56f38e81-284c-5c1f-9d9f-a2955265fc94 | note | Contractor: Resp - RSA
13c943cb-2695-5539-ad76-36cb6526525f | note | Contractor: Type - HP
4d999724-1d62-50de-a1a4-877175464ede | note | Client: Resp - SENEX
a2574d10-4601-57c7-9a7a-68f75c1fa291 | note | Client: Type - HP
23353e0d-79ae-417d-a99b-2a2ec8ae1acc | signoff | HOLD POINT
b5e13dad-b1fd-4e15-9d71-1dd5f62d0e35 | checkpoint | Contractor Construction Manager:
f3297bbb-c1e4-4209-831d-881e48c89e41 | signoff | (Signature)
40cb9a7f-7bac-4105-9d15-5d5e8d5544fc | checkpoint | Superintendent:
45132a77-361f-42bf-81fa-74e5f7e34f2d | signoff | (Signature)
c061cd11-7bc4-4c25-b858-97bf30fed21d | checklist | Tank 2 - ITP002 - Foundation Preparation - Rev1 | itp | ITP002 - Foundation Preparation
ff2eb4bd-5515-42c0-bea2-d330ee62eb1a | section | FOUNDATION PREPARATION
e65b72f7-1dd8-4944-881d-84c77712e959 | checkpoint | 01 - Lot Identification
1057fb08-e528-55b5-9f48-83a24d53ebae | note | Work By - Contractor
f7df40fd-e4b8-526c-b0bd-6c6e46064d6a | note | Standard / Spec - OPS-TETW-CS- SPE-002
45dc69ab-887c-5110-b0da-9d45e93105fb | note | Criteria - Location of Works identified in accordance with project technical specification
e0a4a56d-b991-51e6-96ec-defc35482fd9 | note | Frequency - 1/Lot
3f030ced-d5b0-5f96-ae51-abbc6c438184 | note | Record - ITP Verification Checklist/Lot Map
903cf039-c953-5d0d-9ae7-90aa194ce7a0 | note | Contractor: Resp - RSA
557f7302-e86a-55b2-9595-81ff3d2d356b | note | Contractor: Type - CHK
016c6dd6-cdad-5e5c-8278-98f385edea83 | note | Client: Resp - Senex
ddf8e1d6-81b1-5d03-8e4d-65a20db8fc6c | note | Client: Type - CHK
8f7e531d-d64e-42d8-8c53-f26dd0c3e7c6 | checkpoint | 02 - Foundation Preparation
fba8be6f-72df-5236-8904-00d75a790bb6 | note | Work By - Contractor
b470ee49-e0b3-5b26-a715-c28c3aa0c7e1 | note | Standard / Spec - OPS-TETW-CS- SPE-002
7a92bcc4-200b-5cd9-a465-6c83b4a8e6ce | note | Criteria - Foundation preparation of Lot will be visually inspected for material type, moisture and organic material prior to foundation preparation works.
a360a1d6-e46b-558a-bdd0-7cc93d5681f7 | note | ○ The Subgrade shall be trimmed with a grader, smooth bladed scraper to assist with the inspection process.
99b8591a-3ad0-5f77-9590-7d856bcaaabe | note | Frequency - 1/Lot
6bdc2b44-94ab-560a-bfb8-1768778db04e | note | Record - ITP Verification Checklist/Lot Map
b865cbf4-3682-5ab5-bd86-703d4c173759 | note | Contractor: Resp - RSA
71ce8dfc-5f19-5b41-8051-5a492f983b41 | note | Contractor: Type - WP
8a8de527-bee6-5ef9-97b9-cdf2841328d5 | note | Client: Resp - Senex
7c865ebd-04df-52a6-a88e-62a28604cd43 | note | Client: Type - WP
391e2e9a-26f3-4e1c-9c17-b554dc4940dc | checkpoint | 03 - Foundation Preparation – Proof Rolling
4c546c6d-558d-54a7-b211-192bbab7de2a | note | Work By - Contractor
241ab85d-5e82-50da-9cfd-0cf158c20538 | note | Standard / Spec - OPS-TETW-CS- SPE-002
9ab4e6d1-1050-5594-b240-fde9695c3317 | note | Criteria - Subgrade shall be Proof Rolled in accordance with Queensland Department of Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client.
df4e2d6f-0ee7-5817-9ce0-533a7aae82a9 | note | ○ Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
ad50bc6c-2a37-5279-8ee8-78d660c9df2f | note | Frequency - 1/Lot
40c4218f-85a5-52b6-accb-0b64424038ef | note | Record - ITP Verification Checklist/Lot Map
fd36fb5b-387a-54b2-959d-028c171094af | note | Contractor: Resp - RSA
21c335d8-3edb-5687-92ce-0ed6928cc34a | note | Contractor: Type - HP
2c0e635d-e896-566c-bf05-a6669e5af4f7 | note | Client: Resp - Senex
04c68c90-7c1a-5fa3-bd75-05e63b765bc4 | note | Client: Type - HP
d5a9fabf-d4fc-45da-b6fd-0780c175b59c | signoff | HOLD POINT
59c64654-166b-4969-bf61-b31084bcfbcd | checkpoint | 04 - Dynamic Cone Penetrometer (DCP)
e42d0133-3e63-54c9-86c8-c3ca714bb7d8 | note | Work By - Contractor
66c0c2cf-4d87-54e0-a0dd-56503f3e2a0c | note | Standard / Spec - OPS-TETW-CS- SPE-002
464ccf46-0284-5281-aa57-fdddd9e0bf9f | note | Criteria - DCP testing shall the undertaken in accordance with AS1289.6.3.2 by the superintendent to assess the consistency of the subgrade. DCP test Shall extend to a depth of 1m and achieve a min of 3 blows per 100mm penetration
c29fea68-ee30-58c7-85b0-649eb7445d5e | note | Frequency - 1/2500m2
594582ce-e2cb-5a20-8525-59299856a2c1 | note | Record - NATA certificate
2fcc62e7-3c27-5ba1-b165-5f3080d397bd | note | Contractor: Resp - RSA
d085b044-a8b7-5624-8e89-9315682e1fcf | note | Contractor: Type - HP
59c25bff-6b69-5e7b-b4c2-38bf5c4f29f6 | note | Client: Resp - Senex
381cd4de-77ae-5048-9c4e-57887de3258b | note | Client: Type - HP
6843930e-24d7-4032-8d0c-27a1d5f9ea04 | signoff | HOLD POINT
67aeeaf1-aab9-4214-8989-221348c4fbea | checkpoint | 05 - Foundation Preparation – Ground Surface Treatment
963a7933-d10c-5d63-af11-cfd355cbe92a | note | Work By - Contractor
be5e0ea1-3d77-59fa-9db5-deac02f6c90c | note | Standard / Spec - OPS-TETW-CS- SPE-002
f31eb924-2fa4-54dc-b9be-c16da4f16a91 | note | Criteria - Scarify minimum 200mm, moisture condition and compact.
d1f50ce1-b96d-5bde-9886-00caf6b05324 | note | ○ The Superintend shall inspect the subgrade for conformance with the specification prior to placement of overlying fill.
edc351b5-dd18-537f-a79c-2cd0dc09ef91 | note | Frequency - 1/Lot
d0489882-9e62-59b6-bdbb-0727ac38de74 | note | Record - ITP Verification Checklist/Lot Map
8e15db3d-d58e-562c-9fc8-9fb3ac9993d7 | note | Contractor: Resp - RSA
73cfe39a-9426-5637-8fae-13b1fe39748e | note | Contractor: Type - HP
e725897a-4011-56c6-ad92-6aea1ef2079f | note | Client: Resp - Senex
eb16f5c9-82f9-5820-9392-2baf35ec4aed | note | Client: Type - HP
3ed5e3f3-e228-4e98-8ff2-d5d711539b23 | signoff | HOLD POINT
1038a6d7-23ea-4263-8070-cc6968210462 | checkpoint | 06 - Ground Surface Treatment Testing
2333997e-0421-5c48-8c6d-6f0c157c3ea2 | note | Work By - Contractor
af0132a8-9913-54fa-90d8-7d2b98c11e24 | note | Standard / Spec - OPS-TETW-CS- SPE-002
6af78ace-8e65-5e91-a009-a83e0b81cccd | note | Criteria - Tank Pad foundations surface level shall be scarified, watered and compacted to a density ratio of no less than 96% of standard MDD and -+2 % of OMC.
fd1effc7-42f3-5182-b112-a090eafea012 | note | Frequency - 1/2500m2
b017a2eb-a5d2-58a1-aaec-83e094d62a05 | note | Record - NATA certificate
f12cdcfe-3b8b-58c8-9a81-9fece4814af9 | note | Contractor: Resp - RSA
d495cb85-f966-5089-9e5d-0cab72994735 | note | Contractor: Type - HP
23b47383-148b-5efa-b6d4-7ee657d3269f | note | Client: Resp - Senex
a73236d9-8d43-5090-9fe5-ba168603ead5 | note | Client: Type - HP
660ebc5d-547f-4805-89b2-7381fa2e2aa7 | signoff | HOLD POINT
75d63332-54e0-42b2-b7a9-22a414ed9ee6 | checkpoint | 07 - As built Survey
c3c119f4-30ef-559f-88ad-14e6403970cd | note | Work By - Contractor
0f33480b-fb8f-5162-9bc8-792eeee3bcd9 | note | Standard / Spec - OPS-TETW-CS- SPE-002
6fe23fd1-125b-5924-9084-59e3492e5ef0 | note | Criteria - Finished levels checked for Vertical and horizontal tolerances as required.
4eb86381-7362-58f6-92a2-54bd8f9b7e0b | note | Frequency - 1/Lot
2904109a-dd60-5c9d-8158-4898689a0fd6 | note | Record - Survey as Built
f94d2cb6-85e6-5e2c-9928-47626ee832ae | note | Contractor: Resp - RSA
600c946d-595f-5f13-946d-473dd43c5502 | note | Contractor: Type - HP
a8fd3f39-ea2a-588f-9704-9c624d35268b | note | Client: Resp - Senex
f2bf9fc3-5bb5-5af3-bee9-635f30bf2e75 | note | Client: Type - HP
82d39d3a-1166-4dee-a901-79dc60c8b44b | signoff | HOLD POINT
22898763-993c-46f1-ba7f-4c6a80428722 | checkpoint | Contractor Construction Manager:
19733929-6c78-4fe0-ae54-58a13f6cff08 | signoff | (Signature)
f77be3e4-4cf4-41da-b746-e172ddfc1d1c | checkpoint | Superintendent:
23e52f3b-0963-4027-bc6e-915673b5788d | signoff | (Signature)
63eab2da-0fd1-488b-990b-cbdbca7098e2 | checklist | Tank 2 - ITP003 - Embankment Construction - Rev1 | itp | ITP003 - Embankment Construction
b3cb100d-6ada-4275-a8be-23760d3e45ad | section | EMBANKMENT CONSTRUCTION
65d27ff9-3254-4d2d-b6c2-f12728187096 | checkpoint | 01 - Lot Identification
1aed5c21-55ad-5c2c-b118-7338ce9d2ffe | note | Work By - Contractor
6b02fdf0-4a07-5025-80c8-52a440f902ab | note | Standard / Spec - Technical Specification
ad6a99db-ca04-5fac-ba97-727d49faac20 | note | Criteria - Location of Works identified in accordance with project technical specification
d7e9f40c-9ea1-53d8-8f76-2dddb64ad188 | note | Frequency - 1/Lot
5ecec4bb-9fd9-5816-bc70-bd9336b3f613 | note | Record - ITP, Verification Checklist/Lot Map
8dbe7d8e-e928-5bfc-8264-c4377e05d43c | note | Contractor: Resp - RSA
621e2a5e-97a2-5c72-939a-1b998ded455b | note | Contractor: Type - CHK
afb7c52f-370e-5220-aed8-23202a81706b | note | Client: Resp - Senex
bfccd1a7-f550-52cf-9f43-659a25363687 | note | Client: Type - CHK
d8f48f49-66bd-4f19-a5c3-ad1de4563093 | checkpoint | 02 - Underlying Lot Conforms
d52669b3-0aac-542c-b633-35742139a162 | note | Work By - Contractor
7977071a-11ea-52a7-b371-4a531f96813b | note | Standard / Spec - Technical Specification
a9a87a94-7fae-54e9-9a79-945400387c2a | note | Criteria - Foundation preparation works completed in underlying lot.
b08e377b-0dc4-5461-8eb9-1f52cc53202d | note | Frequency - 1/Lot
9697bac7-c9dc-5c96-9fd2-1376945b742e | note | Record - ITP, Verification Checklist/Lot Map
217fea62-9504-5e12-a352-c77518a50ad2 | note | Contractor: Resp - RSA
4b9085f6-ffb9-5ce9-ba63-732b1c3474f0 | note | Contractor: Type - CHK
f3165ddd-0ccf-5874-89d4-1d5cae1a51f6 | note | Client: Resp - Senex
64c78d09-4f90-5477-a567-cdb22718d55f | note | Client: Type - CHK
a6cdcce3-cc4b-46ac-ad1e-e5e09f1afb19 | checkpoint | 03 - General Fill Material Requirement
2477a3b1-2a6f-5fbc-8a18-14e3cc15fcfd | note | Work By - Contractor
2026f30e-f1e4-5eed-9cc3-0c6cf3bd7d6c | note | Standard / Spec - Technical Specification
7ce5b5d9-b6dc-5b0c-acda-876e4e60f78d | note | Criteria - Grading Requirements
2aa028bc-74f7-544d-93bf-ba859ab5a37d | note | ○ 75mm sieve – 100% passing
c71435ca-ae43-50b5-9bcc-f2560b1cdddc | note | ○ 37.5mm Sieve – 90 to 100% passing 19mm Sieve – 80 to 100% passing
afe0487d-629b-5eee-90be-3d1f37fc0172 | note | ○ 4.75mm Sieve – 60 to 100% passing
80f9a787-971b-5bfc-ad60-5fd070bb4aeb | note | ○ 2.36mm sieve – 40 to 95 % passing 0.075mm Sieve –15 to 90% passing Indicator requirements
8598f204-eb75-598d-8efe-e236017d3c35 | note | ○ Plasticity Index – 10 to 40%
b0664627-77f6-5edd-aa40-a1d93172f8ee | note | ○ Liquid Limit – 20 to 60% Emerson Class 2 (minimum) Organic content 2% (maximum)
97d7e931-95b9-5101-8001-bf91c719e28c | note | Frequency - Refer to Table 11 SPE
b7158fa2-e7b3-5981-9525-24bddd31af24 | note | Record - Laboratory test Certificate
a0580168-02a2-51a2-91d0-0fce25bd758e | note | Contractor: Resp - RSA
d22a6613-be77-54b9-8ba4-494049af4550 | note | Contractor: Type - HP
4e0c9261-4d1f-5cb1-bceb-3914fd55f7a7 | note | Client: Resp - Senex
b8131970-7d49-5251-aca4-65be7e434f9f | note | Client: Type - HP
4df09961-cec3-47c6-995f-2e5a661a354a | signoff | HOLD POINT
7b346a56-ceb4-45e0-925c-85bf2973bf00 | checkpoint | 04 - Fill placement
8c1402b7-d42f-5828-9046-3a4273e782e7 | note | Work By - Contractor
3961a493-a00f-58de-8f99-32c6d07f7715 | note | Standard / Spec - Technical Specification
becf0c82-1d38-5e02-a30a-27d9ce05d3c1 | note | Criteria - General Fill
d86dfcab-5e62-5d9f-b1c6-17e262f59e1f | note | ○ Placed in continuous, approximately horizontal layers for the full width of the area, having a compacted thickness of not more than 300 mm or less than 75 mm. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm prior to the placement of the next layer.
717227e5-20fe-5b56-9621-8bf40f33c6b5 | note | Frequency - Each Lot
35458ce6-f5ed-5527-947c-fbbbd9c2366d | note | Record - ITP, Verification Checklist/Lot Map
5cebf1e2-858b-52e3-8a18-07d6330b6809 | note | Contractor: Resp - RSA
1d47af08-68cb-5305-96a5-02164e5291b1 | note | Contractor: Type - WP
5cfc2afd-2cee-5100-817c-0c8c87794651 | note | Client: Resp - Senex
2c33d615-f298-5bee-a766-7b23585167ee | note | Client: Type - WP
3e3c9a97-7fbf-4d97-9892-161743432a8a | checkpoint | 05 - General Fill Testing
4b8f618e-6e13-5f9a-86ba-7d7663b606ef | note | Work By - Contractor
31826852-4e27-50e8-a2d2-f7f9b72f9e32 | note | Standard / Spec - Technical Specification
b3eee10f-dfb2-5f0f-9146-e4b9517fdcf6 | note | Criteria - ≥ 96 % standard MDD.
c397368c-2f99-5c88-8027-4a0dfd7d94be | note | ○ NOTE: ≥ 98% standard MDD for the Earthen Ring Beam General Fill Section.
2219de29-68a7-559b-ac62-9c4a99321c3d | note | ○ -2% to +2% of OMC
fb994d37-474c-5604-bcc2-d9132fb9cec8 | note | Frequency - Table 10 Technical specification
f09fc4ab-9d98-521f-9e48-aa39c52aef1b | note | Record - Laboratory test Certificate
d93d43c5-7571-53b8-831f-1a83cd33e976 | note | Contractor: Resp - RSA
3b232562-51b9-5e5f-8b96-ded8823598f7 | note | Contractor: Type - HP
09cbeb49-53e6-5638-af3c-602c552b105f | note | Client: Resp - Senex
37dc3712-fbcc-5920-851b-30a8a5bcc8b7 | note | Client: Type - HP
b478062f-9bb5-4417-8c2a-06970eaea279 | signoff | HOLD POINT
34d965ef-f413-4787-97f0-c3ed0ca6a811 | checkpoint | 06 - ERB Inspection
5866dcf2-46dc-573d-a174-8fb9329898b2 | note | Work By - Contractor
4f0451fc-fd44-5d57-b78b-24e7770439d4 | note | Standard / Spec - Technical Specification
5b257e52-37d7-5b11-9655-d5a660659f1e | note | Criteria - Verification of RLs/Elevations filed controls for the ERB
a7a75bf5-0720-54a0-94d9-0ed2736905ac | note | Frequency - Progressive During Fill Placement
b3a60f00-552b-540e-85c9-91a8b9fb92a8 | note | Record - Survey Data
16d6b16f-3005-56e0-933d-975b8bc4441e | note | Contractor: Resp - RSA
01a4e0e1-c5d2-56dd-b414-98e17f9c716a | note | Contractor: Type - CHK
5d83a86f-5502-511f-9d82-6b202c06c592 | note | Client: Resp - Senex
d192bd13-b1f0-53dc-a460-249ee9f2e917 | note | Client: Type - CHK
afad42b5-6a6d-40c7-9198-95fab7c85c11 | checkpoint | 07 - Survey
2551bc72-3a10-5245-91c8-ecdcedccbdf5 | note | Work By - Contractor
1a4d39a4-2fbb-512c-9743-5709bd00acf0 | note | Standard / Spec - Technical Specification
f37a0aef-34b0-5c3b-90e4-51dfffaa57ab | note | Criteria - RSA shall submit 25%, 50%, 75%, 100% tank pad foundation fill placement completion survey to the superintendent within 48 hours of each milestone achievement
b5de8c9e-e5a4-57bb-8ebb-1c164ae44de0 | note | Frequency - 1/Lot
be3ede9d-5804-5daf-9279-fbd2997da3bc | note | Record - ITP, Verification Checklist/Lot Map
c3d5beca-e8eb-5c40-a1c4-169cf2a21116 | note | Contractor: Resp - RSA
63b68dc1-72ac-582a-b215-b458e13c37ca | note | Contractor: Type - HP
219122be-4296-5678-8e1b-6ca25cb1c0ce | note | Client: Resp - Senex
bae01060-1bf3-58ee-8446-4f9bcf65c314 | note | Client: Type - HP
590bf34e-59e4-4b80-94ea-5dfd30a7d451 | signoff | HOLD POINT
4cdb08c1-9349-40a5-9beb-ffacbfc32fda | checkpoint | Contractor Construction Manager:
438fe7e5-c728-4be3-a52f-9a909953c835 | signoff | (Signature)
b51a269c-fadb-4fc0-b266-42d8f9a0df05 | checkpoint | Superintendent:
6a4d6b9e-9d22-4287-9fd2-cca9b4313387 | signoff | (Signature)
df44303f-1b25-4767-8c15-8c8e50226fe9 | checklist | Tank 2 - ITP004 - Capping Layer - Rev1 | itp | ITP004 - Capping Layer
3e5ec0dd-a6fb-4e5a-97e8-6b7346c96853 | section | CAPPING LAYER
f4daf2fb-f02a-4cf5-96a9-46be29c71035 | checkpoint | 01 - Lot Identification
4c72b706-be2a-543c-9b4d-b8fc778585e0 | note | Work By - Contractor
3cc53eb1-1137-50f9-849d-4f725e84b877 | note | Standard / Spec - Technical Specification
3734fa7d-110e-5f06-9dbe-36bb6ef294fc | note | Criteria - Location of Works identified in accordance with project technical specification
0478e7b4-6ea0-5e38-bbed-fc3f33695ca7 | note | Frequency - 1/Lot
9c0e8d88-ea05-53f0-a2fd-76dc4fca342a | note | Record - ITP, Verification Checklist/Lot Map
ef7b9de9-613d-53af-be7b-248a51f58658 | note | Contractor: Resp - RSA
9f7295c4-520a-5547-8cc6-6bb318eaaf4e | note | Contractor: Type - CHK
4f378c85-5e7d-55bb-8df0-47a466aa2b08 | note | Client: Resp - Senex
7be80326-10b4-58c5-bd27-31fc9b45de2c | note | Client: Type - CHK
dcaca35b-2257-4a88-b187-22a07347083b | checkpoint | 02 - Material Approval
7c322eea-e276-57f2-99e1-359e6016f90b | note | Work By - Contractor
1c400491-6330-5718-b140-411625044398 | note | Standard / Spec - Technical Specification
f1a88f83-bca0-5d8e-8e05-902febdee55c | note | Criteria - Material shall meet the requirements under Queensland Department of Main Roads Technical Specification MRTS05 Type 2.5.
722c826c-7343-5bf2-8e87-e75c7434e039 | note | Frequency - 3 tests prior to import
3d84f698-d869-5279-84d6-9ea2bde2da74 | note | Record - Laboratory test Certificate
37f956dd-8538-55fe-a977-892297a97e76 | note | Contractor: Resp - RSA
b221f13a-efba-58a1-a7fa-20b5175e85f9 | note | Contractor: Type - CHK
02224fb7-1540-5e9c-a9ff-66ee8c24088a | note | Client: Resp - Senex
2bcc7dcf-2595-5ad7-9668-ecf1a51eff2b | note | Client: Type - CHK
c0293974-77fe-4d8c-9e9b-619451918b8c | checkpoint | 03 - Subgrade Testing
413858e0-ac3f-5469-bb7e-89cbb2585777 | note | Work By - Contractor
a44449a0-dbb9-512f-aa79-89a38c03249a | note | Standard / Spec - Technical Specification
cc178ab4-b0d4-5133-af76-76d5bca0f412 | note | Criteria - Subgrade shall be tested for material characteristics, moisture, and compaction.
a5699edb-44ae-5c8e-9ebb-afa4be2bb368 | note | ○ >96% SDDR
dc473dc2-635f-5d58-9475-d416704162bb | note | ○ -2% dry to +2% wet OMC
f0f8b1f8-a361-58f9-9d39-e0f4f6d6330f | note | Frequency - 1/2500m3
212d2621-f83f-5471-bfea-c9ada63323db | note | Record - Laboratory test Certificate
71bf8f6a-5d99-5642-a37d-0196b785b89a | note | Contractor: Resp - RSA
8baf823f-0aec-50ed-88ab-3bd3f4c9ab56 | note | Contractor: Type - HP
e611ed04-6cc4-5e0a-9777-e2034e872097 | note | Client: Resp - Senex
88f838b0-36ab-5bce-aabe-17c0df9eaad5 | note | Client: Type - HP
7f56cda4-83d2-4b26-831c-9d2779d25211 | signoff | HOLD POINT
9cf4829c-b772-45b8-b5c0-cad6127c20d5 | checkpoint | 04 - Proof Rolling Subgrade acceptance
5f91f529-8007-5522-a177-33cf02cd5c23 | note | Work By - Contractor
242301f0-37bc-5865-b486-4706d3b18de9 | note | Standard / Spec - Technical Specification
33bb1aed-e6b9-5ca2-a26d-61c1c3591798 | note | Criteria - Subgrade shall be Proof Rolled in accordance with Queensland Department of Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client.
b52be447-1f0b-53cc-a371-ecf793b7d1d2 | note | ○ Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
0da993fd-8a48-55d1-984c-0f04d3ee0821 | note | Frequency - 1/Lot
33bfb718-f4d5-5334-895d-fd8dada4eb08 | note | Record - ITP, Verification Checklist/Lot Map
e0f71d7c-fcda-5d02-b7a9-a3f552fba72b | note | Contractor: Resp - RSA
f801eaf1-a2b7-5ad5-9017-ce6df469db90 | note | Contractor: Type - WP
028ab5ed-5de6-54c8-a792-89001cd9fc0e | note | Client: Resp - Senex
d38c491e-5ab3-55d8-92a3-597e0d091435 | note | Client: Type - WP
2f5cc884-dfe0-4dfc-9585-33f3b026b291 | checkpoint | 05 - Placement of material
500ce660-2b8d-5b60-ba0e-1fd0a20760d1 | note | Work By - Contractor
b7aeeb36-953d-5d9f-bec8-d6d4fd82708c | note | Standard / Spec - Technical Specification
9a8cc3b2-5605-5207-876c-d7d6a069b831 | note | Criteria - Access track and ring road capped with 200 mm depth gravel. Placed in continuous, approximately horizontal layers having a mi compacted thickness of 150 mm and not more than 300 mm.
196af0bc-04b4-5246-837a-098c23ce75a3 | note | Frequency - 1/Lot
3499940d-956e-5c00-8959-6ef763ddc932 | note | Record - ITP, Verification Checklist/Lot Map
7995bc70-9bd1-5baa-82fd-24b717c5d6c2 | note | Contractor: Resp - RSA
b6131a79-53be-5dfc-ae35-3d41f8a3f87d | note | Contractor: Type - CHK
ab0f8487-b97a-59a2-9ea2-92ae1293c19f | note | Client: Resp - Senex
fc127732-671c-5eb7-9b10-a3d6521395c0 | note | Client: Type - CHK
73384eb2-ddcb-4f71-b60e-5c3d941e7c3c | checkpoint | 06 - Material Testing
934642dd-afdc-53fd-a351-75bc21425b50 | note | Work By - Contractor
5384b113-8d50-5a60-8b5c-f3778c7d8162 | note | Standard / Spec - Technical Specification
6de44028-6df4-5cc6-9b8d-15228ab27433 | note | Criteria - Capping Material shall be tested for material characteristics, moisture, and compaction.
b43daf29-9613-5847-ae85-22d900eabeab | note | ○ >100% SDDR
22691bfe-e17d-5225-b49d-106419ca0018 | note | ○ -2% dry to +2% wet OMC
590f5f20-7ce2-55a9-94d4-2d6441164eb5 | note | Frequency - 1/500m3
52c0d30a-63e6-5555-9fee-4b6f41b8e53a | note | Record - Laboratory test Certificate
2f5bd8eb-54a8-51f8-8cba-95f03ce1d3dd | note | Contractor: Resp - RSA
01c700bd-37a5-579a-920c-396fc6f86f95 | note | Contractor: Type - HP
71e69524-8b42-57d4-86dc-dc381d13012d | note | Client: Resp - Senex
d8a6df53-c29d-599b-b7aa-29ff99e36296 | note | Client: Type - HP
9ee04d69-dd76-4804-8e8a-a9a337b57627 | signoff | HOLD POINT
14e40a24-1df2-4904-a246-12cc23c0ed28 | checkpoint | 07 - As built Survey
e0fdc74d-e3c1-53ae-803e-fdccbc9833ed | note | Work By - Contractor
e9672841-918f-5911-ad4b-ca68522f78dc | note | Standard / Spec - Technical Specification
5867b4c6-1753-550b-83fc-c652d15273a3 | note | Criteria - Finished levels checked for Vertical and horizontal tolerances as required. Refer to section 3.4 SPE
96991163-9411-5afe-849f-f14ad1f56861 | note | Frequency - 1/Lot
526017a7-de59-5945-99c7-c80cb9ac1e08 | note | Record - Survey as Built
dbdd18bd-980f-5134-9e64-6adb406fdd5b | note | Contractor: Resp - RSA
cd60a3b1-ec24-5b31-90fb-5682a0314882 | note | Contractor: Type - HP
a6eea985-db14-5f15-916b-bb79cf1e0ff5 | note | Client: Resp - Senex
8f0fde9c-1f78-514e-88fb-0c64cdb6654b | note | Client: Type - HP
51431614-0a84-4d6a-b38a-d183f092b04c | signoff | HOLD POINT
508e1d1b-eb38-45da-96da-c9d07bb8cf29 | checkpoint | Contractor Construction Manager:
7d354ed0-394d-4bcb-8586-a130d19e32aa | signoff | (Signature)
81a21950-b1bf-48bb-97d0-83aeab1d94ec | checkpoint | Superintendent:
6fe36903-8ea6-49bf-bd9d-a3067f2a359a | signoff | (Signature)
1a20cda8-6c1f-4069-b1a2-9f771052469e | checklist | Tank 2 - ITP005 - Surface Water Runoff Management - Rev1 | itp | ITP005 - Surface Water Runoff Management
923464ea-e8b4-48b6-b449-5e9c2e416015 | section | CAPPING LAYER
c4456eff-ec0c-4101-8523-832ee0e9d133 | checkpoint | 01 - Lot Identification
fb892477-fe06-5d87-8f57-ac21ad113986 | note | Work By - Contractor
680c5eca-e747-5b1d-ae95-8f75cc72e37b | note | Standard / Spec - Technical Specification
3f925f83-d9ac-5505-b797-835d6a08fb9a | note | Criteria - Location of works identify as per IFC drawings
bdaaea9e-f026-5063-b272-032d6a034ba4 | note | Frequency - 1/Lot
3c5a9b7a-82f3-5505-9dca-647d7f957bfb | note | Record - ITP Verification Checklist/Lot drawing
cddc4fc1-6f9d-510c-86f1-fe40c3e09223 | note | Contractor: Resp - RSA
fea1cac9-6fdf-5e87-8ff5-68515a9a20e0 | note | Contractor: Type - CHK
f0ba083d-1228-50e1-906b-a56595eb0fc0 | note | Client: Resp - Senex
5efe282c-5629-5812-b6c4-04810ca6d898 | note | Client: Type - CHK
d67fffba-0f85-406b-89e0-1cb57bfd5024 | checkpoint | 02 - Subgrade Preparation
f56d2a98-0b8f-58af-b3df-43635dec590d | note | Work By - Contractor
d4a60f8f-0e48-53c9-9db3-d71de2eac4c6 | note | Standard / Spec - Technical Specification
4979edd3-6bb8-54a9-9dae-2f762f5c988a | note | Criteria - Scarify subsoil to a minimum depth of 150 mm
b45f8d61-ee3f-5502-8afb-9830d3ad47bc | note | Frequency - 1/Lot
bbe13f48-76cc-5e92-bfe4-f8a674d8301c | note | Record - ITP Verification Checklist/Lot drawing
026490df-157b-5e2f-8238-b4b536d392bc | note | Contractor: Resp - RSA
67c88f15-4250-5795-aaef-9d3233724454 | note | Contractor: Type - CHK
37cb800f-a3fc-5096-a465-5c506a8a777c | note | Client: Resp - Senex
99e2f6ad-ad82-592e-b66f-e464d0ee3f40 | note | Client: Type - CHK
9dbbca30-9ce5-4da3-99bf-87569b99039e | checkpoint | 03 - Gypsum Application
288a6f7f-e30f-5582-9ed6-bf6fd711a34c | note | Work By - Contractor
397f53f3-8fda-56de-a6fd-49fe5172cb2a | note | Standard / Spec - Technical Specification
9a075969-b7e8-5bda-a996-0cc09fbd422b | note | Criteria - Apply gypsum to batters and table drains at rate of 5t/ha, and apply water at 10mm/m2 to create adequate topsoil bond with the subgrade
6a2b9d7a-a748-5ff0-bad8-1efb1aaa28e8 | note | Frequency - 1/Lot
9b337aff-3394-5ae9-86ee-b6289ed7e2c4 | note | Record - ITP Verification Checklist/Lot drawing
683d6058-a0a8-5a3a-8d06-99265208aeae | note | Contractor: Resp - RSA
f5f1009a-a3a1-57ba-93d6-89a43652716c | note | Contractor: Type - CHK
448ffc8c-f850-5280-9bdc-cdfea1c19623 | note | Client: Resp - Senex
bc2a2b3d-94a3-5941-9f5e-4a2eff066a38 | note | Client: Type - CHK
d8cbe4ce-dd26-4c01-95e4-8c014572af0a | checkpoint | 04 - Respreading of Topsoil
72c3d17c-db23-5ce4-a095-995c33b3ad46 | note | Work By - Contractor
00d7127e-e0d8-5ec6-a19e-135885abe8a7 | note | Standard / Spec - Technical Specification
58e19760-2b04-5002-beab-4fa65ee8abc0 | note | Criteria - Topsoil is to be placed 300mm thick and trim with grader and scarify to a depth of 100mm.
7b2ef252-6964-5dfb-ba8a-8b23d30836a2 | note | Frequency - 1/Lot
ac8ceeff-4141-5f82-98ea-3c53c45ca01e | note | Record - ITP, Verification Checklist/Lot drawing
ef7572a4-7441-52f8-84b1-b17d6483a085 | note | Contractor: Resp - RSA
9ebfaa09-8993-57e6-aef9-461ef395745c | note | Contractor: Type - CHK
661baa23-9db7-5641-8147-ea3321d31afe | note | Client: Resp - Senex
bbc96eae-2f96-5921-8d72-3bf3784c2176 | note | Client: Type - CHK
a60942b2-922f-4f2e-aa20-697a2b779200 | checkpoint | 05 - Hydro mulch and Grass Seeding
3bc28e85-ff90-5cc5-81d5-630e8f3cca7b | note | Work By - Contractor
931c9acc-99e3-5a25-95a9-855a868f6292 | note | Standard / Spec - Technical Specification
188d4d5f-b834-5071-b5c2-8e1cf5fc79b5 | note | Criteria - Topsoil shall be hydro-mulched using the client-specified seed mix, approved mulch, and fertilizer applied at a rate of 150 kg per hectare.
89415185-3d7f-55f7-b0b3-fbeb6693e463 | note | Frequency - 1/Lot
43b0d2a7-6472-5f17-b604-40fb0f111c22 | note | Record - ITP, Verification Checklist/Lot drawing
89d3010c-b2a8-5ffa-a319-885bdfb13aa9 | note | Contractor: Resp - RSA
9512230f-24c5-5ff3-a3d0-680b32b31f2a | note | Contractor: Type - HP
84b01f76-2e17-51ca-a43c-025c95067188 | note | Client: Resp - Senex
cfbed164-9062-56e0-a7f4-38a724374557 | note | Client: Type - HP
84d7f7f6-afdd-45ad-95e8-5cf5f577d2a2 | signoff | HOLD POINT
cd1f4d7a-5344-49ff-8afd-88162b35cac4 | checkpoint | 06 - Watering of Topsoil
290d149d-3123-5363-9dd9-98736cae3fe5 | note | Work By - Contractor
51f5475a-cacd-5f82-a204-199febcf0034 | note | Standard / Spec - Technical Specification
40ca3303-7705-534d-8e74-492058b6265d | note | Criteria - Watering 10mm/m2 every day for first 8 days, then every second day to get to a total of 14 irrigation days.
48ff9768-16a6-5709-9346-1b4ce0a704a1 | note | Frequency - 1/Lot
ffb008b1-8b20-5977-a005-dd2c6a3a2664 | note | Record - ITP, Verification Checklist/Lot drawing
7f122c5f-4cfe-5bb2-9627-2cce85bdabc6 | note | Contractor: Resp - RSA
25516e0c-8098-5e01-afcc-032145e8577c | note | Contractor: Type - WP
f8b9a1c2-a886-5dc0-bf52-790c2e20cb6e | note | Client: Resp - Senex
0d1d34f8-56e7-550f-bc6a-2c78579dfa08 | note | Client: Type - WP
cb155f0a-fcd0-403f-a53b-51bcac2940f4 | checkpoint | 07 - Topsoil Testing
84bbef49-ac6b-59ba-963f-d277cc799cdd | note | Work By - Contractor
767ff91e-622a-55c1-b052-a45f3c3be875 | note | Standard / Spec - Technical Specification
e0293a9b-7a88-5beb-8ca0-e8690496d72e | note | Criteria - The PH of the topsoil shall be tested to confirm applicability of gypsum
38f698ff-e33d-5283-851f-d2df68cd1843 | note | Frequency - 1/Lot
9e308373-149c-55e4-8018-ae57a916eb3b | note | Record - Test Certificate
30c1004d-1a29-58fd-89f8-b2d7b0812a04 | note | Contractor: Resp - RSA
43a9e74b-238d-5b69-833d-2224447c21b5 | note | Contractor: Type - WP
663e6ff2-056a-5ee8-abbe-85ec0d6fdb73 | note | Client: Resp - Senex
f87d8f62-984b-548d-b16c-6420e6c81d8c | note | Client: Type - WP
b9bf5cac-6773-4dea-b747-f7bb7f14cd0e | checkpoint | 08 - Survey
1aabfae1-42a4-5e74-9201-5b534a4ea44f | note | Work By - Contractor
5c54a419-2736-5b73-94f2-415171c605ba | note | Standard / Spec - Technical Specification
393094ec-4793-5749-892c-78497bafba62 | note | Criteria - As-constructed survey has been completed to record the surface levels on completion. Refer to TS section 3.4
2c22424e-8f4b-56cd-a8fa-5f55f87f4c00 | note | ○ The Contractor shall submit results of each survey to the superintendent within 48hours of undertaking the Survey.
26d1fd39-9beb-54db-a80f-37a4e213c66d | note | Frequency - 1/Lot
222bb37b-2311-5a0d-a34b-c87b33fc3f18 | note | Record - ITP, Verification Checklist/Lot drawing
48d3763c-dc09-5159-b7d4-fffb9bf90c1e | note | Contractor: Resp - RSA
ecf6834e-8f37-5020-abb0-b107668ece2d | note | Contractor: Type - HP
347edd70-5e0d-5b22-8455-e4022763c9c4 | note | Client: Resp - Senex
6708a127-e086-57fe-bbde-e6af43400f95 | note | Client: Type - HP
6e5c2398-7e7a-4ca4-aabd-3368166a4ce8 | signoff | HOLD POINT
90f69c73-9a68-4f7e-a2af-bea323537414 | checkpoint | Contractor Construction Manager:
3f993bcd-98c8-441e-884c-46774ba8eeec | signoff | (Signature)
22118621-c5fc-43e4-8c81-05967137230e | checkpoint | Client Superintendent:
d2bfcb1e-c133-4bef-bb2a-9bb7a5451023 | signoff | (Signature)
ebc170a8-ad4a-4e5c-9cc6-f4641adb8c88 | checklist | Tank 2 - ITP006 - Erosion and Sediment Control - Rev1 | itp | ITP006 - Erosion and Sediment Control
030df2dd-dda1-4725-8ec3-3a97a5b7e21e | section | LOT IDENTIFICATION
d41d4f06-ec0a-4422-bd2c-4565c20fa676 | checkpoint | 01 - Lot Identification
4476f238-740d-5ca2-b581-e0cbd40c176c | note | Work By - Contractor
ec04a124-76ba-5e02-b2d5-215be8b048aa | note | Standard / Spec - Technical Specification/IFC Drawings
d2809721-38ce-5f99-9494-0260ed2959bf | note | Criteria - Location of works identified as per IFC drawings
148d60eb-81f9-5d79-8bf8-74adc2e082a6 | note | Frequency - 1/Lot
1f40b11a-3863-57c7-bc26-b9ba582b5067 | note | Record - ITP Verification Checklist/Lot drawing
d104c999-78eb-55a3-8800-9535f0d81cf0 | note | Contractor: Resp - RSA
d89833e3-7dea-55a7-a83d-461849ca5cfd | note | Contractor: Type - CHK
229ffda6-ea63-5f3d-b04b-cf28defbf001 | note | Client: Resp - Senex
3857b747-54ac-55a1-a653-c5f9d08e098e | note | Client: Type - CHK
5b8ad706-17c2-4618-8b8b-db5021b1f054 | section | TEMPORARY SEDIMENT AND EROSION CONTROL
85458d17-6098-4cad-b9d0-2d75081c3b92 | checkpoint | 02 - Clear identification and demarcation of ‘no go zones’ (where required)
34c59837-a9af-5e3d-bdc3-acce155cef68 | note | Work By - Contractor
3f521018-3487-5753-9a4d-571337209796 | note | Standard / Spec - Technical Specification/IFC Drawings
1c39c79a-f4f4-584a-b684-4a6c9e7c40f0 | note | Criteria - Remove vegetation and disturb soil only in those areas approved for construction work to occur
e288e9aa-94d0-58dc-9d0a-ff8037b46db7 | note | Frequency - 1/Lot
05e4c414-f1b6-5dee-90dd-a42ed537d48c | note | Record - ITP Verification Checklist
0b032a96-e108-5ff6-b15a-7e94938c0be7 | note | Contractor: Resp - RSA
7cf422d5-4464-58c2-9b74-f70396b86b80 | note | Contractor: Type - CHK
b9870a45-42e8-5d92-a7ad-91398300944e | note | Client: Resp - Senex
5f94a2c7-efce-5b31-9446-44eee29438f2 | note | Client: Type - CHK
7837fa6c-83f4-4b71-9c96-6a4d118592d5 | checkpoint | 03 - Installation of temporary sediment and erosion control devices
c7d05510-7be3-50bf-bae6-b9f2300b3ab7 | note | Work By - Contractor
16532c3d-4ea4-5a9c-b5e6-e7759b0f428a | note | Standard / Spec - Technical Specification/IFC Drawings
45894b19-5109-5792-9812-5e35ae6ef230 | note | Criteria - Construction of diversion bunds
68bcaac5-6d87-5b1e-9952-52a22fba721b | note | ○ Excavation of sediment catch sumps and Rumble pad
e5bb70af-da9f-5212-889c-b364f4473c8b | note | ○ Temporary approved construction tracks
4e31e7f7-3b51-5b71-9c94-37de0b0c127b | note | ○ Installation of Silt Fence
0bfab021-169d-5d1c-8382-f3d0c33b9e5f | note | Frequency - 1/Lot
aa741789-7b6f-52ac-ac9b-5dd02f591096 | note | Record - ITP Verification Checklist
cf6e231b-2a3a-553e-b30b-1803bf85f72e | note | Contractor: Resp - RSA
217d9a4d-519e-53d8-ac75-7c99d99a1753 | note | Contractor: Type - HP
cc67bcec-9cb5-5f00-8d23-d5e4820a3ca2 | note | Client: Resp - Senex
f2a89102-7e78-5c4f-b5ee-82815dd30391 | note | Client: Type - HP
f28f8aa5-5729-496f-b541-6564bc7d60e9 | signoff | HOLD POINT
4d600fd5-d913-4918-8adf-f9bd7ef617d0 | checkpoint | 04 - Sediment and erosion control device ongoing inspections
eacf251c-e2cc-5d6c-abd7-2d445636b1a3 | note | Work By - Contractor
53a4e11a-234d-5c23-a97e-94a40d5e367c | note | Standard / Spec - Technical Specification/IFC Drawings
03b23c12-2e4d-51d8-b7e7-e719f6adcf93 | note | Criteria - Inspection of sediment and erosion control devices completed to be completed at the below frequencies
1c2995c5-9f72-5aa4-a513-2da34d8dd98a | note | ○ Rain: >50mm in on day or >100mm over 4 days Prior to shift breaks
75c2fd8d-a60e-5ba5-811a-361fc813d0e6 | note | Frequency - Ongoing
a63bae2e-6ac0-5b87-98af-de8ac06b4a72 | note | Record - Environmental Routine Checklist
16332b64-5508-5378-8d12-33d22980dd6f | note | Contractor: Resp - RSA
d1cb9c2c-98b2-5f48-a5f4-bddbc5eaaefd | note | Contractor: Type - WP
2eb3f210-9dd6-562a-bf34-219d04531d33 | note | Client: Resp - Senex
6218398f-e29e-5d01-a97c-34fd10b8d756 | note | Client: Type - WP
824a0fb4-bed3-4677-b768-306589ed718a | section | PERMANENT SEDIMENT AND EROSION CONTROL – RIP RAP (ROCK PROTECTION)
f99095ab-f50c-4f3f-9b60-d5c7323ee735 | checkpoint | 05 - Underlying Lot conformance - Subgrade
6b40f29f-1657-56a2-b322-976b4f707e01 | note | Work By - Contractor
00b6afe0-2268-57c4-b884-f7f36f37a111 | note | Standard / Spec - Technical Specification/IFC Drawings
8793587e-2aa4-5592-af7a-ed8921150bb2 | note | Criteria - The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile.
c3a67946-feb8-5b61-80f6-89a442afdf2a | note | Frequency - 1/Lot
ed8d662c-5df7-585c-be68-e7b06f38a0fa | note | Record - ITP Verification Checklist
e19e91f8-afa2-50b8-a1ca-fb4728bf1b87 | note | Contractor: Resp - RSA
089730df-c0c5-57f4-b445-9c1b38a6a3d9 | note | Contractor: Type - HP
01b5be53-02a9-525b-85ad-44885e8e3cf9 | note | Client: Resp - Senex
12c9eae1-f9c0-561b-aba2-278534238fe5 | note | Client: Type - HP
747e5232-f640-444d-891a-cb0df09da4a3 | signoff | HOLD POINT
9ed192aa-6664-49af-9663-e81247655c08 | checkpoint | 06 - Conformance Separation Geotextile Material
977b424e-d8fe-522e-b34d-30b41f876ac8 | note | Work By - Contractor
6eb693b8-6ec4-5b05-8549-b5925e339cf5 | note | Standard / Spec - Technical Specification/IFC Drawings
d6fff19e-2898-5dfb-88a3-5ad81252a10c | note | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data Certificates.
8b3ff40e-c593-5a3c-99e0-126953c73188 | note | Frequency - 1/Lot
0f49f060-f020-5cf9-b64e-9ad20288b459 | note | Record - ITP Verification Checklist
8077be90-7aa6-51d5-a880-dc487629ead5 | note | Contractor: Resp - RSA
99807881-14dc-5f26-9b6a-a4e0fa310a49 | note | Contractor: Type - HP
4b17b208-bcb4-5280-ae5a-42aa7e0f5f53 | note | Client: Resp - Senex
7ccc1022-a709-59fa-a1af-8bb786dbfa14 | note | Client: Type - HP
f10f6665-55b1-40c9-8809-3c51b44629a9 | signoff | HOLD POINT
c30e7784-52ac-4814-9a39-a9468f123b27 | checkpoint | 07 - Conformance Rip Rap
55cdebf8-d51c-58c7-80fd-6ad522c04d86 | note | Work By - Contractor
6179fe2c-a9eb-5bff-beb1-9ab4f378a43f | note | Standard / Spec - Technical Specification/IFC Drawings
f72cea1c-f100-5a10-bbb8-1fafa00462db | note | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates.
871095d3-536a-51da-96ac-437eeb7aa462 | note | Frequency - 1/Lot
985ca12f-cbc4-545e-acda-22b5ab26ff8c | note | Record - ITP Verification Checklist
2bddfdf7-a321-5dd9-880b-623f78c00095 | note | Contractor: Resp - RSA
9884e429-ed83-5219-96e1-b2ac5f837ae7 | note | Contractor: Type - HP
f7f27525-5a4a-50a6-bef8-32efe9890cf8 | note | Client: Resp - Senex
104a5066-9c14-5474-a591-a4e7474645b8 | note | Client: Type - HP
d0d3f3b9-674d-4131-80fc-6ed09a48c364 | signoff | HOLD POINT
32c7f469-4808-446a-93af-97bd704359cc | checkpoint | 08 - Separation geotextile placement
f68e8836-ff20-5e29-8528-cf6bf1fc68d6 | note | Work By - Contractor
6f11bef6-e9ba-561a-b952-73ecc446b4d3 | note | Standard / Spec - Technical Specification/IFC Drawings
e786f276-91cb-5a5a-a489-62052be10b16 | note | Criteria - Installation method complies with the requirements of the technical specification and the IFC drawings. Laps to geotextiles shall be a minimum 0.6m. The Superintendent shall inspect subgrade and the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers.
934d7b3d-2338-5fd7-beff-2a8867b7a712 | note | Frequency - 1/Lot
e76e43ba-cea6-5d63-9d8c-f73624fd3feb | note | Record - ITP Verification Checklist
ac1e0448-6502-5ac3-a233-4be93b29c3b1 | note | Contractor: Resp - RSA
4ea61e8f-8e52-54ea-897f-9e7800aee3ba | note | Contractor: Type - HP
796f729a-ca62-5e39-9925-59c527dc43b3 | note | Client: Resp - Senex
e1717d59-536b-5c8f-b05f-0b9d11daff3f | note | Client: Type - HP
beae2495-46ae-4f72-bf26-a83c36886630 | signoff | HOLD POINT
f75c6003-84cf-46b8-88bc-1dd33a6cd613 | checkpoint | 09 - Rip Rap Placement
5fe34c82-3090-589e-a573-b27685677daa | note | Work By - Contractor
b6023391-5fc3-57a5-a5e0-6ff30f0ec946 | note | Standard / Spec - Technical Specification/IFC Drawings
89740eba-14a3-5e3b-be7c-9372480bdea0 | note | Criteria - The contractor shall provide a Work Method Statement for the placement of Rip Rap.
e65160fa-b13d-5ef9-b926-23cc5b66f2b1 | note | ○ Rip rap shall be place in a manner which does not damage the underlying geotextile
9e1e16ed-2945-5864-8b41-7ce0ccc3246b | note | ○ Rock finished smoothed to the final lines and levels.
41d2dcee-e6f1-5e03-91ce-3df191e30436 | note | Frequency - 1/Lot
73b4d688-dcfd-57c2-9377-076459c844cc | note | Record - ITP Verification Checklist
c79efc1c-7a37-58d5-8834-9f76a6621a09 | note | Contractor: Resp - RSA
79801241-0ca9-59a0-8cd3-367c0fd1d90f | note | Contractor: Type - CHK
cc99db8b-23ec-5c83-8a94-90dd3abb5294 | note | Client: Resp - Senex
42a7bf00-47f2-5b97-8308-680d8db10e32 | note | Client: Type - HP
318ed64e-9d16-4684-bbee-eb29553b9b98 | signoff | HOLD POINT
0e556361-3e6f-443c-85b1-1a02eeef8c8e | checkpoint | 10 - Acceptance of works (Rip rap)
a0438526-0ff6-576b-bbf8-9735624cefeb | note | Work By - Contractor
bee7ad7f-17f6-5fc3-bfa6-d09223e1b963 | note | Standard / Spec - Technical Specification/IFC Drawings
3f1541c1-c339-5e1e-9680-f50643c100c0 | note | Criteria - The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works.
99fafa24-39f1-5dfa-9aa6-eafedd3e15de | note | Frequency - 1/Lot
9cd388d2-967c-5e90-8db9-c113d1fb464e | note | Record - ITP Verification Checklist / MDR
f96707d6-357e-55b2-bf48-9d9cc0e0ea92 | note | Contractor: Resp - RSA
759b84f1-b493-5017-bd38-69401c79a5c6 | note | Contractor: Type - CHK
58145695-494e-5c7c-a9c2-876145effa6f | note | Client: Resp - Senex
d1336fa7-0977-5b02-97ee-ca89f119278c | note | Client: Type - HP
7df79827-3433-414c-b97a-a5c4daf7b049 | signoff | HOLD POINT
cd1898e9-6712-4958-991f-90b32e6bc848 | checkpoint | Contractor Construction Manager:
65832b9d-b1f8-49ab-bdcc-00a35f3fec4d | signoff | (Signature)
fa1aa36f-c9d5-41f7-a703-c28c82d4769d | checkpoint | Client Superintendent:
00a51017-d3e7-45c5-83a9-81bc087ea965 | signoff | (Signature)
18012d9d-f0e2-4fb6-a581-69fe8d1e0d8c | checklist | Tank 2 - ITP007 - Leak Detection System - Rev0 | itp | ITP007 - Leak Detection System
a4775600-b4dd-44d6-aaa6-b389d262df03 | section | LEAK DETECTION SYSTEM
850d5623-2c52-4655-b242-fd09abf3a743 | checkpoint | 01 - Lot Identification
9e9a6527-c969-5cc7-a484-b095344933b5 | note | Work By - Contractor
c34be951-0579-5b4c-9ecc-fb24aa7899ea | note | Standard / Spec - Technical Specification/IFC Drawings
f64c4c68-6d1a-5be8-aa57-d22e4783ec88 | note | Criteria - Location of works identified as per IFC drawings
63d516b5-fcd3-5a0b-a681-28b6639a9770 | note | Frequency - 1/Lot
4f5baec2-509a-5dda-8c6f-f609e7034939 | note | Record - ITP, Verification Checklist/Lot drawing
e3049595-4bf5-5118-ad73-7152662c5d19 | note | Contractor: Resp - RSA
9bb3c765-5ad4-59aa-94f7-1fb57e067b9c | note | Contractor: Type - CHK
8a1bb13d-0cf4-5b5f-9c43-dadab7077ec5 | note | Client: Resp - Senex
c32164fd-7e41-5d40-be06-3d12b9fd6bd7 | note | Client: Type - CHK
f42bbd9c-30ae-4877-9903-ea20e03f74b4 | checkpoint | 02 - Survey control and Setout
3932513d-896c-5c0f-a1b7-221efd8a9cb1 | note | Work By - Contractor
ebd1e1dc-c535-5998-b8e1-c006f94ebc1d | note | Standard / Spec - Technical Specification/IFC Drawings
117666b1-771e-5704-a727-4bb97f7007d7 | note | Criteria - Confirm centres of both sump and tank locations
3db35542-8120-5adf-a8e7-6e91cf063121 | note | Frequency - 1/Lot
14b29088-e0f8-5531-b9f1-0c0f51d1b44e | note | Record - ITP, Verification Checklist
7ec6774f-86b4-5f65-bf44-1cad9582e0a0 | note | Contractor: Resp - RSA
de3c4efb-826d-5bbf-bc09-5f307e4a94d6 | note | Contractor: Type - HP
70405fd9-930c-5859-9de6-f86621936fa2 | note | Client: Resp - Senex
37b3198a-215f-5104-9746-50d1c6732358 | note | Client: Type - HP
281ed643-a10b-4ac3-9741-ec14de68c995 | signoff | HOLD POINT
7c1d495c-c94d-471a-9fb1-915c04338b21 | checkpoint | 03 - Excavation of sump
eac5496c-2848-57c6-ab3e-d75909353d5f | note | Work By - Contractor
c3b2151f-8bdd-5612-b675-201002fa5550 | note | Standard / Spec - Technical Specification/IFC Drawings
9fc6f795-910f-515a-b9a3-7aed20fdeaca | note | Criteria - Located at 3m outside from the hinge point of the tank pad. To be trenched to a depth of 3.17 m (to be confirmed on site)
f0288708-718a-570d-9e56-0470064a41b7 | note | ○ Sump excavated to correct dimensions in line with Concept Tanks 0.8m diameter excavation to design depth. Sump pit depth to be determined onsite ensuring sufficient fall from tank centre to sump
00a28ddf-5ae2-5b36-babc-4aad625c9024 | note | Frequency - 1/Lot
1719a825-2f61-5797-9778-4acca0a7a27d | note | Record - ITP, Verification Checklist
917840c5-87fc-5d66-af96-776f539ed8d1 | note | Contractor: Resp - RSA
8befa95a-b3dc-5b11-b1d9-36dce70779d9 | note | Contractor: Type - CHK
839726a6-8d52-5287-a763-4e3e00592a2b | note | Client: Resp - Senex
31f1637e-fcd4-5502-b51f-71668f955195 | note | Client: Type - WP
293cb8f2-071d-4a5d-b81d-6f198865e1ba | checkpoint | 04 - Installation of HDPE sump base and chamber at correct height and level
c7af1349-6376-565f-9911-82fa7c873b65 | note | Work By - Contractor
304acbc2-bd34-55ad-abef-0ce3fdef8a4e | note | Standard / Spec - Technical Specification/IFC Drawings
a0500f10-f383-5a64-86b2-6df9d2d195e2 | note | Criteria - Poly sump base to be installed at 200mm below leak detection pipe.
1a9c07cd-f836-50b9-adda-ae7fb993c32c | note | ○ Sump chamber installed plumb to correct height minimum 150mm above top of tank
ba25e3bc-ab11-524c-8393-c455112d903d | note | Frequency - 1/Lot
669d43e6-1b3e-55d0-9ecc-82baf9199fb5 | note | Record - ITP, Verification Checklist
f6148f06-7df3-5829-8b8a-e7938e4b431a | note | Contractor: Resp - RSA
f157e5f3-2349-554f-8c60-e9d352143f36 | note | Contractor: Type - CHK
bd382bb5-05bc-5a29-a311-77c9f4590cdb | note | Client: Resp - Senex
66eb8df2-49d6-517b-a5c6-05ac212e7ce1 | note | Client: Type - WP
8be98b66-3d7e-4901-9708-a2f1630ac3ed | checkpoint | 05 - Backfill - Sump
4ce81f33-5be0-59a8-8257-14a621f92083 | note | Work By - Contractor
022668df-8cd0-5355-9adb-874a0251b74e | note | Standard / Spec - Technical Specification/IFC Drawings
a750d772-82a2-5358-82d9-fad8cece312c | note | Criteria - Backfill in accordance with CT requirements. Compaction testing in line with Earthworks specification
f3544794-c892-521f-b8af-1086be2401c4 | note | Frequency - 1/Lot
a1a762fe-b644-5ee8-b107-b8f6b1ef0f84 | note | Record - ITP, Verification Checklist / Test
1d8015a8-1fe8-5340-9080-330c40b894a1 | note | Contractor: Resp - RSA
2f3f5303-bcd2-5162-9ba5-3b12fac8c453 | note | Contractor: Type - CHK
7b4a46b9-4c54-5084-840d-676204d0e9a4 | note | Client: Resp - Senex
2fc5fcd7-6216-5144-a669-2bf11fc30c1d | note | Client: Type - HP
2ee7de77-9e4f-4c73-aebe-89ef9b3b3315 | signoff | HOLD POINT
900a27b3-516f-43a7-81c1-1dcef4892d3f | checkpoint | 06 - Leakage pipe trench excavation
3a0ddbc0-f071-5f3e-8e1c-0b1528ae80ba | note | Work By - Contractor
63446989-1d00-5b28-bfd6-80af09bb0686 | note | Standard / Spec - Technical Specification/IFC Drawings
76257d13-2b2b-5342-b60c-35c4c7a51351 | note | Criteria - Trench excavated to correct lines and levels in line with CES drawings.
d78786a6-71a7-57f2-bc65-4c25d358f2ee | note | ○ 1:100 fall to sump
e8ee835b-6e2b-594e-93f4-8cf0f9cef976 | note | ○ Sufficient excavation width to facilitate installation.
d4b46464-51d9-5279-b824-962ea25a9cdf | note | Frequency - 1/Lot
272cd61c-94ca-57e1-91b1-d44f3921dd4a | note | Record - ITP, Verification Checklist
d34058ef-1c14-5afd-8aab-c79b6ad0b79c | note | Contractor: Resp - RSA
cbff2e98-ea94-5ec2-a620-e2f7f11fa9f8 | note | Contractor: Type - CHK
81d2d5cc-3f6d-5522-b7c6-714aaa0cc586 | note | Client: Resp - Senex
b0eacc72-d502-5d1d-b933-0bb00667f3e7 | note | Client: Type - WP
57e9300f-279e-4826-870e-2f62d3a9e562 | checkpoint | 07 - Installation of 50mm HDPE leakage pipe
672bfc5b-4c9d-588a-a2fe-8bfa8baea6d2 | note | Work By - Contractor
fb10706f-3240-593c-b0c7-8fbf6fa3433f | note | Standard / Spec - Technical Specification/IFC Drawings
d978db06-211f-5f53-a937-c07589ec1476 | note | Criteria - 50mm HDPE pipe and bends installed in accordance with CT and manufacturer requirements.
61de4f2f-5670-583d-b66f-c793f7b38939 | note | ○ Minimum 150mm cover at centre of tank Pipe installed on 50mm sand bedding (optional) as per CT recommendations
69ea94df-0f2a-563b-ac60-0a90ee979f9f | note | ○ HDPE pipe riser installed 300mm above FSL at centre of tank, temporary seal to prevent sediment ingress.
2ca6dee2-bcf6-56e8-97a5-791a70408478 | note | ○ Pipe to be left exposed at centre of sump pit
a5fb6576-31fb-5c63-ba8b-5a75c4b6c2d4 | note | Frequency - 1/Lot
985f02f4-3f80-5ba7-971d-d979900d3448 | note | Record - ITP, Verification Checklist
2dab5e45-156a-5f09-b69f-34a439ec10a6 | note | Contractor: Resp - RSA
7a413826-b8c3-5143-a101-5c71d4da10c8 | note | Contractor: Type - CHK
9fb92c16-f7d7-5013-bf1d-0015e99525a1 | note | Client: Resp - Senex
702cdd10-7b9e-5f4b-954e-a547d003faca | note | Client: Type - WP
3f1554ed-4315-4ce2-a2b3-4a78e5588a21 | checkpoint | 08 - Surface Water Runoff
8619a8b6-f08d-5bb7-b909-240c98484c1a | note | Work By - Contractor
59caad6a-3278-5cb2-85af-01afd1470a7c | note | Standard / Spec - Technical Specification/IFC Drawings
39d504c6-2f0c-5f07-95b3-3d40bd9f7060 | note | Criteria - DN110 HDPE pipe for construction surface water runoff to be installed 1:100 fall to swale drain
3b1015bd-2ae5-54a7-bad3-a105195a97cc | note | Frequency - 1/Lot
8f0b3748-05e7-5ca5-a510-30463af19e00 | note | Record - ITP, Verification Checklist
dc5ee0bf-687e-5475-9cbd-f1d0586f06e6 | note | Contractor: Resp - RSA
8451cb0d-315e-5999-b544-395a884f337b | note | Contractor: Type - CHK
f7fed71a-6d79-5572-8330-ef5103fc66eb | note | Client: Resp - Senex
37dccdd1-ca5d-58ca-82ff-d9701d74a113 | note | Client: Type - WP
9c48957b-6a92-484f-a365-772d1412ef60 | checkpoint | 09 - Backfill - Trench
4888c603-d4fd-5835-8e3b-7d73b0de33a0 | note | Work By - Contractor
0bb9e024-1bf9-555d-b07c-de314891acb5 | note | Standard / Spec - Technical Specification/IFC Drawings
2fe012f5-45b5-5a7c-aa95-3a83ea7399b1 | note | Criteria - Backfill in accordance with CES requirements and general earthworks specifications
29fc4d65-50c3-5dc9-b15b-5fe9f7cc1e36 | note | ○ 98% +/-2% moisture (Ring beam area) 96% +/-2% moisture (All other areas)
7a03e4f7-b3b9-5cdc-89b3-13528e7497f2 | note | Frequency - Min 2 tests per lot
684573df-96e6-55fd-b42a-d31c03f413dd | note | Record - ITP, Verification Checklist / Test Report
b26a4fa7-5dcc-561b-8807-85143a55db96 | note | Contractor: Resp - RSA
a7e7d47d-2e7a-56a3-a90b-a7d9339c9f22 | note | Contractor: Type - CHK
ca14f033-138d-5596-9d98-c82da3171d9c | note | Client: Resp - Senex
f32f71c2-7dcd-5c6e-a364-2868d9550ef7 | note | Client: Type - WP
f6dd278a-dea7-4e89-82ad-7a9fa4ffbe57 | checkpoint | 10 - Acceptance of work
5727ea50-36cb-53b6-9106-a676ccdf8fa6 | note | Work By - Contractor
87c0830a-fc24-5a2b-b1eb-237f1f583358 | note | Standard / Spec - Technical Specification/IFC Drawings
2ee7c280-054b-57d4-ad0f-e5be6c385cc2 | note | Criteria - Work completed in accordance with CES requirements.
57835859-75e5-50f4-83bf-dc9dd7bb7d77 | note | ○ Compaction reports received and meeting specification
7efa6c10-a996-5c5c-9f78-d9d8ca2721f7 | note | ○ As-constructed survey data obtained
415d1faf-2cc9-5fb5-b1e9-7a461e1e20cb | note | Frequency - Once per lot
139defcd-aa3d-5092-8a62-934629d4a946 | note | Record - ITP, Verification Checklist
a5f94677-7634-5846-bddd-f1f1c0ed3902 | note | Contractor: Resp - RSA
845f0241-ecd4-5bee-919c-75ff8fa67871 | note | Contractor: Type - CHK
509e6745-1b45-54c7-9841-a33598ae3039 | note | Client: Resp - Senex
a8c0efc9-5026-571d-97e0-d1f9fc759428 | note | Client: Type - HP
9a70b1dc-8d72-4bb3-9827-28fc637ed38c | signoff | HOLD POINT
7d4c2e61-5433-4b67-9c89-72a1919d8e7b | checkpoint | Contractor Construction Manager:
a4928129-7f6f-4e67-bc9f-48c94ebbb49e | signoff | (Signature)
64424a3c-f4af-4813-8c5b-a1306617f38a | checkpoint | Client Superintendent:
df697d6b-6c70-41c0-9bfc-8a8c9b56b913 | signoff | (Signature)