## Sheet1
01 | Lot Identification | Contractor | Technical Specification/IFC Drawings | Location of works identified as per IFC drawings | 1/Lot | ITP Verification Checklist/Lot drawing | RSA | CHK | Senex | CHK | 01 - Lot Identification | Work By - Contractor | Standard / Spec - Technical Specification/IFC Drawings | Criteria - Location of works identified as per IFC drawings | Frequency - 1/Lot | Record - ITP Verification Checklist/Lot drawing | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - CHK | 01 - Lot Identification
02 | Clear identification and demarcation of ‘no go zones’ (where required) | Contractor | Technical Specification/IFC Drawings | Remove vegetation and disturb soil only in those areas approved for construction work to occur | 1/Lot | ITP Verification Checklist | RSA | CHK | Senex | CHK | 02 - Clear identification and demarcation of ‘no go zones’ (where required) | Work By - Contractor | Standard / Spec - Technical Specification/IFC Drawings | Criteria - Remove vegetation and disturb soil only in those areas approved for construction work to occur | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - CHK | Work By - Contractor
03 | Installation of temporary sediment and erosion control devices | Contractor | Technical Specification/IFC Drawings |  Construction of diversion bunds  Excavation of sediment catch sumps and Rumble pad  Temporary approved construction tracks  Installation of Silt Fence | 1/Lot | ITP Verification Checklist | RSA | HP | Senex | HP | 03 - Installation of temporary sediment and erosion control devices | Work By - Contractor | Standard / Spec - Technical Specification/IFC Drawings | Criteria -  Construction of diversion bunds  Excavation of sediment catch sumps and Rumble pad  Temporary approved construction tracks  Installation of Silt Fence | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - HP | Client: Resp - Senex | Client: Type - HP | Standard / Spec - Technical Specification/IFC Drawings
04 | Sediment and erosion control device ongoing inspections | Contractor | Technical Specification/IFC Drawings | Inspection of sediment and erosion control devices completed to be completed at the below frequencies Rain: >50mm in on day or >100mm over 4 days Prior to shift breaks | Ongoing | Environmental Routine Checklist | RSA | WP | Senex | WP | 04 - Sediment and erosion control device ongoing inspections | Work By - Contractor | Standard / Spec - Technical Specification/IFC Drawings | Criteria - Inspection of sediment and erosion control devices completed to be completed at the below frequencies Rain: >50mm in on day or >100mm over 4 days Prior to shift breaks | Frequency - Ongoing | Record - Environmental Routine Checklist | Contractor: Resp - RSA | Contractor: Type - WP | Client: Resp - Senex | Client: Type - WP | Criteria - Location of works identified as per IFC drawings
05 | Underlying Lot conformance - Subgrade | Contractor | Technical Specification/IFC Drawings | The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile. | 1/Lot | ITP Verification Checklist | RSA | HP | Senex | HP | 05 - Underlying Lot conformance - Subgrade | Work By - Contractor | Standard / Spec - Technical Specification/IFC Drawings | Criteria - The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile. | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - HP | Client: Resp - Senex | Client: Type - HP | Frequency - 1/Lot
06 | Conformance Separation Geotextile Material | Contractor | Technical Specification/IFC Drawings | The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data Certificates. | 1/Lot | ITP Verification Checklist | RSA | HP | Senex | HP | 06 - Conformance Separation Geotextile Material | Work By - Contractor | Standard / Spec - Technical Specification/IFC Drawings | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data Certificates. | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - HP | Client: Resp - Senex | Client: Type - HP | Record - ITP Verification Checklist/Lot drawing
07 | Conformance Rip Rap | Contractor | Technical Specification/IFC Drawings | The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates. | 1/Lot | ITP Verification Checklist | RSA | HP | Senex | HP | 07 - Conformance Rip Rap | Work By - Contractor | Standard / Spec - Technical Specification/IFC Drawings | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates. | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - HP | Client: Resp - Senex | Client: Type - HP | Contractor: Resp - RSA
08 | Separation geotextile placement | Contractor | Technical Specification/IFC Drawings | Installation method complies with the requirements of the technical specification and the IFC drawings. Laps to geotextiles shall be a minimum 0.6m. The Superintendent shall inspect subgrade and the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers. | 1/Lot | ITP Verification Checklist | RSA | HP | Senex | HP | 08 - Separation geotextile placement | Work By - Contractor | Standard / Spec - Technical Specification/IFC Drawings | Criteria - Installation method complies with the requirements of the technical specification and the IFC drawings. Laps to geotextiles shall be a minimum 0.6m. The Superintendent shall inspect subgrade and the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers. | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - HP | Client: Resp - Senex | Client: Type - HP | Contractor: Type - CHK
09 | Rip Rap Placement | Contractor | Technical Specification/IFC Drawings | The contractor shall provide a Work Method Statement for the placement of Rip Rap. Rip rap shall be place in a manner which does not damage the underlying geotextile Rock finished smoothed to the final lines and levels. | 1/Lot | ITP Verification Checklist | RSA | CHK | Senex | HP | 09 - Rip Rap Placement | Work By - Contractor | Standard / Spec - Technical Specification/IFC Drawings | Criteria - The contractor shall provide a Work Method Statement for the placement of Rip Rap. Rip rap shall be place in a manner which does not damage the underlying geotextile Rock finished smoothed to the final lines and levels. | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - HP | Client: Resp - Senex
10 | Acceptance of works (Rip rap) | Contractor | Technical Specification/IFC Drawings | The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works. | 1/Lot | ITP Verification Checklist / MDR | RSA | CHK | Senex | HP | 10 - Acceptance of works (Rip rap) | Work By - Contractor | Standard / Spec - Technical Specification/IFC Drawings | Criteria - The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works. | Frequency - 1/Lot | Record - ITP Verification Checklist / MDR | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - HP | Client: Type - CHK
02 - Clear identification and demarcation of ‘no go zones’ (where required)
Work By - Contractor
Standard / Spec - Technical Specification/IFC Drawings
Criteria - Remove vegetation and disturb soil only in those areas approved for construction work to occur
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - CHK
Client: Resp - Senex
Client: Type - CHK
03 - Installation of temporary sediment and erosion control devices
Work By - Contractor
Standard / Spec - Technical Specification/IFC Drawings
Criteria -  Construction of diversion bunds  Excavation of sediment catch sumps and Rumble pad  Temporary approved construction tracks  Installation of Silt Fence
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - HP
Client: Resp - Senex
Client: Type - HP
04 - Sediment and erosion control device ongoing inspections
Work By - Contractor
Standard / Spec - Technical Specification/IFC Drawings
Criteria - Inspection of sediment and erosion control devices completed to be completed at the below frequencies Rain: >50mm in on day or >100mm over 4 days Prior to shift breaks
Frequency - Ongoing
Record - Environmental Routine Checklist
Contractor: Resp - RSA
Contractor: Type - WP
Client: Resp - Senex
Client: Type - WP
05 - Underlying Lot conformance - Subgrade
Work By - Contractor
Standard / Spec - Technical Specification/IFC Drawings
Criteria - The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile.
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - HP
Client: Resp - Senex
Client: Type - HP
06 - Conformance Separation Geotextile Material
Work By - Contractor
Standard / Spec - Technical Specification/IFC Drawings
Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data Certificates.
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - HP
Client: Resp - Senex
Client: Type - HP
07 - Conformance Rip Rap
Work By - Contractor
Standard / Spec - Technical Specification/IFC Drawings
Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates.
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - HP
Client: Resp - Senex
Client: Type - HP
08 - Separation geotextile placement
Work By - Contractor
Standard / Spec - Technical Specification/IFC Drawings
Criteria - Installation method complies with the requirements of the technical specification and the IFC drawings. Laps to geotextiles shall be a minimum 0.6m. The Superintendent shall inspect subgrade and the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers.
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - HP
Client: Resp - Senex
Client: Type - HP
09 - Rip Rap Placement
Work By - Contractor
Standard / Spec - Technical Specification/IFC Drawings
Criteria - The contractor shall provide a Work Method Statement for the placement of Rip Rap. Rip rap shall be place in a manner which does not damage the underlying geotextile Rock finished smoothed to the final lines and levels.
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - CHK
Client: Resp - Senex
Client: Type - HP
10 - Acceptance of works (Rip rap)
Work By - Contractor
Standard / Spec - Technical Specification/IFC Drawings
Criteria - The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works.
Frequency - 1/Lot
Record - ITP Verification Checklist / MDR
Contractor: Resp - RSA
Contractor: Type - CHK
Client: Resp - Senex
Client: Type - HP