## Table 1
Jensen Steel Fabricators Limited |  | OPERATING PROCEDURES SITE | [6 empty] | OPE 009 |  |  | Rev:0
QMS - E |  | Inspection and Test Plan - Erection (ITP-E) | [6 empty] | Approved: LT |  |  | Date: 11.03.2024
Project | ESM #: |  |  | Engineer |  |  | Client |  |  |  | Prepared by: Approved by:
Abbrevia�ons | C = Client, CNC = client nominated consultant, F = Fabricator, I = Client Nominated Inspector
Control categories | H= Hold Point, I= Inspect, W= Witness, R= Review, S= Survey, A = Approve
DESCRIPTION | CONTROL |  | ACCEPTANCE CRITERIA |  | QMS Ref | RESPONSIBILITY |  | ESM/STAGE/Frequency |  | RECORDS/REPORTS |  |  | Inspected by: signature & date
Risk assessment | H |  | AS/NZS 5131 11.2.4 |  | OPE 004 |  |  |  |  | Site Safety Plan |  |  | F | C/I
Erection design (stability check) | H |  | 11.4 |  | OPE 007 | Site Supervisor |  | All
Site survey | S |  | 11.3 |  | OPE 007 / OPE 017 | Site Operations Manager, Site Supervisor/ Independent Surveyor |  |  |  | Record
Delivery and storage | I |  | 2011-05-06 |  | OPE 007, OPE 008 | Site Supervisor
Temporary erection | R |  | 2010-11-05 |  | OPE 007 / OPE 018
Permanent supports | H, S, I |  | 2011-06-01 |  | OPE 007 / OPE 018 |  |  |  |  | Report
Temporary supports, props – doc survey and inspection report | S, R |  | 11.5.2, 3 11.6 |  | OPE 007 / OPE 018 / OPE 011 |  |  |  |  | Report
Installation of bolted connections - Snug tightening (S) | I |  | 8.3, 8.5.1, 13.7 |  | OPE 008 / OPE 011-5 / OPE 023 | Bolting Supervisor |  |  |  | Report
Tensioning of bolted connections – Bearing Type (TB) | I |  | 8.3, 8.5.1, 13.7 |  | OPE 008 / OPE 011-5 / OPE 023 | Bolting Supervisor |  |  |  | Report
Tensioning of bolted connections – Friction Type (TF) | I |  | 8.4.2, 13.7 |  | OPE 008 / OPE 011-5 / OPE 023 | Bolting Supervisor |  |  |  | Report
Mechanical and chemical anchors | I |  | 8.8.3 |  | OPE 008 / OPE 023/ OPE 011 | Site Supervisor |  |  |  | Report
Thin gauge components | I |  | 8.6 |  | OPE 008 / OPE 023/ OPE 011 | Site Supervisor |  |  |  | Report
Removal of braces, props, frames etc. | H, A |  | 2011-05-05 |  | OPE 008 / OPE 011 | Site Operations Manager / Site Supervisor |  |  |  | Record
Site welding | I |  | 7 |  | OPE 008 / OPE 017 | Site Supervisor
Erection and Assembly tolerances | I |  | 13.4 Appendix F |  | OPE 008 / OPE 011 / OPE 017 | Site Supervisor |  |  |  | Report
Repairs to painted surfaces | I |  | 9.12 |  | OPE 017 | Site Supervisor |  |  |  | Report
Completion Final inspection | I |  | 13.11 |  | OPE 011 | Site Supervisor / Client / Quality Manger |  |  |  | Report
Completed QA documentation | I |  | Client’s speciﬁcation |  | OPE 015, OPE 011 | Quality Manager |  |  |  | Report
Final sign oﬀ | P