## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | OP021 ITP - Materials, Assembly, Welding, Inspection and Testing, NDT, Protective Coatings and Erection Documentation | itp |  |  |  |  | Add OP021 ITP - Materials, Assembly, Welding, Inspection and Testing, NDT, Protective Coatings and Erection Documentation Rev 6
section | 1.0 PRE-INSPECTION MEETING
checkpoint | 1.1 Shop drawing review
label | Inspection Activity: R - x
label | Inspected by - C
label | Acceptance Criteria: Reference Standard - Project specification
label | Verifying Document - Shop drawings approved for Construction by Engineer
label | Surveillance Inspection: Jensen - S
label | Surveillance Inspection: Client - H/A
holdpoint | HOLD POINT
checkpoint | 1.2 Discuss the implementation of the quality requirement and to ensure that all requirements of Contract are understood
label | Inspection Activity: R - x
label | Inspected by - C
label | Acceptance Criteria: Reference Standard - Project Specification
label | Verifying Document - QAP, ITP Accepted by Client
label | Surveillance Inspection: Client - H/A
holdpoint | HOLD POINT
section | 2.0 PROCEDURE AND DOCUMENTS
checkpoint | 2.1 Review/Approve quality assurance plan
label | Inspection Activity: R - x
label | Inspected by - DE
label | Acceptance Criteria: Reference Standard - AS/NZS 5131
label | Verifying Document - QAP
label | Surveillance Inspection: Client - H/A
holdpoint | HOLD POINT
checkpoint | 2.2 Review/Approve welding plan
label | Inspection Activity: R - x
label | Inspected by - DE
label | Acceptance Criteria: Reference Standard - AS/NZS 5131
label | Verifying Document - OP030
label | Surveillance Inspection: Client - H/A
holdpoint | HOLD POINT
checkpoint | 2.3 Review/Approve WPS, PQR
label | Inspection Activity: R - x
label | Inspected by - DE
label | Acceptance Criteria: Reference Standard - AS/NZS1554.1
label | Verifying Document - WPS
label | Surveillance Inspection: Client - H/A
holdpoint | HOLD POINT
checkpoint | 2.4 Review/Approve Welder qualification test records
label | Inspection Activity: R - x
label | Inspected by - DE
label | Acceptance Criteria: Reference Standard - AS/NZS2980 / ISO 9606.1
label | Verifying Document - PQR
label | Surveillance Inspection: Client - H/A
holdpoint | HOLD POINT
checkpoint | 2.5 Review/Approve NDE personnel certificate
label | Inspection Activity: R - x
label | Inspected by - DE
label | Acceptance Criteria: Reference Standard - AS/NZS 5131
label | Verifying Document - AS2214 Welding Supervisor Certificates, CBIP Website
label | Surveillance Inspection: Client - H/A
holdpoint | HOLD POINT
checkpoint | 2.6 Paint System Approval
label | Inspection Activity: R - x
label | Inspected by - DE
label | Acceptance Criteria: Reference Standard - AS/NZS 2312
label | Surveillance Inspection: Jensen - H
label | Surveillance Inspection: Client - R
holdpoint | HOLD POINT
section | 3.0 MATERIALS
checkpoint | 3.1 Verify mill certificate and heat marking records both physical marking of material and traceability database record
label | Inspection Activity: D - x
label | Inspection Activity: R - x
label | Inspected by - QAM
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 5
label | Acceptance Criteria: Reference Standard - AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600
label | Verifying Document - Mill certificates, cutting schedule sheets
label | Surveillance Inspection: Frequency - Monthly
label | Surveillance Inspection: Jensen - H
holdpoint | HOLD POINT
checkpoint | 3.2 Inspect all material for any damage
label | Inspection Activity: V - x
label | Inspected by - QAM
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600
label | Verifying Document - Mill certificates, cutting schedule sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - H
holdpoint | HOLD POINT
checkpoint | 3.3 Review mill certificate in accordance with the requirements of project specifications
label | Inspection Activity: R - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600
label | Verifying Document - Mill certificates
label | Surveillance Inspection: Frequency - Monthly
label | Surveillance Inspection: Jensen - H
label | Surveillance Inspection: Client - R
label | Surveillance Inspection: Owner - R
holdpoint | HOLD POINT
checkpoint | 3.4 Review hardware certificate (Bolt, Nut and Washer) meet specification ( for Grade 8.8 UNO)
label | Inspection Activity: R - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - AS/NZS 1252 / AS/NZS 1214
label | Verifying Document - Mill certificates
label | Surveillance Inspection: Frequency - Monthly
label | Surveillance Inspection: Jensen - H
label | Surveillance Inspection: Client - R
holdpoint | HOLD POINT
section | 4.0 MATERIAL PREPARATION
checkpoint | 4.1 Check identification marking on work piece for material traceability
label | Inspection Activity: V - x
label | Inspected by - QAM/FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
label | Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
checkpoint | 4.2 Check edge preparation in accordance with shop drawing and WPS
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
label | Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
checkpoint | 4.3 Check surface cutting profile/ gas notch
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
label | Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
checkpoint | 4.4 Machined and sheared edge preparations and drilled hole shall be debarred
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
label | Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
section | 5.0 ASSEMBLY
checkpoint | 5.1 Check overall pre-weld dimension
label | Inspection Activity: D - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS
label | Verifying Document - Shop drawings, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 5.2 Check weld joint cleanliness
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS
label | Verifying Document - Shop drawings, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 5.3 Arc strikes outside the area of permanent weld shall be ground smooth and visually inspected
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS
label | Verifying Document - Shop drawings, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 5.4 Run-off tabs/Backing bar shall be used on all SAW process
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS
label | Verifying Document - Shop drawings, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
section | 6.0 WELDING
checkpoint | 6.1 Check welder qualification and validity
label | Inspection Activity: R - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
label | Verifying Document - WPS, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 6.2 Monitor electrode storage & usage (1)
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
label | Verifying Document - WPS, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 6.2 Monitor electrode storage & usage (2)
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - Shipping class 3YS minimum
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
label | Verifying Document - WPS, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 6.3 Monitor preheating as per WPS
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
label | Verifying Document - WPS, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 6.4 Monitor welding sequence, parameter, Interpass temperature
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
label | Verifying Document - WPS, Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
section | 7.0 POST WELD INSPECTION
checkpoint | 7.1 Check weld profile/ weld contour is in accordance with specification
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
label | Verifying Document - Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 7.2 Check weld leg, size and length is in accordance with drawing
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
label | Verifying Document - Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 7.3 Check overall dimension in accordance with drawing
label | Inspection Activity: D - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
label | Verifying Document - Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 7.4 Check maximum sweep
label | Inspection Activity: D - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
label | Verifying Document - Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 7.5 Check maximum camber
label | Inspection Activity: D - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
label | Verifying Document - Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 7.6 Check hole size per drawing
label | Inspection Activity: D - x
label | Inspected by - FWI
label | Acceptance Criteria: Document - AS/NZS 5131
label | Acceptance Criteria: Clause - Section 6
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
label | Verifying Document - Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
section | 8.0 NON-DESTRUCTIVE TESTING (NDT)
checkpoint | 8.1 100% Visual scaning all weld and examination of all SP weld
label | Inspection Activity: V - x
label | Inspected by - FWI
label | Acceptance Criteria: Reference Standard - AS 3978 sec 10, AS/NZS 1554.1 Table 6.2.2
label | Verifying Document - Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I / D
checkpoint | 8.2 5-10 % UT for SP butt welds
label | Inspection Activity: N - x
label | Inspected by - FWI
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1 Table 6.2.1, AS 2207
label | Verifying Document - UT Reports
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I / D
checkpoint | 8.3 5% Magnetic particle for SP fillet weld in Seismic areas Noted : Reduced in inspection frequency, if no non-conformances found
label | Inspection Activity: N - x
label | Inspected by - SGS
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1 Table 6.2.2, AS 1171
label | Verifying Document - NDT Reports
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I / D
checkpoint | 8.4 If lack of fusion or cracking is suspected, carry out Magnetic particle testing
label | Inspection Activity: N - x
label | Inspected by - FWI / SGS
label | Acceptance Criteria: Reference Standard - AS/NZS 1554.1 Table 6.2.2, AS 1171
label | Verifying Document - Weld Check Summary sheets
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I / D
section | 9.0 SURFACE PREPARATION AND PAINTING
checkpoint | 9.1 Storage of Paint products
label | Inspection Activity: R - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - Manufacturers Instructions
label | Verifying Document - Paintstore Register
label | Surveillance Inspection: Frequency - Daily
label | Surveillance Inspection: Jensen - I/D
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 9.2 Monitor environment for coating application
label | Inspection Activity: R - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894
label | Verifying Document - Daily Paint Inspection Reports
label | Surveillance Inspection: Frequency - Weekly
label | Surveillance Inspection: Jensen - I/D
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 9.3 Surface preparation shall be in accordance to AS 1267.4 Class 2.5
label | Inspection Activity: V - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894
label | Verifying Document - Daily Paint Inspection Reports
label | Surveillance Inspection: Frequency - Weekly
label | Surveillance Inspection: Jensen - I/D
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 9.4 Check dry film thickness and visual appearance check for coating
label | Inspection Activity: V - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894
label | Verifying Document - Daily Paint Inspection Reports
label | Surveillance Inspection: Frequency - Weekly
label | Surveillance Inspection: Jensen - I/D
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
checkpoint | 9.5 Manufacturer Inspections
label | Inspection Activity: V - x
label | Inspection Activity: D - x
label | Inspected by - Nace Level 2 Inspector
label | Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894
label | Verifying Document - Paint Inspection Reports
label | Surveillance Inspection: Frequency - As Required
label | Surveillance Inspection: Jensen - I/D
label | Surveillance Inspection: Client - M
label | Surveillance Inspection: Owner - M
label | Remark - Note this section does not cover the intumescent test plan. This is still to be confirmed with Fosters/ JSF
section | 10.0 Installation - Onsite
checkpoint | 10.1 Delivery of materials
label | Inspection Activity: V - x
label | Inspection Activity: D - X
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - AS/NZS 5131
label | Verifying Document - Delivery dockets
label | Surveillance Inspection: Frequency - As Required
label | Surveillance Inspection: Jensen - I/D
checkpoint | 10.2 Bolting procedures. As per JSF High Strength Bolting SOP. All Snug bolts to be marked with an "X" on end of bolt once Snug tensioned.
label | Inspection Activity: D - x
label | Inspected by - QAM / C
label | Acceptance Criteria: Reference Standard - AS/NZS 5131
label | Verifying Document - Conqa Site Structural and Bolting reports
label | Surveillance Inspection: Frequency - As Required
label | Surveillance Inspection: Jensen - I/D
label | Surveillance Inspection: Client - I/M
label | Surveillance Inspection: Owner - I/M
checkpoint | 10.3 Screws, bolts & nuts to be Grade 8.8 unless otherwise stated.
label | Inspection Activity: D - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - AS/NZS 5131
label | Verifying Document - Conqa Site Structural and Bolting reports
label | Surveillance Inspection: Frequency - As Required
label | Surveillance Inspection: Jensen - I/D
checkpoint | 10.4 Erection -Tolerances
label | Inspection Activity: D - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - AS/NZS 5131
label | Verifying Document - Conqa Site Structural and Bolting reports
label | Surveillance Inspection: Frequency - As Required
label | Surveillance Inspection: Jensen - I/D
label | Surveillance Inspection: Client - R
label | Surveillance Inspection: Owner - M
checkpoint | 10.5 Paint touch-up
label | Inspection Activity: V - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - AS/NZS 5131/2312
label | Verifying Document - Conqa Site Structural and Bolting reports
label | Surveillance Inspection: Frequency - As Required
label | Surveillance Inspection: Jensen - I/D
label | Surveillance Inspection: Client - W
label | Surveillance Inspection: Owner - M
checkpoint | 10.6 Final inspection
label | Inspection Activity: V - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - AS/NZS 5131
label | Verifying Document - Conqa Site Structural and Bolting reports
label | Surveillance Inspection: Frequency - As Required
label | Surveillance Inspection: Jensen - I/D
label | Surveillance Inspection: Client - W
label | Surveillance Inspection: Owner - M
section | 11.0 FINAL INSPECTION AND DOCUMENTATION
checkpoint | 11.1 General visual inspection of completed Project/Phases
label | Inspection Activity: V - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - Project Specification
label | Verifying Document - Conqa Site Structural and Bolting reports
label | Surveillance Inspection: Frequency - As Required
label | Surveillance Inspection: Jensen - I/D
label | Surveillance Inspection: Client - W
label | Surveillance Inspection: Owner - M
checkpoint | 11.2 Submit Quality Documentation
label | Inspection Activity: R - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - Project Specification
label | Verifying Document - QA Pack for Client
label | Surveillance Inspection: Frequency - As Required
label | Surveillance Inspection: Jensen - D
label | Surveillance Inspection: Client - R
label | Surveillance Inspection: Owner - R
checkpoint | 11.3 Complete Producer Statement
label | Inspection Activity: R - x
label | Inspected by - QAM
label | Acceptance Criteria: Reference Standard - Project Specification
label | Verifying Document - PS3
label | Surveillance Inspection: Frequency - As Required
label | Surveillance Inspection: Jensen - D
label | Surveillance Inspection: Client - R
label | Surveillance Inspection: Owner - R
label | Remark - After project/phase completion
checklist | OPE009 ITP - Erection | itp |  |  |  |  | Add OPE009 ITP - Erection Rev 0
section | Erection
checkpoint | Risk assessment
label | CONTROL - H
label | ACCEPTANCE CRITERIA - AS/NZS 5131, 11.2.4
label | QMS Ref - OPE 004
label | RECORDS/REPORTS - Site Safety Plan
holdpoint | HOLD POINT
checkpoint | Erection design (stability check)
label | CONTROL - H
label | ACCEPTANCE CRITERIA - 11.4
label | QMS Ref - OPE 007
label | RESPONSIBILITY - Site Supervisor
label | ESM/STAGE/Frequency - All
holdpoint | HOLD POINT
checkpoint | Site survey
label | CONTROL - S
label | ACCEPTANCE CRITERIA - 11.3
label | QMS Ref - OPE 007 / OPE 017
label | RESPONSIBILITY - Site Operations Manager, Site Supervisor/ Independent Surveyor
label | RECORDS/REPORTS - Record
checkpoint | Delivery and storage
label | CONTROL - I
label | ACCEPTANCE CRITERIA - 11.5.6
label | QMS Ref - OPE 007, OPE 008
label | RESPONSIBILITY - Site Supervisor
checkpoint | Temporary erection
label | CONTROL - R
label | ACCEPTANCE CRITERIA - 11.5.10
label | QMS Ref - OPE 007 / OPE 018
checkpoint | Permanent supports
label | CONTROL - H, S, I
label | ACCEPTANCE CRITERIA - 11.6.1
label | QMS Ref - OPE 007 / OPE 018
label | RECORDS/REPORTS - Report
holdpoint | HOLD POINT
checkpoint | Temporary supports, props – doc survey and inspection report
label | CONTROL - S, R
label | ACCEPTANCE CRITERIA - 11.5.2, 3, 11.6
label | QMS Ref - OPE 007 / OPE 018 / OPE 011
label | RECORDS/REPORTS - Report
checkpoint | Installation of bolted connections - Snug tightening (S)
label | CONTROL - I
label | ACCEPTANCE CRITERIA - 8.3, 8.5.1, 13.7
label | QMS Ref - OPE 008 / OPE 011-5 / OPE 023
label | RESPONSIBILITY - Bolting Supervisor
label | RECORDS/REPORTS - Report
checkpoint | Tensioning of bolted connections – Bearing Type (TB)
label | CONTROL - I
label | ACCEPTANCE CRITERIA - 8.3, 8.5.1, 13.7
label | QMS Ref - OPE 008 / OPE 011-5 / OPE 023
label | RESPONSIBILITY - Bolting Supervisor
label | RECORDS/REPORTS - Report
checkpoint | Tensioning of bolted connections – Friction Type (TF)
label | CONTROL - I
label | ACCEPTANCE CRITERIA - 8.4.2, 13.7
label | QMS Ref - OPE 008 / OPE 011-5 / OPE 023
label | RESPONSIBILITY - Bolting Supervisor
label | RECORDS/REPORTS - Report
checkpoint | Mechanical and chemical anchors
label | CONTROL - I
label | ACCEPTANCE CRITERIA - 8.8.3
label | QMS Ref - OPE 008 / OPE 023/ OPE 011
label | RESPONSIBILITY - Site Supervisor
label | RECORDS/REPORTS - Report
checkpoint | Thin gauge components
label | CONTROL - I
label | ACCEPTANCE CRITERIA - 8.6
label | QMS Ref - OPE 008 / OPE 023/ OPE 011
label | RESPONSIBILITY - Site Supervisor
label | RECORDS/REPORTS - Report
checkpoint | Removal of braces, props, frames etc.
label | CONTROL - H, A
label | ACCEPTANCE CRITERIA - 11.5.5
label | QMS Ref - OPE 008 / OPE 011
label | RESPONSIBILITY - Site Operations Manager / Site Supervisor
label | RECORDS/REPORTS - Record
holdpoint | HOLD POINT
checkpoint | Site welding
label | CONTROL - I
label | ACCEPTANCE CRITERIA - 7
label | QMS Ref - OPE 008 / OPE 017
label | RESPONSIBILITY - Site Supervisor
checkpoint | Erection and Assembly tolerances
label | CONTROL - I
label | ACCEPTANCE CRITERIA - 13.4 Appendix F
label | QMS Ref - OPE 008 / OPE 011 / OPE 017
label | RESPONSIBILITY - Site Supervisor
label | RECORDS/REPORTS - Report
checkpoint | Repairs to painted surfaces
label | CONTROL - I
label | ACCEPTANCE CRITERIA - 9.12
label | QMS Ref - OPE 017
label | RESPONSIBILITY - Site Supervisor
label | RECORDS/REPORTS - Report
checkpoint | Completion Final inspection
label | CONTROL - I
label | ACCEPTANCE CRITERIA - 13.11
label | QMS Ref - OPE 011
label | RESPONSIBILITY - Site Supervisor / Client / Quality Manger
label | RECORDS/REPORTS - Report
checkpoint | Completed QA documentation
label | CONTROL - I
label | ACCEPTANCE CRITERIA - Client’s speciﬁcation
label | QMS Ref - OPE 015, OPE 011
label | RESPONSIBILITY - Quality Manager
label | RECORDS/REPORTS - Report
checkpoint | Final sign oﬀ
label | CONTROL - P