## Sheet1
1.1 | Shop drawing review |  |  |  | x | C |  |  | Project specification | Shop drawings approved for Construction by Engineer | - | S | H/A | - | 1.1 Shop drawing review | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - C | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - Project specification | Verifying Document - Shop drawings approved for Construction by Engineer | Surveillance Inspection: Frequency - - | Surveillance Inspection: Jensen - S | Surveillance Inspection: Client - H/A | Surveillance Inspection: Owner - - | 1.1 Shop drawing review
1.2 | Discuss the implementation of the quality requirement and to ensure that all requirements of Contract are understood |  |  |  | x | C |  |  | Project Specification | QAP, ITP Accepted by Client | - | - | H/A | - | 1.2 Discuss the implementation of the quality requirement and to ensure that all requirements of Contract are understood | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - C | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - Project Specification | Verifying Document - QAP, ITP Accepted by Client | Surveillance Inspection: Frequency - - | Surveillance Inspection: Jensen - - | Surveillance Inspection: Client - H/A | Surveillance Inspection: Owner - - | Inspection Activity: V -
2.1 | Review/Approve quality assurance plan |  |  |  | x | DE |  |  | AS/NZS 5131 | QAP | - | - | H/A | - | 2.1 Review/Approve quality assurance plan | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - DE | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 5131 | Verifying Document - QAP | Surveillance Inspection: Frequency - - | Surveillance Inspection: Jensen - - | Surveillance Inspection: Client - H/A | Surveillance Inspection: Owner - - | Inspection Activity: D -
2.2 | Review/Approve welding plan |  |  |  | x | DE |  |  | AS/NZS 5131 | OP030 | - | - | H/A | - | 2.2 Review/Approve welding plan | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - DE | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 5131 | Verifying Document - OP030 | Surveillance Inspection: Frequency - - | Surveillance Inspection: Jensen - - | Surveillance Inspection: Client - H/A | Surveillance Inspection: Owner - - | Inspection Activity: N -
2.3 | Review/Approve WPS, PQR |  |  |  | x | DE |  |  | AS/NZS1554.1 | WPS | - | - | H/A | - | 2.3 Review/Approve WPS, PQR | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - DE | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS1554.1 | Verifying Document - WPS | Surveillance Inspection: Frequency - - | Surveillance Inspection: Jensen - - | Surveillance Inspection: Client - H/A | Surveillance Inspection: Owner - - | Inspection Activity: R - x
2.4 | Review/Approve Welder qualification test records |  |  |  | x | DE |  |  | AS/NZS2980 / ISO 9606.1 | PQR | - | - | H/A | - | 2.4 Review/Approve Welder qualification test records | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - DE | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS2980 / ISO 9606.1 | Verifying Document - PQR | Surveillance Inspection: Frequency - - | Surveillance Inspection: Jensen - - | Surveillance Inspection: Client - H/A | Surveillance Inspection: Owner - - | Inspected by - C
2.5 | Review/Approve NDE personnel certificate |  |  |  | x | DE |  |  | AS/NZS 5131 | AS2214 Welding Supervisor Certificates, CBIP Website | - | - | H/A | - | 2.5 Review/Approve NDE personnel certificate | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - DE | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 5131 | Verifying Document - AS2214 Welding Supervisor Certificates, CBIP Website | Surveillance Inspection: Frequency - - | Surveillance Inspection: Jensen - - | Surveillance Inspection: Client - H/A | Surveillance Inspection: Owner - - | Acceptance Criteria: Document -
2.6 | Paint System Approval |  |  |  | x | DE |  |  | AS/NZS 2312 |  | - | H | R | - | 2.6 Paint System Approval | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - DE | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 2312 | Verifying Document - | Surveillance Inspection: Frequency - - | Surveillance Inspection: Jensen - H | Surveillance Inspection: Client - R | Surveillance Inspection: Owner - - | Acceptance Criteria: Clause -
3.1 | Verify mill certificate and heat marking records both physical marking of material and traceability database record |  | x |  | x | QAM | AS/NZS 5131 | Section 5 | AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600 | Mill certificates, cutting schedule sheets | Monthly | H | - | - | 3.1 Verify mill certificate and heat marking records both physical marking of material and traceability database record | Inspection Activity: V - | Inspection Activity: D - x | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - QAM | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 5 | Acceptance Criteria: Reference Standard - AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600 | Verifying Document - Mill certificates, cutting schedule sheets | Surveillance Inspection: Frequency - Monthly | Surveillance Inspection: Jensen - H | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | Acceptance Criteria: Reference Standard - Project specification
3.2 | Inspect all material for any damage | x |  |  |  | QAM | AS/NZS 5131 | Section 6 | AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600 | Mill certificates, cutting schedule sheets | Daily | H | - | - | 3.2 Inspect all material for any damage | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - QAM | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600 | Verifying Document - Mill certificates, cutting schedule sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - H | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | Verifying Document - Shop drawings approved for Construction by Engineer
3.3 | Review mill certificate in accordance with the requirements of project specifications |  |  |  | x | QAM |  |  | AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600 | Mill certificates | Monthly | H | R | R | 3.3 Review mill certificate in accordance with the requirements of project specifications | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600 | Verifying Document - Mill certificates | Surveillance Inspection: Frequency - Monthly | Surveillance Inspection: Jensen - H | Surveillance Inspection: Client - R | Surveillance Inspection: Owner - R | Surveillance Inspection: Frequency - -
3.4 | Review hardware certificate (Bolt, Nut and Washer) meet specification ( for Grade 8.8 UNO) |  |  |  | x | QAM |  |  | AS/NZS 1252 / AS/NZS 1214 | Mill certificates | Monthly | H | R | - | 3.4 Review hardware certificate (Bolt, Nut and Washer) meet specification ( for Grade 8.8 UNO) | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 1252 / AS/NZS 1214 | Verifying Document - Mill certificates | Surveillance Inspection: Frequency - Monthly | Surveillance Inspection: Jensen - H | Surveillance Inspection: Client - R | Surveillance Inspection: Owner - - | Surveillance Inspection: Jensen - S
4.1 | Check identification marking on work piece for material traceability | x |  |  |  | QAM/FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131, WPS | Shop drawing, Cutting schedule sheets, Weld Check Summary sheets | Daily | I | - | - | 4.1 Check identification marking on work piece for material traceability | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - QAM/FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS | Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | Surveillance Inspection: Client - H/A
4.2 | Check edge preparation in accordance with shop drawing and WPS | x |  |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131, WPS | Shop drawing, Cutting schedule sheets, Weld Check Summary sheets | Daily | I | - | - | 4.2 Check edge preparation in accordance with shop drawing and WPS | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS | Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | Surveillance Inspection: Owner - -
4.3 | Check surface cutting profile/ gas notch | x |  |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131, WPS | Shop drawing, Cutting schedule sheets, Weld Check Summary sheets | Daily | I | - | - | 4.3 Check surface cutting profile/ gas notch | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS | Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | 1.2 Discuss the implementation of the quality requirement and to ensure that all requirements of Contract are understood
4.4 | Machined and sheared edge preparations and drilled hole shall be debarred | x |  |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131, WPS | Shop drawing, Cutting schedule sheets, Weld Check Summary sheets | Daily | I | - | - | 4.4 Machined and sheared edge preparations and drilled hole shall be debarred | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS | Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | Inspection Activity: V -
5.1 | Check overall pre-weld dimension |  | x |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS1554.1, AS/NZS 5131, WPS | Shop drawings, Weld Check Summary sheets | Daily | I | M | M | 5.1 Check overall pre-weld dimension | Inspection Activity: V - | Inspection Activity: D - x | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS | Verifying Document - Shop drawings, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Inspection Activity: D -
5.2 | Check weld joint cleanliness | x |  |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS1554.1, AS/NZS 5131, WPS | Shop drawings, Weld Check Summary sheets | Daily | I | M | M | 5.2 Check weld joint cleanliness | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS | Verifying Document - Shop drawings, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Inspection Activity: N -
5.3 | Arc strikes outside the area of permanent weld shall be ground smooth and visually inspected | x |  |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS1554.1, AS/NZS 5131, WPS | Shop drawings, Weld Check Summary sheets | Daily | I | M | M | 5.3 Arc strikes outside the area of permanent weld shall be ground smooth and visually inspected | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS | Verifying Document - Shop drawings, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Inspection Activity: R - x
5.4 | Run-off tabs/Backing bar shall be used on all SAW process | x |  |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS1554.1, AS/NZS 5131, WPS | Shop drawings, Weld Check Summary sheets | Daily | I | M | M | 5.4 Run-off tabs/Backing bar shall be used on all SAW process | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS | Verifying Document - Shop drawings, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Inspected by - C
6.1 | Check welder qualification and validity |  |  |  | x | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131, WPS | WPS, Weld Check Summary sheets | Daily | I | M | M | 6.1 Check welder qualification and validity | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS | Verifying Document - WPS, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Acceptance Criteria: Document -
6.2 | Monitor electrode storage CHAR(AMP) useage | x |  |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131, WPS | WPS, Weld Check Summary sheets | Daily | I | M | M | 6.2 Monitor electrode storage CHAR(AMP) useage | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS | Verifying Document - WPS, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Acceptance Criteria: Clause -
6.2 | Monitor electrode storage CHAR(AMP) useage | x |  |  |  | FWI | Shipping class 3YS minimum | Section 6 | AS/NZS 1554.1, AS/NZS 5131, WPS | WPS, Weld Check Summary sheets | Daily | I | M | M | 6.2 Monitor electrode storage CHAR(AMP) useage | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - Shipping class 3YS minimum | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS | Verifying Document - WPS, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Acceptance Criteria: Reference Standard - Project Specification
6.3 | Monitor preheating as per WPS | x |  |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131, WPS | WPS, Weld Check Summary sheets | Daily | I | M | M | 6.3 Monitor preheating as per WPS | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS | Verifying Document - WPS, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Verifying Document - QAP, ITP Accepted by Client
6.4 | Monitor welding sequence, parameter, Interpass temperature | x |  |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131, WPS | WPS, Weld Check Summary sheets | Daily | I | M | M | 6.4 Monitor welding sequence, parameter, Interpass temperature | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS | Verifying Document - WPS, Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Surveillance Inspection: Frequency - -
7.1 | Check weld profile/ weld contour is in accordance with specification | x |  |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131 | Weld Check Summary sheets | Daily | I | M | M | 7.1 Check weld profile/ weld contour is in accordance with specification | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131 | Verifying Document - Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Surveillance Inspection: Jensen - -
7.2 | Check weld leg, size and length is in accordance with drawing | x |  |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131 | Weld Check Summary sheets | Daily | I | M | M | 7.2 Check weld leg, size and length is in accordance with drawing | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131 | Verifying Document - Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Surveillance Inspection: Client - H/A
7.3 | Check overall dimension in accordance with drawing |  | x |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131 | Weld Check Summary sheets | Daily | I | M | M | 7.3 Check overall dimension in accordance with drawing | Inspection Activity: V - | Inspection Activity: D - x | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131 | Verifying Document - Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Surveillance Inspection: Owner - -
7.4 | Check maximum sweep |  | x |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131 | Weld Check Summary sheets | Daily | I | M | M | 7.4 Check maximum sweep | Inspection Activity: V - | Inspection Activity: D - x | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131 | Verifying Document - Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | 2.1 Review/Approve quality assurance plan
7.5 | Check maximum camber |  | x |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131 | Weld Check Summary sheets | Daily | I | M | M | 7.5 Check maximum camber | Inspection Activity: V - | Inspection Activity: D - x | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131 | Verifying Document - Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Inspection Activity: V -
7.6 | Check hole size per drawing |  | x |  |  | FWI | AS/NZS 5131 | Section 6 | AS/NZS 1554.1, AS/NZS 5131 | Weld Check Summary sheets | Daily | I | M | M | 7.6 Check hole size per drawing | Inspection Activity: V - | Inspection Activity: D - x | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - AS/NZS 5131 | Acceptance Criteria: Clause - Section 6 | Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131 | Verifying Document - Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Inspection Activity: D -
8.1 | 100% Visual scaning all weld and examination of all SP weld | x |  |  |  | FWI |  |  | AS 3978 sec 10, AS/NZS 1554.1 Table 6.2.2 | Weld Check Summary sheets | Daily | I / D | - | - | 8.1 100% Visual scaning all weld and examination of all SP weld | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS 3978 sec 10, AS/NZS 1554.1 Table 6.2.2 | Verifying Document - Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I / D | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | Inspection Activity: N -
8.2 | 5-10 % UT for SP butt welds |  |  | x |  | FWI |  |  | AS/NZS 1554.1 Table 6.2.1, AS 2207 | UT Reports | Daily | I / D | - | - | 8.2 5-10 % UT for SP butt welds | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - x | Inspection Activity: R - | Inspected by - FWI | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 1554.1 Table 6.2.1, AS 2207 | Verifying Document - UT Reports | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I / D | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | Inspection Activity: R - x
8.3 | 5% Magnetic particle for SP fillet weld in Seismic areas Noted : Reduced in inspection frequency, if no non-conformances found |  |  | x |  | SGS |  |  | AS/NZS 1554.1 Table 6.2.2, AS 1171 | NDT Reports | Daily | I / D | - | - | 8.3 5% Magnetic particle for SP fillet weld in Seismic areas Noted : Reduced in inspection frequency, if no non-conformances found | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - x | Inspection Activity: R - | Inspected by - SGS | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 1554.1 Table 6.2.2, AS 1171 | Verifying Document - NDT Reports | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I / D | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | Inspected by - DE
8.4 | If lack of fusion or cracking is suspected, carry out Magnetic particle testing |  |  | x |  | FWI / SGS |  |  | AS/NZS 1554.1 Table 6.2.2, AS 1171 | Weld Check Summary sheets | Daily | I / D | - | - | 8.4 If lack of fusion or cracking is suspected, carry out Magnetic particle testing | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - x | Inspection Activity: R - | Inspected by - FWI / SGS | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 1554.1 Table 6.2.2, AS 1171 | Verifying Document - Weld Check Summary sheets | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I / D | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | Acceptance Criteria: Document -
9.1 | Storage of Paint products |  |  |  | x | QAM |  |  | Manufacturers Instructions | Paintstore Register | Daily | I/D | M | M | 9.1 Storage of Paint products | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - Manufacturers Instructions | Verifying Document - Paintstore Register | Surveillance Inspection: Frequency - Daily | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Acceptance Criteria: Clause -
9.2 | Monitor environment for coating application |  |  |  | x | QAM |  |  | Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894 | Daily Paint Inspection Reports | Weekly | I/D | M | M | 9.2 Monitor environment for coating application | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894 | Verifying Document - Daily Paint Inspection Reports | Surveillance Inspection: Frequency - Weekly | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Acceptance Criteria: Reference Standard - AS/NZS 5131
9.3 | Surface preparation shall be in accordance to AS 1267.4 Class 2.5 | x |  |  |  | QAM |  |  | Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894 | Daily Paint Inspection Reports | Weekly | I/D | M | M | 9.3 Surface preparation shall be in accordance to AS 1267.4 Class 2.5 | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894 | Verifying Document - Daily Paint Inspection Reports | Surveillance Inspection: Frequency - Weekly | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Verifying Document - QAP
9.4 | Check dry film thickness and visual appearance check for coating | x |  |  |  | QAM |  |  | Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894 | Daily Paint Inspection Reports | Weekly | I/D | M | M | 9.4 Check dry film thickness and visual appearance check for coating | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894 | Verifying Document - Daily Paint Inspection Reports | Surveillance Inspection: Frequency - Weekly | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Surveillance Inspection: Frequency - -
9.5 | Manufacturer Inspections | x | x |  |  | Nace Level 2 Inspector |  |  | Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894 | Paint Inspection Reports | As Required | I/D | M | M | 9.5 Manufacturer Inspections | Inspection Activity: V - x | Inspection Activity: D - x | Inspection Activity: N - | Inspection Activity: R - | Inspected by - Nace Level 2 Inspector | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894 | Verifying Document - Paint Inspection Reports | Surveillance Inspection: Frequency - As Required | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - M | Surveillance Inspection: Owner - M | Surveillance Inspection: Jensen - -
10.1 | Delivery of materials | x | X |  |  | QAM |  |  | AS/NZS 5131 | Delivery dockets | As Required | I/D | - | - | 10.1 Delivery of materials | Inspection Activity: V - x | Inspection Activity: D - X | Inspection Activity: N - | Inspection Activity: R - | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 5131 | Verifying Document - Delivery dockets | Surveillance Inspection: Frequency - As Required | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | Surveillance Inspection: Client - H/A
10.2 | Bolting procedures. As per JSF High Strength Bolting SOP. All Snug bolts to be marked with an "X" on end of bolt once Snug tensioned. |  | x |  |  | QAM / C |  |  | AS/NZS 5131 | Conqa Site Structural and Bolting reports | As Required | I/D | I/M | I/M | 10.2 Bolting procedures. As per JSF High Strength Bolting SOP. All Snug bolts to be marked with an "X" on end of bolt once Snug tensioned. | Inspection Activity: V - | Inspection Activity: D - x | Inspection Activity: N - | Inspection Activity: R - | Inspected by - QAM / C | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 5131 | Verifying Document - Conqa Site Structural and Bolting reports | Surveillance Inspection: Frequency - As Required | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - I/M | Surveillance Inspection: Owner - I/M | Surveillance Inspection: Owner - -
10.3 | Screws, bolts CHAR(AMP) nuts to be Grade 8.8 unless otherwise stated. |  | x |  |  | QAM |  |  | AS/NZS 5131 | Conqa Site Structural and Bolting reports | As Required | I/D | - | - | 10.3 Screws, bolts CHAR(AMP) nuts to be Grade 8.8 unless otherwise stated. | Inspection Activity: V - | Inspection Activity: D - x | Inspection Activity: N - | Inspection Activity: R - | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 5131 | Verifying Document - Conqa Site Structural and Bolting reports | Surveillance Inspection: Frequency - As Required | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - - | Surveillance Inspection: Owner - - | 2.2 Review/Approve welding plan
10.4 | Erection -Tolerances |  | x |  |  | QAM |  |  | AS/NZS 5131 | Conqa Site Structural and Bolting reports | As Required | I/D | R | M | 10.4 Erection -Tolerances | Inspection Activity: V - | Inspection Activity: D - x | Inspection Activity: N - | Inspection Activity: R - | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 5131 | Verifying Document - Conqa Site Structural and Bolting reports | Surveillance Inspection: Frequency - As Required | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - R | Surveillance Inspection: Owner - M | Inspection Activity: V -
10.5 | Paint touch-up | x |  |  |  | QAM |  |  | AS/NZS 5131/2312 | Conqa Site Structural and Bolting reports | As Required | I/D | W | M | 10.5 Paint touch-up | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 5131/2312 | Verifying Document - Conqa Site Structural and Bolting reports | Surveillance Inspection: Frequency - As Required | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - W | Surveillance Inspection: Owner - M | Inspection Activity: D -
10.6 | Final inspection | x |  |  |  | QAM |  |  | AS/NZS 5131 | Conqa Site Structural and Bolting reports | As Required | I/D | W | M | 10.6 Final inspection | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - AS/NZS 5131 | Verifying Document - Conqa Site Structural and Bolting reports | Surveillance Inspection: Frequency - As Required | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - W | Surveillance Inspection: Owner - M | Inspection Activity: N -
11.1 | General visual inspection of completed Project/Phases | x |  |  |  | QAM |  |  | Project Specification | Conqa Site Structural and Bolting reports | As Required | I/D | W | M | 11.1 General visual inspection of completed Project/Phases | Inspection Activity: V - x | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - Project Specification | Verifying Document - Conqa Site Structural and Bolting reports | Surveillance Inspection: Frequency - As Required | Surveillance Inspection: Jensen - I/D | Surveillance Inspection: Client - W | Surveillance Inspection: Owner - M | Inspection Activity: R - x
11.2 | Submit Quality Documentation |  |  |  | x | QAM |  |  | Project Specification | QA Pack for Client | As Required | D | R | R | 11.2 Submit Quality Documentation | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - Project Specification | Verifying Document - QA Pack for Client | Surveillance Inspection: Frequency - As Required | Surveillance Inspection: Jensen - D | Surveillance Inspection: Client - R | Surveillance Inspection: Owner - R | Inspected by - DE
11.3 | Complete Producer Statement |  |  |  | x | QAM |  |  | Project Specification | PS3 | As Required | D | R | R | 11.3 Complete Producer Statement | Inspection Activity: V - | Inspection Activity: D - | Inspection Activity: N - | Inspection Activity: R - x | Inspected by - QAM | Acceptance Criteria: Document - | Acceptance Criteria: Clause - | Acceptance Criteria: Reference Standard - Project Specification | Verifying Document - PS3 | Surveillance Inspection: Frequency - As Required | Surveillance Inspection: Jensen - D | Surveillance Inspection: Client - R | Surveillance Inspection: Owner - R | Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 5131
Verifying Document - OP030
Surveillance Inspection: Frequency - -
Surveillance Inspection: Jensen - -
Surveillance Inspection: Client - H/A
Surveillance Inspection: Owner - -
2.3 Review/Approve WPS, PQR
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - DE
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS1554.1
Verifying Document - WPS
Surveillance Inspection: Frequency - -
Surveillance Inspection: Jensen - -
Surveillance Inspection: Client - H/A
Surveillance Inspection: Owner - -
2.4 Review/Approve Welder qualification test records
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - DE
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS2980 / ISO 9606.1
Verifying Document - PQR
Surveillance Inspection: Frequency - -
Surveillance Inspection: Jensen - -
Surveillance Inspection: Client - H/A
Surveillance Inspection: Owner - -
2.5 Review/Approve NDE personnel certificate
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - DE
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 5131
Verifying Document - AS2214 Welding Supervisor Certificates, CBIP Website
Surveillance Inspection: Frequency - -
Surveillance Inspection: Jensen - -
Surveillance Inspection: Client - H/A
Surveillance Inspection: Owner - -
2.6 Paint System Approval
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - DE
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 2312
Verifying Document -
Surveillance Inspection: Frequency - -
Surveillance Inspection: Jensen - H
Surveillance Inspection: Client - R
Surveillance Inspection: Owner - -
3.1 Verify mill certificate and heat marking records both physical marking of material and traceability database record
Inspection Activity: V -
Inspection Activity: D - x
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - QAM
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 5
Acceptance Criteria: Reference Standard - AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600
Verifying Document - Mill certificates, cutting schedule sheets
Surveillance Inspection: Frequency - Monthly
Surveillance Inspection: Jensen - H
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
3.2 Inspect all material for any damage
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - QAM
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600
Verifying Document - Mill certificates, cutting schedule sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - H
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
3.3 Review mill certificate in accordance with the requirements of project specifications
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 3679-1, AS/NZS 3678, AS/NZS 4600
Verifying Document - Mill certificates
Surveillance Inspection: Frequency - Monthly
Surveillance Inspection: Jensen - H
Surveillance Inspection: Client - R
Surveillance Inspection: Owner - R
3.4 Review hardware certificate (Bolt, Nut and Washer) meet specification ( for Grade 8.8 UNO)
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 1252 / AS/NZS 1214
Verifying Document - Mill certificates
Surveillance Inspection: Frequency - Monthly
Surveillance Inspection: Jensen - H
Surveillance Inspection: Client - R
Surveillance Inspection: Owner - -
4.1 Check identification marking on work piece for material traceability
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - QAM/FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
4.2 Check edge preparation in accordance with shop drawing and WPS
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
4.3 Check surface cutting profile/ gas notch
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
4.4 Machined and sheared edge preparations and drilled hole shall be debarred
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
Verifying Document - Shop drawing, Cutting schedule sheets, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
5.1 Check overall pre-weld dimension
Inspection Activity: V -
Inspection Activity: D - x
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS
Verifying Document - Shop drawings, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
5.2 Check weld joint cleanliness
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS
Verifying Document - Shop drawings, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
5.3 Arc strikes outside the area of permanent weld shall be ground smooth and visually inspected
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS
Verifying Document - Shop drawings, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
5.4 Run-off tabs/Backing bar shall be used on all SAW process
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS1554.1, AS/NZS 5131, WPS
Verifying Document - Shop drawings, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
6.1 Check welder qualification and validity
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
Verifying Document - WPS, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
6.2 Monitor electrode storage CHAR(AMP) useage
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
Verifying Document - WPS, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
6.2 Monitor electrode storage CHAR(AMP) useage
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - Shipping class 3YS minimum
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
Verifying Document - WPS, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
6.3 Monitor preheating as per WPS
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
Verifying Document - WPS, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
6.4 Monitor welding sequence, parameter, Interpass temperature
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131, WPS
Verifying Document - WPS, Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
7.1 Check weld profile/ weld contour is in accordance with specification
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
Verifying Document - Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
7.2 Check weld leg, size and length is in accordance with drawing
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
Verifying Document - Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
7.3 Check overall dimension in accordance with drawing
Inspection Activity: V -
Inspection Activity: D - x
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
Verifying Document - Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
7.4 Check maximum sweep
Inspection Activity: V -
Inspection Activity: D - x
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
Verifying Document - Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
7.5 Check maximum camber
Inspection Activity: V -
Inspection Activity: D - x
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
Verifying Document - Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
7.6 Check hole size per drawing
Inspection Activity: V -
Inspection Activity: D - x
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document - AS/NZS 5131
Acceptance Criteria: Clause - Section 6
Acceptance Criteria: Reference Standard - AS/NZS 1554.1, AS/NZS 5131
Verifying Document - Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
8.1 100% Visual scaning all weld and examination of all SP weld
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS 3978 sec 10, AS/NZS 1554.1 Table 6.2.2
Verifying Document - Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I / D
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
8.2 5-10 % UT for SP butt welds
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N - x
Inspection Activity: R -
Inspected by - FWI
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 1554.1 Table 6.2.1, AS 2207
Verifying Document - UT Reports
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I / D
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
8.3 5% Magnetic particle for SP fillet weld in Seismic areas Noted : Reduced in inspection frequency, if no non-conformances found
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N - x
Inspection Activity: R -
Inspected by - SGS
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 1554.1 Table 6.2.2, AS 1171
Verifying Document - NDT Reports
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I / D
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
8.4 If lack of fusion or cracking is suspected, carry out Magnetic particle testing
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N - x
Inspection Activity: R -
Inspected by - FWI / SGS
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 1554.1 Table 6.2.2, AS 1171
Verifying Document - Weld Check Summary sheets
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I / D
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
9.1 Storage of Paint products
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - Manufacturers Instructions
Verifying Document - Paintstore Register
Surveillance Inspection: Frequency - Daily
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
9.2 Monitor environment for coating application
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894
Verifying Document - Daily Paint Inspection Reports
Surveillance Inspection: Frequency - Weekly
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
9.3 Surface preparation shall be in accordance to AS 1267.4 Class 2.5
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894
Verifying Document - Daily Paint Inspection Reports
Surveillance Inspection: Frequency - Weekly
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
9.4 Check dry film thickness and visual appearance check for coating
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894
Verifying Document - Daily Paint Inspection Reports
Surveillance Inspection: Frequency - Weekly
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
9.5 Manufacturer Inspections
Inspection Activity: V - x
Inspection Activity: D - x
Inspection Activity: N -
Inspection Activity: R -
Inspected by - Nace Level 2 Inspector
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - Project Specification, AS/NZS 2312, AS/NZS 5131, AS 3894
Verifying Document - Paint Inspection Reports
Surveillance Inspection: Frequency - As Required
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - M
Surveillance Inspection: Owner - M
10.1 Delivery of materials
Inspection Activity: V - x
Inspection Activity: D - X
Inspection Activity: N -
Inspection Activity: R -
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 5131
Verifying Document - Delivery dockets
Surveillance Inspection: Frequency - As Required
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
10.2 Bolting procedures. As per JSF High Strength Bolting SOP. All Snug bolts to be marked with an "X" on end of bolt once Snug tensioned.
Inspection Activity: V -
Inspection Activity: D - x
Inspection Activity: N -
Inspection Activity: R -
Inspected by - QAM / C
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 5131
Verifying Document - Conqa Site Structural and Bolting reports
Surveillance Inspection: Frequency - As Required
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - I/M
Surveillance Inspection: Owner - I/M
10.3 Screws, bolts CHAR(AMP) nuts to be Grade 8.8 unless otherwise stated.
Inspection Activity: V -
Inspection Activity: D - x
Inspection Activity: N -
Inspection Activity: R -
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 5131
Verifying Document - Conqa Site Structural and Bolting reports
Surveillance Inspection: Frequency - As Required
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - -
Surveillance Inspection: Owner - -
10.4 Erection -Tolerances
Inspection Activity: V -
Inspection Activity: D - x
Inspection Activity: N -
Inspection Activity: R -
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 5131
Verifying Document - Conqa Site Structural and Bolting reports
Surveillance Inspection: Frequency - As Required
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - R
Surveillance Inspection: Owner - M
10.5 Paint touch-up
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 5131/2312
Verifying Document - Conqa Site Structural and Bolting reports
Surveillance Inspection: Frequency - As Required
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - W
Surveillance Inspection: Owner - M
10.6 Final inspection
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - AS/NZS 5131
Verifying Document - Conqa Site Structural and Bolting reports
Surveillance Inspection: Frequency - As Required
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - W
Surveillance Inspection: Owner - M
11.1 General visual inspection of completed Project/Phases
Inspection Activity: V - x
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R -
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - Project Specification
Verifying Document - Conqa Site Structural and Bolting reports
Surveillance Inspection: Frequency - As Required
Surveillance Inspection: Jensen - I/D
Surveillance Inspection: Client - W
Surveillance Inspection: Owner - M
11.2 Submit Quality Documentation
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - Project Specification
Verifying Document - QA Pack for Client
Surveillance Inspection: Frequency - As Required
Surveillance Inspection: Jensen - D
Surveillance Inspection: Client - R
Surveillance Inspection: Owner - R
11.3 Complete Producer Statement
Inspection Activity: V -
Inspection Activity: D -
Inspection Activity: N -
Inspection Activity: R - x
Inspected by - QAM
Acceptance Criteria: Document -
Acceptance Criteria: Clause -
Acceptance Criteria: Reference Standard - Project Specification
Verifying Document - PS3
Surveillance Inspection: Frequency - As Required
Surveillance Inspection: Jensen - D
Surveillance Inspection: Client - R
Surveillance Inspection: Owner - R