## Sheet1
Risk assessment | H | AS/NZS 5131 11.2.4 | OPE 004 |  |  | Site Safety Plan | Risk assessment | CONTROL - H | ACCEPTANCE CRITERIA - AS/NZS 5131 11.2.4 | QMS Ref - OPE 004 | RESPONSIBILITY - | ESM/STAGE/Frequency - | RECORDS/REPORTS - Site Safety Plan | Risk assessment
Erection design (stability check) | H | 11.4 | OPE 007 | Site Supervisor | All |  | Erection design (stability check) | CONTROL - H | ACCEPTANCE CRITERIA - 11.4 | QMS Ref - OPE 007 | RESPONSIBILITY - Site Supervisor | ESM/STAGE/Frequency - All | RECORDS/REPORTS - | CONTROL - H
Site survey | S | 11.3 | OPE 007 / OPE 017 | Site Operations Manager, Site Supervisor/ Independent Surveyor |  | Record | Site survey | CONTROL - S | ACCEPTANCE CRITERIA - 11.3 | QMS Ref - OPE 007 / OPE 017 | RESPONSIBILITY - Site Operations Manager, Site Supervisor/ Independent Surveyor | ESM/STAGE/Frequency - | RECORDS/REPORTS - Record | ACCEPTANCE CRITERIA - AS/NZS 5131 11.2.4
Delivery and storage | I | 11.5.6 | OPE 007, OPE 008 | Site Supervisor |  |  | Delivery and storage | CONTROL - I | ACCEPTANCE CRITERIA - 11.5.6 | QMS Ref - OPE 007, OPE 008 | RESPONSIBILITY - Site Supervisor | ESM/STAGE/Frequency - | RECORDS/REPORTS - | QMS Ref - OPE 004
Temporary erection | R | 11.5.10 | OPE 007 / OPE 018 |  |  |  | Temporary erection | CONTROL - R | ACCEPTANCE CRITERIA - 11.5.10 | QMS Ref - OPE 007 / OPE 018 | RESPONSIBILITY - | ESM/STAGE/Frequency - | RECORDS/REPORTS - | RESPONSIBILITY -
Permanent supports | H, S, I | 11.6.1 | OPE 007 / OPE 018 |  |  | Report | Permanent supports | CONTROL - H, S, I | ACCEPTANCE CRITERIA - 11.6.1 | QMS Ref - OPE 007 / OPE 018 | RESPONSIBILITY - | ESM/STAGE/Frequency - | RECORDS/REPORTS - Report | ESM/STAGE/Frequency -
Temporary supports, props – doc survey and inspection report | S, R | 11.5.2, 3 11.6 | OPE 007 / OPE 018 / OPE 011 |  |  | Report | Temporary supports, props – doc survey and inspection report | CONTROL - S, R | ACCEPTANCE CRITERIA - 11.5.2, 3 11.6 | QMS Ref - OPE 007 / OPE 018 / OPE 011 | RESPONSIBILITY - | ESM/STAGE/Frequency - | RECORDS/REPORTS - Report | RECORDS/REPORTS - Site Safety Plan
Installation of bolted connections - Snug tightening (S) | I | 8.3, 8.5.1, 13.7 | OPE 008 / OPE 011-5 / OPE 023 | Bolting Supervisor |  | Report | Installation of bolted connections - Snug tightening (S) | CONTROL - I | ACCEPTANCE CRITERIA - 8.3, 8.5.1, 13.7 | QMS Ref - OPE 008 / OPE 011-5 / OPE 023 | RESPONSIBILITY - Bolting Supervisor | ESM/STAGE/Frequency - | RECORDS/REPORTS - Report | Erection design (stability check)
Tensioning of bolted connections – Bearing Type (TB) | I | 8.3, 8.5.1, 13.7 | OPE 008 / OPE 011-5 / OPE 023 | Bolting Supervisor |  | Report | Tensioning of bolted connections – Bearing Type (TB) | CONTROL - I | ACCEPTANCE CRITERIA - 8.3, 8.5.1, 13.7 | QMS Ref - OPE 008 / OPE 011-5 / OPE 023 | RESPONSIBILITY - Bolting Supervisor | ESM/STAGE/Frequency - | RECORDS/REPORTS - Report | CONTROL - H
Tensioning of bolted connections – Friction Type (TF) | I | 8.4.2, 13.7 | OPE 008 / OPE 011-5 / OPE 023 | Bolting Supervisor |  | Report | Tensioning of bolted connections – Friction Type (TF) | CONTROL - I | ACCEPTANCE CRITERIA - 8.4.2, 13.7 | QMS Ref - OPE 008 / OPE 011-5 / OPE 023 | RESPONSIBILITY - Bolting Supervisor | ESM/STAGE/Frequency - | RECORDS/REPORTS - Report | ACCEPTANCE CRITERIA - 11.4
Mechanical and chemical anchors | I | 8.8.3 | OPE 008 / OPE 023/ OPE 011 | Site Supervisor |  | Report | Mechanical and chemical anchors | CONTROL - I | ACCEPTANCE CRITERIA - 8.8.3 | QMS Ref - OPE 008 / OPE 023/ OPE 011 | RESPONSIBILITY - Site Supervisor | ESM/STAGE/Frequency - | RECORDS/REPORTS - Report | QMS Ref - OPE 007
Thin gauge components | I | 8.6 | OPE 008 / OPE 023/ OPE 011 | Site Supervisor |  | Report | Thin gauge components | CONTROL - I | ACCEPTANCE CRITERIA - 8.6 | QMS Ref - OPE 008 / OPE 023/ OPE 011 | RESPONSIBILITY - Site Supervisor | ESM/STAGE/Frequency - | RECORDS/REPORTS - Report | RESPONSIBILITY - Site Supervisor
Removal of braces, props, frames etc. | H, A | 11.5.5 | OPE 008 / OPE 011 | Site Operations Manager / Site Supervisor |  | Record | Removal of braces, props, frames etc. | CONTROL - H, A | ACCEPTANCE CRITERIA - 11.5.5 | QMS Ref - OPE 008 / OPE 011 | RESPONSIBILITY - Site Operations Manager / Site Supervisor | ESM/STAGE/Frequency - | RECORDS/REPORTS - Record | ESM/STAGE/Frequency - All
Site welding | I | 7 | OPE 008 / OPE 017 | Site Supervisor |  |  | Site welding | CONTROL - I | ACCEPTANCE CRITERIA - 7 | QMS Ref - OPE 008 / OPE 017 | RESPONSIBILITY - Site Supervisor | ESM/STAGE/Frequency - | RECORDS/REPORTS - | RECORDS/REPORTS -
Erection and Assembly tolerances | I | 13.4 Appendix F | OPE 008 / OPE 011 / OPE 017 | Site Supervisor |  | Report | Erection and Assembly tolerances | CONTROL - I | ACCEPTANCE CRITERIA - 13.4 Appendix F | QMS Ref - OPE 008 / OPE 011 / OPE 017 | RESPONSIBILITY - Site Supervisor | ESM/STAGE/Frequency - | RECORDS/REPORTS - Report | Site survey
Repairs to painted surfaces | I | 9.12 | OPE 017 | Site Supervisor |  | Report | Repairs to painted surfaces | CONTROL - I | ACCEPTANCE CRITERIA - 9.12 | QMS Ref - OPE 017 | RESPONSIBILITY - Site Supervisor | ESM/STAGE/Frequency - | RECORDS/REPORTS - Report | CONTROL - S
Completion Final inspection | I | 13.11 | OPE 011 | Site Supervisor / Client / Quality Manger |  | Report | Completion Final inspection | CONTROL - I | ACCEPTANCE CRITERIA - 13.11 | QMS Ref - OPE 011 | RESPONSIBILITY - Site Supervisor / Client / Quality Manger | ESM/STAGE/Frequency - | RECORDS/REPORTS - Report | ACCEPTANCE CRITERIA - 11.3
Completed QA documentation | I | Client’s speciﬁcation | OPE 015, OPE 011 | Quality Manager |  | Report | Completed QA documentation | CONTROL - I | ACCEPTANCE CRITERIA - Client’s speciﬁcation | QMS Ref - OPE 015, OPE 011 | RESPONSIBILITY - Quality Manager | ESM/STAGE/Frequency - | RECORDS/REPORTS - Report | QMS Ref - OPE 007 / OPE 017
Final sign oﬀ | P | [5 empty] | Final sign oﬀ | CONTROL - P | ACCEPTANCE CRITERIA - | QMS Ref - | RESPONSIBILITY - | ESM/STAGE/Frequency - | RECORDS/REPORTS - | RESPONSIBILITY - Site Operations Manager, Site Supervisor/ Independent Surveyor
ESM/STAGE/Frequency -
RECORDS/REPORTS - Record
Delivery and storage
CONTROL - I
ACCEPTANCE CRITERIA - 11.5.6
QMS Ref - OPE 007, OPE 008
RESPONSIBILITY - Site Supervisor
ESM/STAGE/Frequency -
RECORDS/REPORTS -
Temporary erection
CONTROL - R
ACCEPTANCE CRITERIA - 11.5.10
QMS Ref - OPE 007 / OPE 018
RESPONSIBILITY -
ESM/STAGE/Frequency -
RECORDS/REPORTS -
Permanent supports
CONTROL - H, S, I
ACCEPTANCE CRITERIA - 11.6.1
QMS Ref - OPE 007 / OPE 018
RESPONSIBILITY -
ESM/STAGE/Frequency -
RECORDS/REPORTS - Report
Temporary supports, props – doc survey and inspection report
CONTROL - S, R
ACCEPTANCE CRITERIA - 11.5.2, 3 11.6
QMS Ref - OPE 007 / OPE 018 / OPE 011
RESPONSIBILITY -
ESM/STAGE/Frequency -
RECORDS/REPORTS - Report
Installation of bolted connections - Snug tightening (S)
CONTROL - I
ACCEPTANCE CRITERIA - 8.3, 8.5.1, 13.7
QMS Ref - OPE 008 / OPE 011-5 / OPE 023
RESPONSIBILITY - Bolting Supervisor
ESM/STAGE/Frequency -
RECORDS/REPORTS - Report
Tensioning of bolted connections – Bearing Type (TB)
CONTROL - I
ACCEPTANCE CRITERIA - 8.3, 8.5.1, 13.7
QMS Ref - OPE 008 / OPE 011-5 / OPE 023
RESPONSIBILITY - Bolting Supervisor
ESM/STAGE/Frequency -
RECORDS/REPORTS - Report
Tensioning of bolted connections – Friction Type (TF)
CONTROL - I
ACCEPTANCE CRITERIA - 8.4.2, 13.7
QMS Ref - OPE 008 / OPE 011-5 / OPE 023
RESPONSIBILITY - Bolting Supervisor
ESM/STAGE/Frequency -
RECORDS/REPORTS - Report
Mechanical and chemical anchors
CONTROL - I
ACCEPTANCE CRITERIA - 8.8.3
QMS Ref - OPE 008 / OPE 023/ OPE 011
RESPONSIBILITY - Site Supervisor
ESM/STAGE/Frequency -
RECORDS/REPORTS - Report
Thin gauge components
CONTROL - I
ACCEPTANCE CRITERIA - 8.6
QMS Ref - OPE 008 / OPE 023/ OPE 011
RESPONSIBILITY - Site Supervisor
ESM/STAGE/Frequency -
RECORDS/REPORTS - Report
Removal of braces, props, frames etc.
CONTROL - H, A
ACCEPTANCE CRITERIA - 11.5.5
QMS Ref - OPE 008 / OPE 011
RESPONSIBILITY - Site Operations Manager / Site Supervisor
ESM/STAGE/Frequency -
RECORDS/REPORTS - Record
Site welding
CONTROL - I
ACCEPTANCE CRITERIA - 7
QMS Ref - OPE 008 / OPE 017
RESPONSIBILITY - Site Supervisor
ESM/STAGE/Frequency -
RECORDS/REPORTS -
Erection and Assembly tolerances
CONTROL - I
ACCEPTANCE CRITERIA - 13.4 Appendix F
QMS Ref - OPE 008 / OPE 011 / OPE 017
RESPONSIBILITY - Site Supervisor
ESM/STAGE/Frequency -
RECORDS/REPORTS - Report
Repairs to painted surfaces
CONTROL - I
ACCEPTANCE CRITERIA - 9.12
QMS Ref - OPE 017
RESPONSIBILITY - Site Supervisor
ESM/STAGE/Frequency -
RECORDS/REPORTS - Report
Completion Final inspection
CONTROL - I
ACCEPTANCE CRITERIA - 13.11
QMS Ref - OPE 011
RESPONSIBILITY - Site Supervisor / Client / Quality Manger
ESM/STAGE/Frequency -
RECORDS/REPORTS - Report
Completed QA documentation
CONTROL - I
ACCEPTANCE CRITERIA - Client’s speciﬁcation
QMS Ref - OPE 015, OPE 011
RESPONSIBILITY - Quality Manager
ESM/STAGE/Frequency -
RECORDS/REPORTS - Report
Final sign oﬀ
CONTROL - P
ACCEPTANCE CRITERIA -
QMS Ref -
RESPONSIBILITY -
ESM/STAGE/Frequency -
RECORDS/REPORTS -