## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Rail Checklist |  |  |  |  | Yes | Rail Checklist | 317da0a5-2305-433e-804f-9fd054af0495
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | e8290b74-d9f4-4fff-8ae6-12b9cea20415 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Photo taken of Engraved Line Plate / ID Tag
checkpoint-status |  |  | checkpoint | Video taken of system
checkpoint-status |  |  | checkpoint | Description input of location / person Rail systems shuttle left with
text | ca58e151-497c-4575-8066-88012502f631 |  | textbox | Location / Person:
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Fit Off Checklist - Ladder System |  |  |  |  | Yes | Fit Off Checklist - Ladder System | 50128925-9f69-4831-a8f4-35bae548dede
checkpoint-status |  |  | checkpoint | Installed to manufacturer or PBI Installation instructions
checkpoint-status |  |  | checkpoint | Installed as per AS1657:2018
checkpoint-status |  |  | checkpoint | All fixings secure
checkpoint-status |  |  | checkpoint | Top step of ladder flush with either walk-off kit or building edge
checkpoint-status |  |  | checkpoint | No unsealed penetrations to the roof
checkpoint-status |  |  | checkpoint | If caged, cage start between 2m and 2.2m from ground level?
checkpoint-status |  |  | checkpoint | If ladder is above 3.5m, does it contain a cage?
checkpoint-status |  |  | checkpoint | If ladder is above 6m, does it have a mid-way platform?
checkpoint-status |  |  | checkpoint | Photo uploaded of clean work area
label | 5f50f80d-11fd-53e4-bb26-26011948e759 |  | note | 1 photo required
checkpoint-status |  |  | checkpoint | Video taken
label | 839524b8-34f2-5de6-bd5c-f2d1b61c5f40 |  | note | 1 photo required
checklist-flat |  |  | checklist | Fit Off Checklist - Anchor |  |  |  |  | Yes | Fit Off Checklist - Anchor | 6026ba09-a347-4912-b1d7-acb1949fda97
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | b10f16e7-1750-527a-bef0-cc9c3c802c1d |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Required number of photo(s) taken of installed anchor(s)
select | 875be6d5-570f-560c-85fb-2d01c0f566f5 |  | dropdown | Anchor Type | FROG 1 photo req,L4543 2 photos req,L4544 3 photos req,L4550 2 photos req,L4551 2 photos req,L4552 2 photos req,M16 Chemset 2 photos req,M16 Through BOLT 2 photos req,SAFETOR 3 photos req,Spiratech 1 photo req, 3M Engineered Anchor (2 photos - topside and underside) Nogging in accordance with PBI fixing details (1 photo required)
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Practical Completion |  |  |  |  | Yes | Practical Completion | aee895c3-db96-4ab1-b50c-0eae0b9dfad4
checkpoint-no-status |  |  | checkpoint | System installed and ready for review from Project Manager.
holdpoint |  |  | signoff | Request Review from PM
checkpoint-status |  |  | checkpoint | Project Manager has reviewed, checked and approved system.
checkpoint-status |  |  | checkpoint | PM to send to PBI admin to close out and archive
checklist-flat |  |  | checklist | Roof Access Requirements |  |  |  |  | Yes | Roof Access Requirements | bb67aadd-8230-4fb8-bb31-de50be9a04ea
checkpoint-status |  |  | checkpoint | Brief description of roof access requirements for Recert Team
text | 0334d05e-4855-5b04-b088-823ae99e302b |  | textbox | Description
checklist-flat |  |  | checklist | Pre-Fit Off Checklist |  |  |  |  | Yes | Pre-Fit Off Checklist | d3675730-ee72-4de2-90c8-5d57c7844e02
checkpoint-status |  |  | checkpoint | Confirm structure is in accordance to the details provided
label | f33b5857-8198-41c5-971a-8ab0ef42c8f7 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Plinths/ bases/post installed in accordance with details provided
checkpoint-status |  |  | checkpoint | Photos taken
checklist-flat |  |  | checklist | Fit Off Checklist - Miscellaneous Item |  |  |  |  | Yes | Fit Off Checklist - Miscellaneous Item | d424151c-7e2e-45be-b381-217cd26a8fc3
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | 31d45639-4a4a-4893-9d3e-5407e3a8b1f5 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Photos taken of installed item
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Fit Off Checklist - Line |  |  |  |  | Yes | Fit Off Checklist - Line | da742876-bac6-4303-bb22-5be9f9f3dd7f
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | 6242ec89-db8b-4c92-ac8b-40331fb90cc3 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Photo taken of line pull test and swages
checkpoint-status |  |  | checkpoint | Photo taken of Engraved Line Plate / ID Tag
checkpoint-status |  |  | checkpoint | Video taken of system
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Data Plate, Access Point & Carriages/Travellers |  |  |  |  | Yes | Data Plate, Access Point & Carriages/Travellers | e35e923d-3363-42e5-b2f0-eceb6c321383
checkpoint-no-status |  |  | checkpoint | Details of Data Plate
select | 63469906-f15a-5496-8221-9448894bafda |  | dropdown | Has the Data Plate been installed on site? | Yes,No
label | d20042fa-7b7b-59f5-810f-ad0743858b6a |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of Data Plate
checkpoint-no-status |  |  | checkpoint | Details of Access Point
select | 0e6a920d-bef6-5104-bb3f-af69c22c9a99 |  | dropdown | Has the Access Point been confirmed? | Yes, No
label | d0ddc701-4f77-5d80-a6ea-7cf06d1fbdaf |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of Access Area
checkpoint-no-status |  |  | checkpoint | Details of Rail Carriages/Cable Travellers
select | e64fb688-5f88-58ac-a761-ee142bdb13e1 |  | dropdown | Has the Rail Carriages/Cable Travellers been left on site | Yes, No
label | 09d4b280-ffd0-5382-8504-c7adb1ec24a9 |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of carriages/travellers