## Table 1
[8 empty] | Inspection and Test Plan | [7 empty] | PC ITP No. 05
Reviewed by:
Review date:
| Skirting Install Skirtings are installed in accordance with: - AS1684.2-2010: Residential timber-framed construction | [8 empty] | Project: Frankston Hospital Redevelopment Area/Zone: Level:
PREPARED BY: Inez Giannetti |  |  |  | Signature: |  |  |  |  | KEY
Date: 04/03/2024 | [8 empty] | H – Hold Point (mandatory) H(A) Local Authority Inspection
ITP Revision No: 01 APPROVED BY: Pat Moore Date: 04/03/2024 |  |  |  | Position: Project Administrator Signature: - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - Position: Company Director |  |  |  |  | X – Self Inspection by performer of work H(C) Consultant Inspection S – Surveillance or Monitoring Inspection Frequency: To be completed monthly
Item No. |  | INSPECTION & TEST ITEMS (Include Description, Characteristics & Necessary Inspections) |  |  | Inspection Procedure | ACCEPTANCE CRITERIA Specification / Standard / Drawings Be as specific as possible eg. 300 mm deep |  |  |  |  | VERIFICATION ITEM ACTION COMPLETE | [5 empty] | RECORD AND COMMENTS
[11 empty] | Arc Plastering |  |  | Lendlease
[11 empty] | Key | Sign & Date |  | Key | Sign & Date
1 |  | Approve Samples as follows: - Manufacturer’s / supplier’s recommendations - Product Data - Review CiDD Alerts and Guidelines - Engineering design recommendations - Seismic Design and compliance certificate of framing and fixings provided to Lendlease and approved If applicable, ensure prototype is built / supplied on site |  |  | Prior to Delivery | At project commencement, ensure samples reflect: - Architectural specifications and latest: - Material finishes schedule - Drawings Drawings: Rev: |  |  |  |  | S |  |  | S
2 |  | Check delivery of Skirting is as follows: - Type and material - Colour, Finish and Texture - Size, Section and Thickness |  |  | Visual Inspection upon delivery | Check delivery dockets / checklist to ensure: - Orders comply with design documentation - Deliveries match orders Ensure the below can be provided for all materials (where appropriate) and upon completion of sections: - Traceability - Certificates of Compliance |  |  |  |  | S |  |  | S
3 |  | Complete set out of skirting as follows: - Structure is stripped and free from debris - Ceiling is set out as per plans and provided RL - Levels - Identify skirting codes by framing type and lining applied - Skirting specification required - Method of installation - Reference revision floor plans |  |  | Visual Inspection prior to framing commence ment | Ensure skirting set out is in accordance with: - Architectural Drawings - Builders works Drawings - Coordinated Services Drawings - Provided RL Progression photos to be documented Drawings: Rev: |  |  |  |  | H X |  |  | S
4 |  | Skirting completion is as follows: - Walls are installed to set out - Fixings as per manufacturer’s guidelines - True and plumb - Installation of skirting as per engineers’ details for the wall type |  |  | Visual Inspection | Ensure skirting is installed in accordance with: - Architectural Drawings - Design Specifications - Latest Drawing References and Revisions Progression photos to be documented Hold point. Sign off by other trades witnessed Drawings: Rev: |  |  |  |  | H X |  |  | S
5 |  | Installation of Corners/mitres is as follows: - Skirtings are installed to set out - Fixings as per manufacturer’s guidelines - True and plumb - Installation of corner/mitres as per engineers’ details for the wall type |  |  | Visual Inspection | Ensure corners/mitres are installed in accordance with: - Architectural Drawings - Design Specifications - Latest Drawing References and Revisions Progression photos to be documented Hold point. Sign off by other trades witnessed Drawings: Rev: |  |  |  |  | H X |  |  | S
6 |  | ARCHITECTURAL NOTIFICATION OF FINAL INSPECTION Notice of Inspection: - Correct all Defects - Supply Certificate of Compliance |  |  | Upon Completion | Ensure Final Works Completion is in accordance with: - Client Defects List - Architectural Drawings Drawings: Rev: |  |  |  |  | H H
VERIFICATION IDENTITY |  |  | COMPANY REP. WITH AUTHORITY |  |  |  | SIGNATURE / INITIAL | [5 empty] | ATTACH
Lendlease | [12 empty] |  Product Details
Arc Plastering | [12 empty] |  Sample Material