## Table 1
[8 empty] | Inspection and Test Checklist | [8 empty] | BLL ITP No. 04
Reviewed by:
Review date:
| Speedpanel Speedpanel is installed in accordance with: - AS 1530.4:2014 Methods for fire tests on building materials, components and structures - Fire-resistance tests for elements of construction | [8 empty] | Project: Frankston Hospital Redevelopment Area/Zone: Level:
PREPARED BY: Inez Giannetti |  |  |  | Signature: |  |  |  |  | KEY
Date: 29/02/2024 | [8 empty] | H – Hold Point (mandatory) H(A) Local Authority Inspection
ITP Revision No: 01 APPROVED BY: Pat Moore Date: 29/02/2024 |  |  |  | Position: Project Administrator Signature: - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - Position: Company Director |  |  |  |  | X – Self Inspection (performer of work) H(C) Consultant Inspection S – Surveillance/Monitoring Inspection Frequency: To be completed monthly
Item No. |  | INSPECTION & TEST ITEMS (Include Description, Characteristics & Necessary Inspections) |  |  | Inspection Procedure | ACCEPTANCE CRITERIA Specification / Standard / Drawings |  |  |  |  | RECORD AND COMMENTS
[11 empty] | Arc Plastering |  | Lendlease |  |  | Comments
[11 empty] | Key | Sign & Date | Key |  | Sign & Date
1 |  | Approve Samples as follows: - Manufacturer’s / supplier’s recommendations - Product Data - Review CiDD Alerts and Guidelines - Engineering design recommendations - Seismic Design and compliance certificate of framing and fixings provided to Lendlease and approved If applicable, ensure prototype is built / supplied on site |  |  | Prior to Delivery | At project commencement, ensure samples reflect: - Architectural specifications and latest: - Material finishes schedule - Drawings Drawings: Rev: |  |  |  |  | S |  | S
2 |  | Check delivery of Speedpanel as follows: - Type and material - Colour and Finish - Grade or Class - Size and Thickness - Squareness and Flatness - Edge Profile |  |  | Visual Inspection upon delivery | Check delivery dockets / checklist to ensure: - Orders comply with design documentation - Deliveries match orders Ensure the below can be provided for all materials (where appropriate) and upon completion of sections: - Traceability - Certificates of Compliance |  |  |  |  | S |  | S
3 |  | Complete set out of Speedpanel as follows: - Structure is stripped and free from debris - Identify wall codes by framing type and lining applied - Speedpanel framing specification required - Sequence in which the frame work must be installed - Method of installation - Reference revision floor plans - Identify Services mark outs |  |  | Visual Inspection prior to framing commence ment | Ensure ceiling set out is in accordance with: - Architectural Drawings - Builders works Drawings - Coordinated Services Drawings Progression photos to be documented Drawings: Rev: |  |  |  |  | H X |  | S
4 |  | Speedpanel frame work as follows: - Frame work is installed to set out - Fixings as per manufacturer’s guidelines - True and plumb - Installation of steel framing as per engineers’ details for the wall type |  |  | Visual Inspection prior to fixing speedpanel | Ensure ceiling frame work is installed in accordance with: - Architectural Drawings - Design Specifications - Latest Drawing References and Revisions Progression photos to be documented Hold point. Sign off by other trades witnessed Drawings: Rev: |  |  |  |  | H X |  | S
5 |  | External Works / Inspections to be completed Prior to Closure of Wall: - Services rough in completed - Lendlease Inspections Completed - Insulation Installed (where applicable) |  |  | Visual Inspection Prior to Closure | Ensure the completed works is installed in accordance with: - Architectural Drawings - Design Specifications - Latest Drawing References and Revisions - Verify with Lendlease: Pre-close up checklist is completed Progression photos to be documented Hold point. Sign off by other trades witnessed Drawings: Rev: |  |  |  |  | H X |  | S |  |  | Pre-close Checklist Completion Date:
6 |  | Overall Speedpanel installation as follows: a. Speedpanel - Type and Material - Colour and Finish - Size and Thickness - Neatness of Cutting - Fixing and Jointing - Squareness and Flatness - Smoothness and Uniformity - Lapping and Staggering b. Control Joint - Control Joint Locations c. Insulation (where applicable) - Insulation is installed as per acoustic and thermal requirements |  |  | Visual Inspection upon installation of speedpanel | Ensure the speedpanel, joints and insulation is installed in accordance with: - Architectural Drawings - Design Specifications - Latest Drawing References and Revisions Progression photos to be documented Hold point. Sign off by other trades witnessed Drawings: Rev: |  |  |  |  | H X |  | S
7 |  | Speedpanel Caulking is completed as follows: - Type and Material - Colour - Installed as per acoustic and thermal requirements |  |  | Visual Inspection | Ensure caulking is completed in accordance with: - Materials finishes schedule - Manufacturer’s specifications - All gaps are infilled Progression photos to be documented |  |  |  |  | X
8 |  | ARCHITECTURAL NOTIFICATION OF FINAL INSPECTION Notice of Inspection: - Correct all Defects - Supply Certificate of Compliance |  |  | Upon Completion | Ensure Final Works Completion is in accordance with: - Client Defects List - Architectural Drawings Drawings: Rev: |  |  |  |  | H H
VERIFICATION IDENTITY |  |  | COMPANY REP. WITH AUTHORITY |  |  |  | SIGNATURE / INITIAL | [6 empty] | ATTACH
Lendlease | [13 empty] |  Product Details
Arc Plastering | [13 empty] |  Sample Material