## Table 1
[8 empty] | Inspection and Test Plan | [8 empty] | BLL ITP No. 03
Reviewed by:
Review date:
| Suspended Tile Ceilings Suspended Ceiling Tiles are installed in accordance with: - AS/NZS 2785-2000 – Suspended Ceilings – Design and Installation - AS 1170.0 – Structural Design Actions – Part 0: General Principles - AS 1170.4 – Structural Design Actions – Part 4: Earthquake Actions in Aus | [8 empty] | Project: Frankston Hospital Redevelopment Area/Zone: Level:
PREPARED BY: Inez Giannetti |  |  |  | Signature: |  |  |  |  | KEY
Date: 22/02/2024 | [8 empty] | H – Hold Point (mandatory) H(A) Local Authority Inspection
ITP Revision No: 02 APPROVED BY: Pat Moore Date: 22/02/2024 |  |  |  | Position: Project Administrator Signature: - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - Position: Company Director |  |  |  |  | X – Self Inspection by performer of work H(C) Consultant Inspection S – Surveillance or Monitoring Inspection Frequency: To be completed at zone completion
Item No. |  | INSPECTION & TEST ITEMS (Include Description, Characteristics & Necessary Inspections) |  |  | Inspection Procedure | ACCEPTANCE CRITERIA Specification / Standard / Drawings |  |  |  |  | RECORD AND COMMENTS
[11 empty] | Arc Plastering |  | Lendlease |  |  | Comments
[11 empty] | Key | Sign | Key |  | Sign
1 |  | Approve Samples as follows: - Manufacturer’s / supplier’s recommendations - Product Data - Review CiDD Alerts and Guidelines - Engineering design recommendations - Seismic Design and compliance certificate of framing and fixings provided to Lendlease and approved If applicable, ensure prototype is built / supplied on site |  |  | Prior to Delivery | At project commencement, ensure samples reflect: - Architectural specifications and latest: - Material finishes schedule - Drawings Drawings: Rev: |  |  |  |  | S |  | S
2 |  | Check delivery of Suspended Grid System as follows: - Type and material - Finish - Size and Section Check delivery of Ceiling Tiles as follows: - Type and material - Grade or Class - Colour, Finish and Texture - Size and Thickness - Squareness and Flatness - Edge Profile |  |  | Visual Inspection upon delivery | Check delivery dockets / checklist to ensure: - Orders comply with design documentation - Deliveries match orders Ensure the below can be provided for all materials (where appropriate) and upon completion of sections: - Traceability - Certificates of Compliance |  |  |  |  | S |  | S
3 |  | Complete set out of Ceiling Grids as follows: - Structure is stripped and free from debris - Grid lines are in place – specifically check for building creep - Grid system is set out as per plans and builders works penetrations marked - Levels - Identify ceiling codes by grid system and tiles applied - Suspended Ceiling Grid System and tiles specification required - Sequence in which the Suspended Ceiling Tiles must be installed - Method of installation - Reference revision floor plans - Identify Services mark outs |  |  | Visual Inspection prior to framing commencem ent | Ensure Suspended Grid System and Ceiling Tiles are set out in accordance with: - Architectural Drawings - Builders works Drawings - Coordinated Services Drawings - Provided RL and Perimeter Trim Progression photos to be documented Drawings: Rev: |  |  |  |  | H X |  | S
4 |  | Installation of Suspended Ceiling System is as follows: - Suspended system is installed to set out - Fixings as per manufacturer’s guidelines - True and plumb - Installation of Ceiling System as per engineers’ details for the ceiling type |  |  | Visual Inspection prior to fixing ceiling linings | Ensure Suspended Ceiling System is installed in accordance with: - Architectural Drawings - Design Specifications - Latest Drawing References and Revisions Progression photos to be documented Hold point. Sign off by other trades witnessed Drawings: Rev: |  |  |  |  | H X |  | S
5 |  | Overall Ceiling Tiles installation as follows: a. Ceiling Tiles - Type and Material - Colour and Finish - Size and Thickness - Neatness of Cutting - Fixing and Jointing - Squareness and Flatness - Smoothness and Uniformity - Lapping and Staggering b. Control Joint - Control Joint Locations c. Insulation - Insulation is installed as per acoustic and thermal requirements d. Noggings as required |  |  | Visual Inspection upon installation of lining | Ensure the ceiling tiles, joints and insulation is installed in accordance with: - Architectural Drawings - Design Specifications - Latest Drawing References and Revisions Progression photos to be documented Hold point. Sign off by other trades witnessed Drawings: Rev: |  |  |  |  | H X |  | S
6 |  | External Works / Inspections to be completed Prior to Closure of Ceiling: - Services rough in completed - Lendlease Inspection Completed - Insulation Installed |  |  | Visual Inspection Prior to Closure | Ensure the completed works is installed in accordance with: - Architectural Drawings - Design Specifications - Latest Drawing References and Revisions Verify with Lendlease: Pre-close up checklist is completed Progression photos to be documented Hold point. Sign off by other trades witnessed Drawings: Rev: |  |  |  |  | H X |  | S |  |  | Pre-close Checklist Completion Date:
7 |  | Closing in of Ceiling: - Type and Material - Colour and Finish - Size and Thickness - Neatness of Cutting - Fixing and Jointing - Squareness and Flatness - Smoothness and Uniformity - Lapping and Staggering - Set and Sand Ceiling - Control Joint Locations |  |  | Visual Inspection upon completion of works | Ensure the completed works is installed in accordance with: - Architectural Drawings - Design Specifications - Latest Drawing References and Revisions Progression photos to be documented Hold point. Sign off by other trades witnessed Drawings: Rev: |  |  |  |  | H H |  | H
8 |  | ARCHITECTURAL NOTIFICATION OF FINAL INSPECTION Notice of Inspection: - Correct all Defects - Supply Certificate of Compliance |  |  | Upon Completion | Ensure Final Works Completion is in accordance with: - Client Defects List - Architectural Drawings Drawings: Rev: |  |  |  |  | H H
VERIFICATION IDENTITY |  |  | COMPANY REP. WITH AUTHORITY |  |  |  | SIGNATURE / INITIAL | [6 empty] | ATTACH
Lendlease | [13 empty] |  Product Details
Arc Plastering | [13 empty] |  Sample Material