## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Ceiling | itp |  |  |  |  | Arc - ITP - Ceilings - Rev02
section | Details
checkpoint | 1. Approve Samples as follows:
label | – Manufacturer’s / supplier’s recommendations
label | – Product Data
label | – Review CiDD Alerts and Guidelines
label | – Engineering design recommendations
label | – Seismic Design and compliance certificate of framing and fixings provided to Lendlease and approved
label | ○ If applicable, ensure prototype is built / supplied on site
label | Inspection Procedure - Prior to Delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - At project commencement, ensure samples reflect:
label | – Architectural specifications and latest:
label | – Material finishes schedule
label | – Drawings
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 2. Check delivery of Ceiling Framing as follows:
label | – Type and material
label | – Finish
label | – Size and Section
label | Inspection Procedure - Visual Inspection upon delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Check delivery dockets / checklist to ensure:
label | – Orders comply with design documentation
label | – Deliveries match orders
label | ○ Ensure the below can be provided for all materials (where appropriate) and upon completion of sections:
label | – Traceability
label | – Certificates of Compliance
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 2. Check delivery of Ceiling linings as follows:
label | – Type and material
label | – Grade or Class
label | – Colour, Finish and Texture
label | – Size and Thickness
label | – Squareness and Flatness
label | – Edge Profile
label | Inspection Procedure - Visual Inspection upon delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Check delivery dockets / checklist to ensure:
label | – Orders comply with design documentation
label | – Deliveries match orders
label | ○ Ensure the below can be provided for all materials (where appropriate) and upon completion of sections:
label | – Traceability
label | – Certificates of Compliance
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 3. Complete set out of ceiling as follows:
label | – Structure is stripped and free from debris
label | – Ceiling is set out as per plans and provided RL
label | – Levels
label | – Identify ceiling codes by framing type and lining applied
label | – Ceiling framing specification required
label | – Sequence in which the frame work must be installed
label | – Method of installation
label | – Reference revision floor plans
label | – Identify Services mark outs
label | Inspection Procedure - Visual Inspection prior to framing commencem ent
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure ceiling set out is in accordance with:
label | – Architectural Drawings
label | – Builders works Drawings
label | – Coordinated Services Drawings
label | – Provided RL
label | ○ Progression photos to be documented
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
checkpoint | 4. Ceiling frame work as follows:
label | – Frame work is installed to set out
label | – Fixings as per manufacturer’s guidelines
label | – True and plumb
label | – Installation of steel framing as per engineers’ details for the ceiling type
label | Inspection Procedure - Visual Inspection prior to fixing ceiling linings
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure ceiling frame work is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
holdpoint | HOLD POINT
checkpoint | 5. Overall lining installation as follows:
label | a. Ceiling Linings
label | – Type and Material
label | – Colour and Finish
label | – Size and Thickness
label | – Neatness of Cutting
label | – Fixing and Jointing
label | – Squareness and Flatness
label | – Smoothness and Uniformity
label | – Lapping and Staggering
label | b. Control Joint
label | – Control Joint Locations
label | c. Insulation
label | – Insulation is installed as per acoustic and thermal requirements
label | Inspection Procedure - Visual Inspection upon installation of lining
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure the lining, joints and insulation is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
holdpoint | HOLD POINT
checkpoint | 6. External Works / Inspections to be completed Prior to Closure of Ceiling:
label | – Services rough in completed
label | – Lendlease Inspections Completed
label | – Insulation Installed
label | Inspection Procedure - Visual Inspection Prior to Closure
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure the completed works is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Verify with Lendlease: Pre-close up checklist is completed
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
date | Comments - Pre-close Checklist Completion Date:
holdpoint | HOLD POINT
checkpoint | 7. Closing in of Ceilings:
label | – Type and Material
label | – Colour and Finish
label | – Size and Thickness
label | – Neatness of Cutting
label | – Fixing and Jointing
label | – Squareness and Flatness
label | – Smoothness and Uniformity
label | – Lapping and Staggering
label | – Set and Sand Ceiling
label | – Control Joint Locations
label | Inspection Procedure - Visual Inspection upon completion of works
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure the completed works is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, H
label | Lendlease: Key - H
holdpoint | HOLD POINT
checkpoint | 8. ARCHITECTURAL NOTIFICATION OF FINAL INSPECTION
label | ○ Notice of Inspection:
label | – Correct all Defects
label | – Supply Certificate of Compliance
label | Inspection Procedure - Upon Completion
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure Final Works Completion is in accordance with:
label | – Client Defects List
label | – Architectural Drawings
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, H
checklist | Skirting | itp |  |  |  |  | Arc - ITP - Skirting
section | Details
checkpoint | 1. Approve Samples as follows:
label | – Manufacturer’s / supplier’s recommendations
label | – Product Data
label | – Review CiDD Alerts and Guidelines
label | – Engineering design recommendations
label | – Seismic Design and compliance certificate of framing and fixings provided to Lendlease and approved
label | ○ If applicable, ensure prototype is built / supplied on site
label | Inspection Procedure - Prior to Delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - At project commencement, ensure samples reflect:
label | – Architectural specifications and latest:
label | – Material finishes schedule
label | – Drawings
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 2. Check delivery of Skirting is as follows:
label | – Type and material
label | – Colour, Finish and Texture
label | – Size, Section and Thickness
label | Inspection Procedure - Visual Inspection upon delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Check delivery dockets / checklist to ensure:
label | – Orders comply with design documentation
label | – Deliveries match orders
label | ○ Ensure the below can be provided for all materials (where appropriate) and upon completion of sections:
label | – Traceability
label | – Certificates of Compliance
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 3. Complete set out of skirting as follows:
label | – Structure is stripped and free from debris
label | – Ceiling is set out as per plans and provided RL
label | – Levels
label | – Identify skirting codes by framing type and lining applied
label | – Skirting specification required
label | – Method of installation
label | – Reference revision floor plans
label | Inspection Procedure - Visual Inspection prior to framing commence ment
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure skirting set out is in accordance with:
label | – Architectural Drawings
label | – Builders works Drawings
label | – Coordinated Services Drawings
label | – Provided RL
label | ○ Progression photos to be documented
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
checkpoint | 4. Skirting completion is as follows:
label | – Walls are installed to set out
label | – Fixings as per manufacturer’s guidelines
label | – True and plumb
label | – Installation of skirting as per engineers’ details for the wall type
label | Inspection Procedure - Visual Inspection
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure skirting is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
holdpoint | HOLD POINT
checkpoint | 5. Installation of Corners/mitres is as follows:
label | – Skirtings are installed to set out
label | – Fixings as per manufacturer’s guidelines
label | – True and plumb
label | – Installation of corner/mitres as per engineers’ details for the wall type
label | Inspection Procedure - Visual Inspection
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure corners/mitres are installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
holdpoint | HOLD POINT
checkpoint | 6. ARCHITECTURAL NOTIFICATION OF FINAL INSPECTION
label | ○ Notice of Inspection:
label | – Correct all Defects
label | – Supply Certificate of Compliance
label | Inspection Procedure - Upon Completion
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure Final Works Completion is in accordance with:
label | – Client Defects List
label | – Architectural Drawings
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, H
checklist | Speedpanel | itp |  |  |  |  | Arc - ITP - Speedpanel
section | Details
checkpoint | 1. Approve Samples as follows:
label | – Manufacturer’s / supplier’s recommendations
label | – Product Data
label | – Review CiDD Alerts and Guidelines
label | – Engineering design recommendations
label | – Seismic Design and compliance certificate of framing and fixings provided to Lendlease and approved
label | If applicable, ensure prototype is built / supplied on site
label | Inspection Procedure - Prior to Delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - At project commencement, ensure samples reflect:
label | – Architectural specifications and latest:
label | – Material finishes schedule
label | – Drawings
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 2. Check delivery of Speedpanel as follows:
label | – Type and material
label | – Colour and Finish
label | – Grade or Class
label | – Size and Thickness
label | – Squareness and Flatness
label | – Edge Profile
label | Inspection Procedure - Visual Inspection upon delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Check delivery dockets / checklist to ensure:
label | – Orders comply with design documentation
label | – Deliveries match orders
label | ○ Ensure the below can be provided for all materials (where appropriate) and upon completion of sections:
label | – Traceability
label | – Certificates of Compliance
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 3. Complete set out of Speedpanel as follows:
label | – Structure is stripped and free from debris
label | – Identify wall codes by framing type and lining applied
label | – Speedpanel framing specification required
label | – Sequence in which the frame work must be installed
label | – Method of installation
label | – Reference revision floor plans
label | – Identify Services mark outs
label | Inspection Procedure - Visual Inspection prior to framing commence ment
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure ceiling set out is in accordance with:
label | – Architectural Drawings
label | – Builders works Drawings
label | – Coordinated Services Drawings Progression photos to be documented
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
checkpoint | 4. Speedpanel frame work as follows:
label | – Frame work is installed to set out
label | – Fixings as per manufacturer’s guidelines
label | – True and plumb
label | – Installation of steel framing as per engineers’ details for the wall type
label | Inspection Procedure - Visual Inspection prior to fixing speedpanel
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure ceiling frame work is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
holdpoint | HOLD POINT
checkpoint | 5. External Works / Inspections to be completed Prior to Closure of Wall:
label | – Services rough in completed
label | – Lendlease Inspections Completed
label | – Insulation Installed (where applicable)
label | Inspection Procedure - Visual Inspection Prior to Closure
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure the completed works is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Verify with Lendlease: Pre-close up checklist is completed
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
date | Comments - Pre-close Checklist Completion Date:
holdpoint | HOLD POINT
checkpoint | 6. Overall Speedpanel installation as follows:
label | a. Speedpanel
label | – Type and Material
label | – Colour and Finish
label | – Size and Thickness
label | – Neatness of Cutting
label | – Fixing and Jointing
label | – Squareness and Flatness
label | – Smoothness and Uniformity
label | – Lapping and Staggering
label | b. Control Joint
label | – Control Joint Locations
label | c. Insulation (where applicable)
label | – Insulation is installed as per acoustic and thermal requirements
label | Inspection Procedure - Visual Inspection upon installation of speedpanel
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure the speedpanel, joints and insulation is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
holdpoint | HOLD POINT
checkpoint | 7. Speedpanel Caulking is completed as follows:
label | – Type and Material
label | – Colour
label | – Installed as per acoustic and thermal requirements
label | Inspection Procedure - Visual Inspection
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure caulking is completed in accordance with:
label | – Materials finishes schedule
label | – Manufacturer’s specifications
label | – All gaps are infilled
label | ○ Progression photos to be documented
label | Arc Plastering: Key - X
checkpoint | 8. ARCHITECTURAL NOTIFICATION OF FINAL INSPECTION
label | Notice of Inspection:
label | – Correct all Defects
label | – Supply Certificate of Compliance
label | Inspection Procedure - Upon Completion
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure Final Works Completion is in accordance with:
label | – Client Defects List
label | – Architectural Drawings
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, H
checklist | Suspended Tile Ceiling | itp |  |  |  |  | Arc - ITP - Suspended Tile Ceilings - Rev02
section | Details
checkpoint | 1. Approve Samples as follows:
label | – Manufacturer’s / supplier’s recommendations
label | – Product Data
label | – Review CiDD Alerts and Guidelines
label | – Engineering design recommendations
label | – Seismic Design and compliance certificate of framing and fixings provided to Lendlease and approved
label | ○ If applicable, ensure prototype is built / supplied on site
label | Inspection Procedure - Prior to Delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - At project commencement, ensure samples reflect:
label | – Architectural specifications and latest:
label | – Material finishes schedule
label | – Drawings
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 2. Check delivery of Suspended Grid System as follows:
label | – Type and material
label | – Finish
label | – Size and Section
label | Inspection Procedure - Visual Inspection upon delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Check delivery dockets / checklist to ensure:
label | – Orders comply with design documentation
label | – Deliveries match orders
label | ○ Ensure the below can be provided for all materials (where appropriate) and upon completion of sections:
label | – Traceability
label | – Certificates of Compliance
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 2. Check delivery of Ceiling Tiles as follows:
label | – Type and material
label | – Grade or Class
label | – Colour, Finish and Texture
label | – Size and Thickness
label | – Squareness and Flatness
label | – Edge Profile
label | Inspection Procedure - Visual Inspection upon delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Check delivery dockets / checklist to ensure:
label | – Orders comply with design documentation
label | – Deliveries match orders
label | ○ Ensure the below can be provided for all materials (where appropriate) and upon completion of sections:
label | – Traceability
label | – Certificates of Compliance
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 3. Complete set out of Ceiling Grids as follows:
label | – Structure is stripped and free from debris
label | – Grid lines are in place – specifically check for building creep
label | – Grid system is set out as per plans and builders works penetrations marked
label | – Levels
label | – Identify ceiling codes by grid system and tiles applied
label | – Suspended Ceiling Grid System and tiles specification required
label | – Sequence in which the Suspended Ceiling Tiles must be installed
label | – Method of installation
label | – Reference revision floor plans
label | – Identify Services mark outs
label | Inspection Procedure - Visual Inspection prior to framing commencem ent
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure Suspended Grid System and Ceiling Tiles are set out in accordance with:
label | – Architectural Drawings
label | – Builders works Drawings
label | – Coordinated Services Drawings
label | – Provided RL and Perimeter Trim Progression photos to be documented
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
checkpoint | 4. Installation of Suspended Ceiling System is as follows:
label | – Suspended system is installed to set out
label | – Fixings as per manufacturer’s guidelines
label | – True and plumb
label | – Installation of Ceiling System as per engineers’ details for the ceiling type
label | Inspection Procedure - Visual Inspection prior to fixing ceiling linings
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure Suspended Ceiling System is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
holdpoint | HOLD POINT
checkpoint | 5. Overall Ceiling Tiles installation as follows:
label | a. Ceiling Tiles
label | – Type and Material
label | – Colour and Finish
label | – Size and Thickness
label | – Neatness of Cutting
label | – Fixing and Jointing
label | – Squareness and Flatness
label | – Smoothness and Uniformity
label | – Lapping and Staggering
label | b. Control Joint
label | – Control Joint Locations
label | c. Insulation
label | – Insulation is installed as per acoustic and thermal requirements
label | d. Noggings as required
label | Inspection Procedure - Visual Inspection upon installation of lining
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure the ceiling tiles, joints and insulation is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
holdpoint | HOLD POINT
checkpoint | 6. External Works / Inspections to be completed Prior to Closure of Ceiling:
label | – Services rough in completed
label | – Lendlease Inspection Completed
label | – Insulation Installed
label | Inspection Procedure - Visual Inspection Prior to Closure
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure the completed works is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Verify with Lendlease: Pre-close up checklist is completed
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
date | Comments - Pre-close Checklist Completion Date:
holdpoint | HOLD POINT
checkpoint | 7. Closing in of Ceiling:
label | – Type and Material
label | – Colour and Finish
label | – Size and Thickness
label | – Neatness of Cutting
label | – Fixing and Jointing
label | – Squareness and Flatness
label | – Smoothness and Uniformity
label | – Lapping and Staggering
label | – Set and Sand Ceiling
label | – Control Joint Locations
label | Inspection Procedure - Visual Inspection upon completion of works
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure the completed works is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, H
label | Lendlease: Key - H
holdpoint | HOLD POINT
checkpoint | 8. ARCHITECTURAL NOTIFICATION OF FINAL INSPECTION
label | ○ Notice of Inspection:
label | – Correct all Defects
label | – Supply Certificate of Compliance
label | Inspection Procedure - Upon Completion
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure Final Works Completion is in accordance with:
label | – Client Defects List
label | – Architectural Drawings
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, H
checklist | Wall Framing | itp |  |  |  |  | Arc - ITP - Wall Framing
section | Details
checkpoint | 1. Approve Samples as follows:
label | – Manufacturer’s / supplier’s recommendations
label | – Product Data
label | – Review CiDD Alerts and Guidelines
label | – Engineering design recommendations
label | ○ If applicable, ensure prototype is built / supplied on site
label | Inspection Procedure - Prior to Delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - At project commencement, ensure samples reflect:
label | – Architectural specifications and latest:
label | – Material finishes schedule
label | – Drawings
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 2. Check delivery of Wall Framing as follows:
label | – Type and material
label | – Finish
label | – Size and Section
label | Inspection Procedure - Visual Inspection upon delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Check delivery dockets / checklist to ensure:
label | – Orders comply with design documentation
label | – Deliveries match orders
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 2. Check delivery of Wall linings as follows:
label | – Type and material
label | – Grade or Class
label | – Colour, Finish and Texture
label | – Size and Thickness
label | – Squareness and Flatness
label | – Edge Profile
label | Inspection Procedure - Visual Inspection upon delivery
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Check delivery dockets / checklist to ensure:
label | – Orders comply with design documentation
label | – Deliveries match orders
label | Arc Plastering: Key - S
label | Lendlease: Key - S
checkpoint | 3. Complete set out of Partitions as follows:
label | – Structure is stripped and free from debris
label | – Grid lines are in place – specifically check for building creep
label | – Partitions are set out as per plans and builders works penetrations marked
label | – Levels
label | – Identify wall codes by framing type and lining applied
label | – Wall framing specification required
label | – Sequence in which the frames must be installed
label | – Method of installation
label | – Reference revision floor plans
label | – Identify Services mark outs
label | Inspection Procedure - Visual Inspection prior to framing commencem ent
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure partition set out is in accordance with:
label | – Architectural Drawings
label | – Builders works Drawings
label | – Coordinated Services Drawings
label | Progression photos to be documented
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
checkpoint | 4. Installation of Framing as follows:
label | – Frames installed to set out
label | – Fixings as per manufacturer’s guidelines
label | – True and plumb
label | – Installation of top bracket as per engineers’ details for the wall type
label | Inspection Procedure - Visual Inspection prior to fixing ceiling linings
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure framing is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
holdpoint | HOLD POINT
checkpoint | 5. Overall lining installation as follows:
label | a. Wall Linings
label | – Type and Material
label | – Colour and Finish
label | – Size and Thickness
label | – Neatness of Cutting
label | – Fixing and Jointing
label | – Squareness and Flatness
label | – Smoothness and Uniformity
label | – Lapping and Staggering
label | b. Control Joint
label | – Control Joint Locations
label | c. Insulation
label | – Insulation is installed as per acoustic and thermal requirements
label | d. Noggings as required
label | Inspection Procedure - Visual Inspection upon installation of lining
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure the lining, joints and insulation is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - S
date | Comments - Date:
holdpoint | HOLD POINT
checkpoint | 6. External Works / Inspections to be completed Prior to Closure of Walls:
label | – Services rough in completed
label | – Insulation Installed
label | Inspection Procedure - Visual Inspection Prior to Closure
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure the completed works is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, X
label | Lendlease: Key - H(C)
holdpoint | HOLD POINT
checkpoint | 7. Closing in of Walls:
label | – Type and Material
label | – Colour and Finish
label | – Size and Thickness
label | – Neatness of Cutting
label | – Fixing and Jointing
label | – Squareness and Flatness
label | – Smoothness and Uniformity
label | – Lapping and Staggering
label | – Set and Sand Linings
label | – Control Joint Locations
label | Inspection Procedure - Visual Inspection upon completion of works
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure the completed works is installed in accordance with:
label | – Architectural Drawings
label | – Design Specifications
label | – Latest Drawing References and Revisions
label | ○ Progression photos to be documented
label | ○ Hold point. Sign off by other trades witnessed
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, H
label | Lendlease: Key - H
holdpoint | HOLD POINT
checkpoint | 8. ARCHITECTURAL NOTIFICATION OF FINAL INSPECTION
label | ○ Notice of Inspection:
label | – Correct all Defects
label | – Supply Certificate of Compliance
label | Inspection Procedure - Upon Completion
label | ACCEPTANCE CRITERIA Specification / Standard / Drawings - Ensure Final Works Completion is in accordance with:
label | – Client Defects List
label | – Architectural Drawings
textbox | Drawings:
textbox | Rev:
label | Arc Plastering: Key - H, H