## Saddle Hill
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | Saddle Hill (SH 001) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Repair Surface Depression - Mill and Fill Method |  |  | DN-GD-GP041/Insitu Stabi. Log/ Excavation Log/Scala Log |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) |  |  | Ground Distrubance Permit/Clegg Value Log |  |  |  | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
Downer | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Preparation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP041/Ground Distrubance Permit | YES | W(10%) | R | H |  |  | W & I | Supplier
2 | Milling |  | Sub Sup/Downer Eng | Check depth with a straight edge or string line | Every 10m or based on the site length | DN-GD-GP041 | YES | W(10%) | R | H
3 | Base Layer Acceptance (Clegg Value) |  | Sub Sup/Downer Eng | Value of 25-35 needed | After every 1m | DN-GD-GP041/Clegg Log | YES | W(10%) | R | H
4 | Application of Binder (Tack Coat) |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP041 | YES | W(10%) | R | H
5 | Premix Selection |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP041 | YES | W(10%) | R | H
6 | Laying Premix Material |  | Sub Sup/Downer Eng | Lay Premix in even thickness layers | In-process | DN-GD-GP041 | YES | W(10%) | R | H
7 | Final Compaction |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP041 | NO | W(10%) | R | H
8 | Blinding |  | Sub Sup/Downer Eng | Blinding with sand and restore road marking | In-process | DN-GD-GP041 | NO | R | R | H
9 | Test and Check |  | Sub Sup/Downer Eng | Any depression must be less than 5mm | In-process | DN-GD-GP041 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Luiz Christofoletti |  | Edward Hails
DATE: 15/04/2024 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client