## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - CONOC Operations - Saddle Hill - Repair Surface Depression - Mill and Fill Method | itp |  |  |  |  | ITP - CONOC Operations (Heavy Maintenance) - Saddle Hill - Repair Surface Depression - Mill and Fill Method
checkpoint | 1 - Preparation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Ground Distrubance Permit
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Milling
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Check depth with a straight edge or string line
label | Frequency Of Inspection Or Test - Every 10m or based on the site length
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Base Layer Acceptance (Clegg Value)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Value of 25-35 needed
label | Frequency Of Inspection Or Test - After every 1m
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Clegg Log
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Application of Binder (Tack Coat)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Premix Selection
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Laying Premix Material
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Lay Premix in even thickness layers
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Final Compaction
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Blinding
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Blinding with sand and restore road marking
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Any depression must be less than 5mm
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations - Milton - Repair Surface Depression - Mill and Fill Method | itp |  |  |  |  | ITP - CONOC Operations (Heavy Maintenance) - Milton - Repair Surface Depression - Mill and Fill Method
checkpoint | 1 - Preparation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Ground Distrubance Permit
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Milling
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Check depth with a straight edge or string line
label | Frequency Of Inspection Or Test - Every 10m or based on the site length
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Base Layer Acceptance (Clegg Value)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Value of 25-35 needed
label | Frequency Of Inspection Or Test - After every 1m
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Clegg Log
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Application of Binder (Tack Coat)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Premix Selection
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Laying Premix Material
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Lay Premix in even thickness layers
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Final Compaction
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Blinding
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Blinding with sand and restore road marking
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Any depression must be less than 5mm
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT