## Sheet1
type | name | values | prefix | postfix
checklist | Balcony
section | Substrate inspection
checkpoint | All prior works done
checkpoint | Waterproofing completed by others
section | Balcony deck tiling
checkpoint | Setting out refer to drawing/ COS
checkpoint | Nurajack NM install follow manufacturer specification
checkpoint | Tile lippiness checked and to acceptable standard
checkpoint | Tile interlocked with each others, stable and not moving/rocking
section | Final check and Sign off
checkpoint | Tiling Completed
checkpoint | Photo Taken of Completed Area
signoff | Sign off and Handover
checklist | Variation Contract -
checkpoint | Job Details
textbox | Details of Work (Inc. Location):
textbox | Client:
textbox | Reason for Variation:
textbox | Project:
textbox | Job No:
textbox | Hours:
textbox | Site Instruction No:
textbox | Materials Equipment:
textbox | Agreed Value:
checkpoint | Work Details:
textbox | Details of Work (Inc. Location):
textbox | Name:
textbox | Reason for Variation:
textbox | Hours:
textbox | Materials Equipment:
textbox | Agreed Value:
checkpoint | Foreman Sign Off
textbox | Name:
textbox | Name:
checkpoint | Project Manager Sign Off
textbox | Name:
textbox | Name:
checkpoint | Signature of Authorising Officer
textbox | Name:
checklist | Powder Room and Laundry
section | Substrate inspection
checkpoint | All prior works done
checkpoint | Floor grinded if required
section | Soundproofing
checkpoint | Pe foam tape to perimeter
checkpoint | Install acoustic
section | Waterproofing
checkpoint | band to wall and floor junction/ penetration
checkpoint | SAt Gasket to floor waste
checkpoint | Specified waterproofing 1st coat
checkpoint | Specified waterproofing 2nd coat
checkpoint | waterproof thickness minimum 1 mm after 2 coats
section | Tiling
checkpoint | Setting out tiles according to home owner or construction drawing / Site confirmation
checkpoint | Primer applied prior to tiling
checkpoint | Full coverage of tiles with adhesive
checkpoint | Tile lippiness checked and to acceptable standard( 0.5 mm with 2mm spacers)
checkpoint | Finishing trims & transition bars edge alignment
checkpoint | Skirting Tile Installed
section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
checkpoint | Grout work properly into all joint
checkpoint | Silicone applied to an acceptable finish
section | Completion
checkpoint | Tiling complete
checkpoint | Photo taken of completed area
signoff | Sign off and handover
checklist | Bathroom
section | Substrate inspection
checkpoint | All prior works done
checkpoint | Floor grinded if required
checkpoint | Wall square and plumb
checkpoint | Cavity slider wall installed properly
checkpoint | Ceiling installed and painted
section | Showerbase
checkpoint | Primed
section | Soundproofing (Regupol)
checkpoint | Pe foam tape to perimeter
checkpoint | Install acoustic underlay w/ VS90 plus
section | Waterproofing
checkpoint | band to wall and floor junction/ penetration
checkpoint | Sat Gasket to floor waste
checkpoint | Specified waterproofing 1st coat
checkpoint | Specified waterproofing 2nd coat
checkpoint | waterproof thickness minimum 1 mm after 2 coats
checkpoint | tanking test
section | Tiling
checkpoint | Setting out tiles according to homeowners or construction drawing / Site confirmation
checkpoint | Primer applied prior to tiling
checkpoint | Full coverage of tiles with adhesive
checkpoint | Tile lippiness checked and to acceptable standard
checkpoint | Finishing trims & transition bars edge alignment
checkpoint | Skirting Tile Installed
section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
checkpoint | Grout work properly into all joint
checkpoint | Silicone applied to a acceptable finish
section | Completion
checkpoint | Tiling complete
checkpoint | Photo taken of completed area
signoff | Sign off and handover
checklist | Kitchen splashback
section | Waterproofing
checkpoint | band to wall penetration
checkpoint | Specified waterproofing 1st coat
checkpoint | Specified waterproofing 2nd coat
section | Tiling
checkpoint | Setting out tiles according to construction drawing / Site confirmation
checkpoint | Primer applied prior to tiling
checkpoint | Full coverage of tiles with adhesive
checkpoint | Tile lippiness checked and to acceptable standard
checkpoint | Finishing trims & transition bars edge alignment
section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
checkpoint | Grout work properly into all joint
checkpoint | Silicone applied to an acceptable finish
section | Completion
checkpoint | Tiling complete
checkpoint | Photo taken of completed area
signoff | Sign off and handover
type | name | values | prefix | postfix
checklist | Waterstop for Area:
section | Waterstop Area of Installation
checkpoint | Checklist named with location or text box below or marked up drawing attached
textbox | Description, grid sections, etc:
section | Waterstop Site & Substrate Prep
checkpoint | Substrate is acceptable
checkpoint | Confirm appropriate Waterstop-RX is going to be used in relation to concrete thickness
textbox | Concrete pour date
checkpoint | Substrate photos taken
section | Waterstop Installation
checkpoint | Waterstophas been installed as per specifications
checkpoint | All parties aware of Waterstoprequirements in wet areas
checklist | QA - pool Waterproofing litoproof extreme
checkpoint | Substrate inspected & accepted
note | Substrate must be clean and smooth, dry and free from dust or contaminants
checkpoint | Surfaces primed with approved primer
checkpoint | Application of first layer of approved membrane
checkpoint | Application of second layer of approved membrane (where applicable)
checkpoint | Check that all penetrations are sealed with gasket
checkpoint | Flood test
note | Upload signature
checkpoint | Supplier Final Inspection (where required)
checklist | QA screeding
section
checkpoint | Review Concrete Mix Design
checkpoint | Checklist named with location or text box below or marked up drawing attached
textbox | Description, grid sections, etc:
section | Site & Substrate Prep
checkpoint | Appropriate site conditions for screeding
checkpoint | Substrate photos taken
section | "Pre-concrete pour."
checkpoint | Appropriate detailing done as per specifications
checkpoint | boxing completed as per specificastions
checkpoint | boxing photo taken
section | concrete pouring
checkpoint | Conduct Fresh Concrete Test
checkpoint | Evaluate Concrete Finishing Work
checkpoint | Perform Concrete Strength Test
texbox | Description, grid sections, etc:
note | upload signature
checklist | QA - Internal Waterproofing litoproof extreme
checkpoint | Substrate Visual inspection
checkpoint | Clean all areas of dust and debris
checkpoint | Primer to floors/walls complete
checkpoint | install waterstop
checkpoint | install litoproof extreme
checkpoint | walls and floor corners bandage installed
checkpoint | tanking inspections float test
texbox | Description, grid sections, etc:
note | upload signature