## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | QA - Balconies Waterproofing |  |  |  |  | Yes | QA - Balconies Waterproofing | 3872b6c5-63ba-41b0-af19-853fbe2881c8
checkpoint-status |  |  | checkpoint | Substrate inspected & accepted
label | 78dfe19d-88d6-5a55-8a9c-81aad0fee98c |  | note | Substrate must be clean and smooth, dry and free from dust or contaminants. All sharp points and loose materials to be removed.
checkpoint-status |  |  | checkpoint | Surfaces primed with approved primer
checkpoint-status |  |  | checkpoint | Application of first layer of approved membrane
checkpoint-status |  |  | checkpoint | Application of second layer of approved membrane (where applicable)
checkpoint-status |  |  | checkpoint | Check that all laps are 100 > 150 (sheet membrane systems)
checkpoint-status |  |  | checkpoint | Check that all penetrations are sealed with applicable mastic and membrane
checkpoint-status |  |  | checkpoint | Application of topcoat (where applicable)
checkpoint-status |  |  | checkpoint | Flood test (where applicable)
checkpoint-status |  |  | checkpoint | Walk over to inspect soundness
checkpoint-status |  |  | checkpoint | Builder Final Inspection (where required)
checkpoint-status |  |  | checkpoint | Subcontractor Final Inspection
label | 927f3822-4c04-5e4d-ad0f-5622164a65f5 |  | note | Upload signature
checkpoint-status |  |  | checkpoint | Supplier Final Inspection (where required)
checklist-sectioned |  |  | checklist | Waterstop-RX for Area: |  |  |  |  | Yes | Waterstop-RX for Area: | 3fe68d12-332f-4346-bb74-57175e4e48a6
checkpoint-group |  |  | section | Waterstop-RX Area of Installation
checkpoint-status |  |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | a4982523-6b64-569e-8682-558008e0bb6f |  | textbox | Description, grid sections, etc:
checkpoint-group |  |  | section | Waterstop-RX Site & Substrate Prep
checkpoint-status |  |  | checkpoint | Substrate is acceptable
checkpoint-status |  |  | checkpoint | Confirm appropriate Waterstop-RX is going to be used in relation to concrete thickness
text | a0ee67ad-1092-5f8d-a8d1-9fa2f5649881 |  | textbox | Concrete pour date
checkpoint-status |  |  | checkpoint | Substrate photos taken
checkpoint-group |  |  | section | Waterstop-RX Installation
checkpoint-status |  |  | checkpoint | Waterstop-RX has been installed as per Allco specifications
checkpoint-status |  |  | checkpoint | All parties aware of Waterstop-RX requirements with exposure to climatic conditions
checklist-flat |  |  | checklist | QA - Waterproofing Balconies |  |  |  |  | Yes | QA - Waterproofing Balconies | 44de0950-97cf-4f65-9723-9ed7ff6dccb2
checkpoint-status |  |  | checkpoint | Substrate acceptance / Surface prep
checkpoint-status |  |  | checkpoint | Primer
checkpoint-status |  |  | checkpoint | Coat 1 / Vapour Barrier
checkpoint-status |  |  | checkpoint | Prep in between coats
checkpoint-status |  |  | checkpoint | Coat 2
checkpoint-status |  |  | checkpoint | Drying time / DFT / Testing
checkpoint-status |  |  | checkpoint | Any extras - corflutes, drainage cells, etc
checkpoint-status |  |  | checkpoint | Completions and signoff if necessary
checklist-sectioned |  |  | checklist | Voltex for Area: |  |  |  |  | Yes | Voltex for Area: | 6c6a7427-298d-44d0-bd7a-d51cd3262922
checkpoint-group |  |  | section | Voltex Area of Installation
checkpoint-status |  |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | 8d6259d7-2a5c-5358-9683-7d536ea4ee47 |  | textbox | Description, grid sections, etc:
checkpoint-group |  |  | section | Voltex Site & Substrate Prep
checkpoint-status |  |  | checkpoint | Appropriate site conditions for installation
checkpoint-status |  |  | checkpoint | Appropriate water control in place
text | 7cdab507-92a4-567e-9eca-d4c19a7771c7 |  | textbox | Concrete pour date
checkpoint-status |  |  | checkpoint | Substrate photos taken
checkpoint-group |  |  | section | Voltex Walls, Underslab and Footings
checkpoint-status |  |  | checkpoint | Membrane appropriately laid on substrate with dark grey (woven) side up
checkpoint-status |  |  | checkpoint | 100 mm overlap between each sheet, and stagger sheets end at a minimum of 300mm
checkpoint-status |  |  | checkpoint | Appropriate detailing done to external/internal corners
checkpoint-group |  |  | section | Voltex Penetrations
checkpoint-status |  |  | checkpoint | Penetrations detailed as per Allcos recommendations
checkpoint-group |  |  | section | Voltex Backfill & Protection
checkpoint-status |  |  | checkpoint | Allguard has been installed as per Allco specifications
checkpoint-status |  |  | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
text | 7d8942a6-ed06-5113-b450-4641953d33c5 |  | textbox | Backfill date
checklist-sectioned |  |  | checklist | Balcony |  |  |  |  | Yes | Balcony | 74c1e7cf-0459-4adc-a4ec-a02559918f12
checkpoint-group |  |  | section | Substrate inspection
checkpoint-status |  |  | checkpoint | All prior works done
checkpoint-status |  |  | checkpoint | Waterproofing completed by others
checkpoint-group |  |  | section | Balcony deck tiling
checkpoint-status |  |  | checkpoint | Setting out refer to drawing/ COS
checkpoint-status |  |  | checkpoint | Nurajack NM install follow manufacturer specification
checkpoint-status |  |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status |  |  | checkpoint | Tile interlocked with each others, stable and not moving/rocking
checkpoint-group |  |  | section | Final check and Sign off
checkpoint-status |  |  | checkpoint | Tiling Completed
checkpoint-status |  |  | checkpoint | Photo Taken of Completed Area
holdpoint |  |  | signoff | Sign off and Handover
checklist-flat |  |  | checklist | Protection & Backfill for Area: |  |  |  |  | Yes | Protection & Backfill for Area: | 84857d00-f471-48a6-b3c7-45ccbd153b38
checkpoint-status |  |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | 523a2070-ea82-5982-a3e0-531c9eedd786 |  | textbox | Description, grid sections, etc:
checkpoint-status |  |  | checkpoint | Allguard has been installed as per Allco specifications?
checkpoint-status |  |  | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm?
text | d8628e7f-b881-5932-80aa-fc9466ac446a |  | textbox | Backfill date
checklist-sectioned |  |  | checklist | Sweltite for Area: |  |  |  |  | Yes | Sweltite for Area: | 85eb04ee-8d95-4200-81cf-89b4abb2bd85
checkpoint-group |  |  | section | Sweltite Area of Installation
checkpoint-status |  |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | 7d9b4826-b6f4-5e9d-aee2-87dce1222351 |  | textbox | Description, grid sections, etc:
checkpoint-group |  |  | section | Sweltite Site & Substrate Prep
checkpoint-status |  |  | checkpoint | Appropriate site conditions for installation
checkpoint-status |  |  | checkpoint | Appropriate water control in place
checkpoint-status |  |  | checkpoint | Substrate photos taken
checkpoint-group |  |  | section | Sweltite - Foundation walls
checkpoint-status |  |  | checkpoint | Appropriate detailing done as per Allco specifications
checkpoint-status |  |  | checkpoint | Ensure 100mm laps between membrane
checkpoint-status |  |  | checkpoint | All laps seam taped horizontally & vertically using Allco seam tape
checkpoint-status |  |  | checkpoint | Sweltite exceeds 150mm past F.F.L
checkpoint-status |  |  | checkpoint | Drainage coil has been placed 100mm from the floor/wall joint
checkpoint-group |  |  | section | Sweltite Penetrations
checkpoint-status |  |  | checkpoint | Penetrations detailed appropriately using appropriate accessory Volclay products
checkpoint-group |  |  | section | Sweltite Termination
checkpoint-status |  |  | checkpoint | Termination bar used on vertical & horizonal edges
checkpoint-status |  |  | checkpoint | Cetcoat applied at appropriate areas
checkpoint-status |  |  | checkpoint | Termination sealed off correctly (i.e. M2000, Cetseal)
checkpoint-group |  |  | section | Sweltite Backfill & Protection
checkpoint-status |  |  | checkpoint | Allguard has been installed as per Allco specifications
checkpoint-status |  |  | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
text | 929d2b4a-2e24-5165-a1b8-57c16fd340a7 |  | textbox | Backfill date
checklist-flat |  |  | checklist | QA - Internal Waterproofing |  |  |  |  | Yes | QA - Internal Waterproofing | 9de84fe9-e80b-4712-aa69-6f299d0d3894
checkpoint-status |  |  | checkpoint | Substrate preparation test - Visual inspection
checkpoint-status |  |  | checkpoint | Clean all areas of dust and debris
checkpoint-status |  |  | checkpoint | Primer to floors/walls complete
checkpoint-status |  |  | checkpoint | Sealed all walls and floor corners
checkpoint-status |  |  | checkpoint | Waterproofing to walls & Floors
checkpoint-status |  |  | checkpoint | Water tested all bathrooms & Undertook flood testing - Visual inspection
checkpoint-status |  |  | checkpoint | Ready for screed
checklist-sectioned |  |  | checklist | Bathroom |  |  |  |  | Yes | Bathroom | aa9fd2b1-e3f1-4c7f-8961-c25597c04edb
checkpoint-group |  |  | section | Substrate inspection
checkpoint-status |  |  | checkpoint | All prior works done
checkpoint-status |  |  | checkpoint | Floor grinded if required
checkpoint-status |  |  | checkpoint | Wall square and plumb
checkpoint-status |  |  | checkpoint | Cavity slider wall installed properly
checkpoint-status |  |  | checkpoint | Ceiling installed and painted
checkpoint-group |  |  | section | Showerbase
checkpoint-status |  |  | checkpoint | Primed using Eco prime Grip
checkpoint-group |  |  | section | Soundproofing (Regupol)
checkpoint-status |  |  | checkpoint | Pe foam tape to perimeter
checkpoint-status |  |  | checkpoint | Install acoustic underlay w/ VS90 plus
checkpoint-group |  |  | section | Waterproofing
checkpoint-status |  |  | checkpoint | Mapeband SA to wall and floor junction/ penetration
checkpoint-status |  |  | checkpoint | Mapeband SA Gasket to floor waste
checkpoint-status |  |  | checkpoint | Specified waterproofing 1st coat
checkpoint-status |  |  | checkpoint | Mapenet 150 install with 1st coat waterproofing if using Mapelastic Smart
checkpoint-status |  |  | checkpoint | Mapenet 150 not touching Mapeband SA
checkpoint-status |  |  | checkpoint | Specified waterproofing 2nd coat
checkpoint-status |  |  | checkpoint | Mapenet 150 mesh should be invincible or less visible after 2nd coat to ensure required thickness achieve.
checkpoint-status |  |  | checkpoint | Water test if required
checkpoint-group |  |  | section | Tiling
checkpoint-status |  |  | checkpoint | Setting out tiles according to construction drawing / Site confirmation
checkpoint-status |  |  | checkpoint | Primer applied prior to tiling
checkpoint-status |  |  | checkpoint | Full coverage of tiles with adhesive
checkpoint-status |  |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status |  |  | checkpoint | Finishing trims & transition bars edge alignment
checkpoint-status |  |  | checkpoint | Skirting Tile Installed
checkpoint-group |  |  | section | Grout and silicone
checkpoint-status |  |  | checkpoint | Adhesive fully cured and clean properly
checkpoint-status |  |  | checkpoint | Grout work properly into all joint
checkpoint-status |  |  | checkpoint | Silicone applied to a acceptable finish
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Tiling complete
checkpoint-status |  |  | checkpoint | Photo taken of completed area
holdpoint |  |  | signoff | Sign off and handover
checklist-flat |  |  | checklist | QA - Balcony |  |  |  |  | Yes | QA - Balcony | aea6a339-b68f-438f-b25f-ff246d1215af
checkpoint-status |  |  | checkpoint | Existing coating removed by grinding (photos)
checkpoint-status |  |  | checkpoint | Deck prepared in accordance with specification (photos)
checkpoint-status |  |  | checkpoint | Remove Joint caulking where required (photos)
checkpoint-status |  |  | checkpoint | 1st Coat of Tremco Non-porous primer to steel perimeter@ 100mm (photo's)
checkpoint-status |  |  | checkpoint | 1st Coat of Tremco MPE Epoxy Primer Applied (photo's)
checkpoint-status |  |  | checkpoint | 2nd Coat of Tremco MPE Epoxy Primer with 30/60 broadcast Applied (photo's)
checkpoint-status |  |  | checkpoint | Caulk perimeter steel junction (photos)
checkpoint-status |  |  | checkpoint | Caulk joints as required (photos)
checkpoint-status |  |  | checkpoint | 1st Coat of Tremco Vulkem 350 R Membrane Applied (photo's)
checkpoint-status |  |  | checkpoint | 1st Coat of Tremco Vulkem 951 UV stable trafficable top coat with broadcast 18/40 for non slip Applied (photo's)
checkpoint-status |  |  | checkpoint | 2nd Coat of Tremco Vulkem 951 UV stable trafficable top coat Applied (photo's)
checkpoint-status |  |  | checkpoint | Deck area complete and handover
checkpoint-status |  |  | checkpoint | ILD test report attached
checklist-sectioned |  |  | checklist | Kitchen splashback |  |  |  |  | Yes | Kitchen splashback | b0243021-dfd9-48fc-a5ff-3d45b3f6ad9b
checkpoint-group |  |  | section | Waterproofing
checkpoint-status |  |  | checkpoint | Mapeband SA to all wall penetration
checkpoint-status |  |  | checkpoint | Specified waterproofing 1st coat
checkpoint-status |  |  | checkpoint | Specified waterproofing 2nd coat
checkpoint-group |  |  | section | Tiling
checkpoint-status |  |  | checkpoint | Setting out tiles according to construction drawing / Site confirmation
checkpoint-status |  |  | checkpoint | Primer applied prior to tiling
checkpoint-status |  |  | checkpoint | Full coverage of tiles with adhesive
checkpoint-status |  |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status |  |  | checkpoint | Finishing trims & transition bars edge alignment
checkpoint-group |  |  | section | Grout and silicone
checkpoint-status |  |  | checkpoint | Adhesive fully cured and clean properly
checkpoint-status |  |  | checkpoint | Grout work properly into all joint
checkpoint-status |  |  | checkpoint | Silicone applied to an acceptable finish
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Tiling complete
checkpoint-status |  |  | checkpoint | Photo taken of completed area
holdpoint |  |  | signoff | Sign off and handover
checklist-sectioned |  |  | checklist | Hydrotech for Area: |  |  |  |  | Yes | Hydrotech for Area: | cd4e7183-a176-4da0-a905-fbdfe75813a1
checkpoint-group |  |  | section | Hydrotech Area of Installation
checkpoint-status |  |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | 413f5df7-c1be-5e39-bfc5-7f3af32bb4b3 |  | textbox | Description, grid sections, etc:
checkpoint-group |  |  | section | Hydrotech Site & Substrate Prep
checkpoint-status |  |  | checkpoint | Wind uplift has been considered prior to installation
checkpoint-status |  |  | checkpoint | Ensure all drains and outlets are membrane compatible. Confirm with Allco rep if required
checkpoint-status |  |  | checkpoint | Concrete substrate has been allowed to fully cure with a minimum wood float finish
checkpoint-status |  |  | checkpoint | Substrate clean, dry and free of debris or release agents
checkpoint-status |  |  | checkpoint | Substrate photos taken
checkpoint-group |  |  | section | Hydrotech Horizontal & Vertical Application
checkpoint-status |  |  | checkpoint | Test conducted to ensure membrane creates a mechanical bond to the substrate
label | 702c7c6b-b32c-56a7-94a9-a1805b8c5dcc |  | note | Attach application photo (1 photo per 20m2 or separate area)
checkpoint-status |  |  | checkpoint | First membrane layer applied at 3mm thickness
label | f88065db-4744-51b3-9b0e-14f9e5dc413e |  | note | Attach application photos (1 photo per 20m2)
checkpoint-status |  |  | checkpoint | Top coat of Hydrotech applied at 3mm thickness
label | 5bf40222-8660-5e0b-a68a-281251b58ce2 |  | note | Attach application photos (1 photo per 20m2)
checkpoint-status |  |  | checkpoint | Photo proving total thickness of membrane system is 9mm (including protection layer)
checkpoint-status |  |  | checkpoint | Photo of complete installation
checkpoint-group |  |  | section | Hydrotech Detailing
checkpoint-status |  |  | checkpoint | All penetrations have detailed as per Allco specifications
checkpoint-group |  |  | section | Hydrotech Terminations
checkpoint-status |  |  | checkpoint | Ensure the approved sealant or tape is used for termination
checklist-sectioned |  |  | checklist | Powder Room and Laundry |  |  |  |  | Yes | Powder Room and Laundry | e7733deb-cb45-4a32-b57d-728430afb0ad
checkpoint-group |  |  | section | Substrate inspection
checkpoint-status |  |  | checkpoint | All prior works done
checkpoint-status |  |  | checkpoint | Floor grinded if required
checkpoint-group |  |  | section | Soundproofing (Regupol)
checkpoint-status |  |  | checkpoint | Pe foam tape to perimeter
checkpoint-status |  |  | checkpoint | Install acoustic underlay w/ VS90 plus
checkpoint-group |  |  | section | Waterproofing
checkpoint-status |  |  | checkpoint | Mapeband SA to wall and floor junction/ penetration
checkpoint-status |  |  | checkpoint | Mapeband SA Gasket to floor waste
checkpoint-status |  |  | checkpoint | Specified waterproofing 1st coat
checkpoint-status |  |  | checkpoint | Mapenet 150 install with 1st coat waterproofing if using Mapelastic Smart
checkpoint-status |  |  | checkpoint | Mapenet 150 not touching Mapeband SA
checkpoint-status |  |  | checkpoint | Specified waterproofing 2nd coat
checkpoint-status |  |  | checkpoint | Mapenet 150 mesh should be invincible or less visible after 2nd coat to ensure required thickness achieve.
checkpoint-group |  |  | section | Tiling
checkpoint-status |  |  | checkpoint | Setting out tiles according to construction drawing / Site confirmation
checkpoint-status |  |  | checkpoint | Primer applied prior to tiling
checkpoint-status |  |  | checkpoint | Full coverage of tiles with adhesive
checkpoint-status |  |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status |  |  | checkpoint | Finishing trims & transition bars edge alignment
checkpoint-status |  |  | checkpoint | Skirting Tile Installed
checkpoint-group |  |  | section | Grout and silicone
checkpoint-status |  |  | checkpoint | Adhesive fully cured and clean properly
checkpoint-status |  |  | checkpoint | Grout work properly into all joint
checkpoint-status |  |  | checkpoint | Silicone applied to an acceptable finish
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Tiling complete
checkpoint-status |  |  | checkpoint | Photo taken of completed area
holdpoint |  |  | signoff | Sign off and handover
checklist-flat |  |  | checklist | Document: |  |  |  |  | Yes | Document: | e794f630-bfe5-4296-8944-d7f70c55c79b
checkpoint-status |  |  | checkpoint | Document Attached