## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Powder Room and Laundry |  |  |  |  | Yes | Powder Room and Laundry | 0962fed3-5ad3-4b7c-a2e9-c11be9c2c28a
checkpoint-group |  |  | section | Substrate inspection
checkpoint-status |  |  | checkpoint | All prior works done
checkpoint-status |  |  | checkpoint | Floor grinded if required
checkpoint-group |  |  | section | Soundproofing
checkpoint-status |  |  | checkpoint | Pe foam tape to perimeter
checkpoint-status |  |  | checkpoint | Install acoustic
checkpoint-group |  |  | section | Waterproofing
checkpoint-status |  |  | checkpoint | Band to wall and floor junction/ penetration
checkpoint-status |  |  | checkpoint | SAt Gasket to floor waste
checkpoint-status |  |  | checkpoint | Specified waterproofing 1st coat
checkpoint-status |  |  | checkpoint | Specified waterproofing 2nd coat
checkpoint-status |  |  | checkpoint | Waterproof thickness minimum 1 mm after 2 coats
checkpoint-group |  |  | section | Tiling
checkpoint-status |  |  | checkpoint | Setting out tiles according to home owner or construction drawing / Site confirmation
checkpoint-status |  |  | checkpoint | Primer applied prior to tiling
checkpoint-status |  |  | checkpoint | Full coverage of tiles with adhesive
checkpoint-status |  |  | checkpoint | Tile lippiness checked and to acceptable standard( 0.5 mm with 2mm spacers)
checkpoint-status |  |  | checkpoint | Finishing trims & transition bars edge alignment
checkpoint-status |  |  | checkpoint | Skirting Tile Installed
checkpoint-group |  |  | section | Grout and Silicone
checkpoint-status |  |  | checkpoint | Adhesive fully cured and clean properly
checkpoint-status |  |  | checkpoint | Grout work properly into all joint
checkpoint-status |  |  | checkpoint | Silicone applied to an acceptable finish
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Tiling complete
checkpoint-status |  |  | checkpoint | Photo taken of completed area
holdpoint |  |  | signoff | Sign off and handover
checklist-sectioned |  |  | checklist | Bathroom |  |  |  |  | Yes | Bathroom | cc32ad38-38ca-4237-95c1-1c81de8d69db
checkpoint-group |  |  | section | Substrate Inspection
checkpoint-status |  |  | checkpoint | All prior works done
checkpoint-status |  |  | checkpoint | Floor grinded if required
checkpoint-status |  |  | checkpoint | Wall square and plumb
checkpoint-status |  |  | checkpoint | Cavity slider wall installed properly
checkpoint-status |  |  | checkpoint | Ceiling installed and painted
checkpoint-group |  |  | section | Showerbase
checkpoint-status |  |  | checkpoint | Primed
checkpoint-group |  |  | section | Soundproofing (Regupol)
checkpoint-status |  |  | checkpoint | Pe foam tape to perimeter
checkpoint-status |  |  | checkpoint | Install acoustic underlay w/ VS90 plus
checkpoint-group |  |  | section | Waterproofing
checkpoint-status |  |  | checkpoint | Band to wall and floor junction/ penetration
checkpoint-status |  |  | checkpoint | Sat Gasket to floor waste
checkpoint-status |  |  | checkpoint | Specified waterproofing 1st coat
checkpoint-status |  |  | checkpoint | Specified waterproofing 2nd coat
checkpoint-status |  |  | checkpoint | Waterproof thickness minimum 1 mm after 2 coats
checkpoint-status |  |  | checkpoint | Tanking test
checkpoint-group |  |  | section | Tiling
checkpoint-status |  |  | checkpoint | Setting out tiles according to homeowners or construction drawing / Site confirmation
checkpoint-status |  |  | checkpoint | Primer applied prior to tiling
checkpoint-status |  |  | checkpoint | Full coverage of tiles with adhesive
checkpoint-status |  |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status |  |  | checkpoint | Finishing trims & transition bars edge alignment
checkpoint-status |  |  | checkpoint | Skirting Tile Installed
checkpoint-group |  |  | section | Grout and Silicone
checkpoint-status |  |  | checkpoint | Adhesive fully cured and clean properly
checkpoint-status |  |  | checkpoint | Grout work properly into all joint
checkpoint-status |  |  | checkpoint | Silicone applied to a acceptable finish
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Tiling complete
checkpoint-status |  |  | checkpoint | Photo taken of completed area
holdpoint |  |  | signoff | Sign off and handover
checklist-sectioned |  |  | checklist | QA - Internal Waterproofing Litoproof Extreme |  |  |  |  | Yes | QA - Internal Waterproofing Litoproof Extreme | e5ef6926-dea9-4230-adc5-85de5568a550
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Substrate Visual inspection
checkpoint-status |  |  | checkpoint | Clean all areas of dust and debris
checkpoint-status |  |  | checkpoint | Primer to floors/walls complete
checkpoint-status |  |  | checkpoint | Install waterstop
checkpoint-status |  |  | checkpoint | Install litoproof extreme
checkpoint-status |  |  | checkpoint | Walls and floor corners bandage installed
checkpoint-status |  |  | checkpoint | Tanking inspections float test
text | 8102befe-74c1-52d5-9e46-981a61bc5263 |  | textbox | Description, grid sections, etc:
label | f96c6c77-18d1-5835-bfcf-f4c2f05f6aa9 |  | note | Upload signature
checklist-sectioned |  |  | checklist | Balcony |  |  |  |  | Yes | Balcony | f14bcf57-7231-438b-8691-9def83768b7d
checkpoint-group |  |  | section | Substrate Inspection
checkpoint-status |  |  | checkpoint | All prior works done
checkpoint-status |  |  | checkpoint | Waterproofing completed by others
checkpoint-group |  |  | section | Balcony Deck Tiling
checkpoint-status |  |  | checkpoint | Setting out refer to drawing/ COS
checkpoint-status |  |  | checkpoint | Nurajack NM install follow manufacturer specification
checkpoint-status |  |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status |  |  | checkpoint | Tile interlocked with each others, stable and not moving/rocking
checkpoint-group |  |  | section | Final Check and Sign Off
checkpoint-status |  |  | checkpoint | Tiling Completed
checkpoint-status |  |  | checkpoint | Photo Taken of Completed Area
holdpoint |  |  | signoff | Sign off and Handover
checklist-sectioned |  |  | checklist | QA - Pool Waterproofing Litoproof Extreme |  |  |  |  | Yes | QA - Pool Waterproofing Litoproof Extreme | 89d2e6ee-1439-4682-a213-52f0aec875a7
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Substrate inspected & accepted
label | 5dd6be66-8852-5230-aacd-47b62b0d9d76 |  | note | Substrate must be clean and smooth, dry and free from dust or contaminants
checkpoint-status |  |  | checkpoint | Surfaces primed with approved primer
checkpoint-status |  |  | checkpoint | Application of first layer of approved membrane
checkpoint-status |  |  | checkpoint | Application of second layer of approved membrane (where applicable)
checkpoint-status |  |  | checkpoint | Check that all penetrations are sealed with gasket
checkpoint-status |  |  | checkpoint | Flood test
label | 0241fa03-8670-58c6-aa9b-37e02c2f32c5 |  | note | Upload signature
checkpoint-status |  |  | checkpoint | Supplier Final Inspection (where required)
checklist-sectioned |  |  | checklist | QA - Screeding |  |  |  |  | Yes | QA - Screeding | 7c4a7330-16ad-4c17-84af-d08d36f4eb6b
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Review Concrete Mix Design
checkpoint-status |  |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | afa67e98-2a9f-5f81-86e4-a77b3f8011c8 |  | textbox | Description, grid sections, etc:
checkpoint-group |  |  | section | Site & Substrate Prep
checkpoint-status |  |  | checkpoint | Appropriate site conditions for screeding
checkpoint-status |  |  | checkpoint | Substrate photos taken
checkpoint-group |  |  | section | Pre-concrete Pour
checkpoint-status |  |  | checkpoint | Appropriate detailing done as per specifications
checkpoint-status |  |  | checkpoint | Boxing completed as per specificastions
checkpoint-status |  |  | checkpoint | Boxing photo taken
checkpoint-group |  |  | section | Concrete Pouring
checkpoint-status |  |  | checkpoint | Conduct Fresh Concrete Test
checkpoint-status |  |  | checkpoint | Evaluate Concrete Finishing Work
checkpoint-status |  |  | checkpoint | Perform Concrete Strength Test
text | 7888141a-9f56-5045-8d9b-38663193eb0d |  | textbox | Description, grid sections, etc:
label | 2e320ba5-bad0-56bf-a1b3-e5fe0ad4c639 |  | note | Upload signature
checklist-sectioned |  |  | checklist | Variation Contract - |  |  |  |  | Yes | Variation Contract - | 5e82d528-6d03-4d81-95e6-af1df087970b
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Job Details
text | d53bcb03-0ce6-5c31-aea6-0aad7c7f60ce |  | textbox | Details of Work (Inc. Location):
text | d5f5dafd-7d87-5a56-8c4a-63cbb6ee223e |  | textbox | Client:
text | f457b020-b321-57ed-95f3-2fa6ed85967e |  | textbox | Reason for Variation:
text | dbe990c8-034c-59a9-80e0-7b67fcf4fec2 |  | textbox | Project:
text | c800aa0e-e57c-5b1e-88f9-80e33b647394 |  | textbox | Job No:
text | 6a5637be-681b-5558-976d-7bf293f6377d |  | textbox | Hours:
text | 5071dfe6-9d45-5f98-8011-0d6a73e55d12 |  | textbox | Site Instruction No:
text | c164771c-d964-557a-98a7-301e9bc19fa7 |  | textbox | Materials Equipment:
text | 2df27635-9259-5b8a-847e-02e83d0e2e4a |  | textbox | Agreed Value:
checkpoint-status |  |  | checkpoint | Work Details:
text | 48f257fe-4488-54d5-8c8d-51be6ce0ce19 |  | textbox | Details of Work (Inc. Location):
text | 1329ff60-b408-5a43-a73f-8c533dd11aed |  | textbox | Name:
text | 6865a9e0-d03b-5de8-86ee-430cafec56e8 |  | textbox | Reason for Variation:
text | 9235348a-a573-583f-81b1-845b540d8948 |  | textbox | Hours:
text | eddddb95-c7f9-5e66-9650-ac91609968ea |  | textbox | Materials Equipment:
text | f96dc795-0e7d-5073-bf45-9d7fb09c1cfe |  | textbox | Agreed Value:
checkpoint-status |  |  | checkpoint | Foreman Sign Off
text | 01e8f355-fe2a-5ca3-962b-fb6a3bad42af |  | textbox | Name:
checkpoint-status |  |  | checkpoint | Project Manager Sign Off
text | 7db1540a-f468-5d00-ab53-d4a6a70ca78b |  | textbox | Name:
checkpoint-status |  |  | checkpoint | Signature of Authorising Officer
text | fe9abc82-f79a-588e-b1a6-467340c803f9 |  | textbox | Name:
checklist-sectioned |  |  | checklist | Kitchen Splashback |  |  |  |  | Yes | Kitchen Splashback | 024dbb1d-64cb-44c7-be8c-dc1c6351c523
checkpoint-group |  |  | section | Waterproofing
checkpoint-status |  |  | checkpoint | Band to wall penetration
checkpoint-status |  |  | checkpoint | Specified waterproofing 1st coat
checkpoint-status |  |  | checkpoint | Specified waterproofing 2nd coat
checkpoint-group |  |  | section | Tiling
checkpoint-status |  |  | checkpoint | Setting out tiles according to construction drawing / Site confirmation
checkpoint-status |  |  | checkpoint | Primer applied prior to tiling
checkpoint-status |  |  | checkpoint | Full coverage of tiles with adhesive
checkpoint-status |  |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status |  |  | checkpoint | Finishing trims & transition bars edge alignment
checkpoint-group |  |  | section | Grout and Silicone
checkpoint-status |  |  | checkpoint | Adhesive fully cured and clean properly
checkpoint-status |  |  | checkpoint | Grout work properly into all joint
checkpoint-status |  |  | checkpoint | Silicone applied to an acceptable finish
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Tiling complete
checkpoint-status |  |  | checkpoint | Photo taken of completed area
holdpoint |  |  | signoff | Sign off and handover
checklist-sectioned |  |  | checklist | Waterstop for Area: |  |  |  |  | Yes | Waterstop for Area: | ef9046b1-5ac5-4549-a9b0-760a322ec78f
checkpoint-group |  |  | section | Waterstop Area of Installation
checkpoint-status |  |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | c6c34656-d810-5a1e-8a24-3c6b690ce3d2 |  | textbox | Description, grid sections, etc:
checkpoint-group |  |  | section | Waterstop Site & Substrate Prep
checkpoint-status |  |  | checkpoint | Substrate is acceptable
checkpoint-status |  |  | checkpoint | Confirm appropriate Waterstop-RX is going to be used in relation to concrete thickness
text | 475a96af-4c91-543d-a022-b917263fb7b5 |  | textbox | Concrete pour date
checkpoint-status |  |  | checkpoint | Substrate photos taken
checkpoint-group |  |  | section | Waterstop Installation
checkpoint-status |  |  | checkpoint | Waterstophas been installed as per specifications
checkpoint-status |  |  | checkpoint | All parties aware of Waterstoprequirements in wet areas