## Sheet1
Full Removal and Reinstatement of Membrane System
SECTION | BATCH DETAIL NUMBER OF PRODUCTS
Checkpoint | Enviro Epoxy B
Checkpoint | Enviro 700X
Checkpoint | Enviro 950 TC
SECTION | PRE COMMENCEMENT
Checkpoint | Material Management & Storage
Label | Store materials in a dry, clean place away from direct sunlight.
SECTION | SUBSTRATE PREPERATION: AS 4654.2-2012
Label | Ensure Inherited Surface is prepared to receive primer application. Properly prepare the identified areas by mechanically abrading with the use of a Pressure Washer - Rotary Walk Behind (4000PSI) or Concrete Floor Grinder - Walk Behind to remove both existing membrane system and provide adequate surface contamination and any delaminating material to allow for optimal bonding. The pressure washer shall be used to clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Remove damaged membrane and topcoat from the substrate. The membrane must be removed back to a solid, clean surface. It is imperative that a perfectly clean sound surface is exposed. Use small hand grinders to clean hard to reach areas such as at walls, corners, fixtures, and holes. Sand or generally abrade edges of repair area to give an approximately 50mm wide feathered edge.
SECTION | ENVIRO SHIELD- PRIME COAT
Checkpoint | Weather/RH
Label | Apply within 10-35°C RH must be 0-85%
Checkpoint | Application
Label | Add Enviro Epoxy B Part B (liquid hardener) to the Enviro Epoxy B Part A (base Thoroughly mix with a mechanical mixer at low speed (less than 400 RPM) prior to application. Mix for 5 minutes or until uniform. Allow to stand 5 minutes after mixing and then mix again for a minute. Overlap the existing membrane a min of 100mm, Protect the primed substrate from all contamination.
SECTION | BOND BREAKER
Label | • Apply Enviro Flex FC/compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints. • This is to be a 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas. • Allow to cure prior to over coating with membrane coats.
SECTION | Enviro 700X - First Coat
Checkpoint | Weather/RH
Label | Apply within 10-35°C RH must be 0-85%
Checkpoint | Mixing
Label | • Enviro 700X should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Checkpoint | Application
Label | • Enviro 700X to be applied by roller onto substrate and cut in with brush on terminations. • Allow for re-coating window re-coating as per Data Sheet recommendation before proceeding to second coat. • Overlap existing application to a minimum of 100mm.
SECTION | Enviro 700X - Second Coat
Checkpoint | Weather/RH
Label | Apply within 10-35°C RH must be 0-85%
Checkpoint | Mixing
Label | • Enviro 700X should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Checkpoint | Application
Label | • Enviro 700X to be applied by roller on substrate and cut in with brush on terminations. • Allow membrane to cure as per Data Sheet recommendations.
SECTION | Enviro 950 TC - First Coat
Checkpoint | Weather/RH
Label | Apply within 10-35°C RH must be 0-85%
Checkpoint | Mixing
Label | Add Enviro 950 TC Part A (liquid hardener) to the Enviro 950 TC Part B (base Thoroughly mix with a mechanical mixer at low speed (less than 400 RPM) prior to application. Mix for 5 minutes or until uniform. Allow to stand 5 minutes after mixing and then mix again for a minute. Overlap the existing membrane a min of 100mm, Protect the primed substrate from all contamination.
Label | • Enviro 950 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Checkpoint | Application
Label | • Enviro 950 TC to be applied by roller on previously applied membrane and cut in with brush on terminations. • Allow for re-coating window re-coating as per Data Sheet recommendation before proceeding with second coat.
SECTION | Enviro 950 TC - Second Coat
Checkpoint | Weather/RH
Label | Apply within 10-35°C RH must be 0-85%
Checkpoint | Mixing
Label | • Enviro 950 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Checkpoint | Application
Label | • Enviro 950 TC to be applied by roller on previously applied membrane and cut in with brush on terminations. • Allow membrane to cure as per Data Sheet recommendations.
Checkpoint | QA TESTING
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
SECTION | FINAL BUILDERS SIGN OFF
SIGNOFF | Final Sign off.