## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Fit Off |  |  |  |  | Yes | Fit Off Checklist | 0995f908-51ea-4d5d-a670-2bf7a9714e67
checkpoint-group |  |  | section | Laundry Fit Off
checkpoint-status |  |  | checkpoint | Laundry Trough
checkpoint-status |  |  | checkpoint | Laundry Trough Mixer
checkpoint-status |  |  | checkpoint | Laundry Trough Mini Stops
checkpoint-status |  |  | checkpoint | Laundry Trough Waste
checkpoint-group |  |  | section | Kitchen Fit Off
checkpoint-status |  |  | checkpoint | Kitchen Mini Stops
checkpoint-status |  |  | checkpoint | Kitchen Sink Waste
checkpoint-status |  |  | checkpoint | Kitchen Sink Mixer
checkpoint-status |  |  | checkpoint | Kitchen Dishwasher
checkpoint-status |  |  | checkpoint | Kitchen Cooktop
checkpoint-group |  |  | section | Bathroom Fit Off
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checkpoint-status |  |  | checkpoint | Bathroom Urinal
checklist-flat |  |  | checklist | Daily Site Diary |  |  |  |  | Yes | Add Daily Site Diary Checklist | 0f753d99-d7b7-44ae-b80a-ee2acf9e415f
checkpoint-status |  |  | checkpoint | Attach relevant photos and documents
text | a0aa1e95-7be9-5273-93ad-0a4cdb5a0105 |  | textbox | Time on Site
text | 6e01c180-492e-5bc1-846e-44c9ec3ba0fd |  | textbox | Time off site
text | cc06bdd5-5b85-5a28-9e44-ff5e9b91bfc9 |  | textbox | Vehicles
text | fb855924-f052-5943-a728-9d0aa7209e7e |  | textbox | Plant
text | 3d411984-77f6-511c-bd18-d4e2cb7af5bc |  | textbox | Ryder Plumbing Staff Onsite (list names)
checkpoint-status |  |  | checkpoint | Traffic Control
text | 4282f31f-2616-5e84-98b3-dea740c5204f |  | textbox | Number of Controllers
text | 6af20406-29c6-5820-bfd8-6f6b179ae183 |  | textbox | Time on Site
text | e8432972-8cd3-58b5-b2a0-6a8e47ff03a3 |  | textbox | Time off site
text | c6b2d807-6078-5bf0-a611-6fa603d8b934 |  | textbox | Deliveries / Sub Contractors:
checkpoint-status |  |  | checkpoint | Works Completed
checkpoint-status |  |  | checkpoint | Incomplete Works (add details in comments)
holdpoint |  |  | signoff | Signed off by Ryder Plumbing
checklist-sectioned |  |  | checklist | Toolbox Meeting Checklist |  |  |  |  | Yes | Add Toolbox Meeting Checklist | 0fcdf965-1236-4f14-b8f9-33d6e0f7a0a3
checkpoint-group |  |  | section | Attendance
checkpoint-status |  |  | checkpoint | Attendance - list of attendees added below
checkpoint-status |  |  | checkpoint | Apologies - list of non-attendees added below
checkpoint-group |  |  | section | Minutes
checkpoint-status |  |  | checkpoint | Actions from last meeting
checkpoint-status |  |  | checkpoint | Administration
checkpoint-status |  |  | checkpoint | HR
label | da3a299b-581e-5f36-a3cf-d8f9223a0c65 |  | note | e.g - Site recognition, any HR issues?
checkpoint-status |  |  | checkpoint | Safety: (including hazards / near misses / controls / site specific)
checkpoint-status |  |  | checkpoint | Environment: (including hazards / controls / incidents / impacts)
checkpoint-status |  |  | checkpoint | Training
label | b868c5bb-50e1-5063-a5e0-2fa0a5f65034 |  | note | Competency Assessment Guides (Apprentices) if applicable – are they up to date?
checkpoint-status |  |  | checkpoint | Plant & Equipment
checkpoint-status |  |  | checkpoint | Issues & Customer Feedback
checkpoint-status |  |  | checkpoint | Client/Job specific information:
checkpoint-status |  |  | checkpoint | Memo’s and other office correspondence
checkpoint-group |  |  | section | Document Review
checkpoint-status |  |  | checkpoint | Document uploaded below if applicable
checkpoint-group |  |  | section | New Business / Other
checkpoint-status |  |  | checkpoint | Any new business / other comments added below
checkpoint-group |  |  | section | Meeting Closure
checkpoint-status |  |  | checkpoint | Meeting Closed
text | 2ef67206-1fe4-5d23-a00f-bdc153a549ed |  | textbox | Meeting Closed time
text | c7c8d5fe-4fbb-5046-a920-d85ac8085671 |  | textbox | Date for next meeting
text | 6b89a8bf-6544-5122-b3a5-9e6cb2cccd05 |  | textbox | Minutes taken by (Name)
checklist-flat |  |  | checklist | Suspended Sewer Drainage |  |  |  |  | Yes | Suspended Sewer Drainage Checklist | 1d756ec5-bc83-4db2-959a-dc27127148da
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checkpoint-status |  |  | checkpoint | Test sewer
checklist-flat |  |  | checklist | Pits/Pumps/Tanks |  |  |  |  | Yes | In-Ground Pits/Pumps/Tanks Checklist | 1d936c12-bbab-4acc-97f0-98b1e16a3830
checkpoint-status |  |  | checkpoint | Sewer pump well
checkpoint-status |  |  | checkpoint | Storwater pump well
checkpoint-status |  |  | checkpoint | Stormwater pits
checkpoint-status |  |  | checkpoint | Grease interceptor trap
checkpoint-status |  |  | checkpoint | Conduits rain to IFC location
checkpoint-status |  |  | checkpoint | Torpedo tanks
checkpoint-status |  |  | checkpoint | Stormwater detention system
checklist-flat |  |  | checklist | Corridor |  |  |  |  | Yes | Corridor Checklist | 233e6f4a-fbb4-41e2-a3e6-50a423da7001
checkpoint-status |  |  | checkpoint | Rainwater
checkpoint-status |  |  | checkpoint | Hot Water
checkpoint-status |  |  | checkpoint | Hot Water Lagged
checkpoint-status |  |  | checkpoint | Cold Water
checkpoint-status |  |  | checkpoint | Test Hot Water
checkpoint-status |  |  | checkpoint | Test Cold Water
checkpoint-status |  |  | checkpoint | Test Rain Water
checkpoint-status |  |  | checkpoint | Fire Caulking (Corridor to Apt)
checkpoint-status |  |  | checkpoint | Cold Water Meter Manifold
checklist-flat |  |  | checklist | Commissioning |  |  |  |  | Yes | Commissioning Checklist | 2aaaa2ee-138d-4546-ad68-2daa5c20e37e
checkpoint-status |  |  | checkpoint | Includes bathroom, bathroom ensuite, kitchen, laundry
checkpoint-status |  |  | checkpoint | Test Hot Water Temperature
checkpoint-status |  |  | checkpoint | Test Waste for leaks
checkpoint-status |  |  | checkpoint | Run Cycle on Dishwasher
checklist-flat |  |  | checklist | DDA Bathroom Fit Off |  |  |  |  | Yes | DDA Bathroom Fit Off Checklist | 6364b91c-9105-4ef4-b4ee-7a5e36372635
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checkpoint-status |  |  | checkpoint | Bathroom Urinal
checklist-flat |  |  | checklist | Day Docket |  |  |  |  | Yes | Add Day Docket Checklist | 80c70592-5318-423b-9d8d-967223262727
checkpoint-status |  |  | checkpoint | Details added below
text | b5663d29-d1b1-5b24-83c1-50b1c63a4dfa |  | textbox | Work completed
text | e617efdf-c53d-5511-8408-6ce36b7b91a2 |  | textbox | Materials required
text | 1beed7bc-799c-5440-859e-750c25cb406d |  | textbox | Staff
select | dd59606a-8ffb-5f36-b44d-8668a6a78495 |  | dropdown | Hours | 1, 2, 3, 4, 5, 6, 7, 8
checkpoint-status |  |  | checkpoint | Signed off by Ryder Plumbing
holdpoint |  |  | signoff | Signed off by Builder
checklist-flat |  |  | checklist | Penetrations |  |  |  |  | Yes | Penetrations Checklist | 83725e53-b124-4575-80fd-e03edc5b58e5
checkpoint-status |  |  | checkpoint | All works to be set our as per approved IFC drawings.
checkpoint-status |  |  | checkpoint | Fire collar installation
checkpoint-status |  |  | checkpoint | Cast in drains
checkpoint-status |  |  | checkpoint | Photos of collar end labelling referencing fire matrix if required
checklist-flat |  |  | checklist | Apartment Suspended Drainage |  |  |  |  | Yes | Apartment Suspended Drainage Checklist | ba184bea-400d-46cb-851a-d5a440075a3f
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing. Includes bathroom, bathroom ensuite, kitchen, laundry
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checklist-flat |  |  | checklist | Big Ticket Items (In Ground) |  |  |  |  | Yes | Big Ticket Items (In Ground) | ba54f4b9-10ea-489c-b08c-86c4c1d4d855
checkpoint-status |  |  | checkpoint | Sewer pump well
checkpoint-status |  |  | checkpoint | Storwater pump well
checkpoint-status |  |  | checkpoint | Stormwater pits
checkpoint-status |  |  | checkpoint | Grease interceptor trap
checkpoint-status |  |  | checkpoint | Conduits rain to IFC location
checkpoint-status |  |  | checkpoint | Torpedo tanks
checkpoint-status |  |  | checkpoint | Stormwater detention system
checkpoint-status |  |  | checkpoint | LPOD
checkpoint-status |  |  | checkpoint | Water tap in
checklist-flat |  |  | checklist | Rough In |  |  |  |  | Yes | Rough In Checklist | c51c286d-2dcb-4099-9102-2992c4f0a52c
checkpoint-status |  |  | checkpoint | For apartments includes bathroom, bathroom ensuite, kitchen, laundry
checkpoint-status |  |  | checkpoint | High Level Rough In
checkpoint-status |  |  | checkpoint | Wall Set Out
checkpoint-status |  |  | checkpoint | Wall Rough In
checkpoint-status |  |  | checkpoint | Waste Rollovers
checkpoint-status |  |  | checkpoint | Gas
checkpoint-status |  |  | checkpoint | Test Water
checkpoint-status |  |  | checkpoint | Fire collar installed if necessary
checklist-flat |  |  | checklist | Pipework Checklist |  |  |  |  | Yes | Pipework Checklist | c88260b3-bc8f-4ccd-88c0-c3950c02937a
checkpoint-status |  |  | checkpoint | Pipework, material and fitting installed as per approved IFC drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Pipework checked for correct crimping/welded joins
checkpoint-status |  |  | checkpoint | Tested
checklist-flat |  |  | checklist | Suspended Copper Works |  |  |  |  | Yes | Suspended Copper Works Checklist | cda0a613-c9a6-46d0-94ea-bf6f941179ef
checkpoint-status |  |  | checkpoint | Pipework installed - domestic hot/cold/rain water
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire rated if necessary
checkpoint-status |  |  | checkpoint | Tested
checklist-flat |  |  | checklist | Suspended Stormwater Drainage |  |  |  |  | Yes | Suspended Stormwater Drainage Checklist | db846d74-294b-4bd2-8d46-af5658ff4cb4
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checklist-flat |  |  | checklist | Other Areas Suspended Drainage |  |  |  |  | Yes | Other Areas Suspended Drainage Checklist | e33e393a-2e27-433e-8c8e-a29709ba4379
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing.
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checklist-flat |  |  | checklist | In-Ground Sewer Drainage |  |  |  |  | Yes | In-Ground Sewer Drainage Checklist | eda00818-4bd4-49e8-adbf-d03b7d25c79e
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Pipework checked for correct invert levels & gradients
checkpoint-status |  |  | checkpoint | Book inspection with VBA for in-ground drainage.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Test sewer
checklist-flat |  |  | checklist | In-Ground Stormwater Drainage |  |  |  |  | Yes | In-Ground Stormwater Drainage Checklist | f970fbfd-dca4-46c8-843c-cd1be20ddae6
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Pipework checked for correct invert levels & gradients
checkpoint-status |  |  | checkpoint | Pits checked for correct invert levels & finished floor levels
checkpoint-status |  |  | checkpoint | Ensure correct locations of pits.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.