## res_MON-CON Concrete Pre-pour C
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Waterproofing ITP | itp |  |  |  |  | Waterproofing ITP
section | Waterproofing ITP
checkpoint | 1 - Setting up
label | Acceptance Criteria - Confirm substrate ready for membrane (by builder). Divots to be checked and any major defects to be notified to the builder and minor to be approved by builder prior to commencing)
label | ○ Clean up surface
label | ○ Install and apply bondbreakers as per manufacturer’s specification
label | Inspection Frequency - Before, During and after
label | Reference/s - As per architectural drawings
label | Inspection by - RCC site team, John, Thomas
label | ○ Witness Point. RCC to review and sign off with Smurf
label | Record - Visual
checkpoint | 2 - Priming
label | Acceptance Criteria - Prime onto substrate and allow to completely dry according to manufacturer’s specifications
label | ○ Apply Ardex WPM 265 test if water content of slab greater than 5.5% apply Ardex WPM 300 150 microns (minimum) WFT
label | Inspection Frequency - Before, During and after
label | Reference/s - As per architectural drawings
label | Inspection by - RCC site team, John, Thomas
label | Record - Visual
checkpoint | 2 - 1st coat waterproofing
label | Acceptance Criteria - In accordance with current AS 3740-2021 standards and ASR
label | ○ Apply first coat of Ardex WPM 155, WFT 0.6mm(minimum) per coat checked and confirmed
label | Inspection Frequency - Before, During and after
label | Reference/s - As per architectural drawings
label | Inspection by - RCC site team, John, Thomas
label | Record - Photo / Visual
checkpoint | 3 - 2nd coat waterproofing
label | Acceptance Criteria - In accordance with current AS 3740-2021 standards and ASR
label | ○ Apply 2nd coat Ardex WPM 155, DFT 0.6mm(minimum) per coat checked and confirmed
label | Inspection Frequency - Before, During and after
label | Reference/s - As per architectural drawings
label | Inspection by - RCC site team, John, Thomas
label | Record - Photo / Visual
checkpoint | 4 - Flood Testing
label | Acceptance Criteria - After curing - Flood test with markings. Confirm with RCC site team before and after
label | Inspection Frequency - Before, During and after
label | Reference/s - As per BCA / AS Standards
label | Inspection by - RCC site team, John, Thomas
label | Record - Photo / Visual
checkpoint | 7 - Inspection
label | Acceptance Criteria - Inspection for any damages or missed areas were done in accordance with current AS 3740-2021 standards and ASR v14
label | Inspection Frequency - Before, During and after
label | Reference/s - As per BCA / AS Standards
label | Inspection by - RCC site team, John, Thomas
label | Record - Photo / Visual
checkpoint | I have inspected the works and verified that it complies with the specification.:
textbox | Trade supervisor completing work:
textbox | Project Manager:
holdpoint | Sign ITP
checklist | Tiling ITP | itp |  |  |  |  | Tiling ITP
section | Tiling ITP
checkpoint | 1 - Setting up
label | Acceptance Criteria - Check membrane for any defects, clean up surface prior to screeding
label | Inspection Frequency - Before, During and after
label | Reference/s - As per architectural drawings
label | Inspection by - RCC site team, John, Daniel
label | Record - Visual
checkpoint | 2 - Set out
label | Acceptance Criteria - As per agreed set out client / architectural drawings, any changes in RL or FFL being discussed and approved by RCC site team
label | Inspection Frequency - Before, During and after
label | Reference/s - As per architectural drawings
label | Inspection by - RCC site team, John, Daniel
label | Record - Visual
checkpoint | 3 - Screeding
label | Acceptance Criteria - As per agreed set out client / architectural drawings, any changes in RL or FFL being discussed and approved by RCC site team Use slurry coat and screed approved by Laticrete
label | ○ Changes in RL and FFL have been made as per on site discussion between Matt, Josh and John
label | Inspection Frequency - Before, During and after
label | Reference/s - As per architectural drawings
label | Inspection by - RCC site team, John, Daniel
label | Record - Photo / Visual
checkpoint | 4 - Floor Tiling
label | Acceptance Criteria - Tiles were installed as per set out agreed on site with builder and client’s approval according to AS3958.1-2007
label | Inspection Frequency - Before, During and after
label | Reference/s - As per architectural drawings
label | Inspection by - RCC site team, John, Daniel
label | Record - Photo / Visual
checkpoint | 5 - Wall Tiling
label | Acceptance Criteria - Tiles were installed as per set out agreed on site with builder and client’s approval according to AS3958.1-2007
label | Inspection Frequency - Before, During and after
label | Reference/s - As per architectural drawings
label | Inspection by - RCC site team, John, Daniel
label | Record - Photo / Visual
checkpoint | 6 - Grouting
label | Acceptance Criteria - Cementitious grout (laticrete) installed as per manufacturer’s specification
label | Inspection Frequency - Before, During and after
label | Reference/s - As per architectural drawings
label | Inspection by - RCC site team, John, Daniel
label | Record - Photo / Visual
checkpoint | 7 - Silicone
label | Acceptance Criteria - Silicone (SOUDAL) applied after cleaning as per manufacturer’s specification
label | Inspection Frequency - Before, During and after
label | Reference/s - As per architectural drawings
label | Inspection by - RCC site team, John, Daniel
label | Record - Photo / Visual
checkpoint | I have inspected the works and verified that it complies with the specification.:
textbox | Trade supervisor completing work:
textbox | Project Manager:
holdpoint | Sign ITP