## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Subgrade Preparation-Road-Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Subgrade Preparation-Road-Rev 0 | 056f96e2-dc65-47fe-b608-8999badde738
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | fdd34b50-5bee-5c94-9914-df7b370d3641 |  | note | Document Title: ITP-CIV-CAMMS-Subgrade Preparation - Road
label | ab267e6c-7650-5e93-9dbf-96f5e0bbcc51 |  | note | ITP Description: CAMMS-Subgrade Preparation - Road
label | 764f618d-938d-58f0-99b0-1ca1e9a31b2c |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | df31e635-9d41-589d-9265-71b3e6459160 |  | note | Revision Number: 0
label | 2f8fe6df-e5e4-5680-9069-a4cb4de5ada1 |  | note | Revision Date: 18/08/22
label | 6a71a6a5-00a0-5172-9236-b2060d717c38 |  | note | ITP created by: Victor Mira
label | c30e8323-5eef-5d01-92b9-41ad9e8c2443 |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 572cb9d4-49e6-5a9b-a096-1198ec098c1f |  | note | Reference - VicRoads Section 204
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | d3c18019-2bd6-547b-9265-3b4e03e27f38 |  | note | Reference - VicRoads Section 173
checkpoint-group |  |  | section | 2 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Non Dependent
checkpoint-group |  |  | section | 3 - Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Non Dependent
checkpoint-group |  |  | section | 4 - Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-Out
label | 81d017f2-83e0-50ac-8697-820dc8e11a3b |  | note | Reference - IFC Drawings
label | 094d26e4-b1f2-5bc9-a834-dd3bd3011609 |  | note | Acceptance Criteria - Area has been set out in accordance with the drawings
label | a84eb765-f230-59f5-8a8b-c14c3cf72b4c |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | 1c19ea32-8c09-5d3a-8cb0-a152b6fd1d04 |  | note | Method - Verify
label | 9f77a5ca-5bd6-5ff5-a9c3-0c06aa317d44 |  | note | Frequency - Prior to commencement of excavation
label | a04909b2-0a2e-53c3-bdb6-96be987a5234 |  | note | Category - IP
label | 0ac88d0b-9f5b-5473-ba22-909cba1bf212 |  | note | Responsibility - SE/Surveyor
label | 8bcee0a5-9891-55b4-9a27-fb2ae9150c8e |  | note | Verifying Documents - This ITP
date | 708c77af-8ce2-556d-8132-2ea1c35c1356 |  | date | Date Completed:
checkpoint-group |  |  | section | 5 - Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
label | b6dcd196-318f-5e9e-95f6-528d4e10ebf6 |  | note | Reference - Section 204.06 ( c) Section 204.06 ( e) IFC Drawings
label | 83aae0a6-6b9d-5fec-9da1-d405f9dc08e6 |  | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | 5441e849-479c-5468-9fc5-7f2571b2728c |  | note | In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | 47245560-ba28-5f1d-849c-221aa56de566 |  | note | Assigned CBR ≥ 2.5%
label | b53f8812-ed83-5133-9370-65e49b464bf3 |  | note | If parameters are met, rip and recompact to a depth of 150mm.
label | b79a242f-8dfc-5d88-b7cf-86ce8e7b4d3b |  | note | If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | cc2a3a72-70dd-5922-95c1-53083222d9d1 |  | note | If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
label | bcfa0011-b1bb-501d-907f-2907772b26d6 |  | note | Attach: Laboratory testing Verification:
text | da42f828-f9b9-568f-a12e-809a15e7e728 |  | textbox | Enter: Type A fill Lot Number:
label | 4a550785-31e2-56cf-aeed-b4d18c534e5c |  | note | Method - Verify-Document Review
label | c69312be-39c4-5c49-ae2c-6dd6f7608d1b |  | note | Frequency - Each lot
label | 09d988db-9b1e-5185-8957-8711101b590c |  | note | Category - HP
label | e0ba499a-eb1c-52d3-b789-58616ecf0d2b |  | note | Responsibility - PE/Nominated Authority
label | 7bc4a220-0ec9-5e67-a9b8-aa53d01460d5 |  | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
date | 27c5e308-63d8-510d-8939-a0d47a3fa6ad |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Material classified as silt
label | 5f7f50f0-3b75-5b21-97f4-efd508481491 |  | note | Reference - Section 204.04 b)
label | 469c2365-6ac9-5e80-8681-473ff9c3ccd2 |  | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilization to the satisfaction of the Nominated Authority
label | 56adb619-49e2-5c15-99c7-ad29bbc13538 |  | note | Method - Document Review
label | 265d3519-2b6e-5b10-b5aa-1d97c830b2f9 |  | note | Frequency - Prior to commencing
label | d77edc05-21a8-5d90-8e00-923e689a1ee7 |  | note | Category - HP
label | 65ed1060-76dd-538c-9910-dea9036a3729 |  | note | Responsibility - SE/Nominated Authority
label | 554f3a84-aafa-53fe-a12d-ac4b7a534425 |  | note | Verifying Documents - Superintendent satisfied with Stabilisation
label | bb5187bd-8536-5c0c-878f-b74c686d7edf |  | note | Signed ITP/ records
date | 0b706f09-71ac-50a9-8393-8258e89b4355 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
label | dee7a647-b8a8-5c46-a2a2-53512bd56c4c |  | note | Reference - Section 204.06 f)
label | 0e5faf74-19ff-55d7-9f44-1361a0039134 |  | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | a6045b83-144e-539d-bb05-39c30462286b |  | note | Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | da9e087e-80ac-55b9-a791-2176fd2e8e9c |  | note | Method - Site Inspection/ Document Review
label | 8d9e4cb0-89d7-5d3b-9839-e5064017dfed |  | note | Frequency - Prior construction of the regulating layer
label | e9ff3405-2bef-510e-9d06-503be0fa2255 |  | note | Category - HP
label | f15bba90-6677-549a-9fa8-736c4681bbf5 |  | note | Responsibility - SE/Nominated Authority
label | ca74c18e-6ce5-51ab-b25a-b214115d432a |  | note | Verifying Documents - This ITP
date | b76e13ba-472e-58eb-8f8e-051ade86f4cb |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Unsuitable Material
label | f5762e6a-252d-5eea-a2db-f91ce8194480 |  | note | Reference - Section 204.07 d)
label | 2d8c7b7b-5242-51ec-bc74-810eb899b011 |  | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | 2e55e64a-0592-58f2-90ef-d880e3357df7 |  | note | Method - Visual inspection
label | ba3acae5-437e-5c7a-823d-bf7fe454fca4 |  | note | Frequency - Each lot
label | e805fba9-b73c-5889-93dc-7873391449ef |  | note | Category - HP
label | a93032c6-432f-5120-9c4d-bd14ee36fead |  | note | Responsibility - SE/Nominated Authority
label | 7847bd56-52d8-5851-8856-1e86bf5ae369 |  | note | Verifying Documents - This ITP
date | 867ba0a7-b5dd-5983-9ce9-638ef9fd7653 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Groundwater
label | cbd39376-812f-5ad9-88ab-cf40dd2e2f80 |  | note | Reference - Section 204.06 h)
label | 16826619-2e9e-5a6b-94e2-2ca05cb27231 |  | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | c313b280-406a-503c-a5ca-aa6c1d9d5e2f |  | note | The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | fecb422e-a636-55b9-b651-7bbf22db4632 |  | note | Method - Visual inspection
label | ecc65a18-98c4-5a57-87f3-f39c1cb0dcae |  | note | Frequency - Each lot
label | 03637807-2b0f-5112-b385-7a6901407618 |  | note | Category - HP
label | 732134d2-8b75-516d-9042-69013f68a0d4 |  | note | Responsibility - SE/Nominated Authority
label | 75cc0c13-1248-5a6f-8d2f-86ea12b1c56f |  | note | Verifying Documents - This ITP
date | 87ed565d-5667-5fc8-82e6-ab7d02efaad6 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Cut to Fill Zones
label | bf6b3ac1-5281-5ac0-9228-b30e7bf5c304 |  | note | Reference - Section 204.06 g)
label | cfe6cad4-7059-5ac7-b604-54d8e36e2b40 |  | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
label | e202154c-b981-54b6-82de-9c3127b9d306 |  | note | Method - Site Inspection
label | d7e538e8-3e4d-540a-9e2c-b2312586febd |  | note | Frequency - Each lot
label | a869b10c-6b40-53f9-a38e-ea74afe250ee |  | note | Category - IP
label | 2fcddaa5-9edd-50a9-8d49-66c0d8e6db66 |  | note | Responsibility - SE/Site Supervisor
label | edebc9fb-77dd-56d6-9f4e-fd14a0ab6555 |  | note | Verifying Documents - Sign ITP
date | da315dfc-0586-5ba8-8d2a-88d31f806972 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Proof Roll
label | abf33bb9-5fdb-52cd-a325-38f69546d39a |  | note | Reference - Section 173
label | edcf178a-e26a-505e-bdb6-04d483689d17 |  | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | bb3f8019-1054-5077-9023-b6bea4ca4eda |  | note | Method - Visual inspection
label | ab015910-2658-5966-9f78-9430a0c9002a |  | note | Frequency - Each lot
label | 9197be12-d19f-5ca4-8c0b-2793d62b017a |  | note | Category - HP
label | 721ce0dd-a573-58ba-b3a7-0bed70e49167 |  | note | Responsibility - Site Engineer/Superintendent
label | 858d2eaf-723f-58f9-88bd-a8e7d31c6607 |  | note | Verifying Documents - This ITP
date | 15334f87-3bba-57ce-9354-d62f7906da93 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 - Compaction Testing
label | c4ad0127-7c06-58ed-9b14-e0966936395a |  | note | Reference - Table 204.131
label | 7817aa3c-2b86-53af-ac52-86202633a9fb |  | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
label | 486ff726-b40e-50bf-8c26-d3f03704efdc |  | note | Scale A: Characteristic Density Ratio 99%.
label | bed677cd-45bc-5d6e-8fea-9e8a4c22eea9 |  | note | Scale B: Characteristic Density Ratio 98%.
label | 0a20e21f-53bf-50fc-99c8-1b6e1e4daced |  | note | Scale C: Mean Value of Density Ratio: 100%
label | 7d019dd5-e702-55dd-b40d-7e17bffd6b51 |  | note | Attach: Compaction Test Result:
label | 2e93ad84-53e8-5395-8579-329be8a6989f |  | note | Method - Document Review
label | bb4d8816-26e3-5ece-92dd-da1fc2d82908 |  | note | Frequency - Each lot
label | 5cb56ada-7525-5db0-86d6-7347774ae057 |  | note | Category - IP
label | 5981f34e-1749-5d76-87e7-cc4a156c0b3a |  | note | Responsibility - PE/SE
label | 1069cd4b-e880-5d80-b897-b497b1058913 |  | note | Verifying Documents - Test Records
label | 5d4c9c17-7ed4-5b58-863c-a36b0fe3280f |  | note | Lot Register
date | abfb48e2-30ee-5ce5-8a15-4643e493bc4d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Post Compaction Material Property Testing
label | b45cb912-a745-50f0-99f9-419966923399 |  | note | Reference - Table 204,041
label | 7efff24c-2cbb-5003-a4d4-00ec772d2ddb |  | note | Table 204.141
label | c6e90238-95e2-52c1-8e53-3332287cc525 |  | note | Section 204.14 a) or b)
label | 4a5626d9-7a29-5a06-822a-9b047b44bb93 |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | 59d8ebfe-d528-58fe-9ba1-ff374ef887b1 |  | note | CBR ≥ 3% and Swell ≤ 1.5%
label | 4a121581-1950-5778-963c-7afc9c8aa41e |  | note | Max Permeability = 5X10-9 m/s
label | 16e87b2a-5606-59fc-9f9e-0bc80ee6742c |  | note | Grading: 75.0mm 100%
label | 2a79fc1b-91bc-51e9-b37b-8e7654657f75 |  | note | 4.75mm 40-80%
label | 5c5e41ac-ab43-50ce-a834-098fba7aec4d |  | note | 0.075mm 10-40%
label | e0e04acd-d21b-5da0-8422-001f1bcfb05a |  | note | Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 54f43dc4-d61e-5deb-b7a1-2c88a6da3da7 |  | note | Scale A:
label | bb54881f-31a6-560a-b137-e07ee16258a9 |  | note | CBR & Swell
label | 2bbef769-31e0-5dbe-841b-2e5c100e1105 |  | note | Initial - 1 Lot Test to determine Assigned CBR and swell
label | 220cf4e9-6b0c-5f86-b531-aaba0e96a20c |  | note | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | 43c95da2-2ab1-5629-96b4-7e150a56f278 |  | note | Max Permeability
label | b54215d6-d076-5363-bf89-bf15189da42a |  | note | Initial - 1 test per 2 lots
label | da86e7a7-8756-592f-8491-b2c2c39ecf7f |  | note | Reduced - 1 test per 4 lots
label | e90f33ae-e6e8-57f9-95f9-392dd261aeb3 |  | note | Grading:
label | 2794d8c7-c096-5fbf-b622-2b7f263e3583 |  | note | Initial - 1 test for each lot tested for compaction
label | 2a49c024-6491-505b-8902-d67ee2ae748f |  | note | Reduced - 1 test for every second lot tested for compaction
label | aac3a73a-8baa-54c4-ab24-985caf32c94c |  | note | Max. PI x%Passing 0.425mm & PI
label | c75076a8-2a1b-5088-9607-58ef54990484 |  | note | Initial - 1 test per 2 lots
label | 9d3065a2-ce4c-520e-87dd-e7b82cee1119 |  | note | Reduced - 1 test per 4 lots
label | 909b5e97-a84c-5b1e-b54d-b7eaa1019676 |  | note | Scale B:
label | f866ab87-ba8a-5b2e-bedd-531a910c9e04 |  | note | 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 97a335c2-6d17-51d2-81c4-9e8ef2384e54 |  | note | Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 0b3bc9b4-2ca1-56c3-8eac-f13a5829ef26 |  | note | Attach: Post compaction test results
label | f9aaf5f2-5dba-5f0e-85d9-3486c0edce20 |  | note | Method - Review Document
label | 678fc9c9-eab9-5093-8bae-f6c8b14e7b62 |  | note | Frequency - Refer to Section 204
label | 848d26ab-608d-5759-994b-4dae07155655 |  | note | Category - IP
label | 82e17378-040f-592b-96df-64c2d608cc51 |  | note | Responsibility - PE/SE
label | e0408a22-efe3-572c-a576-03e026050efb |  | note | Verifying Documents - Sign ITP
label | 57a1a3a5-c322-5ff0-9fd0-90b260e39b68 |  | note | Attach Material Property Test Report
date | abb08515-506d-5c6e-8edd-ac2c7b5b5c9e |  | date | Date Completed:
checkpoint-group |  |  | section | 6 - Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Survey Conformance
label | 464c3684-c41d-5314-a509-a757a3761280 |  | note | Reference - VicRoads 204.03f,g and h
label | 0f2f5917-a610-5d09-b8e6-652c2d1ada58 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | e8c67308-c717-5ae7-81dd-0d5688013dc1 |  | note | Level tolerances (Scale A):
label | d4d13d9c-0b54-5d2d-bf9a-7e684c277185 |  | note | Range x = +5, -15mm
label | 2908c60a-5f2a-524a-962e-c5cceb4e5f73 |  | note | Max S = 12 mm
label | 390b3bde-dde7-5445-8bdd-fff98e2f3a7f |  | note | 80 measurements per lot
label | f1dc11f8-6efc-50d4-b559-1f2dfb7d1489 |  | note | Level tolerances (Scale B):
label | d0460f13-2049-55ef-a39a-2ffaa261f1ba |  | note | Range x = +5, -25mm
label | 1209f24a-70be-539e-b723-5dae8eeb6c76 |  | note | Max S = 15 mm
label | 198a14e2-b0de-5204-8733-cb99dc3cf5d1 |  | note | 40 measurements per lot
label | a4b6d4ba-ffc1-509e-b0c2-dd6cfa2c1c5e |  | note | Level tolerances (Scale C):
label | d7ca8de2-9be4-53d4-90df-4ad3cecba1bc |  | note | Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | a1d616de-d64a-50b2-9875-8dc0bd2caa9e |  | note | Method - Review Document
label | c1da78a0-f4e4-56ad-8dd3-c72b1f7eec71 |  | note | Frequency - Each lot
label | 2e8ad31e-a545-5118-8035-b6f4f41f050d |  | note | Category - SCP
label | 870df477-1571-52a4-af26-deb4d2c3421e |  | note | Responsibility - SE/Surveyor
label | 60635c4a-7dc2-5a58-bc8d-8a3d0ad7f781 |  | note | Verifying Documents - Sign ITP
label | 5852b3d7-7d40-5f69-a650-fcb00a90e866 |  | note | Attach Survey Report
date | 5d76aa78-6e65-5d90-9109-175b99668729 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | e398a81e-d8ce-5518-90b1-dfa0ba52d31d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 86040a30-b8ac-5ca2-8179-61fe3a18a4a2 |  | textbox | Print Name:
text | e359971c-b909-5749-88fe-75b132d667e1 |  | textbox | Position:
date | 552a64ae-cf55-5aa0-ac73-f1082b1c619d |  | date | Date:
checklist-sectioned |  |  | checklist | ITP-014-CIV-CAMMS-Footpaths & Shared User Paths | itp |  |  |  | Yes | ITP-014-CIV-CAMMS-Footpaths & Shared User Paths Rev 0 | 1c60bfb1-c3f7-4777-be91-a1f4d1093838
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | fc64aecb-8ca8-5aab-a86c-0bcf339cac52 |  | note | Document Title: ITP-014-CIV-CAMMS-Footpaths & Shared User Paths
label | 2f108b87-5f93-534b-9c9f-cf7319931abe |  | note | ITP Description: CAMMS-Footpaths & Shared User Paths Scale C- 1 (Set-out & Bedding)
label | e25af5ad-7cf9-5d1b-97da-e20ee9463669 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 2cdf6b43-9bfc-5af2-b19d-a7fd09f982f9 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 924e088d-1fee-5dbe-b5fe-a42ff9b53af9 |  | note | Revision Number: 0
label | 1638855d-f9e7-50c4-857b-e143ef552111 |  | note | Revision Date:
label | b89d024e-7ab5-5a38-9ae8-1fd27002a672 |  | note | ITP created by: Victor Mira
label | ac6c96bc-7dff-5f22-827f-34a7e5332d1a |  | note | ITP approved for use by: Victor Mira
label | 2cf64137-1eee-51a4-bc41-88d45ce79308 |  | note | 1.1 Non Dependent
label | 8032ab5b-1907-5f89-a73c-0e2e0d37f108 |  | note | Reference: VicRoads Section 304 August 2013
label | 8b41f279-4a2d-5f90-869b-aca9513c68e5 |  | note | 1.2 Non Dependent
label | 323fc24c-aa3f-5062-91ca-a10e50674e80 |  | note | Reference: VicRoads Section 703 April 2019
label | 4e5f658e-010a-5521-a3d5-66e0cedd0b35 |  | note | 1.3 Non Dependent
label | 9d447e82-9f7a-54c5-8e5a-d398f9437e7e |  | note | Reference: Council EDCM 401
label | e1c12051-86be-5c9a-a3e7-7b50ac01cd14 |  | note | 1.4 Non Dependent
label | 7776f39b-37ab-5ad9-b8ee-ac53d1b0b8ba |  | note | Reference: Council EDCM 501
label | f6c7412d-07d5-5454-9456-b01a0237a513 |  | note | 1.5 Non Dependent
label | cb2dad1f-d6bb-556e-b9b5-5821014183f0 |  | note | Reference: Council EDCM 502
label | d09b53ed-dfe0-50c2-a6b3-71fd028d10b5 |  | note | 1.6 Non Dependent
label | 5981a5fc-fb1f-56af-9084-6797a86b5042 |  | note | Reference: Council EDCM 503
label | f53ea9e0-ffd6-5962-8ba2-a27b026777bc |  | note | 1.7 Non Dependent
label | f726b3c8-e5d0-51de-9c35-7de645e9fb42 |  | note | Reference: AS 1379-2007
label | bfe9837b-08f2-5d4f-804e-86308772b95c |  | note | 1.8 Non Dependent
label | 9b088160-60d9-5331-97f7-703458a58170 |  | note | Reference: VicRoads Section 812 July 2016
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Bedding Material Placement & Compaction
label | 6cf8d671-6ddd-5bce-b60b-f09f7076dfec |  | note | REFERENCE: IFC Drawings:
label | a8b59300-f6a4-52f8-beba-dbc00c90f7b4 |  | note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
label | 2a32b19b-7aad-501b-9250-f92ee8ae0496 |  | note | • 812.04, 703.21
label | e2f59b3f-bb9c-5cd0-ae82-34c8724a5e46 |  | note | – – – – – – – – – – – – – – – – –
label | cf5d6f2e-b5a1-52cb-bc97-7bab6bbe7abc |  | note | ACCEPTANCE CRITERIA: Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
label | 393da40f-56c4-54bf-bf90-9486498bdc6f |  | note | • SUP: SIZE 40mm CLASS 3 CRUSHED ROCK
label | a5d1becf-25ab-501c-be61-4f74627dc1d1 |  | note | • Material is registered with VicRoads in accordance with Code of Practice RC500.02.
text | dbf8a31b-6095-5666-b183-be3865024f62 |  | textbox | • Enter: Teambinder Material Approval number
label | fefa6539-9f89-5b4d-a8dc-0df05f115982 |  | note | – – – – – – – – – – – – – – – – –
label | 818891b5-3c35-56dc-afa6-a8c13f520af4 |  | note | METHOD: Document Review
label | f967724c-47bd-53a1-a795-deb18644b185 |  | note | – – – – – – – – – – – – – – – – –
label | 6df591d4-3915-5799-a8bf-f60a9f2f85a3 |  | note | FREQUENCY: Each Lot
label | d0f19106-ce40-5274-9d12-b5b242ebc1f4 |  | note | – – – – – – – – – – – – – – – – –
label | a1742d23-e519-524b-82b7-1152a6556947 |  | note | CATEGORY: HP
label | 69d9da30-205c-5159-aad3-7979fbf3d027 |  | note | – – – – – – – – – – – – – – – – –
label | b2db3095-9308-5f9d-8cc1-bd59b87ebc94 |  | note | RESPONSIBILITY: Nominated Authority
label | aa7d586f-08bb-5287-aa99-c1c09c01471a |  | note | – – – – – – – – – – – – – – – – –
label | 6cd0fb2a-ed0f-5ccf-8455-e8743f6eb0ac |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 384a9d06-810f-5757-8470-6f8a3584a4a8 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.2 Concrete Mix
label | 587e2ff5-3377-5c6a-9737-4662297424d0 |  | note | REFERENCE: IFC Drawings:
label | 54bf0276-8bde-596f-aafc-1ec40c7aae86 |  | note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
label | d5fcfdd2-85d4-5191-ab69-86de8db6352a |  | note | • 703.05 (a), 703.07
label | 616ab5e2-336d-5d0b-ad9f-543d68ab435c |  | note | – – – – – – – – – – – – – – – – –
label | af8047e4-6c5d-5dd6-8d6e-d79ede21ccf6 |  | note | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
label | e8400f84-b5d2-5e60-9cac-44e3b22add24 |  | note | — Footpaths, Residential driveways and Median islands infills: 25Mpa
label | f29e11f9-5561-5033-a571-5c8f907d7d24 |  | note | — Industrial Crossovers: VR330/32 to be registered by Vicroads
label | b6835f34-a063-5fd0-ae49-fd07d2f7c65b |  | note | — Traffic Islands: 32 Mpa
label | 2d137bee-d452-526d-8d5e-58d61bd69bf0 |  | note | — SUP: VR330/32
label | bb853c93-83a4-5c92-a9e3-6850b99a782c |  | note | • No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
text | d61b1f52-8ca1-5188-8b5c-0fb2632ae7b5 |  | textbox | • Enter: Teambinder Material Approval number
label | 4e27f9c2-e402-5dce-b678-e1874439392c |  | note | – – – – – – – – – – – – – – – – –
label | 3bfcad8f-fb00-5f83-a945-6c172e4c82cb |  | note | METHOD: Document Review
label | dc1fe9ed-9993-5f6a-ad71-04c7ab615499 |  | note | – – – – – – – – – – – – – – – – –
label | 877e5c40-37f3-5a4f-8280-92d362453608 |  | note | FREQUENCY: Each Lot
label | 38a5c72e-c740-514e-8392-f3fb5e4d7964 |  | note | – – – – – – – – – – – – – – – – –
label | ffe9236b-204e-5616-a520-81e6378005f3 |  | note | CATEGORY: HP
label | 7fd05cbe-28b5-5f78-834e-5608846c7585 |  | note | – – – – – – – – – – – – – – – – –
label | 526fd435-6585-5b79-a2e4-ec1fd714a64b |  | note | RESPONSIBILITY: Nominated Authority
label | 793465d6-aa44-55fa-b046-652549626e49 |  | note | – – – – – – – – – – – – – – – – –
label | 80cf2e8e-4081-5caa-9563-0579fa646202 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | ec114962-159a-5efa-84d8-cd5135115557 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.3 Reinforcement
label | 58016811-3a75-5396-be51-73931674fd14 |  | note | REFERENCE: IFC Drawings:
label | 28907ad9-ab70-577c-bb73-c7c959718427 |  | note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
label | c4b981cb-e2e0-5d1f-8f61-728aeeb29c37 |  | note | • 703.16
label | a493c16b-6c95-526b-8842-959191ef116d |  | note | – – – – – – – – – – – – – – – – –
label | e371dd15-ee30-527c-a68c-bb8fd40b5a26 |  | note | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
label | 01601efe-52fd-5c63-b8c9-235c68bbad09 |  | note | • Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
label | eb6919a1-269d-521a-b1f7-08341dce94fe |  | note | • Following steel mesh requirements shall apply as per IFC Drawings:
label | 2f9cb185-9017-5b6d-8752-b562bacc9683 |  | note | — Footpaths, Residential driveways and Median islands infills: SL72
label | 2e33393c-5671-59f7-b034-d87a7f737c52 |  | note | — Industrial Crossovers: SL82
label | 01b616dc-9be4-5e7b-aa56-ec8649077a25 |  | note | — Traffic Islands: SL72
label | bec4b9b9-353d-5a23-8c15-95d037ce9f0b |  | note | — SUP: SL82
text | 929ddc98-2c7d-5487-9fe1-a7599db645c9 |  | textbox | • Enter: Teambinder Material Approval number
label | 2b1da527-f5a8-516c-b41e-c1bb1e0792c9 |  | note | – – – – – – – – – – – – – – – – –
label | 8a1d722a-1809-509b-9050-5daf6acc6099 |  | note | METHOD: Document Review
label | d0a53be3-365c-57a3-a827-3372719be2a9 |  | note | – – – – – – – – – – – – – – – – –
label | f093e72d-922d-56df-a060-ddf83d74ee8d |  | note | FREQUENCY: Each Lot
label | 17292696-9d23-579a-8beb-1e31eefe5f8f |  | note | – – – – – – – – – – – – – – – – –
label | 3a885809-8d07-5e0f-b665-7a31f3000068 |  | note | CATEGORY: HP
label | 4f5be39a-1f7d-5312-a339-15c9ab87cdda |  | note | – – – – – – – – – – – – – – – – –
label | 4366c40c-eb38-5645-bec9-0d804921f217 |  | note | RESPONSIBILITY: Nominated Authority
label | b029ecc8-4e93-51c9-809b-c72892d51a5a |  | note | – – – – – – – – – – – – – – – – –
label | bf0d9fa3-4114-5169-a144-ad88827d18fd |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 486a3b30-f057-57a5-ad5f-38505467e521 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.4 Evaporative Retardant
label | 4269db9d-733d-555b-a67e-ad91612d6ef6 |  | note | REFERENCE: 703.09
label | 0fb45cd7-f885-578c-b37f-fa9e3bab7969 |  | note | 610.17 (f)
label | 58739c78-a1f0-576f-ac11-50fd592c6434 |  | note | – – – – – – – – – – – – – – – – –
label | 35068d34-51d6-5753-832a-b62f558d2f30 |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 0bee3d49-44e5-5d30-8e6b-b8539c0ed88a |  | textbox | • Enter: Teambinder Material Approval number
label | d7b37cf8-5428-5532-b0db-b075abf4c0d8 |  | note | – – – – – – – – – – – – – – – – –
label | a614a7cb-5e5b-5c05-94d1-3e04ee7b1b66 |  | note | METHOD: Document Review
label | 479eba6d-fc0d-5fb0-98df-1d3172f62f08 |  | note | – – – – – – – – – – – – – – – – –
label | a95cd09d-c87f-5918-9a6b-d5be65639d5f |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | 33587df1-4faa-5f3d-9ccb-7fa75c56cb08 |  | note | – – – – – – – – – – – – – – – – –
label | 190380f8-7e93-5e80-bc65-3d582e2d9634 |  | note | CATEGORY: HP
label | 71e339ce-3f02-5a61-a0a4-e3b60a34402e |  | note | – – – – – – – – – – – – – – – – –
label | 24939bdd-7a7f-53c1-85e5-b5cdf9ab4883 |  | note | RESPONSIBILITY: Nominated Authority
label | d6b91cfe-28a1-5a23-b0ee-b10469d27317 |  | note | – – – – – – – – – – – – – – – – –
label | 5deee1ac-d733-5a87-99a9-7a7a4e85461c |  | note | VERIFYING DOCUMENTS: This ITP
date | 164a9300-3aa8-505b-8abc-8bc3be714a06 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | 0220c777-3102-5b5f-844d-d8033d201edc |  | note | REFERENCE: 703.10 (a)
label | 161dc935-85b3-57d4-9d8c-4ef604edef43 |  | note | 610.23 (d)
label | aaeefc51-d650-5e2d-8c79-eb1fb666f5dd |  | note | – – – – – – – – – – – – – – – – –
label | 2e4289d6-4992-5cde-9ca3-222a479fd965 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 5fd56e48-ed02-5830-b2cd-78401458c285 |  | note | • Enter: Teambinder Material Approval number
label | fc00595b-33d3-5c08-820a-284e9b47faf0 |  | note | – – – – – – – – – – – – – – – – –
label | 79727f00-b6d9-5573-8006-f013ae3e0992 |  | note | METHOD: Document Review
label | c75b9a19-ddd7-515f-b697-b9d4a8171ac8 |  | note | – – – – – – – – – – – – – – – – –
label | 09dd4130-df4e-5546-8971-fd956d4755d6 |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | 3344a181-9168-5215-b4bf-39585e28b58e |  | note | – – – – – – – – – – – – – – – – –
label | c0a43d9e-6f4c-501f-8fe2-9c6b18fa19af |  | note | CATEGORY: HP
label | 939d6627-5960-5e9b-a72f-8b8da1082031 |  | note | – – – – – – – – – – – – – – – – –
label | 293663ea-782a-5a3b-b5b3-6592b0498ef4 |  | note | RESPONSIBILITY: Nominated Authority
label | 0b0ef9ac-0fe3-54f4-9956-4b127650cac8 |  | note | – – – – – – – – – – – – – – – – –
label | a0fef5ca-81b6-5182-ae84-c75159d2f570 |  | note | VERIFYING DOCUMENTS: This ITP
date | bcdb33cf-4204-5d39-a4c2-6506e0de92a5 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-group |  |  | section | Preliminaries - Documents
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 9d10619c-bfbf-5e79-ac43-05fe6457591d |  | note | REFERENCE: IFC Drawings
label | 8fdb9dc2-0788-53fb-888c-df916fd7d54f |  | note | 703.17
label | d1e1efc6-2cf0-58a5-8612-0019fe71d8ac |  | note | – – – – – – – – – – – – – – – – –
label | 2e50890d-6661-568a-af96-6fb6c6892468 |  | note | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | 72e27fed-7f33-5565-b571-ca4e653efcfd |  | note | • The Nominated Authority will review and confirm the set out.
label | a3618167-790a-525b-befd-2b57748c2c33 |  | note | Attach: Survey Report
label | 10d33d3b-410c-5c4f-b226-c702ebef23be |  | note | – – – – – – – – – – – – – – – – –
label | 40a07f72-38c7-565b-9431-261b310a95d8 |  | note | METHOD: Document Review, Measure, Visual
label | da6443c3-60c3-501c-8c81-4681760fbe75 |  | note | – – – – – – – – – – – – – – – – –
label | 601f1a56-7564-5bdc-84f0-362ef92923b0 |  | note | FREQUENCY: Each lot
label | 572fac93-01c2-5a55-8d16-fc1f50fed54f |  | note | – – – – – – – – – – – – – – – – –
label | b2145ba2-74b2-5c10-9176-6ed4097edb84 |  | note | CATEGORY: HP
label | afabbe7f-7619-5b7b-a6d4-f1fa3e661805 |  | note | – – – – – – – – – – – – – – – – –
label | 3ef1a0a3-83b2-5e4b-a972-f0830164bbf0 |  | note | RESPONSIBILITY: Nominated Authority
label | dabf51d8-a119-5599-b2b9-59bb919e7712 |  | note | – – – – – – – – – – – – – – – – –
label | 1b57014e-42ac-562f-b038-766ad0a4e0e7 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 933863a6-e1a9-57d3-880a-3a71510e2b63 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.2 Lot Map
label | dffd64ad-5df5-520c-bf8d-369836e87256 |  | note | REFERENCE: MRPA Lot Management Plan
label | 6958710a-48b0-5e85-8b30-f4ea6745366a |  | note | – – – – – – – – – – – – – – – – –
label | 38156042-48fb-516a-9654-9480f42f93b3 |  | note | ACCEPTANCE CRITERIA: Attach Marked drawing indicating the location of this Lot
label | f6950ec2-6676-54da-ab65-4ccf9fe7463d |  | note | Attach: Lot Map
label | 9232d1c8-0608-5613-9a64-b287e742c2f4 |  | note | – – – – – – – – – – – – – – – – –
label | 061c9dcd-f887-55fc-a307-cad4e52820bc |  | note | METHOD: Document
label | f94b2ae7-de4f-50c1-9cf8-834a5c19e8a5 |  | note | – – – – – – – – – – – – – – – – –
label | 4b03d937-79ee-5ab3-a3c5-e0142f595345 |  | note | FREQUENCY: Each Lot
label | 161feabf-050a-5a62-a3bd-dec18600246d |  | note | – – – – – – – – – – – – – – – – –
label | d9d3a16f-5b2b-5808-b8d1-5078a4d7aded |  | note | CATEGORY: HP*
label | c54e9f94-3b4c-520e-bc8a-f512cd474425 |  | note | – – – – – – – – – – – – – – – – –
label | a84586a9-75ca-5c02-9e0a-e9edf28d0472 |  | note | RESPONSIBILITY: SE/PE
label | e55e9821-10f2-5396-a934-7783b839a833 |  | note | – – – – – – – – – – – – – – – – –
label | aa0d9e8f-c45b-5bfb-ba33-c100fc92fa5e |  | note | VERIFYING DOCUMENTS: Attached Lot Map
date | 9a3b2bb2-b018-5fce-bf4c-45a2c30f013b |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Site Clearing & Grubbing
label | 824f16b7-5504-5520-89af-63539b4131a5 |  | note | REFERENCE: IFC Drawings
label | 63cff46f-6793-52d5-b712-48ee2b886e81 |  | note | – – – – – – – – – – – – – – – – –
label | 1a01a863-4283-5b9e-950d-dc7c7e0f2e9f |  | note | ACCEPTANCE CRITERIA: If not completed during the site establishment, the work area needs to be cleared and grubbed.
label | bcb002ed-c54a-5c84-ba1c-ae74f287f356 |  | note | • Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.2
label | d2cbf0de-8864-5800-8cfa-d0da2605145f |  | note | – – – – – – – – – – – – – – – – –
label | 325530fb-4c85-5b6e-91dd-bac4b82ef227 |  | note | METHOD: Visual
label | 7002e901-a768-54e9-9c1a-bb3f62283e06 |  | note | – – – – – – – – – – – – – – – – –
label | 7d6439a6-0f5d-5fc3-a506-9e57b63b5fc7 |  | note | FREQUENCY: Where applicable
label | 5c66bde4-7c46-59ac-994f-f2b2b63bffa8 |  | note | – – – – – – – – – – – – – – – – –
label | 28960d9a-a260-549e-9ebb-d595488aba07 |  | note | CATEGORY: IP
label | e3c7a306-b7ab-5549-bbf1-a80cd1d7437a |  | note | – – – – – – – – – – – – – – – – –
label | 02d8697d-cacb-5548-b81d-2777002d7adb |  | note | RESPONSIBILITY: SE/PE/SPE
label | e17cdc57-5b41-5b00-a925-96891b510103 |  | note | – – – – – – – – – – – – – – – – –
label | 2689933c-9bfb-5199-b9c2-12f97092ec55 |  | note | VERIFYING DOCUMENTS: This ITP
date | 826ffebb-c0fd-5db7-a0e3-8725b1187b50 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 IFC Drawings
label | d2040f26-1129-585d-a04e-9e4dd0594ab8 |  | note | REFERENCE: MRPA Quality Management Plan
label | 4cbad991-90c9-5787-ab7c-75c19e01a2cf |  | note | – – – – – – – – – – – – – – – – –
label | 0a3ab6ec-b0f9-56de-a23d-619705a56626 |  | note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
label | c4a77406-3caf-5ed8-b646-cee3b83bdb22 |  | note | — Using the correct and complete set of drawings
label | f70b89ea-ccfa-5440-a222-c9984d0796d8 |  | note | – – – – – – – – – – – – – – – – –
label | bc6149ad-289a-5733-8710-1aa6faaf94fc |  | note | METHOD: Document Review
label | ccfec7d7-5cc3-5f1b-ba23-2f0ddb86dc42 |  | note | – – – – – – – – – – – – – – – – –
label | 06955dc2-3976-53ea-b905-a67fa5ffe86f |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 35a316b2-84d9-5bfd-a0f2-35bf0b5e74bb |  | note | – – – – – – – – – – – – – – – – –
label | 67dd9aa3-3220-5c84-bf2f-d6dc5b8d7f49 |  | note | CATEGORY: HP*
label | 4997436b-32c9-50c6-b91d-8186a61d0be7 |  | note | – – – – – – – – – – – – – – – – –
label | 261831e2-e762-5b8c-ae0d-81bb37a96507 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 538f1659-0dc1-517d-840c-4265d827e3a4 |  | note | – – – – – – – – – – – – – – – – –
label | 03c82516-a256-55bb-ba2a-98ecac5d95ee |  | note | VERIFYING DOCUMENTS: This ITP
date | 3f46b628-6fdd-53b2-8f15-ca12b72bfa76 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Excavation
label | 2edd880e-25ca-5df8-8906-725de4e202d6 |  | note | REFERENCE: 703.20
label | ef11e3cc-53ab-5b4c-84f5-ca004fe87580 |  | note | IFC Drawings
label | de34e989-22f1-57b1-8409-bda932089800 |  | note | – – – – – – – – – – – – – – – – –
label | 1d68071d-3414-598f-906b-930f7ab82ab1 |  | note | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
label | 761171c7-1d45-56ed-9071-3f79e15be6e9 |  | note | • Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
label | 7f7101e3-7a79-580e-9aad-884f457a3134 |  | note | • Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
label | d6a070d6-b3f8-591d-89b6-dd126c4206d1 |  | note | – – – – – – – – – – – – – – – – –
label | e71dbdd9-2ed0-5221-99d3-2755ba7dec77 |  | note | METHOD: Visual, Measure
label | c2171d5e-0bb8-527c-8efa-fe2d0e7b32f3 |  | note | – – – – – – – – – – – – – – – – –
label | 386d59cc-3935-569d-b4e1-2798cc0d7b5d |  | note | FREQUENCY: Each lot
label | 9fb51219-7d7f-5498-a508-b7e5faafe97b |  | note | – – – – – – – – – – – – – – – – –
label | 1db71cdc-7d19-553a-92b5-47448b584e77 |  | note | CATEGORY: IP
label | 41b1ebda-2f2b-5a07-ac5d-715a749d1496 |  | note | – – – – – – – – – – – – – – – – –
label | 283a0864-daeb-5716-939d-a1344e5c3e65 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e4ec1cb6-47e0-5675-9873-b9bb345accec |  | note | – – – – – – – – – – – – – – – – –
label | e7bb1a59-94a6-5690-ac04-feec752df8ad |  | note | VERIFYING DOCUMENTS: This ITP
date | ad0f3720-ca06-5243-827f-5f736248e98c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Excavation-Pavement Thickness Increases for Crossings
label | 91b7ce80-fdca-5f48-a518-516c8215b2d9 |  | note | REFERENCE: IFC Drawings:
label | f4606c2e-2225-5251-8d36-453041801df1 |  | note | MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
label | 1f5a4bd2-383e-5cba-992a-c8788ac64964 |  | note | Relevant Council drawings:
label | 4fed62d2-4a73-52a9-b5f9-10349528996b |  | note | • EDCM 501
label | feffdea7-0b1b-56f7-bd06-a4cb8cd683bd |  | note | • EDCM 502
label | 42146818-3f06-5882-9145-39fbf9bda4a4 |  | note | • EDCM 503
label | e9aa9d49-09d3-5a53-a516-5154db08a05e |  | note | – – – – – – – – – – – – – – – – –
label | b0ecc7d8-25a1-5430-bb43-9bc6403af567 |  | note | ACCEPTANCE CRITERIA: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
label | 3752e101-f1a7-5be3-b163-7d15d5e0ce95 |  | note | • Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | a99040e7-9699-52f1-b33c-5ec216697087 |  | note | – – – – – – – – – – – – – – – – –
label | d4d308d7-2001-5df6-ae5c-1aa908b710dd |  | note | METHOD: Visual, Measure
label | a91f635e-07e6-57c4-9b7a-58399b857594 |  | note | – – – – – – – – – – – – – – – – –
label | c88c405f-7ee1-58cd-b55e-3536ff7d7f22 |  | note | FREQUENCY: Where applicable, each lot
label | 139cdefe-7068-5093-b7c3-b9b0cd76b890 |  | note | – – – – – – – – – – – – – – – – –
label | 448bb1da-2769-5074-be70-06b4995343e5 |  | note | CATEGORY: IP
label | b7d27708-9ee7-5edb-84c0-8683c5e88f4b |  | note | – – – – – – – – – – – – – – – – –
label | 10f7aedf-5638-5131-9d94-3912623aa1d2 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9ad9e947-e11e-5353-8d50-b67c84f51cd0 |  | note | – – – – – – – – – – – – – – – – –
label | d1e724cf-258d-5383-8b82-4324d3983d07 |  | note | VERIFYING DOCUMENTS: This ITP
date | ab0bed56-a63f-53e0-85d9-3c3768853af1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Bedding Material Placement & Compaction
label | a62ad7f9-4418-5ca1-928f-c49c2d027057 |  | note | REFERENCE: 703.21 IFC Drawings
label | c3ce64b6-83a1-50c2-be61-8a81eb8c9f1d |  | note | IFC Drawings:
label | d8b5e32f-7954-53db-a0fc-0111652fa431 |  | note | MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
label | 8044e6f6-006c-588b-9ed5-fc2371e95a55 |  | note | Relevant Council drawings:
label | 51233942-2fcd-5e19-b11a-d7587c69d5dd |  | note | • EDCM 501
label | 3b8c50c7-dffe-516e-8e4f-a01a931f8610 |  | note | • EDCM 502
label | c4f3086d-2b93-5627-9ee4-37ca76b0d740 |  | note | • EDCM 503
label | 0b6eb486-2761-52c8-abe2-33fdf99a07b2 |  | note | – – – – – – – – – – – – – – – – –
label | 9331c19a-ffa3-5aca-9edf-2d6a5857675e |  | note | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings:
label | fc507a4b-5a4a-536f-896c-1311fca9232c |  | note | • Footpath: Bedding shall 100 mm compacted thickness
label | 2597f2c8-1a7c-55a9-8b5b-a7c03c86cada |  | note | • SUP: Bedding shall be 150 mm compacted thickness
label | 81060463-04f4-53e8-9507-3e2d267ef39e |  | note | • Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
label | 5bb277d5-6e48-5913-b873-3adfe7cd528c |  | note | • The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
label | f0ce2970-0397-5155-b208-b8cf476225ac |  | note | • All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
label | d24c54bf-92ec-54c7-84bf-f9ba8f875019 |  | note | Attach: Bedding Material Delivery Dockets
label | ef5f332c-6d2d-5256-b629-050829a7fa98 |  | note | – – – – – – – – – – – – – – – – –
label | 056d5136-8b52-508c-a956-08dc29cdb080 |  | note | METHOD: Visual, Measure
label | 1986796f-5434-5afe-9f19-cf7ab9afbc46 |  | note | – – – – – – – – – – – – – – – – –
label | db77ab9a-f487-5703-aefa-2ba189dc8e55 |  | note | FREQUENCY: Each lot
label | e34b33c7-6cdc-5080-a18a-d1aa3c7e4c67 |  | note | – – – – – – – – – – – – – – – – –
label | 96d63fab-922d-5a1a-a212-3029f6484d53 |  | note | CATEGORY: IP
label | 24451a31-0f6e-5db8-b3fb-ca2af48243da |  | note | – – – – – – – – – – – – – – – – –
label | 5b2d9421-39ec-5824-afb4-2081fb005df9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 307a4c9e-4a7e-566f-a689-ce8232778445 |  | note | – – – – – – – – – – – – – – – – –
label | 70781a26-aee0-5b2d-9d75-644c0c15ad45 |  | note | VERIFYING DOCUMENTS: This ITP
date | 307c4ad5-0114-5da5-968f-2d4cbba7549f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Shared User Path - Compaction Testing
label | f7055046-1704-54b5-892c-a9790d05e412 |  | note | REFERENCE: 703.21
label | 96ff219a-a485-5220-8a92-23859ed2009c |  | note | 304.08 (a) & (b)
label | c276e749-4663-5803-804f-0a94cc0e7ba8 |  | note | 304.11 (a)
label | 02036880-2462-5910-b34c-cd6ba4720664 |  | note | – – – – – – – – – – – – – – – – –
label | 44906deb-d2c4-57c8-8deb-e0fc1e814f35 |  | note | ACCEPTANCE CRITERIA: Compaction shall meet the following requirements:
label | 770e0c5d-745f-5624-81f1-3442f2f170c3 |  | note | • Scale of Surface Level Measurement = Scale C
label | 54baf202-4778-50d9-b87b-a0d7c3f2e867 |  | note | • Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
label | faf5aed2-cd01-5c3c-a671-fcaed180ee50 |  | note | • Mean Value of Density Ratio % (3 tests) not less than 100%
label | 7c93a7d5-1084-57ca-8617-236331b593f4 |  | note | Attach: Moisture Content Test Results
label | 4ac60631-d0f6-59c9-ad38-372fec2c0910 |  | note | Attach: Mean Value of Density Ratio
label | 29c08839-6bcf-58c0-89bc-dd6e0e7d3fb6 |  | note | – – – – – – – – – – – – – – – – –
label | d7be9aca-0344-5215-9fa5-7d0d9283761a |  | note | METHOD: Document Review, Visual
label | f8145038-161c-5a4c-b352-5b95231d43a8 |  | note | – – – – – – – – – – – – – – – – –
label | a787436c-eebd-5b64-8478-bd927394682e |  | note | FREQUENCY: Where applicable, each lot
label | 06fce67f-78d3-5d75-9e81-3975290504e2 |  | note | – – – – – – – – – – – – – – – – –
label | deef7d98-5542-562f-934c-a3ee2c166610 |  | note | CATEGORY: IP
label | 86c6b7f3-19f7-5292-9280-638677a471a5 |  | note | – – – – – – – – – – – – – – – – –
label | 1763033f-cf33-517a-81ea-c88315d7f593 |  | note | RESPONSIBILITY: SE/PE/SPE
label | ccb9236b-9562-56af-8265-51ab8af71073 |  | note | – – – – – – – – – – – – – – – – –
label | dcc98a4a-7d76-5b58-8efa-fdd69b6f75df |  | note | VERIFYING DOCUMENTS: This ITP
date | d3289d79-b4a5-5819-9eb6-258c58ca6b2f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Shared User Path - Proof-rolling
label | edfb8fc4-2108-5a60-a01c-21c09d6104f6 |  | note | REFERENCE: 703.21
label | 5f335392-563a-545a-8778-97331790766e |  | note | 304.08 (b)
label | eb13201b-147f-590f-9e17-4e79c1f33f98 |  | note | – – – – – – – – – – – – – – – – –
label | b28025f0-967f-5862-879b-dd2774a67dcd |  | note | ACCEPTANCE CRITERIA: Bedding material to be compacted and proof rolled before any construction.
label | 9d3e24d4-1acd-550d-9ac0-b6ee857a1a73 |  | note | • Withstands Test rolling without visible deformation or springing.
label | 54916573-a0bd-582f-bc5b-67d34080e7fc |  | note | – – – – – – – – – – – – – – – – –
label | b8dac25b-d8af-59b9-b7a1-07ad7300fc4f |  | note | METHOD: Visual
label | b5a190da-76a1-5235-b98d-53f5334de64d |  | note | – – – – – – – – – – – – – – – – –
label | 433ddf4c-d15a-53c8-ba66-c8461794edd1 |  | note | FREQUENCY: Where applicable, each lot
label | e6b52f9f-f1a9-5b54-a588-70579cb482db |  | note | – – – – – – – – – – – – – – – – –
label | efc08a40-9130-56fe-a353-b68995f3b27e |  | note | CATEGORY: HP
label | e8cb9039-bfc2-5db4-b3f9-ae985db55988 |  | note | – – – – – – – – – – – – – – – – –
label | 76a14fb2-a069-531a-a665-43fe2b564cb3 |  | note | RESPONSIBILITY: Nominated Authority
label | 64f5b852-408c-5a4f-a488-3b2afc35e65c |  | note | – – – – – – – – – – – – – – – – –
label | 877c355f-6981-5c62-b084-8ac07c6e820f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | e3057b95-07bc-529e-9957-5c43f9c05d52 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 5.6 Formwork Construction & Placement
label | 26993c83-77fc-5452-8e1a-0fe1c08ed83a |  | note | REFERENCE: IFC Drawings
label | 176c8234-27de-5842-9b43-29b711c3d8af |  | note | 703.12
label | a3cf90c9-2709-5c47-82bd-92973de9b538 |  | note | – – – – – – – – – – – – – – – – –
label | 56e04314-8522-59cd-927b-a73f48d7f9a4 |  | note | ACCEPTANCE CRITERIA: Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
label | f7576f40-d753-5b74-9237-9680a8cea8f2 |  | note | • Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
label | 5ecaa007-bce1-5504-8046-6185c3bb17c3 |  | note | • Joints in formwork shall be constructed such that loss of mortar is prevented.
label | bb8b3b60-d586-5a14-8d46-a7f4462b789a |  | note | • Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | a3ae53be-c8e2-5cea-993a-e9577be979dd |  | note | – – – – – – – – – – – – – – – – –
label | 9057814d-e7c3-5cec-8464-3e7ba6035cdc |  | note | METHOD: Visual, Measure
label | ca6c84c9-6ac3-5462-96b4-df1a7112cc32 |  | note | – – – – – – – – – – – – – – – – –
label | 17cd11c0-7da2-5968-a241-c0f7e86327ea |  | note | FREQUENCY: Each lot
label | 23afed9a-5191-54b6-ba5f-5510d7732b8e |  | note | – – – – – – – – – – – – – – – – –
label | 0fe5d45f-2f94-5a3d-bbf1-dea90642ced8 |  | note | CATEGORY: IP
label | 9ea62e38-f7e2-51c8-9d16-1fe3cc3c9234 |  | note | – – – – – – – – – – – – – – – – –
label | 25a0c60d-b1ef-5c94-8a59-79e073928626 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d0f3fd76-b833-59b5-b5be-8c374d804bff |  | note | – – – – – – – – – – – – – – – – –
label | e21a9ccb-2647-50cf-9e2e-96cf4d0e2a60 |  | note | VERIFYING DOCUMENTS: This ITP
date | 220abcae-6cd3-5548-9a28-9b5a6bb2c4d7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Construction Joints & Matching Existing Surfaces
label | 8a8b09d1-8f99-5a05-8c18-ec315f846fea |  | note | REFERENCE: IFC Drawings 703.24
label | 7bc5cf52-36a7-5147-9915-e99bccb1655e |  | note | Relevant Council Standard DrawingsRelevant Council drawings:
label | 82e2f162-32f6-5c1f-a31e-ec8227919785 |  | note | • EDSM 401
label | 6f380e73-1b6c-52a5-8626-f12122f896bf |  | note | • EDCM 501
label | 83e2cab0-1f9e-5e3a-982b-04ff2763c3d5 |  | note | • EDCM 502
label | cf05ebfc-deae-546d-b4d6-6ce32c749274 |  | note | • EDCM 503
label | 8ceaf1cc-cb2b-5339-87e4-3fe1f9af42b7 |  | note | – – – – – – – – – – – – – – – – –
label | 49ca563f-72af-5937-9861-5bd3d540851a |  | note | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
label | 22e95ed1-1dcd-58e9-b520-f6695f7e16bb |  | note | • Consult the relevant Council Standard drawings for the joint detail, these may require:
label | 53202686-541b-5971-8d5b-fbc109adac5c |  | note | i. Concrete cutting of a shear-key
label | c046e412-fc46-5ef5-b891-71594fd70def |  | note | ii. Surface roughening
label | b7e24e42-85c7-54a3-bc1e-1b0c4378bc54 |  | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
label | b28ac9a4-c874-5c17-af71-1bc7c414ab3f |  | note | iv. Cutting a groove for sealant
label | 7e98867c-fe98-5410-937f-c6bdbf8bd84a |  | note | • Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | 1de8c9e7-8d37-51fe-82f8-c08e0983fde2 |  | note | • Transitions between different profiles shall be made in accordance with the drawings.
label | a09cefe6-aa97-5882-b0ab-07edaf7829ab |  | note | • Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
label | 974eddfe-bd5c-519c-b238-3eb13a0df08d |  | note | – – – – – – – – – – – – – – – – –
label | 934846c8-17fb-5a9f-902b-a7d0f1065e4c |  | note | METHOD: Visual, Measure
label | 76e4d39a-eafd-5933-bcd5-e715c2716b39 |  | note | – – – – – – – – – – – – – – – – –
label | f0620072-cafd-5a1d-adb6-de05d497fc22 |  | note | FREQUENCY: Where applicable, each lot
label | 05fd7679-1671-5d50-9d64-fec32a1f18d0 |  | note | – – – – – – – – – – – – – – – – –
label | 3736cd6d-deda-57b1-84d4-1204146bbc34 |  | note | CATEGORY: IP
label | 49edea88-bfdc-5bce-85de-ae2a58d1abbb |  | note | – – – – – – – – – – – – – – – – –
label | 5814f3a5-c87e-52db-8fd4-f9ae51338a49 |  | note | RESPONSIBILITY: SE/PE/SPE
label | cb657ea5-7766-59ca-8a3f-b78283f9f4b7 |  | note | – – – – – – – – – – – – – – – – –
label | 2deca750-4fcc-5eee-8732-55d48f5865a4 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8fd72735-aa04-5f2e-ab73-40223899798e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Isolation Joints
label | ed4496cf-c91c-5951-b62c-9a41cd3a6ddc |  | note | REFERENCE: IFC Drawings 703.26 (c)
label | 39db067e-43e5-5c21-87c6-ab703339097d |  | note | Relevant Council Standard Drawings
label | 67a05e49-8378-5c62-ada5-98b4567e9938 |  | note | • EDSM 401
label | 4ad4478b-5e22-565c-91a5-0784b162e000 |  | note | • EDCM 501
label | 2a4eb86a-7a25-5d06-bde4-65d63509b4ef |  | note | • EDCM 502
label | c9e6b669-f2fe-5154-868e-72e558d1b2e6 |  | note | • EDCM 503
label | 6d6bbb6e-e00c-5f78-89de-e3ee3c6d28ed |  | note | – – – – – – – – – – – – – – – – –
label | c1b0b43c-a59a-51cf-b1e8-ccb4f5ae7377 |  | note | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
label | c06e86d1-9774-5ed5-9a86-f67e131f4672 |  | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
label | 8d8ea595-abf7-5898-87dc-9db659df9000 |  | note | ii. at any location marked on the drawings
label | 76b68988-7455-5c86-bf1b-a0280ac3710a |  | note | • The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 4b9c7047-bd7e-5374-81e3-17076ca26e13 |  | note | – – – – – – – – – – – – – – – – –
label | 5725d20f-eb56-5da3-89fd-b103f9b76d5a |  | note | METHOD: Visual, Measure
label | bc6ad154-0982-5f98-b925-ef473be442b0 |  | note | – – – – – – – – – – – – – – – – –
label | b0f0c8e4-7346-543c-8a17-88b31e565c78 |  | note | FREQUENCY: Where applicable, each lot
label | 2c52a4d4-df1c-5910-8931-714633f28a70 |  | note | – – – – – – – – – – – – – – – – –
label | a37b60a8-181e-55b2-b63c-c7870c73c765 |  | note | CATEGORY: IP
label | a4da6d0f-bbfa-528b-b7f9-ee5180db5c46 |  | note | – – – – – – – – – – – – – – – – –
label | 2d210148-6b06-5456-88c8-d072ae3c7cd1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | efd0419a-3dbc-5aed-86d2-d81832aa773b |  | note | – – – – – – – – – – – – – – – – –
label | 536a1900-70a2-5bb9-b492-7898a36303fb |  | note | VERIFYING DOCUMENTS: This ITP
date | 869c6d21-7a72-5d3c-8f77-d3ca7e640ae0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Expansion Joints
label | ed79a288-24ac-5453-9387-19dc13db620e |  | note | REFERENCE: IFC Drawings 703.26 (a) (ii) & (b) (i)
label | 9b72ee9a-8ece-5ca6-a335-8ab6251491e4 |  | note | Relevant Council Standard Drawings
label | 27c17791-0b8c-5a3d-9c8b-1dc0f7a925f2 |  | note | • EDSM 401
label | af2bf872-7619-59f1-bb20-7f554ad26982 |  | note | • EDCM 501
label | 5d4646a9-f835-5898-ac0c-7d72d39d9684 |  | note | • EDCM 502
label | 9c2d9834-d306-51ee-9884-e44373b75bfa |  | note | • EDCM 503
label | 8d581f1c-d71e-5d7d-8787-bb0aad048d3c |  | note | – – – – – – – – – – – – – – – – –
label | ffb5831e-9f60-51c2-8e04-55ff2df34c33 |  | note | ACCEPTANCE CRITERIA: Where applicable, expansion joints shall be placed:
label | 31c85add-85c2-5ca6-9b77-5ac273cfa3cd |  | note | i. on either side of vehicle crossings
label | baca2adc-be89-51a0-b16f-9178e023d57a |  | note | ii. at junctions with existing footpaths and shared use paths
label | 8f5cddeb-abad-5d21-82d4-6cc6cd8c6942 |  | note | iii. at junctions with bridges
label | 586e2018-eb41-592c-a8b5-e406fe3a2d6b |  | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
label | fa9462c5-061c-58ee-804b-c3988f8c791b |  | note | • The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 99e5eeaa-19a6-5b6d-bbfb-0bf2163dc61e |  | note | • Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
label | 5c54e5c4-37d7-5e22-96eb-ba972ebc7b8c |  | note | • Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
label | 2ca08b03-fce5-58e7-b32e-5f96c7081831 |  | note | – – – – – – – – – – – – – – – – –
label | 5ed258a8-e6cd-5ce3-8cea-e16937398347 |  | note | METHOD: Visual, Measure
label | 12ac50c8-93f1-56f8-9661-93733a5d7cad |  | note | – – – – – – – – – – – – – – – – –
label | 123431c6-9920-5476-b5d7-75062c113e7d |  | note | FREQUENCY: Where applicable, each lot
label | 99a146e8-819a-5f04-a537-d4299f502010 |  | note | – – – – – – – – – – – – – – – – –
label | c9cc577f-50ad-5571-93ab-8bf39a003bf2 |  | note | CATEGORY: IP
label | 1f952491-d27c-5f18-9d8f-f8877939399f |  | note | – – – – – – – – – – – – – – – – –
label | da859022-8219-5fd5-bba7-87b4efd334c2 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 527c57f6-18c2-5ccc-945a-be344114838e |  | note | – – – – – – – – – – – – – – – – –
label | 5c62ce19-9ddf-58cf-b0cc-ce2509fa0239 |  | note | VERIFYING DOCUMENTS: This ITP
date | 77c40173-c4c7-58f7-88f1-6518aef8818c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Reinforcement Placement
label | 8a2a3b92-b378-5656-89d7-0b07556c8194 |  | note | REFERENCE: IFC Drawings 703.13
label | 4133543a-597b-5e10-8f18-e85659481f77 |  | note | • EDSM 401
label | 600f415f-c2b0-5437-a58d-3ff9dbf0b719 |  | note | • EDCM 501
label | 784ef684-668f-5601-b7d5-7e71c3645616 |  | note | • EDCM 502
label | bb3affb7-c3de-5e7d-aedf-8bf458a69e60 |  | note | • EDCM 503
label | 803b0eb8-9dd4-5e60-b2ef-a6e5480dffde |  | note | – – – – – – – – – – – – – – – – –
label | 853353b2-1699-591f-8f75-4f6a86e3f2fb |  | note | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
label | e9a52d0f-d019-5352-b57a-f802f4ae1ab7 |  | note | — Footpaths, Residential driveways and Median islands infills: SL72
label | 90252b38-9017-5414-8802-9cd9eed087be |  | note | — Industrial Crossovers: SL82
label | a9c2518a-496b-522e-b370-ff1573272d16 |  | note | — Traffic Islands: SL72
label | 09868269-99ea-5a3e-956c-f7054f1ae906 |  | note | — SUP: SL82
label | 8389ccc1-ef23-5bd9-8861-661ee4ca2f9e |  | note | • Minimum cover of 50mm at edges has been achieved (including tie wire locations).
label | c2a5e258-0806-51cc-9341-d14bbf14426d |  | note | • Any splice lengths achieve the minimum length and are in contact for this length.
label | 6e8366ab-ac86-58ec-a127-8efc167d7031 |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | dcee12c7-5570-56d6-afe6-1d01e1144607 |  | note | • The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
label | 3d2437c5-bdd5-517c-890a-2d1a495c4c13 |  | note | • Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
label | 3ac8e3e5-fb71-5785-895f-ff6807a165e2 |  | note | – – – – – – – – – – – – – – – – –
label | 99791648-1a85-5aae-a056-bebea5652979 |  | note | METHOD: Measure, Visual
label | 25e7940e-4f80-5fe9-84d4-d92b4ff34543 |  | note | – – – – – – – – – – – – – – – – –
label | 66429bad-dd09-53c8-bb0a-d27cf41ed5ca |  | note | FREQUENCY: Each element
label | bd172e1a-a229-50c0-bf92-99ec507cf49d |  | note | – – – – – – – – – – – – – – – – –
label | 37e4d7f7-4e03-5932-881a-943657e10666 |  | note | CATEGORY: IP
label | 8936e843-2ee4-5060-9811-d27925a7ab59 |  | note | – – – – – – – – – – – – – – – – –
label | e496d13b-8e06-5e21-9bbf-c274a7c889f4 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 72d36f5a-88e3-5cfe-a573-ac4bdfd84a2e |  | note | – – – – – – – – – – – – – – – – –
label | 43cdaaa8-a2e9-5e9f-b49c-323af5c775a4 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8a4feb4a-8138-5b9b-af2e-708ded5bd9bc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Pre-pour Survey
label | f8cc220e-eae7-5846-9416-914b6d86c92d |  | note | REFERENCE: IFC Drawings 703.15
label | c6bfddcb-49c5-50aa-a343-0db2093ca429 |  | note | – – – – – – – – – – – – – – – – –
label | 7c09b625-1c95-5c42-96e9-51138736d5a8 |  | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
label | 461d5096-1466-5b37-810c-c5406c480094 |  | note | Erected formwork and base layer within the tolerances below:
label | 5d0c15cb-1c3e-564f-b9a1-75dc6facdc02 |  | note | • Departure from RL = ±10mm
label | d13e71e1-48f1-5b6c-93cb-776e6529f309 |  | note | • Departure from alignment = ±10mm
label | fc8bac5e-9566-554b-bdfe-5a69479ead9d |  | note | • Rate of change of deviation from RL or alignment = 10mm in 10m
label | f3585ed9-c477-5ac6-8c8a-cb5e2d32013a |  | note | • Irregularities in alignment = 5mm in 3m
label | d1929f03-1641-508c-9697-bd1798cd059c |  | note | • Section dimensions = ±5mm
label | d36b17d3-b832-547b-892b-2ae83733fb4d |  | note | • Section dimensions (less than 25mm) = ±3mm
label | b3be4eb2-75a7-5cc6-b5e9-7f3e98421aea |  | note | • Width of pavement = -5mm, +15mm
label | 84d8ac3b-9ef7-5c63-8b6a-51ebded9a883 |  | note | – – – – – – – – – – – – – – – – –
label | c0bbfe2e-592d-52a3-9d62-4e1e0df3d75f |  | note | METHOD: Measure, Visual
label | a1ef62a1-cef3-5bb0-b8f9-473bedb5b30a |  | note | – – – – – – – – – – – – – – – – –
label | 925ed43a-4f3e-5336-96ed-0ac681acf360 |  | note | FREQUENCY: Each lot
label | ab9287f0-47fe-5598-948d-744127c1963f |  | note | – – – – – – – – – – – – – – – – –
label | b970d517-01db-557b-b406-d9300a8e230c |  | note | CATEGORY: HP*
label | 04d1b7db-fc98-5975-a28b-32845b025555 |  | note | – – – – – – – – – – – – – – – – –
label | 8a53c71f-25d2-526d-8301-5c104418755a |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | fbf98017-68fe-509e-bbec-ba83d65d8d4c |  | note | – – – – – – – – – – – – – – – – –
label | 5544992c-10aa-5128-9ab2-f5ccc28effb5 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8fb8774a-36a2-51d4-9595-bf9d0b58643a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Pre-pour Inspection
label | 9cb9973d-b01c-5c67-af8d-a952ccf78e7b |  | note | REFERENCE: Section 703.09
label | 1712d846-26eb-59dd-9378-1c60bc5ba38e |  | note | Section 703.21
label | dfff3cce-d9bd-510c-a5ef-75d2697f5a8f |  | note | Section 610.17a), b) & c)
label | 00a462d1-dee7-5210-960d-301a7168beb8 |  | note | – – – – – – – – – – – – – – – – –
label | a127eb97-b110-5ce7-a351-e8c599a69da0 |  | note | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
label | d57a7c34-5f20-5f74-8302-140263ac9b4d |  | note | • Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | 241ad0ed-7147-50cd-9642-65e3fbe1ebd9 |  | note | – – – – – – – – – – – – – – – – –
label | ec710015-5f2d-57a2-bae8-3f9521421c4c |  | note | METHOD: Measure, Visual
label | d7626c04-d88c-5a85-ac66-26117d060a11 |  | note | – – – – – – – – – – – – – – – – –
label | 3569d93b-5045-56a8-870a-a230c394a659 |  | note | FREQUENCY: Each lot
label | 161bd7f7-da24-5eb1-86a1-dfa4f99433e0 |  | note | – – – – – – – – – – – – – – – – –
label | ab718df3-7cfb-5511-80eb-32fd7b3d7ae5 |  | note | CATEGORY: HP*
label | 45cccfb2-500a-5825-811c-b351d99358d4 |  | note | – – – – – – – – – – – – – – – – –
label | 6daf87e7-2071-5717-8a36-34f91b4d565a |  | note | RESPONSIBILITY: SE/PE/SPE
label | 698830a0-e138-588e-a3a9-ec8b5156d616 |  | note | – – – – – – – – – – – – – – – – –
label | 7d802580-3d4b-54d8-a857-968bb3a7dd6d |  | note | VERIFYING DOCUMENTS: This ITP
date | da944a5c-0008-5681-9259-22ae8a98b0c3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Weather Conditions & Evaporation Limits
label | 1b7ce114-5047-579b-95f7-909e4ff65cb1 |  | note | REFERENCE: 703.09
label | 49ee9f3d-43be-5d74-b6f6-5747f31faf7d |  | note | 610.17 (a - f)
label | d7b70446-c046-5ea3-bbf3-a7c1eef585ee |  | note | Table 610.171
label | 9f0c2c67-0acd-5117-a9da-11411fe77061 |  | note | – – – – – – – – – – – – – – – – –
label | bba4e4f2-c3da-5a1a-9260-5c93f4def278 |  | note | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
label | 1b66151b-5f6e-56f6-8033-74005a865b17 |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | b89ca60e-bad1-5827-b3b2-4799aa5028bb |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 601874fd-8b64-5e8a-a13f-d3c025c4c068 |  | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | c378cc48-e507-5c26-80e9-6aae670ee0a8 |  | note | • Record: Required information on the Concrete Pour Record.
label | 6962cdcc-0355-5e2a-acdb-f56a5c52a8a6 |  | note | – – – – – – – – – – – – – – – – –
label | b02e77ed-c43f-5229-8b36-0ae1eccc18cf |  | note | METHOD: Measure, Visual
label | a2a8d1fd-e690-5e89-ba61-3a834496da73 |  | note | – – – – – – – – – – – – – – – – –
label | b7c3252f-6a6f-5f13-a520-a01cf480c309 |  | note | FREQUENCY: Each lot
label | 2f8208e7-6d5c-5c83-a49e-94e97bee422b |  | note | – – – – – – – – – – – – – – – – –
label | 137db7ff-93ac-5108-a63e-31cf6762676b |  | note | CATEGORY: IP
label | cf61b922-48eb-5357-83dd-323e756c8a51 |  | note | – – – – – – – – – – – – – – – – –
label | 224f61ea-70ee-5096-a915-aa4c8a36cf19 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 87f28a89-c99b-5e09-a325-12551bd26f08 |  | note | – – – – – – – – – – – – – – – – –
label | de5bd5f2-476d-5d11-8546-92eff40b9acb |  | note | VERIFYING DOCUMENTS: This ITP
date | e9ddba16-afab-5a8b-ab39-658e26363e18 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Concrete Testing - Sampling Frequencies-Footpath
label | 7c822308-28d3-5d9f-8e1d-153738695dab |  | note | REFERENCE: 703.11
label | 91a6eb39-79d4-5589-bb42-68e89b032363 |  | note | AS 1379-2007 Clause 6.2
label | 38ce9c3a-d571-5e7a-ae84-06ec2350f0eb |  | note | – – – – – – – – – – – – – – – – –
label | 38a4dba2-422c-5d00-9a5a-41e416ace718 |  | note | ACCEPTANCE CRITERIA: The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
label | 2273e34e-7685-5ad4-aea3-7647243663b3 |  | note | • Correct quantity of cylinders manufactured per sample.
label | d6bca5d7-78c1-530c-8960-18c3d5262582 |  | note | • Record: Required information on the Concrete Pour Record.
label | c3801267-b369-5782-8cac-ef093809ed59 |  | note | – – – – – – – – – – – – – – – – –
label | b565ab4f-6af5-5ea5-a807-81bf5a4ad375 |  | note | METHOD: Test
label | b608fc54-639f-564a-b3b4-e30bda05c8fc |  | note | – – – – – – – – – – – – – – – – –
label | e9b8da59-52f7-57d3-8cf1-f356fd19689b |  | note | FREQUENCY: Each lot
label | dbc4fbe7-9ac9-5dfb-a441-aabb3d60436b |  | note | – – – – – – – – – – – – – – – – –
label | d9469718-0e8f-5d03-90fc-02c82c40e31a |  | note | CATEGORY: IP
label | d9db5702-8281-585b-9b29-e7dd42fe129c |  | note | – – – – – – – – – – – – – – – – –
label | 27edf007-e425-5fdd-b5ec-0c32d2455a68 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | 6b12c881-92e8-5c15-933f-bf15ab1efb33 |  | note | – – – – – – – – – – – – – – – – –
label | 9893d0a2-171a-5de9-9526-41fab35c8993 |  | note | VERIFYING DOCUMENTS: This ITP
date | cb7bfef7-d9a0-5c81-bc56-81d62a5435da |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Concrete Testing - Sampling Frequencies-SUP
label | cfc2b2c7-e269-599e-a57c-d31045c0afff |  | note | REFERENCE: 703.11
label | fef7fa7f-c7ed-5034-9891-815ce8a3dca0 |  | note | 610.16 (b)
label | a5738060-fe3b-526a-acd5-83b3c6df7ec3 |  | note | – – – – – – – – – – – – – – – – –
label | 42bb920f-aac9-5fcc-938e-fdedcf3e6d5c |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 925fc771-c0e7-51ff-8df2-147775ff2690 |  | note | Shared User Path:
label | 275b4465-e869-5264-b055-0968251bf5ed |  | note | • 0m3 to 10m3 = 1 sample
label | ab9ebe12-612f-5b8c-9252-8199e0a6862b |  | note | • 10m3 to 25m3 = 2 samples
label | fa5a4c9b-bd38-5a07-91f5-55c332768b7f |  | note | • 25m3 to 50m3 = 3 samples
label | c097be04-cbe6-5a39-a000-aef6c5392cfa |  | note | • 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
label | ea27dd71-266a-5d40-99d1-40a5c6e16d55 |  | note | • For each additional 50m3 and additional sample shall be taken.
label | 20a8183e-d0c6-5563-a7f0-570924c2d74c |  | note | • Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
label | 8a0685f2-4d88-5fd3-8248-8be283f61f1d |  | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | d8fba83e-7470-5ffe-9424-fa04132b37dd |  | note | Footpaths:
label | 85354775-fe96-5eef-a58d-5d1bbab2eb8d |  | note | • 0m3 to 50m3 = 1 sample
label | 3f8e2105-ea7b-5838-899f-2d9bda23418c |  | note | • Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | be1bd30c-788e-53e8-bcfd-259df13f51a8 |  | note | • Compressive strength cylinders = 2 no. 28 day strength.
label | a0add223-7449-5303-aa7c-6ce3b1039823 |  | note | • Correct quantity of cylinders manufactured per sample.
label | 92c3fdd3-21a2-5fd9-bfc0-882d33da3a3f |  | note | Record: Required information on the Concrete Pour Record.
label | 44ea6652-ae05-55ec-bde4-28dc2b88f0f1 |  | note | – – – – – – – – – – – – – – – – –
label | 638979f1-2c74-5154-a632-cc1458c6f578 |  | note | METHOD: Test
label | d4d842e8-9007-55df-8058-731e1d3d13fc |  | note | – – – – – – – – – – – – – – – – –
label | a3919df6-a94f-56a7-9a15-a23ed450c7eb |  | note | FREQUENCY: Each lot
label | f8195f6e-8dd4-54e3-9fe2-a1131157f1e1 |  | note | – – – – – – – – – – – – – – – – –
label | 523a6119-f186-597a-a542-0e567780eb58 |  | note | CATEGORY: IP
label | b85f56b2-1047-57d4-ac46-2395059f1542 |  | note | – – – – – – – – – – – – – – – – –
label | df488a7d-a1b4-582c-ab29-b50b37190b58 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | cb830b48-5ea8-517f-9e25-4d7a9d092b03 |  | note | – – – – – – – – – – – – – – – – –
label | 442369a9-855a-50cc-82db-4bdc7b45d9fb |  | note | VERIFYING DOCUMENTS: This ITP
date | 34c3ce19-2868-56fb-80f2-93fcfe8ed2d0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Concrete Testing - Slump
label | c7b3a0f5-40eb-5729-a3ee-c2e0402a9987 |  | note | REFERENCE: 703.11
label | 6aa2443b-18f6-5c2f-a9e7-d59fb8f43649 |  | note | 610.16 (c)
label | 2370b6bd-d597-517a-86de-f200074407e3 |  | note | – – – – – – – – – – – – – – – – –
label | 29d847ee-aca0-5632-8b2d-a9fe0141a6a2 |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | ed2570ce-9f86-51f3-953d-dfd12d768aab |  | note | <60mm = ±10mm
label | 7a94d04a-f5b2-5105-a5f2-54a12272c14b |  | note | ≥60mm to ≤80mm = ±15mm
label | 76f1cc61-1391-5fc2-8459-7cf6343fee1a |  | note | >80mm to ≤110mm = ±20mm
label | adacdba2-65c8-5d76-ba68-2d30448208c8 |  | note | >110mm to ≤150mm = ±30mm
label | 1be0b479-c11c-5355-a1be-508f3ed21167 |  | note | >150mm = ±40mm
label | 38ea3944-7620-52fc-aec0-ee27bdca55f5 |  | note | Record: Required information on the Concrete Pour Record.
label | 02b4bfc4-9900-54d0-a9ad-226d679b13c8 |  | note | – – – – – – – – – – – – – – – – –
label | 4942f767-ca98-5cb3-8fd2-b99c14ae65f1 |  | note | METHOD: Test
label | 15ba736c-06dd-54ce-9dd3-e0fe9c01c07d |  | note | – – – – – – – – – – – – – – – – –
label | a5771780-07f5-597a-b89c-7544dc1faee9 |  | note | FREQUENCY: Each sample
label | 8097f330-cb66-5fc5-861f-2d139480fc77 |  | note | – – – – – – – – – – – – – – – – –
label | 575155e4-fc2a-5af5-86c6-9e625084e46a |  | note | CATEGORY: IP
label | f50227fd-c87b-5573-a8fa-cbdeedb46541 |  | note | – – – – – – – – – – – – – – – – –
label | dbbe2384-288a-5638-850e-f6903c1b6f2a |  | note | RESPONSIBILITY: Concrete Tester
label | ad395592-948f-527e-a59f-f6017760f493 |  | note | – – – – – – – – – – – – – – – – –
label | 6c121bd3-bab7-5473-9aa0-88544b350642 |  | note | VERIFYING DOCUMENTS: This ITP
date | 09d8e152-4bfd-5111-949a-5783a927533f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Placement & Compaction
label | 46f369b1-f154-503c-ad9c-e913308877b2 |  | note | REFERENCE: 703.08
label | 2f1fc36f-0246-5de5-8fed-bbc0de2dbb9f |  | note | – – – – – – – – – – – – – – – – –
label | 87a1de1d-74af-5bb9-925e-650f6691971e |  | note | ACCEPTANCE CRITERIA:
label | f337802c-1557-54d9-a214-7e9096d8b776 |  | note | • All concrete batches are traceable.
label | a84247b3-3c2c-5287-9397-4197644eaba3 |  | note | • Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
label | 35c7ba17-569f-5fe8-869a-86418054d78e |  | note | • Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 5e4ed095-8e1c-5137-9fd4-23da37fb0d0a |  | note | • Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | 9e5e4642-08d8-5982-9dbd-1f10b12bdb95 |  | note | • Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
label | a7edb8d1-24b1-54ca-a561-bbe76adc9b6b |  | note | • Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | dc1076f0-45a0-5969-8e2f-323cb04e172e |  | note | • Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
label | 07d583f6-ab9f-5286-b5d8-2cd1c2b66eeb |  | note | Record: Required information on the Concrete Pour Record.
label | b14bc880-71e7-5c5c-b42c-1b76994422e4 |  | note | Attach: Concrete Pour Record
label | b4ad7267-2427-52e2-ac54-7bd17ecbf6dd |  | note | Attach: Concrete Dockets
label | 20564637-3210-5da4-8048-81f158bbc10c |  | note | – – – – – – – – – – – – – – – – –
label | 572086ba-60f8-5027-8546-35bb30baa9f7 |  | note | METHOD: Visual
label | a96cac2b-db13-5046-b253-119ae7ddcc0e |  | note | – – – – – – – – – – – – – – – – –
label | 7205747a-d00c-5ab6-8eee-78a518ae065c |  | note | FREQUENCY: Each load
label | 21ae167a-b087-5559-bcfc-3e424222878f |  | note | – – – – – – – – – – – – – – – – –
label | 3a068867-be89-5044-b557-cf208d2a8436 |  | note | CATEGORY: SP
label | 86963b1d-5dd7-52f8-bda6-71c6b044ebe9 |  | note | – – – – – – – – – – – – – – – – –
label | 8c28668f-23a4-5579-97e0-e3843fd8090f |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 1effec2d-1027-5bf0-bedc-64141642acb7 |  | note | – – – – – – – – – – – – – – – – –
date | 6c76c8ef-6094-5616-b509-6d3559a299be |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Surface Finishes
label | d305f8e0-120b-5791-8b38-a6f7af72f6eb |  | note | REFERENCE: IFC Drawings
label | 133a62fb-ee34-5a44-b770-9800f86993ed |  | note | Relevant Council Drawings
label | 43a22e9f-1284-5128-9939-e20b617ae9c1 |  | note | 703.25
label | f4a604ec-ab96-5615-95e6-9075e852beb5 |  | note | – – – – – – – – – – – – – – – – –
label | a570ee28-5449-5221-84d6-d9962a015a9f |  | note | ACCEPTANCE CRITERIA: Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top.
label | b95725c2-405f-5323-ac67-ab15a0cffd26 |  | note | • It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
label | 2e46d909-00b1-537b-8ecf-e08ac0cb9093 |  | note | • After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
label | 79c1f51b-967a-51e0-9c2d-ace9428f18c0 |  | note | • Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
label | e9edaef6-7e39-5b19-9ea0-dcff9ab69a6d |  | note | • All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
label | 11a7d353-5255-5be0-a49c-59f3db64d5e4 |  | note | – – – – – – – – – – – – – – – – –
label | eeaa27b9-bec0-5113-95e8-7ec8cd1fba08 |  | note | METHOD: Visual
label | 297417e1-eec2-5891-acb7-0c740a1c1fbe |  | note | – – – – – – – – – – – – – – – – –
label | 0cef983c-8056-5a4d-9074-050959db394c |  | note | FREQUENCY: Each lot
label | 4145afa3-b1e3-597f-9959-3406daa9b236 |  | note | – – – – – – – – – – – – – – – – –
label | 6998986a-ea71-58df-89d1-5b06881f2de4 |  | note | CATEGORY: IP
label | db4a68ae-6594-56a1-9549-8eaf969bb2df |  | note | – – – – – – – – – – – – – – – – –
label | 41a8abbe-569c-577b-96b3-d7192956d877 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 7de01627-a8f6-5edb-8e4b-2cbcd5941c45 |  | note | – – – – – – – – – – – – – – – – –
label | a7ddc907-2e82-5c81-903c-91783938cc32 |  | note | VERIFYING DOCUMENTS: This ITP
date | 354ee154-1167-53a6-83e1-2ea782690584 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 Footpaths - Crack-control Joints / Weaken Plane Joints
label | 5cf3fab7-d224-5f58-b3e0-b08ec89fbe5c |  | note | REFERENCE: IFC Drawings
label | 90830ed8-5405-5b86-a1e8-7d570b7dd3d1 |  | note | Relevant Council Drawings
label | 91b199b3-b9a2-5b9b-b182-c7cdb3bdcd7f |  | note | 703.26 (b) (ii)
label | ee62d189-d4b4-50b4-8a51-700980847ed8 |  | note | – – – – – – – – – – – – – – – – –
label | 826ce92d-caf1-56ca-8068-795b04256c46 |  | note | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
label | d44a59a3-966c-5621-8cb0-065abb7d2fa5 |  | note | – – – – – – – – – – – – – – – – –
label | 22be39fd-fd35-58fc-9611-2cca6fc64f49 |  | note | METHOD: Visual
label | f9be2ba4-04c1-57a2-bbff-bfd42451eb78 |  | note | – – – – – – – – – – – – – – – – –
label | 038f31dc-f99d-5d95-8850-396888698423 |  | note | FREQUENCY: Where applicable, each lot
label | bd1243d3-296e-5e5e-8b90-61bb6e12b2cc |  | note | – – – – – – – – – – – – – – – – –
label | a31b7a81-f4bc-5e54-b70b-951855a9eee2 |  | note | CATEGORY: IP
label | c8337e70-b4e6-53dc-9b1e-fb0684437676 |  | note | – – – – – – – – – – – – – – – – –
label | 566ba001-b394-553e-bd1d-d7ec2a5a02bb |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 67310f25-d900-563c-8f05-aa588ab65080 |  | note | – – – – – – – – – – – – – – – – –
label | 996e1616-713d-53a8-a8d6-b1b5efb959e1 |  | note | VERIFYING DOCUMENTS: This ITP
date | 7f41f349-1542-536e-b48a-b3425cc6f6fc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 Curing
label | dd804e12-e8f9-5f14-94c3-8bb9e9bd45f9 |  | note | REFERENCE: 703.10
label | c7d5da92-988e-5f8c-851d-e0aeff4f08d3 |  | note | – – – – – – – – – – – – – – – – –
label | 2e16ec37-3cb6-593b-b8d9-5c2ffd620e76 |  | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | 2ca0f17f-903f-5d28-ab4b-654f9bfccf0a |  | note | • The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | 0a53e1f9-0503-568c-8006-7e027474b69e |  | note | • Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
label | c3d9d294-ccba-5804-96cb-f1be78887f35 |  | note | • The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
label | 45ef870c-5415-5a80-af70-95ed5b8ca5a8 |  | note | • Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
label | 5cbd600f-3569-5c6a-9614-1122a7b569be |  | note | • Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
label | 0a56bb5e-8884-5a3f-a620-86f35e93519a |  | note | – – – – – – – – – – – – – – – – –
label | 43593746-c9a0-5340-bbaa-b447774d4ddf |  | note | METHOD: Visual
label | 72c23070-e181-5609-a1ae-d87de1b7fd3a |  | note | – – – – – – – – – – – – – – – – –
label | bbcdfd17-5b42-5a13-8db9-9280a405c0da |  | note | FREQUENCY: Each lot
label | 7036eba4-e94c-5ca1-9564-65cd2ff3abed |  | note | – – – – – – – – – – – – – – – – –
label | c8ccd703-3ae5-532c-9d88-ddc93e2c0d3e |  | note | CATEGORY: IP
label | 78c72fbc-3a56-5b26-bda5-eb58eeaf4a4e |  | note | – – – – – – – – – – – – – – – – –
label | a4c68d98-130f-58df-8381-91f84bda3884 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | be38fb10-20e0-5a6d-99c1-0c3b7e8f632e |  | note | – – – – – – – – – – – – – – – – –
label | adad98d8-b5d6-51de-9a47-402665c6b9e1 |  | note | VERIFYING DOCUMENTS: This ITP
date | 7bef9f79-b85b-5d87-8e6d-9e7f64db7cf5 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Shared User Paths - Crack-control Joints / Weaken Plane Joints
label | a793e873-9a4c-51ab-be4d-0beae395eb45 |  | note | REFERENCE: IFC Drawings
label | 6f456919-ded4-5d34-ac81-f082f54b049d |  | note | Relevant Council Drawings
label | 10ab3a2f-b313-5265-a6bd-e312e6fd3446 |  | note | 703.26 (b) (ii)
label | c3a4477d-5230-500a-b5ad-29e1e02f1b81 |  | note | – – – – – – – – – – – – – – – – –
label | 2a8564f9-9eb9-5eaa-ba83-ccd099a19fca |  | note | ACCEPTANCE CRITERIA: Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
label | f86d15df-96ad-5fa1-a514-23158d8800a1 |  | note | <20°C = within 24 hours of finishing operations
label | eb4e598c-bd4e-5716-a1c5-2468982b6840 |  | note | ≥20°C - 35°C = within 4 hours of finishing operations
label | ac73e02c-daab-5d12-a7c5-6c9df337787c |  | note | – – – – – – – – – – – – – – – – –
label | 7b6c9f4f-fbde-5393-a1fc-1df2602a257a |  | note | METHOD: Visual
label | 0f075842-9b55-54a3-8ff6-867fa6e28235 |  | note | – – – – – – – – – – – – – – – – –
label | 9418cd10-b914-5b7f-8155-17cd8e7a4c33 |  | note | FREQUENCY: Where applicable, each lot
label | a0890c7c-b945-59ca-8c0d-84d59b11f299 |  | note | – – – – – – – – – – – – – – – – –
label | 277a12ef-7fe6-589b-80eb-8effd69013d4 |  | note | CATEGORY: IP
label | a42b8a6a-7dd9-5bcb-a14c-c65c64249dfa |  | note | – – – – – – – – – – – – – – – – –
label | c6b54b69-6e26-53b6-a0bb-42271fe92d58 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 6dcac43a-3b09-589e-a394-7da571f5a09c |  | note | – – – – – – – – – – – – – – – – –
label | 4e0d7e43-f19a-57d1-bb4f-713f84fb69fe |  | note | VERIFYING DOCUMENTS: This ITP
date | 0ab4bc8c-b4d4-5809-a9ce-791215d5850d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Protection of Newly Poured Concrete
label | 30eec13f-faa1-5bbf-95a7-e7e2b9ce7caa |  | note | REFERENCE: 703.27
label | 0c73c963-36d0-5e0f-a454-cf6161a3243c |  | note | – – – – – – – – – – – – – – – – –
label | a3a2601c-8250-5096-83b2-37c0bfdb43ac |  | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | bd8c1698-1f5f-5d0d-98a4-cc72acc2472f |  | note | • Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | 388fe6e0-9755-5259-a980-d0d25ac33307 |  | note | – – – – – – – – – – – – – – – – –
label | 7fe9ffde-44cd-5fb1-82a1-bdd71f555b51 |  | note | METHOD: Visual
label | 75401d34-ea5c-5f96-872d-ac78dc20a220 |  | note | – – – – – – – – – – – – – – – – –
label | f87e895c-9bec-5931-8baf-88a6667ce067 |  | note | FREQUENCY: Where applicable, each lot
label | f4b68b52-1594-526f-9fe5-0161755cfb38 |  | note | – – – – – – – – – – – – – – – – –
label | a49a3f74-baa5-5253-9410-18bac69af7c0 |  | note | CATEGORY: IP
label | 0b4a2367-ab8e-5de4-ba5b-360c844f3b60 |  | note | – – – – – – – – – – – – – – – – –
label | 7e62c314-4a4f-5052-8c8d-a087cd55befc |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 7a973b66-5149-52ac-a631-ceafcc97b674 |  | note | – – – – – – – – – – – – – – – – –
label | 45dbfaca-372d-5757-9fea-c4135735a0ce |  | note | VERIFYING DOCUMENTS: This ITP
date | facab81c-b5b9-5779-9042-8ece8c673d88 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Stripping Formwork
label | 5b58007b-839a-573b-8c61-fb7e84ce13d0 |  | note | REFERENCE: 703.12 AS3610 Table C2
label | c21b67ae-f9d7-5022-92b6-967b279ea1b9 |  | note | – – – – – – – – – – – – – – – – –
label | 7a3267cb-c42a-5f3c-a816-933ed82ddf64 |  | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | fc5d575f-344f-5885-baff-ff9b54630dde |  | note | i. 2 days for vertical formwork on external surfaces; and
label | dfc72c9c-0019-5b08-bf02-fbef57829939 |  | note | ii. 1 day for vertical forms on permanently hidden surfaces
label | f487b3fa-166d-5673-9af8-987361cc803c |  | note | – – – – – – – – – – – – – – – – –
label | de7406d1-7d70-5e0f-a995-d5bc18900ebd |  | note | METHOD: Visual
label | 573c1feb-67d0-52f0-94e8-e81af959524b |  | note | – – – – – – – – – – – – – – – – –
label | 84137e56-bdde-5b74-9df2-60edcc42cefc |  | note | FREQUENCY: Each lot
label | 9c8a6f63-d187-5622-a1a3-6f0de56f31c3 |  | note | – – – – – – – – – – – – – – – – –
label | eb5dfad9-64de-5b61-b2f0-fc1c9145977f |  | note | CATEGORY: IP
label | c825ccfb-dcc9-5646-bfa0-2ce51babdb0c |  | note | – – – – – – – – – – – – – – – – –
label | 39fb8dbc-2060-5f12-81bf-8f114e70f850 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 048af16e-1566-5012-813a-4fbf46272637 |  | note | – – – – – – – – – – – – – – – – –
label | 78899bc3-d310-5aa2-b20d-bb1b68052547 |  | note | VERIFYING DOCUMENTS: This ITP
date | 538a9a89-d598-57a9-bd29-b4d156c20739 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Backfilling & Pavement Restoration
label | f022c7bf-af20-5318-98a5-4bcd4c57fc04 |  | note | REFERENCE: 703.29
label | d6dc4644-b203-510c-9651-4eb1e6ced30c |  | note | – – – – – – – – – – – – – – – – –
label | ffa58ac7-f5d1-5c0f-8d78-2f5929376823 |  | note | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
label | 17bb3bae-b9dd-5fdc-b168-87fcc3632451 |  | note | – – – – – – – – – – – – – – – – –
label | d8109c98-d2ee-5328-8cc2-6aeebaeddf55 |  | note | METHOD: Visual, Measure
label | 7e35b5de-efa2-527a-a011-7b46c023795f |  | note | – – – – – – – – – – – – – – – – –
label | 93deeab7-9abc-540e-af9b-eae25dfc18fe |  | note | FREQUENCY: Each lot
label | 38522e5d-3281-5ca2-a33e-429e0da8dc7f |  | note | – – – – – – – – – – – – – – – – –
label | 6a754b11-aac2-5e7b-9862-f26347c0baf7 |  | note | CATEGORY: IP
label | 833599a6-2f7d-54e3-9e48-1623e9f34a88 |  | note | – – – – – – – – – – – – – – – – –
label | 74fc8989-7835-5829-a971-cfe3e9d398bd |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | d4e4c4c0-56fa-56c6-bbcc-1442efdcf61e |  | note | – – – – – – – – – – – – – – – – –
label | c0347f91-19f8-5e82-97fb-ee59d54b7960 |  | note | VERIFYING DOCUMENTS: This ITP
date | dbfb98f0-02e3-53d2-a620-e013ff678769 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Surface Inspection - Cracks
label | 7ead2397-0adf-50af-bc19-558e3ab8a801 |  | note | REFERENCE: 703.3
label | 8d7e1631-8cc6-5a4b-a2c0-52c967ca46d8 |  | note | – – – – – – – – – – – – – – – – –
label | 0be78d8f-77ea-5c7f-b26c-7d6f9c3e1f2b |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
label | e5f43aee-d5ec-54c6-9c55-71c5393fbc69 |  | note | • If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 7d5df0b4-8ab3-5117-8421-879397814129 |  | note | – – – – – – – – – – – – – – – – –
label | 2f088fb5-38e0-5e2e-ad07-8195f841ba1a |  | note | METHOD: Visual, Measure
label | 2747096f-a7ae-5a8d-ad93-5d45713a027a |  | note | – – – – – – – – – – – – – – – – –
label | 3c037d7c-3e14-5c5c-8176-28a255f315ca |  | note | FREQUENCY: Where applicable, each lot
label | 4a37f61c-1909-572c-b006-8879fba2abfd |  | note | – – – – – – – – – – – – – – – – –
label | 5d72d5c1-4050-5fe0-87f9-50a1341b1c81 |  | note | CATEGORY: IP
label | 90f7ea5f-a2d1-51cb-b62c-41eab2703f70 |  | note | – – – – – – – – – – – – – – – – –
label | 84f60089-b222-5e70-91c8-6a3d007fbf3b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3f41cca3-13e3-5ade-bfcf-557fe129d1d1 |  | note | – – – – – – – – – – – – – – – – –
label | bae3beb4-7ae8-5a71-a6f0-64eaf8ba07aa |  | note | VERIFYING DOCUMENTS: This ITP
date | 696b55b8-689a-55cf-9e0f-54febfbde79d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Surface Inspection - Surface Finish
label | 499fbfb4-3ea4-5ad5-af52-87c4d794e6a9 |  | note | REFERENCE: IFC Drawings
label | e662fd3e-fb7c-5152-b9b6-e0abc34986d2 |  | note | Relevant Council Drawings
label | f8db1b73-bc19-5819-8811-4f9fcb9b3828 |  | note | 703.25
label | 695b57e3-6916-5d81-b938-51f441243a69 |  | note | 703.10 (a)
label | 6cc4c7fc-f831-5edf-9378-9794bcb86930 |  | note | AS3610 Clause 3.2
label | d1ff99ea-b0e9-523b-97b2-622de337439a |  | note | – – – – – – – – – – – – – – – – –
label | b2fbffbf-7060-58a6-afad-f7321a0dc19e |  | note | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
label | 6203a806-4ad7-560c-8992-67a11dc567b7 |  | note | • All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
label | eeda3e2f-7ec1-5ea3-801e-80ded35789c6 |  | note | Class of finish:
label | 1363d064-c007-5467-85fd-5e6a29f7fc64 |  | note | • Permanently hidden surfaces = Class 4
label | f5eb1c57-7bd6-5e1d-bfb5-81eb6d7c7254 |  | note | • All other surfaces = Class 3
label | adedacf5-d648-507c-806c-e84896ffa913 |  | note | • At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface
label | 29b77ed9-4632-5ba4-bed4-08738ea01de6 |  | note | • Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | d70d1d1d-af42-5e2e-986f-34085b23dffe |  | note | – – – – – – – – – – – – – – – – –
label | afd53f5d-e2c4-50da-93c0-3e97ef8828e5 |  | note | METHOD: Visual
label | 24f2b796-8f75-5071-9d23-201bb26cc6ef |  | note | – – – – – – – – – – – – – – – – –
label | d9d87fc2-c6e7-5b24-a90a-abcfaea9168e |  | note | FREQUENCY: Each lot
label | a0b74965-2716-5220-8fd6-92313ece6377 |  | note | – – – – – – – – – – – – – – – – –
label | e1c1a68d-3ec1-5b9f-bb83-3f16187e6049 |  | note | CATEGORY: IP
label | 1cbc2db2-a684-50cb-a08f-05594bb59c5f |  | note | – – – – – – – – – – – – – – – – –
label | a2a8d6c9-9dd9-5ef3-b510-5df9d24c9ed7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1ec6f1c1-5789-561e-8451-67b1eb9f0c6f |  | note | – – – – – – – – – – – – – – – – –
label | d1991529-e664-521c-b396-a8b658527ecd |  | note | VERIFYING DOCUMENTS: This ITP
date | af1156b8-a9be-551d-86bb-ae9778cba67b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Compressive Strength Test Results
label | 1979e0c8-0727-56b7-bb53-1f1187b5f5b2 |  | note | REFERENCE: IFC Drawings
label | d73a5c1c-1dd3-5119-9501-ad99bcfcb94f |  | note | Relevant Council Drawings
label | f7a6acee-5381-5d8c-8066-28b307a9c6ba |  | note | 703.11
label | 0b13d961-da4f-5c37-9538-0b5985421643 |  | note | Table 703.111
label | f9a86df8-d46f-5dc4-a8bc-6804cf69f8cd |  | note | Table 610.05.051
label | 83394bf0-9461-5fe2-a0d2-4b940806e33c |  | note | 610.16 (g)
label | 0913f9d9-c49d-5a6b-a6ab-7b954c7c790e |  | note | – – – – – – – – – – – – – – – – –
label | b85d8dbf-cf18-5e60-8630-f763ebb5f128 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 1f9df7a6-4808-5162-ad4a-535f33ad2685 |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | d0c45902-c465-50d8-8b9d-6a3b57e09385 |  | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 2dc67c0b-7f54-5caa-a437-978b7b3bb8e4 |  | note | Attach: Compressive Strength Test Results
label | ff837007-3a0a-5f08-9127-318668a2a6d1 |  | note | – – – – – – – – – – – – – – – – –
label | 81bd8b61-a389-57a4-9eb9-316f0749bf28 |  | note | METHOD: Document Review
label | 6f2e8efc-b499-5eba-adea-c5fb12ccaea0 |  | note | – – – – – – – – – – – – – – – – –
label | 15707c39-2459-5e86-a8d4-600614ab2fc1 |  | note | FREQUENCY: Each cylinder
label | 9b532fc2-7747-5e00-9d6c-66a22cf8ba52 |  | note | – – – – – – – – – – – – – – – – –
label | 96fbf21e-3eaf-5ddb-8b62-5942ffdca4bf |  | note | CATEGORY: IP
label | 5a548fc2-546d-570f-ac5d-34838c38f876 |  | note | – – – – – – – – – – – – – – – – –
label | cc96b10f-107a-56c2-bfdf-787d287ccd0b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4a7546c4-62d9-54ba-b8aa-631bdda85de2 |  | note | – – – – – – – – – – – – – – – – –
label | 9e82bbc2-0fe0-55a7-8019-6a71c9727cf2 |  | note | VERIFYING DOCUMENTS: This ITP
date | 85a55408-7c5e-5c71-b371-7dc6a28fee1b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 As-built Survey
label | 3b1785c8-6b05-5be7-ab8d-7e8739a47dec |  | note | REFERENCE: IFC Drawings 703.15
label | 072c2520-d478-5aee-af51-8501c4806181 |  | note | – – – – – – – – – – – – – – – – –
label | e01ef259-5788-5b24-879e-fe247388baaf |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 20bd3619-dd3e-5c9e-b6f0-370d0ac6de21 |  | note | • Departure from RL = ±10mm
label | 93523ff4-7ee8-5fa7-8223-84feaf58e107 |  | note | • Departure from alignment = ±10mm
label | 9e7d132d-56bc-5989-beb7-60fd18eb1505 |  | note | • Rate of change of deviation from RL or alignment = 10mm in 10m
label | 73722970-6ecf-536f-8a7e-20ae512ae358 |  | note | • Irregularities in alignment = 5mm in 3m
label | 6f2d9bef-c95c-5965-8ed5-c6fab42a4cd3 |  | note | • Section dimensions = ±5mm
label | 04c3aabc-9e3a-59d5-a915-221024efc4f7 |  | note | • Section dimensions (less than 25mm) = ±3mm
label | f11a0f53-42e5-5b15-86f3-404a70a4b74f |  | note | • Width of pavement = -5mm, +15mm
label | 02962a01-7d0d-592d-b5e4-f77fab612757 |  | note | • Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
label | 3d5f971d-a39d-5518-ba27-26ae2a304087 |  | note | Attach: Survey As-builts / Survey Report
label | d2b46dfc-2aeb-52bb-8131-016a6a09a48c |  | note | – – – – – – – – – – – – – – – – –
label | 528efafb-302c-5469-9fb5-2aa827ce21fe |  | note | METHOD: Document Review
label | 26373794-cb24-5462-afe6-4bdcadea9001 |  | note | – – – – – – – – – – – – – – – – –
label | f663d835-f7b7-537e-8002-b91f18f59698 |  | note | FREQUENCY: Each lot
label | bcaa0868-0f71-548a-b0ee-558810c1acae |  | note | – – – – – – – – – – – – – – – – –
label | 35d86f22-684f-58a8-a0a7-31617d809b96 |  | note | CATEGORY: IP
label | dbdfa7d4-05ad-54f5-b1b0-f838a00e3b75 |  | note | – – – – – – – – – – – – – – – – –
label | 9d169127-f349-5524-9b55-f375c6d2088a |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | e16ca35f-0bed-58ab-b2a6-fc9e16f2551c |  | note | – – – – – – – – – – – – – – – – –
label | e43a7615-e588-59de-a3ae-b4efcc962982 |  | note | VERIFYING DOCUMENTS: This ITP
date | fc7e7174-a872-5d75-ba69-d258f3026f82 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Non-conformance Report (NCR) Closure
label | 0a20346a-b826-5f8d-ba87-5e07547dd142 |  | note | REFERENCE: MRPA Quality Management Plan
label | 8e75ba50-1f69-5d8d-bd0f-3d568cc41644 |  | note | – – – – – – – – – – – – – – – – –
label | ff8fe093-e8be-515c-a5ae-91cb0e1ff260 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | b0989557-e6af-5d1a-b841-19a742bf065e |  | note | – – – – – – – – – – – – – – – – –
label | 372eaa1a-2aa7-5a49-bf60-d681e0beef63 |  | note | METHOD: Document Review
label | 82c2c511-aa87-5440-a672-a24bd9c29413 |  | note | – – – – – – – – – – – – – – – – –
label | a145d24f-0212-5fb3-9c8a-6cdd9cc6fd8c |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | e08d8faf-c589-5ceb-a3f1-6f3fee477a76 |  | note | – – – – – – – – – – – – – – – – –
label | adbec5ba-69be-5c1d-b52b-16be4559f46c |  | note | CATEGORY: HP*
label | c3b1e79a-1221-5df5-b8de-35c5d5508a05 |  | note | – – – – – – – – – – – – – – – – –
label | 0f22f408-48c5-54e8-bb22-69390f219322 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 23f152b6-0fc5-5ac4-a670-f4dab71d5e2e |  | note | – – – – – – – – – – – – – – – – –
label | ebdcf9da-7219-533d-bdfd-7da02b9faea8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1739ab08-21bd-5f2f-9fe1-07f6eca7e62e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 40eeb546-a214-598d-8c67-2b2ba2bcd5f5 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 0c1f8dd2-6636-54a9-9036-417480c206f1 |  | textbox | Name:
text | 3838d519-6712-5bed-9623-c063aa840e77 |  | textbox | Position:
date | 741215e0-d9ae-5b0d-bc9b-3af2ecbf0546 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | CHK-002-CIV-CAMMS-Stormwater Drainage Pit Installation Rev 1 | itp |  |  |  | Yes | CHK-002-CIV-CAMMS-Stormwater Drainage Pit Installation Rev 1 | 1cd84ae7-48dd-4ca8-b587-550af6137787
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 7df574cf-f5d9-5be9-9086-add4f035aafa |  | note | Document Title: CHK-CIV-CAMMS-Stormwater Drainage Pipes Installation
label | 64430489-1fb5-5847-83c7-f5aeb3eb074b |  | note | ITP Description: CAMMS-Stormwater Drainage Pipes Installation
label | cbaf7b1a-a4f5-5edf-9fc5-0c2a178959cd |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | a39dfbb6-9011-565b-8658-6e9aa67d1773 |  | note | Revision Number: 1
label | e7c4a04f-a3b2-588d-814d-9adc11f75ce8 |  | note | Revision Date: 7/08/2023
label | 7b15d4d7-0f10-50c5-9c28-73dd50e9e8ee |  | note | ITP created by: Victor Mira
label | 528c2901-ee1b-5207-9f9d-c856a7c56bf5 |  | note | ITP approved for use by: Aldrin Guinchoma
label | fc98df63-72a1-5b07-a503-f18661b74e28 |  | note | 1.1 Non Dependent
label | 9611d24b-2a49-5dae-839f-9892db4717e1 |  | note | Reference: VR 701
label | 2db50318-866c-5495-a161-d6d22525755c |  | note | 1.2 Main ITP
label | 0432f6b4-f44f-5d44-b624-45795dfa4497 |  | note | Reference: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
label | 66c33e35-20b9-514d-aaf3-1eb190da18af |  | note | Acceptance Criteria: This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0
text | c686938c-e90d-5a31-ae0c-8cc236e8d95d |  | textbox | Enter: Main ITP Lot Number
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Bedding
label | a51ee963-3dc9-5a80-84cb-12f0d2aef99e |  | note | REFERENCE: VR 701
label | 34b3b73f-1e79-5e96-b264-06cc7f568741 |  | note | – – – – – – – – – – – – – – – – –
label | 558f00bc-b854-5c3b-8f9a-5bc30a54e566 |  | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
label | 6e5c52c9-2698-5d18-8c7f-df2671bc9738 |  | note | – – – – – – – – – – – – – – – – –
label | 2ad9bcdf-180d-583b-9136-635906f5f440 |  | note | METHOD: Document Review
label | 1f6a5243-3aee-5bae-aaba-e8cae29335e9 |  | note | – – – – – – – – – – – – – – – – –
label | d9a90433-6969-53e1-b3f4-3de439d16783 |  | note | FREQUENCY: Each Lot
label | b5612d37-ef8b-5db0-be9d-6d546427cee3 |  | note | – – – – – – – – – – – – – – – – –
label | b2273257-0b04-5697-a0af-b40760aae948 |  | note | CATEGORY: HP*
label | 9a012584-f898-52c1-88f2-daef0ee68892 |  | note | – – – – – – – – – – – – – – – – –
label | 6513c97c-d50e-54a2-9462-a80875c6485c |  | note | RESPONSIBILITY: SE
label | 36259753-4fd5-5e0a-9c4b-b83858d1554d |  | note | – – – – – – – – – – – – – – – – –
label | 824db693-a2ac-5bf4-ba75-020050ec79e6 |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
date | f9f87500-99ad-511b-bedc-16dd234ee427 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Backfill Material
label | 6cf92675-c519-57a5-bdf8-cd5261dd11d3 |  | note | REFERENCE: VR 701
label | d382f010-3a47-54fe-bc16-c514c807e34d |  | note | – – – – – – – – – – – – – – – – –
label | b244612e-f262-5a4b-886e-affbecf56b63 |  | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
label | 70499952-03df-5927-b9e1-12272ec25b94 |  | note | – – – – – – – – – – – – – – – – –
label | 5771e6c7-9598-5ace-ad7f-ada15099c20e |  | note | METHOD: Document Review
label | fc17d08c-7e34-51aa-97b8-0ce2653a4c03 |  | note | – – – – – – – – – – – – – – – – –
label | 0279a336-ac3b-53c1-8404-6c1c88518074 |  | note | FREQUENCY: Each Lot
label | bdeaf4bc-53eb-53f9-9d0b-4ec12d0521d8 |  | note | – – – – – – – – – – – – – – – – –
label | 415583e4-3339-5ac9-8bae-961eec62c48f |  | note | CATEGORY: HP*
label | 747c4f59-7bcb-5868-9e16-0343e060e5a7 |  | note | – – – – – – – – – – – – – – – – –
label | c09b2723-788e-55f9-82bb-036f53c45191 |  | note | RESPONSIBILITY: SE
label | 2f3039f0-f976-525a-ad40-cbe4538c65c5 |  | note | – – – – – – – – – – – – – – – – –
label | c96ae0c1-eb8c-5f44-b89e-7a456b57552b |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
date | de37c1da-7fe4-5c70-abb5-6f010858d483 |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Subcontractor QA Submissions and ITP
label | d6ff992b-f8b4-521c-b8a9-6907b6d65a76 |  | note | REFERENCE: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
label | 0af65cdc-33fa-5439-bb7f-af062d988e52 |  | note | – – – – – – – – – – – – – – – – –
label | 5dcd3d41-e6d1-539e-9660-e78a51e6b8ef |  | note | ACCEPTANCE CRITERIA: Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
label | 5cd83f85-6c76-5cd3-9f86-e9fde2cb0740 |  | note | ATTACH: Subcontractor Signed ITP
label | b0be07e3-8ab7-5601-bbea-851af57a6791 |  | note | – – – – – – – – – – – – – – – – –
label | 7a5ef945-f9b4-585e-9b51-2d69b3d1b055 |  | note | METHOD: Document Review
label | 306a8f5c-ead9-55a4-9d3a-20c3ba4f9f09 |  | note | – – – – – – – – – – – – – – – – –
label | 24616d3c-df66-58f3-8e5c-dc6080772a18 |  | note | FREQUENCY: Each Lot (in case undertaken by subcontractor)
label | 257f74b8-79c8-5820-b99d-b3f55544e6a1 |  | note | – – – – – – – – – – – – – – – – –
label | ed1bf283-9198-5eab-ad20-7b9075094c42 |  | note | CATEGORY: HP*
label | d566b669-d508-5591-b00b-88ec98cd7bdf |  | note | – – – – – – – – – – – – – – – – –
label | 7982339e-6f8c-54f7-ae3e-055160d059e3 |  | note | RESPONSIBILITY: SE
label | 22f9d0a1-80c5-56f1-a090-96eed053163a |  | note | – – – – – – – – – – – – – – – – –
label | f4619519-28ab-5357-8ec2-bba37762a0ce |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 0453ab66-f447-5572-98db-593e1adb10ce |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set Out
label | 73a8be24-e304-56a1-a1ec-0cc96e65eb30 |  | note | REFERENCE: VR 701.10
label | f5b76864-4d3f-5257-b4a2-edd09e2b3613 |  | note | – – – – – – – – – – – – – – – – –
label | 25589803-ad68-5b64-a013-49483e0420ee |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
label | 27ed5c38-9238-50f3-8056-c91700aa8094 |  | note | – – – – – – – – – – – – – – – – –
label | e9183397-dbd7-5cf2-b5de-d5bf152d8285 |  | note | METHOD: Visual inspection
label | 9dadb0dd-95a1-5a46-9d95-15e2588fc75d |  | note | – – – – – – – – – – – – – – – – –
label | 65c51c20-9874-52b7-80d2-f2ac984b8fce |  | note | FREQUENCY: Each Lot
label | cbb4e4a6-e69e-5244-a6a6-4fdb96988159 |  | note | – – – – – – – – – – – – – – – – –
label | 30db872f-ec5f-595b-b9e5-47f485f26544 |  | note | CATEGORY: HP*
label | 317f77fc-9c98-5c56-9ff6-1348f0bc4db1 |  | note | – – – – – – – – – – – – – – – – –
label | 3aff0fa1-25dd-56de-addf-27dc5eb3b32b |  | note | RESPONSIBILITY: SE
label | f84c2288-90a9-5cf3-b6fe-b992210a2bdb |  | note | – – – – – – – – – – – – – – – – –
label | b37dddfa-be5a-5071-a151-d0a030d7e21b |  | note | VERIFYING DOCUMENTS: This ITP
date | db95a59d-2826-5578-9e33-3b627b17e552 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Pit Excavation
label | 8e3c76fe-66d2-569f-9fef-8e71b08f8c35 |  | note | REFERENCE: VR 705.05
label | bf49f073-19d2-5f3a-a6ad-87f747dca7a5 |  | note | – – – – – – – – – – – – – – – – –
label | d45ab735-209a-5409-ab67-08aacd2280e6 |  | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
label | 54f4d963-371f-5a67-81fb-095edfcbe1b3 |  | note | – – – – – – – – – – – – – – – – –
label | 4346b75c-43ba-54f0-beec-ebcaaa89b93e |  | note | METHOD: Visual inspection
label | a24a592a-beca-58ba-99c2-2b219fd390d5 |  | note | – – – – – – – – – – – – – – – – –
label | 6376ec87-21ac-5c20-b340-92b64c172529 |  | note | FREQUENCY: Each Lot
label | d9cbfaf2-1f10-5966-bd0b-59fa4749e402 |  | note | – – – – – – – – – – – – – – – – –
label | 4bb9de10-9a94-5a7a-a1b2-8c0be1a498c5 |  | note | CATEGORY: IP
label | 6213537b-c203-5d57-8a64-d153d0db5af5 |  | note | – – – – – – – – – – – – – – – – –
label | 90fc654f-d172-5f1b-b0aa-acbd61a8cc5c |  | note | RESPONSIBILITY: SE
label | 9cc6b751-0652-5ac0-8421-5159c89b1841 |  | note | – – – – – – – – – – – – – – – – –
label | 8cc21f61-6246-5df8-9d46-798c7cac16a8 |  | note | VERIFYING DOCUMENTS: This ITP
date | d5809ed8-bf11-59d5-982e-8096075067f9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Excavation Foundation
label | d00c549e-5739-57fc-ba0b-53268e77009c |  | note | REFERENCE: VR 705.05
label | c6810ea7-23c9-547a-aa51-785eac67ba89 |  | note | – – – – – – – – – – – – – – – – –
label | 70cfebd1-c787-5a0a-8e31-5e1a258e9fdc |  | note | ACCEPTANCE CRITERIA: Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
label | 8ec698b6-9e30-559f-aa4a-9b641e0b7b24 |  | note | > 80mm for clay foundations
label | 85c28796-c1f8-5d60-855d-30cabb0793d8 |  | note | > 150mm for rock foundations
label | 4dcab8d4-6da6-5f8c-92a9-e6081708a256 |  | note | – – – – – – – – – – – – – – – – –
label | 31141a1d-e9fe-515c-97b0-e16fbfdd5738 |  | note | METHOD: Visual inspection
label | a23faee8-44be-5a01-9b71-d5fd0d697252 |  | note | – – – – – – – – – – – – – – – – –
label | 24529031-94ff-586c-a77f-de8a32ccbcc3 |  | note | FREQUENCY: Each Lot
label | c0470cb6-65a1-5e64-9827-a8bfc19e8e8c |  | note | – – – – – – – – – – – – – – – – –
label | d6b4a690-c31f-5487-99fe-4b4b5307dff4 |  | note | CATEGORY: IP
label | d0339678-4269-5753-90aa-4e8c24a6b641 |  | note | – – – – – – – – – – – – – – – – –
label | 5ffbfa42-3d98-5e02-b5f8-34993b6b3cd5 |  | note | RESPONSIBILITY: SE
label | f159cf8d-7e56-56b2-b745-6bf9cf5a354a |  | note | – – – – – – – – – – – – – – – – –
label | b965c078-f7dd-57d4-bc53-e07cd6407cd8 |  | note | VERIFYING DOCUMENTS: This ITP
date | ccc994f7-4e6e-5eaf-9851-bc2968a9d199 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Placement of Pit-Conformity with drawings
label | 1197db57-e12d-5e19-a7fd-444413f33ab5 |  | note | REFERENCE: VR 701.10
label | b47a9489-2e11-56e4-a8db-4b5bfab522a3 |  | note | – – – – – – – – – – – – – – – – –
label | 90d5b3ae-4052-56d0-bf77-e3eb3785530b |  | note | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
label | 60b3d2ac-545b-5104-a0a8-a3f6bf2d876c |  | note | Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | eec40ff5-2023-5fb6-8e3e-2aa60929756d |  | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | fb062500-5f73-5b7f-98a5-60e43f2aa087 |  | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | 7af37a0e-1f5e-57ed-b5dc-63b75e47310e |  | note | (c) invert level of pipes at pits ±50 mm
label | 675724d7-aa12-58eb-9ae0-5ea4fd96f9ac |  | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | e68c2296-901d-57fc-95c5-719a2498c4b5 |  | note | ATTACH: Survey Report
label | 9e94baf2-28a4-5811-b8c3-2ac9fc82c8de |  | note | – – – – – – – – – – – – – – – – –
label | 02e69115-43fc-5167-b4bc-efb1d3c322bc |  | note | METHOD: Measure
label | b744d03c-046a-56a6-97cf-5e7c8c8207a5 |  | note | – – – – – – – – – – – – – – – – –
label | 5201e616-f5ea-5c62-aede-f9930b923a08 |  | note | FREQUENCY: Each Lot
label | 1d40a946-c135-50fd-a61a-9080dab81a75 |  | note | – – – – – – – – – – – – – – – – –
label | 4f10842e-9cc2-57be-a3f7-1e3f48d10953 |  | note | CATEGORY: HP*
label | e1dcf850-3055-53fb-afd8-c9b2c656fd98 |  | note | – – – – – – – – – – – – – – – – –
label | b17740d5-f311-5496-b30d-132fb6207c32 |  | note | RESPONSIBILITY: SE
label | 6930c120-4235-58ef-bb92-edd22c82d228 |  | note | – – – – – – – – – – – – – – – – –
label | dc46b88a-6035-5ff3-9b64-c88fc7b24de9 |  | note | VERIFYING DOCUMENTS: Survey Report
date | 53af2b8b-3462-566f-887b-d3e905e572b1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Jointing
label | c1aeb1d8-4b03-5282-9640-3912db8b24c9 |  | note | REFERENCE: VR 705.11
label | 6aeb4d15-f457-5111-b5cf-098e9907160b |  | note | – – – – – – – – – – – – – – – – –
label | b214aec2-3f46-5e1c-bca0-e63d89d38f70 |  | note | ACCEPTANCE CRITERIA: All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
label | 191e4a7d-f077-5156-9944-3f57475ad9db |  | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
label | a7bc5dcf-34f0-5d12-8041-51229c1d064e |  | note | – – – – – – – – – – – – – – – – –
label | b4912e8d-362b-5d80-9eff-14a11173c2a4 |  | note | METHOD: Visual inspection
label | 6adc9f93-5c59-516a-bc96-fdfe7ab5dc08 |  | note | – – – – – – – – – – – – – – – – –
label | f4890521-0dea-56a2-8d2e-7dddd4455608 |  | note | FREQUENCY: Each Lot
label | 7dd600ab-fa3a-5432-8c7a-65e3b938adc6 |  | note | – – – – – – – – – – – – – – – – –
label | 347b66ac-6f6a-572d-9c06-76e2b28cc99e |  | note | CATEGORY: IP
label | 31e73d5a-b7e6-543a-8202-9a1e5e836fb2 |  | note | – – – – – – – – – – – – – – – – –
label | 2125187f-bfa8-553e-a09c-ac4c14cac571 |  | note | RESPONSIBILITY: SE
label | a1e72024-6da4-5eb3-96e5-44630836e99c |  | note | – – – – – – – – – – – – – – – – –
label | b0b7488a-f4dd-5830-832e-eac37d83d6bb |  | note | VERIFYING DOCUMENTS: This ITP
date | 1ada8404-2e49-51fd-aae6-c2fb4e3c3d37 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Shaping of Floor
label | 83c68943-a770-50f1-8bbe-50f7a558f2f8 |  | note | REFERENCE: VR 705.13
label | 121b67d9-b16e-552c-a812-2ff320b9703b |  | note | – – – – – – – – – – – – – – – – –
label | ab27325d-a328-5c42-aa14-91e87c252d11 |  | note | ACCEPTANCE CRITERIA: Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
label | 2d28cc72-f797-5cd8-b1a5-b6c202688c1a |  | note | – – – – – – – – – – – – – – – – –
label | ead84078-e393-5aa7-8814-7eb8006ad09f |  | note | METHOD: Visual inspection
label | a1985ac3-bfcb-5ad4-a098-0f73ab1bd819 |  | note | – – – – – – – – – – – – – – – – –
label | 3139d89b-4284-57c0-af4f-b967f7bcb8db |  | note | FREQUENCY: Each Lot
label | 94a251ba-f974-57e5-9314-cac1e3c413ec |  | note | – – – – – – – – – – – – – – – – –
label | 65e41cac-0a6f-5470-bfc7-e9d0f3c594dd |  | note | CATEGORY: IP
label | de7c61d8-a06d-5c8e-ad90-ba6d24dc358c |  | note | – – – – – – – – – – – – – – – – –
label | 6f4c2ce2-46ed-5f55-ab33-52a34346d654 |  | note | RESPONSIBILITY: SE
label | 14edf8a5-7ef8-50af-bd84-a327786e7602 |  | note | – – – – – – – – – – – – – – – – –
label | c744f5ed-f5df-5173-94a1-f4a02867b7b0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6edbad1b-c249-5db6-81b8-0baea5a1a68a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Step Irons
label | c61fe9d0-67f1-5374-bbe3-01256c113b16 |  | note | REFERENCE: VR 705.12
label | a86ae905-9833-5d78-b791-936614f9644b |  | note | – – – – – – – – – – – – – – – – –
label | 7076dde8-11d7-52ec-a751-948aaff616ca |  | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
label | ae581563-3a85-581e-92fc-db77825ef46a |  | note | – – – – – – – – – – – – – – – – –
label | 754ca9ec-43d2-5d4b-b63d-363005b622cc |  | note | METHOD: Visual inspection
label | 8bab9961-cfcf-5d76-a76b-480966e6639c |  | note | – – – – – – – – – – – – – – – – –
label | be474652-ae50-56d9-bdbe-f302138c15a9 |  | note | FREQUENCY: Each Lot
label | 4d3daa42-21e9-5036-bc98-fca930cc182a |  | note | – – – – – – – – – – – – – – – – –
label | 1c1536a0-6002-52d7-b55d-b7f6bbd1fd34 |  | note | CATEGORY: IP
label | dd5464d8-0ee7-58c1-971a-7a9909ff6190 |  | note | – – – – – – – – – – – – – – – – –
label | c0226dc6-84c9-544f-b166-fdfcd92c0797 |  | note | RESPONSIBILITY: SE
label | c0e820b6-7d18-51e6-a6ed-aeefd25f98d1 |  | note | – – – – – – – – – – – – – – – – –
label | 014146ba-f8cc-5025-86be-23e48f1af23d |  | note | VERIFYING DOCUMENTS: This ITP
date | 371f9f5e-77f3-5abc-94ad-659047c0ab2c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Fitting of Covers
label | ed15ad3e-3f68-50d0-a1f0-6ec1f6ef1808 |  | note | REFERENCE: VR 705.17
label | 3b36ea0d-7b96-58a0-b981-0ef1456bffba |  | note | – – – – – – – – – – – – – – – – –
label | 6dc455fa-e465-5bf2-8316-ca4e431c6cf7 |  | note | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
label | db238a2f-f7d5-590f-9023-df1fc2106f73 |  | note | ○ Height shall be within 10mm of the design level
label | 867db234-8d12-5f11-aae8-07c183ff8e82 |  | note | – – – – – – – – – – – – – – – – –
label | ba2082fb-9940-51db-83f5-8bcd77679b5e |  | note | METHOD: Visual inspection
label | b65dc473-e48c-5a9a-8b48-ce1c319190b3 |  | note | – – – – – – – – – – – – – – – – –
label | 50fbe3fa-a0f7-53f7-b161-f95283274a33 |  | note | FREQUENCY: Each Lot
label | 5b5ffd0a-4242-5057-951b-35936828104f |  | note | – – – – – – – – – – – – – – – – –
label | 43437974-eb1f-5146-ad63-4cb505fc668a |  | note | CATEGORY: IP
label | 2a360a8b-dabf-5e4d-996b-7b173c3e0f85 |  | note | – – – – – – – – – – – – – – – – –
label | 3402fd93-9d83-596a-bb0c-ccfd86d7d352 |  | note | RESPONSIBILITY: SE
label | 63a46bc4-5604-5055-9e87-8024842abcf9 |  | note | – – – – – – – – – – – – – – – – –
label | 7c08583b-a59c-5de0-a759-aa7995090e34 |  | note | VERIFYING DOCUMENTS: This ITP
date | 25551026-69ff-5cf4-8431-f141e4e46fa3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Backfilling Around Drainage Pits
label | 2a2c81e1-b06d-552b-923a-b357218cbd96 |  | note | REFERENCE: VR 705.18
label | 0211df3e-5e38-59be-8c3d-2007fe8ab761 |  | note | – – – – – – – – – – – – – – – – –
label | 2d6a4481-dd16-5f3c-bc83-2f1cf52d4000 |  | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
label | 6228ed74-c55b-5752-8329-28e3bffc8916 |  | note | – – – – – – – – – – – – – – – – –
label | 5bcea257-78f3-5644-8b0f-89ea202b666f |  | note | METHOD: Visual inspection
label | 2a7e3ca3-b0fc-5657-bb6d-5c2c42caf3ee |  | note | – – – – – – – – – – – – – – – – –
label | bfc1c3ec-b36a-5c23-b953-7c76b76d4ffa |  | note | FREQUENCY: Each Lot
label | 1a7d99c8-4407-50b0-9a73-b46242efd5e7 |  | note | – – – – – – – – – – – – – – – – –
label | 789b3d55-fe90-5433-a885-4d49dd55e2db |  | note | CATEGORY: IP
label | abd78ff8-e541-5890-83cc-4b2ae9c5a53c |  | note | – – – – – – – – – – – – – – – – –
label | 7729992b-acfe-50c9-b04f-e055b95c0bee |  | note | RESPONSIBILITY: SE
label | 8c58fa92-838e-5437-9aa3-be5c8347ccd5 |  | note | – – – – – – – – – – – – – – – – –
label | f1eee706-c8d5-501f-b134-8b3341bcf0f9 |  | note | VERIFYING DOCUMENTS: This ITP
date | aa0cc01b-85ff-5d88-85a6-cc371b7c6e37 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Compaction and Moisture content tests
label | 0249829a-3845-555c-92d4-d8d10572bd2d |  | note | REFERENCE: VR 701.20
label | 38befb03-24f3-5202-bff4-d3355c3efccf |  | note | – – – – – – – – – – – – – – – – –
label | 3aa2813a-d52f-5da5-87c9-ea5b05e67663 |  | note | ACCEPTANCE CRITERIA: Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
label | c2295d14-4dc2-5ff0-9d72-40eb4550dd47 |  | note | ATTACH: Compaction and Moisture content test results:
label | cf0b6e9b-2b02-52ec-938d-996ff33bb333 |  | note | – – – – – – – – – – – – – – – – –
label | 718196ee-30c5-5cb3-b275-e8eb0942252b |  | note | METHOD: Document Review
label | 51e0dc48-3ec2-5ef7-9933-14541246a624 |  | note | – – – – – – – – – – – – – – – – –
label | afaa8fd3-b7e4-5c0c-a835-bf6371f8035e |  | note | FREQUENCY: Each Lot
label | 2bc2ef11-8de0-590a-8258-ae437ee95fb9 |  | note | – – – – – – – – – – – – – – – – –
label | 44aac192-4f60-5d2e-82fb-884be39445ae |  | note | CATEGORY: IP
label | d6ae4eb6-2a03-53c5-9b0c-3f0a70cdbd29 |  | note | – – – – – – – – – – – – – – – – –
label | 6509d2f1-05ff-587e-a4b2-be748aef3d92 |  | note | RESPONSIBILITY: SE/PE
label | 204a42da-a6d9-5d88-95e9-6627c13ed239 |  | note | – – – – – – – – – – – – – – – – –
label | d0f840f4-6d21-562b-a59b-30eea623f72d |  | note | VERIFYING DOCUMENTS: Test Results
date | af9ff277-14d4-525d-8b20-9dab81f4fcbe |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 CCTV Inspection
label | f52aaa2e-e099-59d8-b9c8-443d4000c0c3 |  | note | REFERENCE: VR 701.30
label | 4becab17-fa1d-5f35-94e7-eabce37541b2 |  | note | – – – – – – – – – – – – – – – – –
label | 9ee6f303-63c2-5b72-9e31-02868a5a1b1c |  | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | 8ad489b3-a3ee-52d3-9626-ccfdff579a53 |  | note | ATTACH: CCTV Report (PDF):
label | dd4b8e20-d1dd-59a2-b75e-e85fb1dd156a |  | note | – – – – – – – – – – – – – – – – –
label | bc5bd3e2-40cd-50cc-90fd-51c1ce1da06b |  | note | METHOD: Document Review
label | fcbe654d-84cf-51ed-a8fd-f318bbd6cc5c |  | note | – – – – – – – – – – – – – – – – –
label | 00a5e66b-01ce-56a5-9cd7-abd64adf1ca7 |  | note | FREQUENCY: Each Lot
label | 5db14538-e50a-5631-98f5-518370b9f5cf |  | note | – – – – – – – – – – – – – – – – –
label | 3d8d1de8-5c04-519a-b02e-659e47e1499d |  | note | CATEGORY: HP
label | e6cd3f7d-487c-5966-9c37-555a94d61353 |  | note | – – – – – – – – – – – – – – – – –
label | d3d9d94c-f673-544f-a261-3b798460fd92 |  | note | RESPONSIBILITY: Nominated Authority
label | 2a2f41ca-2ed0-5bbb-8d4f-9b715f183563 |  | note | – – – – – – – – – – – – – – – – –
label | 16d55ea8-5240-5042-a75e-db43bc17896d |  | note | VERIFYING DOCUMENTS: CCTV Reports
date | 9c8838ae-3792-5be0-86a4-60b098a8adde |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | fdad069f-7ec1-52c8-ae44-94ae15930a04 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 1d878e06-1ad1-5d8f-90d2-9c6b4d835de6 |  | textbox | Name:
text | 517711e7-2302-54e4-9be7-f460e9d5ff7c |  | textbox | Position:
date | 2fdbcd54-6ffa-5cc3-9a38-408da8145a46 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-094-CIV-CAMMS-Landscape-Gabion Installation Rev 0 | itp |  |  |  | Yes | ITP-094-CIV-CAMMS-Landscape-Gabion Installation Rev 0 | 1d065ee2-ab1f-49f1-ba5e-bfb8f96b76c3
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | dc8f7f82-1155-5cfb-bfa9-9fa7c3514f6d |  | note | Document Title: ITP-094-CIV-CAMMS-Landscape-Gabion Installation
label | 5da8352d-2457-516c-b84c-f4e8ecae9989 |  | note | ITP Description: CAMMS-Landscape-Gabion Installation
label | ff8af672-2a82-5333-a5e4-ea4eb945b291 |  | note | Discipline (e.g. CIV/STR/RAIL: 094-CIV
label | 5788765b-aaef-57d4-8ab5-8fb6a8a8aba4 |  | note | Revision Number: 0
label | 3a46ffb5-3e37-5a22-906a-37aef05417c9 |  | note | Revision Date: 22/10/23
label | 68d5c53a-7cf0-5370-8fc5-499cdb15f435 |  | note | ITP created by: VM
label | 36fca933-bf0d-5c8c-89a6-b09e70df02c6 |  | note | ITP approved for use by: VM
label | 5b2dcfc5-6901-566d-a47c-ed496b12a4ff |  | note | 1.1 Vicroads Section 715 2013
label | 6694cc88-6538-5b05-a89a-d4883571e9e7 |  | note | 1.2 Vicroads Section 801 2018
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Gabion Baskets, fasteners and braces
label | dae8219f-d4bd-56cb-a388-d7085cf7c9ce |  | note | REFERENCE - IFC Drawings: MRP-052-D-SMEC-DRG-71-MPK-AUD-5001
label | 45b5ac7a-0a48-5b81-afb4-d47102142088 |  | note | – – – – – – – – – – – – – – – – –
label | 0ab65484-5852-584a-87a9-fa444990d5e4 |  | note | ACCEPTANCE CRITERIA - Gabion baskets are to be Maccaferri 8x10 double twisted steel woven wire mesh with an internal wire diameter of 2.7mm. The mesh shall be GALMAC (95% zinc and 5% aluminium) and PVC coated.
text | 91e8a95d-683f-5e63-9b46-54ede051c157 |  | textbox | Enter: Teambinder Material Approval number
label | 8ae4409e-6145-5918-a17b-f9e27c723e73 |  | note | – – – – – – – – – – – – – – – – –
label | e18eae37-7707-50dc-ab1c-d235379a2b88 |  | note | METHOD - Document review
label | ba693890-cb26-531d-8113-56a18fb637b1 |  | note | – – – – – – – – – – – – – – – – –
label | 9d8965f3-ab6b-5c27-9229-5283bdc16074 |  | note | FREQUENCY - Prior commencement of work
label | 7a3d8876-b8d8-5913-9d06-044bdd3e4739 |  | note | – – – – – – – – – – – – – – – – –
label | 1d4f982e-1879-59c8-8102-6da2f6aa07b3 |  | note | CATEGORY - HP
label | af2b7f93-0b3f-5866-840e-99e6c1323607 |  | note | – – – – – – – – – – – – – – – – –
label | 62239a14-2496-5980-9b35-4a780dac3e84 |  | note | RESPONSIBILITY - Nominated Authority
label | 6e4ee5d6-e2c5-58c4-8f23-38e8e6ba76bb |  | note | – – – – – – – – – – – – – – – – –
label | c44f338e-38db-58c0-9764-8bfacbcbbf21 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release TeamBinder Material approval
date | 0a749ab6-fef9-5ce0-9f33-858a2baa577e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Fill Materials
label | ea354c8a-91a1-5db1-86f4-8c463aa04483 |  | note | REFERENCE - IFC Drawings: MRP-052-D-SMEC-DRG-71-MPK-AUD-5001 VR 801.03 VR 715.05 (a) and (b)
label | 3c43d4e8-2f7b-55f1-8a92-2c86f42c18b6 |  | note | – – – – – – – – – – – – – – – – –
label | 11d27b9e-a377-5796-89da-0db41a49052b |  | note | ACCEPTANCE CRITERIA - Prior to the commencement of work, the Contractor shall nominate the proposed source of rock and supply the specified test results for approval by the Superintendent. All rock used for gabion fill material and rock mattress fill material shall comply with the material requirements for ‘sound’ rock as specified in Section 801 and the Los Angeles Value (LAV) requirements of Table 801.033.
label | 58fdaba6-28b3-578d-86e0-388ee85b13a2 |  | note | The rock shall have a minimum apparent particle density of 2.5 t/m3 In addition, the rock shall have a minimum wet strength of 100 kN and a wet/dry strength variation not exceeding 35%
label | 47df15c7-63d9-5939-8f77-73910dadea87 |  | note | Rock Dimension: Min: 100mm Max:250mm
text | f105f97d-1bd7-5367-9432-a2e080d7b59e |  | textbox | Enter: Teambinder Material Approval number
label | 41c1e5d7-22f2-5006-bf4f-f49dd5ef0fcd |  | note | – – – – – – – – – – – – – – – – –
label | cec8bbab-aa2b-5943-9d4c-5edf87df26ef |  | note | METHOD - Document review
label | 67d5258a-9813-5482-ba09-bd90397a6bdf |  | note | – – – – – – – – – – – – – – – – –
label | 80a0bd85-1eac-5ee1-a0f5-3208f639e095 |  | note | FREQUENCY - Prior commencement of work
label | 215db4ba-53d6-56bc-981f-cdfa44cee051 |  | note | – – – – – – – – – – – – – – – – –
label | 14bed077-a419-57b6-8ea0-0f9ee413df78 |  | note | CATEGORY - HP
label | 54ff64ff-96b6-5c61-8cd6-0c61e70f0efa |  | note | – – – – – – – – – – – – – – – – –
label | 96cf0bfa-ef2a-5beb-a94d-39368f200f81 |  | note | RESPONSIBILITY - Nominated Authority
label | 97382930-9ada-5c90-90ab-d7dfddfb69b5 |  | note | – – – – – – – – – – – – – – – – –
label | 4cbea1c2-91a0-5e4f-87d4-b0d2ac7b3926 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release TeamBinder Material approval
date | 338867d2-2907-5538-86ef-75981dc7f885 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Geotextile
label | 5077d9f5-fcb8-5327-aa59-4ef0a7c5f52b |  | note | REFERENCE - IFC Drawings: MRP-052-D-SMEC-DRG-71-MPK-AUD-500
label | d6f34e86-41e3-5288-8ffb-afc11b8d07ab |  | note | – – – – – – – – – – – – – – – – –
label | 4851f91e-e426-595f-ba37-0397b21a6432 |  | note | ACCEPTANCE CRITERIA - BIDIM A34 or approved equivalent Geotextile
text | ab268f67-f3b3-51e1-b584-c06c9d4d3484 |  | textbox | Enter: Teambinder Material Approval number
label | 2683f2b2-a76a-56a4-ba96-6cf49c3cefb7 |  | note | – – – – – – – – – – – – – – – – –
label | c66e1457-d1c6-579a-a42d-f3548d6c151d |  | note | METHOD - Document review
label | 26789f02-56ab-5a10-be4a-96619462b867 |  | note | – – – – – – – – – – – – – – – – –
label | 134f6fb4-02dd-574f-adbe-4dfb489d0eb1 |  | note | FREQUENCY - Prior commencement of work
label | 88a24e26-2ff6-5a91-9c2d-e297d3301745 |  | note | – – – – – – – – – – – – – – – – –
label | 091925c7-a7fb-54e0-a557-5400720ba9c3 |  | note | CATEGORY - HP
label | 85cae1ed-1abd-532a-bd4d-14eb73a64e8d |  | note | – – – – – – – – – – – – – – – – –
label | 295a5198-f3e2-5b8d-b466-8ef457ccdef2 |  | note | RESPONSIBILITY - Nominated Authority
label | 51877171-a372-5743-a455-2d6a315a2494 |  | note | – – – – – – – – – – – – – – – – –
label | 4c4bbdde-4064-5b85-885c-97f7988bcca6 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release TeamBinder Material approval
date | cc8b66cf-8420-5036-87ed-c7ce8fc647d9 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Granular Material
label | 02a0d020-44e4-5593-b077-183572f57497 |  | note | REFERENCE - IFC Drawings: MRP-052-D-SMEC-DRG-71-MPK-AUD-5001 VR 715.08 (e )
label | 62eaee7b-9ab3-57e5-b50e-500ec1b55dc4 |  | note | – – – – – – – – – – – – – – – – –
label | 99b0390d-3869-5ff0-9f87-9132fa78178f |  | note | ACCEPTANCE CRITERIA - Permeable fill material, consisting of Grade A4, A5, A6, B1, B2, B3 or B4 granular filter material which shall comply with the requirements of Section 702.
text | 964381f9-03ff-5a90-8151-26399def3577 |  | textbox | Enter: Teambinder Material Approval number
label | c02c264f-62e4-5c72-aaf2-1b7b82e50c00 |  | note | – – – – – – – – – – – – – – – – –
label | 8241cd66-8cf1-540d-9a3f-4c2e71e91263 |  | note | METHOD - Document review
label | 90953cc6-23fe-53ef-93d0-f64da8c8985d |  | note | – – – – – – – – – – – – – – – – –
label | 8c7e453f-65fd-5da4-b2df-8fedd43c9aaf |  | note | FREQUENCY - Prior commencement of work
label | 2e1b83d9-02d0-5e7c-a0a5-77143b42d5c3 |  | note | – – – – – – – – – – – – – – – – –
label | b2e8f93a-fef5-5c80-a72a-3deb0766388b |  | note | CATEGORY - HP
label | 5db6ab25-12f1-598b-bc3a-6d7c9573e6e6 |  | note | – – – – – – – – – – – – – – – – –
label | 96108946-0464-5377-831d-9b0b90f6b638 |  | note | RESPONSIBILITY - Nominated Authority
label | ac70e190-ddce-5d5e-acbb-502249f1fcfa |  | note | – – – – – – – – – – – – – – – – –
label | 4ebdcbed-b079-55da-9bf7-59b25f2c1be4 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release TeamBinder Material approval
date | 9b1ea8b4-9246-532c-aa46-9e22b48b642b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Documents
checkpoint-status |  |  | checkpoint | 3.1 - Prefilled Gabions
label | 98eaa892-a39f-5bba-8635-fd9834473954 |  | note | REFERENCE - VR 715.06 (e )
label | b62dd403-d0ce-56ac-aac4-5a978d0ab2f9 |  | note | – – – – – – – – – – – – – – – – –
label | f5a927c3-5894-5bbe-bbf9-359f16140417 |  | note | ACCEPTANCE CRITERIA - The use of prefilled gabions is not permitted without the prior written approval of the Superintendent. The Contractor shall submit a procedure for filling, lifting and transporting prefilled gabions for approval by the Superintendent. The procedure shall demonstrate that the prefilled gabions will not vary by more than 75 mm from a 3 metre straight edge laid across the surface after installation.
label | 79eecdaf-1cfb-58c5-8546-b2d0203f1c06 |  | note | Prefilled gabions shall be installed in the positions shown on the drawings and each prefilled gabion shall be connected to all adjacent prefilled gabions by connecting accessible abutting edges only with fasteners at maximum 150 mm intervals. The exposed sides of the prefilled gabions after installation shall not vary by more than 75 mm from a 3 metre straight edge laid across the surface after installation. Where bulges and depressions greater than 75 mm are present after installation, the prefilled gabions shall be replaced.
label | a70faaf3-a85e-5e7a-9b31-705fa2df53fe |  | note | – – – – – – – – – – – – – – – – –
label | 20cd774a-23cb-5623-be5a-9fa1298a4d6f |  | note | METHOD - Document Review
label | 587a878a-a597-50ab-94ba-a4d17e0aeba9 |  | note | – – – – – – – – – – – – – – – – –
label | 0ae201ef-6592-563e-943f-dfa10c0ba53b |  | note | FREQUENCY - Prior commencement of work
label | 8b6c6b57-c8c1-5b4c-aeb8-179d5805834a |  | note | – – – – – – – – – – – – – – – – –
label | 3c1e22e2-9a0b-570c-b437-f46aa75b1c17 |  | note | CATEGORY - HP
label | 15652c31-f4a2-5b37-b1ef-c40ea2172e28 |  | note | – – – – – – – – – – – – – – – – –
label | 53d4e1b7-56e2-52ad-b959-87aeb16f3762 |  | note | RESPONSIBILITY - Nominated Authority
label | 56ca5e45-989e-5d57-9822-147e01e3c9f8 |  | note | – – – – – – – – – – – – – – – – –
label | a32eaf0a-fea7-55fb-95c7-9b52907c23ba |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | c3a9ff46-b92c-5115-8cf1-774d0163b78e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out of Precast Elements
label | 473323a3-1eff-5cf0-92ce-fffe2bff192b |  | note | REFERENCE - IFC Drawings MRP-052-D-SMEC-DRG-71-MPK-AUD-5001
label | c6caff38-041e-51ed-af41-35852cf175ae |  | note | – – – – – – – – – – – – – – – – –
label | 8e1d380d-2b6b-5060-ac2e-0cdc0907b93e |  | note | ACCEPTANCE CRITERIA - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
label | 404e3802-971f-5af6-bae4-2591332ec062 |  | note | – – – – – – – – – – – – – – – – –
label | 0b14988b-d583-5500-9379-1bf50357a022 |  | note | METHOD - Measure Visual
label | 103aa95b-b071-56e8-9425-329753a53000 |  | note | – – – – – – – – – – – – – – – – –
label | 393b1c7c-3a77-562f-89bc-c99a4ac2473e |  | note | FREQUENCY - When Applicable
label | a04c692c-adda-5e86-a4be-004c29ee8a64 |  | note | – – – – – – – – – – – – – – – – –
label | 0f3f085e-67c5-5af9-b534-c718124f6937 |  | note | CATEGORY - IP
label | 585fd690-40be-5d69-aa47-3823ebe0547a |  | note | – – – – – – – – – – – – – – – – –
label | 46ae5c05-81a1-5712-8422-103872b28894 |  | note | RESPONSIBILITY - Surveyor SE/PE/SPE
label | 74fadf98-5e0e-5ac5-a1fc-a5dc1fa4c5c9 |  | note | – – – – – – – – – – – – – – – – –
label | 3efc1678-1355-53c9-978f-ec3a1bbbb340 |  | note | VERIFYING DOCUMENTS - This ITP
date | 4011b5a8-fc56-5b75-9daa-6664f0e13930 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Geotextile
label | 48e1226b-eb29-5b92-8d28-deef0daa87c4 |  | note | REFERENCE - IFC Drawings MRP-052-D-SMEC-DRG-71-MPK-AUD-5001
label | d5a31a34-9421-58e7-8cc9-57039ab7c498 |  | note | – – – – – – – – – – – – – – – – –
label | 3e43843f-9fd7-5206-8fdf-fb3d41b8a406 |  | note | ACCEPTANCE CRITERIA - BIDIM A34 or approved equivalent Geotextile to be installed on both side of granular material with minimum 300 lap length
label | 56c60f94-db9f-58d6-8667-576339896883 |  | note | – – – – – – – – – – – – – – – – –
label | 48fa609c-bdc0-521c-bf42-bf227a68ae71 |  | note | METHOD - Visual
label | 4811cfff-7a51-5b84-9e69-788cd1d8f59d |  | note | – – – – – – – – – – – – – – – – –
label | 6c304dc7-e68c-574e-923a-72d191bbef6c |  | note | FREQUENCY - Prior Granular material installation
label | cf83f462-fe32-50ab-8b65-abe1b452d882 |  | note | – – – – – – – – – – – – – – – – –
label | 745f09a2-3f78-5c43-9bd9-7b32ed66cff2 |  | note | CATEGORY - IP
label | 73bf0a3e-e696-5a4d-8658-28981a2d5040 |  | note | – – – – – – – – – – – – – – – – –
label | 7e14f22a-caea-5fda-bd19-48fef85e224b |  | note | RESPONSIBILITY - SE
label | 433c4eed-a087-581c-babe-4c35407fae64 |  | note | – – – – – – – – – – – – – – – – –
label | 256e2ee1-bd45-5ef4-a38a-298f79b5c480 |  | note | VERIFYING DOCUMENTS - This ITP
date | e7e8e689-68f4-5a3e-8ddc-a97df1b39a12 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Drainage
label | a843eca0-7991-541d-ae27-03059984496e |  | note | REFERENCE - VR 715.08 (e )
label | 92d04066-ace3-5919-824f-682566e49600 |  | note | – – – – – – – – – – – – – – – – –
label | 3fd81bde-ec6f-5e86-a123-697c887cd3f3 |  | note | ACCEPTANCE CRITERIA - a subsurface drainage pipe shall be placed at the base of the rear of the gabion retaining structure.
label | 0f552095-7a1f-57e7-91fa-8856c0ccb70f |  | note | – – – – – – – – – – – – – – – – –
label | 755026ab-8623-5d27-9344-475f67617d69 |  | note | METHOD - Visual
label | 6517d0a4-ebb9-5389-a29c-79267f520b11 |  | note | – – – – – – – – – – – – – – – – –
label | a5e7b074-d204-56d5-8fe0-8f303daaf58c |  | note | FREQUENCY - When Applicable
label | c3dbb8e3-cccb-5598-8fe9-a8630d50df77 |  | note | – – – – – – – – – – – – – – – – –
label | 94350136-b226-5a5a-b25b-f7d30a39d169 |  | note | CATEGORY - IP
label | 5af08818-75c8-5f7b-924c-8dda1d00b26d |  | note | – – – – – – – – – – – – – – – – –
label | bcb07cd3-8068-59e8-9470-297c25a308dc |  | note | RESPONSIBILITY - SE
label | 8ecd38e2-a11a-536a-8017-a4c7556d5862 |  | note | – – – – – – – – – – – – – – – – –
label | a006c953-624a-5c74-bd65-4125d60c008a |  | note | VERIFYING DOCUMENTS - This ITP
date | e46c565d-f4b8-5e3f-a4b3-58683d62d420 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Gabion Slope
label | c9391591-5127-5819-91ce-6565506fba14 |  | note | REFERENCE - IFC Drawings VR 715.08 (c )
label | 235698da-a2f1-55d4-803b-aeaf7babde45 |  | note | – – – – – – – – – – – – – – – – –
label | 72b8585d-3faf-5fd3-b964-efaf5cb72eab |  | note | ACCEPTANCE CRITERIA - the prepared surface for Gabion Installation shall have a slope of 10(H):1(V).
label | 107e34cc-bf95-59de-9d1c-9f5e3d83dca8 |  | note | – – – – – – – – – – – – – – – – –
label | 9f9bbf39-c56c-519a-8310-a785bec1a01d |  | note | METHOD - Measure Visual
label | 07d133e1-dce7-5073-8f3a-2653bdccdd89 |  | note | – – – – – – – – – – – – – – – – –
label | 1b69bbf8-6264-525f-b3b1-7eb75631b26b |  | note | FREQUENCY - Prior Gabion Installation
label | 89ad19d2-dd96-58f1-a114-b7bfb0e83300 |  | note | – – – – – – – – – – – – – – – – –
label | 818dbf5b-16a4-5110-acd0-4bc7b019ab76 |  | note | CATEGORY - IP
label | 2690ab0c-5651-56d0-9c31-2a3be2eb30b5 |  | note | – – – – – – – – – – – – – – – – –
label | f1256acc-03df-5d1e-b36f-c118333903b2 |  | note | RESPONSIBILITY - SE
label | bd7a91e3-aed9-57d4-80ed-7ce8c0933012 |  | note | – – – – – – – – – – – – – – – – –
label | 9decc740-4f0e-55a8-a278-136a80768542 |  | note | VERIFYING DOCUMENTS - This ITP
date | 902a9699-4e0e-5dbf-ba1a-9f63f2859936 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Geotextile
label | 21236359-b3d0-55d9-bece-86431e6f5958 |  | note | REFERENCE - IFC Drawings MRP-052-D-SMEC-DRG-71-MPK-AUD-5001
label | c3b2399c-3df2-5eeb-b52b-065e05192a9a |  | note | – – – – – – – – – – – – – – – – –
label | e5231a6e-7535-586d-9430-fe279cf77bf8 |  | note | ACCEPTANCE CRITERIA - BIDIM A34 or approved equivalent Geotextile to be installed on both side of granular material with minimum 300 lap length
label | b6f91c62-d65b-5ba6-b255-fb84817262b9 |  | note | – – – – – – – – – – – – – – – – –
label | c623aad2-de4c-5b53-9b9b-c977bc90b6c9 |  | note | METHOD - Visual
label | 3375e852-9678-5d8e-a2e0-fe9371795a3c |  | note | – – – – – – – – – – – – – – – – –
label | 7f427618-dc4c-5233-853f-583e187079cd |  | note | FREQUENCY - After Granular Material Installation
label | e1843df7-2459-5851-9d40-1b50d359462c |  | note | – – – – – – – – – – – – – – – – –
label | ab11b3a8-ac98-5aea-a294-78197fa6541a |  | note | CATEGORY - IP
label | 2ae6dd2c-c08a-5ada-9577-40a3b92f7d69 |  | note | – – – – – – – – – – – – – – – – –
label | 4d235ccd-06c1-57dc-853a-d56311ec6ac8 |  | note | RESPONSIBILITY - SE
label | bb6d6204-7c08-52d7-867a-742b28202660 |  | note | – – – – – – – – – – – – – – – – –
label | f4532c54-bbc8-5d78-bcc8-55fbc23b1008 |  | note | VERIFYING DOCUMENTS - This ITP
date | edd01852-7b77-53f8-a8ff-9543e78e6f97 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Gabion Installation
label | d9d36d42-5c50-5920-988e-5c67e27cd63b |  | note | REFERENCE - VR 715.06 (c )
label | 1c252a72-e8a2-500e-bb66-b21886b7719e |  | note | – – – – – – – – – – – – – – – – –
label | fa118b86-3616-5c4d-8739-e1d02c042ab9 |  | note | ACCEPTANCE CRITERIA - Gabions shall be installed in the positions shown on the drawings and each gabion shall be connected to all adjacent gabions by connecting all abutting edges with fasteners at maximum 150 mm intervals.
label | 520d592f-b8b5-5c77-951b-2ad5c9b7ef20 |  | note | ensure the sides of the installed gabions do not vary by more than 50 mm from a 3 metre straight edge laid across the surface prior to, during and after filling with gabion fill material.
label | f11d243b-d704-5b4e-934e-a9dc6d647d06 |  | note | – – – – – – – – – – – – – – – – –
label | 7a53ceea-7df8-5874-bd89-d1ac18fdc6a6 |  | note | METHOD - Visual Measure
label | 60e1ece9-faba-585c-b6cd-048c94a651e6 |  | note | – – – – – – – – – – – – – – – – –
label | 991b75d9-1815-5d44-837f-36b21f4fb436 |  | note | FREQUENCY - Prior gabion fill
label | aaa5cfcf-0456-5b9c-88a3-7832bbb25bf0 |  | note | – – – – – – – – – – – – – – – – –
label | 4380367d-a6e4-5135-b88c-5382e34d13cc |  | note | CATEGORY - IP
label | bcdc3d30-3103-5c6d-92a9-e55237f8f938 |  | note | – – – – – – – – – – – – – – – – –
label | 0f35e8f6-e500-5be6-b386-10fefc7b43e9 |  | note | RESPONSIBILITY - SE
label | f12c795a-82d1-57bc-a052-546df073bb83 |  | note | – – – – – – – – – – – – – – – – –
label | fc5a7203-249f-592d-b6cc-797df35b8a4a |  | note | VERIFYING DOCUMENTS - This ITP
date | 131a1ced-3a1a-533c-be3a-822f6fd80b6b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Gabion Fill
label | 0f338a56-a415-526d-8539-64dbe9dbe29c |  | note | REFERENCE - VR 715.06 (d)
label | 7ccdec6f-7ab2-5a9f-a07c-8154215865d0 |  | note | – – – – – – – – – – – – – – – – –
label | aa544384-ae66-51b9-9bf4-ef71589fc2da |  | note | ACCEPTANCE CRITERIA - Gabions shall be one third filled and braces installed at evenly distributed horizontal centres. Gabions shall then be two thirds filled and additional braces installed at evenly distributed horizontal centres. Gabions shall then be fully filled, the selvedge wires on the lids connected to selvedge wires at all abutting edges with fasteners at maximum 150 mm interval.
label | 0dc7d2b3-1ed0-55c2-8442-8d19f6002e6a |  | note | – – – – – – – – – – – – – – – – –
label | 58ea6881-fb9d-5c7a-9232-d97fd2fa7177 |  | note | METHOD - Visual
label | 969b4de5-1ba7-52ea-98a8-124dd1ad4edc |  | note | – – – – – – – – – – – – – – – – –
label | 088e3103-985f-5fa5-a66a-64ff7376c2f2 |  | note | FREQUENCY - When Applicable
label | c85ec3e1-c804-5470-8609-abbea3b5659e |  | note | – – – – – – – – – – – – – – – – –
label | 75b836b2-5ddc-5f74-a007-77017a901dcb |  | note | CATEGORY - IP
label | 9e673b67-53e7-5768-823b-b6b2366533be |  | note | – – – – – – – – – – – – – – – – –
label | 04e966f5-3e23-568a-9784-ac8ab6a4fc32 |  | note | RESPONSIBILITY - SE
label | 7b8ab931-a310-52a7-ad2a-bc0b13f462dc |  | note | – – – – – – – – – – – – – – – – –
label | bb450039-a8e3-5ab9-a63f-228ccafed790 |  | note | VERIFYING DOCUMENTS - This ITP
date | f79a6ac0-538f-583a-8669-913f8835e70c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Gabion Fill-Bulges
label | 85728b4c-2430-5224-8331-9a206c4ed9dd |  | note | REFERENCE - VR 715.06 (d)
label | cb7a4293-3285-52c2-8d5a-8ba88dcf7181 |  | note | – – – – – – – – – – – – – – – – –
label | c0ee6b65-6672-57de-ab5f-646c0daef843 |  | note | ACCEPTANCE CRITERIA - Where bulges and depressions greater than 50 mm are present after filling, the gabions shall be refilled.
label | c9544a9a-d716-5f8c-adca-e8db6d16da96 |  | note | – – – – – – – – – – – – – – – – –
label | 75d6ae74-6559-5a9d-983a-7a7dfe991819 |  | note | METHOD - Measure Visual
label | 27786386-49a9-5d65-90e3-c2fb845467a0 |  | note | – – – – – – – – – – – – – – – – –
label | 7723c371-baf6-58fb-9c7d-78bfb3be064b |  | note | FREQUENCY - After Gabion Fill
label | 061d5c76-861e-5da3-93a5-9d98ada514dd |  | note | – – – – – – – – – – – – – – – – –
label | fbdd97a7-497e-527e-b241-e1ec9af5ccad |  | note | CATEGORY - IP
label | 212f612f-704a-58bf-ba5b-deda1e6568c2 |  | note | – – – – – – – – – – – – – – – – –
label | a61b487b-005a-52d9-aac1-df05d9168a0b |  | note | RESPONSIBILITY - SE/PE
label | 04e6fb6c-bf65-5f7e-903b-8237fbc0bc13 |  | note | – – – – – – – – – – – – – – – – –
label | c4c6136c-11a7-5a03-bbfa-0f8f3a46246b |  | note | VERIFYING DOCUMENTS - This ITP
date | cc9820fe-6b92-5cbf-bc3e-24db1c84e2ce |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | fb7aa274-f0c0-591e-a68a-e45f7cf7ab93 |  | note | REFERENCE - IFC Drawings MRP-052-D-SMEC-DRG-71-MPK-AUD-5001 VR 670.05
label | af74a1f5-0362-531e-bce8-d3be4f969e08 |  | note | – – – – – – – – – – – – – – – – –
label | 00633d25-c6cd-59bf-8a11-ba11e32db93c |  | note | ACCEPTANCE CRITERIA - Provide record of dimensional measurements face and top of gabions have 1 in 10 slope
label | e87000d8-23fb-57f4-9844-2796646ee845 |  | note | sides of the installed gabions do not vary by more than 50 mm from a 3 metre straight edge laid across the surface after filling with gabion fill material. Attach: Survey As-builts / Survey Report
label | 9f5c0252-52a4-5811-9713-94c4b4d8497e |  | note | – – – – – – – – – – – – – – – – –
label | e6c8f4c5-6be0-5b99-85cd-fb195a3c8630 |  | note | METHOD - Document Review
label | 3d4d905f-9a88-582a-b2b4-81554bcbe320 |  | note | – – – – – – – – – – – – – – – – –
label | ef392d91-3b4d-5e3d-bc0e-37e51b38b729 |  | note | FREQUENCY - Each element
label | adfb2e7c-df2f-599b-93ae-db9add9f87cf |  | note | – – – – – – – – – – – – – – – – –
label | 3e97f780-ba62-5bf7-8e06-d6e416705fa2 |  | note | CATEGORY - IP
label | 67380632-8e3d-594d-8ad5-cdb91f27fa34 |  | note | – – – – – – – – – – – – – – – – –
label | 42bb5961-63f4-558c-9af0-cdcf0be58d5a |  | note | RESPONSIBILITY - Surveyor SE/PE/SPE
label | 992e304e-74c1-565d-acb5-b663009bf45b |  | note | – – – – – – – – – – – – – – – – –
label | b59b1b01-0117-525e-9cff-0b201255a716 |  | note | VERIFYING DOCUMENTS - This ITP
date | ff716d70-b4ab-5cd1-8d75-6ff9b73bd23e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | d2e998fd-c214-55c6-b9b1-7896add91e3f |  | note | REFERENCE - MRPA Quality Management Plan
label | 9c172bbd-6f59-5ea3-941a-21fc7f20c2b8 |  | note | – – – – – – – – – – – – – – – – –
label | ab3b2fc6-0e6c-5848-8ad5-0be4e1975872 |  | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 7eda5c35-646c-51a2-b1b5-680473c78c35 |  | note | – – – – – – – – – – – – – – – – –
label | 29224242-ac44-5d29-911a-d0ddc8090041 |  | note | METHOD - Document Review
label | 03aa3a75-76ce-57f9-a79e-6a15aeb2adcb |  | note | – – – – – – – – – – – – – – – – –
label | ffaf3254-48c2-5bf1-a1a1-02c271e761bc |  | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
label | d899794d-3942-5e62-b0a2-fb293b017004 |  | note | – – – – – – – – – – – – – – – – –
label | f94fec33-f5d4-5000-9267-08617d24c0b2 |  | note | CATEGORY - HP*
label | 7909221c-a4a5-52a1-a309-33df32b407d2 |  | note | – – – – – – – – – – – – – – – – –
label | a4b4843a-3e83-567c-ad6b-e350c1e6d81d |  | note | RESPONSIBILITY - SE/PE/SPE
label | 2a17fb74-cd29-5f30-8b8e-1522abb7609c |  | note | – – – – – – – – – – – – – – – – –
label | 45b7db7f-42af-546b-8bf0-847f59d5317f |  | note | VERIFYING DOCUMENTS - This ITP
date | 24657e7f-071c-5991-a2fd-046923357749 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | fa63c729-d6d5-5285-9978-e90117550dab |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | aa81e6cc-e842-56c9-8896-976f33fff5c7 |  | textbox | Name:
text | 7cc29c6e-1bb1-5684-a1b6-79c68527240c |  | textbox | Position:
date | caa4ec30-b4d6-535d-b248-b8776dd06099 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-100-CIV-CAMMS-Conduit and Pits-MTM Carpark Lighting Rev 0 | itp |  |  |  | Yes | ITP-100-CIV-CAMMS-Conduit and Pits-MTM Carpark Lighting Rev 0 | 22315306-c9d3-40c7-8244-b02d4ba8a164
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | c8e2573a-f5bb-5533-ada9-262498a56a5c |  | note | Document Title: ITP-CIV Conduit and Pit (Supply and Install) - MTM Car Park Lighting
label | c7345d86-4e48-5180-a519-35e968613dfb |  | note | ITP Description: Conduit and Pits- MTM Car Park Lighting
label | c819d0ac-c7ea-5b98-bdb6-9f2d0d8ead10 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | e8bd6909-564c-5540-b17f-1059a9f6ae74 |  | note | Revision Number: 0
label | af16634a-1761-5f8f-be32-594e8aaab8dd |  | note | Revision Date: 14/11/23
label | fd1a7f0e-f9e9-5876-8ebf-082ec92547b5 |  | note | ITP created by: Romualdo Magpantay
label | 8174b1d4-6ed6-5adc-b258-624455261e15 |  | note | ITP approved for use by: Victor Mira
label | 0d4c80c0-1e23-5bef-9903-29f1c3331c59 |  | note | 1.1 L1-CHE-STD-035
label | 769a62ae-c2c8-5972-a950-8a36abab8d38 |  | note | 1.3 AS /NZS 3000
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - Obtain and review manufacturer documentations for the supply of materials: LV + HV Conduits; Communication Conduits; Fixing and Supporting Materials; Pits
label | 1de505fa-fbf1-501b-99ea-44792f01387b |  | note | REFERENCE - IFC Drawing Supplier Specification AS /NZS 3000
label | 15e5a57f-aa0d-57b7-a823-ecacdec6ae0c |  | note | – – – – – – – – – – – – – – – – –
label | 5b235efd-9039-5fbc-98b2-7962ca98b491 |  | note | ACCEPTANCE CRITERIA - Materials comply with relevant specifications.
label | 2d8f1bc2-895b-58b3-9d85-ec42147b5b74 |  | note | Obtain conformance certificates and submit to the Nominated Authority prior inclusion into the works.
label | 1099f750-658f-5f4d-a399-44309cf655d4 |  | note | METHOD - Visual
label | df1b2d48-7d05-5d5d-bb97-3bb240b91a76 |  | note | – – – – – – – – – – – – – – – – –
label | b1100ac7-d4fb-5769-946f-5c77fc23d6af |  | note | FREQUENCY - Once
label | c99bc3c1-654e-52f0-8d02-2273adec06d1 |  | note | – – – – – – – – – – – – – – – – –
label | 25d9cd69-89c5-5628-a2f0-23f372fbad9d |  | note | CATEGORY - HP
label | 1bb64c40-c3ed-5402-8298-1744382f650e |  | note | – – – – – – – – – – – – – – – – –
label | 42894303-6f14-538f-9746-85e4715ac056 |  | note | RESPONSIBILITY - Nominated Authority
label | bf0bd466-3846-5ab2-a411-154b9cb5850b |  | note | – – – – – – – – – – – – – – – – –
label | 34d0e280-81b7-5961-8824-f1d4eb5521f5 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 9a0c78ef-4715-5f03-b52c-423feebb9f4e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Inspect supplied items upon delivery
label | e652ba8a-e12a-574d-938e-75042559ae3b |  | note | REFERENCE - IFC Drawing Supplier Specification AS /NZS 3000
label | f274297d-d030-5ffb-b382-536cad986eb5 |  | note | – – – – – – – – – – – – – – – – –
label | e6b170f9-f8ee-5ef6-8750-8c416e52eaf8 |  | note | ACCEPTANCE CRITERIA - Supplied items are to correct spec, class, size and undamaged
label | 6e1f385c-dce0-5dd2-b1c4-379dcb730380 |  | note | METHOD - Testing
label | e5686f89-6959-5f91-9d8d-48dc9fb3efa5 |  | note | – – – – – – – – – – – – – – – – –
label | 5765e429-7189-55de-a78d-d5ba8b2314cf |  | note | FREQUENCY - Once
label | d8f77548-727a-52f5-b008-a30f27cc5659 |  | note | – – – – – – – – – – – – – – – – –
label | 0b016d32-0470-5131-9246-18d529c05e0f |  | note | CATEGORY - IP
label | f66d76e3-63cd-5c37-8f9e-2a758485942b |  | note | – – – – – – – – – – – – – – – – –
label | 336de7b3-b32b-51f4-ad6f-614031654240 |  | note | RESPONSIBILITY - Electricians Site /Project Engineer
label | 6b0e730d-2254-59dc-8eb5-5dca1bb3bae3 |  | note | – – – – – – – – – – – – – – – – –
label | 7c56bcac-29a2-5234-a6cc-c3bc2f796be5 |  | note | VERIFYING DOCUMENTS - This ITP
date | 7088d0b4-fad2-5eba-b768-2477864fae09 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 - Excavation of Conduit Trenches & Pits
label | 6b879a95-965d-5abb-9458-0aeb0ec9ae3e |  | note | REFERENCE - AS/NZS 3000 clause 3.9 IFC Drawings
label | c09713ca-8b10-50bb-adea-14bf214642da |  | note | – – – – – – – – – – – – – – – – –
label | 0a743f2b-a3d9-5827-bc33-88d1083a768e |  | note | ACCEPTANCE CRITERIA - Install the conduits after earthworks have been completed to subgrade level.
label | 10b34923-1d52-5a55-ab26-28ddb6207a1f |  | note | Installation of the conduits must be in accordance in the design dwgs.
label | e7f6267c-e8c6-55c7-800f-7e1ad215bd61 |  | note | Where the conduits run beneath a road, provide a minimum cover of 500 mm from the top of the conduits to the underside of the pavement; in all other areas, provide a cover of 500 mm to finished surface level.
label | afff9ad3-b42b-5fb6-a086-adfb9802283c |  | note | METHOD - Inspection
label | 65af1f46-5b3b-525f-96b2-7aafe923b0d4 |  | note | – – – – – – – – – – – – – – – – –
label | 6e807a94-dec6-5201-90f7-450ff7150037 |  | note | FREQUENCY - Once
label | 9a91238d-b936-5d8d-97a2-bc9d37178c37 |  | note | – – – – – – – – – – – – – – – – –
label | 224b0574-c74d-569a-a76e-d14a4e5b6fea |  | note | CATEGORY - IP
label | 8c0e961d-0d62-5ae1-9d98-9aca1f188a42 |  | note | – – – – – – – – – – – – – – – – –
label | dbfc6af9-4151-5af5-a611-f09508611c27 |  | note | RESPONSIBILITY - Supervisor /PE/SPE
label | 4b597301-52c3-54f1-b7d6-38db7a58ab7a |  | note | – – – – – – – – – – – – – – – – –
label | 83f26cb0-dbe8-5d85-a796-bde26eb57623 |  | note | VERIFYING DOCUMENTS - This ITP
date | 95ce063f-8321-5c66-9cd2-bb101f5e068c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Sand bedding, laying and backfilling
label | 184a7f5c-9727-5582-8965-bda0a07cc70e |  | note | REFERENCE - AS/NZS 3000 clause 3.11.4.5 IFC Drawings
label | 3cc1bb38-51ca-5620-836a-85d1e4f67bc8 |  | note | – – – – – – – – – – – – – – – – –
label | 31d27c48-c18e-5d40-b63a-90aa5a09880a |  | note | ACCEPTANCE CRITERIA - Use a min. 50mm compacted sand for bedding if not shown on the design drawings.
label | c3f17516-856f-5c6e-83c3-05be683aefd9 |  | note | Lay the conduit on a straight grade and line
label | 67127c30-83f3-535f-976c-2f805b7c6abb |  | note | Compact backfill over the conduits to 100% relative compaction or depend on IFC drawing & pavement design requirements.
label | 8eac3615-e189-5edd-95fa-36e7352463ce |  | note | METHOD - Inspection
label | cc5570e1-f085-5130-9e3f-93a0a576b159 |  | note | – – – – – – – – – – – – – – – – –
label | 0c79e275-50f4-56d4-b8aa-e06ab129faef |  | note | FREQUENCY - Once
label | 07ceb22e-327d-5ad9-bde8-ae644354517b |  | note | – – – – – – – – – – – – – – – – –
label | 1bd7b188-4990-5d0e-9a6b-29c21f0e6c55 |  | note | CATEGORY - IP
label | 5585d1b5-d0f0-5f53-a6e9-83eed53b18bd |  | note | – – – – – – – – – – – – – – – – –
label | a94e34e0-cc6e-5de1-bae7-e7e1df76bfdc |  | note | RESPONSIBILITY - Supervisor /PE/SPE
label | 1056d4d9-b479-5e49-a612-89005795754a |  | note | – – – – – – – – – – – – – – – – –
label | afad662c-690d-59bd-a5f9-ff5931fec07d |  | note | VERIFYING DOCUMENTS - This ITP
date | 6ca79da3-b81f-570f-b4e7-4c1826dc52cb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Install conduits according to manufacturer’s instructions, relevant drawings and Standards
label | 426941a7-1271-52c7-8728-03abaeed4f99 |  | note | REFERENCE - AS/NZS 3000 clause 3.9 IFC Drawings
label | 8e4707af-bc9e-5655-9f53-12451238807e |  | note | – – – – – – – – – – – – – – – – –
label | 03d747c1-797a-55f9-9f71-7596c452ab8e |  | note | ACCEPTANCE CRITERIA - The works are constructed in accordance with AS/NZS 3000 Wiring Rules and Services and the installation Rules of AS 2067.
label | 0f9b2567-4f58-5d5d-b3c2-7b1ffab369f2 |  | note | Conduits are joined together with solvent cement, generally in accordance with clause 4.2 of AS/NZS 2032 and all joints are water tight and free of foreign matter
label | b2d2cd41-dacf-55c9-9ea0-cb789266564d |  | note | Conduits are inline & positioned evenly
label | a6a2e318-0ae7-564a-86e5-3e4e8c20c189 |  | note | Location of each conduit is as per Design Drawings
label | dce1c70d-da32-5b0d-b44c-86343fd5c364 |  | note | METHOD - Inspection
label | fca34d27-ba13-586e-b132-7a6af4e10ebf |  | note | – – – – – – – – – – – – – – – – –
label | ed01c251-045b-5807-99dd-32a5c6651415 |  | note | FREQUENCY - Once
label | 1f4de40d-bf85-54af-94da-a830c3b62f58 |  | note | – – – – – – – – – – – – – – – – –
label | 8d0902e6-ec28-59cd-b8ea-409779d6660a |  | note | CATEGORY - IP
label | 7831144d-9abb-5916-8a7a-2a29e59b5aad |  | note | – – – – – – – – – – – – – – – – –
label | bcf8dd24-0836-5288-b734-6ef32800560a |  | note | RESPONSIBILITY - Supervisor /PE/SPE
label | d3ccadc5-5382-5145-9dc8-5292221da15f |  | note | – – – – – – – – – – – – – – – – –
label | 99d2a4ce-4bc6-562e-8d37-ad688bef9678 |  | note | VERIFYING DOCUMENTS - This ITP
date | fb16c52f-08ca-5017-8345-989a221468d7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Installation of Electrical and Communication Pits
label | 01fe9711-59e4-5574-96f3-cf6dc25dd549 |  | note | REFERENCE - IFC Drawings L1-CHE-STD-035 section 12.6
label | a4c9f930-fdc6-59e1-b7c9-8870aaa441db |  | note | – – – – – – – – – – – – – – – – –
label | fffe7d52-c6f0-5a27-8d01-a079f8983051 |  | note | ACCEPTANCE CRITERIA - Compliance to IFC Drawings, Schedules & relevant specification:
label | b319b499-c1c8-5ad7-9274-8df5010ea781 |  | note | Correct pit as per the IFC drawings
label | fd3a4bac-d9cd-5ada-899f-1fd44596c8f4 |  | note | Soil underneath pit bedding is to be firmly packed prior to install
label | 8753bc25-29bd-502c-8908-29fcf77b2495 |  | note | Bedding according to IFC drawings to be placed
label | 28f5ee6e-a405-58a1-bb20-8dd6720a7b2c |  | note | Pit orientation is correct
label | c85f2c37-3919-53fb-ab90-6adec7e6cc5c |  | note | Lids & covers to comply with technical specification"
label | acf3135b-bab0-5a1c-8661-b26be3eccb3d |  | note | METHOD - Inspection
label | 96a1a733-219e-5fcb-8fda-000c750c9bc6 |  | note | – – – – – – – – – – – – – – – – –
label | bb208823-a97d-56c1-b52a-ca2a80934c4b |  | note | FREQUENCY - Once
label | f541a735-7d1f-5e68-990d-deea652cbf86 |  | note | – – – – – – – – – – – – – – – – –
label | 6bb916c5-be21-54ac-9902-4d1ad90284f2 |  | note | CATEGORY - IP
label | ce71f16e-11ff-554f-96b7-c00be29297fa |  | note | – – – – – – – – – – – – – – – – –
label | 6460b0c6-7e6c-5a15-9c23-a46b73e5a295 |  | note | RESPONSIBILITY - Supervisor /PE/SPE
label | f7d666ab-4c33-5258-a284-d4190f4f28c9 |  | note | – – – – – – – – – – – – – – – – –
label | b7f1a222-fc40-5ffc-9615-643897ecc754 |  | note | VERIFYING DOCUMENTS - This ITP
date | 62e5f6f0-803d-56cf-b4d4-444ed8a8599a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Marker Tapes
label | 42fb1561-4a38-5256-9d38-3330f47daebf |  | note | REFERENCE - AS/NZS 3000 clause 3.11.4.5 IFC Drawings
label | 9ed54012-14ab-59d0-93d6-03cc2d1d3925 |  | note | – – – – – – – – – – – – – – – – –
label | e27f2ba6-53ba-5792-9503-10649155224c |  | note | ACCEPTANCE CRITERIA - Wiring systems installed underground shall be identified by an orange marker tape complying AS/NZS 2648.1. Positioned at approximately 50% of depth cover above wiring system or any additional mechanical protection provided that system.
label | 259741ca-6a53-533d-a15f-0db759f446fc |  | note | METHOD - Inspection
label | 69c677a5-e9a0-5b8a-82be-9f1092d82626 |  | note | – – – – – – – – – – – – – – – – –
label | 7d1afe7d-eaa7-5dfb-ab6b-f55f360c4eb2 |  | note | FREQUENCY - Once
label | c1f60d3e-2744-5c3e-8b60-1ce39f054f2b |  | note | – – – – – – – – – – – – – – – – –
label | 3b371355-dfb1-5b27-9ccd-ca46fc44ab33 |  | note | CATEGORY - IP
label | 6e32c0c2-901a-5667-92c8-49f222b3aadc |  | note | – – – – – – – – – – – – – – – – –
label | 2a8c7e8a-dbca-51ba-abce-13e0aa59db12 |  | note | RESPONSIBILITY - Supervisor /PE/SPE
label | 53eee367-cd40-5413-b859-ad7c7abf12da |  | note | – – – – – – – – – – – – – – – – –
label | 6e5ca827-1655-501d-b7c4-5b710f27ff27 |  | note | VERIFYING DOCUMENTS - This ITP
date | 653e9029-ee51-52a1-b667-79b38a8a0b95 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Install draw-in rope to all electrical conduits(if applicable)
label | e095f0e8-6308-5833-88d4-20a3deac4ecf |  | note | REFERENCE - IFC Drawings QA & Work method of statement
label | 3ddb84cb-91c3-5b2f-8840-5c91bd0ab11e |  | note | – – – – – – – – – – – – – – – – –
label | f94c23ea-d530-5737-acf0-c52025244c95 |  | note | ACCEPTANCE CRITERIA - Polypropylene draw-in rope consisting of one continuous length of not less than 4mm dia. in all electrical conduits or specify in methodology
label | 01230e05-c32c-52b8-9ad9-0cdb79dac638 |  | note | METHOD - Inspection
label | 7e63ca7c-f9be-5b37-8259-82fbdf63e1f3 |  | note | – – – – – – – – – – – – – – – – –
label | d21fa1df-a75b-56c6-904b-0ede6143bc05 |  | note | FREQUENCY - Once,
label | a5bfe798-f7af-5d81-85b4-f457b87f4fa5 |  | note | – – – – – – – – – – – – – – – – –
label | 646f39b8-22ac-50b5-8bdb-e77567baf38a |  | note | CATEGORY - IP
label | 53aa9af8-bbdf-5004-8746-d78494358479 |  | note | – – – – – – – – – – – – – – – – –
label | 3d980a71-37cb-5e19-9fc5-e18f5482d4fc |  | note | RESPONSIBILITY - Supervisor /PE/SPE
label | a48b6bdd-1cb1-5882-91f6-2c0c2fd9130e |  | note | – – – – – – – – – – – – – – – – –
label | a8122057-c507-5ea6-baf9-d79011613927 |  | note | VERIFYING DOCUMENTS - This ITP
date | af95bc0c-1ce5-57a8-a6f3-5e733730193a |  | date | Date Completed:
checkpoint-group |  |  | section | Post Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - As-built Survey (if required)
label | ab272358-9626-5c42-946d-2da12b764f56 |  | note | REFERENCE - As Built Drawings Asset Change form
label | 25b94861-1e28-5bce-bcc1-05ac8a5f76a8 |  | note | – – – – – – – – – – – – – – – – –
label | 57a6b5bb-24f8-59fb-aead-531245bc6a22 |  | note | ACCEPTANCE CRITERIA - Survey activities undertaken to validate correct construction Attach: Survey Report, Engineering Asset From
label | 312c885d-5c7e-519d-848b-b92c16d66183 |  | note | METHOD - Survey Document Review
label | 2cf0ccad-a3b5-59bd-8829-9579a25ea1b7 |  | note | – – – – – – – – – – – – – – – – –
label | bc4ea126-aed1-5a50-862a-41fc6c7d0c0f |  | note | FREQUENCY - Per lot
label | 4c5a9646-42db-568b-ba0a-d670913770a3 |  | note | – – – – – – – – – – – – – – – – –
label | e3d37258-5882-567b-9279-b8342db1fdcc |  | note | CATEGORY - IP
label | f0d1fa1a-b42b-5dea-bc9e-6aa7fa4c9663 |  | note | – – – – – – – – – – – – – – – – –
label | 4b9c380a-ce6a-5f26-b7ba-70018e9cf44c |  | note | RESPONSIBILITY - Supervisor /PE/SPE
label | 1ac4158e-7942-5433-ad25-4aa3deb334f6 |  | note | – – – – – – – – – – – – – – – – –
label | f7e331ec-76a4-5ca4-ae89-f436805c0879 |  | note | VERIFYING DOCUMENTS - This ITP
date | 95d99e60-8756-59a7-ba6b-bc462d8f6dd6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | fcccf96f-c336-5068-a2d1-b413d0f3fe30 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c075c35a-be26-529f-b116-08839f87947a |  | textbox | Name:
text | 7b95b945-11fb-5d57-b499-b86af62214f1 |  | textbox | Position:
date | 5ddacc2b-28e9-51ad-a557-8f5725742be9 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-015-CIV-Kerb and Channel | itp |  |  |  | Yes | ITP-015-CIV-Kerb and Channel Rev 0 | 22fcf66c-a0ad-449a-92df-cae9fe300731
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 009b0b85-9846-5614-af5c-6da2e07d8d4e |  | note | Document Title: ITP-015-CIV-Kerb and Channel
label | 8e4cd3d1-5f7b-5ac9-a1c9-34ed64a1f4a0 |  | note | ITP Description: Kerb and Channel
label | 279ed2e7-32d4-5936-b07f-d48e25ef4dc0 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 08edf004-81e7-53e8-97c4-7c9660c80106 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 30041052-cbf3-55ed-b6ae-b7fbd92a47a0 |  | note | Revision Number: 0
label | 81f54f9a-eabf-51c6-a1b5-0ca5c5f6facc |  | note | Revision Date: 16/12/22
label | b27efb9b-eaec-5d39-8e5d-0f1c68d107b9 |  | note | ITP created by: Isaac El Zayat
label | 85cb20cc-9585-5124-9f83-14abb38e8d07 |  | note | ITP approved for use by: Victor Mira
label | 4da3ae0b-4114-51e6-97b5-785a8ac619f5 |  | note | 1.1 Non Dependent
label | 6a6bfb6c-7aaa-53c0-b742-bc335d701a13 |  | note | Reference: VicRoads Section 703, VR SD2001, VR SD2102, AS 2876, AS1379
checkpoint-group |  |  | section | Preliminary Works - Materials
checkpoint-status |  |  | checkpoint | 2.2 Mix design
label | 5a1e31d0-1433-5127-b719-bb224dbf4fed |  | note | REFERENCE: SD2001, AS1379, Section 703.05, 703.06, 703.07
label | 8793c194-1e10-554d-baba-46e1a2e2ce34 |  | note | – – – – – – – – – – – – – – – – –
label | 8eafa027-8be4-55b7-b9ab-3479bc59c5fa |  | note | ACCEPTANCE CRITERIA:
label | 43240ca2-6ae1-55ba-ab46-b290e6e97c36 |  | note | • Approved VR mix design to be used.
label | d209a6f0-4ea1-54c8-8082-85599a7c703a |  | note | • Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
label | 642f9ae3-9d5d-597a-875f-b277941b7f36 |  | note | • Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
text | ecb5dee0-693c-5ce4-8f99-6cb88b2f3f68 |  | textbox | TeamBinder Material approval number for the Concrete Mix:
label | 8b4e5bef-7cec-557f-b9c2-d28c26d32703 |  | note | – – – – – – – – – – – – – – – – –
label | 9566883c-5415-5899-b2bf-2f8528c0747a |  | note | METHOD: Verify
label | 0e1b9cd4-2298-54da-890d-a9da8a433df7 |  | note | – – – – – – – – – – – – – – – – –
label | 64406640-093c-5ab1-94ca-c198fdfbb48c |  | note | FREQUENCY: Prior to commencing any activity
label | 6b1bff78-a382-5d8f-941a-1c6bc7402bf3 |  | note | – – – – – – – – – – – – – – – – –
label | c277bca8-e2e2-5a74-81ef-03f2fc86fe65 |  | note | CATEGORY: HP*
label | d8b9718f-a502-51e9-bce0-52c48db7ea9a |  | note | – – – – – – – – – – – – – – – – –
label | 9a8b911c-3756-527c-866e-78af2271508f |  | note | RESPONSIBILITY: SE
label | dfc5ba5e-77c1-52a0-8d2e-ca67b450428e |  | note | – – – – – – – – – – – – – – – – –
label | 77d1c512-a251-5e45-871b-f47aa5375d9a |  | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
date | 8367bae0-fcd3-555a-b029-59899f8e8ac9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Bedding Material
label | 3f88161f-836e-5002-9fcc-7511fa33b95f |  | note | REFERENCE: Section 703.21, IFC Drawings
label | ac6f147d-5a1b-5c89-bc6f-c65b465810db |  | note | – – – – – – – – – – – – – – – – –
label | 3124cdba-0d58-517f-89ca-34c9d074f356 |  | note | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete. Or as per IFC drawings.
text | c09a2139-8a75-5bf7-8534-5be27a59f2e3 |  | textbox | TeamBinder Material approval number for Bedding:
label | 700d8d35-3f8b-5a7e-b35f-189bfd952f57 |  | note | – – – – – – – – – – – – – – – – –
label | d5f75223-6290-56fc-95fa-04b3be68cef7 |  | note | METHOD: Verify
label | e0d1da42-71f6-5610-8941-4d3047319a28 |  | note | – – – – – – – – – – – – – – – – –
label | 8001c62e-9bd4-54d8-9425-fe4b2208f154 |  | note | FREQUENCY: Prior to commencing any activity
label | b5f9d8b5-41ab-53c1-8ce9-45f150c78daa |  | note | – – – – – – – – – – – – – – – – –
label | 08969635-ca1c-5832-aeef-12845160994a |  | note | CATEGORY: HP*
label | 75af38ea-b85d-5599-8705-40a8f42c1925 |  | note | – – – – – – – – – – – – – – – – –
label | 04bbaeb1-101e-5abf-a235-ce4040acd89f |  | note | RESPONSIBILITY: SE
label | 6fcd0518-73de-5aae-8f6a-9ba46514dbea |  | note | – – – – – – – – – – – – – – – – –
label | 0b5b12d4-df9a-591a-983c-dee10f7e9e4e |  | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
date | 3fb8d8af-92c0-50a5-8307-2461a9285eb2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Curing Compound
label | 61f038ff-a538-521d-802a-ec36cf4706e7 |  | note | REFERENCE: Section 703.10
label | b1da764f-27d6-5683-bc32-8d054e37b362 |  | note | – – – – – – – – – – – – – – – – –
label | 60becb14-06d5-51e9-a0cc-9d69b13cf074 |  | note | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
text | 47ecf238-462b-5c39-9e08-94d6f71087b9 |  | textbox | TeamBinder Material approval number for Curing Compound:
label | 49538ff9-08ae-5200-b458-c42c5df4c5e5 |  | note | – – – – – – – – – – – – – – – – –
label | 0b46957e-ca8d-5bb2-ae28-a5de1b125aad |  | note | METHOD: Verify
label | 0df53f6b-5df3-5a27-8a2a-f5e07f13cf38 |  | note | – – – – – – – – – – – – – – – – –
label | 68fa5587-8371-50fd-a663-f9c3f51094aa |  | note | FREQUENCY: Prior to commencing any activity
label | ee31a341-1b6e-5a46-aae1-389ada6a2143 |  | note | – – – – – – – – – – – – – – – – –
label | ea3ab702-60eb-51ea-b466-f56ab6e095d1 |  | note | CATEGORY: HP*
label | a2471272-8939-5d84-bdbb-e3c68d5c0a56 |  | note | – – – – – – – – – – – – – – – – –
label | 2673e2a4-8c75-5d69-89af-008d801cbe18 |  | note | RESPONSIBILITY: SE
label | 74ade77c-72af-5f7e-a438-018e05965d50 |  | note | – – – – – – – – – – – – – – – – –
label | 8e18faf4-e444-501c-95eb-892c115520c2 |  | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
date | d7db750f-139c-51c3-95bc-b46d2f545483 |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminary Works - Documents
checkpoint-status |  |  | checkpoint | 2.1 Check for correct documentation
label | b089b2dd-0ed3-556c-8452-7d7c711a1860 |  | note | REFERENCE: Drawing and Drawing Register
label | d310df17-1eac-59f8-ac80-664d3456deae |  | note | – – – – – – – – – – – – – – – – –
label | d30c3627-8542-574b-9f0c-1f9479c83b41 |  | note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
label | 15535d57-b1dc-5dc5-9f66-549d32c244b1 |  | note | — Using the correct and complete set of drawings
label | eab875e9-ed1e-5661-baf0-7cfddbf2497c |  | note | — All drawings are the latest version
label | 3496e985-cd51-5836-8ae8-25497a41bdba |  | note | – – – – – – – – – – – – – – – – –
label | 7bba940b-7573-583a-933b-eb54cce6fad2 |  | note | METHOD: Visual inspection
label | e1e5375f-d8e6-5217-ae9a-950206aa9d28 |  | note | – – – – – – – – – – – – – – – – –
label | ad6e408a-5f75-539f-8550-2d67e445564a |  | note | FREQUENCY: Prior to commencing any activity
label | 510557e8-898e-53e2-b0c3-cadcc5e69d7f |  | note | – – – – – – – – – – – – – – – – –
label | 560153af-ff1f-52c1-b6e4-1dd671530a5f |  | note | CATEGORY: HP*
label | b2221f28-849b-5ffe-9768-1f27cbe8fe6b |  | note | – – – – – – – – – – – – – – – – –
label | 6f409df5-9355-5653-9425-4fac4fa72f02 |  | note | RESPONSIBILITY: SE/PE
label | 9cc20667-ffea-5efe-a1fc-8b3c1a517a68 |  | note | – – – – – – – – – – – – – – – – –
label | d67c355f-b28b-5099-9fba-142a1921e2d5 |  | note | VERIFYING DOCUMENTS: ITP Signed
date | 4e1f5115-7a9f-527d-82e5-8baca0eeebf8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Lot Map
label | 25c6853a-ca66-59ac-8360-4b7b170c585a |  | note | REFERENCE: MRPA Lot Management Procedure
label | b07ac09c-3dd2-58f7-a691-f8769256a2a5 |  | note | – – – – – – – – – – – – – – – – –
label | 858ac52e-8b77-5071-a5c2-dcd7d5bb6a5b |  | note | ACCEPTANCE CRITERIA: Upload a Marked up drawing which indicates the Location of this Lot:
label | b91f64c7-b080-50fa-a9e6-0ad3fdb7777c |  | note | • Attach: Lot Map
label | 0b7343d5-a27c-5d06-a6f8-c456907956b4 |  | note | – – – – – – – – – – – – – – – – –
label | 8fd4a064-bc41-57c0-acb6-eecd748be9de |  | note | METHOD: Document Review
label | 4ba919f4-4429-52e1-a2ee-1af0e0854d36 |  | note | – – – – – – – – – – – – – – – – –
label | 00af3142-1828-5895-83e8-c4380681a228 |  | note | FREQUENCY: For Each Lot
label | 5f4369f2-e676-50d6-aa7b-61e4cc08ce04 |  | note | – – – – – – – – – – – – – – – – –
label | 0d75dd56-b586-5b30-8e04-fe641d01648b |  | note | CATEGORY: HP*
label | 494e161b-c42b-5e4b-b066-8f36ce71fbf4 |  | note | – – – – – – – – – – – – – – – – –
label | b4f2fbe0-c030-5e42-ad84-8daeeaee4cb5 |  | note | RESPONSIBILITY: SE/PE
label | 10acd828-c5a4-5eb5-9a2b-58a7ee12c6de |  | note | – – – – – – – – – – – – – – – – –
label | d9e1c5ea-fe89-574c-bb96-9c33c51277a1 |  | note | VERIFYING DOCUMENTS: Lot Map
date | 4af5d2c5-f998-52c1-b1dc-75ce709ac8e3 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Setting out
label | ee1cd808-b1ab-5de7-abda-bd2942e76034 |  | note | REFERENCE: Section 703.17
label | 2ea82630-6349-5ace-a425-4dcff0016e85 |  | note | – – – – – – – – – – – – – – – – –
label | d4f58911-e05b-589c-bd08-c026cc414f5e |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawing.
label | a527abec-1c47-59cf-aeea-f5f1a69bc8fe |  | note | • The superintendent will review and confirm set out.
label | 679a21c0-8e9a-5640-9198-1580ce2ef4b5 |  | note | • The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | b176c907-217d-5baa-96f1-2d0019832074 |  | note | • Attach: Survey Report
label | 272bffe1-98be-5648-b25b-5bca165b1ba6 |  | note | – – – – – – – – – – – – – – – – –
label | 61639091-b4f2-562e-a8f5-54c9b1b463c7 |  | note | METHOD: verify
label | b86a650d-92d2-5b1a-b7fb-50faafed41a6 |  | note | – – – – – – – – – – – – – – – – –
label | b9e12d7a-9283-59ae-80cc-efa2a9cd6bc2 |  | note | FREQUENCY: Prior to start
label | 04abb4cd-6f69-56d1-99d9-d0b016486091 |  | note | – – – – – – – – – – – – – – – – –
label | e75d6c7d-6bb8-5258-9767-4f3c7fc3f64e |  | note | CATEGORY: HP
label | 374fa501-585b-5ca6-972e-ff8bb40754c9 |  | note | – – – – – – – – – – – – – – – – –
label | cac21d97-d6fd-5507-bbde-174256a8e3d2 |  | note | RESPONSIBILITY: Surveyor
label | 423d1ee1-7568-5d97-a833-7c37985c2d19 |  | note | – – – – – – – – – – – – – – – – –
label | 5753d09d-593b-5b1a-891b-c6a460f8b7aa |  | note | VERIFYING DOCUMENTS: ITP signed, Survey Report
date | d9dd448a-3d30-5653-b413-63785620a962 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Temporary drainage provisions
label | afed759f-ef43-5f74-8ac8-91311cdc52c1 |  | note | REFERENCE: Section 703.18
label | 65195814-84d0-549b-b70d-5e131c58ac6b |  | note | – – – – – – – – – – – – – – – – –
label | a975d8a7-7105-567f-8f77-d94a0bf3f357 |  | note | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
label | d4888a9b-eeda-5dfd-af28-4d99de92d99f |  | note | • Need to obtain prior written approval from the relevant waterway authority prior to diversion.
label | 5424461f-402e-5904-96db-e4f883d4d906 |  | note | – – – – – – – – – – – – – – – – –
label | 2877beca-e0d9-586e-aa4f-b49d5b5882c9 |  | note | METHOD: Visual inspection
label | 8dbd7bd2-0688-599c-bf9c-1954887680c6 |  | note | – – – – – – – – – – – – – – – – –
label | 56f1874b-5f7f-5f40-8f1b-5076edd78285 |  | note | FREQUENCY: If required
label | 21b1b06b-4f0b-5377-ae70-ef1f3e74d4cb |  | note | – – – – – – – – – – – – – – – – –
label | 29ee0ee9-f4ad-50b9-a28f-7082a28f0845 |  | note | CATEGORY: WP
label | 69e90580-b5aa-5466-b0fc-f385fd1951c5 |  | note | – – – – – – – – – – – – – – – – –
label | 9063ceec-b994-5c58-8421-7dcd9c192c72 |  | note | RESPONSIBILITY: SE
label | 56e94125-92c9-5603-8485-62bbfef69a7a |  | note | – – – – – – – – – – – – – – – – –
label | 57c5f410-d939-52e0-abce-b5467a1f79bc |  | note | VERIFYING DOCUMENTS: ITP signed
date | 409adc9c-44f0-578a-ae1a-fd192031a10c |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Bedding
label | 762e074b-09b0-5f70-a982-8d4196e3d2b5 |  | note | REFERENCE: Section 703.21
label | 1f432c39-c800-52ff-bf4c-d4b97bbfd710 |  | note | – – – – – – – – – – – – – – – – –
label | 6ac67939-de31-586d-be8b-460dfd4371d0 |  | note | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm.
label | 01c1d797-0791-5092-bc6f-914e4e57e1c2 |  | note | • Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted .
label | 779bf67d-5b60-573d-b0e8-2451582262c0 |  | note | – – – – – – – – – – – – – – – – –
label | c3ae9df2-6a9e-5018-919b-4e8e6e95dd9c |  | note | METHOD: Visual Measure
label | fee4b89c-7e7a-5571-8890-6f31e1ec0b20 |  | note | – – – – – – – – – – – – – – – – –
label | 31820287-2dc3-5455-a253-9d97f69214f9 |  | note | FREQUENCY: Each lot
label | 7b7702d2-f36a-5f06-b68c-431db18b357e |  | note | – – – – – – – – – – – – – – – – –
label | 974ffea1-9efe-5b12-b512-d85fbce3e7e8 |  | note | CATEGORY: WP
label | 82b47de5-51b5-56c2-a135-8b9ee01c830a |  | note | – – – – – – – – – – – – – – – – –
label | 51da41f6-443f-5562-b683-9583346140be |  | note | RESPONSIBILITY: SE
label | a5583990-b09f-52a0-b6b7-747a6adfa500 |  | note | – – – – – – – – – – – – – – – – –
label | c903959d-2fb7-5d21-84dc-7a480bf134ae |  | note | VERIFYING DOCUMENTS: ITP signed
date | e689c30f-096a-5f8a-8623-11f5f46932a9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Formwork
label | a4e581fb-eae2-5f2c-bf70-4f87f2deb2e8 |  | note | REFERENCE: Section 703.12 AS3610
label | c2426949-9386-5e76-bc89-2bc6ac81e3e5 |  | note | – – – – – – – – – – – – – – – – –
label | 7d811fad-11f6-53d6-86df-7dfb2435b51e |  | note | ACCEPTANCE CRITERIA: Joints in formwork shall be constructed such that loss of mortar is prevented.
label | 7b68ad43-b84e-525b-8869-e9dbd9dc1816 |  | note | • Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | 00b4020f-da86-54e2-af50-77b58619d00e |  | note | – – – – – – – – – – – – – – – – –
label | f5a55a3a-da4e-568d-93ed-13a90b3a99d6 |  | note | METHOD: Visual Inspection
label | 4ac166ae-ef69-56fa-82d4-7f0018da575c |  | note | – – – – – – – – – – – – – – – – –
label | b5ba3980-e514-56db-be2b-55d96b4d4138 |  | note | FREQUENCY: Each lot
label | abdf5389-c925-5760-9865-a19dc1055804 |  | note | – – – – – – – – – – – – – – – – –
label | 6e6bf7d0-db77-54b6-8307-42dc1f64aafc |  | note | CATEGORY: WP
label | 2ae4c4dd-e6d6-5ceb-aae6-1f5416ddf467 |  | note | – – – – – – – – – – – – – – – – –
label | a9b399a3-bc6c-54b4-a5e6-be1c73b624d1 |  | note | RESPONSIBILITY: SE
label | 6bd8b126-7b3f-5121-9558-da2159121c06 |  | note | – – – – – – – – – – – – – – – – –
label | f3515dbd-2b91-5e81-8fab-6c8aa52dd635 |  | note | VERIFYING DOCUMENTS: ITP signed
date | 51a8bc98-68f9-5244-924e-72956176d9d9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Pre Pour Check
label | 30baf684-2e7d-56f1-a2b8-9be588dc0cda |  | note | REFERENCE: Section 703.09
label | 06524336-786d-53b0-a173-ee9cf1731a51 |  | note | • Section 703.21 Section 610.17a), b) & c)
label | ee0bc2c9-5437-57d9-921a-8494e634ed2e |  | note | – – – – – – – – – – – – – – – – –
label | c7eda2f9-47ca-50ba-9379-059346e9f733 |  | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
label | 0aff6cfe-7592-51d3-83c9-85c7f1e6d16e |  | note | • Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
label | 2ff43214-00af-59b5-91c8-34898d62a1e6 |  | note | – – – – – – – – – – – – – – – – –
label | a8d953e5-f3a7-522a-a210-b8e86066ccea |  | note | METHOD: Verify
label | 8cbb57f0-ed39-54bd-8bea-61334b0e011e |  | note | – – – – – – – – – – – – – – – – –
label | 96ca5d0f-f5e3-5c5a-9e20-504e0724dd38 |  | note | FREQUENCY: Each lot
label | 7a9e86f8-3c13-599f-9024-2fbbb50eae3b |  | note | – – – – – – – – – – – – – – – – –
label | 4d8723a7-d5aa-5a24-9347-8d6ea4fbe9e9 |  | note | CATEGORY: HP*
label | 923b0363-8d9f-5708-be9d-eb349fd8ef69 |  | note | – – – – – – – – – – – – – – – – –
label | 5d394e83-a893-5d69-a796-c04d06770e5d |  | note | RESPONSIBILITY: SE
label | 10ded6b2-7e61-5acf-afe3-c9e96d310eab |  | note | – – – – – – – – – – – – – – – – –
label | 3bac01d7-37e2-5b2c-a4bd-3c9587d247c2 |  | note | VERIFYING DOCUMENTS: ITP signed
text | 8857eb30-6500-5acd-a913-4cac7773ec65 |  | textbox | • Ambient temperature |  |  | °C
date | 84f4e73d-ae50-5a59-af17-95797e4a3c10 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Concrete placement
label | 97d25d60-2d9d-5ff1-8cc5-2e15b5f49ed7 |  | note | REFERENCE: Section 703.08
label | 4c67b128-d675-561d-a7c0-d3676ab56b3b |  | note | • Section 703.23
label | d1976323-729e-5dee-85cc-402c6e0ad413 |  | note | – – – – – – – – – – – – – – – – –
label | a453678e-4d7f-5dbc-9dad-0662b61e443d |  | note | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
label | e95107d3-55c3-52b6-84cc-ba60e1b7fdcf |  | note | • Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
label | d0dc435a-0cae-5269-8df4-80f8a96e1ff2 |  | note | • Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | f187b065-aab8-53ac-a948-3ec22cdefd7d |  | note | • Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
label | b573af53-3a28-56ec-b7e2-d722e97901cc |  | note | – – – – – – – – – – – – – – – – –
label | f93a55ea-918e-55bd-81ed-35ea57823e63 |  | note | METHOD: Visual Measure
label | ba191213-2c60-5fcf-9c45-44d431e1c5d2 |  | note | – – – – – – – – – – – – – – – – –
label | 87b8aa60-9242-59cf-a301-2d4468011640 |  | note | FREQUENCY: Each lot
label | 984a11bb-2358-5d8e-a9db-5ed68f0bfd86 |  | note | – – – – – – – – – – – – – – – – –
label | f8bff205-3d92-59fc-86ce-9b7c2833c3c7 |  | note | CATEGORY: IP
label | e4539e86-91bd-5b87-b94b-fece5a5107c8 |  | note | – – – – – – – – – – – – – – – – –
label | c06d336f-eada-55e2-b7cb-e3d5b288119a |  | note | RESPONSIBILITY: SE
label | 2f978d3c-a969-57a9-934b-8b19da5f644d |  | note | – – – – – – – – – – – – – – – – –
label | c25bb7be-cb48-54cd-b3df-dbb2fc2ed6dd |  | note | VERIFYING DOCUMENTS: ITP signed
text | 389eac80-4b90-5616-876b-c820306bfb6f |  | textbox | • Ambient temperature |  |  | °C
date | 0b9815e2-e554-5505-8d8b-ea8888151527 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Transitions
label | a70f7862-7afc-5d27-ba2e-647af3c7d687 |  | note | REFERENCE: Section 703.24
label | 367a3d26-bba8-512d-bd98-d9e047429ba0 |  | note | – – – – – – – – – – – – – – – – –
label | 868b422b-89f5-55f5-86a5-ba6231419071 |  | note | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | 2f9f3818-52c1-53a7-8221-c187f9ba2be2 |  | note | – – – – – – – – – – – – – – – – –
label | 82cd302e-1025-5a7a-9621-ceb66d2596da |  | note | METHOD: Site inspection
label | ec0bbbcc-b596-5bf1-ae78-e3b904b260ab |  | note | – – – – – – – – – – – – – – – – –
label | 1cb8a997-e4d1-53f2-8868-a15389d32d4f |  | note | FREQUENCY: Each lot
label | 3b2a7db5-adee-56da-aa6a-761d60a940c9 |  | note | – – – – – – – – – – – – – – – – –
label | 5ec20c83-e723-504c-a18c-753aed4171b8 |  | note | CATEGORY: IP
label | 9dec7131-157d-569c-8402-f29e888c4ca8 |  | note | – – – – – – – – – – – – – – – – –
label | e0b9855f-608a-54a8-a74e-7c39e96e565b |  | note | RESPONSIBILITY: SE
label | 81464237-b855-5d07-94ec-e0471f379bed |  | note | – – – – – – – – – – – – – – – – –
label | a8b1c20c-e129-523c-a859-bafaae70a86f |  | note | VERIFYING DOCUMENTS: ITP Signed
date | e5af150d-2872-50b6-b682-ee01631f183c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Surface Finish
label | e2cce273-6889-56f8-92f4-43029d8a655f |  | note | REFERENCE: Section 703.25
label | c12925be-f6df-56ab-819b-1cc8f57e9413 |  | note | – – – – – – – – – – – – – – – – –
label | cb06741a-4c72-5ca6-98f6-44a2872c45fd |  | note | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
label | 3e8792a9-8cc4-5727-a16b-de3bdf4a939c |  | note | • Renderings shall be applied within 30 minutes of extrusion.
label | 5c7d8232-bf6d-5d6d-85af-cc03fc7d668d |  | note | • Concrete to have a neat appearance and uniform colour.
label | 036b6852-8bda-556f-8d52-c4817df800e6 |  | note | • Class 3 finish required for external surfaces.
label | 00d6088d-768a-570d-b615-b38b0ce8d6e8 |  | note | • Class 4 finish required for permanently hidden surfaces.
label | a4410fd8-ad28-59c3-afb0-1d43fff233c7 |  | note | – – – – – – – – – – – – – – – – –
label | 9ddc50e0-a96b-5e66-82c8-3ff0d3f34d9b |  | note | METHOD: Visual inspection
label | 2611502c-2341-515c-a0aa-6b11e45502fd |  | note | – – – – – – – – – – – – – – – – –
label | ffd3fe30-e166-5cf8-a4bf-0f630ec2fcba |  | note | FREQUENCY: Each lot
label | 2b3a7f2b-058c-5e13-9a21-9ba982f9487f |  | note | – – – – – – – – – – – – – – – – –
label | 48bb5cdd-285e-53b0-95d7-f864b0c32b55 |  | note | CATEGORY: IP
label | f2c9f1bd-38ca-5e8c-a59d-57149dedb2fd |  | note | – – – – – – – – – – – – – – – – –
label | 58e1083f-f1de-5594-b66c-4a5a153f3888 |  | note | RESPONSIBILITY: SE
label | e6c3818a-96a1-58be-9efd-c611bf72c2e7 |  | note | – – – – – – – – – – – – – – – – –
label | 62733df5-2d7d-5b44-9d4e-bffe563d43ab |  | note | VERIFYING DOCUMENTS: ITP signed
date | d8fbc71d-57e8-5743-b75f-91ae1931c025 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Formwork Stripping
label | 8cd16c0f-d64d-5c27-8ae0-d0160eab4ff5 |  | note | REFERENCE: Section 703.12 AS3610
label | 079c25a5-2ae6-5a6c-9794-4eeac559f2a0 |  | note | – – – – – – – – – – – – – – – – –
label | f7f521c0-29ba-5a76-b77f-90f959d7d1d4 |  | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
label | 96cf3f77-42fe-5c67-a270-7655b15cae76 |  | note | — External faces 2 days
label | 8b9e71cb-7e14-54ab-bb38-f93f4db82125 |  | note | — Permanently hidden faces 1 day
label | 3f317d8c-103e-5dc8-950d-5385adae7a95 |  | note | – – – – – – – – – – – – – – – – –
label | 21d4e2cc-50f2-5ec7-b5d9-c95bdae1d5e8 |  | note | METHOD: Visual inspection
label | 944faf6c-248b-5a69-a353-daddbb58d855 |  | note | – – – – – – – – – – – – – – – – –
label | 0d415d2c-e161-55e6-aad2-2e77c447ed7f |  | note | FREQUENCY: Each lot
label | 183e9d0f-ce7e-5c2f-a36d-89b67df6f380 |  | note | – – – – – – – – – – – – – – – – –
label | 0745439a-7834-5775-b7c0-2bdb3733ad4a |  | note | CATEGORY: IP
label | d5296fb9-c7c4-5f08-8dd0-45d96dd871a5 |  | note | – – – – – – – – – – – – – – – – –
label | cb36f7ab-8c72-5f1f-8deb-94e3a66f943c |  | note | RESPONSIBILITY: SE
label | bb5c6b2f-aace-5248-adf3-0dee630eef34 |  | note | – – – – – – – – – – – – – – – – –
label | 5d455bf4-5b35-5107-97b0-d426561cb69b |  | note | VERIFYING DOCUMENTS: ITP signed
date | dcd2f75e-2a2e-5cb0-ba78-c18d5e249eaf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Tolerance
label | c3853922-80f3-5e00-9cd6-b5988d626edd |  | note | REFERENCE: Section 703.15
label | 435638de-3348-5ab4-b3e0-d5c88a3f63a0 |  | note | – – – – – – – – – – – – – – – – –
label | 2beebf03-c889-5f59-a2ff-29a5980200b6 |  | note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
label | cfb08aa2-049b-5afa-941a-c22764935765 |  | note | • Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
label | 466c0f4a-0b8f-5f7d-ab92-0a3778d61095 |  | note | • Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
label | 5cb1ab23-4d07-54a5-b346-0e1f1eb6800a |  | note | – – – – – – – – – – – – – – – – –
label | 4665ba93-f357-5753-aeac-607934073db6 |  | note | METHOD: verify
label | 156e4141-c22f-530e-b78c-a1c41913bb8f |  | note | – – – – – – – – – – – – – – – – –
label | 6d26b9a2-93bb-5759-9eb4-a5161e397e75 |  | note | FREQUENCY: Each lot
label | b84af3ed-c98e-5353-bf3d-7a2ebbdd0bb0 |  | note | – – – – – – – – – – – – – – – – –
label | 6e794285-36a2-5f20-9b85-02abb4f31faa |  | note | CATEGORY: IP
label | 9afed74c-c3c6-5085-9d38-096420c8f94a |  | note | – – – – – – – – – – – – – – – – –
label | f58a24d7-8e1c-58d4-b035-179f723eb92c |  | note | RESPONSIBILITY: SE/surveyor
label | 02ffc599-1b03-5f7a-a91b-bf46c9e3bc51 |  | note | – – – – – – – – – – – – – – – – –
label | 4333273e-35e8-5f6a-a09d-dcc6cd31c61f |  | note | VERIFYING DOCUMENTS: ITP signed
date | 7791fecf-236f-55ff-a55e-a4c8df9734e9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Curing
label | ebf09df0-ad3f-5597-a52c-43e1019388ed |  | note | REFERENCE: Section 703.10
label | 2492748a-7e0d-5b62-8d28-1cabc397e541 |  | note | – – – – – – – – – – – – – – – – –
label | f9e58fc1-f6b7-5aa0-8425-eeb39c60903e |  | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
label | 8afbe40c-fc27-5d42-b7cc-dce8872c3e0b |  | note | • Concrete edgings shall be cured for a period of not less than three days after placing the concrete
label | ce3bc838-3ec9-58f9-a212-3c24d645ec89 |  | note | – – – – – – – – – – – – – – – – –
label | 13152c2a-95dc-5719-ad53-d5c775880512 |  | note | METHOD: Visual inspection
label | e0fb99c3-8f0a-5412-90c4-67b2173c5bb4 |  | note | – – – – – – – – – – – – – – – – –
label | f3393bbd-b7df-566f-9856-60308bb611c6 |  | note | FREQUENCY: Each lot
label | 91c7a221-c076-527d-aa37-79f07284bc72 |  | note | – – – – – – – – – – – – – – – – –
label | cfed0bd8-d7e7-5b03-92f0-7eff30d5228e |  | note | CATEGORY: IP
label | a3a08ea3-dab5-5d11-a225-aaacb43aeb3c |  | note | – – – – – – – – – – – – – – – – –
label | 6c1f6035-dafd-588f-847b-15b524c96de3 |  | note | RESPONSIBILITY: SE
label | 22667bc1-31d9-569e-b1cc-64ebf92f49e5 |  | note | – – – – – – – – – – – – – – – – –
label | 76096f2b-7bf6-5d15-baee-06e1d0b98498 |  | note | VERIFYING DOCUMENTS: ITP signed
date | e8130cbf-f9a2-5e6d-b48f-5a502abcb9ef |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Joints
label | a0bb2f58-3e6e-5873-82b9-ece37a5919ec |  | note | REFERENCE: Section 703.26
label | 733ef3cb-67c5-53a4-9163-3cd517af738a |  | note | – – – – – – – – – – – – – – – – –
label | 3cae0f6d-fd4c-51f7-858c-9b204c83c23c |  | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | c4d87c0b-8d92-5891-97ee-807cc6942e16 |  | note | • Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
label | b09d8351-574c-57f9-97ad-ebd336252a82 |  | note | • Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
label | b6b1a498-fa86-5232-90a6-264b6686b6c9 |  | note | – – – – – – – – – – – – – – – – –
label | 9e5fce19-5968-5463-b362-bb9ed55ec795 |  | note | METHOD: Verify
label | 402318eb-1302-549b-9d71-19a3f2241917 |  | note | – – – – – – – – – – – – – – – – –
label | e7ee3b1f-4df6-540f-9bf7-70bd3868d8c0 |  | note | FREQUENCY: Each joint
label | e437408c-86c4-5ae2-8384-5158916c265e |  | note | – – – – – – – – – – – – – – – – –
label | 6eb3f885-598e-5e4c-8955-87e2846583cc |  | note | CATEGORY: IP
label | c7408ffa-65c4-50f0-a968-5d899d018740 |  | note | – – – – – – – – – – – – – – – – –
label | 70192751-eef3-50b7-8c6a-98769cc33366 |  | note | RESPONSIBILITY: SE
label | cad2f531-1933-55ef-957b-dd25accb966c |  | note | – – – – – – – – – – – – – – – – –
label | 552756b1-ed02-5e65-9269-6ce88839e38e |  | note | VERIFYING DOCUMENTS: ITP signed
date | bc8abcd0-a917-5ff6-aeac-b5fbdf9e0e1a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.12 Protection of Concrete
label | 959b6dbc-f3ac-5e35-b527-d1c30c3c4747 |  | note | REFERENCE: Section 703.27
label | c9b79e65-4a4c-5850-b30e-84a22c2f51ef |  | note | – – – – – – – – – – – – – – – – –
label | 468cb98b-54ec-5912-9d10-26c0853e8de0 |  | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
label | bdca8787-9673-5e89-8a50-1d3cf111d014 |  | note | – – – – – – – – – – – – – – – – –
label | 5fdeaf08-9073-5f52-95ab-cc8655c64907 |  | note | METHOD: Visual inspection
label | c4406c1f-c0dd-5c42-ae38-cfba8dc04016 |  | note | – – – – – – – – – – – – – – – – –
label | 9333eb06-61aa-51a1-8574-cec5ae75005a |  | note | FREQUENCY: Each lot
label | 2c8121c8-2c15-5571-a3ad-26e9c6527689 |  | note | – – – – – – – – – – – – – – – – –
label | 813d5c6a-c556-5dd7-ad1b-326453b38415 |  | note | CATEGORY: IP
label | 10f83bf2-0a18-52a8-9732-08d4bf8f5cbe |  | note | – – – – – – – – – – – – – – – – –
label | 4639477c-bab4-5c56-8abd-3cdf300aadd0 |  | note | RESPONSIBILITY: SE
label | 892f4fde-4c58-572c-8b17-5ae44c42e64c |  | note | – – – – – – – – – – – – – – – – –
label | ba13e856-cf09-52ce-8787-9ab380eb47fd |  | note | VERIFYING DOCUMENTS: ITP signed
date | e5559e0c-3b1d-5a35-bdbc-35a34941301c |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.11 Backfilling
label | 96243620-d8af-5026-a3e8-22c684be9021 |  | note | REFERENCE: Vic Road spec 703.29
label | 87daaec3-edc4-5729-9749-0eb9764c1536 |  | note | – – – – – – – – – – – – – – – – –
label | 34f01fde-79a6-534c-9559-5e7721172357 |  | note | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
label | a30e9da3-66c6-5efa-82e6-04f1f436e86f |  | note | – – – – – – – – – – – – – – – – –
label | 3d7d27cc-9ca0-52cb-a5b5-2b38f8375dae |  | note | METHOD: Verify
label | 825441a6-079b-57b9-8f77-bfdc38243bed |  | note | – – – – – – – – – – – – – – – – –
label | 1e040e0b-44e5-58a7-b526-7223c1235c20 |  | note | FREQUENCY: Each lot
label | e2a56c45-b0ed-5131-8be4-ad1e817cd65a |  | note | – – – – – – – – – – – – – – – – –
label | 0be29f85-517c-5697-8f89-d331516ad9d4 |  | note | CATEGORY: IP
label | 20522701-70c6-58dc-8023-62df75a7b42f |  | note | – – – – – – – – – – – – – – – – –
label | b41aff00-9f7b-598e-8c53-cc55fb738205 |  | note | RESPONSIBILITY: SE
label | aa3cce91-cd4b-5f43-9baa-c8c262ce4727 |  | note | – – – – – – – – – – – – – – – – –
label | 568072ef-cab2-5f0f-91a5-3b4c710c92ae |  | note | VERIFYING DOCUMENTS: ITP signed
date | d2738909-f493-500c-a210-74278be6cffb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.13 Cracking of Concrete
label | ce3b039c-fe3d-5b3f-85f7-b57327933b5b |  | note | REFERENCE: Section 703.30
label | d8fb20ce-e6af-5768-8b5d-bfa7e8d41021 |  | note | – – – – – – – – – – – – – – – – –
label | 9df8d181-a87a-5a65-9249-ebf76de0209e |  | note | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | 0291f27c-6ea3-5ee2-a774-89232d96b77a |  | note | • Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | f0d337ed-50b3-5a80-883f-0345054f5252 |  | note | – – – – – – – – – – – – – – – – –
label | 5081422d-1071-5bd6-a9a0-fcff59140841 |  | note | METHOD: Visual inspection
label | 99719de9-a20b-5ed0-88c4-21c82daa072d |  | note | – – – – – – – – – – – – – – – – –
label | e328e7db-4e24-5365-be0d-dd2c8d17f3e3 |  | note | FREQUENCY: Each lot
label | 92ac3266-6315-5b82-ac74-55e0d8041f9a |  | note | – – – – – – – – – – – – – – – – –
label | 38d32c31-22d9-5f71-bf6c-5625fef12e71 |  | note | CATEGORY: IP
label | 3d2abd5d-dbfc-50e0-8325-1ed0614c3ce9 |  | note | – – – – – – – – – – – – – – – – –
label | 1dd766f1-84be-58d8-b010-628f6a212902 |  | note | RESPONSIBILITY: SE
label | 9ef08ed0-ad3d-572f-8726-f8cf71523b99 |  | note | – – – – – – – – – – – – – – – – –
label | fb690325-b569-5f74-9e9f-0006cdf26706 |  | note | VERIFYING DOCUMENTS: ITP signed
date | d3debc66-acac-5800-a133-342282f4112f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Survey Conformance
label | 48f386d9-e891-56b0-b48a-4130ebef8ea8 |  | note | REFERENCE: Section 703.15
label | d0cde9ff-d7eb-577a-8c81-2389fe200a56 |  | note | – – – – – – – – – – – – – – – – –
label | 212fa810-0edb-56b0-9be4-d673b80d497f |  | note | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
label | 908eff10-dc74-5615-bc30-e9e067eaa990 |  | note | • The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
label | a66b95da-ba89-5b84-bcf9-03285b16f05b |  | note | • Attach: Survey Report
label | 82a7a7df-3920-5950-b4d4-691a6e87a490 |  | note | – – – – – – – – – – – – – – – – –
label | b76f4d81-6966-5877-a4ea-4ce052ba65b5 |  | note | METHOD: Document Review
label | 97cf5121-552e-50aa-9217-6ed19b1e8d82 |  | note | – – – – – – – – – – – – – – – – –
label | 7529e5f3-71c8-5887-a7a1-b39569f9fefd |  | note | FREQUENCY: Completion of each lot
label | 8828a3cd-5602-550a-92fd-d30f144630a4 |  | note | – – – – – – – – – – – – – – – – –
label | b5df1611-b2a5-5d8c-a802-db7e2fb4291c |  | note | CATEGORY: WP
label | 2e8947d8-87e1-51be-908c-0efc3f9dc70d |  | note | – – – – – – – – – – – – – – – – –
label | 413e8387-5863-5a84-a547-8eb44eb11754 |  | note | RESPONSIBILITY: PE/Surveyor
label | 55e01e22-2108-5570-aaf6-e70f1496463d |  | note | – – – – – – – – – – – – – – – – –
label | 21217774-bc07-5336-a4c7-76a8dddd62cb |  | note | VERIFYING DOCUMENTS: As-built survey records
date | 8738316f-9035-5a07-aa07-353b4ac60f8b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Non-conformance Report (NCR) Closure
label | e63f7585-6d92-5e3b-8e04-0743155b9476 |  | note | REFERENCE: MRPA Quality Management Plan
label | 32fd29ee-3e7d-5842-8022-711df6208df5 |  | note | – – – – – – – – – – – – – – – – –
label | b8fd2f27-dc9e-57da-ab25-d90874e511f6 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 2dfad744-b8f5-5f37-a717-1bc72c3239f9 |  | note | – – – – – – – – – – – – – – – – –
label | 2f2539de-9689-5dc2-990a-dffd492ddb64 |  | note | METHOD: Document Review
label | 8640e715-861a-545f-95ff-4df95d71dae8 |  | note | – – – – – – – – – – – – – – – – –
label | 9af60c05-0e22-5b15-9ebc-d8cc63ad5a9d |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 8e47ec21-3b6b-50e1-8e3b-199a1965be49 |  | note | – – – – – – – – – – – – – – – – –
label | f6aee78f-c149-521d-b195-e1a5010f7292 |  | note | CATEGORY: HP*
label | 34cf2938-d5e6-535f-afc1-0477abb95559 |  | note | – – – – – – – – – – – – – – – – –
label | 752bddc7-82f6-5f35-9ce7-10e7ae754737 |  | note | RESPONSIBILITY: PE/SPE
label | abbf31a0-f7f9-5da1-91bf-ddbb7deb2b8f |  | note | – – – – – – – – – – – – – – – – –
label | 3627b31b-b6cc-5936-bfd0-ff5e60a2f675 |  | note | VERIFYING DOCUMENTS: This ITP
date | ddce8c90-b6a9-58fd-acc6-7797f8635757 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0927ae82-0d62-5e42-887e-da772c788e52 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 46f07742-a894-558c-9d53-37f89eb49b2a |  | textbox | Name:
text | 03fd852b-f6d1-5d0b-a5ba-1082c30f747e |  | textbox | Position:
date | 2302becd-6551-58f6-8a4d-cb3b25790f67 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-006-STR-RSS Walls-Material Inspection-Precast Panel | itp |  |  |  | Yes | CHK-006-STR-RSS Walls-Material Inspection-Precast Panel | 313e7df7-988c-4daa-84ae-9d7ae79f17ed
checkpoint-status |  |  | checkpoint | CHK-006-STR-RSS Walls-Material Inspection-Precast Panel
label | ac5edd73-6e20-52e4-a760-be910f5f5a0d |  | note | Document Title: CHK-006-STR-RSS Walls-Material Inspection-Precast Panel
label | 540ebf6c-f1b4-5ffa-bd28-5c706dfe9943 |  | note | Check list Description: RSS Walls-Material Inspection-Precat Panels
label | 183c6d9b-0c29-55ac-a633-bd56dbf76f80 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 409b8ea2-a030-5be0-832c-6688aca814a6 |  | note | Revision Number: 0
label | 4d1240fa-1edd-5b8c-b89e-ce6a74229fa6 |  | note | Revision Date: 10/01/2023
label | 8af45c10-8d78-5af0-bb78-197d0a445b8c |  | note | ITP created by: Victor Mira
label | 46bb26c6-1933-5609-9d26-940e889d2e6f |  | note | ITP approved for use by: Victor Mira
checkpoint-status |  |  | checkpoint | 1 - Delivery Details
label | 60273477-7ef2-5a33-a52a-6cea6585f58f |  | note | ACCEPTANCE CRITERIA:
text | baa7506c-3dcb-562e-afba-a3da00889db8 |  | textbox | Enter: Delivery Docket Number:
date | 3ca3bd2c-42c9-50c1-bdc8-d595a5201638 |  | date | Enter:Delivery Date:
text | 06e4a677-de18-51a6-a156-0eabb2acf21f |  | textbox | Enter:Element ID (s):
label | 8db3a2eb-c85b-5102-bd80-f417b34deeaf |  | note | Attach: Delivery Docket and packaging Slip
label | a4332fad-104b-54e5-996b-530be58304bd |  | note | – – – – – – – – – – – – – – – – –
label | 3bc4ddc6-e0db-558b-950b-e88d6184e6ca |  | note | METHOD: Document Review, Visual
label | 8b55c965-eaac-506b-a16c-0ec092d28821 |  | note | – – – – – – – – – – – – – – – – –
label | 4d1caa2f-51c9-5601-a3cd-d4322dc836e4 |  | note | FREQUENCY: Each Delivery
label | ec4b310f-f153-5a86-94f5-3c8bf6193598 |  | note | – – – – – – – – – – – – – – – – –
label | 6b9b74a3-a4e7-5515-b52b-6cf618f27bfe |  | note | CATEGORY: IP
label | 0064734b-03d3-5e3e-8779-0f43e392cd22 |  | note | – – – – – – – – – – – – – – – – –
label | f9c07177-761a-544e-8a1e-d1f130292c91 |  | note | RESPONSIBILITY: PE/SE
label | 6bb02a3a-5877-5afb-a869-d37d7de6fbb5 |  | note | – – – – – – – – – – – – – – – – –
label | b84c28ec-5879-5751-a16b-ea95dd744b7d |  | note | VERIFYING DOCUMENTS: This Checklist
label | c0844c2e-65d2-5205-876f-a15c003b3f82 |  | note | – – – – – – – – – – – – – – – – –
date | cf9384ff-0988-5c1a-98cb-6f3a1947ee66 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Packaging Inspection-Quantity
label | 2c939a38-81ea-54b4-ae98-7fb28c55ff70 |  | note | ACCEPTANCE CRITERIA: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
label | 8cc12b92-6a55-5e82-ab81-f44b63fb31c8 |  | note | – – – – – – – – – – – – – – – – –
label | 141aff59-f6b3-5128-b26b-6d4785953063 |  | note | METHOD: Visual
label | afa3fca9-73a8-5345-bb0b-2e506e060073 |  | note | – – – – – – – – – – – – – – – – –
label | a64cd12c-51d5-571f-837a-a3ea0fbfef7e |  | note | FREQUENCY: Each Delivery
label | 6d64a809-08f6-5d20-ab7d-af538613b6f4 |  | note | – – – – – – – – – – – – – – – – –
label | a587e540-ba9f-59f2-9c47-27ab1a6851be |  | note | CATEGORY: IP
label | 9eafcef3-cc79-52b9-8161-6b5172602033 |  | note | – – – – – – – – – – – – – – – – –
label | 7a789e1d-6cbb-5492-a211-bf553756bb2c |  | note | RESPONSIBILITY: PE/SE
label | 6c549f55-3dfd-5750-8e09-03c7c3d58739 |  | note | – – – – – – – – – – – – – – – – –
label | 2a77fc91-5c63-5d84-a935-76e99d7c4251 |  | note | VERIFYING DOCUMENTS: This Checklist
label | b1abcaa1-5043-50e3-8e03-290b58c9ac94 |  | note | – – – – – – – – – – – – – – – – –
date | bfb8e544-731d-53e7-a914-6c6a3d6ce2d1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Packaging Inspection-Delivery Contents
label | 44637807-0117-593e-ba57-40b39017b72a |  | note | ACCEPTANCE CRITERIA: Do the contents of the delivery match the freight list/packaging slip?
label | 067a42c7-5c30-56aa-b7d7-39dddfc4aa03 |  | note | – – – – – – – – – – – – – – – – –
label | a5d19921-5e2d-5e50-939b-f6e042e199ec |  | note | METHOD: Document Review, Visual
label | ce7bd541-91b4-5c90-af51-6f93d33e2154 |  | note | – – – – – – – – – – – – – – – – –
label | 9931d534-5cbd-506c-9dcb-2c465b2f6bdf |  | note | FREQUENCY: Each Delivery
label | 6de1d315-65df-5db7-a2ed-7fa067d7fa72 |  | note | – – – – – – – – – – – – – – – – –
label | 0cb8d113-dc0f-562d-969e-2935a0854b9d |  | note | CATEGORY: IP
label | f561b983-f950-5112-a612-7b162a30de06 |  | note | – – – – – – – – – – – – – – – – –
label | c86d5575-8da3-5504-beb0-37e3533f6547 |  | note | RESPONSIBILITY: PE/SE
label | b14d5a16-7534-58d3-9e70-f6ee9db5754d |  | note | – – – – – – – – – – – – – – – – –
label | cc211635-99da-5a06-b01e-90521ae4bfb0 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 47ef8d8a-53dd-55cc-9517-daea42bc373b |  | note | – – – – – – – – – – – – – – – – –
date | e733808a-0dbc-596e-aebf-f8aab43194cd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Packaging Inspection-Birth Certificate
label | 2a7681ca-5cfe-55af-b0d4-ec1b11020bff |  | note | ACCEPTANCE CRITERIA:
label | d4481b27-a6a6-5560-823c-2ef9cda2ac8a |  | note | • Is the delivery accompanied by Precast items Birth Certificates?
label | 8002dc21-1eb4-566d-accb-7276922a7e5b |  | note | • Precast components are to be marked on the birth certificate.
label | aae48f17-e47d-548e-a983-619de2b00734 |  | note | • Cast date and lot are to be marked on the birth certificate.
label | d074f40f-10ac-546c-a47f-4adf571e9edc |  | note | – – – – – – – – – – – – – – – – –
label | 2a2b9e50-7e45-5d2b-a697-e5beca6b95fb |  | note | METHOD: Document Review
label | a8c0ea8a-23e2-54b9-9cea-3d905ee9ad02 |  | note | – – – – – – – – – – – – – – – – –
label | 3d08238d-47d4-545b-b372-bb673060895d |  | note | FREQUENCY: Each Precast item
label | 94450fb1-4c26-53a6-ba09-55771f8e0ed0 |  | note | – – – – – – – – – – – – – – – – –
label | 96ff9385-c26e-5c92-957e-6d8eb8eb70df |  | note | CATEGORY: IP
label | d6a9e2ec-da0b-5643-ab2a-26a7ed71d4db |  | note | – – – – – – – – – – – – – – – – –
label | e1deaa13-56ea-5955-b219-8ad681673d91 |  | note | RESPONSIBILITY: PE/SE
label | c62e72d8-61ba-5575-b7c7-2ee06411258a |  | note | – – – – – – – – – – – – – – – – –
label | 408bf047-21bf-5139-9c5d-0e1f19264394 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 0ffaf530-3fff-5b03-b707-b9a3819ebfa2 |  | note | – – – – – – – – – – – – – – – – –
date | a90ed40d-6af4-5d67-bb71-5138a8fcbaad |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Packaging Inspection-Transport
label | 56ecfda4-718a-5681-b017-b631157b84c7 |  | note | ACCEPTANCE CRITERIA:
label | 6b59c57c-23a9-5d9c-9798-f191b7ae612d |  | note | • Is the condition of packaging acceptable.
label | 8ee2cecb-6f4c-54cd-9155-bed05c5f53d3 |  | note | • Precast items are protected from damage during the transport
label | 322e8bdf-b70d-5273-a8d8-2763506e3764 |  | note | – – – – – – – – – – – – – – – – –
label | ff67cd7f-e168-5370-adc4-588c98d5a1bf |  | note | METHOD: Visual
label | 1acf9516-e1f8-5012-8802-dee4e265109b |  | note | – – – – – – – – – – – – – – – – –
label | 83c7b5f1-47d9-540e-8c4e-1d0fc1a34c9b |  | note | FREQUENCY: Each Precast item
label | b4283930-0b52-5a64-9756-34548f987351 |  | note | – – – – – – – – – – – – – – – – –
label | 5268a7c4-9515-5204-8d46-73a007105002 |  | note | CATEGORY: IP
label | d6882759-d191-56e1-ade0-14a05483af07 |  | note | – – – – – – – – – – – – – – – – –
label | 4591baa1-e954-5650-8c34-eddc93e2564d |  | note | RESPONSIBILITY: PE/SE
label | 8116e11c-008f-5688-afc9-3cb491e8c5b9 |  | note | – – – – – – – – – – – – – – – – –
label | a0740bbb-e6dd-5b57-acb9-bff3729489a0 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 2dccbe44-7cb3-5dc7-9ac3-a20ebe8d74e3 |  | note | – – – – – – – – – – – – – – – – –
date | 9f52efd2-21ba-5818-b4fd-75674ccacc36 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Fault IDs:
label | cef238d6-5c6f-550c-88a7-58e004654303 |  | note | ACCEPTANCE CRITERIA:
label | 4f48e937-57df-57b7-9c1e-fc165e780826 |  | note | For each precast type delivered, check for the following:
label | a59cc754-7e6a-51a6-8f4e-77d313007bfc |  | note | 1 - Identification markings match the panel type
label | d522f9c2-362a-580a-b0c7-faf17fd6bfe8 |  | note | 2 - Panels fabricated as per drawings
label | 74ec8e7e-319f-56d5-a6a0-cbe7db10eb71 |  | note | 3 - Cracks
label | 55b6f328-5801-593b-9463-06399c5906dc |  | note | 4 - Spalling/Damage to concrete surface
label | 812157e1-ca2c-5a54-99d8-1d647fd37775 |  | note | 5 - Exposed Reinforcement
label | 5ae7f3a3-4d52-5c54-a05d-8390778b92db |  | note | 6 - Damage to Anti-Graffiti coating
label | a526de2b-9271-5cd5-91b3-89203110cbe9 |  | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
label | 2965dd20-3081-5efd-85ea-3f43d9233e8a |  | note | – – – – – – – – – – – – – – – – –
date | 6d46abf9-9d1e-53cf-8b0e-51eb86ef55a1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 1
label | a8a4a087-c64e-5618-9144-dd4cddb1e805 |  | note | REFERENCE: Item 6 on this Checklist
label | c3fa6549-a783-546c-a10a-cf3df1e21627 |  | note | – – – – – – – – – – – – – – – – –
label | 9275fc6a-f433-5c5d-83f5-130113b212a3 |  | note | ACCEPTANCE CRITERIA:
label | 813e2a2f-99f7-58c9-adbd-0622532f8c73 |  | note | For Each Precast type delivered:
text | 9df27243-4a23-50c6-afe9-d34dada6ccd1 |  | textbox | Enter: Panel Identification:
text | 16e93610-a04c-521c-8b4d-303bfd082d86 |  | textbox | Enter: Quantity:
text | c66c2cc0-87d7-569a-be49-eaf51ad9553f |  | textbox | Enter: Fault ID if any:
label | 1108a98d-a019-5750-a215-5532512f1799 |  | note | – – – – – – – – – – – – – – – – –
label | 0f148067-53ec-5a73-88d0-a490f9a4accf |  | note | METHOD: Visual, Measure
label | 425734c6-f35a-5d49-b16f-b7df4e6a7934 |  | note | – – – – – – – – – – – – – – – – –
label | d474eefa-34ed-5822-ac17-b49994d3b3b0 |  | note | FREQUENCY: Each precast type delivered
label | d2349433-dbd4-5d83-9680-eff2c74bc8a6 |  | note | – – – – – – – – – – – – – – – – –
label | ad01b4e5-9788-54eb-b04a-0691bf1a9298 |  | note | CATEGORY: IP
label | 932b5eee-d44d-51fa-92dd-7d5048174bab |  | note | – – – – – – – – – – – – – – – – –
label | b7b394c0-7e37-5b03-b6d3-b25920d0010f |  | note | RESPONSIBILITY: PE/SE
label | 6f53b868-9796-593a-a2fb-773ec9ea673e |  | note | – – – – – – – – – – – – – – – – –
label | 5feaa888-10d4-5854-91a7-d97b60fa2a78 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 4f62c0da-4de9-58ea-b629-b7f42523dcaf |  | note | – – – – – – – – – – – – – – – – –
date | 4006c81d-15dc-5548-bfcb-54679a79b22f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 2
label | f07aeae9-7223-55f2-ae87-4a40daea0545 |  | note | REFERENCE: Item 6 on this Checklist
label | 6a055545-62cb-5c4a-b6de-95767e0932cf |  | note | – – – – – – – – – – – – – – – – –
label | 1978fc90-3763-5606-87aa-fcd2b8708603 |  | note | ACCEPTANCE CRITERIA:
label | ef62d64f-d158-5a9c-992b-8e1f0729d9b7 |  | note | For Each Precast type delivered:
text | 0ea5f888-a04d-5d0b-90ce-2348047d3300 |  | textbox | Enter: Panel Identification:
text | 5204f43c-feec-5cb8-b41b-2258340d0165 |  | textbox | Enter: Quantity:
text | 952bf077-dbc6-54dc-b294-42dd17fbec2f |  | textbox | Enter: Fault ID if any:
label | 71fbb545-7c18-53fc-8a6f-92b5b29049b2 |  | note | – – – – – – – – – – – – – – – – –
label | b6519440-e62d-5beb-8da5-d9310f3cac56 |  | note | METHOD: Visual, Measure
label | d62ac89c-231c-57cb-bbda-4815fd2c64c0 |  | note | – – – – – – – – – – – – – – – – –
label | 11c7e122-b43b-58ec-b540-ea2925066e7d |  | note | FREQUENCY: Each precast type delivered
label | 4ae7d4f0-9c6d-5286-96f6-b117d71879a7 |  | note | – – – – – – – – – – – – – – – – –
label | 7fa11b9e-ca58-59d9-b1d0-4f1804805569 |  | note | CATEGORY: IP
label | 1ca45c9f-10f4-501b-aedd-1bcd8772a241 |  | note | – – – – – – – – – – – – – – – – –
label | d9fa76c6-3ba1-5653-b91e-7562dd0c75c0 |  | note | RESPONSIBILITY: PE/SE
label | 5e1ddcca-44cd-5d63-aef6-e0b87ecc8f52 |  | note | – – – – – – – – – – – – – – – – –
label | b3be098b-970b-5636-b912-ff7a666146a3 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 9eeaf66e-3bb0-5f7d-8813-b1984d15a14b |  | note | – – – – – – – – – – – – – – – – –
date | 0f4dd411-229d-5716-9ba0-4d0b55d9e68b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 3
label | 2d87ef1c-8f60-5c7f-864b-17728689403b |  | note | REFERENCE: Item 6 on this Checklist
label | 790ca294-6b64-56a6-a12f-c0656767da4e |  | note | – – – – – – – – – – – – – – – – –
label | 6b5345a7-ff31-5419-ac33-24d8f80a847a |  | note | ACCEPTANCE CRITERIA:
label | 8e0d1eb6-d670-5fb7-836d-df17d6fa9cac |  | note | For Each Precast type delivered:
text | a913e891-6641-5028-b4ef-b66f9f2aa94d |  | textbox | Enter: Panel Identification:
text | 41d2ff53-0760-586e-bb74-8417af85be48 |  | textbox | Enter: Quantity:
text | 9e7ff219-81c8-575d-a2fb-53b2adfe6cc9 |  | textbox | Enter: Fault ID if any:
label | 7627461e-6f66-519e-a773-ee4478b89ef1 |  | note | – – – – – – – – – – – – – – – – –
label | 3e096089-5811-52f4-bdaf-58b2cd047136 |  | note | METHOD: Visual, Measure
label | 3cbea1cc-4f27-5a04-9549-93a1986c20fd |  | note | – – – – – – – – – – – – – – – – –
label | 1387ba6c-268f-5ead-ae8d-a85578a32c38 |  | note | FREQUENCY: Each precast type delivered
label | 815cbfb0-50d0-59fc-b772-090087d3b088 |  | note | – – – – – – – – – – – – – – – – –
label | e2c1c86b-0e35-529f-bc4f-9703a924dfcc |  | note | CATEGORY: IP
label | c0abfb4f-9956-5eea-8e57-c4353d798ea9 |  | note | – – – – – – – – – – – – – – – – –
label | 10a66208-b658-5abe-9b58-1c8f185d2c20 |  | note | RESPONSIBILITY: PE/SE
label | 2b2282bf-106a-53f7-928d-2172be60b736 |  | note | – – – – – – – – – – – – – – – – –
label | bbda3e97-eaca-59fc-956c-e1bdf549f50f |  | note | VERIFYING DOCUMENTS: This Checklist
label | f8f0f1de-c021-554a-8317-49ff73c83163 |  | note | – – – – – – – – – – – – – – – – –
date | 6bbfa326-4c76-56d4-852a-3dc49a787749 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 4
label | 354db6dc-6974-5527-8fe9-1761b182816c |  | note | REFERENCE: Item 6 on this Checklist
label | 49482c2f-45f4-58e8-bbc4-e9262dc95407 |  | note | – – – – – – – – – – – – – – – – –
label | 997abe63-2d43-5f18-be6f-0a94fc5eea9b |  | note | ACCEPTANCE CRITERIA:
label | 312a903e-a072-5ea7-9697-c960e018cfa5 |  | note | For Each Precast type delivered:
text | da2c7c98-7ade-5a67-9dfc-6db2206cc420 |  | textbox | Enter: Panel Identification:
text | 10cf4eb6-3405-5676-b0b2-60762439a730 |  | textbox | Enter: Quantity:
text | f90fc5d1-e2e3-5d95-a6b7-3e69a5a7ce48 |  | textbox | Enter: Fault ID if any:
label | 5f48a64b-7e1e-59d6-8d0a-d4e9e878021d |  | note | – – – – – – – – – – – – – – – – –
label | cd46ec4e-c38e-5876-91c3-8114ebf0f307 |  | note | METHOD: Visual, Measure
label | 32cdd89c-7559-55ad-b6c4-d109068b566d |  | note | – – – – – – – – – – – – – – – – –
label | 8219af12-3336-5a70-a271-0f83a2741fe8 |  | note | FREQUENCY: Each precast type delivered
label | 9857d3f0-1159-52cd-9ad7-19c4f4cab54e |  | note | – – – – – – – – – – – – – – – – –
label | 56b96a14-5b78-5714-9dfd-0e8a381eded8 |  | note | CATEGORY: IP
label | 5549fc18-a277-560f-b0c4-509d13afdbba |  | note | – – – – – – – – – – – – – – – – –
label | 427a5cee-4d45-5074-a58a-d1f52abb5c07 |  | note | RESPONSIBILITY: PE/SE
label | 72148379-34cb-53c4-8d34-8a90d5e0cc7d |  | note | – – – – – – – – – – – – – – – – –
label | 3d881835-44b8-589e-8466-8a7469492952 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 8e880aa1-e27a-58aa-ad11-68b34950efa1 |  | note | – – – – – – – – – – – – – – – – –
date | ed9caf5a-6463-5e3d-aa01-f50aa535ecca |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 5
label | 47888e0d-d607-5104-9b75-47c945ee2270 |  | note | REFERENCE: Item 6 on this Checklist
label | b36823e1-2f11-5d72-83f0-82c81623552b |  | note | – – – – – – – – – – – – – – – – –
label | 04d0e2ca-3844-5cc8-9fa5-cfa4e1c5b83e |  | note | ACCEPTANCE CRITERIA:
label | 43b40a23-44f8-550d-a1f8-8730597c762d |  | note | For Each Precast type delivered:
text | 0abf1b8e-05e5-5830-8835-b7e2375a64d3 |  | textbox | Enter: Panel Identification:
text | cc9f462a-6d43-5004-a154-079841b578d8 |  | textbox | Enter: Quantity:
text | ae4d8888-70e7-5cd3-a39d-b071160a0469 |  | textbox | Enter: Fault ID if any:
label | 341c7ab1-e6bc-5432-b05a-b89e39c9ba6a |  | note | – – – – – – – – – – – – – – – – –
label | 249776ee-0a73-577d-958c-f3cb013335b5 |  | note | METHOD: Visual, Measure
label | bda34787-ad9e-5329-8c6f-c323e800d32c |  | note | – – – – – – – – – – – – – – – – –
label | 90d403d9-19ca-5c51-94ab-f83737f775f0 |  | note | FREQUENCY: Each precast type delivered
label | cf35e0de-2d92-5a93-9060-b6a0270a4f20 |  | note | – – – – – – – – – – – – – – – – –
label | c4e24de9-b78d-5b73-b2ea-d9058b4f8897 |  | note | CATEGORY: IP
label | 7db5d3c8-13ef-54fb-bdf9-47c54d1bcc36 |  | note | – – – – – – – – – – – – – – – – –
label | 527055f2-ee0d-5507-80cb-4206d0058f24 |  | note | RESPONSIBILITY: PE/SE
label | 460ecc90-04ed-5102-a7eb-1b1ea1237cc7 |  | note | – – – – – – – – – – – – – – – – –
label | 229ac313-57e6-5d4a-a083-d244e16fd660 |  | note | VERIFYING DOCUMENTS: This Checklist
label | baea465d-b7f0-5602-a5fb-a21847896353 |  | note | – – – – – – – – – – – – – – – – –
date | 055cd4cb-c1ad-5841-a4b6-f769b4750f49 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 3f78dd43-87cc-5048-8b2a-748801709492 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | fc6eb294-38c6-5f28-b8df-227c405d5b55 |  | textbox | Name:
text | b95ff21b-3cda-5b53-b6ee-9d0d60d2db9c |  | textbox | Position:
date | d77b3e99-6ffc-5997-8edd-b221a471e9ae |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-064-CIV-Camms-Subsoil Drainage | itp |  |  |  | Yes | ITP-064-CIV-Camms-Subsoil Drainage Rev 0 | 328594a1-b038-4632-841d-abcb4423fa37
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 223b0d2c-3ad1-56b8-80ec-58bb7ad19633 |  | note | Document Title: ITP-064-CIV-Camms-Subsoil Drainage
label | 30270e79-b3d3-5fa1-9137-5ecf3bfc75bd |  | note | ITP Description: Camms-Subsoil Drainage
label | 6360cc78-4d34-59db-b37d-8f4bcfed3fe2 |  | note | ITP number: 064
label | 0617ff07-8f9a-5a90-844a-a8e69c7d0acb |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 697068eb-20fc-5c24-8cbf-77ff499c3014 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 437327fe-7dad-5a00-9b7d-7fc2524cde01 |  | note | Revision Number: 0
label | 17308af7-7dd5-5664-b16f-4d6c910c3a6f |  | note | Revision Date: 25/08/2023
label | f85bc733-f5c6-5b58-872c-6e91ec6046a4 |  | note | ITP created by: Victor Mira
label | 9111f9c4-4586-5e75-b95c-6d6770173e82 |  | note | ITP approved for use by: Victor Mira
label | 49779406-2028-5ad9-9b4a-afa5bd748972 |  | note | 1.1 Non Dependent
label | ae0ba8ff-c579-5296-9cb1-72c1c9f25140 |  | note | Reference: VicRoads Section 702 (May '19)
checkpoint-group |  |  | section | Preliminaries-Material
checkpoint-status |  |  | checkpoint | 2.1 Pipes
label | ad320cd1-d513-5770-baf2-1d5692761d82 |  | note | REFERENCE: IFC Drawings VR 702.04
label | 7888bd4e-e524-5f18-b2aa-e002ad6298a2 |  | note | – – – – – – – – – – – – – – – – –
label | b2e1e87b-67b3-510c-aba8-1ad86478de7a |  | note | ACCEPTANCE CRITERIA: All subsurface drainage shall be Category 1, 100mm DIA Class 1000 Perforated Plastic Pipe. Perforations shall be max 1.5mm and minimum length of 150mm per sqm
text | e74f9856-fe8d-54aa-997d-6618c7e1bd2d |  | textbox | Reference: Material approval in Teambinder:
label | 69dedc43-6a8c-560d-a486-0086769d178a |  | note | – – – – – – – – – – – – – – – – –
label | 3a505534-3950-57bc-8423-c11efd6af2bd |  | note | METHOD: Verify, Document Review
label | 29384606-94e0-52e4-bb83-2a0d82be92ae |  | note | – – – – – – – – – – – – – – – – –
label | e9cbfeb1-f69f-5fc5-847d-bac3f4bce198 |  | note | FREQUENCY: When applicable
label | 711c5ad3-d104-5803-9466-fae3980991d1 |  | note | – – – – – – – – – – – – – – – – –
label | 211bd6c6-3f4e-51ab-9c81-b9ad224d9d11 |  | note | CATEGORY: HP
label | 8df55bae-1372-567d-b7e2-336cdb907da0 |  | note | – – – – – – – – – – – – – – – – –
label | c56baebe-e9d8-52c5-a1cb-e7f5b47227b9 |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 210ff46d-fab4-5878-b5e6-6d9a644d8f5b |  | note | – – – – – – – – – – – – – – – – –
label | 0445998d-32b6-5dc3-b39e-ad1b07397700 |  | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | 97b0c6be-fce0-5181-8d56-da57d139e228 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Granular material: Filter Sand
label | 392a48c5-453f-52e2-a206-0cbda7d32509 |  | note | REFERENCE: IFC Drawings VR 702.05
label | d671c00e-0e67-5951-a044-46666a8b242a |  | note | – – – – – – – – – – – – – – – – –
label | 845bd644-d556-58cf-affb-84051d8308a9 |  | note | ACCEPTANCE CRITERIA: Filter sand to be Grade A4 and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
text | 418322fe-ee6f-569e-8374-eb8d5a59a6f2 |  | textbox | Reference: Material approval in Teambinder:
label | 4993dbaa-31ef-5985-84f2-67ef4e782d57 |  | note | – – – – – – – – – – – – – – – – –
label | d292d8f9-63fc-5cee-9157-b0243cee16a9 |  | note | METHOD: Verify, Document Review
label | 7bc58052-bc09-5074-b91d-35239ff0d606 |  | note | – – – – – – – – – – – – – – – – –
label | d3374012-141c-5986-b6ec-0189225139a7 |  | note | FREQUENCY: When applicable
label | f4c44e8a-ad8c-5a8b-9d66-0298ae97e17b |  | note | – – – – – – – – – – – – – – – – –
label | 7c3fff35-12d4-5ea0-882d-e461bb3ceecf |  | note | CATEGORY: HP
label | 6f3f33cd-86e3-57ba-a085-2783b130c844 |  | note | – – – – – – – – – – – – – – – – –
label | 875d8957-e9b5-5395-9e8b-50d18d687a6f |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 9c9a9703-27ff-506f-a892-7cf12dcab1a5 |  | note | – – – – – – – – – – – – – – – – –
label | 5adf73e8-8cd4-591f-bec7-d925be689ec5 |  | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | 7ce70ac0-27c8-5b0f-81e3-501ca9caef44 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Granular Material: No Fines Concrete
label | 6aacd5f3-cb35-5d9e-9394-3746fef96829 |  | note | REFERENCE: IFC Drawings VR 702.05 (e)
label | a21ee16a-ebc1-5af0-b3f9-5192d22fc0de |  | note | – – – – – – – – – – – – – – – – –
label | a8804812-0d2e-53bd-8aff-d9df10522c75 |  | note | ACCEPTANCE CRITERIA: No Fines Concrete: Shall comply with 702.05 e)
text | eb1c8c7d-2fb6-5c05-bf72-043a530a30b2 |  | textbox | Reference: Material approval in Teambinder:
label | 54b8aaa7-ff18-51e6-912d-f1ab7255b292 |  | note | – – – – – – – – – – – – – – – – –
label | c1b8771f-4111-5a6a-a3cb-968a51bb37b5 |  | note | METHOD: Verify, Document Review
label | b07d1228-19d8-5610-bf62-1d5076c6ea24 |  | note | – – – – – – – – – – – – – – – – –
label | 4cc1d15c-6ec6-5ef9-924d-f9b6f8c09f14 |  | note | FREQUENCY: When applicable
label | 10217def-f238-5874-ac6e-f0ecda99dbba |  | note | – – – – – – – – – – – – – – – – –
label | c7643d10-6b37-543d-940a-a6e011927c15 |  | note | CATEGORY: HP
label | 778a2521-88e2-5111-b370-1874d6f1fc97 |  | note | – – – – – – – – – – – – – – – – –
label | dd24add1-d439-59cb-a74f-1f08617f9508 |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 8a8dae74-bb6d-5623-b706-b9e15ac232bb |  | note | – – – – – – – – – – – – – – – – –
label | 0c42065f-dbde-5afa-9964-e7180171f909 |  | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | 0504269c-fcf7-5608-b075-e64ea6fb90a8 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Geo textile
label | 81778578-aa6c-58ce-9fb6-656220350163 |  | note | REFERENCE: IFC Drawings VR 702.06
label | 3fe6ea64-d722-570d-b169-50845b8c92ba |  | note | – – – – – – – – – – – – – – – – –
label | 321385ae-d98d-5867-9b91-d07521c5b949 |  | note | ACCEPTANCE CRITERIA: Geotextiles: Shall comply with table 702.061
text | 3a2898e4-f608-5921-b2d2-fbde1acec35f |  | textbox | Reference: Material approval in Teambinder:
label | 36d11dfb-13b0-52b3-96d0-c63d760dffdd |  | note | – – – – – – – – – – – – – – – – –
label | cd917559-d63c-58da-af75-9f8e296cf5d5 |  | note | METHOD: Verify, Document Review
label | ae1937ef-cb80-5552-860d-7f1b8b3f4f4e |  | note | – – – – – – – – – – – – – – – – –
label | c2740d06-0f55-5c37-99f1-0884ede507a5 |  | note | FREQUENCY: When applicable
label | d24dbe77-1263-5da2-82ac-1aebc7969538 |  | note | – – – – – – – – – – – – – – – – –
label | 87d3e67d-4cb3-524e-92c1-72bba099bb96 |  | note | CATEGORY: HP
label | a775694e-b20a-5b0d-b2f2-917c59012904 |  | note | – – – – – – – – – – – – – – – – –
label | 59682769-8944-5c75-9296-179237625c19 |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 8bde81c3-abb2-5dcf-93c9-c9cde23ae97a |  | note | – – – – – – – – – – – – – – – – –
label | a03b1452-3167-5279-8152-dcc423eea80f |  | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | 67ce31e4-1a38-507b-9b91-bde456e2585c |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Subsurface Drain Pits
label | 7166ec74-842a-52c0-8c9e-60414b75784b |  | note | REFERENCE: IFC Drawings Section 702.04, 702.05 & 702.06
label | b8cc41f4-2546-54b4-a721-f2e74fb2e680 |  | note | – – – – – – – – – – – – – – – – –
label | 48f47bcb-5d10-5e9f-bc6b-037e896c121d |  | note | ACCEPTANCE CRITERIA: Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
label | 61dac00d-25e2-535a-b2fb-bfc8bd7ea1bf |  | note | Pit Lids:
label | 81a9cebb-de18-58e4-9eec-e941ae8a2f5a |  | note | ○ Type M3 circular lid (as per SD 1051) for Type S1 pit
label | a37f48c0-e8e2-5c36-acd5-58c363a40468 |  | note | Flushout risers:
label | 03354c30-8189-5a95-ac65-44bbf1bbbc29 |  | note | ○ As per SD 1631
text | ed03f129-a18d-5fc0-9227-4205581618b9 |  | textbox | Reference: Material approval in Teambinder:
label | fddb66f1-20ec-5d56-b882-159f66e379ed |  | note | – – – – – – – – – – – – – – – – –
label | b1dbf31b-119d-5c70-b0bf-cceeff3b1687 |  | note | METHOD: Verify, Document Review
label | 70cb9710-32d7-501c-b3f2-9d5ffabf6773 |  | note | – – – – – – – – – – – – – – – – –
label | bb405c9d-2d9a-533d-8512-99ef0c46642d |  | note | FREQUENCY: When applicable
label | 648780d4-7ebd-5c2e-b87b-8e04896dc93a |  | note | – – – – – – – – – – – – – – – – –
label | 5a3debd1-da4a-58d4-9a86-77b04e3bfc3f |  | note | CATEGORY: HP
label | 685308de-3efb-5ac8-a304-cf5fcca5be7e |  | note | – – – – – – – – – – – – – – – – –
label | e46f8b0b-56cd-54dc-8e52-7139f0f2d744 |  | note | RESPONSIBILITY: PE/Nominated Authority
label | f48488b7-4bf6-5ea2-a036-57462b762266 |  | note | – – – – – – – – – – – – – – – – –
label | 6c4ed988-6060-5ec5-9006-29a8c8df788e |  | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | b51a6027-a6d1-583b-b8a4-850b7ea42e5c |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set Out
label | d1b1cf07-5142-5c50-b589-2408fd53c900 |  | note | REFERENCE: Section 702.03
label | f44f36c1-f320-5faa-8983-75ad1685264a |  | note | – – – – – – – – – – – – – – – – –
label | f883e6e7-1fe8-5075-9c3a-c711e35f456b |  | note | ACCEPTANCE CRITERIA: Survey to set out Subsurface Drainage line.
label | 20561308-5d86-56bf-aeeb-0081c8d4b164 |  | note | – – – – – – – – – – – – – – – – –
label | 11fb2c58-10a5-579b-8423-d2b68c306aea |  | note | METHOD: Visual inspection
label | cb703ecd-abf4-5ef4-8976-cd89e4ef2373 |  | note | – – – – – – – – – – – – – – – – –
label | b2ac7d41-6f5d-5d2d-a58d-431ab2bb0fed |  | note | FREQUENCY: Each Lot
label | 514e65cf-c49a-5211-a9cd-df5ccd4dc7b5 |  | note | – – – – – – – – – – – – – – – – –
label | 82701a79-bb10-5d63-8875-d401f5bc6121 |  | note | CATEGORY: HP*
label | 8b2df9ba-60ef-590b-9a13-675ab9ca41d8 |  | note | – – – – – – – – – – – – – – – – –
label | 15772541-a9f0-5d60-abba-ecbc497f231b |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 527bab38-b4fa-54fb-81ef-80add5ce2683 |  | note | – – – – – – – – – – – – – – – – –
label | 93d6e0ff-7dd0-56d6-a355-ed34864b7842 |  | note | VERIFYING DOCUMENTS: This ITP
date | c7f15d8e-93a1-58ca-b207-e46ab550a9f6 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Trench Excavation
label | 661fe79b-16e7-5855-bf71-ed761b39edd4 |  | note | REFERENCE: IFC Drawings Section 702.08
label | 11a8261d-b74e-59f6-b5ae-532101d92d83 |  | note | – – – – – – – – – – – – – – – – –
label | 67c42339-00cb-5a4c-bd3c-45fc63c843ff |  | note | ACCEPTANCE CRITERIA: The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
label | 5e8c7609-1033-50d7-bc0a-086b6289e61e |  | note | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
label | 86c9f432-9bf6-59de-87b1-d45d9c6d8b0b |  | note | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | cd4a7fef-7ad9-582d-bd0d-9e6cfcd4d342 |  | note | ○ Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile.
label | d681045b-d1ea-5597-8e60-629dc51bdff0 |  | note | – – – – – – – – – – – – – – – – –
label | 17094f5f-d90a-57cf-904c-58ae93d913c1 |  | note | METHOD: Visual Inspection
label | 324a6958-9bbd-5dcb-a414-194ae7bb80f6 |  | note | – – – – – – – – – – – – – – – – –
label | 46498051-723d-5876-9b3d-291b24f79c59 |  | note | FREQUENCY: Each lot
label | f4ad3f2c-bd58-54da-97ea-e22958a49308 |  | note | – – – – – – – – – – – – – – – – –
label | 54c487ba-0cc9-586e-b883-9e28779e178b |  | note | CATEGORY: IP
label | ae335c79-afb6-5302-a970-7fc93d15b6d9 |  | note | – – – – – – – – – – – – – – – – –
label | c30f26ee-7d67-5160-8572-31e105142253 |  | note | RESPONSIBILITY: SE
label | a649b776-45a0-5d51-82d1-6beb46204955 |  | note | – – – – – – – – – – – – – – – – –
label | 7350bad7-51da-5ab4-b28e-9dff8b45ac42 |  | note | VERIFYING DOCUMENTS: This ITP
date | 29b8e8ba-b9f2-5248-82f0-0d622823bc34 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Trench Excavation
label | ebb7dc59-9356-5318-9cc2-7433d7b61021 |  | note | REFERENCE: Section 702.08
label | 90ead8bb-4464-5433-b927-b96bc032882f |  | note | – – – – – – – – – – – – – – – – –
label | 94252925-0b78-54d3-a88b-14ae542ead41 |  | note | ACCEPTANCE CRITERIA: The base of the trench shall be inspected to verify compliance with the requirements in VR 702.08 prior to placing bedding in completed excavations. The Superintendent shall be notified at least 24 hours prior to the inspection.
label | e1d4c714-d07d-58b2-b3a6-40491685a9f6 |  | note | – – – – – – – – – – – – – – – – –
label | d0de1a42-45a3-5ee2-a109-761f033c74ab |  | note | METHOD: Visual Inspection
label | 3470fb73-1c29-5eb2-ac48-badf7c662f20 |  | note | – – – – – – – – – – – – – – – – –
label | c8c76721-d00b-57af-87cd-284a0b88b909 |  | note | FREQUENCY: Each lot
label | 451d11d0-beaf-576b-9d4b-4a1b86629cd9 |  | note | – – – – – – – – – – – – – – – – –
label | 92540288-1ceb-54bf-a9de-9e3402372714 |  | note | CATEGORY: HP
label | 84e44b67-17b5-516d-8747-bbe7d4201b05 |  | note | – – – – – – – – – – – – – – – – –
label | ae75bb50-18f9-5952-8e32-3dfebe50f722 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | fff89529-b6c7-58a3-af96-324148b1b121 |  | note | – – – – – – – – – – – – – – – – –
label | 9a213ecf-92cc-56d7-841c-7f6dc9d51be5 |  | note | VERIFYING DOCUMENTS: Nominated Authority sign off This Line
date | 9d110091-7947-5949-8432-a318b90b21c3 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 Placement of bedding
label | 6352ef75-873f-5913-8497-823d0d2e0a14 |  | note | REFERENCE: Section 702.09 c)
label | f2141dbd-a2cc-500d-81db-02ff8c8d2496 |  | note | – – – – – – – – – – – – – – – – –
label | 4275028d-5876-550b-95cf-c9418b6772b7 |  | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | 7ef4c7b9-cfab-5408-b070-f24b9c901329 |  | note | – – – – – – – – – – – – – – – – –
label | 535514df-bd81-5752-9c58-9dae8862722d |  | note | METHOD: Visual inspection
label | b0880e88-bcf2-548b-9cf4-1779d0a51bf2 |  | note | – – – – – – – – – – – – – – – – –
label | 2163b7c0-16f2-5026-b77e-28d77486bebf |  | note | FREQUENCY: Each lot
label | 44aaa6bf-55df-565f-8633-99c19e737be9 |  | note | – – – – – – – – – – – – – – – – –
label | cfa4987c-b334-5bbd-a603-bb44901c36e5 |  | note | CATEGORY: IP
label | 910c0b86-db75-5ca5-a46d-9ec1a1a7abc7 |  | note | – – – – – – – – – – – – – – – – –
label | 7c31dfb0-3dd9-5346-8f4f-df6f0d4477b3 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | efa7d249-c6dc-5347-b357-222c0b771f31 |  | note | – – – – – – – – – – – – – – – – –
label | 7adcd9de-2990-5b65-b65a-b5bd174d21c6 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3e4fd575-d9e9-517d-a996-ee24412ae4f4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Traficable Pavements
label | 83f79c6b-895f-5f7d-87f8-733597ea8980 |  | note | REFERENCE: IFC Drawings SD 1601 EDCM 201
label | 592ec90a-ead9-519e-aae0-748e7cc3b373 |  | note | – – – – – – – – – – – – – – – – –
label | 1beb45e8-8c35-5242-98f4-2ff0d4915883 |  | note | ACCEPTANCE CRITERIA: Choose pass when applicable. All Subsurface drains located within trafficed pavement shall be Type 2 with no fines concrete filter with filter fabric wrapped around the trench in accordance with SD 1601 and EDCM 201
label | 8d80a685-9c7f-514c-9e51-c0e0f0ef599b |  | note | – – – – – – – – – – – – – – – – –
label | 7bad1aca-7629-563b-a2cb-7810f9285333 |  | note | METHOD: Visual inspection
label | ac4d1809-780b-55b4-9b8f-6f18bf8dad3f |  | note | – – – – – – – – – – – – – – – – –
label | 7b915726-e0f8-5ab3-93ba-16773a4719e2 |  | note | FREQUENCY: Each lot
label | 142e4ebf-012b-5c00-8f2b-8ff07c426c54 |  | note | – – – – – – – – – – – – – – – – –
label | 3029b127-23dd-5a95-82ad-273c0a48d166 |  | note | CATEGORY: IP
label | cb09e6c3-ca04-56f6-a0e3-bafd58aa8b20 |  | note | – – – – – – – – – – – – – – – – –
label | 1e5e72be-ec78-5309-b092-22cc78e415fd |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 864072a7-3b4e-5511-8bc9-380565994add |  | note | – – – – – – – – – – – – – – – – –
label | 1bf402fc-5ca6-54b4-8531-b9215df55373 |  | note | VERIFYING DOCUMENTS: This ITP
date | 807ba1e5-fd1d-5761-9bf0-e36ea29360b8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Outside trafficable pavement
label | 02309151-6e19-5fe8-929d-4e461be58099 |  | note | REFERENCE: IFC Drawings SD 1601 EDCM 201
label | 1de0aa46-781b-56f0-9071-7a452926dc93 |  | note | – – – – – – – – – – – – – – – – –
label | 225889c8-3e7e-5370-bc4e-b0be3144b0f7 |  | note | ACCEPTANCE CRITERIA: Choose pass when applicable pavement drains outside trafficable pavement shall be type 3 with grade A4 Sandfilter and Geotextile wrapped around the pipe with minimum 150mm lapping length
label | e349a62d-922f-5bf3-863d-ee570df53eaa |  | note | – – – – – – – – – – – – – – – – –
label | 5db7c435-422e-5c7d-972e-49d6d2431568 |  | note | METHOD: Visual inspection
label | caa6096a-3a32-5973-9611-9cd762e37ed0 |  | note | – – – – – – – – – – – – – – – – –
label | c377d37c-0926-51c4-91fa-b2b8209e134e |  | note | FREQUENCY: Each lot
label | a19e93cf-0666-58cb-aa11-1670f53e38fb |  | note | – – – – – – – – – – – – – – – – –
label | f79651bd-af77-50ee-8632-459a2c6cf953 |  | note | CATEGORY: IP
label | 0d1988a7-7fc8-57e5-9b46-dfe7c03d0311 |  | note | – – – – – – – – – – – – – – – – –
label | 61b9990e-9a74-5d75-9606-d3473c81d2bc |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 19c18cc8-c938-5435-8432-b3453851a6b3 |  | note | – – – – – – – – – – – – – – – – –
label | f5509942-6160-5f9a-9a72-cc22fae19087 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1a26727d-aed3-5d78-80bd-071d1276ad94 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Pipe and Geotextile Installation (if required)
label | 7be27a2a-34e9-53f0-a7a8-3c7ce33314bf |  | note | REFERENCE: Section 702.03, 702.09
label | 8ce6cc77-ad41-5c1f-81e9-50cb4029f5b3 |  | note | – – – – – – – – – – – – – – – – –
label | 368ef659-8ba2-5231-a250-5330e9afa726 |  | note | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped (Mininmum 150mm lap)
label | 9e6492b8-9a01-5266-86f2-7d04d8829209 |  | note | – – – – – – – – – – – – – – – – –
label | 4c673f60-d54b-5f3a-85ac-564022ac5948 |  | note | METHOD: Visual inspection
label | 7a66df37-82ac-5d62-babf-9724bc9ec498 |  | note | – – – – – – – – – – – – – – – – –
label | 42b54d67-9b58-5330-857d-3e97bc752a9e |  | note | FREQUENCY: Each lot
label | 5f0af623-0bb4-54ed-95d3-fdeba88f9a92 |  | note | – – – – – – – – – – – – – – – – –
label | 8ba322f0-5558-5b90-9916-dbc9d8b67e93 |  | note | CATEGORY: IP
label | f374df57-3a23-531f-9bb5-c151c0bd9a75 |  | note | – – – – – – – – – – – – – – – – –
label | 5be86664-cee7-52b8-acfd-108216016127 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f00f5db1-e16f-5550-b0dc-d7ce8f7d5e9f |  | note | – – – – – – – – – – – – – – – – –
label | 9741c474-168e-57af-baf2-9f0410438e9a |  | note | VERIFYING DOCUMENTS: This ITP
date | 73d9d33f-6fd9-56e1-8b89-162deb0cb68d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Backfill Installation (Granular Filter Material)
label | 0aef6f47-19c3-563d-a2e3-0da1fb6f8b7c |  | note | REFERENCE: Section 702.09 (g)
label | da015142-4f9d-5d09-9569-a7b3e2755705 |  | note | – – – – – – – – – – – – – – – – –
label | 74885978-42e7-514a-80ff-d26e12dc56e3 |  | note | ACCEPTANCE CRITERIA: Material shall be placed moist and compacted in layers not exceeding 300mm. The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | 32a1d23d-67a1-5e43-ae17-7ea9b0cd1359 |  | note | – – – – – – – – – – – – – – – – –
label | c216fd60-4314-59a7-988b-b9fb92c27dc7 |  | note | METHOD: Visual, Doc. Review
label | 2b3e18c9-56a3-541f-894e-b72d1394f981 |  | note | – – – – – – – – – – – – – – – – –
label | 01d5e196-0257-5b67-939d-3d5289208e83 |  | note | FREQUENCY: Each lot
label | 54acd19d-df41-5ff2-b72b-1fbece9c8186 |  | note | – – – – – – – – – – – – – – – – –
label | 2f3e00e4-590c-579c-a381-daf1e82984be |  | note | CATEGORY: HP
label | 5400ad1b-387a-5d8d-bef2-e00b093f6943 |  | note | – – – – – – – – – – – – – – – – –
label | a367d568-54b4-54c2-b57c-60c944e82332 |  | note | RESPONSIBILITY: SE, Nominated Authority
label | 49499501-404c-5eb0-b30e-9fc57d16b5bc |  | note | – – – – – – – – – – – – – – – – –
label | b74d31f7-4fea-5c8f-aafe-f3afd3397081 |  | note | VERIFYING DOCUMENTS: Nominated Authority sign off This Line
date | e1195d99-06e6-5a23-bdc5-b909e7843889 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.6 Backfill Installation (No Fines)
label | e88650b9-76af-5b70-a1b7-a1ffc1f90998 |  | note | REFERENCE: Section 702.09 (g)
label | 01993c7f-3cd0-5b61-8d13-27577f4367d4 |  | note | – – – – – – – – – – – – – – – – –
label | 94cb30c5-3a4b-5fab-80d1-55deda9263bc |  | note | ACCEPTANCE CRITERIA: All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
label | 327aa2b9-6df1-57eb-bfec-39f56490b50d |  | note | ATTACH: No Fines Delivery Dockets
label | 3b22ed43-6274-5a82-a0a5-79a07539d44b |  | note | – – – – – – – – – – – – – – – – –
label | 1e5b7e4d-cf7d-5e74-b003-66e2480d3c94 |  | note | METHOD: Visual
label | b570a203-c5af-5a52-b8c9-8b93562c2cd7 |  | note | – – – – – – – – – – – – – – – – –
label | e1b341d8-4e1d-58e3-bcec-0fffae354405 |  | note | FREQUENCY: Each lot
label | e125e6c7-6905-5899-b9d0-4be2e46b27db |  | note | – – – – – – – – – – – – – – – – –
label | 1820f737-090e-52d7-85c2-01361b3f965c |  | note | CATEGORY: HP
label | 4b65adb5-4c10-555b-af37-5bbebf9e499c |  | note | – – – – – – – – – – – – – – – – –
label | cd6c7d48-ff96-5336-89d0-0028425ef7b4 |  | note | RESPONSIBILITY: SE, Nominated Authority
label | 3524a130-48cc-58a2-a0bc-650fb701e5a3 |  | note | – – – – – – – – – – – – – – – – –
label | 85d4684a-8e75-5839-b608-c6c604807c36 |  | note | VERIFYING DOCUMENTS: Nominated Authority sign off This Line
date | efed2f77-05eb-5f28-b365-02761f067055 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.7 Install Pits and Flushouts
label | a88e01d8-cff9-5c65-b377-d9ef8bee72a1 |  | note | REFERENCE: Section 702.10
label | b0bfa166-afe9-56ba-8c99-4c67280f64ed |  | note | – – – – – – – – – – – – – – – – –
label | 19bf3af6-66fa-51a3-a5a3-789c9cdc8a69 |  | note | ACCEPTANCE CRITERIA: Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
label | 930a7c73-1ce2-5d4d-973f-fec882dab224 |  | note | – – – – – – – – – – – – – – – – –
label | a4fbdf46-3a27-5b18-8bb7-b3f4eaf47402 |  | note | METHOD: Visual
label | ef0b20fc-068b-5fb3-8494-bd8eb68ae768 |  | note | – – – – – – – – – – – – – – – – –
label | 563d07a0-a2b2-590d-9e72-721757dc8eb5 |  | note | FREQUENCY: Each lot
label | 6b766156-0d85-51ab-aaae-f9d2b3a9fb39 |  | note | – – – – – – – – – – – – – – – – –
label | 40969138-ab4d-5954-bb2e-13761a8d8078 |  | note | CATEGORY: WP
label | 86c25fb3-c01f-5740-8130-5d3955cd1fd5 |  | note | – – – – – – – – – – – – – – – – –
label | bfc0ccc2-098e-5369-bfd9-e8643745015e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c142f26d-a54c-568c-8819-b852b569dbd2 |  | note | – – – – – – – – – – – – – – – – –
label | 12b52656-9083-5f71-a56a-c5eb6a45c1dd |  | note | VERIFYING DOCUMENTS: This ITP
date | 2fb61bd9-d32c-55d7-bc4d-3e990c1f2e68 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Marker Points
label | d2423496-33f1-56d9-a5e4-02fd85bd27a9 |  | note | REFERENCE: Section 702.11
label | 879bb2ff-5c09-54cd-b9cc-8b5eadc0bf0e |  | note | – – – – – – – – – – – – – – – – –
label | ff644092-90ae-5781-8990-0f0e1743ceb6 |  | note | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
label | 1aa7c060-1ff1-5cd9-9dcd-040ca0ed2994 |  | note | – – – – – – – – – – – – – – – – –
label | 390ed56d-dfc7-523b-8b54-ca653ed3778c |  | note | METHOD: Visual
label | 1debdfad-5370-57c4-bb8a-f1b88266393c |  | note | – – – – – – – – – – – – – – – – –
label | 0d4decbb-dfce-5b04-9a3e-0b7e07255f7f |  | note | FREQUENCY: Each outlet
label | bfe32616-8cf4-5ee2-aefd-33d54248c13a |  | note | – – – – – – – – – – – – – – – – –
label | 9e6fb235-3827-57b2-b946-d09f8859c9a8 |  | note | CATEGORY: IP
label | 03e89885-1f8b-5973-9101-74cda6f7e405 |  | note | – – – – – – – – – – – – – – – – –
label | 2cafc7f2-fd4b-5b65-a241-2a56159934c6 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 0f07cd4f-0a24-5605-bf19-8150b2450386 |  | note | – – – – – – – – – – – – – – – – –
label | 4bb6e1a8-61ef-5c68-99a4-d12696eff1fe |  | note | VERIFYING DOCUMENTS: This ITP
date | fd4d50b0-d9c6-553b-abba-18ef49596c3d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Flushing
label | d9df1078-f742-5f2d-ba05-955234d12b16 |  | note | REFERENCE: Section 702.09 (h)
label | b59eb089-7582-51bf-b371-c07f2a28b225 |  | note | – – – – – – – – – – – – – – – – –
label | 73178e35-db89-596d-8c9d-f192a097e0cb |  | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
label | fb9fc945-8256-5d14-9dd8-02f69a15a4c2 |  | note | – – – – – – – – – – – – – – – – –
label | 7a0c7f96-0f89-565d-9b51-7cec676d77af |  | note | METHOD: Record Review
label | a320c0b1-91e3-530f-b57c-a9f90fbacdbf |  | note | – – – – – – – – – – – – – – – – –
label | 6355fb38-bf86-5b5e-80d2-eb76cfc5f9c7 |  | note | FREQUENCY: Each lot
label | 7373be6d-1d26-5092-bb8f-828ac76e0d23 |  | note | – – – – – – – – – – – – – – – – –
label | 6149a29a-81f7-5627-9427-578d865be348 |  | note | CATEGORY: HP
label | 272a25b9-8708-5bc5-9933-b0a08c6ae1ff |  | note | – – – – – – – – – – – – – – – – –
label | 798d86e9-bb54-526e-9b21-e0f74a0c0832 |  | note | RESPONSIBILITY: SE, Nominated Authority
label | 2ccaf1bf-6301-5b64-8b69-cf1503358dc4 |  | note | – – – – – – – – – – – – – – – – –
label | 74586954-43ea-57c8-a48a-961e64e56505 |  | note | VERIFYING DOCUMENTS: Nominated Authority sign off This Line
date | 52b4c826-39c7-52de-83da-b942443b45e8 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.10 CCTV
label | a7547f65-32a2-517c-aef2-eb07d691f129 |  | note | REFERENCE: Section 702.09 (g)
label | 135ab358-38a9-5daf-a92b-b972081d18b3 |  | note | – – – – – – – – – – – – – – – – –
label | e58dc51f-f63d-5548-a60a-3a9009dd1073 |  | note | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the NA.
label | ce167f57-f687-5759-ba31-46500d3eec34 |  | note | – – – – – – – – – – – – – – – – –
label | 6541004b-bdb7-56f1-b9e3-dd6a07507d2e |  | note | METHOD: Record Review
label | f010c7ce-ec14-531c-a393-9aa63fe422ff |  | note | – – – – – – – – – – – – – – – – –
label | 7705da50-5cf2-5759-adb5-681eefbfa1cd |  | note | FREQUENCY: Each lot
label | 9905d565-e368-5007-b311-f52b582c015d |  | note | – – – – – – – – – – – – – – – – –
label | 5b600943-db0a-5bf7-937e-bf4d0ea4101d |  | note | CATEGORY: HP
label | 27a96fad-88cf-5ee8-87f2-0c98666131b0 |  | note | – – – – – – – – – – – – – – – – –
label | 003bf701-632f-55bb-88fe-1b7834ae462d |  | note | RESPONSIBILITY: SE, Nominated Authority
label | db577e83-fc2f-5f45-aa42-2ce3093ba0d2 |  | note | – – – – – – – – – – – – – – – – –
label | c7cd57d7-4e1e-5fe6-a577-dea587513376 |  | note | VERIFYING DOCUMENTS: Nominated Authority sign off This Line
date | 9741bc94-0d7a-58f7-a4ae-d538c96d8b2e |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 As Built Information
label | faa8abdc-9a6d-5add-bc91-b63b48193e7c |  | note | REFERENCE: Section 702.03
label | 65cacae3-26a0-568f-b12b-7f0ddd4221fa |  | note | – – – – – – – – – – – – – – – – –
label | dac71a8e-d255-5651-8c95-26427196281e |  | note | ACCEPTANCE CRITERIA: The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line.
label | 997bdaf9-5b10-5ad6-b140-7daad74c9459 |  | note | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
label | 6cdc0372-108c-5c3f-bfef-e3c3542acd3a |  | note | – – – – – – – – – – – – – – – – –
label | 4b7d5497-3605-595e-adca-9b7af961ac70 |  | note | METHOD: Document Review
label | a0ba024e-425c-5adc-86f7-542e1fa84537 |  | note | – – – – – – – – – – – – – – – – –
label | 18872195-5f51-53be-a3af-2aa9595f019e |  | note | FREQUENCY: Each lot
label | c138b29d-a61f-598c-9b67-04fd79083329 |  | note | – – – – – – – – – – – – – – – – –
label | 11458d67-424e-5317-b4e7-b12e8e5cbbe7 |  | note | CATEGORY: IP
label | b122b5b7-52b5-5a53-b5d6-d189d052f56e |  | note | – – – – – – – – – – – – – – – – –
label | 8c0604aa-5206-5623-b528-64c1787ab9bd |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 9ee80fad-f40a-5cd0-a5eb-ed53753e4cd4 |  | note | – – – – – – – – – – – – – – – – –
label | 4dc84691-88e5-51e9-bb15-2cd7b9137816 |  | note | VERIFYING DOCUMENTS: Attach Survey Conformance Report
date | 4f64e290-3f82-5f89-b82d-645555a26210 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 2bee27ed-6217-59e3-b899-5a4c7e3f135c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | b7973fbc-7efe-5d88-962c-f3fafa68d41d |  | textbox | Name:
text | fdcd30b9-b999-50e7-87cd-ab3f41142427 |  | textbox | Position:
date | 22d1f343-e8eb-5445-9eb7-629e222f43dd |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-011-CIV-Horizontal Directional Drilling-SEW | itp |  |  |  | Yes | ITP-011-CIV-Horizontal Directional Drilling-SEW Rev 0 | 332c00dd-19de-4c57-9867-94146d38bbaf
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 594202cd-753b-5596-9863-0bb6960a7a4a |  | note | Document Title: ITP-011-CIV-Horizontal Directional Drilling-SEW
label | 2537f71b-7e3e-5e8d-a6e0-93f79e7123e1 |  | note | ITP Description: Camms Road Horizontal Directional Drilling-SEW
label | 358409e2-c10a-5728-8883-367fdc6c2812 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | cbc62f4b-5f42-5e2d-9d34-5b9698fad27f |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 3a41fccd-d231-5c59-9b6c-ec0c0db376f4 |  | note | Revision Number: 0
label | 1710aec5-d79a-5e7f-9061-daa68fcf2e60 |  | note | Revision Date: 19/10/2022
label | 9a819ced-bfee-5246-bcf0-69b23a06da50 |  | note | ITP created by: Michelle Lim
label | 907cfa7d-9421-5a51-ac4b-60be5b3eefef |  | note | ITP approved for use by: Victor Mira
label | cec8e546-510d-5b0a-b8e6-e54fdb5f9916 |  | note | 1.1 - Non Dependent
label | 066a2041-b978-5836-8f65-fee1884afee9 |  | note | Reference Documents:
label | 8b1b0b6d-bc9f-597a-8506-a0052467461c |  | note | • IFC Drawings:
label | 4d2e2828-35ae-51c3-989f-9c51209fdfad |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
checkpoint-group |  |  | section | Preliminary Works-Materials
checkpoint-status |  |  | checkpoint | 2.1 Encasing Pipe
label | f27dc97a-465d-5b65-a8da-19527d9695d9 |  | note | REFERENCE:
label | b486b0c9-74ff-5f55-b5bc-9bd16b25e384 |  | note | IFC Drawings:
label | b19a9169-897d-582b-9778-3042552d041b |  | note | MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 27c4b792-9f0f-5d71-bf1a-07683f75c575 |  | note | – – – – – – – – – – – – – – – – –
label | b76027bd-55e5-5357-8acd-47c83f7db264 |  | note | ACCEPTANCE CRITERIA:
label | d6d94163-4bae-523b-9f00-ec49b7141974 |  | note | • All pipes must meet project specification
label | 56654f91-6d06-529e-ae8e-aefbc6e964cf |  | note | • DN 450 PE100 WSA PS-207 PN12.5
text | c57dc0d5-1125-5a3a-a5a3-705d2dedd498 |  | textbox | Reference: Material approval in Teambinder:
label | c950936d-3493-5bab-bbde-8d09a6b63c95 |  | note | – – – – – – – – – – – – – – – – –
label | bfe08a55-643a-5ed7-b201-bd7399e5be76 |  | note | METHOD: Document Review
label | 25c39180-e0e5-5ed3-90f3-1737363a6611 |  | note | – – – – – – – – – – – – – – – – –
label | c241a703-6b7d-522e-961a-cc8074b13bb4 |  | note | FREQUENCY: Prior to commencement
label | 66ada1ad-bb0a-5a02-9b6e-9c9f0dc98dbf |  | note | – – – – – – – – – – – – – – – – –
label | 050e52a4-bf5d-5b88-b4fa-513111892406 |  | note | CATEGORY: HP
label | 4492e1c4-8444-51b5-bf5d-01ef722f318d |  | note | – – – – – – – – – – – – – – – – –
label | 27119c0f-84d9-5ec9-a6c2-12197698058b |  | note | RESPONSIBILITY: PE/SPE
label | 459a4dd1-1897-53e7-8c60-528c3bf8dad2 |  | note | – – – – – – – – – – – – – – – – –
label | 04cd85f5-2208-5a1b-a35a-c785aca3ae48 |  | note | VERIFYING DOCUMENTS: Material compliance certificate
date | 54a5aea3-436c-5136-a598-2f35c70dbf5a |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Carrier Pipe
label | 1befb960-40e0-5a6f-961e-950186c996a6 |  | note | REFERENCE:
label | 151e937b-135f-5287-955a-b84df52fbaee |  | note | • IFC Drawings:
label | 32560fc8-68e9-5585-9b77-d30362285386 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 5f819ae6-a6c1-50ad-aee7-5ffe8e42381f |  | note | – – – – – – – – – – – – – – – – –
label | f3fdbe16-a13b-58c7-b017-9d897adc293e |  | note | ACCEPTANCE CRITERIA:
label | b69e4949-6e95-53a4-a9d1-6bc6f5aee3a6 |  | note | • All pipes must meet project specification
label | ff93fea9-fe21-539e-8d4b-f9c8ac214d88 |  | note | • DN 280 PE100 WSA PS-207 PN16
text | 0323cfe3-26a0-5fe9-b628-d9d905bd9034 |  | textbox | Reference: Material approval in Teambinder:
label | 48266a9d-6afe-54c3-b966-7375908dd36c |  | note | – – – – – – – – – – – – – – – – –
label | 2e43a314-dbfd-5648-99a5-a492a1b328bb |  | note | METHOD: Document Review
label | a06c9042-ebc1-553c-93bc-7bb08afaed5b |  | note | – – – – – – – – – – – – – – – – –
label | 70cfe2b6-2cde-5805-adcb-590602de46bc |  | note | FREQUENCY: Prior to commencement
label | 0529d6e3-42d0-5d92-9ae6-d2c61577df36 |  | note | – – – – – – – – – – – – – – – – –
label | 921353ea-dfb3-553c-832d-5fb0ec2c6491 |  | note | CATEGORY: HP
label | 099b39ea-6e82-50ba-9d2c-01c49a76cac8 |  | note | – – – – – – – – – – – – – – – – –
label | d375b4b5-8ace-54ed-988a-08fec1ec6aa3 |  | note | RESPONSIBILITY: PE/SPE
label | a4983a64-1d80-5a81-9ea3-34ceb4263daa |  | note | – – – – – – – – – – – – – – – – –
label | a455e8c3-85b5-563d-bf2e-6435789c9b08 |  | note | VERIFYING DOCUMENTS: Material compliance certificate
date | 3202d9ea-7455-59fb-b1d8-e938d8004196 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Grout
label | b33d0c7f-eb01-571b-a0d1-e6b1a37f54e4 |  | note | REFERENCE:
label | 5f6db095-9b25-5e0a-8fb5-3b1b31a0eb5e |  | note | IFC Drawings:
label | 61b41ca6-6a3f-53fb-a2bd-bccb7f4dbc39 |  | note | MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | f283cd0a-2839-5ae7-b556-489704b68ebd |  | note | – – – – – – – – – – – – – – – – –
label | 8243181f-4881-54f3-8490-0d89348de683 |  | note | ACCEPTANCE CRITERIA:
label | ba33b3d8-e3bd-561b-b286-592c1dbdbe8b |  | note | • Review and approval of grout specification
text | f8855979-fd96-5d59-9465-347a0d126231 |  | textbox | Reference: Material approval in Teambinder:
label | a15b09d7-f3b6-5560-a9d4-a30991d85e27 |  | note | – – – – – – – – – – – – – – – – –
label | 679923e0-6864-5b1b-9656-3ebe4d5f1a94 |  | note | METHOD: Document review
label | 5d0d09e3-434a-575e-8647-25ce08e29ad7 |  | note | – – – – – – – – – – – – – – – – –
label | bb7c7d6d-7a37-58da-af0f-8f55c65844ad |  | note | FREQUENCY: Prior to commencement
label | 0e2df113-2403-5876-91df-1255b3184622 |  | note | – – – – – – – – – – – – – – – – –
label | 493d73e8-f734-52f5-8b4a-f412e63844ca |  | note | CATEGORY: HP
label | 569850e2-5b71-5509-a27e-afe14c4802ca |  | note | – – – – – – – – – – – – – – – – –
label | c6acce66-962a-5155-98ec-aee29c1cad0f |  | note | RESPONSIBILITY: PE/SPE
label | 83553e16-22b1-5108-a805-da18d00e7084 |  | note | – – – – – – – – – – – – – – – – –
label | 65242605-46e1-57e5-a395-fadbfe79329d |  | note | VERIFYING DOCUMENTS: Material compliance certificate
date | 188bf3ba-6aaa-5f75-acbd-253e9680efde |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminary Works-Procedures and Documents
checkpoint-status |  |  | checkpoint | 3.1 PE Welders Qualifications
label | 4dca9fd7-06a2-5b53-8fdb-f53c08b41f6f |  | note | ACCEPTANCE CRITERIA:
label | 20508239-a87b-540c-afb4-5cc94e642a43 |  | note | • PE welders are to be pre-Qualified
text | f476c1d9-de59-54c3-9675-8af1987005e6 |  | textbox | Reference:Teambinder Hold point release number:
label | 7a5153b8-f8bc-5ddb-abb3-17097886d42b |  | note | – – – – – – – – – – – – – – – – –
label | 099925fb-2e79-537a-ac63-1815dd43b745 |  | note | METHOD: Document review
label | 340bcbb0-1389-5a51-bf48-43dba8a3c2f9 |  | note | – – – – – – – – – – – – – – – – –
label | 7cd5c0dc-8acb-5452-a007-b93b81cf6d31 |  | note | FREQUENCY: Prior to commencement
label | b13657b8-46e6-5496-8802-3fbeb0669420 |  | note | – – – – – – – – – – – – – – – – –
label | 2fad386f-d2ae-59b9-9427-747d0d16d3d3 |  | note | CATEGORY: HP
label | 9921bff7-ee10-5131-97cb-b23cc064f546 |  | note | – – – – – – – – – – – – – – – – –
label | e69dd4fb-4ffd-5993-9c7c-4573d38b16b8 |  | note | RESPONSIBILITY: SE/PE
label | 217af1d9-6cdd-5c23-8476-22126784da54 |  | note | – – – – – – – – – – – – – – – – –
label | 3036a08e-ad90-59e4-854f-9a952dde079e |  | note | VERIFYING DOCUMENTS: Teambinder approval number
label | 762d2bc4-3eec-5229-a318-21678d7198fc |  | note | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Check that current revision drawings are being used
label | a2f8ea2b-f915-51bc-8c54-95b47552e3a4 |  | note | REFERENCE:
label | 15272c7b-21a2-5841-8b56-152a2316890e |  | note | • IFC Drawings:
label | 2e68038a-f333-5898-b1f6-95aaa2272272 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | b696da9a-fc28-506e-b419-124b462943d4 |  | note | – – – – – – – – – – – – – – – – –
label | c960b9c4-3a63-5067-bb6c-efd67aea9544 |  | note | ACCEPTANCE CRITERIA:
label | 7b2e62a2-832a-5d50-b751-e3d3f510b822 |  | note | • Drawing revison must be confirmed with the design manager
label | 2ae58921-ccc6-56d8-88c5-d2cbb64f68dd |  | note | – – – – – – – – – – – – – – – – –
label | f5d65023-22d8-56c1-8600-d4f4eb78e2d1 |  | note | METHOD: Document review
label | ad9a53e2-a247-5941-ba94-87b96ba54eb3 |  | note | – – – – – – – – – – – – – – – – –
label | 07e5c8b8-3a61-5406-ab9e-6c213dedc8e2 |  | note | FREQUENCY: Prior to commencement
label | 813bf685-3cde-5084-99f7-4b914cdc101d |  | note | – – – – – – – – – – – – – – – – –
label | bc3dab5a-82e9-55af-ab68-d0734f00f6db |  | note | CATEGORY: HP*
label | 59ce0d43-3347-5490-b36a-8e8838ea3cd1 |  | note | – – – – – – – – – – – – – – – – –
label | c5118c6d-bb92-5304-bbd8-c4d7f0bf2190 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 5ca3e899-c508-5dfa-aade-4983e80c56fa |  | note | – – – – – – – – – – – – – – – – –
label | b8ee6e6e-f40c-57ee-8684-aec9f07f680c |  | note | VERIFYING DOCUMENTS: Design drawings.
label | 7b0e5ab9-120f-5125-852d-ed7449d9109f |  | note | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out
label | 81925f84-9ba5-5f88-a0c6-b74cb1a4ccfe |  | note | REFERENCE:
label | 0bf5c138-a201-509b-89be-4c58a7420892 |  | note | • AS 4799-2000
label | e092658d-b826-5e1d-81bd-a09fe6789493 |  | note | • IFC Drawings:MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 1774d723-a28d-5b99-8e3f-532d534d02c8 |  | note | • DBYD Asset owners responses and requirements.
label | f29c9fbc-7713-58d6-81bb-c9b8de68184f |  | note | • MTM: L1-INF-PRO-001
label | c654265b-d5f2-5575-9074-1e13f26a7b6c |  | note | – – – – – – – – – – – – – – – – –
label | d31496d5-e439-51b7-aaef-327d19dd519a |  | note | ACCEPTANCE CRITERIA:
label | 3ee7f4f1-cba9-5634-8b7c-5ac47f82a871 |  | note | • Set out line and level of drilling works.
label | e0f58ae4-711f-53d2-a5bd-f274cdb34f9d |  | note | • Survey to mark out existing services.
label | caf47d9d-c3ce-54e8-b607-443aa84b8a15 |  | note | • Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
label | a92d5347-fa6e-506d-b3f1-705c78890d4e |  | note | – – – – – – – – – – – – – – – – –
label | dcb28227-6ea2-510e-aa11-f0185c0772d5 |  | note | METHOD:
label | 9752359e-ddc6-5ed8-9741-d29d57e54a9c |  | note | • Measure
label | 9212176d-caa3-5cde-87a1-13832d3099a7 |  | note | • Visual
label | 5bcea817-c8b2-5c79-9b13-a2d492a7c9db |  | note | – – – – – – – – – – – – – – – – –
label | baa7f63c-fd53-5f59-9040-a08e6e2cc135 |  | note | FREQUENCY: Each element
label | d5a8f3d6-0eb9-5073-ad2a-33f6f11d3afc |  | note | – – – – – – – – – – – – – – – – –
label | 8964c69e-45fa-51a2-84ec-6c43533aa9fb |  | note | CATEGORY: IP
label | 5df1efbf-f06d-5092-bd98-9c4fcb0fea20 |  | note | – – – – – – – – – – – – – – – – –
label | 6d3fae94-420f-5c8c-ab85-ce12ce06c24a |  | note | RESPONSIBILITY:
label | 559f05e3-d9e7-5d52-ad30-1aa96a062b83 |  | note | • Surveyor
label | 4395640e-1a6a-55c1-8ec8-6dc4aed86598 |  | note | • SE/PE/SPE
label | 2da80737-a1cf-572d-8dd9-f4b8a69468f0 |  | note | – – – – – – – – – – – – – – – – –
label | c97655ee-d80a-57c7-8323-1c2f244a2333 |  | note | VERIFYING DOCUMENTS: This ITP
label | bb0842ff-47e2-5849-b34c-b8c22fd32749 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Pipe welding
label | c5164130-de0b-573d-a552-3531e28ff7a7 |  | note | REFERENCE:
label | d65f2cfb-6c62-551e-8a42-066984948d96 |  | note | • IFC Drawings:
label | 3b5f76ab-e32d-5151-bd93-83c1ff53c2e5 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | a183cc98-ed38-5778-93ba-37fa453e79df |  | note | – – – – – – – – – – – – – – – – –
label | 310f2324-8e13-57fa-9429-3aa08e8c06b2 |  | note | ACCEPTANCE CRITERIA:
label | 21d85847-ef00-54c1-bdf2-59e6f64fe114 |  | note | • Joints are to be butt welded.
label | 8b39d3b3-f145-553a-b0db-662fb44a0c03 |  | note | • Butt Welding records to be supplied.
label | 012b21c2-61a8-54c9-9b6d-26bff825a234 |  | note | • ATTACH: Welding Record
label | c023b849-3929-58c4-b307-500653759347 |  | note | – – – – – – – – – – – – – – – – –
label | 17d940c2-19c1-53d4-a496-171ca31958b5 |  | note | METHOD: Document review
label | 192f0664-f681-55ae-bbf8-c1bdd9f3145a |  | note | – – – – – – – – – – – – – – – – –
label | caf3a73a-2018-53b0-bda4-7d39632c5acd |  | note | FREQUENCY: All Joints
label | ccc8031d-70fc-5226-8eb4-5783fe90c8cf |  | note | – – – – – – – – – – – – – – – – –
label | 275d49de-5e01-55a0-872f-86eb4fd41bee |  | note | CATEGORY: IP
label | 4605fea5-392e-53f0-85ac-3b4f142f7202 |  | note | – – – – – – – – – – – – – – – – –
label | 58d53df4-1132-51ea-a706-ccd917ceba6c |  | note | RESPONSIBILITY: SE/Site Supervisor/Survey
label | 5fe30491-e7e5-52da-a9fd-8dddad89f2fa |  | note | – – – – – – – – – – – – – – – – –
label | 2b6bf1a6-e473-5c80-8997-e8ebf47594a7 |  | note | VERIFYING DOCUMENTS:
label | e02a3cee-0d06-58b6-b138-f395756b5e63 |  | note | • Sign ITP
label | 2b57f5b0-472f-5588-b51b-59568a30a01a |  | note | • Butt Welding Records
label | c0dc88e9-8abb-5487-b9d3-8ab0e0a6978e |  | note | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Drill rig setout
label | ca198b3e-3330-5b0b-b320-90f3255af96a |  | note | REFERENCE: Drill Shot Plan
label | 60af4ff3-5c69-5695-9fc9-bc1dc490b178 |  | note | – – – – – – – – – – – – – – – – –
label | 54d1e2ce-7b8a-5589-a84f-0e521bc37d44 |  | note | ACCEPTANCE CRITERIA: Location as per current Drill shot plans
label | e6a944cf-9ca9-53ba-80c3-65278f770130 |  | note | – – – – – – – – – – – – – – – – –
label | f8bef584-428e-50bb-91fd-dfb633ada44a |  | note | METHOD: Visual
label | dbdc74eb-3579-5ab1-a2d8-ec9450dcf256 |  | note | – – – – – – – – – – – – – – – – –
label | 79d91c7f-8379-549a-a6c6-1cb9f1b0ae26 |  | note | FREQUENCY: Prior to commencement
label | 4fc8711d-287c-52c3-9f99-52f05e41becc |  | note | – – – – – – – – – – – – – – – – –
label | df60d1cb-3b0d-5852-99f7-f76b123f520e |  | note | CATEGORY: SP
label | 78a1ae66-9d5f-5948-aef1-40fa65841bc3 |  | note | – – – – – – – – – – – – – – – – –
label | d1bff473-ff49-5fc9-9d61-d05ffb7a907f |  | note | RESPONSIBILITY: SE
label | e65f3255-2dcf-5b87-b34b-95770fd2dbb2 |  | note | – – – – – – – – – – – – – – – – –
label | b608fe5b-8da0-56e9-ae69-153ed02e09c0 |  | note | VERIFYING DOCUMENTS: This ITP
label | dcd32bde-6d11-5b1a-b901-a8d003fa744a |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Installation of Pipeline (Trenchless method)
label | 950309da-42a1-51eb-b977-9cd83a372479 |  | note | REFERENCE:
label | 6e6985fe-e114-57b6-a5a2-aed7c3719971 |  | note | • IFC Drawings:
label | 4961e4ae-53ec-5b96-9a3e-72bf8c9eec05 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 530c2be0-9ea9-553e-8af1-b07a7d584c6f |  | note | – – – – – – – – – – – – – – – – –
label | 92391f99-98cd-58f5-8ae0-19956661e8a5 |  | note | ACCEPTANCE CRITERIA:
label | 12545a48-5452-51ac-aadb-bfb771509473 |  | note | • Drill to be installed as per the survey setout.
label | 7d87cbc3-099e-536c-bf46-45759bdc8b49 |  | note | • Bore longs to be supplied.
label | 5d810578-ffc3-5d6e-b448-d998d40163c4 |  | note | • ATTACH: Bore Logs
label | f16c687f-383a-5058-850c-30542aae41a6 |  | note | – – – – – – – – – – – – – – – – –
label | 8c75a063-3dad-560c-b065-41b00bfb0ffa |  | note | METHOD: Document review
label | adec6c1b-d466-51fe-aabb-b52e60634a9c |  | note | – – – – – – – – – – – – – – – – –
label | 3e97917a-28d8-5ce5-84cb-476d6ee71c91 |  | note | FREQUENCY: During pilot bore
label | 495438da-b8e5-59d1-8ad0-56aa9f6b219e |  | note | – – – – – – – – – – – – – – – – –
label | 3cc63faa-5eca-5b6c-a820-be8d6e753db7 |  | note | CATEGORY: IP
label | ecd706a2-c73c-5959-b0d3-7efd9621e588 |  | note | – – – – – – – – – – – – – – – – –
label | 90e46edd-2f1a-51a1-bda7-2415219e449b |  | note | RESPONSIBILITY: SE
label | 787a3658-a0f8-57a1-b20b-9b8ac932e321 |  | note | – – – – – – – – – – – – – – – – –
label | 310bfe9f-9a4a-5a0f-98ba-ad38519c244c |  | note | VERIFYING DOCUMENTS: Bore logs
label | 996d0d75-1331-5096-a06b-91a765fb64a0 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Mixing of grout
label | 9db30508-fbdd-501c-8b31-31997af9d048 |  | note | REFERENCE: Grout Manufacturer Technical Data Sheet
label | e871a985-fc21-51b2-b3f7-ea99d87dfc18 |  | note | – – – – – – – – – – – – – – – – –
label | 4f11ec8a-9173-5c6f-9ef1-4aa2750f9d3a |  | note | ACCEPTANCE CRITERIA:
label | 67bf306f-7779-5984-8172-50a3fa7cc3f1 |  | note | • Mixing and proportioning of grouting to take place as per Technical Data Sheet provided with product.
label | 0ce1f4c9-4d9d-5d8a-8de3-51b064b625ac |  | note | • Only whole bags of product shall be used.
label | 4398a09b-e9a2-5e02-8488-f726dc78f233 |  | note | • Grouting shall not commence when temperature is below 5 degrees Celsius or above 35 degrees Celsius
label | 917677a6-eda8-5256-8830-1d9b0e8c53b7 |  | note | • Grout mixture should be mixed adequately and free from lumps
text | f20e1f01-55a4-5146-a78c-766f9fa3b8e4 |  | textbox | Grout Volume Used
label | b41212d3-ebba-5f2e-acd0-16bd3a8ef3f2 |  | note | – – – – – – – – – – – – – – – – –
label | 5e2a00de-8b51-52e3-9463-0f3da076c80f |  | note | METHOD: Document review/Measure
label | bc72fbb7-a47a-5f7e-898a-0343db585e60 |  | note | – – – – – – – – – – – – – – – – –
label | 8b8eff9c-275e-5e5c-b10c-056e025d09f6 |  | note | FREQUENCY: During grouting process
label | 6dc8c19a-1550-5dd2-9693-c5c891c895e5 |  | note | – – – – – – – – – – – – – – – – –
label | 74b3cb0a-c274-51af-acb2-5b0940d23559 |  | note | CATEGORY: IP
label | 1cb31917-2400-56a7-9997-9e66330e9b9d |  | note | – – – – – – – – – – – – – – – – –
label | bb622d29-b2a9-5c9e-820d-2518042753c3 |  | note | RESPONSIBILITY: SE
label | 787bf020-a954-5c22-85a1-f0894baf39de |  | note | – – – – – – – – – – – – – – – – –
label | d30200d0-7115-5fc2-bba7-ec59afbe9df8 |  | note | VERIFYING DOCUMENTS: Sign ITP.
label | 17579022-ba7e-5997-8674-375212647634 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Clean surrounding faces and remove excess grout
label | 04eb82ed-13c5-5a2e-9089-49cee7e9825d |  | note | ACCEPTANCE CRITERIA: Area free of excess grout and spillage
label | 4562dc7d-e3ad-5653-84fb-9d8fda7ed60c |  | note | – – – – – – – – – – – – – – – – –
label | 071a445b-c6b6-5f4a-99eb-fff9176a0e2a |  | note | METHOD: Visual
label | 9ded60c8-3fce-581b-b677-13e93657b89a |  | note | – – – – – – – – – – – – – – – – –
label | ecd7ab3f-b4f2-5acc-b79c-1301a43f444a |  | note | FREQUENCY: Each shaft
label | 375bb4d9-0a0b-5b3d-b3b7-2b0293f4ad78 |  | note | – – – – – – – – – – – – – – – – –
label | 5d1c7ef9-b6be-5c9c-b509-91cedcb284cd |  | note | CATEGORY: WP
label | 6d9da102-e3fb-5edd-be82-dbbb9489735b |  | note | – – – – – – – – – – – – – – – – –
label | 63230b97-da5c-5b7f-bf82-c78e1155bd56 |  | note | RESPONSIBILITY: SE
label | 4b4fbb0a-8cc1-5b44-bd3e-9cbf4a58cf69 |  | note | – – – – – – – – – – – – – – – – –
label | 7f212852-d647-5967-af5b-69616eb4d24f |  | note | VERIFYING DOCUMENTS: Sign ITP
label | 3e014d06-1ac5-5edc-9912-a5f5be29d3cb |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Curing
label | 1107e5f5-1375-5f6f-92e8-58e32cf98391 |  | note | REFERENCE: Grout Manufacturer Technical Data Sheet
label | 3808c881-0830-54a9-b345-ac38fe09909c |  | note | – – – – – – – – – – – – – – – – –
label | d45c4e82-ca6a-5e57-9c2e-2a6183738939 |  | note | ACCEPTANCE CRITERIA: Curing in accordance with TDS
label | 5843d4bb-1eed-5ea8-970e-c428e365a78d |  | note | – – – – – – – – – – – – – – – – –
label | cc9df75e-d5b0-5d51-b72a-ff9554716f58 |  | note | METHOD: Document review
label | 209215c5-14a2-5b78-a232-f49ba4e8839e |  | note | – – – – – – – – – – – – – – – – –
label | bb7ffd13-5804-5fc5-a997-675917adf21d |  | note | FREQUENCY: All pipe
label | 245a2d41-b64f-5b61-b79d-096992745599 |  | note | – – – – – – – – – – – – – – – – –
label | 800d86d8-f6ce-519c-ac99-94ff3389c9c6 |  | note | CATEGORY: IP
label | ca7f872d-d36f-501f-a27d-31e3bd827ba5 |  | note | – – – – – – – – – – – – – – – – –
label | 7755aad7-613a-5478-8549-532ded782ae2 |  | note | RESPONSIBILITY: SE
label | 5e3baa93-cf75-5edd-b4da-e07763680a27 |  | note | – – – – – – – – – – – – – – – – –
label | c6d8845d-af86-52f7-bf37-4bc929e82920 |  | note | VERIFYING DOCUMENTS: Sign ITP
label | beadbb23-fcb9-5317-bad4-50a04f6ddd6e |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Auditing
label | 8d17e61a-9357-59e3-9139-3a4a8a726247 |  | note | REFERENCE: IFC Drawings
label | 45b2b9f8-95a5-50e7-a2e3-ce29f401f7b6 |  | note | – – – – – – – – – – – – – – – – –
label | f4fa4e4c-2e52-5d6d-9d57-fae1f57a3332 |  | note | ACCEPTANCE CRITERIA:
label | 04c8a3c4-47d6-56b4-aedd-3633316dc4a4 |  | note | • Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts.
label | 2bc29c96-73af-5ae8-8870-d0c05c41e5fd |  | note | • ATTACH: Audit report
label | 42cd9895-37c9-5503-b72d-d0ea2e234637 |  | note | – – – – – – – – – – – – – – – – –
label | 018758f4-14be-59ec-8df2-ee94405b3edf |  | note | METHOD: Record and Review
label | ef21f3fc-9457-52e4-a615-2f5de08199c1 |  | note | – – – – – – – – – – – – – – – – –
label | 0e79791b-4844-515f-9d12-6196a38a4ee6 |  | note | FREQUENCY: Prior to backfill of exit/entry shafts
label | 6c8c069f-2118-58ff-a0be-336d337a8e74 |  | note | – – – – – – – – – – – – – – – – –
label | 3a5deebe-7807-5c01-9649-11371dfe5f65 |  | note | CATEGORY: HP
label | b08e8626-8b05-583c-a42d-b1afd2ab319a |  | note | – – – – – – – – – – – – – – – – –
label | 8407faad-fe99-5281-a6c2-6b1665e1d4af |  | note | RESPONSIBILITY: Nominated Authority (SEW)
label | b86b6029-0104-5c87-bdee-506a682270cc |  | note | – – – – – – – – – – – – – – – – –
label | 9b96fb1b-b13e-56b0-9f62-c04ab2a2ab04 |  | note | VERIFYING DOCUMENTS:
label | 9841058c-4bd9-580e-b5fd-b23d3543fbbc |  | note | • Sign ITP
label | 622ac85f-99cc-5ace-bdcf-38e43929c27a |  | note | • Auditing Report
label | f82c2662-dadb-5541-9fab-46f8ae5fd1b4 |  | note | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 Reinstatement
label | 28935bf7-2072-54a5-ab66-7e476edc5924 |  | note | REFERENCE:
label | 5fbfcd2b-25fc-5f99-bfcc-1fe697c80964 |  | note | • IFC Drawings:
label | 1b6ed5ce-a905-531a-a01a-400bec0d4b31 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 8eca3a04-fd0f-5729-9fc9-66224c1ad0f2 |  | note | • MRWA-W-201 Table 201-A & 201-B
label | 0c7e7815-f49f-5912-9209-0a94b69be761 |  | note | – – – – – – – – – – – – – – – – –
label | 514c1f69-f0b8-5127-8376-a2cdde16db83 |  | note | ACCEPTANCE CRITERIA:
label | fd3395ca-0356-5a00-bc66-4417970535a4 |  | note | • REINSTATEMENT OF BORE SHAFTS SHALL FOLLOW MRWA BACKFILL SPECIFICATION MRWA-W-201 Table 201-A & 201-B;
label | 87dd418b-347b-581c-91ef-417f9ea89b2a |  | note | • Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified.
label | 98fa1ce4-82c4-5420-bda6-f756834c9943 |  | note | – – – – – – – – – – – – – – – – –
label | a88b8de7-041d-5a18-aa6e-46cd501a6ea1 |  | note | METHOD: Visual
label | e47897ea-47ce-5152-83e2-979b2adb7721 |  | note | – – – – – – – – – – – – – – – – –
label | 500a549a-417d-56bb-bae9-8a392b8703a3 |  | note | FREQUENCY: Each shaft
label | 4c5c3e00-a888-5484-b5b8-7fae6b0bc3d4 |  | note | – – – – – – – – – – – – – – – – –
label | ca78556b-8d05-504b-ba9a-871f1b1dd6d9 |  | note | CATEGORY: IP
label | aed93e4e-811d-57af-9162-463ec7d025c1 |  | note | – – – – – – – – – – – – – – – – –
label | 36fb1be4-a0d8-5f1c-b969-a40b749c1787 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b8eb4b2d-3ddc-5f5b-99a5-d54cddd03e6c |  | note | – – – – – – – – – – – – – – – – –
label | 5fc0f876-6de0-5c97-a5d1-f320325e3822 |  | note | VERIFYING DOCUMENTS: Sign ITP
label | 6ba38a78-7ad4-5c98-9af1-1232279b1de8 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Subcontractor ITP
label | 3d0474ca-8ede-5c05-970e-ca004062474d |  | note | REFERENCE: N/A
label | ec8532ac-08f7-52fb-970f-911028415f17 |  | note | – – – – – – – – – – – – – – – – –
label | 20fb4c92-dcd3-5736-aa0c-c7573e70a22f |  | note | ACCEPTANCE CRITERIA:
label | 6d65d288-049f-5e16-b5c0-0bb4ab8c5db7 |  | note | • Acceptance and closeout of subcontractor ITP
label | 9ab9bdac-ffc7-5044-a3ec-96682ee8e6f3 |  | note | • ATTACHED: Completed and Signed Subcontractor ITP
label | 22a5af48-4e6f-59e4-95cc-8d2bc8e8b29c |  | note | – – – – – – – – – – – – – – – – –
label | e2a050ff-67b9-55d0-8cea-fec89c02b3d7 |  | note | METHOD: Document review
label | bf789d76-144b-5b36-829b-884be41d08bc |  | note | – – – – – – – – – – – – – – – – –
label | c2c33ad5-2f00-52c7-8aa1-7df2459d020a |  | note | FREQUENCY: Each element
label | 5cee562f-4791-54e5-847c-97f2f9d4e71a |  | note | – – – – – – – – – – – – – – – – –
label | d6bb1a7a-eaf4-5054-9a6f-676656a41923 |  | note | CATEGORY: HP*
label | ea807eb1-ba9c-5582-a443-d770b5561c4d |  | note | – – – – – – – – – – – – – – – – –
label | 37c12ab1-16df-5bb9-a301-c6c251804a6e |  | note | RESPONSIBILITY: SE/SPE
label | 63928657-0fa0-5095-b054-018573ff975e |  | note | – – – – – – – – – – – – – – – – –
label | 9419710d-e3d7-5546-bc4c-1ad473700bdd |  | note | VERIFYING DOCUMENTS:
label | d9b02aa1-eee4-5be3-809b-c53d8fb8f900 |  | note | • Subcontractor Signed ITP
label | 34cbcacf-28db-5604-a03b-4e3dd0d39893 |  | note | • Completed
label | 5f4797c7-3fe1-5756-8303-6a2ee26b7a5a |  | note | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Non-conformance Report (NCR) Closure
label | ed77b383-9afd-5445-a88a-59b2f6dde804 |  | note | REFERENCE: MRPA Quality Management Plan
label | 9b372559-fa82-537a-97dd-d64605787674 |  | note | – – – – – – – – – – – – – – – – –
label | 843dc03b-4666-5bca-a546-7909e4b53078 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | da01ccb1-acbc-5435-a925-3b014c6602a0 |  | note | – – – – – – – – – – – – – – – – –
label | 2729d196-9e8e-5ce4-9275-5cc6dec3d6df |  | note | METHOD: Document Review
label | 5be44998-113e-59f2-a297-f4163a911d8f |  | note | – – – – – – – – – – – – – – – – –
label | 7eba0c3b-9830-5232-9dde-d86a08ffc15a |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 2fe01a24-ce75-5f79-891f-7b8ffbbd83de |  | note | – – – – – – – – – – – – – – – – –
label | b17d3002-c15d-5443-996d-aacbcbbe4142 |  | note | CATEGORY: HP*
label | 47d15316-bd32-5b79-a481-ebbfe4c2acb7 |  | note | – – – – – – – – – – – – – – – – –
label | f3380249-61f3-570a-ab24-9e2ce44b4a2d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9ebb0d7e-f9e6-5a8b-b9e5-b9f9740e18f1 |  | note | – – – – – – – – – – – – – – – – –
label | a703bc0c-bdde-50fb-9fdd-30c7f49a4455 |  | note | VERIFYING DOCUMENTS: This ITP
label | 9841c41d-4989-5458-9a94-9fa7eceb349c |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 As-built Survey
label | 171690da-27ab-5517-9c0c-0c02446418f0 |  | note | REFERENCE:
label | d0a60653-ae5a-5b2c-9c04-5a5541c7195a |  | note | • IFC Drawings:
label | a465dd06-ce20-511d-bfd6-6ad378a7df18 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 767dc9f4-696f-5e47-bf77-54eb5707e92c |  | note | – – – – – – – – – – – – – – – – –
label | 860d64d9-d4fa-5ad1-81ec-65eae70bbd37 |  | note | ACCEPTANCE CRITERIA:
label | adb3440a-82a7-5332-a9a0-9b2dd76ac5d7 |  | note | • Survey as built report to be compiled.
label | 32c1f56f-2213-5cc9-935c-d0d6e4dc8f0f |  | note | • Borelog obtained from subcontractor
label | cc0787b3-7748-5ed9-8a55-fec486ecf974 |  | note | • Autocad and PDF reports are to be supplied.
label | dd8ef055-31e8-5215-a9a4-466ae6398084 |  | note | • ATTACH: Survey As-Built Report
label | 5b12c7f5-f902-586a-9e12-11e060115c8b |  | note | – – – – – – – – – – – – – – – – –
label | 12b78f14-494c-53db-bf18-35e142b7deac |  | note | METHOD: Document Review
label | 90ccf9ed-b0d3-5b66-9f8c-47b7a02fa60b |  | note | – – – – – – – – – – – – – – – – –
label | 31e60aee-da0b-52d6-b109-6fab7ede0034 |  | note | FREQUENCY: Each element
label | 81963a14-10e8-55c5-aeae-b110b6452aaf |  | note | – – – – – – – – – – – – – – – – –
label | 5ddc6d32-4b47-57cd-92ff-8a63ad420c00 |  | note | CATEGORY: IP
label | b86633a4-a74b-51e4-a32f-735f93a43ca2 |  | note | – – – – – – – – – – – – – – – – –
label | 818307c3-8d34-5068-bccd-f27af1ff7434 |  | note | RESPONSIBILITY:
label | 5ea08cbb-4dc1-5bc7-8794-3a63d2b446ee |  | note | • Surveyor
label | 45f02f97-a58a-5b67-9584-3adda4258ec7 |  | note | • SE/PE/SPE
label | c92cffe6-c983-5067-bfa3-0c64a2d442f2 |  | note | – – – – – – – – – – – – – – – – –
label | d150ff4a-5bc2-5ed5-9d7a-fe8bb378e54c |  | note | VERIFYING DOCUMENTS: Survey As Report
label | 4d02fd2d-5f0d-5791-a4de-62d3da29cf66 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Red-line / As-constructed IFC Drawings
label | 7e25e6b8-03e9-5213-8703-527758880c03 |  | note | REFERENCE: MRPA Quality Management Plan
label | 30138de3-d288-5cbb-a1d6-ba24bdc823f4 |  | note | – – – – – – – – – – – – – – – – –
label | 3ecf4149-407c-5bd6-bb50-a016298caea5 |  | note | ACCEPTANCE CRITERIA:
label | 93140037-d863-5865-a497-d1553c245f7b |  | note | • All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
label | 7e97ed1b-5e72-5e0e-afc0-494b6621f3c8 |  | note | – – – – – – – – – – – – – – – – –
label | 1aaa41cf-a026-552b-b5bf-8a7e2d293099 |  | note | METHOD: Document Review
label | 03471765-4b60-5a0a-9f29-6712b725cb65 |  | note | – – – – – – – – – – – – – – – – –
label | f0d925e8-5c37-5989-aa95-78e3915beffd |  | note | FREQUENCY: Once, after construction of the design package
label | 69fa3425-e8aa-5c63-ba21-cd44a911d260 |  | note | – – – – – – – – – – – – – – – – –
label | 30007985-af9f-5d99-85b7-aab60723f2e2 |  | note | CATEGORY: WP
label | df3398b8-7d79-51d2-b0c1-ad4ee0d9cf40 |  | note | – – – – – – – – – – – – – – – – –
label | b3878b90-29d0-52e4-92cd-45df7df196de |  | note | RESPONSIBILITY: SE/PE/SPE
label | 55d502f7-7bfc-5d4f-83fd-32139500bad0 |  | note | – – – – – – – – – – – – – – – – –
label | 68cdcb72-8070-5353-8bcd-f7e46afe6726 |  | note | VERIFYING DOCUMENTS: This ITP
label | 7cdb9fe5-aba4-5a35-9d81-d49e9d4d8dfa |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 48cd75a8-1d9c-5b4a-bcad-2add2460a467 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 0e2c2a88-5eee-5aa9-99e0-fbf6553b2cd4 |  | textbox | Name:
text | 55b01236-1702-5672-8bd0-b183ccfec4b1 |  | textbox | Position:
date | 92c17c32-0d4c-5a7b-bb58-7ed6b3f94864 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-068-CIV-Camms-Rail Delineation Fencing-Permanent | itp |  |  |  | Yes | ITP-068-CIV-Camms-Rail Delineation Fencing-Permanent Rev 0 | 39bf0162-ac6c-4327-b2c4-cb88edad1692
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | a57e6373-6c84-5438-a7bd-fcc223e5ac78 |  | note | Document Title: ITP-068-CIV-Camms-Rail Delineation Fencing-Permanent
label | 1f3232ef-08c9-5954-a9a6-163c65b9708a |  | note | ITP Description: Camms-Rail Delineation Fencing-Permanent
label | 0c441597-8c63-54cd-81bb-8fcbdd91534f |  | note | ITP number: 068
label | ce63fcb6-f875-58ff-b67e-72b88bfa50da |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 94eb38ea-bc56-5aff-8262-f52e74942c25 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 8b0e58d8-c7ec-5ad5-884b-88f5608057e3 |  | note | Revision Number: 0
label | 553fbc11-0a60-5023-8ce3-c5e6a8f5ca6a |  | note | Revision Date: 1/09/2023
label | 2d3ade14-ab27-516e-9b79-6070481626a5 |  | note | ITP created by: Diana Delac
label | 8e1b54c1-5ab8-5061-bcf0-34112ffc9819 |  | note | ITP approved for use by: Victor Mira
label | 04ffa2de-5165-54ec-8769-a05939ae3c18 |  | note | 1.1 Non Dependent
label | dc3eaf52-96b3-5639-9f1a-45756693cbfa |  | note | Reference: IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025, VicRoads Section 610, VicRoads Section 630
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete
label | 03482413-7877-55f5-a81a-b19e241bc40d |  | note | REFERENCE: IFC Drawings Section 610.07 Table 610.071
label | 575b9ec8-a122-5acb-aa9a-74aa6ee07414 |  | note | – – – – – – – – – – – – – – – – –
label | 8eba0b82-dd90-5361-ab17-f2e7fdec530b |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | b6cf38ba-7c87-5e70-9f3a-8d5a962194f3 |  | note | ○ 32MPa concrete to be used as per IFC drawings.
label | 7c07d845-acdb-5a45-9be9-981ab32d759f |  | note | – – – – – – – – – – – – – – – – –
label | 6446ac3f-fc69-5e6c-bd13-97ba3b6ae42b |  | note | METHOD: Document Review
label | 2a95a6dc-56b3-53ac-8c81-c9fe2b9870d9 |  | note | – – – – – – – – – – – – – – – – –
label | 4a627530-1b68-5112-ba75-426fefd7d84e |  | note | FREQUENCY: Each Mix
label | a151fd9c-7dcc-5836-97c1-a4e34a97412f |  | note | – – – – – – – – – – – – – – – – –
label | 9bcd73a0-2dd1-5f65-beb9-6bc03c6492cb |  | note | CATEGORY: HP
label | 483fe473-264d-5441-992f-38a78ca84d1a |  | note | – – – – – – – – – – – – – – – – –
label | 3d349b35-3199-5a2c-8995-08660047321c |  | note | RESPONSIBILITY: SE/Site Supervisor
label | d9cd75de-d90d-5c48-8846-df63ca2c19cf |  | note | – – – – – – – – – – – – – – – – –
label | d8736a69-41b5-55b6-9ae3-f8c8792e266f |  | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | 6c3e6cca-587c-5455-9331-110e43316c52 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Steel Columns, Cladding, Handrails, etc
label | 19b5b0d8-05cf-58e7-b3d1-73c2ce1735fb |  | note | REFERENCE: IFC Drawings AS41000, AS1163
label | 28dc68f2-c31e-5013-91da-2f17a3d8131e |  | note | – – – – – – – – – – – – – – – – –
label | 2d0c4e75-35f9-5926-8995-ba554c445b8e |  | note | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | ba909e5e-208a-53a3-a932-3fc02592616b |  | note | ○ Steel section sizes must be checked on site.
label | d8008cad-3ff2-5ff1-95a7-64202a1d03bb |  | note | ○ Steel posts to be CHS with a grade of C250
label | 136929e9-28bb-5f05-9edd-7cc88de2a691 |  | note | – – – – – – – – – – – – – – – – –
label | 724bf44d-b6f5-59d8-939f-245fe9d3efbb |  | note | METHOD: Document review, Visual and Measure
label | d9c5a5d1-ea9e-507f-ab2f-08396bc9e765 |  | note | – – – – – – – – – – – – – – – – –
label | 7a1dd9b2-6b7c-58b4-b624-1111b4eb8931 |  | note | FREQUENCY: All elements
label | 6fdeae3f-a3a7-58ec-908b-60e2ef84ab72 |  | note | – – – – – – – – – – – – – – – – –
label | 267cf75c-aef3-5ecb-91c7-2708e150d745 |  | note | CATEGORY: IP
label | c92ac14c-9103-5dc0-99e2-5f88cd6e5469 |  | note | – – – – – – – – – – – – – – – – –
label | 996493de-fc60-5a8f-b1bd-2feb4218ea2d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 2e429866-204b-554f-aad4-ee4bdcf07760 |  | note | – – – – – – – – – – – – – – – – –
label | 2a9bfed0-a8da-5d91-bb32-a23f9712dffc |  | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | 5843432c-9707-5d72-82a1-929e2411ef90 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 943f3233-04d8-5a02-87ae-3b72fbb4709e |  | note | REFERENCE: IFC Drawings
label | be937814-dc20-56de-b537-70c431edee3f |  | note | – – – – – – – – – – – – – – – – –
label | a8a390c9-93ab-59b4-a837-5edb6d574f5f |  | note | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | 73e6be46-b648-53af-a08c-68ed9546fa26 |  | note | ○ Offset checked against the running edge prior to installation of posts.
label | e83e6502-14c8-596e-b0fc-9c9e624de159 |  | note | – – – – – – – – – – – – – – – – –
label | da2f40a2-8708-5af9-a5d2-ca6bc5752af9 |  | note | METHOD: Measure, Visual
label | 2808c498-ff36-5ac4-80fe-f2068e5a3395 |  | note | – – – – – – – – – – – – – – – – –
label | a00f745c-4fd9-581d-8406-574a3bc7fef0 |  | note | FREQUENCY: Each element
label | 8e4e5bd9-f80b-5bf1-8d71-146a37c420ce |  | note | – – – – – – – – – – – – – – – – –
label | 4c8bc3f9-6321-5594-be0a-192d1139e9cd |  | note | CATEGORY: IP
label | 94e6c9b7-da97-53b4-a097-bbd8a34a2a45 |  | note | – – – – – – – – – – – – – – – – –
label | 219794f9-26b2-52d6-a1bd-e156ca8643d3 |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | 5a2da160-ff3c-5ea4-a6d0-c927aa346d37 |  | note | – – – – – – – – – – – – – – – – –
label | 3dc1c89b-3d7c-561a-9f41-4f206dd94af5 |  | note | VERIFYING DOCUMENTS: This ITP
date | b31c8904-d1a4-54b7-9c32-122ef9d708a7 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Excavation works
label | be22943f-6191-5163-a813-dcf2eda28968 |  | note | REFERENCE: IFC Drawings L1-CHE-STD-005
label | 365c99b9-1575-5640-af30-b7f27c245f7b |  | note | – – – – – – – – – – – – – – – – –
label | 98a13656-cfc4-5070-9700-1a52e0162cd5 |  | note | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine footing of existing structures.
label | da5a4a82-f202-58ab-81c0-22caa78c6355 |  | note | ○ Follow asset owners guidelines for work around their service.
label | cba62071-249a-5cd1-a39c-16547479b9de |  | note | ○ Excavation must use Non Distructive Digging in the rail corridor
label | a540a740-6b1b-540b-a132-5a5bba2f2314 |  | note | – – – – – – – – – – – – – – – – –
label | f6fdd09c-eab1-5283-b415-34b587549ab4 |  | note | METHOD: Visual
label | a27775b5-d3af-5b32-b82a-149e57519369 |  | note | – – – – – – – – – – – – – – – – –
label | 6c79df3f-8b8e-5ee8-9003-515930934733 |  | note | CATEGORY: IP
label | fb138e74-438c-54c1-b896-80722b6bc5a4 |  | note | – – – – – – – – – – – – – – – – –
label | 5e197712-25fc-50c1-bd85-aef995edc73d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 42bec5b2-5801-559a-8d56-64ef041b053d |  | note | – – – – – – – – – – – – – – – – –
label | 4c6b1a8f-7be8-50b4-8f8f-1afd19c08a4e |  | note | VERIFYING DOCUMENTS: This ITP
date | 863b3f46-35fb-536f-8fab-af1d8415b525 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Ground Conditions
label | 9dd176d1-089e-5032-a088-b12c1cf822a7 |  | note | REFERENCE: IFC Drawings
label | 306a8174-b45a-5e0f-999b-6c899ab04f7f |  | note | – – – – – – – – – – – – – – – – –
label | 677e3559-fbdb-5c1e-b788-174a59bce7e5 |  | note | ACCEPTANCE CRITERIA: All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | ebeda8f3-7d68-53b7-9287-aa3b763c01f0 |  | note | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | 369da022-a256-5651-8269-513f3462da6d |  | note | – – – – – – – – – – – – – – – – –
label | 446e4d2a-a64a-568a-bb20-05166ab8adc1 |  | note | METHOD: Visual
label | af307f27-3749-5aad-9177-4724264e712c |  | note | – – – – – – – – – – – – – – – – –
label | 0e217f49-0596-588c-b181-70e9a5c1204c |  | note | FREQUENCY: Each post
label | b1fd1597-7606-5106-ade5-4a3c0d3db1fd |  | note | – – – – – – – – – – – – – – – – –
label | bac28b7f-4b62-55be-bcdd-57da3615048d |  | note | CATEGORY: IP
label | 854db2ce-e79d-5c2f-a1a9-1b78f2c00425 |  | note | – – – – – – – – – – – – – – – – –
label | 6a8eb069-0963-5b57-a3d1-1a68e5cbc08a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c6762728-a084-5c4f-9429-a6d61cd57cde |  | note | – – – – – – – – – – – – – – – – –
label | 2a37fd14-e237-5083-b03c-cd4301786564 |  | note | VERIFYING DOCUMENTS: This ITP
date | 35d09f8a-1846-5e5b-a8c9-b5ab2c8f4c07 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 MTM OHW Structures
label | fc834490-c3b9-52c7-9180-61544e35a902 |  | note | REFERENCE: IFC Drawings L1-CHE-STD-005
label | b3211c98-2640-5155-b0b4-7ab0a178e1f5 |  | note | – – – – – – – – – – – – – – – – –
label | e696a3ba-cf5f-5fbf-bc03-5db891efe1a0 |  | note | ACCEPTANCE CRITERIA: Fencing must be a minimum 2m away from OHW Structures.
label | 406b9a2b-045f-55b8-b06e-808555f7a6e0 |  | note | ○ Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level.
label | 056d7d50-8a5a-5eeb-8af4-2ec67addd809 |  | note | – – – – – – – – – – – – – – – – –
label | 78118626-7bd2-587c-a85d-36549ca17464 |  | note | METHOD: Measure
label | b0797988-fcb9-5b32-a539-ba42a110e5bb |  | note | – – – – – – – – – – – – – – – – –
label | be0044c8-c1b0-5be1-a129-5ea02667d860 |  | note | FREQUENCY: Each Overhead
label | bd744bdd-48af-5726-ba8d-4b068b89c5bf |  | note | – – – – – – – – – – – – – – – – –
label | 820b3625-0297-5cbf-bc00-c4a2f30ddcba |  | note | CATEGORY: IP
label | c0f47115-b33d-564e-9c0c-df7daf01a848 |  | note | – – – – – – – – – – – – – – – – –
label | 4ab9d08e-e84a-5f7f-a1db-3e697c9edbb8 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 0f4eb9ea-0a9b-5944-b7e8-a8a5a1b588c5 |  | note | – – – – – – – – – – – – – – – – –
label | 21e8a96b-b882-5a4f-a310-695640b13ad0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6d7c513a-8e17-5d2d-8c0c-bdb0cf53dcae |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Fence Post Foundation
label | e69fcf15-0eb3-54d7-93fe-a94d81f406a9 |  | note | REFERENCE: IFC Drawings L1-CHE-STD-005
label | ba5969b8-1ce8-57da-b65b-a5df83bcb361 |  | note | – – – – – – – – – – – – – – – – –
label | 9118114c-5c86-5139-8c42-544c49caf236 |  | note | ACCEPTANCE CRITERIA: 32MPa concrete.
label | 6c204d28-521b-5cae-a978-890b2ac59713 |  | note | ○ Footing to be a min. 1m clear from proposed TTC footing
label | fb0380e3-58a9-57f3-9eaf-97950fb981b7 |  | note | Typical Footing:
label | 4f1e4824-fbe6-5fff-8e39-4bf4e9d54b7a |  | note | ○ Footing dimension 900mm deep, cross section 300mm X 300mm
label | e92e1aa8-5d80-5d74-8fd9-207a5acea8e6 |  | note | ○ DN80 MS Pipe (88.9 X 4CHS) to be installed full depth.
label | 1bd83c99-f518-555a-a266-78393598ff2c |  | note | Alternative Strip Footing:
label | ddf0f96c-dca4-5007-aa95-071a83c154f7 |  | note | ○ 800x800x300mm thick
label | 0a1b175c-d867-599b-801c-f9fcb03b965e |  | note | ○ 101.6 x 4.0 CHS sleeve to be cast into footing.
label | 1918c9c4-3b71-5c3a-a71b-9415af5d4448 |  | note | ○ 150x150x5 thick base plate welded to sleeve.
label | 0476b6d5-548a-55b8-b677-3bfd560d9c35 |  | note | ○ Refer to IFC drawing for reinforcement details.
label | e3eba1bc-fc41-5da0-93e2-145727a81971 |  | note | – – – – – – – – – – – – – – – – –
label | b4451f33-b24e-5672-b024-effc0e4df43c |  | note | METHOD: Measure
label | 1f504bff-bcb0-54a4-b787-ac4564b62a1a |  | note | – – – – – – – – – – – – – – – – –
label | b2a170bb-781c-5639-bb04-570ebd1da17f |  | note | FREQUENCY: Each footing
label | 49a55460-ebf4-59ee-bcd4-f9ebc643d881 |  | note | – – – – – – – – – – – – – – – – –
label | 4bc0ac54-7f5a-5427-a6a2-4b943317a51a |  | note | CATEGORY: IP
label | b61c94a4-1bf3-501e-bb96-c14fc9540e23 |  | note | – – – – – – – – – – – – – – – – –
label | bf1c3828-1ac5-5795-a3d2-032440acf948 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ab01d0de-f7b0-5ab3-94fa-86d44519a336 |  | note | – – – – – – – – – – – – – – – – –
label | 666900c3-8b94-5562-95ef-f5e1c03aaa41 |  | note | VERIFYING DOCUMENTS: Post and concrete dockets
date | 4129ec96-5702-583e-9dae-974bbf7b3262 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Fence Post Installation
label | 6bb64549-92b0-58c6-b2bb-719e12e2bec3 |  | note | REFERENCE: IFC Drawings L1-CHE-STD-005
label | fce78729-15b1-5b22-81ae-b2ae5812cd9f |  | note | – – – – – – – – – – – – – – – – –
label | b27bd061-e683-5421-9c5b-ef27dce0f423 |  | note | ACCEPTANCE CRITERIA: Maximum post spacing to be 2.7m ± 250mm, two spans at 1350CTRS at gates, at the ends and at Refuge bays.
label | 5780c8a3-8499-5473-9986-658e904be349 |  | note | ○ An individual fence space may be increased to Max. 3100mm locally to avois clashes with services.
label | c3cff7b5-dad5-5b05-b64c-a99ba31e0aad |  | note | ○ Minimum offsets from centre of the rail to the fence: 3000mm
label | d891245b-9d8d-500d-b230-cb9a94d2dfe2 |  | note | ○ Alignment tolerance: +20mm to -0 (- being closer to the track)
label | b37fc71f-5d31-53a9-858e-cd1348a0dcee |  | note | ○ Max. post height 1800mm above ground level.
label | 2f06626b-19ee-5372-89a5-5d1fa599685f |  | note | ○ Vertical Tolerance (Hight Risk Areas): ±20mm from the design line.
label | ca4e4fca-c5db-5bad-8597-dfe38174b2a8 |  | note | – – – – – – – – – – – – – – – – –
label | e0cab40f-e43e-5ea2-82f5-95359b254511 |  | note | METHOD: Measure
label | 16aedc4d-a647-56d8-b42e-dd432eb3751e |  | note | – – – – – – – – – – – – – – – – –
label | f27a8811-3444-50b6-b050-0bd8a645a32d |  | note | FREQUENCY: Each post
label | 8ae76887-72f1-56ec-9c29-f8e4c9889696 |  | note | – – – – – – – – – – – – – – – – –
label | 3a572a1d-a11c-5a32-9240-7873abe09e2e |  | note | CATEGORY: IP
label | 25c20aa9-41da-5b1d-8701-4ff2b1d48986 |  | note | – – – – – – – – – – – – – – – – –
label | edf7a07e-1be6-5687-92eb-ac93170d2a95 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 527884be-110e-5f56-a7b4-ee7e05ee2cb0 |  | note | – – – – – – – – – – – – – – – – –
label | 61b6cc04-3f6f-5380-9a09-f84a3116c548 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Dockets
date | 07e62123-e888-5ffa-8d63-7642e1ebb2a2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Chain Wire Mesh Installation
label | eae15eeb-066a-588e-be6b-384d9dc0577f |  | note | REFERENCE: IFC Drawings
label | de66fd0b-6a28-597d-81a0-5404ed73fd39 |  | note | – – – – – – – – – – – – – – – – –
label | 07277ce1-3ea1-5fe8-affc-7fc1069ed3a4 |  | note | ACCEPTANCE CRITERIA: Chain-wire mesh 1800x50x2.50 to be fixed to fence post with 1.57mm tie wire.
label | 3a8272bf-169a-5a0c-935b-16f520d72099 |  | note | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
label | faf544f3-90bd-563d-99de-00477f399369 |  | note | ○ 3 NO. W10Z TWIN-STRAND 3.15mm DIA. WIRES TWISTED BETWEEN POSTS. TENSIONED TO 1kN.
label | 3df28dce-c65a-54ee-80b3-8866f7b91f1c |  | note | – – – – – – – – – – – – – – – – –
label | 1dd63361-fce8-5aef-b8d5-07abd2ce9ede |  | note | METHOD: Visual
label | 1495472a-49e6-54d4-8dff-5138ff023530 |  | note | – – – – – – – – – – – – – – – – –
label | 9f6799c8-5a60-5069-a1a8-d88ef59f2647 |  | note | FREQUENCY: Each element
label | 222c237d-7108-562d-ad9b-98598244c145 |  | note | – – – – – – – – – – – – – – – – –
label | c73bedf9-dba5-5ceb-a026-1e709f1f584a |  | note | CATEGORY: IP
label | 2bf82f74-0d5e-5865-8b89-78115859fef0 |  | note | – – – – – – – – – – – – – – – – –
label | 0e4102b7-5fea-5bd7-b788-aa42ca43b5ae |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 7f74e7c7-fd08-53cf-996c-2c170f971ac7 |  | note | – – – – – – – – – – – – – – – – –
label | b03177e2-f135-5f61-a2c8-39f868fe5a54 |  | note | VERIFYING DOCUMENTS: This ITP, Delivery dockets
date | c8b7855f-d6c3-53cc-b514-b529d828f172 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Bracing
label | 152af2f5-c557-544d-b5c6-dcda60d85479 |  | note | REFERENCE: IFC Drawings
label | 67a77e66-ec18-5062-8a31-8eca148c0c57 |  | note | – – – – – – – – – – – – – – – – –
label | ccf24918-b9e0-59ab-81cf-149854a2e8b9 |  | note | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | 9e43ea7c-e4e0-5775-bf53-b12c964898af |  | note | ○ Bracing to be installed on both sides of the fence at the fence corners.
label | 0d857e09-e423-57bd-82dc-d489a8b86d58 |  | note | – – – – – – – – – – – – – – – – –
label | 28668059-7b9e-5f12-a141-bebcb590c8c3 |  | note | METHOD: Visual
label | 473126a9-b51a-5d12-a89f-71e91636ccaa |  | note | – – – – – – – – – – – – – – – – –
label | 5e29d34d-d3ab-57a1-b56f-c759385c657d |  | note | FREQUENCY: Each element
label | cfa74ad7-4201-5659-b6c4-070212169424 |  | note | – – – – – – – – – – – – – – – – –
label | 34b115f0-c838-5e7d-a41c-28d37eb16508 |  | note | CATEGORY: IP
label | 3912b956-fe24-5c9c-82a5-35ee25debd74 |  | note | – – – – – – – – – – – – – – – – –
label | 04a142e7-a214-5e7b-84b1-ecc23c3a2b93 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1435c5a3-fcb2-5d80-ae33-6013d7804d8d |  | note | – – – – – – – – – – – – – – – – –
label | 0ed6b7f2-47c6-52e4-b5f9-f832e6df731f |  | note | VERIFYING DOCUMENTS: This ITP, Steel delivery dockts
date | bcb839dd-e323-5ccc-a3bd-06b982e730cd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Refuge Installation
label | 177b0340-14aa-56d5-a3f0-91f4b441a82f |  | note | REFERENCE: IFC Drawings
label | a50a6e72-ef04-5519-9748-68d8266b0bc1 |  | note | – – – – – – – – – – – – – – – – –
label | 830bcd4c-f7d1-5fde-bc8f-06d775034135 |  | note | ACCEPTANCE CRITERIA: Refuge Access to only open from track side.
label | 2d70ca02-3fc1-5f7d-9e88-4866411c1444 |  | note | ○ No chain wire mesh to be installed at refuge access.
label | 7a6ce0f1-b331-5b06-bb33-b956e6703dc5 |  | note | ○ Refuge Access to be located every 20m max. along the fence.
label | cc671801-f7b5-51e1-b517-a9f0657e3d33 |  | note | ○ 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | db87ef8d-67d9-59ec-aa0a-1e8f9a3cff7b |  | note | – – – – – – – – – – – – – – – – –
label | 81c1c25b-1044-59fc-a345-47dca3290225 |  | note | METHOD: Visual/Measure
label | 338b0eca-9c50-52b3-bc1a-acf23536692f |  | note | – – – – – – – – – – – – – – – – –
label | 79370984-b87b-5e25-b218-aeda6b5c92f5 |  | note | FREQUENCY: Every 20m Max.
label | 2206273c-1e60-5961-bc6d-bf27421e0e97 |  | note | – – – – – – – – – – – – – – – – –
label | 1bfc3e0b-ad05-5248-a05e-97d3732ff7ab |  | note | CATEGORY: IP
label | eb5c8513-50d5-5477-954f-80f9fc701265 |  | note | – – – – – – – – – – – – – – – – –
label | f1ac2919-c58d-5a4b-9d8a-e2fbc53c76a2 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 293b6e7f-54d4-552c-ac5c-793e2847a815 |  | note | – – – – – – – – – – – – – – – – –
label | 406f810b-65b9-5ae6-afec-b102277588b7 |  | note | VERIFYING DOCUMENTS: This ITP
date | daeea0b1-ded1-5dc0-b1d0-11ce77255ed4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Gate Post Foundation
label | 7c807239-272f-5681-af6a-caa114e5ce7a |  | note | REFERENCE: IFC Drawings
label | 444e54c9-cbdc-50b8-aa1d-7fb31bd6ccf6 |  | note | – – – – – – – – – – – – – – – – –
label | b61fea4c-0167-5adc-a7a8-60fd298dbeb7 |  | note | ACCEPTANCE CRITERIA: 350mm DIA. PILE
label | 603f6bca-08b3-58b3-9035-b391e9bae199 |  | note | ○ 1300mm DEPTH
label | b4e65452-3cc0-5869-aa7a-69575df8cbfe |  | note | ○ 1200mm POST EMBEDMENT
label | a7f4c0cf-918b-5fcb-aec1-177dfdeb7794 |  | note | ○ 101.6 x 4 CHS GATE POST.
label | 472350f0-2823-5d40-8e7b-ed9bb2181acf |  | note | ○ 1200 EMBEDMENT
label | 86d54c53-79cc-50db-b116-3a6920eccf1f |  | note | ○ 32MPa Concrete
label | 6e3cbf6a-bd73-5afd-ba2f-1fb94f6a4038 |  | note | – – – – – – – – – – – – – – – – –
label | 8a1f0f87-e3f3-5a40-800b-9cca76d7fafd |  | note | METHOD: Visual/Measure
label | 4c76021a-201e-5955-9537-a6a2a1930a09 |  | note | – – – – – – – – – – – – – – – – –
label | d0840f48-1513-5d71-b28a-54fe56c8b6cc |  | note | FREQUENCY: Each footing
label | e399e4f2-1e30-5e87-be61-4a685aa1e66a |  | note | – – – – – – – – – – – – – – – – –
label | 0822206b-e981-5b5d-8309-611ca55f0dec |  | note | CATEGORY: IP
label | 1721b3a9-e70a-515c-ab3c-b260eaba1abb |  | note | – – – – – – – – – – – – – – – – –
label | b844bbc1-a158-52bf-ab4b-49c9b0331a25 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3344fcf0-ee4c-5b7b-aaf5-9b5b33045d79 |  | note | – – – – – – – – – – – – – – – – –
label | b319128c-1f44-544e-914b-5c1057dc255e |  | note | VERIFYING DOCUMENTS: Post and Concrete Dockets
date | 0ded8955-45c9-5a69-bc93-2ef46b172dd2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Gate Installation - Post
label | 5dedf914-c935-5547-838f-982493e2fc9c |  | note | REFERENCE: IFC Drawings
label | ba73d9e9-9f6c-5938-8367-09126eac0137 |  | note | – – – – – – – – – – – – – – – – –
label | 9249b28d-baa2-5d8a-a3d8-47f61819a400 |  | note | ACCEPTANCE CRITERIA: 3000mm nominal clear between the gate posts.
label | dd1858d7-b77b-5356-a234-d330cd1280ac |  | note | ○ Minimum offsets from centre of the rail to the fence: 3000mm
label | fd9fe2f3-e0b4-5e5d-ad53-5194cee6329a |  | note | ○ Alignment tolerance: +20mm to -0 (- being closer to the track)
label | 7f3c557b-ae2d-58bc-8540-ea2b6e3027ea |  | note | ○ Max. post height 1800mm above ground level.
label | 0ea65928-5bea-5813-8abf-95a7421f598d |  | note | ○ Vertical Tolerance (Hight Risk Areas): ±20mm from the design line.
label | 361ad3f8-9c25-5a84-be7f-ba401d38941d |  | note | – – – – – – – – – – – – – – – – –
label | fd4e0b07-1fff-5dac-a5e7-331929b58650 |  | note | METHOD: Measure
label | 3995e8d2-ae3d-5b82-a395-f8afd91a700a |  | note | – – – – – – – – – – – – – – – – –
label | 0013037f-ece0-5ee5-ae92-b0b4dc1159b0 |  | note | FREQUENCY: Each Post
label | ac3c165e-4b83-5fe8-b601-517223b3f695 |  | note | – – – – – – – – – – – – – – – – –
label | 9c1ca540-657c-5c5c-98bd-40efc585dc3f |  | note | CATEGORY: IP
label | 770bdd69-53a1-54b6-b455-da27a2af4f62 |  | note | – – – – – – – – – – – – – – – – –
label | 44d2d5a9-bb3f-5e96-86d2-13af3d22002f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 7cc41873-4e2f-52f9-8db7-75bd949c8645 |  | note | – – – – – – – – – – – – – – – – –
label | b4bb3a83-8b1c-5690-8c4e-a9226ba21c2d |  | note | VERIFYING DOCUMENTS: Delivery Dockets
date | 680f408b-7249-5db1-a73d-8a70f1eede70 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.11 Gate Installation - Gate
label | edb72685-da44-56fb-aaad-d662c2c2c81d |  | note | REFERENCE: IFC Drawings
label | 5d06e0ec-6244-5929-a7a4-9221850f9a65 |  | note | – – – – – – – – – – – – – – – – –
label | 9ae315b0-da20-53da-8970-5669e01a6206 |  | note | ACCEPTANCE CRITERIA: 2 NO. 1800mm (H) x 1500mm (W) ROUND TOP GATE
label | 416df41b-b1cd-5a33-939e-7771e37410dc |  | note | ○ MINIMUM 2 NO. FENCE BAYS MUST BE PRESENT EITHER SIDE OF GATE TO ALLOW BRACING TO BE INSTALLED.
label | 9b09ff7e-0e60-5ca5-9307-ed49548f8d52 |  | note | – – – – – – – – – – – – – – – – –
label | 6fad09e5-b58f-5529-8466-75c6bac622ef |  | note | METHOD: Measure
label | c8f5bd81-9cd7-5bb3-8d6e-dfc421c5e408 |  | note | – – – – – – – – – – – – – – – – –
label | 4600f9cd-5a53-5fd8-9f1a-af373488c6e1 |  | note | FREQUENCY: Each Gate
label | e244ede1-68bc-5a1b-ad9e-27aa7c29739e |  | note | – – – – – – – – – – – – – – – – –
label | fccec112-8d2e-5150-a8d8-6022f9155215 |  | note | CATEGORY: IP
label | f25dddf6-ef54-56c4-90cd-99d143709fea |  | note | – – – – – – – – – – – – – – – – –
label | d6517d19-8cc8-5fa4-8b0c-4020d8f3c07a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 457a176e-204c-5baa-8a43-4cd2b12d89ae |  | note | – – – – – – – – – – – – – – – – –
label | d5f20e9f-f8a5-569c-99e2-3766327e0fa9 |  | note | VERIFYING DOCUMENTS: Delivery Dockets
date | 7d2f7906-d688-55e1-a892-c8780a9b6bd4 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Fence Height and Track Clearance
label | 4999f63c-c05c-5937-8e58-aa606a8f7bf6 |  | note | REFERENCE: IFC Drawings
label | 161252b0-e8e5-5eef-8a6b-6ea5ce38e471 |  | note | – – – – – – – – – – – – – – – – –
label | 73456859-2594-54e8-a803-02295df40104 |  | note | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | 050e4e33-ee18-562f-b72c-e0755ebca835 |  | note | – – – – – – – – – – – – – – – – –
label | e6717125-fb10-55ce-bdc2-c3e664e19018 |  | note | METHOD: Measure
label | bc9bc939-0839-5b51-94f0-c575a1427b04 |  | note | – – – – – – – – – – – – – – – – –
label | af45a5af-fa0c-50b9-a6ac-085b53746ad3 |  | note | FREQUENCY: Each lot
label | 4d06612d-41be-5eec-95c1-1f92215067fb |  | note | – – – – – – – – – – – – – – – – –
label | 332d683f-2633-59de-b7bb-ca6de7f997f2 |  | note | CATEGORY: IP
label | 0c5a70ff-d8ea-5287-8e22-7c1a0e3a889c |  | note | – – – – – – – – – – – – – – – – –
label | fa3b7cc0-3738-53f3-8be7-0592c1655a98 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 294d17c8-b2e7-5325-8eb9-de40fe2c21f6 |  | note | – – – – – – – – – – – – – – – – –
label | b1c2a6e2-5fdf-5419-9ead-7f094e2d60d8 |  | note | VERIFYING DOCUMENTS: This ITP
date | a507b197-c211-5903-b947-2f3512aaf161 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 3a793c8f-af61-56f7-afec-be4ea827ba10 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 7f77ff3e-b23b-5e16-9f12-516627622817 |  | textbox | Name:
text | 05ae69e3-e890-5e54-86d2-6fd587a11dc6 |  | textbox | Position:
date | 765a7a80-ac34-5ec1-b77b-35e742042f84 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-052-Camms-OHLE Wire Regrading | itp |  |  |  | Yes | ITP-052-Camms-OHLE Wire Regrading Rev 0 | 3e069579-dc44-4076-b921-92ca4956219e
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 7f037e8b-a44e-5d5a-9603-a374ec135f78 |  | note | Document Title: ITP-052-MRPA-Camms-OHLE Wire Regrading
label | 53043bed-9cbf-5b5a-9430-04d13084b9fd |  | note | ITP Description: OHLE
label | 47c525be-d9fd-5463-881b-85fb39336694 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 625f96c4-711b-51f2-958e-6d9a84516fe6 |  | note | Discipline (e.g. CIV/STR/RAIL): OHLE
label | ee8392c1-c456-531a-865e-b76c4c993345 |  | note | Revision Number: 0
label | 91d12b99-afa8-5005-9a4f-7cbe1eccf5ed |  | note | Revision Date: 26/06/2023
label | f658f12c-2925-56f1-89ea-ff347d293415 |  | note | ITP created by: Nikhil Siram
label | 8ebf8754-aee7-57a0-a2b1-04bb6a3da88f |  | note | ITP approved for use by: Victor Mira
label | 72c02d52-e105-50bd-8216-014278ad6451 |  | note | 1.1 Overhead Line Electrification
label | a8b0f882-0c97-5ff1-a35d-1fa8ede9d886 |  | note | Reference: L1-CHE-STD-011(1) MEST 000002-02(1)
label | 08bb6f67-5920-506e-9783-3840d474ead9 |  | note | 1.2 Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | 0b5c4120-5516-54c9-802f-f58c9fed04f4 |  | note | Reference: VRIOGS 001 AS 4100
label | c36fbe0e-9a38-5025-b07e-c6dfea626ab2 |  | note | 1.3 Electrical Networks Standard Electrical Networks Principles and Performance
label | b98945f5-d15b-5899-b407-5c16f3fffc37 |  | note | Reference: L1-CHE-STD-015(1) MEST 000002-06(1
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Procurement Materials delivered/collected to stores/Site.
label | b915d0b2-cd73-5fa7-ac26-166d45c7cf2c |  | note | REFERENCE: Contractor - Site Material Control procedure.
label | 38833b4f-b7e9-59ba-a7fa-0d7848c79ab8 |  | note | • Cat5 Material received -Camms and Camms Tracking sheet
label | be89df3d-905c-538d-bf29-1c0034f544cf |  | note | – – – – – – – – – – – – – – – – –
label | 2ed993e1-982b-55b4-bcdf-d6e85a258556 |  | note | ACCEPTANCE CRITERIA: Ensure materials are delivered/collected as required. Certificates of Conformity provided by MRPA
label | 32216e13-dc06-5758-8c03-f120ec2eb3be |  | note | – – – – – – – – – – – – – – – – –
label | 957893bf-7f7c-5782-b06d-266457ccaff0 |  | note | METHOD: Document Review
label | fd5c785b-22ce-5ec5-aff7-94a6b35164ca |  | note | – – – – – – – – – – – – – – – – –
label | c428cd55-f0a3-5e1c-a34f-416da412ccaa |  | note | FREQUENCY: Once for each supplier, prior to works start
label | d1ea52d3-a854-5562-b39e-7cd55267c5c1 |  | note | – – – – – – – – – – – – – – – – –
label | 84a29e99-10e4-5e82-be88-f55624f936c5 |  | note | CATEGORY: IP
label | c4867068-de9c-5392-8e04-29cb61eb8814 |  | note | – – – – – – – – – – – – – – – – –
label | e32b1cc7-6492-5870-9664-f97439087249 |  | note | RESPONSIBILITY: MRPA Issue, CAT5 Receive
label | c41a05e3-b5b8-5c66-8ff9-c14580d6b40a |  | note | – – – – – – – – – – – – – – – – –
label | 759a5f40-c084-5a31-8776-9d4b52388653 |  | note | RESPONSIBLE PERSON: MRPA
label | 91d4340f-68a7-57ab-8a2c-2f38b181a5e4 |  | note | – – – – – – – – – – – – – – – – –
label | 312dbf83-a94c-5e53-ab37-90325eb0b587 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 47fed2d5-f6de-5513-a2bc-8ae5ab6140b3 |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Produce Work Package Plan
label | f7dda7e1-5f8e-5974-b5d9-d9e266e64352 |  | note | REFERENCE: Work Package Plan WAP_BR_184
label | 3c1ea572-63f7-5b46-9f1a-55a0ae3a2aad |  | note | – – – – – – – – – – – – – – – – –
label | 0738ccbc-2ca6-538e-a328-b1fa0c56e323 |  | note | ACCEPTANCE CRITERIA: Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
label | e3f82f64-1767-5457-82cb-238b709d2769 |  | note | – – – – – – – – – – – – – – – – –
label | c23a1a4c-6a68-54de-9192-0857a2fe3146 |  | note | METHOD: Document Review
label | 2c62436c-4d0d-5751-b0f8-f0de5e080ad5 |  | note | – – – – – – – – – – – – – – – – –
label | ba37ec5f-a934-56c1-8a98-07314c55e806 |  | note | FREQUENCY: Prior to Works Start, TBC in accordance with MTM Standards
label | e6a25559-04da-5d9a-9834-d07e97255e4a |  | note | – – – – – – – – – – – – – – – – –
label | 9c536746-3427-5f6e-a1d3-62b59b69851a |  | note | CATEGORY: HP
label | b8550e56-e6a0-5bd2-ae38-b874f0172448 |  | note | – – – – – – – – – – – – – – – – –
label | 364d40dd-ecb3-5d14-aaf6-994379f1cc9c |  | note | RESPONSIBILITY: MRPA/CAT5
label | b1592a37-9bd9-5898-afc3-1c6c96836bc5 |  | note | – – – – – – – – – – – – – – – – –
label | 6e3db35b-24c4-516a-a9e2-5a2dc520a1c1 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 492800d3-9ef4-5218-9d62-7b74d66e97b0 |  | note | – – – – – – – – – – – – – – – – –
label | f3508e5d-1929-5881-a88e-bc51d04d1037 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 3d54628b-ed28-545f-a9c7-ddcf73bd1ea9 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Approval of IFC drawings
label | daab2dc2-2aed-51c3-b213-88e0e797ac25 |  | note | REFERENCE: Contractor Design Management procedure. MRP-DPK-089-00-ETN
label | a7f2f744-7855-58f0-b53e-531372b719e6 |  | note | – – – – – – – – – – – – – – – – –
label | cccb2177-5819-5e36-84d9-2c44b1fa8a50 |  | note | ACCEPTANCE CRITERIA: Ensure correct and most recent revision of IFC design drawings are used for construction.
label | b6870423-34fc-565f-af0a-d4b5b0e8ed4e |  | note | – – – – – – – – – – – – – – – – –
label | 015f9e3e-e603-5731-bb31-b0209137c562 |  | note | METHOD: Document/Drawings Review
label | cdca1ab1-6792-5cb9-bdfe-040f2db1cecb |  | note | – – – – – – – – – – – – – – – – –
label | e1a50e6c-e614-5f6f-b0f8-c70d57d66b11 |  | note | FREQUENCY: Prior to Works and at regular intervals. TBC in accordance with MTM Standards
label | e7cf17b1-eb7a-599e-bd63-a2319292b595 |  | note | – – – – – – – – – – – – – – – – –
label | 4164e0b3-50f9-5cea-8120-2b5939957bb4 |  | note | CATEGORY: HP
label | d4e9218b-2e8b-5bcb-9256-9302e2c07d56 |  | note | – – – – – – – – – – – – – – – – –
label | 71f01712-bfb3-590f-b535-adb04e1f6c76 |  | note | RESPONSIBILITY: MRPA/CAT5
label | 15d9f55d-e96c-589c-9457-3a3f1f20c6ab |  | note | – – – – – – – – – – – – – – – – –
label | 4ba7541a-75f2-5268-8f4c-356de02935e8 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 3d9cd67c-25e8-561c-aba0-7750c17dccc5 |  | note | – – – – – – – – – – – – – – – – –
label | 4d17844e-5bec-5dcc-98f9-2a5aa1862d7c |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | dc1590f4-d914-56dd-ac85-ef9f48b65ff5 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 Task Specific Permits
label | a808d0b8-aa5f-52eb-bb55-758c634db23d |  | note | REFERENCE: Working at height permit. Hot works Permit, Permit to dig. OHLE SWMS
label | bead0857-905f-566a-9e08-39499fd01f95 |  | note | – – – – – – – – – – – – – – – – –
label | 094081ce-9cb1-5ecd-881b-bde34674b09f |  | note | ACCEPTANCE CRITERIA: Ensure all task and activities have relevant permits issued and received.
label | 95d4028c-79e4-5766-9146-e381ed40f719 |  | note | • Task Permits to be generated and signed off by appointed person.
label | e7f90e76-d86d-5b71-9c64-cec3ff1224f0 |  | note | • Task specific documents - MTM to issue permit to enter/Isolation permits etc.
label | 80c11bb6-ee93-50a7-8b8f-ae5af84f5707 |  | note | – – – – – – – – – – – – – – – – –
label | d082b57b-8388-5991-bf9e-138e52d52e3f |  | note | METHOD: Visual, Document Review
label | 828110d4-0118-5ca8-b864-504a6f16826a |  | note | – – – – – – – – – – – – – – – – –
label | e2d9d51f-9c47-552f-b774-4ecb322a5ba1 |  | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
label | dbf625f0-38f4-553a-8365-e71799eb3993 |  | note | – – – – – – – – – – – – – – – – –
label | 5e322afc-0925-5e25-9744-aa64441b4247 |  | note | CATEGORY: IP
label | e70fefbe-c4c9-5034-b50a-392f197a0c0e |  | note | – – – – – – – – – – – – – – – – –
label | b5aa28b4-f368-521d-b673-63c3efa8d01c |  | note | RESPONSIBILITY: CAT5/MRPA
label | 97252ea3-6a2a-5094-a75c-92e3a5bc267a |  | note | – – – – – – – – – – – – – – – – –
label | 79ad0ba1-ca6f-5d03-a14c-0f93e04b1149 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | c40b0d11-dd78-5c0e-a23a-29b5ebad50d9 |  | note | – – – – – – – – – – – – – – – – –
label | a16ad815-6ca3-57d1-9f7a-c01f91de63b6 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 701222c5-a8da-5053-97d9-e5ae57d700a4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Cantilever assembled.
label | 82682ea8-eac1-5ffd-a28b-2ba320c9fd00 |  | note | REFERENCE: Cantilever assembled as per IFC design.
label | e93646ee-9aa6-5ea2-8207-b5cbd2265519 |  | note | – – – – – – – – – – – – – – – – –
label | 8791b9f0-d88f-505c-8e32-8dc9d7489877 |  | note | ACCEPTANCE CRITERIA: Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | c6626f11-fd00-5451-8d27-8cde469dd7cd |  | note | – – – – – – – – – – – – – – – – –
label | 273c7330-b499-5368-9b94-d73d42877db6 |  | note | METHOD: Visual, Document Review
label | 2eac80c8-2b26-5c2f-8639-39ebc8604c6d |  | note | – – – – – – – – – – – – – – – – –
label | 957ef78a-150c-57f4-9bca-d88bf2c55e47 |  | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
label | b9f39006-85a1-5ad1-b045-dc7f590b54bd |  | note | – – – – – – – – – – – – – – – – –
label | cf0cfa87-bd51-5f49-954a-d4bd4c73e1fc |  | note | CATEGORY: IP
label | 83b9f923-19e7-5367-9967-a39716089705 |  | note | – – – – – – – – – – – – – – – – –
label | 25a44824-3c70-58ac-a5b0-a3572caefdae |  | note | RESPONSIBILITY: CAT5/MRPA
label | 399fa014-5f00-50f8-97b7-0aed6575a214 |  | note | – – – – – – – – – – – – – – – – –
label | 88278720-ecfc-5a4a-a7c5-c956c3bdf696 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | a9a93280-2e44-58bb-9de9-92ade7f0f8f5 |  | note | – – – – – – – – – – – – – – – – –
label | 743d75fe-9895-56ee-a8a7-b50f3e2bb9cb |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 48b61c1d-2662-55f9-aad5-bf5eff091374 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Pre-Installation check
label | 008719b5-3a53-5155-888a-5c14600ee012 |  | note | REFERENCE: IFC wiring layouts, IFC cross sections and BOQ. Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
label | 42c04ab1-4d8b-539f-aa8b-7b21ad7b8169 |  | note | – – – – – – – – – – – – – – – – –
label | 5e171dd5-bce9-58c6-a8b9-db0a41114f58 |  | note | ACCEPTANCE CRITERIA: Ensure that locations matches most relevant IFC drawings
label | 4522dd04-3965-5424-8d21-43e9eaf7c77a |  | note | – – – – – – – – – – – – – – – – –
label | 617ea455-e148-5877-baba-af6348ccbdd1 |  | note | METHOD: Visual, Document Review
label | f6500899-b549-5fca-a2fd-0e3dce75fcb4 |  | note | – – – – – – – – – – – – – – – – –
label | 0feab0e1-999a-5006-accd-6794aa3f3634 |  | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
label | 331c84f8-ff0a-5a83-a122-f66ada9ed036 |  | note | – – – – – – – – – – – – – – – – –
label | 05897bad-f57c-58be-9b6d-4fbec5e2fc17 |  | note | CATEGORY: IP
label | b7b05c6d-b610-53f9-8f97-32a0549c6c79 |  | note | – – – – – – – – – – – – – – – – –
label | 08e9dc80-7a64-5f16-9550-4e2f6e745092 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 456db8f1-c810-54b1-a198-f5e7f18b9d81 |  | note | – – – – – – – – – – – – – – – – –
label | 5d3cbece-bd97-52a3-84d5-84b42cc37caf |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 220aa530-c9ab-59f7-b2c7-37c349cae5d0 |  | note | – – – – – – – – – – – – – – – – –
label | 385e5964-a7ed-553c-ab20-fe8641954384 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | f4700221-cd3d-5521-b38d-f74c58b1cae7 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Cantilever installed.
label | b655e08a-d10c-5b3b-b19e-18a5271e9d65 |  | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | b7e372a0-17d7-508e-ac1f-bcc496322509 |  | note | – – – – – – – – – – – – – – – – –
label | 4f56830a-1f89-597f-ada8-a80e321e3586 |  | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
label | a6464319-40e6-58c4-aed0-8d8683c1ab9d |  | note | – – – – – – – – – – – – – – – – –
label | c5700654-3324-531d-803d-34c0d1823b9b |  | note | METHOD: Measure, Visual
label | 7e9e2ec5-0e44-5061-83b4-5e74cf41c217 |  | note | – – – – – – – – – – – – – – – – –
label | 50528d9d-8801-5311-a853-180696539ba7 |  | note | FREQUENCY: Each OHLE Structure
label | 2280b815-5adf-51fa-9bc6-0141a56b62d4 |  | note | – – – – – – – – – – – – – – – – –
label | 6eb8d0b5-85ba-5386-b207-3cd6e96d7caa |  | note | CATEGORY: IP
label | e6ddc833-9811-5e84-885d-4720742885d9 |  | note | – – – – – – – – – – – – – – – – –
label | 206d02c7-2c90-5fc6-9cf8-d0b9c45b3f93 |  | note | RESPONSIBILITY: CAT5/MRPA
label | c6e6c0b0-d5ad-5b47-8119-e69fdd03247a |  | note | – – – – – – – – – – – – – – – – –
label | a4469103-9cfc-5592-95da-f030161bc8fb |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 87e3ad8b-766a-5f6d-877b-a08c5c82775e |  | note | – – – – – – – – – – – – – – – – –
label | 00b5a61b-fd20-5305-93a9-f22851ee6109 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 2454fee9-b5c9-59e6-8741-3980486f880a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Install SPS to correct height / position relative to track
label | b9ceb6bf-6c7f-5d71-9556-dd13c681e6db |  | note | REFERENCE: Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | a6525e78-ce89-50ab-9a23-33109072429b |  | note | – – – – – – – – – – – – – – – – –
label | a16ff898-5fbc-5c1c-81b2-0ff5ef55901f |  | note | ACCEPTANCE CRITERIA: Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | 687a0a09-507f-54fc-b5c7-435ff15b6149 |  | note | – – – – – – – – – – – – – – – – –
label | 5f7c9c99-338e-5ca6-9c56-4ab70f0a5c6c |  | note | METHOD: Measure, Visual
label | 50a8aa95-bbdc-5f5f-87f8-c239ae2fa9f8 |  | note | – – – – – – – – – – – – – – – – –
label | ecec2481-866b-53c2-8a9d-92c1f843daa9 |  | note | FREQUENCY: Each OHLE Structure
label | b3a7a143-d37e-5c6f-bdbb-7363618bc5ad |  | note | – – – – – – – – – – – – – – – – –
label | f68d0f5c-0ca7-5e6b-965d-be750dd22a08 |  | note | CATEGORY: IP
label | 8b183e01-89f5-561b-a439-14b33fc9c40c |  | note | – – – – – – – – – – – – – – – – –
label | 9299f6d5-3e4b-5ad6-adb0-b78ef4ffc81e |  | note | RESPONSIBILITY: CAT5/MRPA
label | 073442c5-0eed-51d6-ba33-6b55c7e6ded4 |  | note | – – – – – – – – – – – – – – – – –
label | 4142f8b9-1c96-5760-ad66-058cd0e7e29a |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | c3ca1f90-b682-5d99-8cc4-42ca5471b319 |  | note | – – – – – – – – – – – – – – – – –
label | 6ca1b428-9103-5da3-b015-b2177c576956 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | e1091334-a650-58d8-aecb-08442d71ecf8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Cantilever checked once installed.
label | 15250df2-9ee9-5601-bf60-120eb6dbe1dc |  | note | REFERENCE: Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
label | 66bf0ab2-468e-517e-8e73-464cbf403e66 |  | note | – – – – – – – – – – – – – – – – –
label | 93231bf7-63d7-5c04-87fa-b89c5ee9e86d |  | note | ACCEPTANCE CRITERIA: Supervision checking to ensure that equipment is installed correctly.
label | 068427c2-4b8b-5d5b-9146-6324dd35add7 |  | note | – – – – – – – – – – – – – – – – –
label | 322cbb2f-823f-56d1-9d87-dd79e49d4a97 |  | note | METHOD: Measure, Visual
label | add3e80d-0cd0-51af-be70-21c1161a2692 |  | note | – – – – – – – – – – – – – – – – –
label | 5c52cdbb-ed71-52c6-90e5-f3e1302a4d52 |  | note | FREQUENCY: Each OHLE Structure
label | e62a5da6-8207-5d8c-b406-10bdd2978f17 |  | note | – – – – – – – – – – – – – – – – –
label | f85cf3d7-ac7c-5156-8b7a-2225afa21ef9 |  | note | CATEGORY: IP
label | b71e627e-c0c6-5ae4-b6fe-97fe840c43bd |  | note | – – – – – – – – – – – – – – – – –
label | fe7bf8db-6dae-5a52-9b67-a5c48ff8c37d |  | note | RESPONSIBILITY: CAT5/MRPA
label | 92cf09b7-1def-5108-b254-67e8537eb6bc |  | note | – – – – – – – – – – – – – – – – –
label | 3d603d75-9b8b-57c5-92e4-9ddb0e4e956a |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 27dc2827-9d17-5ee1-99b3-d90f546d16c4 |  | note | – – – – – – – – – – – – – – – – –
label | 1dffedf7-1f23-5b8a-b2d2-eb21f7f9d785 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | b570491b-f830-5ae9-be51-d0c2c1308e2e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Installation of wire supports at the correct height and stagger.
label | 39cec311-4f6a-50be-9a3d-6cfebae96b43 |  | note | REFERENCE: Install as per design drawings.
label | 3f793b06-3ee1-5218-9667-24d9c7b6cb28 |  | note | – – – – – – – – – – – – – – – – –
label | cfe32586-4407-5f7e-9cf3-9e28173b863f |  | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
label | c733b666-05fa-5441-b29c-79f0cf84aaa6 |  | note | – – – – – – – – – – – – – – – – –
label | 87db0936-97f9-54da-9d9b-55a7b9b6e72d |  | note | METHOD: Visual
label | 53d8f9e5-ac8d-51eb-8519-dc5c9da91b98 |  | note | – – – – – – – – – – – – – – – – –
label | 89ebf06a-3099-5cf4-9c59-701f8eadd4a8 |  | note | FREQUENCY: Each OHLE BWA structure
label | 92e71d3f-ea6f-5800-8c18-dd2d65386ff5 |  | note | – – – – – – – – – – – – – – – – –
label | 90d56878-3d43-5c1a-b160-40e4e8254ffd |  | note | CATEGORY: IP
label | 9f01578f-7c3a-5d68-9dc7-e6d2deb7e230 |  | note | – – – – – – – – – – – – – – – – –
label | 8990cf0a-31e0-5ca2-aff7-7e9830191951 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 95fe7077-f667-56b5-b465-466eac0d3595 |  | note | – – – – – – – – – – – – – – – – –
label | c2dc6271-e043-5ef8-a87f-dfdeeb3d83d1 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 3dd2a51f-974d-5ff3-91db-224738b4a1f0 |  | note | – – – – – – – – – – – – – – – – –
label | 7c85d623-2e01-540b-afc3-94806c9776b2 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 34ca3eb1-5d7c-5f24-a513-15242fecd520 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Installation of small parts
label | 89dbf4ae-f221-5251-9178-12ad2ddec806 |  | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
label | 547163e1-1dbe-5a77-800a-a24dfe97229a |  | note | – – – – – – – – – – – – – – – – –
label | 18c78d7e-6c1b-5c36-a76a-a653220e9ee8 |  | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
label | 895720b3-ce04-5244-a0a1-e6cc91359aec |  | note | – – – – – – – – – – – – – – – – –
label | 99037496-7b4f-51f0-a0fb-00fc2bbebf8e |  | note | METHOD: Measure, Visual
label | 8ec6eb79-8caa-558f-9133-0ba7e9e9dc94 |  | note | – – – – – – – – – – – – – – – – –
label | 8e8ebdb6-ddb2-5e80-96c7-5ecb7735bc7a |  | note | FREQUENCY: Prior termination
label | 9ee91cb2-f8e4-54dd-b9f9-0167d8917f24 |  | note | – – – – – – – – – – – – – – – – –
label | ef6709a8-490c-5c92-9ea1-e26143088e0d |  | note | CATEGORY: IP
label | 904744dd-88e8-5a45-a581-599c47e455d7 |  | note | – – – – – – – – – – – – – – – – –
label | 183e3647-d825-556f-a172-3927b7037ac4 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 8485e1b8-4f6b-5cbe-9591-c328f0666417 |  | note | – – – – – – – – – – – – – – – – –
label | 7c09ce64-4044-58b3-8a03-360f9c4a8bb8 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | b447d557-d283-55f7-a578-6411998654b6 |  | note | – – – – – – – – – – – – – – – – –
label | bf4c814c-c948-5ecc-b4c9-ec4b7069ef25 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 9a884449-bd96-5bbf-a87b-4868422621f2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Complete Clearance Checks
label | 44be5dfa-59d5-54d1-8d27-cd4ef267ffae |  | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
label | 8c401aa5-9ea8-57c4-a816-ff39bd33f697 |  | note | – – – – – – – – – – – – – – – – –
label | e5b49eee-a4eb-5f8d-9c92-0895b185827d |  | note | ACCEPTANCE CRITERIA: Visual inspection for clearance and wire staging from Hirail EWP
label | 15d9299f-55af-59a2-878c-d07e7ccea1b0 |  | note | – – – – – – – – – – – – – – – – –
label | 06d1cce7-975b-5c19-9b27-a0166171e8e1 |  | note | METHOD: Measure, Visual
label | c0a53bb4-e0c5-5130-bd2a-ef1b3c2e8037 |  | note | – – – – – – – – – – – – – – – – –
label | 1642612c-7bad-52f0-a69e-0c7ac867fb82 |  | note | FREQUENCY: Prior termination
label | 57191d1d-7298-519b-97b5-c2d0d3a1f287 |  | note | – – – – – – – – – – – – – – – – –
label | 6669ac8f-0d57-5e1f-8da8-57de4d05fea7 |  | note | CATEGORY: IP
label | c80c2d3a-e537-5e6f-b370-35837757b1f5 |  | note | – – – – – – – – – – – – – – – – –
label | 911164aa-eb8a-5272-b276-9adaa5c400a2 |  | note | RESPONSIBILITY: CAT5/MRPA
label | d0fafb12-19ed-5d4c-8788-6fe9bb494e4e |  | note | – – – – – – – – – – – – – – – – –
label | 7bef70f8-b115-55af-b3a9-e3fe388346eb |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 94f8bac1-91bb-5cc5-87ef-ea195ad71a77 |  | note | – – – – – – – – – – – – – – – – –
label | b2239774-035d-52af-a474-a00d73b5db5a |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | c26c48b3-a1f9-5bc7-b579-33e824652a9d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Comnplete Pan Run Test
label | bbf62334-33a1-585b-aea8-1daae39c818d |  | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
label | 26f399eb-c7d6-5c1b-a525-b31a548fd3b5 |  | note | – – – – – – – – – – – – – – – – –
label | 664fd989-293c-504b-82fe-9f0f8ee1716a |  | note | ACCEPTANCE CRITERIA: Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
label | 2403e822-f8e1-5c16-8183-2ff504bf8e23 |  | note | – – – – – – – – – – – – – – – – –
label | 4df8c84e-b55e-5097-8b23-0a507713ff7f |  | note | METHOD: Measure, Visual
label | 53285d54-f76b-58e3-a763-d3717e5f7d2a |  | note | – – – – – – – – – – – – – – – – –
label | 74de396a-5e30-5306-a596-c46bcb1f2bbd |  | note | FREQUENCY: Prior termination
label | 276ff33b-a2a2-59b3-bf8d-adac1d5b0f48 |  | note | – – – – – – – – – – – – – – – – –
label | 54e5b85b-6f1e-57c4-a3e1-41565bcacc1f |  | note | CATEGORY: IP
label | ffe18dee-153c-50eb-8752-91dabfae2277 |  | note | – – – – – – – – – – – – – – – – –
label | 09a051f6-c5aa-547e-af32-336824f55700 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 625da7bf-dba0-57ae-b9c8-7965b4299edc |  | note | – – – – – – – – – – – – – – – – –
label | 51153f68-0754-51a2-84da-5cf6d11fef86 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | d49273f1-f9a7-5eb3-858a-e83d3396cee4 |  | note | – – – – – – – – – – – – – – – – –
label | 3e88eb90-4b86-5fe0-946e-2e11c8d69442 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | cc2d6bc9-6c72-58a1-9445-13931429cefd |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Defects/Temporary Works
label | 7b9c7309-6740-5046-a1d4-118a5e730fdc |  | note | REFERENCE: IFC wiring layouts, cross sections and design drawings.
label | e5525e6b-77db-54b4-a094-dd3c1ade290e |  | note | – – – – – – – – – – – – – – – – –
label | a365e8ce-f6fd-514f-bae9-14bd963ea124 |  | note | ACCEPTANCE CRITERIA: Ensure all Defects/Temporary works are capture and closed out correctly.
label | d55e9bba-a8ac-56d0-8782-7b66e9aa9225 |  | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
label | cd65cd3c-b9f3-5a4f-8947-baf8c9bb44c0 |  | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | f5f9e784-a78f-57bd-95b0-20e312c2670e |  | note | – – – – – – – – – – – – – – – – –
label | 3b24d9e7-85ef-5c41-9da4-1e071e6927fe |  | note | METHOD: Document Review, Visual
label | dd0e9eb6-939d-55fb-9a5a-d67a658f4d3e |  | note | – – – – – – – – – – – – – – – – –
label | d95ee0f7-7cbb-5485-8734-3747dede0290 |  | note | FREQUENCY: Each OHLE Structure
label | f0de3209-c97f-54f9-996e-10c96f6ebf1f |  | note | – – – – – – – – – – – – – – – – –
label | ef9ced3d-a83e-5611-9e3f-446d2c49b6f2 |  | note | CATEGORY: IP
label | 368cf96d-8307-5f91-a645-656e432623ca |  | note | – – – – – – – – – – – – – – – – –
label | a2b0f75c-a1b3-58a1-b226-44a51a80a311 |  | note | RESPONSIBILITY: CAT5/MRPA
label | cc289432-23da-56c7-8233-8b8332f69cbc |  | note | – – – – – – – – – – – – – – – – –
label | 74efecc3-2b74-5924-8b6a-af233458f03e |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 09ab1626-e632-574b-962e-d2c95b99dc4a |  | note | – – – – – – – – – – – – – – – – –
label | 9df425a0-d091-5736-bb46-e8543792b16e |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 6c68e43a-5f2a-51c4-8c25-fb576890d8ec |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Relevant documentation readily available. (As-built Survey)
label | af04dcc4-73ff-5c42-87f8-93d32cc76ca7 |  | note | REFERENCE: As built drawings and check sheets to accordance to MTM Design spec.
label | 2cc67f1f-a952-59de-a97c-e9e8812c27eb |  | note | – – – – – – – – – – – – – – – – –
label | 4904c319-99b0-53e1-9ad9-b23ebb2c4fb7 |  | note | ACCEPTANCE CRITERIA: Ensure delivery of relevant documentation to client. As built drawings and check sheets. CAT5/OHLE/CHK/002 check sheets.
label | 12579014-46ae-5a8e-8803-d055df398069 |  | note | – – – – – – – – – – – – – – – – –
label | bef7e962-e822-542e-9dff-0a5ca691e3c5 |  | note | METHOD: Document Review, Visual
label | 51677779-e4ab-554d-8f3f-2a77576cf007 |  | note | – – – – – – – – – – – – – – – – –
label | 4b7b1792-4acc-581e-bc31-fb0d4d81385b |  | note | FREQUENCY: Each OHLE Structure
label | 5f1053a0-9540-5412-be2d-ba70fd7395f8 |  | note | – – – – – – – – – – – – – – – – –
label | 2c0b0420-07b1-55d3-8c82-304925009eee |  | note | CATEGORY: IP
label | c9b92bb2-1b98-5860-ab7c-9acc67ec2c5e |  | note | – – – – – – – – – – – – – – – – –
label | 33dac561-1109-5bd1-9ead-ccb86f5d7fba |  | note | RESPONSIBILITY: CAT5/MRPA
label | 97c578cf-e6cd-5750-8bd7-75c58b3794c9 |  | note | – – – – – – – – – – – – – – – – –
label | e2deb94f-6051-5f53-b884-cffa55ae5cc4 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | f94d271e-6f3b-50f6-8284-e889005d2f0b |  | note | – – – – – – – – – – – – – – – – –
label | dfc785f6-5e49-50c3-bd34-3dd4d97c5d18 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 6e81c321-7e57-578f-aaea-ef0f314ab6b2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | 5d500144-6b31-5380-8222-e47aadfdc0fb |  | note | REFERENCE: MTM Quality Management Plan
label | a8f351cf-6512-56b7-9166-1798c0736c0a |  | note | – – – – – – – – – – – – – – – – –
label | bbc3a735-c784-51ef-85eb-8b908835cf7d |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | d94d17d8-ce51-5d28-9207-e3a05b8a5ce7 |  | note | – – – – – – – – – – – – – – – – –
label | 76864d21-f301-5908-a794-25c4eaa6d6ed |  | note | METHOD: Document Review
label | 5fed554b-8559-500d-8a98-c4a0d062e58f |  | note | – – – – – – – – – – – – – – – – –
label | 77b4577f-2bc4-5ab6-8d5f-6222b03883c0 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 7f85264d-5eab-5384-9e4e-2efcba1cb8ee |  | note | – – – – – – – – – – – – – – – – –
label | 740b0f1c-0ac6-56c2-bce9-6ab1d7422f4e |  | note | CATEGORY: HP
label | 549b3d4e-c593-5a5c-b0b8-9c6e975c5bab |  | note | – – – – – – – – – – – – – – – – –
label | dcb2b9c1-a381-5a48-a23d-500eb3cfc7ae |  | note | RESPONSIBILITY: CAT5/MRPA
label | 2190a9dc-c31f-5d75-aea3-87ce1df711a8 |  | note | – – – – – – – – – – – – – – – – –
label | 12f69d58-fa0e-5d14-af7f-07d4d3050ab8 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 18d9a169-f6e2-58df-9c27-7e7663f782d5 |  | note | – – – – – – – – – – – – – – – – –
label | 9d2a06fc-69b8-5d49-966e-1cf7bc40c52b |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 14c42c22-4397-58b1-8c5f-1881a2356aaf |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | f5d26889-266a-5e18-9fe0-824d714db650 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | f15432e8-4726-5aa8-9b8b-7d3a375a2788 |  | textbox | Name:
text | bee45e76-87e1-5fd7-9100-21a2627e5db1 |  | textbox | Position:
date | 2c65977d-b9a6-5274-b320-4d567966eee3 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-009-STR-Bored Piling | itp |  |  |  | Yes | ITP-009-STR-Bored Piling Rev 0 | 4b9003f8-8151-4362-b039-66f19e04c449
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 52fa5381-7f92-5400-8bb4-c481246ece1b |  | note | Document Title: ITP-009-STR-Bored Piling
label | 2c2d6ba4-28ff-5076-a45a-fc0c47d69bd2 |  | note | ITP Description: Bored Piling
label | 77c717b2-e162-59c0-bf4d-a77a8dd9890c |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 212aef7c-d24e-5d6b-9a39-d5f01812b080 |  | note | Discipline (e.g. CIV/STR/RAIL): 009-STR
label | ad7bfeee-8a64-5903-b907-0feec7fec2e1 |  | note | Revision Number: 0
label | edc909c4-fc3c-553b-8537-14f3aba04e62 |  | note | Revision Date: 11/10/2022
label | 8a5b7355-f54e-543d-a7e4-226209c7c883 |  | note | ITP created by:
label | 23af4e33-d6aa-54a6-9d2b-1711eefd90f6 |  | note | ITP approved for use by:
label | 718adae9-f64d-536f-92ba-1652c207c1ae |  | note | 1.1 - Non Dependent
label | 0631f35f-66c7-597d-8183-07b7471efa09 |  | note | Reference Documents:
label | 575cff68-dc4e-5649-a878-f9e5f0ecf925 |  | note | • VicRoads Section 606 July 2017
label | 67083365-e0a9-5f1e-b3a8-874277c2df0a |  | note | 1.2 - Non Dependent
label | c8bf7e37-ab26-5aa6-ae0a-42f9985b02b3 |  | note | Reference Documents:
label | d639850f-b897-5bde-9f50-7c295372c345 |  | note | • VicRoads Section 610 Feb 2020
label | 9cc3e9c1-75cf-51bb-a7bf-ce607728c2f8 |  | note | 1.3 - Non Dependent
label | 518986af-874e-552f-a608-00d1f86d359e |  | note | Reference Documents:
label | 919e322e-ef2f-5ce2-a4e9-93bb2f88fb9d |  | note | • VicRoads Section 611 November 2018
label | c0451440-8b56-5621-82f4-43e48354165f |  | note | 1.4 - Non Dependent
label | cab47aea-ad32-5f28-a5cf-a62be25952ea |  | note | Reference Documents:
label | 8f7ef28f-6a38-583f-8a36-171b9231c81f |  | note | • AS2159-2009
label | b07381a8-e3fa-5378-a29d-d34fe583c33d |  | note | 1.5 - Non Dependent
label | 4350757c-864a-57a9-8d5a-f089b4625da6 |  | note | Reference Documents:
label | 5407deb2-665b-5435-a4b3-f0520ed3e10c |  | note | • AS3810.1 2018
label | c7480114-60c6-585a-9bc7-cfa268204117 |  | note | 1.6 - Non Dependent
label | 7989f8de-ed7e-50c7-8bae-fb46ecc70ba6 |  | note | Reference Documents:
label | 33fd1675-48d2-5a36-bf5d-0a1b7082c2cc |  | note | • AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | f9ec52d7-6720-55bb-84fe-3df33308254e |  | note | REFERENCE:
label | bc1d6b24-9ed7-5e78-885f-5c6906aeec78 |  | note | 610.07
label | d5f9ba87-c25d-5a0d-9d3a-0bf2a9e56902 |  | note | Table 610.071
label | 5cc1974a-89ac-50de-a22c-9e997d95f708 |  | note | – – – – – – – – – – – – – – – – –
label | 4b367dd5-7fd4-579d-be68-7cf5f43be6bd |  | note | ACCEPTANCE CRITERIA:
label | d2966f00-9e6c-5176-8791-0162a375ccac |  | note | • Concrete Mix is Registered with VicRoads.
label | f3dccb5b-632e-59da-90c8-6046af1fe44b |  | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 3ec1d9a1-482e-5f18-a417-4772bb8a96b7 |  | textbox | Enter: Teambinder Material Approval number
label | f9a27263-c218-5491-90c4-414147c419c3 |  | note | – – – – – – – – – – – – – – – – –
label | 94b11045-40ce-512a-a7e2-3ae694fc84d5 |  | note | METHOD: Document Review
label | 2e927562-6c57-554b-aec9-e3f97f8feb09 |  | note | – – – – – – – – – – – – – – – – –
label | ef74f23c-255d-5a34-8508-733bf9614ad4 |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 097f1e5f-7c08-52e6-9e98-e5f40280abc0 |  | note | – – – – – – – – – – – – – – – – –
label | 726d6a41-cd0c-5581-8b45-ad8c45db4106 |  | note | CATEGORY: HP
label | 8567a3c6-ff1d-530c-893c-b185657990d5 |  | note | – – – – – – – – – – – – – – – – –
label | c3685c7e-02c6-5789-a7de-f3b87a5bde25 |  | note | RESPONSIBILITY: Nominated Authority
label | 1df1af45-6b20-5bb8-a996-bdc8c24b506b |  | note | – – – – – – – – – – – – – – – – –
label | eda71dd0-47f9-52cc-8905-0264cb5ff5f0 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | d5f28fdb-0736-55ce-af0d-cd5e94e71eea |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | b7b645b3-b7e7-5152-9940-259c96e79482 |  | note | REFERENCE: 611.05 (a)
label | ff285166-ba8f-5825-b52f-b6360968bf45 |  | note | – – – – – – – – – – – – – – – – –
label | 0d385491-a8e7-536b-a73d-b029e6425a66 |  | note | ACCEPTANCE CRITERIA:
label | ae7df377-9991-53d8-8a25-ced6a531d247 |  | note | • Current ACRS certification for materials and for bar processing.
label | 46010d56-c566-59a1-9858-089bd6178f46 |  | note | • Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | dfffbb20-5088-5def-ba55-934af8647721 |  | textbox | Enter: Teambinder Material Approval number
label | 442ea5fc-60da-5758-93b6-af84dc2f115c |  | note | – – – – – – – – – – – – – – – – –
label | 7ae33f1f-c621-5ee6-8d60-f61621b0a78d |  | note | METHOD: Document Review
label | b8095f3a-228f-5fc9-9ff4-dfb1450c45f8 |  | note | – – – – – – – – – – – – – – – – –
label | 48c4a90a-eb2a-5e72-8f33-f0fdd24b6fa7 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | cfde858b-1517-5d88-afc1-5d649dbadf4e |  | note | – – – – – – – – – – – – – – – – –
label | 283bfbc9-07df-5a76-affc-c89f27e70428 |  | note | CATEGORY: HP
label | 88d87da6-b010-55e4-bb4d-593715776e9d |  | note | – – – – – – – – – – – – – – – – –
label | 32052a74-8e98-548a-aa1c-8a913f377fcc |  | note | RESPONSIBILITY: Nominated Authority
label | b8bee204-2f5d-52d8-b4c8-416f859e5b88 |  | note | – – – – – – – – – – – – – – – – –
label | f59a0a9a-ca38-533e-88a8-e55f8d7ecc3a |  | note | VERIFYING DOCUMENTS: This ITP
date | 0c7b12a2-1600-578a-9322-1f0e95e3191e |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
label | 32bbadad-28f5-50d2-a490-3dcd320ac940 |  | note | REFERENCE: 610.26 (a)
label | 7060c616-badc-5c47-98d2-703ef853a4e4 |  | note | – – – – – – – – – – – – – – – – –
label | 14e47d4f-c4d9-5d6e-a1c3-dacb68ae5d98 |  | note | ACCEPTANCE CRITERIA:
label | 1a9fc080-304c-55ff-a894-17423053f614 |  | note | • Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
label | ec19b6d3-11cb-5e52-8ae7-95de4bcae11f |  | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 113caa8c-c6d2-5dea-b154-47eb162b7fb6 |  | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 534a4b5c-4f95-5a44-9d89-2b6497937196 |  | textbox | Enter: Teambinder Material Approval number
label | 94afac09-2b06-5244-92cd-289d1a6b4d5f |  | note | – – – – – – – – – – – – – – – – –
label | af2fa23d-5fb8-524e-bc71-de17e9e6a3c7 |  | note | METHOD: Document Review
label | 0937d39c-0c3e-5f37-88f0-d7c46b26a16a |  | note | – – – – – – – – – – – – – – – – –
label | 1f5d6159-5a96-52b7-ae5a-1bb080f0273f |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 54a88e2c-5f7e-5bb3-bcaa-12f26321c2d7 |  | note | – – – – – – – – – – – – – – – – –
label | d2850ffb-79e8-55ce-b986-1e2a64b4ea64 |  | note | CATEGORY: HP
label | 66a4e47c-d3dd-5665-a9c7-6ff3320041da |  | note | – – – – – – – – – – – – – – – – –
label | e9122874-018a-52b0-aeba-bc3d7e58ac97 |  | note | RESPONSIBILITY: Nominated Authority
label | 94283f24-ba4d-5d86-a8f2-55f4785487a0 |  | note | – – – – – – – – – – – – – – – – –
label | 6f7bc0e9-6f25-573d-9da7-5d97e74bea91 |  | note | VERIFYING DOCUMENTS: This ITP
date | f0f2c9ea-9da7-5c02-bd77-f2b2639e3703 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Working Platform certification
label | c9e4fb5c-4829-5061-a064-0a52b86c89aa |  | note | REFERENCE: -
label | 51b1090b-0474-59c2-aaf7-131e1bbc1fce |  | note | – – – – – – – – – – – – – – – – –
label | 60f8af1f-d74e-5c56-8ddd-73469eedfa30 |  | note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement
label | fecc628b-fddf-5eeb-a058-2c9a67fa8374 |  | note | – – – – – – – – – – – – – – – – –
label | 96fc436b-6d09-54d9-95ec-2dfae3171c60 |  | note | METHOD: Document Review
label | c66cd20b-5523-526a-aaf0-5b85b3c1fbe3 |  | note | – – – – – – – – – – – – – – – – –
label | 0f00208e-d935-5441-bbfc-514206980546 |  | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | c8735659-aac2-5253-8d38-e94de6acc01d |  | note | – – – – – – – – – – – – – – – – –
label | a8f3fade-3d78-5549-98fc-4ee905da09be |  | note | CATEGORY: HP
label | bf0b0c4d-6034-5447-92d4-e1bceffb901b |  | note | – – – – – – – – – – – – – – – – –
label | 452d6077-ec8f-5fd5-9057-a0a04ed247a0 |  | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | eb1bc9ac-1ab7-5ee4-8302-d69fde181891 |  | note | – – – – – – – – – – – – – – – – –
label | 0a968724-9d11-5cdb-beba-d5914832af2e |  | note | VERIFYING DOCUMENTS: This ITP
date | a19a7013-27b6-593e-8057-7fa4b759e953 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Piling Operations Work Procedure
label | 7e0a8aec-8c0d-5e82-a802-6c51c52758b6 |  | note | REFERENCE: 606.03 (a)
label | b654e747-4464-5618-8d4e-97f46135f2fd |  | note | – – – – – – – – – – – – – – – – –
label | 237272d8-7bac-5850-9bb4-0a559bb24df2 |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | dba8e25f-02da-5316-a336-edce6a4cc564 |  | textbox | Enter: Teambinder Approval number
label | b43d955d-8809-5d56-876a-15520799e107 |  | note | – – – – – – – – – – – – – – – – –
label | 992ee446-b5f2-5adf-8b9b-62659a7cffc8 |  | note | METHOD: Document Review
label | 16f05ef8-045a-5684-a382-94b23f48f4e8 |  | note | – – – – – – – – – – – – – – – – –
label | 8ff5aed5-e4b7-5710-b054-d47b46c6785d |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | 2ffc20a8-fc6d-5ec9-95b2-3f6301b8cd90 |  | note | – – – – – – – – – – – – – – – – –
label | d016d519-254b-5051-969b-e6c840c7a8cb |  | note | CATEGORY: HP
label | a703042d-3146-5a80-9dfd-13565613045b |  | note | – – – – – – – – – – – – – – – – –
label | 2a800fe2-935c-563c-beed-5b51b71a2ac7 |  | note | RESPONSIBILITY: Nominated Authority
label | a8fd2277-c0a2-5dc1-9695-853a14ca90f7 |  | note | – – – – – – – – – – – – – – – – –
label | cd1e4829-73d9-5521-8942-c523e937f55d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 7122e299-8fbc-536a-811d-e84fa6a22b98 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Temporary Steel Casings
label | e456b16a-c8d7-5389-a6cf-babf89ce0824 |  | note | REFERENCE: 606.03 (b)
label | 15f7d266-1a3c-5a82-b4ab-7de09688bd26 |  | note | – – – – – – – – – – – – – – – – –
label | a3810d3e-de68-5ee8-be9b-4e03b846d72b |  | note | ACCEPTANCE CRITERIA:
label | ea95881e-68bd-51dd-800e-9676018bb233 |  | note | • Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | 6816b67f-c68f-58c9-a6f4-f9c122148828 |  | note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | 98c193b3-cc16-5646-abe5-f506d745acd1 |  | note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
text | a3e0d1f4-e5e5-520a-91bf-262386541ce0 |  | textbox | Enter: Teambinder Approval number
label | 840f39f5-2ccb-5b6d-b116-c6cecabe12c3 |  | note | – – – – – – – – – – – – – – – – –
label | 8da83028-0f4c-5b66-97a8-424124829e68 |  | note | METHOD: Document Review
label | fd670178-9c0b-5d44-ba69-a92ba4a230f6 |  | note | – – – – – – – – – – – – – – – – –
label | a4d4bf0d-6890-5ad2-b75d-72b7f1badb39 |  | note | FREQUENCY: Where applicable, once, prior to use
label | ae147cdd-8a5f-578d-98fa-dfac104a3ebe |  | note | – – – – – – – – – – – – – – – – –
label | 50db6fdc-db64-5ea1-b605-fc7b6d2d7d98 |  | note | CATEGORY: HP
label | 910a22f3-f2d5-56a5-ac5f-01799149a16b |  | note | – – – – – – – – – – – – – – – – –
label | fb1bffe3-e28e-5275-a001-e6443bc8c0eb |  | note | RESPONSIBILITY: Nominated Authority
label | f113513b-2ee4-5f6b-8230-4c9344fa080f |  | note | – – – – – – – – – – – – – – – – –
label | 4225087c-1077-599d-9446-8f51535a0e72 |  | note | VERIFYING DOCUMENTS: This ITP
date | 81a88703-350a-52b7-aee3-8206ee4fddfa |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Casting Under Water Procedure
label | 3904a830-e946-5547-ac51-4f3f42350611 |  | note | REFERENCE: 606.06 (a)
label | 1feb4396-f8ec-5887-8ebc-10aad9a808a5 |  | note | – – – – – – – – – – – – – – – – –
label | ddd424a8-bf09-5690-a6f4-fa40184de56d |  | note | ACCEPTANCE CRITERIA:
label | c4c19078-6ee8-5f5f-9a44-1a6790cdd662 |  | note | • Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
text | d64fa74a-75ea-5e0d-859a-469bc5cc1a09 |  | textbox | Enter: Teambinder Approval number
label | b57fde01-cfd8-53e1-bd8b-300635f51798 |  | note | • Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | d8bfe649-68f9-55e6-8de3-ef97007e4f82 |  | note | – – – – – – – – – – – – – – – – –
label | 72ad5a3a-213c-57cd-bc2c-6b437e11d4f9 |  | note | METHOD: Document Review
label | f505e575-d09e-5f2f-95a6-f2aed13d72ff |  | note | – – – – – – – – – – – – – – – – –
label | f03ced72-3ddc-592f-9882-f81dfee1e333 |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | 54d6169d-96ad-5c02-a41f-11729127d64b |  | note | – – – – – – – – – – – – – – – – –
label | b69d86b2-4034-586e-a7f2-58141432e7d4 |  | note | CATEGORY: HP
label | f030e221-75de-59f2-9fb5-59f5d926efbb |  | note | – – – – – – – – – – – – – – – – –
label | eaf51dec-df6e-54b4-b3b1-0cc51f498499 |  | note | RESPONSIBILITY: Nominated Authority
label | 283fa6bc-6a03-595f-8e85-ea52a0bab996 |  | note | – – – – – – – – – – – – – – – – –
label | 35dbb304-b0e8-5f41-96b9-39123e49f810 |  | note | VERIFYING DOCUMENTS: This ITP
date | 4c33449e-1b0c-532c-97f5-a8e4efafa85c |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Boring With Bentonite or Polymer Fluids
label | 001dc125-dcd6-500c-b420-146886b3499d |  | note | REFERENCE: 606.03 (c)
label | cad15905-5e4c-5ac9-a64e-ce4ad1bf0ed3 |  | note | – – – – – – – – – – – – – – – – –
label | 3af5c556-d1f7-5e00-92b9-024c1e91c924 |  | note | ACCEPTANCE CRITERIA:
label | cb30b0de-6d9e-5046-80b5-1e8cb88fa2b9 |  | note | • Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
text | 47b75531-5066-5a4a-a26c-40dca3632c5c |  | textbox | Enter: Teambinder Approval number
label | 3a493e96-db69-5009-af28-a35957d3ef3b |  | note | • Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | f643b916-514f-51e7-b97f-c24360263e2d |  | note | – – – – – – – – – – – – – – – – –
label | f4ff55eb-ba61-5634-b993-5dce25069366 |  | note | METHOD: Document Review
label | 5f2147e1-f783-5eb0-96c6-d117ac625072 |  | note | – – – – – – – – – – – – – – – – –
label | 28c8f4e8-f3ff-5124-a6a2-693f2a05e4cb |  | note | FREQUENCY: Where applicable, once, prior to commencement of boring
label | fd389d57-d3b3-53dd-aadf-41006fa174fb |  | note | – – – – – – – – – – – – – – – – –
label | b74a2502-8205-5a38-8f97-538c1ce29ef3 |  | note | CATEGORY: HP
label | 221f2711-fc8e-5269-a37a-625b1c929fca |  | note | – – – – – – – – – – – – – – – – –
label | 4e9ebe07-00b8-5e0d-82a6-84ef2b4cab31 |  | note | RESPONSIBILITY: Nominated Authority
label | 1967d4e7-4006-5266-8c12-b6d372fd00cb |  | note | – – – – – – – – – – – – – – – – –
label | 3a7be694-a908-507e-bcdb-43603b85c5cb |  | note | VERIFYING DOCUMENTS: This ITP
date | 0aba3beb-476d-506e-a983-e974ec4bfd94 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Dynamic Pile Testing Procedure
label | 5c07b1d6-dfab-55af-884a-b2ab6c762879 |  | note | REFERENCE: 606.07 (c)
label | 311bb4cc-d826-5393-9a1a-f113d584a08a |  | note | – – – – – – – – – – – – – – – – –
label | e52526ea-2d66-50d1-944a-a4f5f8df5910 |  | note | ACCEPTANCE CRITERIA:
label | 509d0494-64ae-580a-8da7-fd3d3182fb73 |  | note | • Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | b27127e5-91fb-5ecd-ae5f-ce5e6b4acb6f |  | textbox | Enter: Teambinder Approval number
label | ea01df4d-f709-5346-98a5-9ff262eae81b |  | note | – – – – – – – – – – – – – – – – –
label | 1e281150-2ed2-5815-b3c0-4fa6ddb382a4 |  | note | METHOD: Document Review
label | d511e08c-8e2b-53e7-9900-7ffbbd9265f7 |  | note | – – – – – – – – – – – – – – – – –
label | 1f6a6b1f-e44c-549a-8d1e-20988b13f84d |  | note | FREQUENCY: Once, prior to testing
label | dca58c95-8f65-5839-a3e1-c300cbace64c |  | note | – – – – – – – – – – – – – – – – –
label | 4ab1edfd-ba09-592c-b8d8-2b6f28654398 |  | note | CATEGORY: HP
label | 3a49772c-9aaf-5eb9-bb29-e80d4b9fac20 |  | note | – – – – – – – – – – – – – – – – –
label | a4811b54-06b9-5d26-917c-0552e93865a3 |  | note | RESPONSIBILITY: Nominated Authority
label | 6f4dfdbb-d5cb-5874-a4f8-b22a736f2017 |  | note | – – – – – – – – – – – – – – – – –
label | 12ee48f1-8ff3-5fa8-9f68-ac9cb5c79f6b |  | note | VERIFYING DOCUMENTS: This ITP
date | 36f2f781-e3f2-5f62-9061-df0e41067a62 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Pre-qualified Pile Testing Consultant
label | 949c090a-5f08-5478-9eb9-6b2fb2145728 |  | note | REFERENCE: 606.07
label | 09c15931-e4bb-58dd-836b-8b0b863c2717 |  | note | – – – – – – – – – – – – – – – – –
label | 3c834cca-0f6f-595c-b3de-63a23b889d32 |  | note | ACCEPTANCE CRITERIA:
label | b4fef640-36d5-5b6e-b6b6-9b672c17bf15 |  | note | • All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | f28bab00-9f1b-57f8-9958-581c59292a44 |  | note | • Details of the consultant to be submitted for review to the Nominated Authority.
text | 3c43dcb3-7d79-54f9-9ecb-03341fd36f83 |  | textbox | Enter: Teambinder Approval number
label | e0719f0f-37a7-547a-beb3-0ab744ba6858 |  | note | – – – – – – – – – – – – – – – – –
label | 84c6e1f6-b75f-5960-8675-c755ced3f94b |  | note | METHOD: Document Review
label | f8dcb74b-0736-5426-b6be-72a377d687b4 |  | note | – – – – – – – – – – – – – – – – –
label | 19e8dd95-773c-5617-95f5-b454f79d18f1 |  | note | FREQUENCY: Once, two weeks prior to testing
label | 6eb426a9-07a8-5571-b4b0-6512dacfaae8 |  | note | – – – – – – – – – – – – – – – – –
label | b47cbffb-8af6-5ebd-83da-13bb8b8f5687 |  | note | CATEGORY: HP
label | 80ea157a-988b-5387-b602-03c8da33540e |  | note | – – – – – – – – – – – – – – – – –
label | 59de6927-5da8-59a6-b9b9-a19d305d753c |  | note | RESPONSIBILITY: Nominated Authority
label | 6dc45cdb-bd59-54ee-ab9c-a05020fd66d9 |  | note | – – – – – – – – – – – – – – – – –
label | 3cd28b57-5c72-54d7-9e0e-d414e4b26e79 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 9cdf8e14-9488-5b38-8040-390d6ea14540 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 Reinforcement Welding Specifications & Qualifications
label | 8cb2dcf2-d2e2-536e-8ec0-d6d35742729c |  | note | REFERENCE:
label | b1b97f39-2c31-5948-a5b4-ca0da3e2a3b9 |  | note | 611.13 (a)
label | 331e3d42-96b1-53f1-9875-c5a9aa890b7d |  | note | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
label | e2be3a92-7881-584e-bd7f-0d57324f1113 |  | note | 611.14 (b)
label | 0f60840c-ca66-585e-a265-e0df8930d415 |  | note | – – – – – – – – – – – – – – – – –
label | 8abf435e-7794-569b-a13e-fc285151a1ac |  | note | ACCEPTANCE CRITERIA:
label | 2a818cbe-8250-5e8c-89b8-2430bf6c9a07 |  | note | • Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
text | 586166c3-49ec-54bd-b857-cf46a11f2986 |  | textbox | Enter: Teambinder Approval number
label | 2e94e801-47c7-5274-bd39-b3b02a470390 |  | note | – – – – – – – – – – – – – – – – –
label | 17c3899e-091e-5d74-8d0d-4a92be387f37 |  | note | METHOD: Document Review
label | 271f5e56-1024-5b77-a684-6f28a9b9cdff |  | note | – – – – – – – – – – – – – – – – –
label | 0a7ada04-4fef-592c-949c-055aeb489e27 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | a4446d8f-7149-5d79-8a9d-cb8e2e8d7778 |  | note | – – – – – – – – – – – – – – – – –
label | 713edab5-8dbe-5af2-99e6-c4858e002de9 |  | note | CATEGORY: HP
label | c5d29d56-b783-5749-8390-dc308aeb2eff |  | note | – – – – – – – – – – – – – – – – –
label | a04f2a76-5638-5d24-a37a-f52ea38a45e7 |  | note | RESPONSIBILITY: Nominated Authority
label | d8c3d317-3413-5bd8-a09c-1fb5868066eb |  | note | – – – – – – – – – – – – – – – – –
label | 64b8b438-ce43-5734-a700-b629b8637bf1 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 4d25c1c1-cab2-5c6f-b794-8a7657e7fffa |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 184b4294-9264-5d23-9241-a14978164234 |  | note | REFERENCE: MRPA Quality Management Plan
label | e34b3ec0-4605-580a-a874-a7333aefa49c |  | note | – – – – – – – – – – – – – – – – –
label | e708b842-f867-5ed4-987f-15f35eefddc0 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | eb7b3bf9-5f26-5bf0-a66d-200d2c199c98 |  | note | – – – – – – – – – – – – – – – – –
label | 9e098647-e160-51c4-a177-1ac024c58e85 |  | note | METHOD: Document Review
label | e55d27e2-ec5c-54c3-999f-60b054cf55a3 |  | note | – – – – – – – – – – – – – – – – –
label | 573758ee-451a-57e6-b043-5e7ed4a35c0f |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 56994085-35d4-5b8c-acd9-7ba3150e9cca |  | note | – – – – – – – – – – – – – – – – –
label | baf905ab-df5d-58e4-b646-6523719ed01b |  | note | CATEGORY: HP*
label | 638c8d54-14fe-5022-849e-1a073f04efb8 |  | note | – – – – – – – – – – – – – – – – –
label | 05c42d70-6fd4-5c9d-bc4d-ba732ad6827a |  | note | RESPONSIBILITY: All
label | d2da4d9a-c9ec-5b36-936d-f211763c1e2f |  | note | – – – – – – – – – – – – – – – – –
label | 139bb36e-43d3-543d-9790-752c4c651087 |  | note | VERIFYING DOCUMENTS: This ITP
date | 71cdfdfe-aaca-5fa1-b02d-7047ed2cb65d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | f3055229-ef38-52a4-b376-6c66da9578ca |  | note | REFERENCE:
label | 875064e2-333f-547b-bb63-cb4b507ce67b |  | note | IFC Drawings
label | d2ede88d-da9c-5a22-b693-614edca97541 |  | note | 606.08 (a - c)
label | 140794b2-b54a-5de4-9202-60f37206c7de |  | note | – – – – – – – – – – – – – – – – –
label | a799edfb-4eb8-5c88-945e-fa8d5878da16 |  | note | ACCEPTANCE CRITERIA:
label | 5ab8ccbe-6c44-53e0-ba6d-2a21b51ecb02 |  | note | • Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | 82b057a4-0456-5261-a05d-e0a7886deacd |  | note | • Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | b4d5d1cc-5ffb-5f15-8079-50466a497e7c |  | note | – – – – – – – – – – – – – – – – –
label | 9ef45056-24a6-50fc-bf87-37e19594a74e |  | note | METHOD:
label | 56229457-b904-56fa-ab8b-f6bdd85cc5eb |  | note | • Measure
label | 945f6558-c0b2-50eb-ae6c-8e5eb5a0dce3 |  | note | • Visual
label | bc17366f-0a5d-54bb-85c0-00b1b5071f11 |  | note | – – – – – – – – – – – – – – – – –
label | 41a877a3-3719-5e42-9909-5531286b1a43 |  | note | FREQUENCY: Each pile
label | cd381719-59c7-5f86-b2bf-43c2fde0b344 |  | note | – – – – – – – – – – – – – – – – –
label | 202c6e27-3bdb-50ca-bc14-3f29091c8e8b |  | note | CATEGORY: IP
label | 4664b29c-57e1-5240-8f2a-3c1e692fe09d |  | note | – – – – – – – – – – – – – – – – –
label | d860bf65-5f60-59a5-a820-7ef21770edcb |  | note | RESPONSIBILITY:
label | 6ce8eade-cb1e-54df-9db5-919817011b5a |  | note | • Surveyor
label | 0a94276e-331f-514c-b770-0332d60bf15b |  | note | • SE
label | dc614ca9-eaa0-5f4b-8068-c83f7bc01a2d |  | note | – – – – – – – – – – – – – – – – –
label | f3c3d0be-9661-5e9e-9b51-084573630029 |  | note | VERIFYING DOCUMENTS: This ITP
date | a94efc2c-a997-50f9-8473-05e6d9530fde |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | 5e338647-ed2d-57cd-8efb-e55936763916 |  | note | REFERENCE: 606.04
label | 46d1ace9-4e9a-5a2f-8375-6c7694d6c94b |  | note | – – – – – – – – – – – – – – – – –
label | 8415349c-8677-56ed-b1db-78971afeba43 |  | note | ACCEPTANCE CRITERIA:
label | d26b7935-1345-5298-a7a2-4b2f9299ad20 |  | note | • Pile construction shall not:
label | 6c1a4094-15a0-5b4e-a469-bffcd696d9f5 |  | note | i. result in damage to adjacent newly cast piles due to ground vibration.
label | 9b2b3aad-edb8-53b6-9a16-e79b4b73551a |  | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
label | 256723e0-9f86-50e6-b97f-ba588e25efaf |  | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | 805b535a-ed9b-5dea-a9a4-7b3d0e3c1225 |  | note | – – – – – – – – – – – – – – – – –
label | 981f3aab-68bd-5a49-951b-3c5148b18cf5 |  | note | METHOD:
label | dc17e302-2089-5633-85ca-c46ecbe2cb17 |  | note | • Measure
label | 9919623d-8707-5d8d-9483-a38fe79a16d5 |  | note | • Visual
label | 4c01efbb-bd0c-52ff-bfd5-4d319894697e |  | note | – – – – – – – – – – – – – – – – –
label | 5bb3c1e5-fc40-5e55-9b45-3348da745c30 |  | note | FREQUENCY: Each pile
label | 8f0650ad-4594-5447-9144-881d88ca72a7 |  | note | – – – – – – – – – – – – – – – – –
label | d9a81f05-ecf8-5479-8cd0-4ad55c62c049 |  | note | CATEGORY: HP*
label | 1123222d-0b36-5b39-a79b-7e328f0fe89b |  | note | – – – – – – – – – – – – – – – – –
label | ef2c4f50-59ab-54e5-98b9-86cd5787f04e |  | note | RESPONSIBILITY: SPE/PE
label | a862cc19-4139-59ea-af80-6df0d0cc65a1 |  | note | – – – – – – – – – – – – – – – – –
label | 985b2886-668e-5af2-a2ef-39931d3a9a89 |  | note | VERIFYING DOCUMENTS: This ITP
date | 4b241ed0-be67-5111-9d39-649aa1f480be |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Boring Operations
label | 5b8af99e-6c5d-59a3-9a34-31a3c89f19c2 |  | note | REFERENCE:
label | 6cb2092f-3bee-57f1-bfaa-ea142eada30b |  | note | IFC Drawings
label | 9e1d41b5-515e-5faf-80af-7ca645aae55d |  | note | 606.03 (a)
label | 0ebfafec-d047-55b8-8b9f-fb20a3d7b14c |  | note | – – – – – – – – – – – – – – – – –
label | 2c0095f2-2862-5410-8304-30fa06960bb1 |  | note | ACCEPTANCE CRITERIA:
label | 8f47e637-4c94-5d3f-8a53-d9444e603c9d |  | note | • Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | 45d3792e-2573-595f-98aa-4ded19451085 |  | note | • Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | 9a6812e1-fefd-57aa-93ee-489b4126985b |  | note | • Excavation clean and de-watered (where applicable) for inspection.
label | 2594c267-2586-5cc9-99bb-0dc569a2e9c3 |  | note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
label | 2bdb2e0d-c713-592e-9607-df67e49431a1 |  | note | • Excavated material to be disposed of as appropriate to maintain a clean site.
label | 6c6206c5-872e-5527-bc8d-f4612a28aa8b |  | note | – – – – – – – – – – – – – – – – –
label | b30ccc7b-c7ea-5cd1-989c-60f3bab8602e |  | note | METHOD:
label | ff2424e6-d1a3-593c-9ceb-f8eba0c46367 |  | note | • Measure
label | c7afa41d-1be8-5cc2-b24f-f687ba6d9f01 |  | note | • Visual
label | 1b71b34d-9333-5ea6-9daa-44018cd4d030 |  | note | – – – – – – – – – – – – – – – – –
label | 267c3edc-82f0-5db2-b49a-f79abfc15457 |  | note | FREQUENCY: Each pile
label | cad0a253-f81a-5778-a573-a340303072a3 |  | note | – – – – – – – – – – – – – – – – –
label | 53757d1c-896a-5a95-930f-8ba012c46f85 |  | note | CATEGORY: IP
label | de9826b9-4550-53bd-b625-90c97b4a8360 |  | note | – – – – – – – – – – – – – – – – –
label | e2693023-ac06-53ce-9719-35dcea95b488 |  | note | RESPONSIBILITY:
label | 86d7c5d0-7977-5460-bfa9-155136dc450f |  | note | • Surveyor
label | 28ed8a7b-8426-5b58-ad05-260bc888747f |  | note | • SE/PE/SPE
label | f6056cfe-6072-530d-91c2-9c1903b24262 |  | note | – – – – – – – – – – – – – – – – –
label | 37247ee1-c7e7-5830-9005-f9318539760e |  | note | VERIFYING DOCUMENTS: This ITP
date | 0e630cdb-cc92-57ea-a7bf-7fb3249d973f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Extension
label | b6797db5-8f1a-5193-960d-6162774d4f57 |  | note | REFERENCE: IFC Drawings
label | 3a642acc-e973-5d2d-aa46-dd87c899619a |  | note | – – – – – – – – – – – – – – – – –
label | c64c778e-233b-5376-8d93-58cb46d78714 |  | note | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
label | 537b60d5-be34-589b-80c6-8e505b721fb3 |  | note | – – – – – – – – – – – – – – – – –
label | f9d6c7d1-f73b-57a8-b17c-b1170d72b340 |  | note | METHOD:
label | f62c4634-93b5-5502-a923-081f923fa7e7 |  | note | • Measure
label | ef2e9789-c3e2-5ce9-b88b-193c4e2fa5bc |  | note | • Visual
label | 923f0a66-f885-54c3-8756-8ca88e3c4c04 |  | note | – – – – – – – – – – – – – – – – –
label | 2dd2653e-7e45-5caa-8540-fb632987de53 |  | note | FREQUENCY: Where applicable, each pile
label | f66a9886-1989-597a-8d65-4071e9baf443 |  | note | – – – – – – – – – – – – – – – – –
label | 1965134d-646e-5749-a673-1b742a458048 |  | note | CATEGORY: IP
label | 64a24485-efd7-560e-93bf-de8310b5e2c2 |  | note | – – – – – – – – – – – – – – – – –
label | 0f0c593e-22e2-5351-a7e5-b3981c0e8ed0 |  | note | RESPONSIBILITY:
label | 14f0ab65-6e6e-5ea9-a9f2-4904c8dfb1f5 |  | note | • Surveyor
label | 02c1340f-0d7a-54ae-96d7-fd6b22c44ab4 |  | note | • SE/PE/SPE
label | 1d028e00-25b3-5ae6-b554-cc6154120bd6 |  | note | – – – – – – – – – – – – – – – – –
label | 93cdbda8-4d09-504c-a9e8-cb72349e854e |  | note | VERIFYING DOCUMENTS: This ITP
date | a008f0c7-beb7-54d4-9e90-344c0e389b4c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Inspection of Pile Excavation
label | 908cf23f-a48f-5715-9380-6f6741f5c945 |  | note | REFERENCE: 606.05
label | 43730929-0469-5104-97d1-539ba8ddcfa4 |  | note | – – – – – – – – – – – – – – – – –
label | 22636935-6f74-555c-accb-83e50300849a |  | note | ACCEPTANCE CRITERIA:
label | 41772c49-c836-596d-beb4-93d795f80af2 |  | note | • Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | c4178880-fc19-50d1-8b1d-0d6d9e8c45c2 |  | note | • Attach: Geotechnical Field Sheet or Report
label | d77bd15a-2d42-5ba6-9692-9f5b46ef2821 |  | note | – – – – – – – – – – – – – – – – –
label | 4723d3fb-304b-594b-bfb0-38be12df114c |  | note | METHOD:
label | e5e7e527-9976-58be-99e5-40f80b5d7062 |  | note | • Measure
label | 27174d12-2b72-562b-ba02-e7d57e432b9c |  | note | • Visual
label | 9a1ebe36-dd48-5550-a665-28757e5893ec |  | note | – – – – – – – – – – – – – – – – –
label | e522095b-7525-594e-9fe0-59f394ebe085 |  | note | FREQUENCY: Each pile
label | 8a5c9aa4-19b2-59f6-9917-d0fb942dccc9 |  | note | – – – – – – – – – – – – – – – – –
label | b0d24629-e0bc-54ff-831f-c1a0770848d8 |  | note | CATEGORY: HP
label | 44fe9f1a-8592-538a-a376-a0e9b073f85b |  | note | – – – – – – – – – – – – – – – – –
label | e8f481f0-f047-5c74-b6e2-6062226d91d6 |  | note | RESPONSIBILITY: Geotechnical Engineer
label | f7ace0eb-22c6-5e2d-aa8e-24b52ae0251e |  | note | – – – – – – – – – – – – – – – – –
label | dc33544c-3543-547d-afae-15a5226c47d1 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | e7a266df-097b-5cb4-9207-b97035b57229 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Reinforcement - Placement
label | fb41695d-4601-5774-8c57-71aebac387d8 |  | note | REFERENCE:
label | 5fc19c93-04b7-570b-887f-8eff9e08a652 |  | note | IFC Drawings
label | b9fdaf84-1330-5f0f-a850-b0b8367ccac2 |  | note | 611.06
label | 55106d6f-c2c8-527c-937f-a245e8a0f34f |  | note | 611.09
label | 8757a8ad-d9e6-59f3-9af0-8486e1160e0c |  | note | 611.10
label | 70741d57-6763-523f-9ce2-c2f7f8063189 |  | note | 611.11
label | 86d984d2-fa34-544c-bed1-7ea5c8f433ae |  | note | 611.12
label | 4c82e585-c868-5105-90bd-96812e916b48 |  | note | 606.06 (a)
label | 293bf9ab-dac9-542c-b580-d648291a88bf |  | note | – – – – – – – – – – – – – – – – –
label | f3c08f0f-9589-5fb6-bdb2-4d8a211963ac |  | note | ACCEPTANCE CRITERIA:
label | 0f567ff5-3e64-5b63-b122-32a19e365626 |  | note | • The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 1ef96832-5a55-551a-8ceb-38c496149828 |  | note | • Projecting reinforcement is the correct length and location.
label | 933c190b-94b3-52a5-a3cd-621be900be85 |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | 28f3d39a-6ccb-58e8-98a4-3722bde1216f |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | c9bb9db2-51c2-59bc-ab3b-4465f37f24c9 |  | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 276cf8db-c4d6-5f63-8aa4-812b031c619f |  | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 40728aff-b0dc-5831-8e20-31693cc312c5 |  | note | – – – – – – – – – – – – – – – – –
label | 7b68cae8-22fc-58a6-a69f-47637d29e8ad |  | note | METHOD:
label | 9c04c931-5e42-5e8b-af6d-27ad8ae3e1d6 |  | note | • Measure
label | fe4fa412-8332-552c-ba52-490cb7a8d57a |  | note | • Visual
label | 884ff9db-867f-5993-b8b2-330fe176e154 |  | note | – – – – – – – – – – – – – – – – –
label | 3bf54891-f033-51bf-853d-f113f73ffdf4 |  | note | FREQUENCY: Each pile
label | 0702d125-2bf3-5898-b54b-5178a030d226 |  | note | – – – – – – – – – – – – – – – – –
label | 6f92b7db-1bfe-51ee-a86f-fcb05d65cd30 |  | note | CATEGORY: IP
label | 113626d2-601d-5a41-8b35-fada598facba |  | note | – – – – – – – – – – – – – – – – –
label | 95bfc037-64d4-54af-be32-250046e6b1d6 |  | note | RESPONSIBILITY:
label | 4f38a872-d9c6-5602-a9cc-4bd5a9862d8d |  | note | • Foreman
label | 3c001345-f79d-52ce-b27e-1ffbfc5a8d41 |  | note | • SE/PE/SPE
label | ed0c5e4d-1b95-51b4-8f0b-b167ff730859 |  | note | – – – – – – – – – – – – – – – – –
label | 662074ae-ffc4-57bb-abeb-f06a9eadc7b1 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2254d36e-4dd1-5b4b-8192-1cec69b60d7f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement - Electrical Continuity
label | 6c2ffd54-2acf-5267-9f86-5164124cf2e5 |  | note | REFERENCE:
label | f4e76d9c-5430-5e17-881e-8dc644f4fe6a |  | note | IFC Drawings
label | 747e0529-ad44-597e-9684-d7f6c48e2fa4 |  | note | 610.29 (d)
label | c718903d-0cb8-55cb-9fc8-a469b2e8e2d2 |  | note | 610.43
label | b115b553-24b5-50f7-90ab-17aae259db3e |  | note | – – – – – – – – – – – – – – – – –
label | 979818ba-544d-540d-8bc4-d47010142c4c |  | note | ACCEPTANCE CRITERIA:
label | 78e47b44-8d11-5134-b149-710d33ff2d44 |  | note | • Pile reinforcement cage to be made electrically continuous by:
label | e7dd9145-1004-580b-be2f-b167866c6ce4 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | e16569dc-fcc6-5f73-a617-cadec8df7798 |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | 16c0a444-c56a-57b2-ba60-695cccb5254c |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 47f22b2d-bd2d-54a4-9404-984ffdedaca8 |  | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | 1a69d8df-d934-50ec-8225-2c4c33b0f9e8 |  | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | c4cb3727-fa70-573a-90ef-f1e56bc8e7eb |  | note | – – – – – – – – – – – – – – – – –
label | 50f3482d-792e-540b-bcce-475b3b72ace5 |  | note | METHOD:
label | 15a1905b-0ef8-5981-bf03-18dccba90531 |  | note | • Measure
label | 78d99041-3651-552e-a44d-13825c6226b3 |  | note | • Visual
label | c32ee306-a0c6-5276-9482-5e620c25f987 |  | note | – – – – – – – – – – – – – – – – –
label | 20f753cb-730b-5964-a754-baaee7889514 |  | note | FREQUENCY: Where applicable, each pile
label | 8981778c-3d94-5e45-95d1-35c111cda609 |  | note | – – – – – – – – – – – – – – – – –
label | 9a3bb6cd-5dd3-515d-8fc6-992495f38c71 |  | note | CATEGORY: IP
label | 6efb60c4-7dd4-582c-b5a7-73c8a77c852a |  | note | – – – – – – – – – – – – – – – – –
label | 30fc4f1e-3e2c-574e-9706-7169f65fbcc3 |  | note | RESPONSIBILITY:
label | 94d6596b-3067-5047-8928-feec3addb5d6 |  | note | • Earthing Engineer
label | 776b0787-d915-5d7c-a5d0-e435ab62b959 |  | note | • SE/PE/SPE
label | 0906dde0-2855-5f04-a52e-f5c041ba9f9d |  | note | – – – – – – – – – – – – – – – – –
label | 8731249b-b035-597a-a7ab-48e0c6b92d5e |  | note | VERIFYING DOCUMENTS: This ITP
date | c13d8d7a-518a-566c-8612-7513718b8798 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | f0a91598-6448-57bc-b8af-f38b277da2e3 |  | note | REFERENCE:
label | bc3857fb-626c-5787-a7a7-8dae8a1d7662 |  | note | IFC Drawings
label | 3700168f-c94a-5bbb-bc1e-501cbf60bae7 |  | note | 610.46 (a), Table 610.462
label | f1b455e0-5de8-5a2d-9901-2c92d942eb11 |  | note | 610.47 (a), Table 610.472
label | 585df82c-bc6d-5a4d-bd19-0d3ee9f4853a |  | note | AS3810.1 Table 3.3.6.2
label | 1a07fe37-4f67-5626-a373-85006a15b895 |  | note | – – – – – – – – – – – – – – – – –
label | 3221b025-b921-5202-94a8-270b087f1070 |  | note | ACCEPTANCE CRITERIA:
label | a4d9b194-d415-598c-9848-0bfaabb3cbe8 |  | note | • All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | c44d62cc-b033-51bc-aae0-4112ac8426e1 |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 5456c545-8965-50fb-b79e-4f7c42629d45 |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | c5b6b0ff-9bc5-556d-8821-122d431eb926 |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 6458a195-221c-5ee8-ac7b-68e3caeac690 |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | b75b63b6-12fb-558e-b0e6-931064d31e30 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 1fd5e36b-a5ee-5923-885d-d4efb50e25ee |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 9c6ba492-b335-5918-a3d3-5aacabbbb3b5 |  | note | iii. Ducts and conduit location = ±12mm
label | d941cae4-0d08-5d92-837f-64b6f65ba284 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | da8101df-b5c9-571c-9b80-e24e791e5547 |  | note | – – – – – – – – – – – – – – – – –
label | 4c678050-0bb9-5753-8227-4762d3b70fe2 |  | note | METHOD:
label | 5cbb054c-9bfe-5fc3-b45b-49fb4d73bea3 |  | note | • Measure
label | 36e075bc-4c5a-55f9-982f-23ccc72baa72 |  | note | • Visual
label | 8c534a50-b451-5ee6-83a4-0b21e571e45d |  | note | – – – – – – – – – – – – – – – – –
label | c24a57ef-338d-57b3-91da-d67e322098a9 |  | note | FREQUENCY: Where applicable, each pile
label | bc04cb35-4eaa-5514-ab3c-7c1106067e18 |  | note | – – – – – – – – – – – – – – – – –
label | 7b90119f-9bdd-5db5-900c-858d5fb5df06 |  | note | CATEGORY: IP
label | a1aec0ae-3db3-51cf-80af-e622c01e660d |  | note | – – – – – – – – – – – – – – – – –
label | b4d93bb1-6dc3-5085-8293-26f0bf2f5f5f |  | note | RESPONSIBILITY:
label | d37adf33-1060-5967-9655-8318ca04949b |  | note | • Foreman
label | e035e217-0090-540f-be1d-a9d97b8884bb |  | note | • SE/PE/SPE
label | 100b2ddc-6c43-5a86-8355-0eecdd95943d |  | note | – – – – – – – – – – – – – – – – –
label | e6290714-cee7-5643-865e-03ea3479b016 |  | note | VERIFYING DOCUMENTS: This ITP
date | 7fc1ead9-e925-51a7-b6a6-fce481acbdd8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pre-pour Inspection
label | ccb1aea9-6ca7-53ea-b218-af9499528574 |  | note | REFERENCE:
label | a9891590-b6c8-55ff-b539-f439bddec7a0 |  | note | IFC Drawings
label | 683d2725-6d12-5768-802f-ee1f467d677c |  | note | 610.18 (a) (ii) & (iii)
label | 6ef80670-3582-5f72-be8b-5d527fcf7ad4 |  | note | – – – – – – – – – – – – – – – – –
label | e9b1522e-ac3a-5c3e-9c5b-9e907f9054a9 |  | note | ACCEPTANCE CRITERIA:
label | aaae04ef-c689-58c7-8f25-b5f5a6bcbe75 |  | note | • Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | de845f86-3434-50d1-9344-6a7005ed30c7 |  | note | • All foreign material has been completely removed from the excavation.
label | d56c7d52-e2c5-5907-b8ae-3c35c7f67c17 |  | note | – – – – – – – – – – – – – – – – –
label | 8a6aa75e-5d48-553d-b102-5e9ef49fbe8d |  | note | METHOD:
label | f0c3167d-6bd7-5381-8fe3-43d7b4e3421e |  | note | • Measure
label | 57e01dd4-ce13-5445-8f2b-de1e37be6e3f |  | note | • Visual
label | 6a0aea67-d1fa-5741-9e52-4e3d497105f2 |  | note | – – – – – – – – – – – – – – – – –
label | 34f8de60-219e-5434-9e08-fa22065fad92 |  | note | FREQUENCY: Each pile
label | 384dc97d-5246-5180-9fb8-db077d00cc5a |  | note | – – – – – – – – – – – – – – – – –
label | 20e89be9-7499-5664-aa4c-1aa6951ff23b |  | note | CATEGORY: HP
label | 3211e7f8-57ac-5a84-83f4-de7231dc18f5 |  | note | – – – – – – – – – – – – – – – – –
label | db64ed9b-83c2-5eac-992c-3375022d095d |  | note | RESPONSIBILITY: Nominated Authority
label | 43caab17-7a72-5fdc-b4b8-f9618f690fb9 |  | note | – – – – – – – – – – – – – – – – –
label | 8fd5b646-bab6-5104-9b39-44210d140ce2 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 2b0094f7-efa9-53b7-bee3-fe70277c95fa |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Weather Conditions & Evaporation Limits
label | 4ae13755-0459-5a88-862b-b2ec265b2ad8 |  | note | REFERENCE:
label | da60b163-8e44-5513-b514-041d7e9b62b0 |  | note | Hot and/or Cold Weather Concreting Procedure
label | 837243e0-2032-5278-8fb0-18512655f7f8 |  | note | 610.17
label | 495dcee6-6065-53b4-ad86-a1f1d80c5a8e |  | note | 610.17 (a) & (e)
label | 75141da4-fffc-576e-bb8a-01e101f6b2cb |  | note | Table 610.171
label | 9326bd23-5b67-501e-97a9-1a0ec8271e7a |  | note | – – – – – – – – – – – – – – – – –
label | 98598ef7-ea29-5a29-8c7e-817e6935ad69 |  | note | ACCEPTANCE CRITERIA:
label | 799a343f-1b38-520f-8134-012a086119d7 |  | note | • All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 64ae8e62-55c5-531c-aa46-4e5f71532de5 |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 5da17b89-0d0a-52e3-b0eb-b801f7d7e379 |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | d7ac17e7-4e97-508e-92c1-41f7111e4535 |  | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | bb4f1306-aa0b-5670-8bfa-7d031abdf776 |  | note | • Record: Required information on the Concrete Pour Record.
label | 0138f79c-efa8-585c-ba68-e0f6b976b926 |  | note | – – – – – – – – – – – – – – – – –
label | d5d7887b-04d7-5c7c-afb9-274f49cace75 |  | note | METHOD:
label | efe53f2c-74c1-5899-a49b-aff7568f3d0e |  | note | • Measure
label | 231c83f2-f1ad-5fb4-822b-101796f8338f |  | note | • Visual
label | e6785d06-da06-5be5-8b13-6bf2cfabebce |  | note | – – – – – – – – – – – – – – – – –
label | c074d7ed-b147-52f8-b849-9e371c8153bd |  | note | FREQUENCY: Each pile
label | 047b7264-e22b-54bb-830a-ea13e5a8b523 |  | note | – – – – – – – – – – – – – – – – –
label | a85730ce-ef27-534f-a464-29cbd462dbdd |  | note | CATEGORY: IP
label | 2b776525-4e6a-5dcd-8047-ccad2afa9bef |  | note | – – – – – – – – – – – – – – – – –
label | 9360dad6-667a-57fb-8e03-754531855cea |  | note | RESPONSIBILITY:
label | 5c07b353-4e98-57f7-9b89-bef30c66c002 |  | note | • Foreman
label | d743607e-3c9e-5708-baed-7068ffc1e981 |  | note | • SE/PE/SPE
label | 6379ad95-c7c8-55cd-ba97-952e5fe11a8d |  | note | – – – – – – – – – – – – – – – – –
label | 70a3e1f6-79b8-5651-b3d7-d0cd19ebfab9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 07515d90-b409-51b8-8ea3-8837206546ec |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Sampling Frequency
label | 1382ce67-6442-5c1b-aa61-e326e19ff602 |  | note | REFERENCE:
label | 74328e2d-331e-5997-8f59-d5f4444882d4 |  | note | Site Sampling & Testing Procedure
label | 75e52dc4-202a-54e7-96e5-815be23ee4b6 |  | note | 610.16 (b), Table 610.161
label | bc6492e5-c756-5ead-b454-83a7111cd4e8 |  | note | – – – – – – – – – – – – – – – – –
label | 92a280e0-b343-54c8-91e3-9fb087904179 |  | note | ACCEPTANCE CRITERIA:
label | 1a785b38-c52c-59d5-8af6-a64fd799bd23 |  | note | • Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 5199c201-07bc-5da1-ad6c-88c62a209bd1 |  | note | 0m3 to 10m3 = 1 sample
label | a689f10f-4bda-582c-9ebb-f7c6c1482eba |  | note | 10m3 to 25m3 = 2 samples
label | 92602b1d-849b-58e9-a91b-013dbed21be8 |  | note | 25m3 to 50m3 = 3 samples
label | cefcecbd-49b9-53dd-a4c4-abc29209cade |  | note | 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
label | b9a12f12-b1cb-5d49-a7fa-ddb24c17f29b |  | note | • For each additional 50m3 and additional sample shall be taken.
label | 7dede268-4ff3-5730-b6b5-0ef669c80fac |  | note | • Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | db88e327-3a66-582f-a5d5-a459573de9d9 |  | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 6a0cfb67-553c-5fcc-a96c-082b9f5e0d37 |  | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 65517170-454d-51a7-8f81-2eef058f0aaa |  | note | • Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 4ce33dbc-6d13-5020-b3fb-1e5e0101db82 |  | note | • Record: Required information on the Concrete Pour Record.
label | bdf0bd54-13af-50a9-a5af-4007b5bf58ef |  | note | – – – – – – – – – – – – – – – – –
label | 87be18f7-a81b-557d-b277-4780894811c1 |  | note | METHOD: Test
label | 3b2f5893-e05f-582d-8c0b-7b5e76629253 |  | note | – – – – – – – – – – – – – – – – –
label | 852eca50-5c93-555b-ab86-258795766bed |  | note | FREQUENCY: Each pile
label | ea8f2c30-c385-5d66-b8f2-9edb55226947 |  | note | – – – – – – – – – – – – – – – – –
label | 54bfc334-b141-5188-81d2-565f61d5c802 |  | note | CATEGORY: IP
label | b5fcb9e3-0d7d-5cde-a2bf-2ff2be3fc568 |  | note | – – – – – – – – – – – – – – – – –
label | 710cdc76-9746-5928-9675-c5180ca05cb4 |  | note | RESPONSIBILITY:
label | 26214e97-442a-57fc-9baf-ba2a926a479e |  | note | • Concrete Tester
label | 67d349a6-8821-5e46-a034-05c84a206983 |  | note | • Foreman
label | 1d8c52c9-e16c-599a-a750-8ebaf021dc8a |  | note | • SE/PE/SPE
label | 6d7f106c-999d-5491-ae16-d0a98809ccf8 |  | note | – – – – – – – – – – – – – – – – –
label | f7732eda-68e9-5186-bbb9-90f1c44c1244 |  | note | VERIFYING DOCUMENTS: This ITP
date | c82d4c33-ea30-5911-8c68-d1709c6646dc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
label | 303c18a3-aafc-555c-aedf-dcdb9165d8c4 |  | note | REFERENCE: 610.13 (b)
label | 0f5311cd-fc2d-5270-8aaf-fcd70e91fc97 |  | note | – – – – – – – – – – – – – – – – –
label | e6692335-b494-5984-8e42-3a1b7b6ece48 |  | note | ACCEPTANCE CRITERIA:
label | eed3bb58-905c-5e0d-a1c9-6a52bc81abb6 |  | note | • Spread range = 550mm to 750mm
label | 000e0527-af76-584b-86b1-9aab605d80cf |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 5e9bde99-95f2-5f34-94b2-622908681825 |  | note | • Passability = ≤10mm (aggregate height differential)
label | d796fb8a-3094-541b-a455-03dc12782410 |  | note | • Record: Required information on the Concrete Pour Record.
label | 1bc37562-78b2-5cde-9d30-c02ac544979e |  | note | – – – – – – – – – – – – – – – – –
label | 1261a5c6-4c8b-56d8-b20d-e0af62150bc2 |  | note | METHOD: Test
label | aaa9aca6-cfcc-5ee1-a6ee-82e4af00af55 |  | note | – – – – – – – – – – – – – – – – –
label | 7d37e873-ecb8-5432-9dd1-8ecbf51e63b9 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | b0d0dda2-d781-5ce1-8bcd-53504ca3b69e |  | note | – – – – – – – – – – – – – – – – –
label | cd78d7fe-d772-5aa3-a192-42b7cbf83d8a |  | note | CATEGORY: IP
label | 22e1bc46-81d8-575b-9ef3-ffb8ee076f2d |  | note | – – – – – – – – – – – – – – – – –
label | 3163e72a-fb4a-5c06-aa8d-6dd92d9e8314 |  | note | RESPONSIBILITY: Concrete Tester
label | 55964e68-9a0c-5e51-8ef4-3ddf844f409a |  | note | – – – – – – – – – – – – – – – – –
label | ef799eb4-9997-5cbf-99d6-c2fa1cc04a09 |  | note | VERIFYING DOCUMENTS: This ITP
date | c6719e76-32f8-5c24-a0c9-ed771379883c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
label | e22309a8-efd7-5d10-aedc-4165fdbaa8b9 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16
label | da1614cc-ff53-5d9a-82ff-11182e2a5948 |  | note | – – – – – – – – – – – – – – – – –
label | 3bdd4925-ad2d-556d-8427-df34ed6cd274 |  | note | ACCEPTANCE CRITERIA:
label | cae0acd7-cd78-57dd-a033-b2940e16e295 |  | note | • Correct quantity of cylinders manufactured per sample.
label | 6773aefc-1b63-5003-87b3-36acf215458e |  | note | • Record: Required information on the Concrete Pour Record.
label | 57942b8a-3d0f-5678-a346-19c5be20c6c6 |  | note | – – – – – – – – – – – – – – – – –
label | b8672514-f96e-507d-89fd-a5dd611aa725 |  | note | METHOD: Test
label | b7f6e96e-63a7-507f-91f5-cf308d9de5c6 |  | note | – – – – – – – – – – – – – – – – –
label | 20b7fbfe-7a6f-5c34-b3a1-371f5365e9ec |  | note | FREQUENCY: Each sample
label | 131c288a-3c39-5202-9266-69faf2868d85 |  | note | – – – – – – – – – – – – – – – – –
label | 4ca6b648-9d3a-54f8-b604-cc68911b68ca |  | note | CATEGORY: IP
label | 1f661a58-c6d8-5b27-a06e-338ded7b56a1 |  | note | – – – – – – – – – – – – – – – – –
label | 082603b4-a64b-5353-8469-684876be589a |  | note | RESPONSIBILITY: Concrete Tester
label | 90cc3038-3c79-5108-97b9-ccdf32aac757 |  | note | – – – – – – – – – – – – – – – – –
label | a30a2b2e-373f-538a-86bd-3fcb4dc6e6b0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6d71efc3-3367-5ed7-8143-c3dea5fed8a4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
label | b9bde0a9-e2c0-56bb-a5c9-2f44083d3c51 |  | note | REFERENCE:
label | e920d1f1-481e-559c-9879-17320836f83f |  | note | Piling Quality Procedure
label | a10fdfb0-8200-5717-8b38-16d01aec4caa |  | note | 610.18 (a) & (b)
label | 80dc3c58-7689-56ab-bbce-7295add6fd7a |  | note | 610.18 (d) (i)
label | 9c399a3f-4ff3-5506-a2fa-618e96496364 |  | note | 606.06 (a & b)
label | 1baf149c-76c4-5d03-9720-4da2f518124c |  | note | – – – – – – – – – – – – – – – – –
label | cd5dca6d-abf6-5dbb-875f-c5231b3b35aa |  | note | ACCEPTANCE CRITERIA:
label | b8ed5be6-917f-55ed-8fd1-b2e0dbe69d83 |  | note | • Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | c1a383a0-40c3-5b1e-9b75-146387fd68ee |  | note | • All concrete batches are traceable.
label | 2a18c480-6373-51b0-972d-4f2573bb0310 |  | note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | f9a1b51f-aa43-55c8-84bc-7427d2e4da2e |  | note | • The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | dab8a50c-6537-54a6-8a51-c4201edeed08 |  | note | • The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | 1eba0a67-f756-51a8-97f6-73138a96ebc7 |  | note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | 9d39f2c6-377e-58ab-ad7c-65b3fb4e036e |  | note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | 6f866d9c-837c-5ced-b28d-461e43a6f045 |  | note | • Record: Required information on the Concrete Pour Record.
label | 4942db2c-94a3-5c5b-8f03-73d7d8423123 |  | note | • Attach: Concrete Pour Record
label | 0ed615ae-5db2-557c-8143-b152be104781 |  | note | • Attach: Concrete Dockets
label | 489b190e-963b-57fa-92b7-fdd3d627512a |  | note | – – – – – – – – – – – – – – – – –
label | 32b4b13e-3501-5f7c-86c8-5db8b0fac90a |  | note | METHOD: Visual
label | 75b35f67-d095-58a5-a983-ecf8f6a97074 |  | note | – – – – – – – – – – – – – – – – –
label | 5224947d-5a5d-5706-a32a-d30689777d16 |  | note | FREQUENCY: Each load
label | 2da807b5-69ef-5129-b0c4-ef29dac04bce |  | note | – – – – – – – – – – – – – – – – –
label | 5f33d5e9-a7c4-5016-a9c4-75ab44fcf37e |  | note | CATEGORY: SP
label | dc36632e-6146-51d7-9a8a-c93e70fb9c98 |  | note | – – – – – – – – – – – – – – – – –
label | 1aece2e7-4ee5-5058-af7a-7c3fc32a8bd9 |  | note | RESPONSIBILITY:
label | 9cc3dbd6-6995-5b02-9fe3-6d62f54d39ce |  | note | • Foreman
label | ea66409b-3b62-52da-9a48-e9162ebe1ce8 |  | note | • SE/PE/SPE
label | 95a280e8-1e05-5d86-999a-01f56e5d1d5a |  | note | – – – – – – – – – – – – – – – – –
label | f584ae30-c695-5e36-9405-42dc8fdfb163 |  | note | VERIFYING DOCUMENTS: -
date | 037ce166-0947-5186-b04f-ab15fa2cf586 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes
label | 54b23332-f6d2-58c8-bdb8-2cfcd6d95ce9 |  | note | REFERENCE:
label | 28755c5a-1ab9-5660-a909-6ee2ece84536 |  | note | IFC Drawings
label | 2c6ab414-5ac8-521e-a7fa-9d648a772315 |  | note | 610.31
label | 61b45c5f-b92e-5289-ad93-00007c9f43eb |  | note | 610.20
label | 6024488d-5a47-52f7-924e-e50e5d6932b3 |  | note | – – – – – – – – – – – – – – – – –
label | a290f02e-9011-54c9-9e13-3687b5e78242 |  | note | ACCEPTANCE CRITERIA:
label | c4f963cc-0787-5bc2-84a7-53534be4b2d9 |  | note | • Surface finish as per IFC drawings.
label | cd9eb635-5653-5508-97c9-29ab62c51889 |  | note | • Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 9e557e50-6e31-5351-90b3-a39aeb7319ab |  | note | • Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | c1be53e4-f452-5051-823d-c98efdfcde57 |  | note | – – – – – – – – – – – – – – – – –
label | 4d56bedb-05c3-598d-88b0-d2f790f7a463 |  | note | METHOD: Visual
label | dcd67dd7-5c6f-52e2-aa14-6262c9d22380 |  | note | – – – – – – – – – – – – – – – – –
label | 5b42095c-06d5-5970-a086-c553e74a1c79 |  | note | FREQUENCY: Each pile
label | 58216b22-1f28-5631-8176-833e4537e0d3 |  | note | – – – – – – – – – – – – – – – – –
label | 64f6bf28-96df-56c2-bd8a-5c653cda82d5 |  | note | CATEGORY: IP
label | b29802c0-88a4-500f-80cb-6dc0068865ef |  | note | – – – – – – – – – – – – – – – – –
label | 5b7a1df3-5357-51e3-9629-095e3014d68a |  | note | RESPONSIBILITY:
label | 416d0cdc-a0fe-52f7-94d3-bcda9fc58b6b |  | note | • Foreman
label | 78ce9bba-778e-56dd-9af8-678555530bf7 |  | note | • SE/PE/SPE
label | be0914e2-d937-5f0d-8091-e7b52a85b66b |  | note | – – – – – – – – – – – – – – – – –
label | fe398dd9-dcca-5197-b23e-a27b7827af03 |  | note | VERIFYING DOCUMENTS: This ITP
date | d70f9596-c0f5-5d99-aa33-031038e5e544 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | 57ac4ef7-3180-5f93-a597-68aaf4004dd1 |  | note | REFERENCE:
label | 77cb3b31-38f0-511d-abe5-3886d87ac2e9 |  | note | IFC Drawings
label | 6328244c-0eb1-5887-9925-2e1a2e30562a |  | note | AS2159 Clause 7.2.2 - 3
label | 83400853-922c-580f-906d-09bc355cd34b |  | note | 606.06 (a & b)
label | f185fb5f-52cf-572f-97fc-da463f57c461 |  | note | – – – – – – – – – – – – – – – – –
label | 0967324a-56da-5304-bfa8-00fcfe3f4d42 |  | note | ACCEPTANCE CRITERIA:
label | eac07fbf-ad08-5c3b-aa7a-c7c5fb225336 |  | note | • Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | ce62f0c3-820b-50f4-8157-a18511f8ad2b |  | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage
label | a6aad965-612a-5db0-b51d-360cb78121f9 |  | note | • Any weak or damaged concrete shall be removed back to sound concrete.
label | 151dce38-db41-55ae-9b07-eeb5f414e78d |  | note | – – – – – – – – – – – – – – – – –
label | d72d7461-58e5-5480-822a-23bf5b7f172b |  | note | METHOD:
label | 66f35c34-0d3a-568c-a1f9-a8bc96dd55b5 |  | note | • Measure
label | 43017313-852a-5c9f-bfb2-b0e19d9dba5b |  | note | • Visual
label | 621871e5-c198-5791-b7a6-c2a4fa792f51 |  | note | – – – – – – – – – – – – – – – – –
label | 19280a38-6c64-5a91-bb5b-42860b9bdb9a |  | note | FREQUENCY: Where applicable, each pile
label | 7a857f0e-001a-5013-ad5b-6fef219c49db |  | note | – – – – – – – – – – – – – – – – –
label | eb00e354-43c7-5564-b1e7-ef4c7061fd71 |  | note | CATEGORY: IP
label | 8e307f85-9399-57b1-99e4-f1a3cf1f901e |  | note | – – – – – – – – – – – – – – – – –
label | 12cce601-0234-5f90-94f1-5f5b110f2207 |  | note | RESPONSIBILITY: SE/PE/SPE
label | dbf961a5-1034-50a6-9e28-33eb80fee433 |  | note | – – – – – – – – – – – – – – – – –
label | 9f509c76-b16a-5cd3-a442-c444f76fbcbf |  | note | VERIFYING DOCUMENTS: This ITP
date | a6a5ec34-0f1c-5311-8404-f6a0870a2dd6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | 018b039f-a339-5a07-a183-a13207ec9921 |  | note | REFERENCE:
label | 3d2f4a8a-f69c-5639-8981-e093765e1b2b |  | note | IFC Drawings
label | a55c7d51-a36b-5d5c-ae45-1e49a14cdded |  | note | Table 610.05.051
label | 20283e48-23f9-567c-8bd7-0f0db228e924 |  | note | 610.16 (g)
label | 19507a1e-2f45-57a6-aa9a-3bbc068ecf43 |  | note | – – – – – – – – – – – – – – – – –
label | 37e28c28-67b4-5e35-9ec2-e8e7d8199060 |  | note | ACCEPTANCE CRITERIA:
label | 9c9bc6bf-4609-5c13-8a10-9e82e8de1128 |  | note | • 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | d404a19d-6b3b-5ec1-bd77-3a5f5e0acad5 |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | a2c58583-8ee6-5c47-9229-7452c82dd4ab |  | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | cab6a59d-97ec-5d00-a5fa-6a94b18cdce1 |  | note | • Attach: Compressive Strength Test Results
label | e8685b9d-b648-50b9-b42e-fdc9355d53a3 |  | note | – – – – – – – – – – – – – – – – –
label | 01e3c3c3-f425-5e44-a519-ad5c1be5ac29 |  | note | METHOD: Document Review
label | ee056bc5-698c-508f-b8f8-bb143bb50893 |  | note | – – – – – – – – – – – – – – – – –
label | 76a92605-10e7-523e-8544-32491ba28c3b |  | note | FREQUENCY: Each cylinder
label | 99e391c5-39f3-5821-8619-e30c9a210363 |  | note | – – – – – – – – – – – – – – – – –
label | 667fe7b3-1bb7-5a41-b5f0-7c45ca3d2ea1 |  | note | CATEGORY: IP
label | 47e69056-4475-58b5-826f-a024c7be5973 |  | note | – – – – – – – – – – – – – – – – –
label | 7b0c03d5-e352-579b-972b-12677865986c |  | note | RESPONSIBILITY: SE/PE/SPE
label | aa0536f2-da3f-5268-919b-deba77fb7345 |  | note | – – – – – – – – – – – – – – – – –
label | a212881b-6a5d-5d29-95bf-dc31525feb4e |  | note | VERIFYING DOCUMENTS: This ITP
date | 79778218-cdc8-514f-bdf9-8ec579ff9b34 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 826b09e2-5acf-5937-a427-c24c62581328 |  | note | REFERENCE:
label | 178fe60f-99d5-56a9-b9d5-f83fd0fa29c9 |  | note | 606.07 (a, d & e)
label | 0c80ff81-7c06-5070-9f44-426a57f98e41 |  | note | AS2159 Clause 8.8
label | a67840f8-85cb-5fa5-9c4f-48ecbbf35da3 |  | note | – – – – – – – – – – – – – – – – –
label | 2115b309-6921-533e-8e50-119400ae4b79 |  | note | ACCEPTANCE CRITERIA:
label | 363adf33-a47f-5e3b-a030-11f9370a51df |  | note | • Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | b9c9f5b4-f236-57da-a7ad-2314cf5b9832 |  | note | • Cross-sectional area = ≥95%
label | ddd2fff0-5d55-55c6-b96d-9000b6c4341f |  | note | • If any test fails, all piles shall be tested.
label | 87cdf53a-6968-5dd8-ba4a-4d8a7663e5da |  | note | • Attach: Pile Integrity Test Report
label | 8675b9ca-caf4-5895-a256-0b760b0a4439 |  | note | – – – – – – – – – – – – – – – – –
label | 64b3f293-c8fe-5bd5-a181-9edfc2e05a97 |  | note | METHOD: Document Review
label | 31de156a-3c3b-5a8b-b97a-4d3000ca4ac3 |  | note | – – – – – – – – – – – – – – – – –
label | db5037ec-e767-5eac-85b6-34a9be1741c8 |  | note | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
label | 73e42e9a-f2d7-5a88-91e1-14a9a0a000d7 |  | note | – – – – – – – – – – – – – – – – –
label | 19353df2-86b2-5bed-b2ac-8053c33a33e3 |  | note | CATEGORY: IP
label | cdb4b066-07b3-5569-9554-29997dd48a90 |  | note | – – – – – – – – – – – – – – – – –
label | ec0086b0-eaf0-5608-bbe9-91f7f455c94e |  | note | RESPONSIBILITY:
label | 5feb6007-5c92-5779-ab27-ebfc1e5b1b4f |  | note | • Testing Consultant
label | 13aaad43-ab15-525d-b123-32132ce3b5de |  | note | • SE/PE/SPE
label | b201d981-87af-55cf-815e-97ac3b1b35c6 |  | note | – – – – – – – – – – – – – – – – –
label | 6d442335-0a49-5934-b136-8b5168f9c7a1 |  | note | VERIFYING DOCUMENTS: This ITP
date | 555c01ab-f524-5c8b-bf0b-91a8a97f5338 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Static Load Testing
label | 50c78768-997f-5a34-ac91-dad527fa6f7a |  | note | REFERENCE:
label | f1f80288-9bfe-5312-978e-b251b1957cf5 |  | note | IFC Drawings
label | e5eb585e-983c-5c68-8052-3a36d4c639ae |  | note | 606.07 (b, d & e)
label | 917e537a-d454-5cc9-90ce-e9ca60034e51 |  | note | AS2159 Clause 8.4
label | 9ae5e0e0-ea3d-53ea-9e2f-bffaab8d4207 |  | note | – – – – – – – – – – – – – – – – –
label | bdd66bdc-3792-580b-a277-1a53b8381fb6 |  | note | ACCEPTANCE CRITERIA:
label | 823fe2c8-5b4c-5baf-90c0-bedfd7e38c0d |  | note | • Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
label | 314c269f-dabf-5cf5-9b63-e2dd09d9ea61 |  | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
label | c4b9c380-5026-5aec-b94f-5d98d27a89e4 |  | note | ii. Creep rate = <2mm / log cycle of time at the test load
label | 3bc6b4a0-3194-5acb-abe1-df13493c0087 |  | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
label | 67b30180-469a-5906-b41f-72d0f1bd165c |  | note | • Attach: Static Load Test Report
label | bc37be61-31ba-5a2f-b31b-aa5718ae65a3 |  | note | – – – – – – – – – – – – – – – – –
label | 65789b53-aad5-5164-9b45-d54ef6d1e2c0 |  | note | METHOD: Document Review
label | a9b6920c-80c2-5a6a-b47b-77b857a83bb1 |  | note | – – – – – – – – – – – – – – – – –
label | 7e156a4b-7472-5860-8917-bf6eb08ac747 |  | note | FREQUENCY: Where applicable, as shown on the IFC Drawings
label | 4e2ed3f8-e41a-5271-84a7-2422fc5c123e |  | note | – – – – – – – – – – – – – – – – –
label | cc194558-c95d-56de-b720-fe593387e962 |  | note | CATEGORY: IP
label | ddba2631-47e9-5658-b192-21f95203141c |  | note | – – – – – – – – – – – – – – – – –
label | fb3931d0-472e-55e2-8048-3f98ebbecb71 |  | note | RESPONSIBILITY:
label | 031dbfbd-1a66-563b-b2c7-272075a743b1 |  | note | • Testing Consultant
label | be480f71-62d4-5fb8-b72c-86f87041d877 |  | note | • SE/PE/SPE
label | 8d0439c2-1728-5571-9f4b-730a69361077 |  | note | – – – – – – – – – – – – – – – – –
label | b77062a7-d772-5b49-9338-aa876453f6af |  | note | VERIFYING DOCUMENTS: This ITP
date | e2d5a759-2266-5135-9a5e-fbf28a44bd56 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Dynamic Pile Testing
label | 6783e93d-db0e-5111-936d-89b29a4d5829 |  | note | REFERENCE:
label | 905a8cbc-70f9-5811-9e9e-7ed5be7eaa9a |  | note | 606.07 (c, d & e)
label | 4148c449-24e6-5f17-a91f-b0eb878cf391 |  | note | AS2159 Clause 8.7
label | 0b7523a3-9c64-57da-832d-544bbc8c08bf |  | note | – – – – – – – – – – – – – – – – –
label | 394320c4-7c38-5d87-8f40-ef68fbcbb160 |  | note | ACCEPTANCE CRITERIA:
label | 9eda13c5-cf5c-5df6-a846-73c3d13bccca |  | note | • Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | b77086dc-caf0-5267-9b9b-d4ae7270a282 |  | note | • Measured Ultimate capacity = ≥ values on IFC drawings
label | 57c1eab3-52bc-5978-b49f-8dcf05a90a01 |  | note | • Attach: Dynamic Pile Test Report
label | a85b13aa-9071-5e29-b755-b246f17f43d3 |  | note | – – – – – – – – – – – – – – – – –
label | f04bab84-378b-5a98-8e27-bd22a600df67 |  | note | METHOD: Document Review
label | a4f3cee2-08b8-56cd-a28b-6a3fe2502061 |  | note | – – – – – – – – – – – – – – – – –
label | 62a19c15-e109-5b71-a1aa-ec5bf030ef88 |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
label | aa49f960-b032-55b4-9aa9-1b331b2e4908 |  | note | – – – – – – – – – – – – – – – – –
label | ad6add9a-f414-5a2f-9260-3ab51cc518c4 |  | note | CATEGORY: IP
label | 84f10c7a-a1e3-5614-bd8d-c31687d956d4 |  | note | – – – – – – – – – – – – – – – – –
label | 38fd1f3f-c3c2-5b65-86cb-9982681e33e2 |  | note | RESPONSIBILITY:
label | dd87504c-d29b-5ae8-958f-90adcfab9ebc |  | note | • Testing Consultant
label | 1de3a340-ac6b-5754-88b7-63568f37beed |  | note | • SE/PE/SPE
label | 7023f29d-8eff-5bff-b28d-b16cb2f1ccc5 |  | note | – – – – – – – – – – – – – – – – –
label | ac175a20-c97d-5d33-a317-d9165b551d22 |  | note | VERIFYING DOCUMENTS: This ITP
date | 642ad420-07a5-522f-99af-041b1cf7fc2f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 As-built Survey
label | 4cdd0235-2ab6-53b4-b53d-619a25c432a4 |  | note | REFERENCE:
label | 004e708f-0dca-50ae-9204-6d57ec2fe97a |  | note | IFC Drawings
label | 0f4fbd8c-dfe2-5b38-911c-1da8a2113963 |  | note | 606.08 (a - c)
label | 0e1fe053-7f9c-52c6-93b2-dc4f0736c41a |  | note | AS2159 Clause 7.2.2
label | 4b8c1096-cc44-528e-bd6d-bfbc72fe463b |  | note | – – – – – – – – – – – – – – – – –
label | 8e9bf5c1-77d7-57a3-9578-81e60ddc3f1e |  | note | ACCEPTANCE CRITERIA:
label | 53e733e2-ca49-51c4-8994-e11c8a570709 |  | note | • The following tolerances apply to piles:
label | 3c90fde0-514c-5893-98c4-f20bfbc80bae |  | note | i. Pile head plan location = ±75mm
label | a50801ab-9431-5776-9a33-e09d2ad1b631 |  | note | ii. Variance from vertical or rake = 1:100
label | eed0d59e-fb38-53ae-854e-12c3eeab07e3 |  | note | iii. Irregularities in straightness = 1:100
label | c096ed3d-29c5-5737-b9af-98a634078ccc |  | note | iv. RL = ±25mm
label | d86e1be4-38a6-5ad0-a8ac-1f7566d930da |  | note | • Attach: Survey As-builts / Survey Report
label | 49801844-e8d1-5daa-b70f-26434b192901 |  | note | – – – – – – – – – – – – – – – – –
label | 7485bfdf-aeb8-5a92-8814-26c7fc371eaf |  | note | METHOD: Document Review
label | aa3b6c8e-4337-5778-9fb9-e0c752f9c3f0 |  | note | – – – – – – – – – – – – – – – – –
label | 83339143-0ed4-5ed2-b638-39feffd3cc13 |  | note | FREQUENCY: Each pile
label | 573e4047-7f15-588a-9ad8-8febb2ef9a6d |  | note | – – – – – – – – – – – – – – – – –
label | e11eff2c-70ee-5516-8cd9-21f16ab2e446 |  | note | CATEGORY: IP
label | 4db3adef-c0fb-5084-9ef9-6d1c8f868dce |  | note | – – – – – – – – – – – – – – – – –
label | 5df88f8a-aa8d-59b7-af48-74c9f5f5d606 |  | note | RESPONSIBILITY:
label | 02344539-6ddb-565d-8de2-0a04ea56130f |  | note | • Surveyor
label | 1e8695b6-e59d-509b-983b-2f53608e8330 |  | note | • SE/PE/SPE
label | 26d2248d-17a8-53dd-b8d9-fcbaaa58928b |  | note | – – – – – – – – – – – – – – – – –
label | 73b814fd-49c2-52f6-8c00-78dab99430b8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 38988427-198f-59aa-a768-7fcf0b9be95e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Non-conformance Report (NCR) Closure
label | 172fefa4-2020-53c9-8a46-50f0eb5b4e2c |  | note | REFERENCE: MRPA Quality Management Plan
label | 5be0cf20-429d-52c2-b9a1-f4541d32a22e |  | note | – – – – – – – – – – – – – – – – –
label | bd862dc9-136c-5aeb-9240-c21a8fc96cc2 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 9a714d65-ded6-50c6-853d-825813251398 |  | note | – – – – – – – – – – – – – – – – –
label | d8900b95-7084-5c47-9b22-1986774213d6 |  | note | METHOD: Document Review
label | f3f15852-56f3-5611-ac87-ac264dc08296 |  | note | – – – – – – – – – – – – – – – – –
label | 466ba696-9e22-51b5-b8af-458a049ceb5d |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | b7c7420e-bc68-5ec6-bf80-966d3a395c88 |  | note | – – – – – – – – – – – – – – – – –
label | 56ac734d-7949-54c8-9d09-e8f6787b8047 |  | note | CATEGORY: HP*
label | 4adf119d-67f3-53a7-ac4d-d7b5ff5f396d |  | note | – – – – – – – – – – – – – – – – –
label | 34936249-80e7-5026-aaa8-30a4773fae3e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7a240b43-c51a-5c13-ba4f-fee782441a98 |  | note | – – – – – – – – – – – – – – – – –
label | 53b7aafe-c15b-51f4-b76b-3148a40fb715 |  | note | VERIFYING DOCUMENTS: This ITP
date | fb3248d7-dc7b-5bb9-ad86-f3d608eb7e36 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 3c51eba2-4d52-5331-8f96-d11d9fd4b388 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 7cae7b1d-daad-5634-bab5-092af6643f14 |  | textbox | Name:
text | 6278deb0-64b7-5254-9809-24d46396795b |  | textbox | Position:
date | 9f617c41-f000-5ffc-a960-c0b823d39d37 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-062-CIV-Camms-Hot mix Asphalt | itp |  |  |  | Yes | ITP-062-CIV-Camms-Hot mix Asphalt Rev 0 | 50007c25-3069-49d4-b6e3-9de97ba9dbf9
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | cd537407-d953-5df5-9489-fd6d5fa20afb |  | note | Document Title: ITP-CIV-Camms- Hot Mix Asphalt
label | 0674bf51-e583-5c14-9aeb-1b43920245da |  | note | ITP Description: Camms- Hot Mix Asphalt
label | 344ed78c-526e-50e0-82a8-f08800487c39 |  | note | ITP number: 062
label | 764db54a-4bf9-5925-b4c6-b1585f09a073 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ecb7bce8-4433-5237-b191-8a7d884947ac |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 7e1f63ec-6c8b-5b6d-b30d-d15bb5fb7fda |  | note | Revision Number: 0
label | ae2185af-560e-5d94-bb3f-fc8218574449 |  | note | Revision Date: 31/08/2023
label | 5283c278-b659-589d-a785-31f967aa62f4 |  | note | ITP created by: Victor Mira
label | 3605730d-df93-5de9-b7a7-cc4aa2539ff6 |  | note | ITP approved for use by: Victor Mira
label | b42f2a66-69c5-5165-9bb8-fd073206e778 |  | note | 1.1 Non Dependent
label | a6169124-16db-51fc-8f6e-6705f1c3c11b |  | note | Reference: VR 407 - July 2022
label | 01e468c8-99bf-5327-9bad-6b210fcced5c |  | note | 1.2 Non Dependent
label | b6cb1a51-c72d-5dad-9b5c-2171bda86181 |  | note | Reference: VR 173 - Oct 2008
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Mix Design
label | f5d84941-efb1-5bf2-99aa-d995d0b1597c |  | note | REFERENCE: VR 407.09
label | 1373e354-13d6-53ad-9966-517a3094ae9e |  | note | – – – – – – – – – – – – – – – – –
label | 009313df-5dae-55a7-8b3a-44bb2be50d69 |  | note | ACCEPTANCE CRITERIA: All asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport as ‘General’, unless otherwise approved by the Department of Transport. The registration for all mixes incorporated into the works shall be current at the time of their use.
text | 0c2a0a04-8967-5c47-b038-051e2f3532e8 |  | textbox | Enter: Teambinder Approval number
label | 6c1580e1-4cce-57c6-9c43-8f1119a0ec5b |  | note | – – – – – – – – – – – – – – – – –
label | 0c3eae2c-e2a3-5356-a44b-238eea6a8715 |  | note | METHOD: Document Review
label | 7310c9cb-52f3-5e53-8b5a-ec917e49134d |  | note | – – – – – – – – – – – – – – – – –
label | 43ac833e-604f-5677-82bb-ec6022af18d1 |  | note | FREQUENCY: Each Mix
label | 56559046-e86f-5fb2-baf1-82739c81d220 |  | note | – – – – – – – – – – – – – – – – –
label | 1ff63f6e-26e0-5379-a890-1432444ebd29 |  | note | CATEGORY: HP
label | e7d12540-31dd-532b-a676-52e0a6e0973f |  | note | – – – – – – – – – – – – – – – – –
label | 5258e5ea-c0c2-54b2-b0d4-1663b0a44e1c |  | note | RESPONSIBILITY: PE/Nominated authority
label | 00503c32-573c-50c9-9c0b-0e35257747bc |  | note | – – – – – – – – – – – – – – – – –
label | 9164c4f8-58a9-5e9f-a13d-9c48ae0c3c13 |  | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | 1dea9a50-bc94-5e42-959a-9b0d0a19557d |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Bituminous Materials-Tack Coat
label | b1253f3d-f4da-5179-9cec-740bc55067a8 |  | note | REFERENCE: VR 407.08 (d)
label | 455a07f0-a9d5-5660-96ea-7d3cfa8806d7 |  | note | – – – – – – – – – – – – – – – – –
label | 2c2188f8-b83e-55eb-8260-cb6a2ecff04c |  | note | ACCEPTANCE CRITERIA: Tack coat shall consist of a bituminous based binder.
label | 38206b94-cdca-5113-90ec-6b9839c627a4 |  | note | ○ Only trackless tack coat or a tack coat application system that prevents pickup of the tack coat must be used.
label | e38b384c-4465-56a0-8fac-42663694bd94 |  | note | ○ The Contractor shall submit the details of the trackless tack coat proposed to be used in the works.
text | 239c862f-33ef-573a-97f5-f3b2ebb9247e |  | textbox | Enter: Teambinder Approval number
label | 9413792f-4ff0-543e-aa9f-219e55d9982b |  | note | – – – – – – – – – – – – – – – – –
label | 78f6a437-f4ca-55b1-9514-4cf08111aea4 |  | note | METHOD: Document Review
label | 142ac287-c3af-578a-ac63-b1e1f44eda42 |  | note | – – – – – – – – – – – – – – – – –
label | 9a64a841-e9a4-5dae-a585-7379c7c63c4c |  | note | FREQUENCY: Each Material
label | 152d9056-a14e-5d08-b87e-f7665d3f7a34 |  | note | – – – – – – – – – – – – – – – – –
label | 911a7a9a-450d-5fbd-aa3f-83b6ea2cdc7f |  | note | CATEGORY: HP
label | c452e0ff-73e5-55c5-b86e-7a59a13d84a8 |  | note | – – – – – – – – – – – – – – – – –
label | 40187339-9b70-5703-9834-1c247b6a471a |  | note | RESPONSIBILITY: PE/Nominated authority
label | 9d0f19f0-96ed-5750-9be7-6bfe6b95ba5e |  | note | – – – – – – – – – – – – – – – – –
label | c5b48ce5-8334-5362-ac98-863b891ae178 |  | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | 54238ff8-5730-52fd-9c14-a4d6ecf0fd1e |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Asphalt Quality Plan
label | 7fc33216-0d32-52cc-8011-f80153b529c2 |  | note | REFERENCE: VR 407.04, VR 407.11
label | d90deb5a-1537-5601-a007-73fb3b13ac93 |  | note | – – – – – – – – – – – – – – – – –
label | 2a6fa307-1f82-5947-8cb7-50e16f091dac |  | note | ACCEPTANCE CRITERIA: the Contractor shall provide an asphalt quality plan that addresses the following requirements:
label | 980c0e1e-5930-578d-ba5f-53c4eb471b33 |  | note | ○ RAP Management plan (Approved by DTP)
label | 6a796449-ddb9-55a1-b9af-e4228170d3a6 |  | note | ○ asphalt loading and transportation to minimise segregation and achieve adequate mix temperature on delivery to site
label | c984d24d-06fa-55bd-bce2-c1344092484b |  | note | ○ measuring and recording of pavement temperature, wind speed and weather conditions
label | e201796f-3105-56dd-b205-8926559811ad |  | note | ○ achieving a uniform application of tack coat
label | 3322a231-4cfc-56e4-9068-60e21bc4763e |  | note | ○ achieving uniform asphalt placement including determination of paving speed and paving plans
label | a29dc359-7d8a-5fb0-bb00-1bd44d3d4098 |  | note | ○ determination of appropriate compaction equipment, number of rollers and rolling patterns required to achieve density
label | 2a5a53d5-5994-5146-873e-472a33671020 |  | note | ○ procedures to maximise density at joints.
label | e382e97d-0f36-5159-99ee-96f51fa0ed4e |  | note | ○ Production, storage, discharge and compaction temperature ranges for warm mix asphalt shall be included in the Contractor’s asphalt quality plan.
text | e2d1a194-5a27-5760-881f-794354c24ed8 |  | textbox | Enter: Teambinder Approval number
label | dea01140-3491-5948-b3eb-43c228331d3a |  | note | – – – – – – – – – – – – – – – – –
label | 7cd3ae41-d2f4-5226-9b94-ee510e2194af |  | note | METHOD: Document Review
label | 5b99f6fb-1823-55b2-8e81-8a5691e7901e |  | note | – – – – – – – – – – – – – – – – –
label | e406b754-0a24-5f62-9152-ae80b8bc1f5a |  | note | FREQUENCY: Each Lot
label | 9631d4ce-cd14-5b84-bb9c-9507cc9077e6 |  | note | – – – – – – – – – – – – – – – – –
label | de02eece-e83d-5413-821c-5f2e6e8032c3 |  | note | CATEGORY: HP
label | 56a56adf-7799-50f2-995f-ed61dc7021ba |  | note | – – – – – – – – – – – – – – – – –
label | 5e8b9fa6-99b3-551e-9a8d-bb9ee2ea03c3 |  | note | RESPONSIBILITY: PE/Nominated authority
label | a5125678-d24c-5ab5-920b-3c06ba405471 |  | note | – – – – – – – – – – – – – – – – –
label | b78575ea-0f4c-58c5-82a0-785de0ba78d2 |  | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | ce2d91d0-9a4e-5b24-b002-774a258dc9de |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 RAP Management Plan
label | 56418b58-c85d-52c6-b785-f34fc68df656 |  | note | REFERENCE: VR 407.13 (f)
label | 643bed1d-adc3-50f5-b225-41aaed62422c |  | note | – – – – – – – – – – – – – – – – –
label | bb1d2f49-565d-5aae-bca2-31acf026d245 |  | note | ACCEPTANCE CRITERIA: No asphalt containing RAP shall be supplied until the Department of Transport approved RAP Management Plan has been submitted at least 14 days prior to the asphalt works commencing and approval to proceed is given by the Superintendent.
text | 7ea794b8-293d-56e0-9a1d-c32024803548 |  | textbox | Enter: Teambinder Approval number
label | eb7e1ef2-9211-52ea-8cc9-dbef504592d6 |  | note | – – – – – – – – – – – – – – – – –
label | e7d14fd1-7991-5175-8b5a-df5cdb0653ca |  | note | METHOD: Document Review
label | 81827c98-262f-55ce-b413-5b05a4cb61d2 |  | note | – – – – – – – – – – – – – – – – –
label | 77e17331-bd40-546e-a7e9-46dfd85e3ef5 |  | note | FREQUENCY: Each Lot
label | e8372f95-0d2c-501c-b60e-881e516bb1e4 |  | note | – – – – – – – – – – – – – – – – –
label | e1ba5894-e87a-5735-bf05-144785768bd6 |  | note | CATEGORY: HP
label | 2880b794-6e60-5c30-bb6a-5954d45a919a |  | note | – – – – – – – – – – – – – – – – –
label | 89a79a58-bd3d-562f-939a-a8637dcd7c4b |  | note | RESPONSIBILITY: PE/Nominated authority
label | 2d9b9ea1-5a35-5c12-b5f3-7a906de1aa68 |  | note | – – – – – – – – – – – – – – – – –
label | 64cba6f8-fbd4-50e6-87f9-d953af3e2f5c |  | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | b4864b63-44a3-5605-b39a-0adfd3e0131d |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Cold weather placement
label | eb4d908a-4de3-5d9e-9021-436f67c39b88 |  | note | REFERENCE: VR 407.17 (b)
label | 1a10e329-61b0-5c4b-85c1-c812db18a723 |  | note | – – – – – – – – – – – – – – – – –
label | 275d97fe-4c5c-5bbc-8c6a-12722df69482 |  | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent placement of dense graded asphalt in layers 35 mm or greater may take place at pavement temperatures up to 5ºC below the minimum temperatures specified in Table 407.171.
label | 3ab1e170-0170-5da1-8513-55b53f687bd8 |  | note | ○ Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
text | b9139079-f679-56ec-a69f-acae89cb7279 |  | textbox | Enter: Teambinder Approval number
label | bd559f22-c004-53b0-b049-b3a6b6b44e42 |  | note | – – – – – – – – – – – – – – – – –
label | 95225699-533b-5b32-ac68-ce9fd06e08d5 |  | note | METHOD: Document Review
label | 7baafca7-86ec-5a54-931a-799a9f50ca91 |  | note | – – – – – – – – – – – – – – – – –
label | b9f49b3b-c76f-5b83-8cb2-c6bc9f8fe9a3 |  | note | FREQUENCY: Each Lot
label | 36f0dc34-76a0-566b-98ef-45c094654f36 |  | note | – – – – – – – – – – – – – – – – –
label | 50994449-89e4-5a77-80ed-5f4c055c921b |  | note | CATEGORY: HP
label | 34ded333-c5cf-5da2-aabc-6ee5d7848042 |  | note | – – – – – – – – – – – – – – – – –
label | 9b21e233-dfc9-5671-a34b-8fa715a0bb9d |  | note | RESPONSIBILITY: PE/Nominated authority
label | c29569d4-03e9-5672-81ba-3d4af2a2cb5e |  | note | – – – – – – – – – – – – – – – – –
label | 553447e7-b0f9-58ef-838b-a3f1e368a8de |  | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | f1e18499-52a5-59e9-976f-67b554812efb |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 7acde98e-db51-52c1-a9dc-1ab2f9971d65 |  | note | REFERENCE: MRPA Quality Management Plan
label | 1ae612e9-8ca0-5405-ba1c-24e9fc7f4496 |  | note | – – – – – – – – – – – – – – – – –
label | 47708421-dafa-55c3-b1f2-1cb847204952 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | f3e7579a-4eb5-5ac8-af86-f952118bc326 |  | note | – – – – – – – – – – – – – – – – –
label | 11fa8990-40ca-544f-bdd0-a5624923743a |  | note | METHOD: Document Review
label | 12e42ec6-0a75-5cad-aed3-e7d96ef4f809 |  | note | – – – – – – – – – – – – – – – – –
label | 266e748c-666d-5017-a84e-6201303062c5 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | c72bde3c-0ddf-53c1-beab-ffffc1225ad8 |  | note | – – – – – – – – – – – – – – – – –
label | a5b009cc-b4c5-5806-8139-01c5b632c92e |  | note | CATEGORY: HP*
label | 075ba898-6864-5fb4-9c5e-8a09ede6901a |  | note | – – – – – – – – – – – – – – – – –
label | 1f441fbe-bf0c-569d-8884-864a2ece7bd3 |  | note | RESPONSIBILITY: PE/SE
label | 163ccfc4-4115-5eff-b440-ff24d26d9602 |  | note | – – – – – – – – – – – – – – – – –
label | 5f1eacb7-2092-51a0-9ce5-3c59905cfcec |  | note | VERIFYING DOCUMENTS: This ITP
date | 518bf858-c569-5c19-901e-a5289f4c8f23 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Lot Map-and Lot size
label | 950532d9-7d45-5bb2-85cf-092db43615e3 |  | note | REFERENCE: VR 407.21 (a), VR 407.27 (b) (i)
label | 89be17ed-4bf2-53a3-83a3-0819503a5981 |  | note | – – – – – – – – – – – – – – – – –
label | c0a0d889-2e17-532b-b09e-8efbd3b72efb |  | note | ACCEPTANCE CRITERIA: A lot presented for testing shall consist of an asphalt layer which is placed in one shift under uniform conditions and is essentially homogeneous in respect to placement methods, materials and appearance.
label | a2351bf3-cf69-5842-88fb-8c47b3b996c8 |  | note | ○ The location of all joints shall be planned prior commencement to achieve the specified offsets between layers and the position of joints in the wearing course.
label | 92b900b1-4720-5152-a78e-d2454161c3b7 |  | note | ATTACH: Lot Map with planned location of Joints
label | e3f9d81b-c3ba-5929-894d-c30af7b7ba5e |  | note | – – – – – – – – – – – – – – – – –
label | ee1d7a4c-15c0-57e9-8d74-fe4346954151 |  | note | METHOD: Document review
label | 38d6c506-6a82-5058-a49b-baa81086230c |  | note | – – – – – – – – – – – – – – – – –
label | 4dd4b984-fab2-54d2-aba4-737e81fe302e |  | note | FREQUENCY: Each Lot
label | f71663b3-8f6b-5cf5-b0fa-3c8928a26765 |  | note | – – – – – – – – – – – – – – – – –
label | e1241a24-7858-5a4c-bad9-9d4e6003250d |  | note | CATEGORY: HP*
label | 14ee7fad-095f-5b5a-af26-d75368283190 |  | note | – – – – – – – – – – – – – – – – –
label | a66738b7-7546-5945-aac8-3afe7405ffb8 |  | note | RESPONSIBILITY: PE/SE
label | 9c69f175-1f8a-5350-9f34-602c2cfa3834 |  | note | – – – – – – – – – – – – – – – – –
label | 0f95a2f3-621a-5088-be47-35f1b43c5655 |  | note | VERIFYING DOCUMENTS: attached Lot Map
date | f4913e8b-604f-5d6a-a258-2a5128dfca4a |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Ambient Conditions-Surface conditions
label | c76d6cec-ff24-5085-af92-1719b5e0e7e9 |  | note | REFERENCE: VR 407.17 (a), VR 407.18
label | b18e2787-bd29-5cbc-b36d-0b348232dc59 |  | note | – – – – – – – – – – – – – – – – –
label | 5a8168eb-2933-5814-b8d1-23f836f49219 |  | note | ACCEPTANCE CRITERIA: The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent.
label | 62d1eab0-9089-5ff2-b9a2-a38b4722551d |  | note | ○ The Contractor shall remove all loose and deleterious material and sweep clean the area upon which asphalt is to be placed.
label | baa0a31f-a309-5392-9506-832eeb41114b |  | note | – – – – – – – – – – – – – – – – –
label | e7a8d085-4ccc-598a-87b3-9ea513c6714c |  | note | METHOD: Visual
label | f590f875-e791-540f-9b87-9406272bbb5f |  | note | – – – – – – – – – – – – – – – – –
label | 2007fcfd-5a45-563d-807b-dac7e92a8a66 |  | note | FREQUENCY: Each Lot
label | d7bbf2ec-1790-5957-871c-4ffa2c9a8133 |  | note | – – – – – – – – – – – – – – – – –
label | b86969ea-9a2c-5de8-9b6a-4beddc05721e |  | note | CATEGORY: IP
label | 6b673e8a-ab34-51b7-bd56-960706ad61f6 |  | note | – – – – – – – – – – – – – – – – –
label | 179af4b1-00e2-5207-8c31-b43b85edf07e |  | note | RESPONSIBILITY: PE/SE
label | da1b6631-4957-5068-a7b7-0bdbbd4fa731 |  | note | – – – – – – – – – – – – – – – – –
label | 6fb0f538-deb3-5f2a-81b2-4d26d53fba09 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3d8c8ba3-7ba2-5f6c-8db1-60260e82f374 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Ambient Conditions-Surface Temperature
label | fdd2f5d1-a2f6-5065-b241-31e52ee507ad |  | note | REFERENCE: VR 407.17 (a)
label | 27f878d6-c466-56ff-b667-b5c2dd870d7d |  | note | – – – – – – – – – – – – – – – – –
label | 8ccc9597-4a98-592e-a4ee-c3f08f16e200 |  | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed when the majority of the area to be paved has a surface temperature less than that detailed in Table 407.171 and as below:
label | e8097eba-ecba-546b-b2be-949cda2163a4 |  | note | – Specified binder class of C170 or C320:
label | 72dd1413-b31e-55ba-a975-c9b7d137972f |  | note | ○ Wearing course: 10°C
label | 6bfd6a88-3c07-5c1b-b71f-42413391d590 |  | note | ○ Other courses: 5°C
label | d854339b-7537-5ad1-a6eb-6b2e893e4e6f |  | note | – Specified binder class of C600 or containing a PMB:
label | b01b0eba-5067-59ed-bed2-efb033bc2515 |  | note | ○ Wearing Course 15°C
label | 3692ee19-876e-5b2e-8c3c-22acd83e3610 |  | note | ○ Other courses 10°C
label | 9d7de5a8-4800-589a-bce6-6b85b64cb10a |  | note | – – – – – – – – – – – – – – – – –
label | 82e83f36-a6d8-5e4d-803d-600bec377f67 |  | note | METHOD: Measure
label | 6e46e4ef-e7e5-5560-b94d-294a6061a45d |  | note | – – – – – – – – – – – – – – – – –
label | 1c42d614-e333-57eb-9997-9577a1c9c98b |  | note | FREQUENCY: Each Lot
label | 8d8ee915-2bfc-542e-ab67-26ab823e93da |  | note | – – – – – – – – – – – – – – – – –
label | 7002cbe2-efac-5ff7-9102-17e3d28a1088 |  | note | CATEGORY: IP
label | 6e6f253f-0ef0-573a-a66b-e0d4cf4160b1 |  | note | – – – – – – – – – – – – – – – – –
label | bc99cfdf-2b5c-5863-b87d-f826adfd700e |  | note | RESPONSIBILITY: PE/SE
label | f6be84a9-a274-590d-8571-aff02d0475ae |  | note | – – – – – – – – – – – – – – – – –
label | 97a7bf82-e18c-597d-83f9-f57bd2ccfb2a |  | note | VERIFYING DOCUMENTS: This ITP
date | 8012997f-7868-5ca4-adc0-35dfc88ae71e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Joints and Junctions-Layer by Layer-Transverse Joints
label | dfa0d220-4b47-59ba-975f-02d5b63297f8 |  | note | REFERENCE: VR 407.21 (b)
label | 183ea01a-e817-5ef4-8560-46e7244ee6bd |  | note | – – – – – – – – – – – – – – – – –
label | 80b913a1-d734-5be9-b388-c17e80ea3903 |  | note | ACCEPTANCE CRITERIA: Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
label | 0105396f-898a-5e79-a50e-b509e941303a |  | note | – All transverse joints shall be offset from layer to layer by not less than 2 m.
label | d1108c9d-fdd1-55d8-90a7-6b894a794487 |  | note | – – – – – – – – – – – – – – – – –
label | 70edbaff-19f9-5e2f-802c-cbdcfd72fb47 |  | note | METHOD: Visual Measure
label | a810bed1-491a-59aa-9a1e-8f90b15dc103 |  | note | – – – – – – – – – – – – – – – – –
label | 5c4e0df7-21cb-5dde-94fb-fee80f4def63 |  | note | FREQUENCY: Each Lot
label | 65c16432-861f-59b3-bef9-ce63cdd4330d |  | note | – – – – – – – – – – – – – – – – –
label | 1ccc627d-cb65-5d4c-b20b-a5398ca9fc4f |  | note | CATEGORY: IP
label | a18ae20c-21de-5b15-83fd-a10c32bc21c1 |  | note | – – – – – – – – – – – – – – – – –
label | e210b838-ee10-504e-9256-59c4c34e264a |  | note | RESPONSIBILITY: PE/SE
label | acb24c27-85d3-50c3-9a83-a3881b654c84 |  | note | – – – – – – – – – – – – – – – – –
label | 9273b358-0e92-5866-b57e-7a07a48cec09 |  | note | VERIFYING DOCUMENTS: This ITP
date | f9eca0fe-8c1d-5f23-b377-6d71a200c9c2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Joints and Junctions-Layer by Layer-Longitudinal Joints
label | 30f57080-2166-56b0-8eac-2ab9f9acedab |  | note | REFERENCE: VR 407.21 (c )
label | c7a145ce-1b07-57ba-9c2c-f2b79740def4 |  | note | – – – – – – – – – – – – – – – – –
label | 25c1f5c5-95c5-5e70-b305-f052e174e52c |  | note | ACCEPTANCE CRITERIA: Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
label | 9b67a593-370d-5cac-a9fa-681a96a0030d |  | note | – Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
label | bb8e5449-092c-5174-9dcc-452a6f552607 |  | note | – Longitudinal joints shall be parallel to the traffic lanes.
label | 085ef60b-f536-5bbe-906d-5d07daf85c93 |  | note | – Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
label | 8324aebd-d943-5cd0-bba9-71f8a2bb6223 |  | note | – – – – – – – – – – – – – – – – –
label | 02d6961c-5b70-59ce-8ad7-1204d1298cec |  | note | METHOD: Visual Measure
label | 6bd4176e-df14-5924-87bb-289e82ff259f |  | note | – – – – – – – – – – – – – – – – –
label | eb333087-88f8-536c-897f-ecf1e5735400 |  | note | FREQUENCY: Each Lot
label | a8569118-f406-5d25-968f-86c1ec595acf |  | note | – – – – – – – – – – – – – – – – –
label | 32cac5ae-4164-5078-8d06-d73187a5798c |  | note | CATEGORY: IP
label | 1d685d7b-5258-575f-b112-29b312866a79 |  | note | – – – – – – – – – – – – – – – – –
label | f777d58e-422c-5920-8937-d1678d7c9131 |  | note | RESPONSIBILITY: PE/SE
label | 6802e11e-ce7d-5818-9bfb-6075b8733aa1 |  | note | – – – – – – – – – – – – – – – – –
label | 05df1811-c915-54b7-88d5-9465182a4988 |  | note | VERIFYING DOCUMENTS: This ITP
date | f22810ef-5d52-5431-8ab5-41866ea6a026 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Joints and Junctions-Abutting existing pavement
label | b1a9fa49-a17b-5188-9a65-4a3d0aa7c847 |  | note | REFERENCE: VR 407.21 (c)
label | 0d33d88f-9ed9-5130-88fb-91bbd55824b4 |  | note | – – – – – – – – – – – – – – – – –
label | 6df74434-ec09-54e7-aade-672104f2c197 |  | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
label | 97d1a17f-d144-524e-a467-af68c9b0d8c6 |  | note | – At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied.
label | 25edcfb4-cd14-572e-89d1-980407dccb67 |  | note | – – – – – – – – – – – – – – – – –
label | 4e82d951-9e5c-53ba-b682-340cfc1d7e5e |  | note | METHOD: Visual Measure
label | 6f441771-fafe-5cab-ab5e-d589234bc5b2 |  | note | – – – – – – – – – – – – – – – – –
label | 944ae2c0-7df7-540d-9201-6ccffdfaf6ab |  | note | FREQUENCY: Where applicable
label | 0df1abf4-b7af-5d38-b66d-5b1b510f248c |  | note | – – – – – – – – – – – – – – – – –
label | 1ded6393-e884-53da-b87f-4d9275d99755 |  | note | CATEGORY: IP
label | 740c0c23-497f-5673-9a37-a761ab7a427c |  | note | – – – – – – – – – – – – – – – – –
label | 3d0679e6-1875-5cd9-9144-49bb3be99b0e |  | note | RESPONSIBILITY: PE/SE
label | 44b359a5-ac75-5bd5-befb-b999cad25ae7 |  | note | – – – – – – – – – – – – – – – – –
label | 6aae4f4e-19ef-5c73-a355-43d84e50b164 |  | note | VERIFYING DOCUMENTS: This ITP
date | 435413f4-fa24-5ab7-a5ba-2f862ede0bb3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Joints and Junctions-Junctions at limits of works
label | 92d667e9-6e99-5683-ac39-7a02cf7f874c |  | note | REFERENCE: VR 407.21 (d) VR 402
label | a4983ae8-8503-5ace-a7ea-367a781ac709 |  | note | – – – – – – – – – – – – – – – – –
label | e02b1c09-7131-5408-9b4d-998b022aad03 |  | note | ACCEPTANCE CRITERIA: At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
label | 3a473b27-4ca3-57bf-b852-0ab1a40332d5 |  | note | The chase shall be cut by removal of a wedge of asphalt tapering from zero to a depth of 2.5 times the nominal size of the asphalt from the existing pavement to the minimum length as follows:
label | 2f26761c-a94b-5b69-939c-bfeb23d9fcba |  | note | (i) at side streets and median openings – 600 mm
label | ad8532da-fefc-527a-8c9a-9d8ec69a31e6 |  | note | (ii) on through carriageways with a speed limit of 80 km/h or less – 3 m
label | 1aeb76ce-6cef-5ea1-8c82-bacf3a0a5c18 |  | note | (iii) on through carriageways with a speed limit of more than 80 km/h – 6 m.
label | d25460c5-10c2-5425-a7ff-1d3b05869e10 |  | note | – – – – – – – – – – – – – – – – –
label | 6f190ff2-a9fb-53c5-9434-17058c228c5a |  | note | METHOD: Visual Measure
label | 62d929ea-7a66-5ec5-9ed3-946ad9c0bcb8 |  | note | – – – – – – – – – – – – – – – – –
label | 0eeb2196-f649-59c0-80f5-b2d3eb2d3b6e |  | note | FREQUENCY: Where applicable
label | 3ff373b9-2081-5246-83cf-ccf315ae93e7 |  | note | – – – – – – – – – – – – – – – – –
label | 30ad62ef-e25f-59a3-9734-ff6837888a27 |  | note | CATEGORY: IP
label | 964015f8-24fe-5fb3-ba4e-f2a72d43a232 |  | note | – – – – – – – – – – – – – – – – –
label | 90882e12-c0d3-582b-871a-84a5dd387709 |  | note | RESPONSIBILITY: PE/SE
label | 3f006ff3-8eff-5eec-b89a-82b6a90e67a2 |  | note | – – – – – – – – – – – – – – – – –
label | 6f0675a8-4b0d-5166-8222-c1545c0b5387 |  | note | VERIFYING DOCUMENTS: This ITP
date | 87a6debb-0232-5349-9c76-878e6a58cbd9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Application of Tack Coat
label | fccfb4af-996c-5d99-8286-2e6f0ff4bfb7 |  | note | REFERENCE: VR 407.19
label | a989cbdc-a25b-552d-b84f-537cf6eddbb9 |  | note | – – – – – – – – – – – – – – – – –
label | 559bed17-0b4f-5e00-8d1d-98a49015b437 |  | note | ACCEPTANCE CRITERIA: A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed.
label | 7c0e6acd-96bb-5e85-8032-e15fa9f2076e |  | note | The application rate for the tack coat shall be 0.15 to 0.30 L/m2 of residual bitumen for joints and chases rates shall be doubled.
label | 217c4f2d-16b4-5b02-a4cd-25ff4a722d63 |  | note | The Contractor may omit the tack coat where asphalt is to be spread over
label | a6c1bfd9-e892-5477-83f5-4db8908d2840 |  | note | – A clean, un-trafficked, freshly laid asphalt, or
label | 1b3a64a5-61d2-5ec7-8a51-47fa8b97df2b |  | note | – A clean primed surface, or
label | 5078096c-0dd7-52f3-ba70-6faa31a5aae1 |  | note | – Granular material where the overall asphalt depth is 150mm or greater.
label | 90380a52-ee82-5c15-b1a4-753a610ed7a4 |  | note | PHOTOGRAPHIC EVIDENCEshall be supplied to show that tack has been applied.
label | a42d1eb8-400f-58cc-b900-9269a1eefa30 |  | note | ATTACH: Photographic Evidence
label | 81d78496-4349-5a25-b9d6-c088e299b27a |  | note | – – – – – – – – – – – – – – – – –
label | 40c66908-fc56-518f-a153-8d201c28a045 |  | note | METHOD: Visual
label | 2f64bba1-3c50-5c69-89eb-7a596e47f862 |  | note | – – – – – – – – – – – – – – – – –
label | 7b71454c-f212-56a8-a4e1-b7aa66b35223 |  | note | FREQUENCY: Where applicable
label | ad4ae6b7-fb60-59ce-9bc5-d985d5c6a58c |  | note | – – – – – – – – – – – – – – – – –
label | 1f3f5cf5-2d23-5397-8353-c3081b619301 |  | note | CATEGORY: SP
label | c8b1e6cc-256f-5672-9e85-3391ba5bbbec |  | note | – – – – – – – – – – – – – – – – –
label | 1fa2cff3-939c-59da-8b1c-6ffdab5d7e13 |  | note | RESPONSIBILITY: PE/SE
label | 58fc4272-915e-576c-b5df-21fb8884f804 |  | note | – – – – – – – – – – – – – – – – –
label | ad59bc87-c02d-5201-9e73-8b405d1e0d14 |  | note | VERIFYING DOCUMENTS: This ITP
date | b60ec27d-8a13-513e-94a6-22220406dd75 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Joints and Junctions
label | fd65b00f-fad4-598e-8fed-0c7ea508d47a |  | note | REFERENCE: VR 407.21 (a)
label | fdee2718-38b5-5820-b63a-cb18de463f65 |  | note | – – – – – – – – – – – – – – – – –
label | e9091c30-7e56-5ba9-948d-f2a354798d99 |  | note | ACCEPTANCE CRITERIA: All joints shall be well bonded and sealed
label | 63c1530c-3cae-5f23-9335-70996828129d |  | note | – All cold joints and abutting concrete edges shall be tack coated
label | 9590d250-b6ef-5972-8e4f-1c64287d94f5 |  | note | – – – – – – – – – – – – – – – – –
label | 0b58c3a1-c4e4-5c14-98d9-ca2bc7486b2a |  | note | METHOD: Visual
label | d501bdf3-bcd0-5eaa-80c3-85173e996a83 |  | note | – – – – – – – – – – – – – – – – –
label | 1d98920c-b9c5-5654-9299-d35327a24d40 |  | note | FREQUENCY: Where applicable
label | c5d49af9-9ed4-5a92-8500-0bc59b539eb9 |  | note | – – – – – – – – – – – – – – – – –
label | 7536a19b-4df5-5bee-8ba6-b62324dfb748 |  | note | CATEGORY: SP
label | 289f708e-bf1d-5cfc-afa3-40fe99b1e087 |  | note | – – – – – – – – – – – – – – – – –
label | d63b2f3c-b630-5def-a77a-3770ade476c3 |  | note | RESPONSIBILITY: PE/SE
label | 68616d17-e0c3-56ee-9b79-dc900bbfc144 |  | note | – – – – – – – – – – – – – – – – –
label | 3b9091aa-ef4b-5624-94ec-caf9249467a3 |  | note | VERIFYING DOCUMENTS: This ITP
date | 29297888-1752-5093-a3da-608b12250e9a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Delivery Dockets
label | e5874b82-5aaa-596b-ae0e-6e97e8ac08f4 |  | note | REFERENCE: VR 407.20
label | 8eb0ec58-b2f4-5328-b0f2-0a7d2f5901da |  | note | – – – – – – – – – – – – – – – – –
label | 9201f8e7-c8b3-5d33-8916-4fb2515177a1 |  | note | ACCEPTANCE CRITERIA: Asphalt delivered to the site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site.
label | 338e8dc4-dc43-59ff-9842-fcf56ec04dab |  | note | ○ Maximum Asphalt temperature at discharge from the plant is 175°C
label | dfb301d9-54f9-53f0-908d-7a6a55af65fa |  | note | ATTACH: Mix Delivery Docket
label | e17799a1-f3fa-5925-ac49-f3958fa90f42 |  | note | – – – – – – – – – – – – – – – – –
label | a355fa94-323b-5f73-b570-fd2c3100e997 |  | note | METHOD: Document review
label | 295b66f4-be52-5a56-b16c-b9c06ed27fab |  | note | – – – – – – – – – – – – – – – – –
label | 315a54d3-9461-574d-88a3-b5ac1500ed00 |  | note | FREQUENCY: Each Lot
label | f498333c-9ba4-508e-af92-5827d4c4508a |  | note | – – – – – – – – – – – – – – – – –
label | 0f234bcc-8e16-5cf6-ad1d-29991b2f4af4 |  | note | CATEGORY: IP
label | 1dc7b340-2c23-5ac3-bc6b-57a8dd4ddfa0 |  | note | – – – – – – – – – – – – – – – – –
label | 5a460210-dc55-5689-86b6-f1d8f89cb53a |  | note | RESPONSIBILITY: PE/SE
label | 83d675d2-7247-5af7-a6f4-3cbb02c40706 |  | note | – – – – – – – – – – – – – – – – –
label | 1493d9c2-dadb-5321-96ae-453963ea5078 |  | note | VERIFYING DOCUMENTS: This ITP
date | ca123bbe-8ce2-5087-92f6-84d4ecd3cb17 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Commencement of Placement
label | 0cbb6bb6-adee-568d-a206-30cd94735956 |  | note | REFERENCE: VR 407.23
label | 07ca2d9a-da73-5d7c-bedc-0e041c7d0864 |  | note | – – – – – – – – – – – – – – – – –
label | 130a58c4-916e-54a1-b4f8-6afea591cfff |  | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent.
label | c1294e06-7306-50d8-b775-97e040990960 |  | note | – – – – – – – – – – – – – – – – –
label | 988d2206-0b8a-5292-b3c3-80bb57f9e208 |  | note | METHOD: Visual
label | 01f14ae0-0194-50cc-8e77-3552cf87dfef |  | note | – – – – – – – – – – – – – – – – –
label | e5185e8b-1b7a-5b33-9e6a-b9ae4dc1aaac |  | note | FREQUENCY: Each Lot
label | 18afff0e-fc8d-5d79-a8ff-57a426f522ad |  | note | – – – – – – – – – – – – – – – – –
label | 755404b2-b6ac-5880-a135-0b8c53a2d89a |  | note | CATEGORY: HP
label | eee84bb1-0c70-5362-a9d9-d0702f44a596 |  | note | – – – – – – – – – – – – – – – – –
label | 08cfab37-0ba9-54b5-83fe-18bc111ee086 |  | note | RESPONSIBILITY: SE/Nominated authority
label | 075ba49a-1cf9-5cad-b708-a9bf6d64acb8 |  | note | – – – – – – – – – – – – – – – – –
label | c4db0d37-fbf2-5b26-b785-d92c3555b44e |  | note | VERIFYING DOCUMENTS: This ITP
date | b4741c3b-7635-5230-a5c0-7db765bdbd02 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.11 Paving of Asphalt
label | dbb05382-e62a-5393-a5f2-e009091ebfc3 |  | note | REFERENCE: VR 407.25
label | dfebb45a-1ef5-54bc-9a35-0e83acd964ce |  | note | – – – – – – – – – – – – – – – – –
label | 79469d79-8b42-53f7-a6f8-006dde9af96b |  | note | ACCEPTANCE CRITERIA: Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings.
label | 609af035-f0f4-509b-9e05-a19983529e53 |  | note | ○ All asphalt shall be spread with paving machine (or by hand if not accessible by Paver) to form a smooth asphalt mat without segregation, tearing or gouging.
label | 55a3b74d-0192-56a8-b220-90259144c43e |  | note | – – – – – – – – – – – – – – – – –
label | f68df99a-ba7c-5d7b-8a83-02e2062691fa |  | note | METHOD: Visual
label | 89462cd1-a933-5643-b431-a2f25bc4a1f5 |  | note | – – – – – – – – – – – – – – – – –
label | fbba681b-9aea-5a4f-a075-455749808563 |  | note | FREQUENCY: Each Lot
label | 7d41f924-5ffa-5e78-8c85-f33f03846c29 |  | note | – – – – – – – – – – – – – – – – –
label | 60d0b5af-3283-5aa6-90e5-0500ce35931c |  | note | CATEGORY: SP
label | 5c6339e9-953a-538f-8283-a2b65640a382 |  | note | – – – – – – – – – – – – – – – – –
label | 0a73cc20-335f-5ea4-a3d3-100d28c04e29 |  | note | RESPONSIBILITY: SE/PE
label | b525ffd1-8189-5a55-89c1-1bbbd194722e |  | note | – – – – – – – – – – – – – – – – –
label | a16212c4-ea54-5d1e-bfeb-6ff7ca3c9cd7 |  | note | VERIFYING DOCUMENTS: This ITP
date | 02f4542e-2e7e-5e08-9c5b-26a5737f8ff7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Paving of Asphalt
label | 466396db-6813-57e3-be96-b86523984614 |  | note | REFERENCE: VR 407.25
label | 7a62335a-1fe6-5c7d-ab94-f567194d07e1 |  | note | – – – – – – – – – – – – – – – – –
label | 7c2213d1-6f52-50d5-9455-6d34d0a64025 |  | note | ACCEPTANCE CRITERIA: If the paver is required to stop and asphalt in front of the screed cools to below 120°C, a transverse joint shall be constructed.
label | 341a407f-88bb-5d87-9b28-98854160765b |  | note | – – – – – – – – – – – – – – – – –
label | a7a0655e-e7be-5ae0-ba8f-7bb98cb28765 |  | note | METHOD: Measure
label | 6612c72e-6b9a-5b86-a445-2e2a461f67b9 |  | note | – – – – – – – – – – – – – – – – –
label | 53d49ec1-42ce-5ae8-8f58-53cd67763fb1 |  | note | FREQUENCY: Where applicable
label | 661b6bdd-dd94-5eb6-93be-19b5e4d7ee66 |  | note | – – – – – – – – – – – – – – – – –
label | d9fa58d1-bd3c-53d3-86e6-df191c16ecb2 |  | note | CATEGORY: IP
label | 43dcc8f9-bf36-554c-90e5-dce87d8f6888 |  | note | – – – – – – – – – – – – – – – – –
label | 1e0cd73c-c1b1-5a66-bb08-3e822976100c |  | note | RESPONSIBILITY: SE
label | df52a6f6-3b06-5a01-9036-156eb2c3f218 |  | note | – – – – – – – – – – – – – – – – –
label | a47b537a-c88c-5a1d-8167-f7453ff6653b |  | note | VERIFYING DOCUMENTS: This ITP
date | 77062c5a-5fd2-5946-8d10-06c138fab152 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Compaction
label | b0a7a75c-b161-5fd9-8c62-dbc661802ff7 |  | note | REFERENCE: VR 407.26
label | b969772a-8464-56fd-b5ac-e5ff5f6999bf |  | note | – – – – – – – – – – – – – – – – –
label | 80243149-d8c2-53d2-9126-15c849fa3bcc |  | note | ACCEPTANCE CRITERIA: Asphalt shall be uniformly . Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
label | e8feebc4-fd8b-521c-9bff-c72c398723ce |  | note | ○ Vibratory rolling shall not be used to compact asphalt on bridge decks.
label | 98e50845-bce4-5013-8544-34b014cd95e2 |  | note | – – – – – – – – – – – – – – – – –
label | 65609171-bb2d-5671-9297-62ac9e8d37e5 |  | note | METHOD: Visual
label | 9244d442-6e85-5e6c-972b-95bd692baffe |  | note | – – – – – – – – – – – – – – – – –
label | 8c9150a9-afb9-543e-ba92-4ba69eda3c6e |  | note | FREQUENCY: Each Lot
label | 50c040cf-69ed-5adf-963d-1325477d025b |  | note | – – – – – – – – – – – – – – – – –
label | 7c04a6e0-09c1-535b-b232-3dbd8b96ac31 |  | note | CATEGORY: SP
label | a00456ad-21e4-5cf4-8d51-a21559a607ec |  | note | – – – – – – – – – – – – – – – – –
label | 2b8477fd-f5da-5fd8-8d9e-8eb174435f98 |  | note | RESPONSIBILITY: SE
label | c5ad8c5f-f630-5ba5-aec5-44e7ad688f9b |  | note | – – – – – – – – – – – – – – – – –
label | ae5bf1c2-228e-5f17-8adc-68b65fcda574 |  | note | VERIFYING DOCUMENTS: This ITP
date | bab8bf87-2cb0-5a47-b179-be361740ec8a |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Compaction test-Lots larger than 500 sqm
label | 6f813c49-db05-5c1d-9648-43c2ca97cfb9 |  | note | REFERENCE: VR 407.27 (b) (i)
label | b03268ba-1d20-5e1d-9c91-217bc865cd34 |  | note | – – – – – – – – – – – – – – – – –
label | 33562f9f-9b0f-5f95-8f3b-111f52d7f6bc |  | note | ACCEPTANCE CRITERIA: The work (excluding longitudinal edge strips) represented by a lot of six tests shall be assessed as shown in Table 407.271.
label | 5f51d2a2-e4de-5d87-90b3-7284f656718f |  | note | ○ For lots exceeding 500 m2 density testing of the longitudinal edge strips (200 mm from the longitudinal joint) for the wearing course shall be undertaken and results reported as a separate lot.
label | d8434e77-6f5c-5d95-88f7-8ce2897326fe |  | note | ○ The Characteristic Value of the Density Ratio determined for the longitudinal edge strips within the lot shall be submitted for report only
label | 9627baec-0299-53b1-8b0c-a443663241fa |  | note | ATTACH: Compaction test report
label | d386923a-253c-52bf-a825-381ac1845a36 |  | note | ATTACH: Wearing course joint strip compaction test results
label | 76bf6bd0-9389-528e-b47e-ffe5d5c3644b |  | note | – – – – – – – – – – – – – – – – –
label | 25d91773-1313-53ff-9604-61fc9e59b230 |  | note | METHOD: Document Review
label | 1a7a1d14-b5f7-5120-9f21-41cee53b54a9 |  | note | – – – – – – – – – – – – – – – – –
label | 0c09c8bb-fb5f-5dbe-9590-5242e197d10e |  | note | FREQUENCY: Each Lot Where Applicable
label | 4127ae94-63c7-5e96-a037-2ed8ca438858 |  | note | – – – – – – – – – – – – – – – – –
label | d46a49b3-dbe9-5cbc-8cdf-6b6b690f4a6c |  | note | CATEGORY: HP
label | 5311c2e8-fff4-5e05-8c67-22efc498e079 |  | note | – – – – – – – – – – – – – – – – –
label | 4d020c22-8046-51f7-a045-2200e754b15f |  | note | RESPONSIBILITY: Nominated authority
label | 905e0962-96b3-5eb3-a487-fa37461195e8 |  | note | – – – – – – – – – – – – – – – – –
label | 12affb95-e105-50e0-9c84-d9607b1633cd |  | note | VERIFYING DOCUMENTS: This ITP
date | 91ac4cfa-cdbd-5e3a-a2ac-91f4e7d400cd |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 Compaction test frequency-Lots smaller than 500 sqm
label | 06470bff-c7fd-5f3d-b1b6-139001b07773 |  | note | REFERENCE: VR 407.27 (b) (ii), VR 173.04 (d)
label | 07009b77-9129-57f4-88dd-8add34cb69b1 |  | note | – – – – – – – – – – – – – – – – –
label | a22576d1-693e-5a86-862d-7a402003565a |  | note | ACCEPTANCE CRITERIA: acceptance of the lot shall be based on the mean values of 3 individual tests. The lot will be accepted if the mean value of the individual tests exceeds by 2.0% or more the appropriate compaction scale requirement for the characteristic value of density ratio for a lot of six tests.
label | 153577bb-a7db-513d-8fe3-10dfe88f1c48 |  | note | ATTACH: Compaction test results
label | cf35486e-0a0f-5814-a287-0738bef58e61 |  | note | – – – – – – – – – – – – – – – – –
label | 52a0653b-ad2d-590a-8ddb-6c94fff39013 |  | note | METHOD: Document Review
label | f57dfe75-f57a-5128-98b5-c3c50578a190 |  | note | – – – – – – – – – – – – – – – – –
label | 973e5389-1e63-59d1-9a8f-153afaebc512 |  | note | FREQUENCY: Each Lot Where Applicable
label | b348c6e1-4013-5fa0-a921-97b537d975b5 |  | note | – – – – – – – – – – – – – – – – –
label | bfb31804-69f6-5be4-8080-0833879fbd02 |  | note | CATEGORY: HP
label | 2c2d4a67-3feb-5aa6-9b7d-99584d4a9ab0 |  | note | – – – – – – – – – – – – – – – – –
label | c5d98eff-8a43-55ed-93f2-ff467e1502f7 |  | note | RESPONSIBILITY: Nominated authority
label | ad12d534-3673-5a23-8b54-5f40897607d1 |  | note | – – – – – – – – – – – – – – – – –
label | d928a42f-d5bd-5ca5-b10a-250d1c070f7f |  | note | VERIFYING DOCUMENTS: This ITP
date | 059033c7-85d1-5322-bc5f-cb7132d78d7b |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3 Surface finish and conformity with drawings-Surface Finish and shape
label | 3984ceed-8d78-5542-aa96-ab6fb2be437e |  | note | REFERENCE: VR 407.29 (a) (i), VR 407.29 (a) (ii), VR 407.29 (a) (iii)
label | 784941fe-0ba2-5a59-9fb2-4a9c3e9902b8 |  | note | – – – – – – – – – – – – – – – – –
label | dba28a92-13be-5c27-82b8-0afce1fec009 |  | note | ACCEPTANCE CRITERIA: The finished surface of any asphalt course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks.
label | 892889bf-b3c0-5997-b9e4-9b630d65ee32 |  | note | ○ No point on the finished surface of the wearing course: shall lie more than 4 mm below a 3 m straight edge
label | 09ae1fa6-a932-50f4-8192-1c5f06b39f0a |  | note | ○ For intermediate and base course layers: the distance below the straight edge shall not exceed 6 mm and 10 mm respectively.
label | c9bb5df8-7058-589c-89c8-de85793b910e |  | note | ○ Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel
label | d59810d0-7a76-55a0-81a6-ac2161df1f95 |  | note | – – – – – – – – – – – – – – – – –
label | bbdd40b8-b36c-5c83-b9be-80eb7c2d30ca |  | note | METHOD: Measure
label | 9bb84f08-a366-5387-ae93-d184bdbbcb1f |  | note | – – – – – – – – – – – – – – – – –
label | b57fbba1-cbd8-5e55-8d79-bcfb7ca57671 |  | note | FREQUENCY: Each Lot Where Applicable
label | fce50d96-8c6a-5c59-b1ef-a9d4856f558f |  | note | – – – – – – – – – – – – – – – – –
label | 38cd3c92-04dd-524a-bc60-d91bf5ee48bf |  | note | CATEGORY: IP
label | f69424c2-55e8-560f-87a5-ae996664ebb8 |  | note | – – – – – – – – – – – – – – – – –
label | f3ed35a2-9110-5a3a-803f-2faa8f523bc7 |  | note | RESPONSIBILITY: SE/PE
label | 4a8da2f5-4621-5d7f-bb82-a165593dced7 |  | note | – – – – – – – – – – – – – – – – –
label | 1a7981c7-67eb-531a-8cd6-3fae51ca5f41 |  | note | VERIFYING DOCUMENTS: This ITP
date | 39e084f3-df53-54c7-854f-62546d9509f7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Surface finish and conformity with drawings-Alignment and width
label | 84bfd0d9-5beb-5166-b79c-aae6c169b114 |  | note | REFERENCE: VR 407.29 (a) (iv), VR 407.29 (a) (v)
label | a7be89a5-1b42-5f72-a4ea-c02fc087a3b0 |  | note | – – – – – – – – – – – – – – – – –
label | d8d2a7f0-9192-5dc8-8c15-940104a36070 |  | note | ACCEPTANCE CRITERIA: Where asphalt pavement is not placed against a concrete edging:
label | 2e088f21-442d-51a3-9b07-c26fde334e29 |  | note | ○ the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside,from design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m.
label | 9ba5e597-5c83-5ff0-bfc9-2429bc608d98 |  | note | ○ the width of asphalt layers shall not be less than the design more than 50 mm or greater than the design by more than 100 mm. The average width over any 300 m shall not be less than the design.
label | 69b21af5-aed7-5b6c-97e7-467bbf981cea |  | note | – – – – – – – – – – – – – – – – –
label | 65087b1f-ddad-5e59-b328-ddadbba3224d |  | note | METHOD: Measure
label | 5d351e52-0a31-5267-90aa-94d8e7b0f981 |  | note | – – – – – – – – – – – – – – – – –
label | 04774719-9cba-51c3-8c00-3a609fc10a96 |  | note | FREQUENCY: Each Lot Where Applicable
label | e4ff00d6-b8d2-5a0f-a093-afb25de1e07c |  | note | – – – – – – – – – – – – – – – – –
label | a1fa7b03-0784-5617-a94a-9bb916712251 |  | note | CATEGORY: IP
label | 42c053eb-a814-5d11-9b3b-b96f57dc8588 |  | note | – – – – – – – – – – – – – – – – –
label | 6b14c8fd-8f05-5e51-8836-b211d3128356 |  | note | RESPONSIBILITY: Surveyor/SE/PE
label | a709247f-d0e1-505e-b057-62466b6ae63d |  | note | – – – – – – – – – – – – – – – – –
label | 5fabed27-f765-50b4-87c2-2ac9ec1f299f |  | note | VERIFYING DOCUMENTS: This ITP
date | acb6a0f0-a6ab-5865-9d3c-c26e30259381 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Conformity with drawings-Scale A and Scale B
label | 65f47442-a972-5898-ab0e-7d1c14fe04e5 |  | note | REFERENCE: VR 407.29 (b) (i), VR 407.292, VR 407.293, VR 173.05
label | ddbc65a4-7701-5bd6-a310-9dbc32e729d9 |  | note | – – – – – – – – – – – – – – – – –
label | 321c7f0b-9a3a-5c17-8318-644709afa9b7 |  | note | ACCEPTANCE CRITERIA: the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.05
label | 842169f1-362f-5ba8-9268-947f254e925b |  | note | ○ Number of measurements and acceptable tolerances are to be as per tables VR 407.292 and VR 407.293
label | ddfff70e-f472-5306-b4f7-cb8c4f371186 |  | note | – – – – – – – – – – – – – – – – –
label | c9d5aa2d-cd98-5aaa-8694-3023ba8009f1 |  | note | METHOD: Measure
label | fb96a74d-48e4-5236-9d44-3af8afb93a5a |  | note | – – – – – – – – – – – – – – – – –
label | 63b2aeab-c2ad-54db-a456-4ed350ef9a79 |  | note | FREQUENCY: Each Lot Where Applicable
label | 1ab0947b-0152-5487-b1d5-c432daa5d1ba |  | note | – – – – – – – – – – – – – – – – –
label | 94ddd3eb-981b-5760-b763-210a6dd5d0ad |  | note | CATEGORY: IP
label | 68a22621-8479-5544-b77e-f8e66794275b |  | note | – – – – – – – – – – – – – – – – –
label | 34856c0c-18b6-5bd2-8ac6-ca64f2ee05f3 |  | note | RESPONSIBILITY: Surveyor/SE/PE
label | 429cfffd-1b86-5f9e-a6bb-56b98a2c1da8 |  | note | – – – – – – – – – – – – – – – – –
label | 771f5e4c-b42d-511f-9c14-c710221ee5d9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0b8ebf94-fe54-541a-880c-95822323a3d9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Conformity with drawings-Scale C
label | e413365d-4f6c-599c-ae16-2204bd13407d |  | note | REFERENCE: VR 407.29 (b) (ii), VR 173.06 (c), VR 173.06 (d)
label | 9dead0e8-f97b-5d99-a007-0367a4860eda |  | note | – – – – – – – – – – – – – – – – –
label | 51f1b9f6-ca74-5418-83f9-8506596c5c9e |  | note | ACCEPTANCE CRITERIA: the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.06
label | 1f347b48-7122-537a-9143-41e12148c30b |  | note | ○ The level of the top of each asphalt course shall not differ from the specified level by more than 15 mm for intermediate and base courses and 10 mm for wearing course.
label | cbd4b5ee-6c07-5af3-a786-dc7e7b4d3ecd |  | note | ○ For the purpose of this clause, the maximum lot size shall not be more than 4,000 m2 of pavement area.
label | 1575755b-fb5f-56ae-9b3d-c6e6ae4e6687 |  | note | – – – – – – – – – – – – – – – – –
label | 18a5f75f-6638-5041-857d-8c4072ba1d92 |  | note | METHOD: Measure
label | 2ea5b410-7ce0-5b25-b10f-b90cf75f1c6b |  | note | – – – – – – – – – – – – – – – – –
label | 0296dbc3-1759-5fd1-8fbe-1b420be378dd |  | note | FREQUENCY: Each Lot Where Applicable
label | 52da61fa-cbb0-5211-a1ea-24b112975c13 |  | note | – – – – – – – – – – – – – – – – –
label | 05250c98-1b04-53b7-8a60-c87cd60861de |  | note | CATEGORY: IP
label | 8f31c65c-149e-5cca-b3f4-ba513da9daab |  | note | – – – – – – – – – – – – – – – – –
label | e99b2d37-c5a3-54e6-8c87-332cf5433647 |  | note | RESPONSIBILITY: Surveyor/SE/PE
label | 87d6372a-5823-5beb-95b5-2f032133b090 |  | note | – – – – – – – – – – – – – – – – –
label | daf7358f-381c-574e-b6a7-87477b7b33e4 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3f6f5af4-0aae-508b-9b41-4bdde7845431 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 36b1fa06-5842-52f7-b2f8-f3f9cf43c51b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 21ae3396-b38a-5d59-8219-c241dc3d0174 |  | textbox | Name:
text | ccaf0677-7b5d-55c0-a309-fb0e69a1733d |  | textbox | Position:
date | 2efab7e9-9558-5129-92eb-d8fa89ee2312 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Rail Delineation Temporary Fencing Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Rail Delineation Temporary Fencing Rev 0 | 5270c116-1c67-40b5-8e34-ca23d9c50e84
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | 1.1 - Referenced Documentation
label | 0086e2b0-069c-589a-9be8-ffff175534b6 |  | note | Reference - IFC Drawings, L1-CHE-STD-005, L1-CHE-STD-025
checkpoint-group |  |  | section | 2 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete
label | 09c1327a-14b7-5d30-9e4f-2b0d44c01611 |  | note | Frequency - Each Mix
label | 7f42c11d-e549-5e8a-a2cb-3378f5b5ede6 |  | note | Acceptance Criteria - 32MPa concrete to be used as per IFC drawings.
label | 6f09df4d-6fd3-5751-97bf-b925c7b93f23 |  | note | Reference - IFC Drawings
label | e5584958-1795-500e-9983-0b92ba017ff7 |  | note | Inspection / Test Method - Document Review
label | 95c7e122-33b9-5aa5-bfe4-f33eaf68e18d |  | note | HP
label | ce5a7141-ae67-5066-9f75-d2ef4d9140c4 |  | note | Responsibility - SE/Site Supervisor
date | 412a98b8-2967-5cb4-8448-614ec314ab0e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Steel components
label | 163316ae-2a48-53f9-b716-a782f6800f6b |  | note | Frequency - All elements
label | f1df3b1d-11d2-564f-a653-a30d8522ab62 |  | note | Acceptance Criteria - All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250
label | 7985a2e7-99a8-5554-89ad-a41ac7d1d649 |  | note | Reference - IFC Drawings, AS41000, AS1163
label | 4be22392-8002-5946-a48d-b249d02f57e3 |  | note | Inspection / Test Method - Document review, Visual and Measure
label | faaef798-13dd-51c1-806c-c750a31db5c5 |  | note | IP
label | 761fde72-2897-5272-81de-2495ff94b6eb |  | note | Responsibility - SE/Site Supervisor
date | f789bffb-9db8-5405-920f-4f533fe109ef |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Excavation works
label | 1b981071-dc0b-5dfc-b34f-ab4747cab6a6 |  | note | Frequency -
label | 2ba09585-1337-54bc-9213-e39f142c743b |  | note | Acceptance Criteria - Excavation for post foundation must not undermine track and comply with PTDT requirements.
label | 6d1c9ef3-ade0-56b3-92fa-f84b95bc3f18 |  | note | Follow asset owners guidelines for work around their service.
label | 75b96e0a-5c62-5791-af6f-273775b2e82f |  | note | Excavation must use Non Distructive Digging in the rail corridor
label | c8d3de30-4275-5c0c-ab66-126fe514dc82 |  | note | Reference - IFC Drawings, L1-CHE-STD-005
label | a092c613-d32b-5c58-b5a9-50661a135510 |  | note | Inspection / Test Method - Visual
label | 982b54c3-a0b9-5bd0-90cb-793f0f91d498 |  | note | IP
label | ba1447fe-e6b8-539a-b40d-50b7e737dab7 |  | note | Responsibility - SE/Site Supervisor
date | b9aa6b10-a341-5192-bc6a-e3b7422b8cdd |  | date | Date Completed:
checkpoint-group |  |  | section | 4 - Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | 33dfe856-f3c6-54c7-8e2f-daa109bb89c9 |  | note | Frequency - Each element
label | 55cd3fed-ec0f-5726-b22d-b0cc194c92b0 |  | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | fb87e010-88b1-5d95-b57d-13f4767e19fe |  | note | Offset checked against the running edge prior to installation of posts.
label | 978ea0ca-24e0-55d6-be9b-11f219218b76 |  | note | Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
label | 3aefea3a-379f-5ed7-8971-ea72c58219af |  | note | Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
label | 3111979b-40ac-58ff-98b3-41f2f0d792a0 |  | note | Reference - IFC Drawings
label | fd6b2e49-8a3f-51c0-8ea7-758c5a819481 |  | note | Inspection / Test Method - Measure,Visual inspect
label | 620d5139-ada9-50bb-ad4b-fb4c136d1dd0 |  | note | IP
label | e6bec084-f1d8-50e3-8a13-f38ee96e2352 |  | note | Responsibility - Surveyor, SE/PE/SPE
date | cc004d4b-f8da-52fd-a71b-87e846ba37a7 |  | date | Date Completed:
checkpoint-group |  |  | section | 5 - Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Ground Conditions
label | 3b647908-ad1f-5138-97cb-9c07bf0f995a |  | note | Frequency - Each post
label | 014de3ca-70d5-5024-946d-e6b16d0dcf19 |  | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | 5d503c7f-fe35-5418-b162-f7b4da3317cd |  | note | Reference - IFC Drawings
label | 015207d6-4103-5ace-86b5-2631625fe05d |  | note | Inspection / Test Method - Visual
label | 3d33ff62-2377-5851-afd9-6b4c45abdcbe |  | note | IP
label | f125ab25-a848-5ed7-8626-2a0e9a132c80 |  | note | Responsibility - SE/Site Supervisor
date | 2dca586f-780e-5a82-9464-3cd6e089f878 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Post Foundation
label | efbee789-59b3-5e81-be4e-b85286d6dbd2 |  | note | Frequency - Each footing
label | 758a26d3-3759-5fe7-90cc-914a2e714284 |  | note | Acceptance Criteria - Up track (Alongside central pier): - 300mm Dia, - 2000mm Depth, - 2700mm Typical Spacing
label | 8bf885f8-5906-5a7f-a69e-5d708a83cef6 |  | note | Up track (Outside central pier): - 300mm Dia, - 800mm Depth, - 2700mm Typical Spacing
label | 58d8f381-f8db-5729-acea-384d0deced60 |  | note | Down track: - 300mm Dia, - 800mm Depth, - 2700mm Typical Spacing
label | 6162211d-6853-5d34-b78d-cc140ade841f |  | note | Gates: - 350mm Dia, - 1400mm Depth, - 1350mm & 4000mm Spacing
label | 53d8b440-a441-5108-98b8-4216cc55b442 |  | note | Reference - IFC Drawings
label | 22c9d0ab-759a-5578-a4ad-f2471910d875 |  | note | Inspection / Test Method - Measure
label | 53160ea6-6be8-56ca-9108-9fda89a25a30 |  | note | IP
label | ef38cdb4-0a89-504c-a2a2-cf1885f81ee8 |  | note | Responsibility - SE/Site Supervisor
date | 1b827650-a385-5aae-945c-13bc5e4407f3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Post Installation
label | 6879d564-32d7-537a-8c91-6a279cbbe56f |  | note | Frequency - Each post
label | ef9a6d0f-f836-5e7c-9a21-f85263fae68c |  | note | Acceptance Criteria - Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
label | b7ff9f17-187a-54de-bd12-ef5091eb8aa4 |  | note | Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
label | 34ce9ac0-b48f-5fa0-aa81-6d8261e4ec3a |  | note | Maximum post spacing to be 3.1m
label | 326cc269-9341-58b1-bcf5-de497b000c4a |  | note | Two spans at 1350CTRS at the end and at Refuge bays.
label | 6a8af9b1-34c1-5c24-acdd-7d87fdde5bc3 |  | note | Max. post height 1800mm above ground level.
label | ac562a8c-2048-56a3-b239-1621c82fc825 |  | note | Vertical Tolerance: ±20mm from the design line.
label | 0e784094-747c-52ec-b837-1a616ee0520d |  | note | Reference - IFC Drawings, L1-CHE-STD-005
label | cc6f6ece-ce87-5c13-a6e5-692d239898b3 |  | note | Inspection / Test Method - Measure
label | c36e509d-350e-5704-88f4-cb17721fb240 |  | note | IP
label | 30eaa3a9-5ca2-5698-bb46-48207b2da5a4 |  | note | Responsibility - SE/Site Supervisor
date | 963ae305-28be-5f09-b696-9e7a75d16deb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Chain Wire Mesh Installation
label | 470ab7db-2b49-5b02-9fe4-02b3b333e558 |  | note | Frequency - Each element
label | 3f0a80b4-ec1a-5df5-9044-740d00b3628c |  | note | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
label | 8315e12e-9191-575e-b5a7-7e120c08451f |  | note | Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
label | a1963063-b220-58d8-af20-6354e3e91caa |  | note | Reference - IFC Drawings
label | 24e24fa4-1a60-5e7e-926f-e74dc01bb110 |  | note | Inspection / Test Method - Visual
label | b530c5ab-ff4f-5c1b-89b1-5f1de151cdeb |  | note | IP
label | 2f55e57f-79f9-501f-ad09-218d99a5bd74 |  | note | Responsibility - SE/Site Supervisor
date | d68013c9-1a71-5296-bd68-d22d2ea49c5a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Bracing
label | 160a48ed-146e-5ede-88ad-dfb7d85c1a2b |  | note | Frequency - Each element
label | 72f490a6-fdc7-5a68-b6f7-1ad95fbc200e |  | note | Acceptance Criteria - 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | 9a35470b-0d07-589d-be00-ee119a12c6c9 |  | note | Bracing to be installed on both sides of the fence at the fence corners
label | 823c0a41-ffb2-5b15-b081-f88bb856b31a |  | note | Reference - IFC Drawings
label | c60ae786-ae67-5b21-8088-200ff7d41fb5 |  | note | Inspection / Test Method - Visual
label | ebb5177b-7c2a-5174-9eeb-9c870a1c0e7e |  | note | IP
label | 77979268-1229-55a9-8d55-37d9cba713b6 |  | note | Responsibility - SE/Site Supervisor
date | b38a3644-2fd0-5ceb-88d0-6f08a87c8647 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Refuge Installation
label | 4ae06e8b-772b-52ef-8d69-3688e2b65f20 |  | note | Frequency - Each element
label | e76a52b9-fa80-58c4-8041-b854be1496c4 |  | note | Acceptance Criteria - Refuge Access to only open from track side.
label | b87f7d02-caa0-59a3-b292-4c783b9259aa |  | note | No chain wire mesh to be installed at refuge access.
label | 879f7031-7787-5232-8719-f1ec8b8582f9 |  | note | Refuge Access to be located maximum 10m along down track and staggered from up track refuge.
label | 70b41c8a-2abc-5a05-87a9-194eaa26edb3 |  | note | 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | 7179bcef-ccff-5ca7-8e87-f1ebeffce2f8 |  | note | Reference - IFC Drawings
label | 1288de59-4202-570b-961c-856e89717308 |  | note | Inspection / Test Method - Visual
label | 32b970e0-f7e5-5784-a288-b81d8a2f9d61 |  | note | IP
label | a654e461-afbf-5895-baa7-92e8a8ba9d2d |  | note | Responsibility - SE/Site Supervisor
date | 48369f25-0869-5c59-816e-c17790fc45c6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Refuge Signage
label | 673c09e5-862e-5d2c-98ba-6413e340a8d9 |  | note | Frequency - Each element
label | e5000628-cad0-5684-9b91-87b70291c218 |  | note | Acceptance Criteria - Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
label | d9388aaa-5621-538a-ae34-b3ddcc1877fb |  | note | Reference - IFC Drawings
label | 79acefc3-1e3a-5e2d-996c-8ef68c740bd9 |  | note | Inspection / Test Method - Visual
label | 562ff33e-5c20-5f4e-8605-12fb6b095923 |  | note | IP
label | 447301e4-8c61-5df6-8d57-660875cfe6de |  | note | Responsibility - SE/Site Supervisor
date | 6fcb30fe-1d2e-54c2-a7ad-bef5aef2b176 |  | date | Date Completed:
checkpoint-group |  |  | section | 6 - Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Fence Height and Track Clearance
label | 47a120ce-b7f4-5aeb-8dee-4e13d065602d |  | note | Frequency - Each lot
label | cc40d2a0-a501-50ac-99dd-416b2503904e |  | note | Acceptance Criteria - Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | 76338719-8d67-5316-924e-11c7d1e7978a |  | note | Reference - IFC Drawings
label | 47871499-9815-5917-8b1e-f62d11d6a238 |  | note | Inspection / Test Method - Measure
label | 2162d943-628c-57b2-b695-d9436c46ee02 |  | note | IP
label | 9e3e266f-0a95-59d9-9026-87dc8414f9de |  | note | Responsibility - SE/Site Supervisor
date | 0a653097-3e0f-5e7d-b7ac-f6f5fb3b3314 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 2d995c11-3f8d-511c-867e-e8a9a98b9228 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d5b9598d-5fe5-5e89-a571-b32eaa3c0aa3 |  | textbox | Print Name:
text | 33204aeb-f0cc-5abf-9a3a-03a18e6f926a |  | textbox | Position:
text | 1ef87d97-d9b6-544d-8671-f34297db17f9 |  | textbox | Work Completed On:
date | 354353d3-bfb4-5f39-87d2-c14a100016b6 |  | date | Date:
checklist-sectioned |  |  | checklist | ITP-072-CIV-Camms-Guard Rail Installation Rev 0 | itp |  |  |  | Yes | ITP-072-CIV-Camms-Guard Rail Installation Rev 0 | 54001b4b-9982-4c7e-8d71-3427066ff86d
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 82b23b62-3ef7-52f2-943b-c8eebaf58a71 |  | note | Document Title: ITP-072-CIV-CAMMS-Guard Rail Installation
label | 65b2166f-415d-5dbd-b9d6-3be35907f464 |  | note | ITP Description: CAMMS-Guard Rail Installation
label | d4515f5d-5e17-5e7b-871d-871902935459 |  | note | Discipline (e.g. CIV/STR/RAIL: 072-CIV
label | aa6f9dc5-7bcb-5f02-8522-9f463af1be79 |  | note | Revision Number: 0
label | 55ac858b-ea94-5857-9e01-5f61e905c19c |  | note | Revision Date: 23/10/23
label | 436f7e8d-aa50-5083-9557-7715c2617a03 |  | note | ITP created by: Romualdo Magpantay
label | 848508c3-009a-5f72-9b27-d949c377556f |  | note | ITP approved for use by: VM
label | d2d300e8-609e-57eb-9065-fede9343abf9 |  | note | 1.1 VicRoads Section 708 November 2018
label | 54564107-6d0a-5fe2-acfd-2a1f3f42c601 |  | note | 1.2 VicRoads Section 703 April 2019
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Accepted Products and material confirmation
label | 94963a06-e7db-575d-bf22-359acc3199c7 |  | note | REFERENCE - VicRoads Spec. Cl.708.04
label | d2c7ede0-ab0e-54a3-8ffb-524967c875cd |  | note | – – – – – – – – – – – – – – – – –
label | 6a3273b0-be02-5c83-84e9-bff4049da44b |  | note | ACCEPTANCE CRITERIA - Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. Check design drawing for correct type of barrier, transitions and/or end connection and any additional material component requirements
label | 374fb8d0-8d8c-541a-a48a-3a1a1fd56d19 |  | note | – – – – – – – – – – – – – – – – –
label | 9fc2a447-b94f-584f-a6d9-c79526124e17 |  | note | METHOD - Document Review
label | cc1fbb7a-506f-51d5-b647-a9d12f4ea472 |  | note | – – – – – – – – – – – – – – – – –
label | 79fb14b8-a0f3-57fe-bf24-af1336a16f27 |  | note | FREQUENCY - Each member material component
label | 9db0e6f7-eb1b-5bc4-add3-71c8c6757d9c |  | note | – – – – – – – – – – – – – – – – –
label | 59e20f07-c69d-5d4f-94ec-4af1a6e217d2 |  | note | CATEGORY - HP*
label | 560abb65-c407-5e80-a285-820c032618bd |  | note | – – – – – – – – – – – – – – – – –
label | 78bfd3cc-2ef8-54e1-b9ff-f4f52711a4b9 |  | note | RESPONSIBILITY - Nominated Authority
label | f1d76b4b-4259-5a6a-81a1-4db483ad2933 |  | note | – – – – – – – – – – – – – – – – –
label | b2040bb9-809e-5efa-b3e5-aa63fc4f5b51 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 350c2b4d-d8f1-5b0b-9660-7c283c7066b4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Identification of guard fence components
label | a848ce52-c516-5576-a2ee-c04702516d31 |  | note | REFERENCE - VicRoads Spec. Cl.708.05 (a)
label | 0971fc47-5c53-589f-9bb5-7861e75afeb0 |  | note | – – – – – – – – – – – – – – – – –
label | f71a8348-e4df-5e64-af40-1491a8c5174b |  | note | ACCEPTANCE CRITERIA - w-beam sections, both ends of posts and all plastic components of proprietary end treatments unobtrusively and permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
label | c4faac22-4a3a-5a73-b325-df915b593bb8 |  | note | – – – – – – – – – – – – – – – – –
label | 962a1b31-fc40-5c74-907d-21b26cb87fff |  | note | METHOD - Visual
label | c2cd7664-fc2c-5125-bc4a-36ae701f7555 |  | note | – – – – – – – – – – – – – – – – –
label | e05102ff-66af-55c0-8f09-19923bba335d |  | note | FREQUENCY - Each member material component
label | 8bf4c5c2-b299-5368-991e-b0e5e40de56e |  | note | – – – – – – – – – – – – – – – – –
label | b755ebc7-56d7-50cd-94a7-f03b4130629e |  | note | CATEGORY - IP
label | 853d0ae8-52a4-5ecd-bfd7-3b506f88978c |  | note | – – – – – – – – – – – – – – – – –
label | f7f6c48f-845a-5661-a361-f2e73046b0a8 |  | note | RESPONSIBILITY - SE/PE/SPE
label | c9c1316f-d9e5-5cc0-a570-d60a04a21906 |  | note | – – – – – – – – – – – – – – – – –
label | 0c463bc3-6413-515a-9fc4-e293f0ac5b4d |  | note | VERIFYING DOCUMENTS - This ITP
date | 36c44c6e-3022-5096-a461-17ea2686988c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Obtain and submit Material Test Certificate of Compliance for the barrier systems
label | 074950ac-8a17-5c0c-9c2a-035c6b29495e |  | note | REFERENCE - VicRoads Spec. Cl.708.05(b & c) AS/NZS 1594, AS1627, AS 4680 ISO/IEC 17025 a
label | 3933d5e4-fd9f-5f55-8475-19b43865eba3 |  | note | – – – – – – – – – – – – – – – – –
label | 17e603b9-984d-532e-8bef-316f1ccc75bc |  | note | ACCEPTANCE CRITERIA - W-beams and terminal sections shall comply with AS/NZS1594 Grade HA350. Steel posts and blocks shall comply with AS/NZS1594 Grade HA250. Treated in accordance with AS1627- Parts 1 & 4. All test reports shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for that laboratory.
label | 99d8307d-3b5f-5d80-8b24-520db46390c0 |  | note | – – – – – – – – – – – – – – – – –
label | 9291cb4d-30af-5e0a-90c0-61efa698390e |  | note | METHOD - Document Review
label | 1a5eb091-38ae-5192-a910-2da4755485c9 |  | note | – – – – – – – – – – – – – – – – –
label | a4171703-1f6c-553e-971b-409f9497825f |  | note | FREQUENCY - Min 14 days prior to commencing, 1 per 1000m of material
label | 3767b16a-48c9-53fc-9e08-7f7b64865ec4 |  | note | – – – – – – – – – – – – – – – – –
label | fefcd163-c6a8-5716-9bd2-c51153c51df6 |  | note | CATEGORY - HP*
label | 54ecc864-5c35-5269-9748-b82213aa95e1 |  | note | – – – – – – – – – – – – – – – – –
label | 7d8af2f5-8df3-577c-a546-bea1602a2531 |  | note | RESPONSIBILITY - Nominated Authority
label | 0c1e2774-d3f6-5bd4-9115-47f51ee11b8b |  | note | – – – – – – – – – – – – – – – – –
label | afecae50-3dff-546c-87c3-6ea47b2ab57a |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 9fe066a9-00f8-5ae1-ab9a-c2305f86ade4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Verification of Protective treatment/ galvanisation records
label | e43e4f80-e917-5c9e-bca1-95ce1dcd8705 |  | note | REFERENCE - VicRoads Spec. Cl.708.05(d)
label | 9c71c6a1-9ef4-5984-b32b-80dc651e0e0f |  | note | – – – – – – – – – – – – – – – – –
label | 728705e6-57e4-526e-8644-6e71bbcd56d5 |  | note | ACCEPTANCE CRITERIA - Surface preparation in accordance with AS1627 parts 1 & 4. and finished by Hot-dipped galvanizing in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/ requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform. Hot-dipped galvanized coating on bolts, nuts & washers shall comply with AS 1214
label | cd5a3d17-d4fb-538d-b274-53a3fb006608 |  | note | – – – – – – – – – – – – – – – – –
label | 4989bbe5-b541-5920-bcfc-1d834c2a4d47 |  | note | METHOD - Document Review
label | d59df069-d04d-5333-99dc-c8ee396ae00c |  | note | – – – – – – – – – – – – – – – – –
label | 022d5f8d-01f6-533d-a238-530a41cef390 |  | note | FREQUENCY - Min 14 days prior to commencing, 1 per 1000m of material
label | 20a6ef16-851f-58dc-82c2-8f013656cfa2 |  | note | – – – – – – – – – – – – – – – – –
label | a3716d44-287e-5fd7-ae8f-190c2f69ee9b |  | note | CATEGORY - HP*
label | da42ecfd-fd3a-5789-8728-88b3ee8daf21 |  | note | – – – – – – – – – – – – – – – – –
label | bb5f31ee-fb62-5810-aa0a-e153be500c28 |  | note | RESPONSIBILITY - Nominated Authority
label | 1f491064-8164-5b52-9556-2ba724732b52 |  | note | – – – – – – – – – – – – – – – – –
label | 247b2229-1c1d-592f-be00-b1d53d22b0cb |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | a00656aa-590b-5532-a01a-55d71df56d2c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Concrete mix design
label | a6943853-ac7f-5788-b3d1-bf4131613c10 |  | note | REFERENCE - VicRoads Spec. Cl.703 Cl.708.05(g) AS1379
label | 5139b15b-28d6-5d39-81cb-b6b48236703b |  | note | – – – – – – – – – – – – – – – – –
label | 5936f923-fec6-51ac-91d9-ed92781ced1a |  | note | ACCEPTANCE CRITERIA - Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either:
label | f8522860-760f-5701-a88e-3182792645db |  | note | (i) Portland cement-based concrete, N20 strength grade,
label | d88badc7-52bd-5b62-8dac-bcd648c68289 |  | note | or (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
label | 83f7c3cb-21ae-56a1-8d2b-b080e81b2d2f |  | note | – – – – – – – – – – – – – – – – –
label | cef55e43-62e3-5029-aadf-a8b6a0fff93e |  | note | METHOD - Document Review
label | fe055e4b-7804-53de-99f7-02968e6c3236 |  | note | – – – – – – – – – – – – – – – – –
label | 2ff6ee62-19be-5568-ae47-5de3c659af2f |  | note | FREQUENCY - Prior to Commencing
label | 320d38f1-a1ff-52eb-986c-89a69ca39a66 |  | note | – – – – – – – – – – – – – – – – –
label | 55555545-d88e-5ca8-a37b-015b161378c1 |  | note | CATEGORY - IP
label | bb8efd48-135a-520a-a115-e34e251f878a |  | note | – – – – – – – – – – – – – – – – –
label | c4e11eb0-31df-52f7-8459-8ea87c565095 |  | note | RESPONSIBILITY - SE/PE/SPE
label | adbd36a4-c296-5e65-a5de-114af1d423d0 |  | note | – – – – – – – – – – – – – – – – –
label | c105de9f-c101-578e-a7a8-9728d9187650 |  | note | VERIFYING DOCUMENTS - This ITP
date | 80b64533-e43d-5e81-85c5-f140a1b6561b |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 3.1 - Survey Set-out
label | 3cdce3e7-f901-57dc-9cfe-1633ece4b46e |  | note | REFERENCE - Project Spec. Cl.1190.07 IFC Drawings
label | f55676b6-fed8-5070-87a7-939c3242084b |  | note | – – – – – – – – – – – – – – – – –
label | 4da8df9b-736c-5459-ac8a-af92adbf676f |  | note | ACCEPTANCE CRITERIA - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.463 (November 2018) / 610.473 (March/June 2019) as applicable to the element. Attach: Survey As-builts / Survey Report
label | 52f652ab-bec5-5bcd-819f-3c5a7e339d35 |  | note | – – – – – – – – – – – – – – – – –
label | 5784262a-f21a-5e4c-baab-db3a23d25a32 |  | note | METHOD - Measure Visual
label | 866395fb-5d53-5d88-aed1-e9f744d949a8 |  | note | – – – – – – – – – – – – – – – – –
label | 0115bfb4-d2cc-5009-ac06-4f2a3026cab5 |  | note | FREQUENCY - Prior to Commencing Excavation
label | 9d9d65d4-ad97-5aa5-84b8-93acfe182f47 |  | note | – – – – – – – – – – – – – – – – –
label | 93a33afc-b96e-5771-903f-4058dcbd70eb |  | note | CATEGORY - IP
label | d15625b5-472d-507f-a839-60a6af9da258 |  | note | – – – – – – – – – – – – – – – – –
label | 89b86516-b40f-5451-b4c6-174fd075dab1 |  | note | RESPONSIBILITY - Surveyor SE/PE/SPE
label | c2357cfb-978c-5ccd-addf-a165aeb4fab4 |  | note | – – – – – – – – – – – – – – – – –
label | 4c31f4b0-b482-5243-a2f6-9b33d42e0f22 |  | note | VERIFYING DOCUMENTS - This ITP
date | 857657f0-d137-5a20-b7e6-596aff02dc94 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Obtain approval of location and length
label | 775fb8e4-2af5-5929-909a-83f567f6f42d |  | note | REFERENCE - VicRoads Spec. Cl.708.08 IFC Drawings
label | 8809f555-2bee-5923-85b8-14eb839ffa78 |  | note | – – – – – – – – – – – – – – – – –
label | e2953ee3-021d-5a60-a5c3-d0f031b84f82 |  | note | ACCEPTANCE CRITERIA - The required location and length of all guard fence shall be confirmed with the Superintendent.
label | 6f053db6-27aa-5ce7-b561-7b53b8cf293a |  | note | – – – – – – – – – – – – – – – – –
label | 1150ca6f-82c2-5350-9bfc-834d0fa0fde1 |  | note | METHOD - Measure Visual
label | 81d25978-2a24-50c5-8506-c1121d54460c |  | note | – – – – – – – – – – – – – – – – –
label | 211c14d3-8a0c-5ded-a5fa-9e83afc06427 |  | note | FREQUENCY - Prior to Installation
label | 6ceb7af0-1f51-59cd-9e65-dfb50c339651 |  | note | – – – – – – – – – – – – – – – – –
label | 50a4e27e-491c-5df1-aae4-fa6ab325ffae |  | note | CATEGORY - HP*
label | fe9e4b9c-0d6f-5c23-9c71-6f228d736001 |  | note | – – – – – – – – – – – – – – – – –
label | 903cead8-744e-5d88-9f03-4e732f52d035 |  | note | RESPONSIBILITY - Nominated Authority
label | 5a6fbbb5-556d-5041-85da-0e0be3e04c85 |  | note | – – – – – – – – – – – – – – – – –
label | eb36a0d9-7b34-516c-ba31-b96fd173a6b1 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 68ff2de3-e534-5895-9dbc-3a98af70ebbb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Install posts, rails and terminations
label | 63322a83-9035-5319-a521-49c5c1fcc15f |  | note | REFERENCE - IFC Drawings VicRoads Spec. Cl.708 .07(a & d ) IFC Drawings
label | e5522b35-1ec9-55c5-bf68-20b3449bf7eb |  | note | – – – – – – – – – – – – – – – – –
label | 99885303-c314-53a7-9528-dfa11837dd8e |  | note | ACCEPTANCE CRITERIA - Posts shall be installed to the depth, line and spacing shown on the drawings. Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
label | 1e493c91-a2c6-583d-81ee-60f96876b464 |  | note | – – – – – – – – – – – – – – – – –
label | 48240ff6-65df-54a8-818d-5545d033984c |  | note | METHOD - Measure Visual
label | a5927c30-f8cc-5702-8684-97e217f5b761 |  | note | – – – – – – – – – – – – – – – – –
label | 28d6fda5-244b-5ab1-b6cd-812fee7c649f |  | note | FREQUENCY - During construction.
label | 92dbd572-9470-582c-b9e5-55827fb187dd |  | note | – – – – – – – – – – – – – – – – –
label | 07554b30-497f-5bdf-9aa7-3294a11054ab |  | note | CATEGORY - IP
label | da26a078-286d-5d73-938f-cbbda1d0da2c |  | note | – – – – – – – – – – – – – – – – –
label | 200ea55f-cb62-5626-a87b-ec64ce465ac0 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 9fe44cdb-8a7c-5dc3-9fca-b3a5bddb0bee |  | note | – – – – – – – – – – – – – – – – –
label | 2e66fcaa-4991-541b-98f3-e5c638a9572e |  | note | VERIFYING DOCUMENTS - This ITP
date | 918c487d-b3d0-537f-83c9-ea505c7c4f93 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Construct crushed rock base for maintenance strip
label | 13884c1d-726f-503c-8c39-fa42f65c0f19 |  | note | REFERENCE - VicRoads Spec. Cl.708 .11 Cl.812
label | 2d16a55b-3fda-5af4-b405-fef952370454 |  | note | – – – – – – – – – – – – – – – – –
label | 27d81ed4-a6fe-5554-a81d-ac772009175e |  | note | ACCEPTANCE CRITERIA - Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
label | b69150ab-6422-5c5c-abe1-1a78b795eb1e |  | note | – – – – – – – – – – – – – – – – –
label | 1977afef-c4df-51ea-8418-5ee05bd7d474 |  | note | METHOD - Measure Visual
label | 171cccc2-3d54-5f7e-99d3-098c66a8a5cd |  | note | – – – – – – – – – – – – – – – – –
label | bc5c2c13-2e9c-56cf-945e-a413070152a5 |  | note | FREQUENCY - During construction.
label | e492ec48-0c9d-5e79-abd2-e5bf2a114a9f |  | note | – – – – – – – – – – – – – – – – –
label | ea339fea-eade-5b10-8fd9-4d2f73ad0012 |  | note | CATEGORY - IP
label | 52c064db-0a54-5f3f-979d-55b97882c4d0 |  | note | – – – – – – – – – – – – – – – – –
label | df302e44-18e9-5b19-925f-14434590b196 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 56b40a33-d7b7-564d-9796-ef41a518dcea |  | note | – – – – – – – – – – – – – – – – –
label | b4862ef6-10dc-53f6-b78d-ed44eeb81422 |  | note | VERIFYING DOCUMENTS - This ITP
date | 97b6c269-9d67-5a83-bab5-3e12b1276c81 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Construct concrete maintenance strip
label | 9bc2232e-8d56-51f3-9709-e685efc5696b |  | note | REFERENCE - VicRoads Spec. Cl.708.12a Cl.708.5g Cl.703.11
label | 50c8b30b-6bc4-5300-9d22-99becb764fd7 |  | note | – – – – – – – – – – – – – – – – –
label | a21fc973-417e-5e51-a3cb-2103c5e7e266 |  | note | ACCEPTANCE CRITERIA - Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam, Concrete testing at 1/50m3 per day, expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set
label | aac44286-0e85-540e-8a0d-065749ce6f60 |  | note | – – – – – – – – – – – – – – – – –
label | e94d002b-768c-5a2a-ac07-8075f6900a22 |  | note | METHOD - Measure Visual
label | 47d8cfb0-506f-5cdd-be78-b691fd17ea9c |  | note | – – – – – – – – – – – – – – – – –
label | caca3420-d0d9-51d1-b355-7540b28b42e1 |  | note | FREQUENCY - During construction.
label | 22227338-efca-5501-a879-bbee654a6d9d |  | note | – – – – – – – – – – – – – – – – –
label | ad0eda72-75d3-54f0-af18-5e553edc8bff |  | note | CATEGORY - IP
label | 77bc2108-9d3a-5c7b-84ef-a5b5b75bd81c |  | note | – – – – – – – – – – – – – – – – –
label | 3596273e-6851-57bc-a8f9-bfb91b45d3f7 |  | note | RESPONSIBILITY - SE/PE/SPE
label | a131608e-267a-5a34-8ae9-0c2252d30e6c |  | note | – – – – – – – – – – – – – – – – –
label | ed20ca43-cf51-52e2-8fca-716ed595a932 |  | note | VERIFYING DOCUMENTS - This ITP
date | b21d4635-7519-5aeb-ae5b-9797abde91f9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Curing of concrete maintenance strip
label | 834939b0-4774-5595-bd27-badd6cca41ee |  | note | REFERENCE - VicRoads Spec. Cl.708.16 Cl.703
label | 2e82939a-f069-50bf-91e0-4fc89a4c55e2 |  | note | – – – – – – – – – – – – – – – – –
label | ab567fe7-649f-5e8b-91de-850d8529da8b |  | note | ACCEPTANCE CRITERIA - Concrete shall be cured either by water curing,wet hessian,polyethylene sheeting adequately sealed against moisture losses, curing compound or combination thereof. Curing compounds to be in accordance with AS3799.
label | 38c625bb-e20e-5fc9-8e14-eb229a67bbe3 |  | note | – – – – – – – – – – – – – – – – –
label | e2012c9f-3b57-5ba7-a454-7f9a0c05307e |  | note | METHOD - Measure Visual
label | ddcdbdfd-f347-55fa-92e5-2e009d93b96a |  | note | – – – – – – – – – – – – – – – – –
label | 8222ca4b-5b2e-5dbf-96ae-27b8961be5a6 |  | note | FREQUENCY - no less than 7 days after concrete placement
label | 131c94fb-b911-5c9c-828d-7c864d218e50 |  | note | – – – – – – – – – – – – – – – – –
label | 91a516e1-ff99-597f-943d-fa6801c450d8 |  | note | CATEGORY - IP
label | 32f14dcb-ed5d-5cd1-9be9-23396af71fa1 |  | note | – – – – – – – – – – – – – – – – –
label | a1500bf7-4dca-564c-9d8b-ed4f80401df9 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 692af370-32e7-583b-9541-1084fd77dbc0 |  | note | – – – – – – – – – – – – – – – – –
label | 98cae74a-910b-5a3f-a665-c14abf7f0c06 |  | note | VERIFYING DOCUMENTS - This ITP
date | c7cd3262-f971-5eab-a4f6-d56d9fbfc27a |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Delineators
label | 0b172b35-56e0-5447-9dc7-41d7d7e54f00 |  | note | REFERENCE - VicRoads Spec. Cl.708.11 Cl.703.12
label | 0f6c0501-4df5-56a1-8c49-0f4f94be66aa |  | note | – – – – – – – – – – – – – – – – –
label | eddeb38e-b347-5e1f-b598-a19ce9cd8249 |  | note | ACCEPTANCE CRITERIA - Appropriately coloured delineators fastened to top of w-beam at 15m spacings, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2
label | d7ae0eeb-91cc-5c6b-a4f3-865703cf7003 |  | note | – – – – – – – – – – – – – – – – –
label | fbcc816b-9fd6-5ea2-947d-bf17405c044d |  | note | METHOD - Visual Document Review
label | 686cd750-5b0e-57a9-889b-377bc9eb09bd |  | note | – – – – – – – – – – – – – – – – –
label | 8cd86a43-e587-5c9d-9171-0ecda9368c99 |  | note | FREQUENCY - Once, immediately following the installation and prior to any Work commencing on the members
label | 2d22cd5a-d15a-582b-8dc3-f168267731f6 |  | note | – – – – – – – – – – – – – – – – –
label | 298f847b-9276-5344-91eb-8033e2b6bccd |  | note | CATEGORY - IP
label | c75f7561-d8b0-549a-9502-c12319a2af41 |  | note | – – – – – – – – – – – – – – – – –
label | c983b847-66f5-54d7-8224-4152fa7d7a4b |  | note | RESPONSIBILITY - SE/PE/SPE
label | 09d0cd0b-df57-531a-b1db-24b61b6c1096 |  | note | – – – – – – – – – – – – – – – – –
label | e991797f-1ff6-5a00-a4ba-d351cd9fe1e6 |  | note | VERIFYING DOCUMENTS - This ITP
date | ffc1355a-e81f-5227-96c1-997805fe9369 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Existing Sign & markings Reinstatement
label | 8abd2aa2-d915-5476-9403-5501235792c4 |  | note | REFERENCE - VicRoads Spec. Cl.708.17 IFC Drawings
label | 21a306f5-2a0a-5fb2-9208-f412550e1667 |  | note | – – – – – – – – – – – – – – – – –
label | d68915a2-5f58-5d81-bc24-a74e5f9eb2c5 |  | note | ACCEPTANCE CRITERIA - The Contractor shall reinstate all signs to a standard not less than the pre-existing condition and to the satisfaction of the Superintendent
label | 30d89f3f-66f2-5557-8aa2-fcbd48f8e73a |  | note | – – – – – – – – – – – – – – – – –
label | 266130ac-3085-57a8-99b6-03e35c953730 |  | note | METHOD - Document Review
label | 65ba85eb-3576-55a5-803c-e7d2a9746ba6 |  | note | – – – – – – – – – – – – – – – – –
label | aa217918-9a43-51a1-878a-6c77725d1973 |  | note | FREQUENCY - Each element
label | b6184caf-1b17-5b12-841c-833879f1b6a7 |  | note | – – – – – – – – – – – – – – – – –
label | 70f292e2-9ed0-51ed-838b-6e94800f8e5b |  | note | CATEGORY - HP*
label | 7ddfac4b-0427-5378-acf8-048fd153792e |  | note | – – – – – – – – – – – – – – – – –
label | 51397d9a-bb07-59e5-ba70-70cb937262c5 |  | note | RESPONSIBILITY - Nominated Authority
label | 2ffcb092-7ef9-5448-bb19-9f5239242d70 |  | note | – – – – – – – – – – – – – – – – –
label | 16a31a1e-4ecf-5a3b-a504-6f34eaa909fe |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 5b85e757-ead1-5a92-a55c-13093cb9a4d4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Compliance Audit of Safety Barrier System Installation
label | 36a374a5-fe0f-546e-ae20-8763b0088b69 |  | note | REFERENCE - VicRoads Spec. Cl.708.10
label | 5449d44e-259b-5e4b-a97c-339ec39d3d10 |  | note | – – – – – – – – – – – – – – – – –
label | 30cff094-508b-55a0-b8fa-243b9113914e |  | note | ACCEPTANCE CRITERIA - A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance(CoC) shall be provided certifying that the products have installed in accordance with the manufacturer's installation Manual and specification for each end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
label | 9bb0a481-df85-5c0f-98b7-547d39ff943e |  | note | – – – – – – – – – – – – – – – – –
label | 4c7e88a0-711e-5de5-8c6b-973003650208 |  | note | METHOD - Visual Document Review
label | 97b0cbd6-23b4-538d-9944-a45f1f81fd83 |  | note | – – – – – – – – – – – – – – – – –
label | e711afeb-b619-54d3-9621-2458277c4256 |  | note | FREQUENCY - Each bridge beam
label | 904edc75-33c4-58c8-9522-ddfdbc78218b |  | note | – – – – – – – – – – – – – – – – –
label | 2f2f53dc-33fa-5e3c-8ecf-a60f50896f69 |  | note | CATEGORY - HP*
label | b64241cc-ae41-53c7-bd82-4a350f85c46c |  | note | – – – – – – – – – – – – – – – – –
label | ede47391-1a1d-5ecd-b7dc-5ef011382260 |  | note | RESPONSIBILITY - Nominated Authority
label | 0cd428c2-e5b1-5e48-a0db-78f2351df370 |  | note | – – – – – – – – – – – – – – – – –
label | 9715a0d8-773b-5267-b489-8130b699600e |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | c4f3f2bb-0f4e-55b2-9575-ec5ebd98640c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Survey data captured for as-built purposes
label | 629d9b3f-bf9d-5a94-8a93-fe6ce3e95c4f |  | note | REFERENCE - IFC Drawings VicRoads Spec. Cl.708
label | 545a034e-8d14-52c0-9565-fdc291558cf1 |  | note | – – – – – – – – – – – – – – – – –
label | 1f5e1a1a-c9b0-51dd-b6e0-74265d087085 |  | note | ACCEPTANCE CRITERIA - As-built Drawings Tolerances as per VicRoads Specifications, Clause 708.
label | 8ee36ae8-d394-5fea-9904-5c18c7e3d92c |  | note | – – – – – – – – – – – – – – – – –
label | 8088b2bb-9528-5ab3-aa7c-bdc70f9e9d20 |  | note | METHOD - Visual Document Review
label | fb6be460-5c87-5a45-86eb-1a81bfe78277 |  | note | – – – – – – – – – – – – – – – – –
label | 30f56c2f-b48f-5937-9f38-c068bde1f817 |  | note | FREQUENCY - Where applicable
label | b1685301-80a3-5c93-b54a-8bd732aea12d |  | note | – – – – – – – – – – – – – – – – –
label | 5a92c24c-3c07-51ec-a19c-c06828c9f60e |  | note | CATEGORY - IP
label | 41ba2519-f1e2-5b87-a795-770821be3e91 |  | note | – – – – – – – – – – – – – – – – –
label | 8596a6fd-8081-56e3-bb28-a926969d1f74 |  | note | RESPONSIBILITY - Surveyor SE/PE/SPE
label | 6759cdf4-d63c-5a1e-acc7-3c2148891a74 |  | note | – – – – – – – – – – – – – – – – –
label | ef8f588b-0b40-5021-8eb6-bd648cd98c0f |  | note | VERIFYING DOCUMENTS - This ITP
date | 851cc58f-264e-54a8-8fb5-0472bba03832 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Non-conformance Report (NCR) Closure
label | 20c34106-880c-5db6-8317-affb1ec9a20c |  | note | REFERENCE - MRPA Quality Management Plan
label | 5b7ab7a8-90c4-5b6b-bbaf-bbc899564089 |  | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 68ae1207-536a-5229-b0fe-3a53b53752db |  | note | METHOD - Document Review
label | 7c997f6d-4bcd-5c61-912a-e6f7fce3529a |  | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
label | 50c61542-6cba-578c-b4a3-12bc7e9515f3 |  | note | CATEGORY - HP*
label | ec95e029-d625-5785-be50-67f5d57a9fa6 |  | note | RESPONSIBILITY - Nominated Authority
label | a5c64c5c-591e-5a20-ad2e-12955afbfc9c |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 02f46d5c-b07a-5f42-8eb1-fff4717f3a1f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 880c875d-405f-5c69-aaa7-e3b0381ba932 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | a13b5fef-0dd1-5d06-a7c3-058757147f6c |  | textbox | Name:
text | 9bbd1a84-07fd-516b-a6aa-4d18ed488629 |  | textbox | Position:
date | 1e9f7a3b-d55c-504e-8aa6-d99c1f5bd818 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-071-STR-CAMMS-Misc Steel Structures Installation | itp |  |  |  | Yes | ITP-071-STR-CAMMS-Misc Steel Structures Installation Rev 0 | 5882545d-6cd5-4d36-9e59-1c3c830a7218
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 0a2e1c47-7340-5b3f-8764-e085ef3ed92d |  | note | Document Title: ITP-071-STR-CAMMS-Misc Steel Structures Installation
label | c7ae375f-824c-5c14-a949-51d8ec9704b0 |  | note | ITP Description: CAMMS-Misc Steel Structures Installation
label | 49c4ca71-7153-5408-bf1a-65dc7b1aa4d5 |  | note | ITP number: 071-STR
label | ec7c88cd-c3d8-516d-a2fc-2db74928f840 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | bf9c367c-c461-56ad-9350-facda5257f2f |  | note | Discipline (e.g. CIV/STR/RAIL): 071-STR
label | cc08fc7d-c126-5406-922f-ba85f35ed742 |  | note | Revision Number: 0
label | a10a735a-4553-5063-94df-a61fac71a44b |  | note | Revision Date: 19/10/2023
label | 5aed2e42-e571-511d-a777-bd0e01f795b9 |  | note | ITP created by: VM
label | 81167fd5-5df6-5e0b-be50-33bae7c89c78 |  | note | ITP approved for use by: VM
label | f40e625c-c50c-535e-a563-2c80bb59b517 |  | note | 1.1 Non Dependent
label | f2a31085-8c43-539d-b846-32b5ea7d771c |  | note | Reference: VicRoads Section 610 June 2019
label | 8ea4e2de-41a5-5134-a8c7-04db1257211d |  | note | 1.2 Non Dependent
label | 42990769-e530-52f7-8f81-32e648c5567f |  | note | Reference: VicRoads Section 630 October 2013
label | c179ea1f-384b-5a1e-930f-68215b597808 |  | note | 1.3 Non Dependent
label | a8367d3f-16c4-5bb4-9ac8-755c8befbc59 |  | note | Reference: VicRoads Section 631 February 2009
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Structural Steel Components
label | 3bcbf007-9f50-5f57-a6c8-4a15edaf354e |  | note | REFERENCE: IFC Drawings, MRPA Quality Management Plan
label | 1ac02e33-3cc4-564f-bb33-74d346389197 |  | note | – – – – – – – – – – – – – – – – –
label | 19f3a24f-bdf8-51f3-b875-5cfd490c1028 |  | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | 49130c6b-044e-5728-a11a-09ecc67a0820 |  | note | Typically this consists of but not limited to:
label | 36331dfc-ab80-583e-8380-961739931d83 |  | note | i. Certificate of Compliance
label | d02d6c41-eb7e-5cb5-b93f-d3029c926e71 |  | note | ii. Completed ITP
label | 320e1213-c26b-5b34-83c0-9999b311c478 |  | note | iii. Weld Procedure Specifications
label | c692bb33-5383-5d6c-a042-0062565afefe |  | note | iv. Weld Procedure Qualifications
label | b0446422-5bfc-57d7-ac31-12ce0fbd4e95 |  | note | v. Welder Qualifications
label | ba5ae09b-76d6-5c13-b37d-6a7ed919c692 |  | note | vi. Material Certificates and traceability
label | 779adffb-464e-54ad-b6f6-c067bd86e9ea |  | note | vii. Quality Assurance check sheets
label | 40b4dc0a-d12a-58a3-a729-1d69784edc26 |  | note | viii. Welding Consumable batch certificates
label | 82838f74-8c2c-5126-852e-eb252b2360c8 |  | note | ix. Coating certificate(s)
label | 0a720351-29c0-5832-af84-016a82ef0e4b |  | note | x. Non-destructive Testing (NDT) Reports
label | fe8bccf8-5daa-518e-86b8-94db7f117742 |  | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | 392266c0-0d18-5879-8631-b10043fa4521 |  | note | Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
text | 8d959e88-47db-5356-ba11-4b335cfa82d9 |  | textbox | Enter: Teambinder Material Approval number
label | 3499584d-8888-5a85-8d06-5acbb308579f |  | note | – – – – – – – – – – – – – – – – –
label | d17c9c50-8f08-59ea-9c16-28b5e169dcf7 |  | note | METHOD: Document Review
label | a5a45326-eabf-5045-ba5e-b3ac92c76494 |  | note | – – – – – – – – – – – – – – – – –
label | a09a495c-23a9-562a-8672-fc69f40409c2 |  | note | FREQUENCY: Each component
label | f2fffc30-08af-5a27-8b5b-3570fdb4bbbb |  | note | – – – – – – – – – – – – – – – – –
label | 8722da09-7cef-529f-83d3-c0caf404c0ba |  | note | CATEGORY: IP
label | 781d1950-0e34-541b-9d86-73f65f83ebd4 |  | note | – – – – – – – – – – – – – – – – –
label | f9293f7b-1d7c-5cc9-8847-c5ffaf65d20f |  | note | RESPONSIBILITY: PE/SE/SPE
label | 86c1a4c9-d002-5058-9694-0dd1eee33131 |  | note | – – – – – – – – – – – – – – – – –
label | 7f66bfc4-0d32-578f-9afb-cdab4fe861a8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 877cf115-7e5f-579b-9c8e-fd07ad2eee7b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Fasteners
label | a962027d-767d-5a97-9e83-95c0a7e94ecb |  | note | REFERENCE: 630.20 IFC Drawing
label | e769e3a3-0edf-5f2c-890e-30ead2318f11 |  | note | – – – – – – – – – – – – – – – – –
label | ee2c6067-771f-54f2-93bc-bc17327a2aa0 |  | note | ACCEPTANCE CRITERIA: Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
text | e929f389-a836-5154-9187-29a180274b86 |  | textbox | Enter: Teambinder Material Approval number
label | e131432c-7f1f-511d-b2b9-08ab359b33eb |  | note | – – – – – – – – – – – – – – – – –
label | 8bdda4a2-1996-57f4-9377-c83c91985256 |  | note | METHOD: Document review
label | 2829c864-57ce-5585-823d-4830040f8220 |  | note | – – – – – – – – – – – – – – – – –
label | b2976db5-3a77-5221-b255-6d5354f80f56 |  | note | FREQUENCY: Where applicable
label | 7c3428a7-c891-5404-88b1-ae133bdb80b6 |  | note | – – – – – – – – – – – – – – – – –
label | baa2c4f4-7532-5ecf-9b5a-4fa3c24fa900 |  | note | CATEGORY: IP
label | 58f551f7-264c-5fe2-a2e4-59f88f9c9862 |  | note | – – – – – – – – – – – – – – – – –
label | 0cbcfe19-2be0-5bef-bdba-ad94c90023e7 |  | note | RESPONSIBILITY: PE/Nominated Authority
date | 2c2ba8aa-a072-584a-90b9-0ce0fc5dc1d0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Base Plate Structural Grout or Mortar
label | ff6f6727-4f45-5c91-89d5-a1eca2325d6c |  | note | REFERENCE: IFC Drawings 610.33
label | e8b024b3-7427-566f-9e48-bfa1e90e3a9d |  | note | – – – – – – – – – – – – – – – – –
label | 3b25a756-4172-5ded-abc2-788ad7cafcc1 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 0b014222-e100-52e3-80b7-9c1957696344 |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
label | fcb2c206-4931-58d4-9247-22ac01af0f7f |  | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
label | 8ad3ca3f-c77e-5be0-a154-8a65971a7c60 |  | note | iii. have a flowable consistency
label | a331578e-a9dc-5ae9-9565-8c6b9374783e |  | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
label | 4d96bfd0-7d7d-5210-9a43-f1045d260f3a |  | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
text | 85ba5378-a69a-57df-a885-b257b66af24d |  | textbox | Enter: Teambinder Material Approval number
label | 4d0a9fcf-9fba-563d-aca9-cc16d21c58bc |  | note | – – – – – – – – – – – – – – – – –
label | fbd0bc1c-ef69-5b29-9087-c179d4a915d9 |  | note | METHOD: Document Review
label | 0a7f24b3-2de3-5ee5-b95a-0bfb50e2d405 |  | note | – – – – – – – – – – – – – – – – –
label | d0861656-2758-5dbb-abdb-9f61e5d715ad |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 67f8bae3-e30a-51c5-b0d0-1733c6ed0b8d |  | note | – – – – – – – – – – – – – – – – –
label | 280d9f61-1cd8-5487-b0bf-9f7fee962a17 |  | note | CATEGORY: HP
label | a5c04869-1516-5923-b5cb-aea912c3ad0f |  | note | – – – – – – – – – – – – – – – – –
label | 4431a47a-a0b8-513c-b321-bb5d60a77301 |  | note | RESPONSIBILITY: Nominated Authority
label | e694a03e-6e53-5f36-966d-3a20506c8227 |  | note | – – – – – – – – – – – – – – – – –
label | 8388878a-81ae-5669-8327-26261484df40 |  | note | VERIFYING DOCUMENTS: This ITP
date | 079d2cc5-1a21-5594-a514-d4688b74809e |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Curing Compound
label | aaa41da2-9d64-58b7-bd25-c8e61a0ead9e |  | note | REFERENCE: 610.23 (d)
label | ac1f99b9-08c7-56af-a0d3-135582738426 |  | note | – – – – – – – – – – – – – – – – –
label | f9ea40e0-337b-505c-880f-5765b0a9717f |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | f48eef30-7892-56a0-9138-ecc762a2e664 |  | note | Note: This may be the same product used for the concrete curing
text | 46fb93fe-91a0-50d5-ac27-d34ca947b11d |  | textbox | Enter: Teambinder Material Approval number
label | f0da5e36-8ed9-55f9-be0a-59b747b84b1e |  | note | – – – – – – – – – – – – – – – – –
label | 83831218-8dac-529e-b55c-9bb809176bdb |  | note | METHOD: Document Review
label | 17269f30-1994-54a7-b77a-2300f924ca81 |  | note | – – – – – – – – – – – – – – – – –
label | 3cd729f4-a9bb-5f96-9bd2-3ccb943df45c |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | 84eee047-c476-5721-ad04-077579b06d75 |  | note | – – – – – – – – – – – – – – – – –
label | 328a75ed-7c14-51cc-b542-d5b7873f576f |  | note | CATEGORY: HP
label | 94085182-fc66-5668-a7b2-99654a44f1db |  | note | – – – – – – – – – – – – – – – – –
label | 3a3b0008-7c1b-56ef-ae27-4e7090cbd22d |  | note | RESPONSIBILITY: Nominated Authority
label | 446825f9-a237-5cef-b0a6-0f7046ec90c6 |  | note | – – – – – – – – – – – – – – – – –
label | 89bdabb9-2ad5-5ac6-943a-658d3fca8c5e |  | note | VERIFYING DOCUMENTS: This ITP
date | fbec225c-4776-5597-a38d-f75fb3a8046e |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures
checkpoint-status |  |  | checkpoint | 3.1 Installation Methodology & Works Method Statiment
label | 51dc04f2-11d1-5cd0-b6ee-7c0f4111c578 |  | note | REFERENCE: 630.20 AS5131 Clause 11.2.3
label | 110365cf-32ac-5d0a-b5a7-7b1b05ccacf6 |  | note | – – – – – – – – – – – – – – – – –
label | ec71104f-b8e2-5361-bbdf-813be3ad01fd |  | note | ACCEPTANCE CRITERIA: Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
label | 9593fbe2-2235-5414-b069-66ba2fe607a0 |  | note | – Transported to site;
label | 710da349-0a41-5e6b-b4c0-5f7d4b22272b |  | note | – Handled on site;
label | 71596a3f-ceb2-5758-8f63-5780b96ab60a |  | note | – Installation Procedure (subcontracor ITP's);
label | 4a7ee33d-8eda-5e8b-b870-330767cc8d23 |  | note | Attach: Subcontractor ITP
text | 2231d431-6861-596f-8234-3a2249472627 |  | textbox | Enter: Teambinder Approval number
label | 0e266731-3a2f-55c6-8fda-229104700875 |  | note | – – – – – – – – – – – – – – – – –
label | 978a8541-20fe-5fc7-abc8-e8d75db74a6d |  | note | METHOD: Document Review
label | 271c49cf-239a-58a6-b4e5-7f50690e6143 |  | note | – – – – – – – – – – – – – – – – –
label | 9369a1cc-16bf-5c9f-96fb-019c56d5e4bc |  | note | FREQUENCY: Where applicable, once, 14 days prior to use of devices
label | 67145e40-7e2f-5890-b9cf-e6da3f18c441 |  | note | – – – – – – – – – – – – – – – – –
label | 0b3b80de-ab1d-5d53-86d2-f5536d9fd2db |  | note | CATEGORY: HP
label | 9886b822-d68e-5f4e-b988-ec067200bd5d |  | note | – – – – – – – – – – – – – – – – –
label | 4c0f37b2-1066-5787-8133-2b1298f69b1b |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 445dde3c-57d2-5ede-9280-6fedb5a1476a |  | note | – – – – – – – – – – – – – – – – –
label | bbb87d0d-2af5-5e01-b86b-758e39ee1a0c |  | note | VERIFYING DOCUMENTS: Subcontractor ITP, ConQA Hold Point Release
date | 0b622732-1767-5cbe-a676-9c3db1ae0a9c |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 52654f6a-6fd9-5cab-8caa-a11c12f074d7 |  | note | REFERENCE: MRPA Quality Management Plan
label | 8ce0fc28-619d-5b4f-90cd-004e03d4d0e2 |  | note | – – – – – – – – – – – – – – – – –
label | 57779f15-4ce4-5c18-a351-cb65b304e92d |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 9141a7b6-4e4c-50fa-b9e2-5ab73f08945b |  | note | – – – – – – – – – – – – – – – – –
label | 82ca71b6-dfd5-5465-a94b-908e9011c36a |  | note | METHOD: Document Review
label | 03bd1db9-6c12-5307-9f72-a96bb583ac6d |  | note | – – – – – – – – – – – – – – – – –
label | a63d500b-b8dc-5318-89e4-9fb52322d391 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | d9b80911-206f-51f2-b93b-02e6ba528262 |  | note | – – – – – – – – – – – – – – – – –
label | 6b3bcb9c-a6aa-5eec-9f2a-478e871b94a6 |  | note | CATEGORY: HP*
label | 6da00efd-7168-5073-94a6-2c1e9743720e |  | note | – – – – – – – – – – – – – – – – –
label | db3e41cc-1b66-5d8b-926d-6b76ac08ab8f |  | note | RESPONSIBILITY: All
label | 1bc3ecab-afa8-5418-9803-67beb8e7a546 |  | note | – – – – – – – – – – – – – – – – –
label | 3275e42b-9ac6-5e5d-8cb0-415489c8ee96 |  | note | VERIFYING DOCUMENTS: This ITP
date | f5c4cddd-33a3-5c86-88c7-3be41c9d5f58 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Materials Inspection
label | 9bd2dbb0-0e0e-59db-bd54-6d87e69c2f44 |  | note | REFERENCE: IFC Drawings VR 630
label | 843ed5a5-af17-5811-84a0-c1e652056be2 |  | note | – – – – – – – – – – – – – – – – –
label | bac5ae7d-ac5d-5132-a003-20252764ec05 |  | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | 695ae0f7-239b-59da-ade0-0f728fea60ef |  | note | – – – – – – – – – – – – – – – – –
label | 4a5ae102-d93d-53ee-8a9a-596f08cc5f41 |  | note | METHOD: Visual
label | 5b1654b0-ffa4-5ec7-a2aa-14509eacc637 |  | note | – – – – – – – – – – – – – – – – –
label | 3ba94177-ced5-5c1f-bf71-75e198d93fb8 |  | note | FREQUENCY: Each component
label | 4740e64b-1d0f-50df-a2d1-a85eba9dd610 |  | note | – – – – – – – – – – – – – – – – –
label | 0999593c-4fdc-5a3c-a6c9-b40c1d343b1c |  | note | CATEGORY: IP
label | c09ec2b1-7e5a-5d2b-bf14-2a109bddd4b6 |  | note | – – – – – – – – – – – – – – – – –
label | 430bc4b8-d6ba-5bfb-8473-f11b49485e6b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0491c2be-80a9-5035-b660-1b39ff081d92 |  | note | – – – – – – – – – – – – – – – – –
label | deb1d081-1737-5850-9b19-79f9474ad21a |  | note | VERIFYING DOCUMENTS: This ITP
date | 610621b9-330d-516d-bbac-af1b6bfe2107 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Materials Inspection
label | 209882ea-e170-5b5b-9a63-b120a8a66a36 |  | note | REFERENCE: IFC Drawings VR 630
label | 4532218a-3cf7-5226-8e7d-71886aabd0be |  | note | – – – – – – – – – – – – – – – – –
label | 1165988a-8670-5f2d-9b00-919468a01553 |  | note | ACCEPTANCE CRITERIA: Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | 2286699f-a3f0-5f31-b32e-41a8620854d8 |  | note | ○ Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | d44fdbb7-6ffc-5ffa-b7b5-b6fab11f5f9b |  | note | – – – – – – – – – – – – – – – – –
label | 83cbcd6d-7a54-5f2c-835d-a4ef3102c180 |  | note | METHOD: Visual
label | 9ada9ffc-12cb-5e14-8f3a-a026d4ff2c0e |  | note | – – – – – – – – – – – – – – – – –
label | c25d5bfc-28e5-53e8-9f66-3808afc05f90 |  | note | FREQUENCY: Each component
label | f5a65288-1b26-56cd-a0d2-ca4fa838c8ba |  | note | – – – – – – – – – – – – – – – – –
label | 038c5f3b-b9f0-5e27-aea1-2b6c79dc0fc7 |  | note | CATEGORY: IP
label | 76ede48d-ab03-5dcf-8c83-4f5a10ec45f8 |  | note | – – – – – – – – – – – – – – – – –
label | c4a38398-79eb-53a7-b65b-12a225f0b567 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 044dc338-f1f7-581c-8411-90966b8be723 |  | note | – – – – – – – – – – – – – – – – –
label | 8a2a20be-432c-59f3-92f1-e900b70db791 |  | note | VERIFYING DOCUMENTS: This ITP
date | f2c4dbf5-cb16-50d9-a5d2-5a57b023e48c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Materials Inspection
label | e4c15a54-9cea-5759-a7f9-7d1b7ad39f7b |  | note | REFERENCE: IFC Drawings VR 631
label | 3882f9a3-5349-5464-9f6d-6410eb5a230b |  | note | – – – – – – – – – – – – – – – – –
label | 493a2b32-9b52-5315-b844-95f7e16cd06f |  | note | ACCEPTANCE CRITERIA: Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | f7f5af58-8ae8-5e9f-af39-4812127cca27 |  | note | – – – – – – – – – – – – – – – – –
label | c3f480ea-1764-54bf-b19e-820655ac6986 |  | note | METHOD: Visual
label | a9f6fbe7-6b26-53db-a7ff-bb45b64686f0 |  | note | – – – – – – – – – – – – – – – – –
label | d0ac0203-886e-5f1f-98c2-5e5b2f7b95ef |  | note | FREQUENCY: Each component
label | 231a5f64-ca6c-5644-b21a-084ca08272f5 |  | note | – – – – – – – – – – – – – – – – –
label | 677fcd64-2f81-506a-8ba7-055f66ad768b |  | note | CATEGORY: IP
label | cd7d13ed-f8a6-5f4e-b383-773c6fef7dd8 |  | note | – – – – – – – – – – – – – – – – –
label | cdbe72b0-db78-5ea0-afdd-bd1ad6af6c43 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 98e14dec-bb4e-51de-9712-b9cbd4ccd417 |  | note | – – – – – – – – – – – – – – – – –
label | 93ae9f20-e083-54d9-8f39-c6ef03af3aab |  | note | VERIFYING DOCUMENTS: This ITP
date | 43f04db6-2316-542c-a983-d26911dddac4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Materials Inspection
label | b50963fa-40cd-54e8-81ea-ddbd6f020398 |  | note | REFERENCE: IFC Drawings VR 631
label | 7c8d5246-b6a4-53a9-a0c5-dd5471ff223e |  | note | – – – – – – – – – – – – – – – – –
label | 70c084a8-5247-5c83-bc88-78dbced05d24 |  | note | ACCEPTANCE CRITERIA: Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | ed6732ea-73d2-58e5-95d9-f9fb66aebc29 |  | note | – – – – – – – – – – – – – – – – –
label | 5d49762d-edd5-537b-b81c-48d74ef810f8 |  | note | METHOD: Visual
label | a7b098be-a2db-566a-a7c0-b052755467c4 |  | note | – – – – – – – – – – – – – – – – –
label | f169f40a-8737-518c-9889-92502341cf7f |  | note | FREQUENCY: Each component
label | eb551fa5-ce81-5301-bdfe-2d993c5ea3c0 |  | note | – – – – – – – – – – – – – – – – –
label | 22ccfd6c-5d0e-5454-9dac-1c6dd20dbc48 |  | note | CATEGORY: IP
label | d22d8281-5168-5677-b442-14de671e9f68 |  | note | – – – – – – – – – – – – – – – – –
label | f967bcc2-bfe8-5afa-9333-f64edf833579 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c8402184-fba1-5228-b099-8fc6b047f7e5 |  | note | – – – – – – – – – – – – – – – – –
label | d8e80e69-45f4-502d-a55a-9b8e06fc2f6b |  | note | VERIFYING DOCUMENTS: This ITP
date | 984dec67-c896-5cde-aeb2-54829e4192e3 |  | date | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Bearing / Mounting Surface Preparation
label | 909b39e2-6899-5709-a336-50987c9f81dc |  | note | REFERENCE: IFC Drawings Product TDS
label | a0a0e6a8-8424-55ab-b1d4-fcca113099af |  | note | – – – – – – – – – – – – – – – – –
label | bf9128f9-ad4c-5cd8-a850-e53e77cba0fc |  | note | ACCEPTANCE CRITERIA: Ensure the bearing surface clean and free from loose particles that will prevent solid seating of the parts
label | 8691abb6-34ca-555d-a921-f050fc618980 |  | note | – – – – – – – – – – – – – – – – –
label | 4ba37971-2f81-5322-a0fe-9c5c5331e826 |  | note | METHOD: Visual
label | 4fb6044d-bb99-5353-8d0a-2e67e90637a5 |  | note | – – – – – – – – – – – – – – – – –
label | 9611cabc-5d17-576c-8dc1-cfcb39100341 |  | note | FREQUENCY: Where applicable, each installation location
label | f022d1e3-deb6-5ff1-99cc-ca5241eb7f5b |  | note | – – – – – – – – – – – – – – – – –
label | d43e6027-1135-5b0e-816e-404e7959fadd |  | note | CATEGORY: IP
label | 7195d153-5052-5893-90a4-472971dc7eb0 |  | note | – – – – – – – – – – – – – – – – –
label | f8ccd01c-4fed-5310-b143-6ca578fdd383 |  | note | RESPONSIBILITY: SE/PE/SPE
label | be5f15f8-f084-5029-b324-9d1f163794bb |  | note | – – – – – – – – – – – – – – – – –
label | e3ce4ccd-8dde-5246-9522-5a56a822ac9c |  | note | VERIFYING DOCUMENTS: This ITP
date | f7bc1530-c8cd-5b55-bb70-8de654d1b2a1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Structural Steel Handling
label | 5b7a2467-70be-58e1-b859-664b30970b00 |  | note | REFERENCE: 630.09, 631.14
label | 5b60b148-d349-5d4e-b170-ec1aac8db525 |  | note | – – – – – – – – – – – – – – – – –
label | 725ae0f9-66ab-53a9-b459-38540fa7cbb8 |  | note | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | fe8aca8c-f70f-5c1b-a5f3-91f592c43da6 |  | note | – – – – – – – – – – – – – – – – –
label | 1060d1e8-dff3-5456-ab4e-3b5137b9afc9 |  | note | METHOD: Visual
label | 9fb3c4fa-1b23-5bb1-86a4-3fe5cdd28d8a |  | note | – – – – – – – – – – – – – – – – –
label | 992306e5-d1c5-5e17-8308-e2dbfee31ece |  | note | FREQUENCY: Each component
label | 17bc16e2-45e4-5c75-81b0-381fa6c856aa |  | note | – – – – – – – – – – – – – – – – –
label | 02a2ac09-b9af-5b6c-9f35-f583b540ee58 |  | note | CATEGORY: IP
label | 982d8e50-7c9d-5709-a945-bed1663aa482 |  | note | – – – – – – – – – – – – – – – – –
label | 2ee6ac8b-0ffc-5e59-8a09-82441bc37511 |  | note | RESPONSIBILITY: SE/PE/SPE
label | cdaf6525-0e00-59ec-9e75-15465ac675be |  | note | – – – – – – – – – – – – – – – – –
label | cd4a4ab9-8378-55bb-9f20-fed1a7e0ace8 |  | note | VERIFYING DOCUMENTS: This ITP
date | ed66e667-c9ea-5b23-8210-060ebdff7897 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Structural Steel Erection
label | d906088b-89b1-5233-8aa7-04ae27a33427 |  | note | REFERENCE: AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
label | 481c6762-21c8-59a8-8e05-47c85fbf7f47 |  | note | – – – – – – – – – – – – – – – – –
label | 9d4b8aed-390e-5421-88a3-5687a4ef5835 |  | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
label | ba256092-a55b-52e0-a5d0-01801ba9523c |  | note | ○ Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | 522b1ebb-6a8c-5bae-8309-a28a1f544e8a |  | note | ○ Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
label | bd253ff0-3443-557c-8bcb-49aebc71b856 |  | note | ○ Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm
label | 1d502d65-ff6e-53ec-92de-386b59a6a944 |  | note | ○ Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | 5557d915-b702-54df-9c0f-4e5590b34046 |  | note | – – – – – – – – – – – – – – – – –
label | c4aa6e41-71e5-5e8c-8a6d-88f4fb7d5a4d |  | note | METHOD: Measure Visual
label | a065c3e9-6efa-5f17-b265-750c64ae7490 |  | note | – – – – – – – – – – – – – – – – –
label | 13e6b0ea-da10-560c-9563-61fff52f52a3 |  | note | FREQUENCY: Each component
label | b5899223-4fe5-5d5b-82c0-b0efd7e348be |  | note | – – – – – – – – – – – – – – – – –
label | 6e4e16c5-e581-5c78-9cf9-0579864ddc60 |  | note | CATEGORY: IP
label | 5e8add9c-1eed-5687-ae00-ce35a07abe98 |  | note | – – – – – – – – – – – – – – – – –
label | 7041da97-413a-51ff-b012-5c9e3803257d |  | note | RESPONSIBILITY: SE/PE/SPE
label | ff1f8a5b-c8d3-5d87-a7bb-6abb115733ba |  | note | – – – – – – – – – – – – – – – – –
label | 678b6130-20fd-5cba-ba71-a3c0ba02a868 |  | note | VERIFYING DOCUMENTS: This ITP
date | 389a8162-3f12-5308-9954-4f7d9db1ae1e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Fastener Tightening - Snug Tight Condition
label | 902592f3-466f-5829-b359-14fe71e33a14 |  | note | REFERENCE: IFC Drawings VR 630
label | e90bfa9a-a642-51af-ba42-7af7ba37d427 |  | note | – – – – – – – – – – – – – – – – –
label | 1551de8e-f147-5a57-b27a-b4f8e430ae77 |  | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | c202ba40-299d-5eb6-88d2-c0cd5140a90b |  | note | For posts base plates, the arrangement is to be (from the base plate):
label | a9eda965-2645-5603-8bd8-36ed02068339 |  | note | – Base Plate
label | 87588c18-96ac-5fbb-8d75-3dbcf528a652 |  | note | – Washer as specified
label | c8f28365-07bd-56c7-bf8d-9481d8efb898 |  | note | – Lock Nut as specified
label | 815901cc-629e-5f79-be81-a42efd1ee006 |  | note | – Nut
label | 2e32a635-5a46-501b-a21a-e5f81730a099 |  | note | – Bolt protrusion (1 clear tread)
label | 96cd2534-a091-5038-91d6-16dcc7692065 |  | note | – – – – – – – – – – – – – – – – –
label | 5235d99c-0edd-5e72-8e04-96fb3d7fc66a |  | note | METHOD: Visual
label | 4f021e42-22ba-5771-82ab-cdf47f529d92 |  | note | – – – – – – – – – – – – – – – – –
label | 2dc744e6-539d-5157-b3f6-75fbb91b8ba4 |  | note | FREQUENCY: Where applicable, each bolted connection
label | f697e389-9457-5cc5-ba4f-4ad7c4535cc7 |  | note | – – – – – – – – – – – – – – – – –
label | 6a95fb44-053e-53e6-88d6-a628db9ef1a1 |  | note | CATEGORY: IP
label | 4e4e03e0-b77c-5fbe-8a29-8a3e57b8e221 |  | note | – – – – – – – – – – – – – – – – –
label | dbe39650-61dd-54a6-b011-70273d959c56 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7091ead0-1669-5129-96db-0939c189a778 |  | note | – – – – – – – – – – – – – – – – –
label | a7d90e46-7a29-5c08-93a9-659408447306 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5b73cfba-c596-53b6-a7e6-ffca89b7f0c5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Fastener Tightening - Snug Tight Condition
label | d9b66b83-6873-5dd2-af6c-162b81a91f50 |  | note | REFERENCE: IFC Drawings VR 630
label | 39217c04-974f-5e53-9005-1ebfa11a41d7 |  | note | – – – – – – – – – – – – – – – – –
label | 6c755a7b-f559-5c4a-92d9-14ce2f0928e9 |  | note | ACCEPTANCE CRITERIA: Washers shall cover the hole or slotted hole completely by 0.5 x bolt diamter.
label | 652091b6-8180-5a80-9fe8-b8ee2d23a975 |  | note | ○ Tapered washers shall be positioned if specified.
label | 1a6b2788-9743-5ae9-8742-51c745485ee1 |  | note | ○ Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | 86139dc0-7e7f-53e8-8a27-cc362421730d |  | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | fdcb904e-4b07-561f-800a-8d086638a1e7 |  | note | – – – – – – – – – – – – – – – – –
label | 14582ed0-99fa-5957-860b-97315e2f950e |  | note | METHOD: Measure Visual
label | 8a7c959e-94e3-5c8b-89bd-827d6ade9eb5 |  | note | – – – – – – – – – – – – – – – – –
label | b0b4c3d2-46a8-5c80-a70a-d27e6babb22f |  | note | FREQUENCY: Where applicable, each bolted connection
label | c5c9be4f-ab58-5285-aa54-55bdd934ac63 |  | note | – – – – – – – – – – – – – – – – –
label | 2413e9b8-0fc7-575b-9f73-77e5affb379a |  | note | CATEGORY: IP
label | 2245d4cc-15e6-5917-9c1d-6b88ad01e159 |  | note | – – – – – – – – – – – – – – – – –
label | a7e70c91-f432-5204-bed5-2ca1a96bc979 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 63bec8b4-7cbe-5d48-9958-f4696c48e9da |  | note | – – – – – – – – – – – – – – – – –
label | 5b5c2677-7a6e-5a34-b87c-4e03c5d11810 |  | note | VERIFYING DOCUMENTS: This ITP
date | 84e46c57-4b02-5762-9054-5dd7c248717c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Survey Conformance
label | 73e8df7f-3bf2-54bb-9005-2caa4203c8a4 |  | note | REFERENCE: IFC Drawings AS4100 Clause 15.3.1 - 7, AS5131 Appendix F, Table F3
label | bc2761ce-047e-55b1-9078-e8b3e424207c |  | note | – – – – – – – – – – – – – – – – –
label | 66f7ba5e-3f66-5959-8e7a-bc01beaa215b |  | note | ACCEPTANCE CRITERIA: Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
label | 65060cca-94e1-58dd-9f4b-9f1023d3b3a7 |  | note | Departure from RL = ±10mm
label | 81618609-0afc-5ecf-86d2-ebf1fe3ff159 |  | note | Departure from plan position = ±6mm
label | ee2757af-0e00-5c67-ade8-1be417e9a1bd |  | note | Departure from alignment = ±6mm
label | 894839df-55e4-57e7-a835-139048cef249 |  | note | Irregularities in alignment = 25mm in 30m
label | 7f716bbf-9ce8-5f91-a018-9931e7bbfeba |  | note | Projection of bolt = +25mm, 5mm
label | 74b24105-ae2b-5b64-9a67-8c751806bd80 |  | note | Location of beam = ±3mm
label | de77c721-9c5d-5b36-9d5f-31cdc4415a6a |  | note | Location of column = height/500, 10mm max.
label | 46e7ec9b-cb81-5aeb-b202-a252a2d3fa6a |  | note | – – – – – – – – – – – – – – – – –
label | 677e18ad-5b99-56f8-9648-bcde1ab354b4 |  | note | METHOD: Measure Visual
label | ed0ebc8f-718e-5de7-ab3e-ed9b5a462fc3 |  | note | – – – – – – – – – – – – – – – – –
label | 4a4290b4-f20c-5f34-adf0-21a0ede063e4 |  | note | FREQUENCY: Each element
label | 18dfde7a-53be-5165-8ddb-fef90a2f5037 |  | note | – – – – – – – – – – – – – – – – –
label | d82ed0ab-658e-5bd3-8130-2c3d422a39f7 |  | note | CATEGORY: HP*
label | 18af9f30-f70c-5588-b979-2ab294c26851 |  | note | – – – – – – – – – – – – – – – – –
label | bff0b20f-9e36-52e1-a00d-9712d45fb4b4 |  | note | RESPONSIBILITY: PE/Surveyor
label | 83c11df8-874f-52dd-9bd7-fb95fb73ab1a |  | note | – – – – – – – – – – – – – – – – –
label | 56ad6857-94a9-5161-9469-fd3fa98d8562 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8055f74b-cc25-5b2a-b282-346309c7e84d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Base Plate Formwork Construction & Placement
label | 7494e5af-5a0c-5514-a798-671f79f853f6 |  | note | REFERENCE: IFC Drawings
label | ecd263aa-1150-5f6b-a903-2d01b78668de |  | note | – – – – – – – – – – – – – – – – –
label | 7fbf05ac-025c-5c8f-abf0-2d786e89e506 |  | note | ACCEPTANCE CRITERIA: Dimensions as per drawings to achieve the profile.
label | f65bcce2-8210-5026-997b-10aeda6ed54a |  | note | ○ Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
label | f461e8ed-4a09-59b8-9fac-5c32365d5dbf |  | note | – – – – – – – – – – – – – – – – –
label | 52424e64-4251-5652-90b1-8d06bf1d0748 |  | note | METHOD: Measure Visual
label | 79c53382-ba76-5663-995e-5b2e5d7594b3 |  | note | – – – – – – – – – – – – – – – – –
label | e6824297-cda0-5b61-9e7b-dfec9de06c1d |  | note | FREQUENCY: Each post location
label | 468ca9a8-41b6-522b-a6de-2759abbf8a73 |  | note | – – – – – – – – – – – – – – – – –
label | 41d3b0f4-d8b6-5cfb-99ba-5f260713de2d |  | note | CATEGORY: IP
label | a2ab8af2-48af-5ba4-9629-c58465c13c42 |  | note | – – – – – – – – – – – – – – – – –
label | 8b9f603b-698a-5f82-bf9c-e74cf2bf8877 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 10fbf9ce-0080-58b4-961f-a59b5e4b57d1 |  | note | – – – – – – – – – – – – – – – – –
label | 760be2f9-492a-5a15-b4b4-3e3d6311a013 |  | note | VERIFYING DOCUMENTS: This ITP
date | aa8b235c-213c-5f33-8baa-b292ae9d8544 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pre-soaking Concrete Surface
label | 9bfa0cf8-00b5-5c05-8510-2f762a7dec86 |  | note | REFERENCE: Product TDS
label | a46db344-dca9-56af-9d2d-e5ca72f4fa9d |  | note | – – – – – – – – – – – – – – – – –
label | 3b96d95f-353c-53d5-bfbc-7a621f0894ec |  | note | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
label | 406e4edf-5de3-5f66-8e02-ec461e1c3df9 |  | note | ○ Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
label | 87218078-aea9-55ee-94aa-fb5770dbd6c4 |  | note | – – – – – – – – – – – – – – – – –
label | 1dfec62a-408b-5e44-8552-d8687d27eab6 |  | note | METHOD: Visual
label | 12ecb538-6ec0-5bb5-8ad3-507a4a5c02d4 |  | note | – – – – – – – – – – – – – – – – –
label | 3eb08e72-9dd5-55a0-8120-f05ef19de456 |  | note | FREQUENCY: Each post location
label | 6346d5fe-ec4d-53aa-8a15-9c8f848dabb4 |  | note | – – – – – – – – – – – – – – – – –
label | 63e914ef-94fe-559d-b471-ef7c1201973c |  | note | CATEGORY: IP
label | 81a18b99-2d12-5e8d-a120-5b3757cd8e33 |  | note | – – – – – – – – – – – – – – – – –
label | c36bf2ee-f52c-5708-9d05-fe77c217af07 |  | note | RESPONSIBILITY: SE/PE/SPE
label | ef4113c0-f961-57a7-9e3a-05247536f2db |  | note | – – – – – – – – – – – – – – – – –
label | c3084a24-0cbb-5b2c-bfa4-9080e08532a8 |  | note | VERIFYING DOCUMENTS: This ITP
date | f7939b1f-da1b-5b32-883d-65d810aa085e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Weather Conditions
label | de04d12e-39f6-5b86-a411-96ca4735ca4e |  | note | REFERENCE: 610.17 Table 610.171
label | db81cf0d-4d6e-5f01-95c4-622da531cd95 |  | note | – – – – – – – – – – – – – – – – –
label | 3beee39a-dc15-57f5-84fa-671b422613f0 |  | note | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
label | ca3d6dc1-37de-548f-8bc7-90e38620d08c |  | note | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | e6e69aef-750c-56fa-94cc-3d43c2d9ff23 |  | note | Record: Required information on the Grout Pour Record.
label | f61345f1-d2ba-565d-b19f-7d7bd33b4508 |  | note | – – – – – – – – – – – – – – – – –
label | 7e0685c3-6ab3-5662-9ded-1bc8a0ff6089 |  | note | METHOD: Measure Visual
label | 82c85939-f95b-561a-b4ea-3e217459996c |  | note | – – – – – – – – – – – – – – – – –
label | d4808221-00d3-58c4-9d18-ccae79168d24 |  | note | FREQUENCY: Each lot
label | ac86092c-43a6-5a8d-b080-05ffcb56b5e1 |  | note | – – – – – – – – – – – – – – – – –
label | ffbdb9bb-4c75-5c65-8b78-e2e3499d809a |  | note | CATEGORY: IP
label | bf59f8b6-9818-5260-a93a-8b7cff028d9d |  | note | – – – – – – – – – – – – – – – – –
label | dbda5b95-a48e-59c0-9cd2-71d3102605fc |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 21d2a2ac-89fc-5840-9be8-3a6726e96412 |  | note | – – – – – – – – – – – – – – – – –
label | d1b76cba-58f4-5254-b68f-5f09f9c09af6 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1c493179-139f-5f14-a9cb-ca5ad8daa574 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Mixing Product
label | 9b71886b-8a93-56f4-830a-1833e6c8270a |  | note | REFERENCE: Product TDS 610.28
label | 849130c5-b500-5ba1-95ce-adbd9f4819f1 |  | note | – – – – – – – – – – – – – – – – –
label | 5c1d4375-491d-5ab4-a9a4-20d2139741ca |  | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | 07471dc4-5e29-5833-b525-8fdf9c4e5673 |  | note | ○ Only whole bags to be mixed with potable water.
label | 417e79df-4e0f-5a56-aca7-e8c95eafaea3 |  | note | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
label | 6efe9d2c-6bb4-5f2e-a0aa-4e4014d3b4c3 |  | note | ○ Product poured into the mixer slowly.
label | c84f7888-fc52-5562-a56c-bf295b72b2a9 |  | note | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
text | a3bba657-8b62-5af8-975c-fbd69501b557 |  | textbox | Enter: Required information on the Grout Pour Record.
label | e3ccdde1-b46d-5c8e-804f-c8132cce223e |  | note | – – – – – – – – – – – – – – – – –
label | c81a303d-0c90-5267-91dc-cabac1b6bb35 |  | note | METHOD: Measure Visual
label | b98a401c-0f3f-5d56-847b-e348c2886a92 |  | note | – – – – – – – – – – – – – – – – –
label | c4d984aa-91ad-5198-8808-893a1d7dfbb1 |  | note | FREQUENCY: Each batch
label | b0c35d06-9c74-5334-8ae0-c91c461e4039 |  | note | – – – – – – – – – – – – – – – – –
label | 8fa51c16-8160-5363-908e-d8f2cbcdb408 |  | note | CATEGORY: IP
label | c261a69c-24ef-5e38-9102-6a185f921a71 |  | note | – – – – – – – – – – – – – – – – –
label | ba7552ee-cba4-5b7d-8f9e-2a5052b13cc6 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 92464402-7965-55ca-a6bb-5472e4e19015 |  | note | – – – – – – – – – – – – – – – – –
label | 3fb78345-7461-5b0f-864c-846489e99461 |  | note | VERIFYING DOCUMENTS: This ITP
date | e432b470-0d4c-574e-9e3f-c2d517b660cd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Product Testing - Compressive Strength Cubes
label | 0d1af1b1-cbc3-51db-a00d-aea50aadcdee |  | note | REFERENCE: 610.28, 610.33
label | 18a2ea5e-38a8-5b15-bc97-b5e833b22f6c |  | note | – – – – – – – – – – – – – – – – –
label | 96a71ecb-8597-5307-b5c2-42669e7c3caf |  | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | a5596a49-8b2a-5816-99d8-302897ff7221 |  | note | ○ Testing is be in accordance with the following frequencies:
label | 0a5d1b0f-8416-56b9-aa1e-4fb6a58c27ff |  | note | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 109d2e62-2f2d-5096-8c29-249188a0a238 |  | note | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
text | 3297b0c3-93be-5a7b-986e-19067ac6c849 |  | textbox | Enter: Required information on the Grout Pour Record.
label | 7e6c5a9b-baae-53ac-b7bd-0df192ac4dda |  | note | – – – – – – – – – – – – – – – – –
label | b81cdec9-439f-50ef-8948-8e0a44a7e01a |  | note | METHOD: Test
label | 89a5e3d2-1e48-5af4-8ae4-62c5d489debf |  | note | – – – – – – – – – – – – – – – – –
label | e7db39a6-279d-510f-905b-7d77ded4e884 |  | note | FREQUENCY: Each lot
label | e238b7fc-1cfe-5ff2-b5c5-1ff57936ede9 |  | note | – – – – – – – – – – – – – – – – –
label | bbdd3c9c-7a22-5aad-a051-a6a43fd08c82 |  | note | CATEGORY: IP
label | dbb5ce6a-b56b-5da2-a160-0f12ffa5f265 |  | note | – – – – – – – – – – – – – – – – –
label | 89070aae-3329-5c48-b2d4-dcbb6a50a17b |  | note | RESPONSIBILITY: Tester, SE/PE/SPE
label | 3c6dcc10-0202-5328-a1f5-e91aad9a914d |  | note | – – – – – – – – – – – – – – – – –
label | fa08af79-c597-5934-95c9-ff553c30194b |  | note | VERIFYING DOCUMENTS: This ITP
date | 31a02fb0-69d8-5bd7-b22d-cc3d0b3a6e7d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction
label | 55ed5723-fd68-58a5-82df-d058b3cbf68c |  | note | REFERENCE: Product TDS
label | b71a7c4a-1f50-5acb-92d5-b1d85947816b |  | note | – – – – – – – – – – – – – – – – –
label | cd77e5ac-bace-5ce6-ba5d-fe0a6249ea54 |  | note | ACCEPTANCE CRITERIA: All batches are traceable.
label | 7a7c1ef0-b9d9-5dfc-b361-816060ee885c |  | note | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | be1cd4f8-b37c-5cfb-abd5-aba19b9a6ec9 |  | note | ○ Product should flow to all areas and self consolidate.
label | 3794cee2-8b7f-547b-832f-cae53aa160aa |  | note | ○ Product that stiffens or is showing signs of stiffening shall not be used.
text | 67b2f3d8-1efd-5625-a62d-771e6f540397 |  | textbox | Enter: Required information on the Grout Pour Record
label | 3c98ba03-73f1-5d9d-a706-5c671447414d |  | note | – – – – – – – – – – – – – – – – –
label | 51c516be-486f-50a7-b8d7-01f52d9ad306 |  | note | METHOD: Visual
label | 3969e6bd-0c8a-5e37-9448-cd0e45270dd8 |  | note | – – – – – – – – – – – – – – – – –
label | 2ad24021-9281-51a2-ac47-de6cf1115247 |  | note | FREQUENCY: Each post location
label | 8090aa51-191f-5f90-b616-1355b7efee1b |  | note | – – – – – – – – – – – – – – – – –
label | 3323d8f0-6d06-5894-86a7-a2b475ef1888 |  | note | CATEGORY: IP
label | a505a31d-9154-519c-bc7f-a5cb81949d48 |  | note | – – – – – – – – – – – – – – – – –
label | d6a20d0a-a42c-5251-b973-00842680c296 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 38a1093b-492c-53df-9cb5-75d0449151a4 |  | note | – – – – – – – – – – – – – – – – –
label | 1d9c8c46-cd7c-55b1-b942-57366f8bd397 |  | note | VERIFYING DOCUMENTS: This ITP
date | cf06c4a1-77c5-569f-8c02-2821ed1290c1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes & Protection of Works
label | c86ec3b0-83e0-5fa7-b026-d2e5498b6dd4 |  | note | REFERENCE: IFC Drawings 610.17
label | f58fe14b-1fa7-5471-8ac9-be14052f132b |  | note | – – – – – – – – – – – – – – – – –
label | f2482c51-cd7e-51b6-bede-4300c79ff743 |  | note | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
label | c9f6763e-ac67-54ba-afab-c0b47889157d |  | note | ○ All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 83cf87a3-10d2-53ef-8cf2-08abae7fc2e0 |  | note | – – – – – – – – – – – – – – – – –
label | b184db20-655c-5fb9-9b58-a6031d66b174 |  | note | METHOD: Visual
label | 594f1038-1120-5beb-9219-789ecfc7f525 |  | note | – – – – – – – – – – – – – – – – –
label | 63ff8e40-fe27-581a-9462-2bfa435bc450 |  | note | FREQUENCY: Where applicable, each post location
label | e822b1e7-79bd-5e83-bbfe-da666d87be31 |  | note | – – – – – – – – – – – – – – – – –
label | 73fefb6c-9bc6-536a-85c1-fa486289edb6 |  | note | CATEGORY: IP
label | bdbe686c-a55b-51fc-8f86-1e9ae22da449 |  | note | – – – – – – – – – – – – – – – – –
label | d3887502-4171-5e4d-9733-0834d101186d |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 6f014ad4-6dc0-597c-992f-7de0a672b8e6 |  | note | – – – – – – – – – – – – – – – – –
label | 0e33ec44-3453-5534-a86b-b77fb3dc83f5 |  | note | VERIFYING DOCUMENTS: This ITP
date | b07528f3-8812-56bc-b819-f39a74d5658d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Curing
label | b7b09716-9d8b-5871-a3d0-119c0c47724e |  | note | REFERENCE: Curing Methodology 610.23 Table 610.231
label | 1f2761d7-4d98-5735-8d5c-76cb8487dbeb |  | note | – – – – – – – – – – – – – – – – –
label | 09676e3f-1495-5548-ae6e-87f26f452800 |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | 12520440-5a48-53fd-a1b6-ff119e36fe65 |  | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | 7cc29ab7-0415-5fd0-a83c-95141ee2fa02 |  | note | – – – – – – – – – – – – – – – – –
label | 96ac61b8-7082-578c-bda5-fa7f7ef6949c |  | note | METHOD: Visual
label | 245cd506-8e97-5a93-8396-1e671ff6b556 |  | note | – – – – – – – – – – – – – – – – –
label | 967410ae-13c1-5cd8-ae06-0f251e65accb |  | note | FREQUENCY: Where applicable, each post location
label | 1c5c2034-36a2-57ee-ac47-a6ae9aa480d3 |  | note | – – – – – – – – – – – – – – – – –
label | 6708c31c-7f2b-58d4-9dfa-8344648dbe6f |  | note | CATEGORY: IP
label | 3ea3d624-ff25-57b0-adb2-134a940b3d76 |  | note | – – – – – – – – – – – – – – – – –
label | 9bcdf00d-1a84-5944-b92e-628f4eae56fc |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 954b6b94-5fac-5329-b337-0d0be32dcdf5 |  | note | – – – – – – – – – – – – – – – – –
label | db1e0631-da94-5338-8d89-6a996f040402 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2d2fa3ad-c84a-569a-8512-cc4d6d76a680 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Architectural Steel Erection
label | 411f45f4-4456-5c23-a5d3-f9652b99ab6c |  | note | REFERENCE: AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
label | 5b61c660-e404-5864-a26f-71ae46fa0a29 |  | note | – – – – – – – – – – – – – – – – –
label | d5452fff-83d7-5db1-85a7-22880eb3a218 |  | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level and square
label | 474d9227-e2ba-5c83-a645-d6bb427c9103 |  | note | ○ Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely
label | 993a0480-5979-50d4-83ce-c5fea56d4fbd |  | note | – – – – – – – – – – – – – – – – –
label | e28c0195-7b46-5b51-9f70-77a80134ef9c |  | note | METHOD: Measure Visual
label | ee421339-abd7-551c-b030-5ec57c785c1a |  | note | – – – – – – – – – – – – – – – – –
label | 88ce866f-700d-5130-b2b8-381ba79b294d |  | note | FREQUENCY: Each component
label | ee007ed9-98ee-5869-a552-ff0f85a39561 |  | note | – – – – – – – – – – – – – – – – –
label | 9fd83fe1-3c2e-5b0b-affd-54cdf7186119 |  | note | CATEGORY: IP
label | 43824180-8197-5374-9505-789eb7820027 |  | note | – – – – – – – – – – – – – – – – –
label | 20093675-30f5-5c02-a6e5-392231784da0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 87d02455-48eb-5484-abf5-9567d085d29b |  | note | – – – – – – – – – – – – – – – – –
label | 460a9a58-7e76-56b4-9b4d-333bb850ac70 |  | note | VERIFYING DOCUMENTS: This ITP
date | ebede3b6-ec4f-573f-a068-e269721d2f54 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Architectural Steel Erection-Fasteners
label | 6ecc7b07-67dc-5538-9b32-91d80165db7e |  | note | REFERENCE: IFC Drawings VR 630
label | 2358f4a5-1391-5228-a2a3-3a6b79c9a988 |  | note | – – – – – – – – – – – – – – – – –
label | 55bcf192-d99e-5403-92ad-b51ffa390af0 |  | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | 68e3f5b4-c044-5e98-ba1e-0526dcf1e560 |  | note | For architectural/Security screens, the arrangement is to be (from themounting post):
label | 81412b19-93a5-5545-9488-77ef34ca6445 |  | note | – Post
label | 385ead42-c001-5fa7-a4a0-542d9ec62a60 |  | note | – Washer (s) as specified
label | 2e062e7e-f451-577c-8604-7d109de86cb2 |  | note | – Insulating washer
label | 7294e174-8489-56f8-bd53-4e85406e0cf8 |  | note | – insulating bush
label | 14f9ceca-5036-5906-9022-d700079c0584 |  | note | – Insulating washer
label | d6612cfc-d8a0-5763-8583-5cb7066fae94 |  | note | – washer as specified
label | c405b4df-2883-5e94-a65f-7e8de537b6a4 |  | note | – Lock nut
label | e60667d4-c95f-5e7f-92a3-9f02918a7bb8 |  | note | – Nut
label | bead8ac4-09a1-5f73-8816-c066037e5681 |  | note | – Bolt protrusion (1 clear tread)
label | 4565aae7-89e7-58fc-bcc2-d34abae601e9 |  | note | – – – – – – – – – – – – – – – – –
label | 6b18fea4-8c1a-5357-9067-21903bf7673c |  | note | METHOD: Measure Visual
label | 44ecf696-c720-540b-95b9-e60a2284b4e7 |  | note | – – – – – – – – – – – – – – – – –
label | 94f8ad67-04a6-5f48-b4d5-a4c728a3ab05 |  | note | FREQUENCY: Where applicable, each bolted connection
label | 150f16bd-d9a4-597c-9e7b-321c92de0f83 |  | note | – – – – – – – – – – – – – – – – –
label | 7c99ac79-6349-5be5-9492-61eb9364280e |  | note | CATEGORY: IP
label | 2c85d2a5-0a5d-517f-983e-ffa7384c627b |  | note | – – – – – – – – – – – – – – – – –
label | 24a11027-06db-516a-acce-8e6bdfc94947 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d733ef9b-6ad3-5938-8b10-1087d606118e |  | note | – – – – – – – – – – – – – – – – –
label | f4071065-fdf7-5bec-a749-b49c50e10e4f |  | note | VERIFYING DOCUMENTS: This ITP
date | 1142a3d7-313d-5edc-847f-471ebc8224a9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Installation of Electrical Isolation Materials
label | c54ac554-3f13-56c6-8e02-8bee6ec8e504 |  | note | REFERENCE: IFC Drawings
label | de5555f6-983e-5ce0-921b-976a5fb464dc |  | note | – – – – – – – – – – – – – – – – –
label | b12735fb-70e0-5e92-9c8b-4ca37a3e989f |  | note | ACCEPTANCE CRITERIA: Installation of Electrical Isolation Material in locations specified on the IFC drawings.
label | 6351b676-71c9-594f-9afe-781b3edddee5 |  | note | – – – – – – – – – – – – – – – – –
label | 8451ba0b-549e-5306-b42a-fb2a6e10831e |  | note | METHOD: Visual
label | 0793e2b8-f54e-5483-9e7d-02e69afba980 |  | note | – – – – – – – – – – – – – – – – –
label | 9cc634af-5531-5f5a-8ec5-cdd2541fcf09 |  | note | FREQUENCY: Each component
label | 6b5261af-a50b-5667-bf20-c6b2260c741e |  | note | – – – – – – – – – – – – – – – – –
label | b0e3755e-001f-5a82-b570-8ad53fe4e2ba |  | note | CATEGORY: IP
label | a5e8b8b3-2eb0-543b-9457-6e4060b4dbd6 |  | note | – – – – – – – – – – – – – – – – –
label | 631f89f4-5fc4-5763-a5b8-c8df635d5e00 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 46f4475d-94ee-5ac9-929a-fe9ec709e880 |  | note | – – – – – – – – – – – – – – – – –
label | d9da9c92-c36f-54aa-acb3-4bcf5a493473 |  | note | VERIFYING DOCUMENTS: This ITP
date | 4652c51e-ff2a-5117-90e3-65145fac639a |  | date | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Inspection of Coating
label | 5dd988b3-dd7f-5839-8954-533dde15bbc9 |  | note | REFERENCE: IFC Drawings VR 630
label | c8b428a2-5382-5cd6-832d-034ba6b549c6 |  | note | – – – – – – – – – – – – – – – – –
label | 98889dc3-ffc5-5895-a699-77bae67ff2a0 |  | note | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
label | d0bcba86-3fc1-5f2e-ade9-ce669857a52a |  | note | ○ Where damage exists, it shall be repaired using an approved repair procedure.
label | 73126c07-3af5-5a51-88e7-a5532c2abe8c |  | note | – – – – – – – – – – – – – – – – –
label | 59732d79-043e-51ca-9b18-6b59f70541a0 |  | note | METHOD: Visual
label | c8563ab3-b1ac-5d0e-a89b-d2b771896193 |  | note | – – – – – – – – – – – – – – – – –
label | 5a733e2a-24f3-5579-b64f-05375319ba2a |  | note | FREQUENCY: Each component
label | 2146effa-67cb-5a0e-a83e-44ad9b0480eb |  | note | – – – – – – – – – – – – – – – – –
label | bbe248b5-d7e8-5b47-9be5-8fbde9e94303 |  | note | CATEGORY: IP
label | 79d96d0a-0df7-5034-88cb-d59bc77cfd3d |  | note | – – – – – – – – – – – – – – – – –
label | 4171feb4-38a2-5b42-858b-971b7ad16dfd |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9bebd783-7cd3-53b7-8cca-84ed5dc703a3 |  | note | – – – – – – – – – – – – – – – – –
label | 1493dfdd-9dbb-5846-a534-052ab21adce7 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6ed2feef-af6c-55ae-93f4-90806d64236c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | 503d5725-55d5-50ae-b788-593ba87cfe23 |  | note | REFERENCE: IFC Drawings Product TDS 610.28, 610.33
label | 83f01d5d-ef4e-5a6a-853b-2e1ebdecfd74 |  | note | – – – – – – – – – – – – – – – – –
label | 21454668-ef77-5de5-80fa-ce6d5f500c93 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | 1fdc4f21-8580-503e-8b75-004c797bfb46 |  | note | ○ 28 day compressive strength per sample comply with the design strength.
label | e91ca24d-d45f-57ba-9186-b99e7817af86 |  | note | Attach: Compressive Strength Test Results
label | 52b2d012-2da2-55fb-abf3-5f32cbd2eee8 |  | note | – – – – – – – – – – – – – – – – –
label | be2835a8-b505-5a6b-b455-9e62a419758c |  | note | METHOD: Document Review
label | 4ea15f57-7bc6-59d7-b207-c872fcd4a28c |  | note | – – – – – – – – – – – – – – – – –
label | 4853bfdc-1248-54f7-9770-9281edaffe82 |  | note | FREQUENCY: Each cube
label | 2d00e3b0-23c7-552b-9ad2-48fb990a98f6 |  | note | – – – – – – – – – – – – – – – – –
label | f69c02c7-8ecc-5e2f-96dc-4477362caae1 |  | note | CATEGORY: IP
label | e2ad6aa5-0e9b-5823-9846-5db7499cdd0c |  | note | – – – – – – – – – – – – – – – – –
label | bd03b8a6-385e-524a-897c-587c9423b8ff |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8b392606-084f-5ea6-9b85-8cb34ed1c8cc |  | note | – – – – – – – – – – – – – – – – –
label | 55c081ec-711d-50a7-bc3a-9ce8b34cc770 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3bde3944-476e-50f5-93eb-ac388099dca4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 As-built Survey
label | b9f9e5be-b38c-5d1c-b210-6b6e4cf690ab |  | note | REFERENCE: IFC Drawings AS5131 Appendix F, Table F3
label | bf19be9c-aa1e-5810-9445-6058882b9e7e |  | note | – – – – – – – – – – – – – – – – –
label | 1df1a46b-ac33-5bb1-9135-848c6e1a9a08 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 80418c72-2ad7-52d7-92f8-80615a19c9da |  | note | Departure from RL = ±10mm
label | e01c79db-2b91-5d32-b354-44354d85803e |  | note | Departure from plan position = ±6mm
label | 93d0528e-5dd9-5326-bd5b-e979a3cd1b4a |  | note | Departure from alignment = ±6mm
label | 161c214e-b223-53f3-a93e-0eb7b505c6e2 |  | note | Irregularities in alignment = 25mm in 30m
label | 57395037-c14c-5a2b-a81f-2675b1b4ef45 |  | note | Projection of bolt = +25mm, 5mm
label | fb3719df-075d-50e5-8361-f3f673c46dc8 |  | note | Location of beam = ±3mm
label | cdeca45a-4f11-57be-b2be-3f0946c05d18 |  | note | Location of column = height/500, 10mm max.
label | 8f28c26a-016e-56ea-88b4-8b09a025f061 |  | note | Attach: Survey As-builts / Survey Report
label | 62a28fe5-791d-5bb7-8f53-e259d69fd811 |  | note | – – – – – – – – – – – – – – – – –
label | ad742a09-685a-5761-9d64-0d7c8a844685 |  | note | METHOD: Document Review
label | e519db12-bfcb-5697-b952-642b8f71e189 |  | note | – – – – – – – – – – – – – – – – –
label | c06d6ffe-d873-5651-b8ba-a0061311b2f5 |  | note | FREQUENCY: Each element
label | 221beff5-de0b-5e14-ab0d-cc44a4f396df |  | note | – – – – – – – – – – – – – – – – –
label | 5a47b616-0c9d-54a7-b711-f65d73ccff27 |  | note | CATEGORY: IP
label | bfc4a7dc-80ff-50fa-a252-f669b7c3825f |  | note | – – – – – – – – – – – – – – – – –
label | aaf1e232-e236-54cb-b405-0f6a6a3fd7e7 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | f73fc5d5-8ac6-575a-a7c2-b31c4c69f080 |  | note | – – – – – – – – – – – – – – – – –
label | 7c7fc7de-2b50-546a-86a6-7381fac8c864 |  | note | VERIFYING DOCUMENTS: This ITP
date | 970800d8-68d4-557e-8d06-c815ce5ec9fe |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | ee4baa96-a9ac-5fea-a089-6de591fdbbf5 |  | note | REFERENCE: MRPA Quality Management Plan
label | 5be83803-03bf-5bdb-906c-207757a5d36c |  | note | – – – – – – – – – – – – – – – – –
label | 496e407c-2004-58fa-a6f7-d1965bb7a931 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | b694aef0-68b3-5e75-aab4-0952fe479cda |  | note | – – – – – – – – – – – – – – – – –
label | 41bc13d5-d404-58e3-a643-6a19a5b2c643 |  | note | METHOD: Document Review
label | 6286ef5a-6d36-52c6-a20b-a8f16010f306 |  | note | – – – – – – – – – – – – – – – – –
label | 36f65f50-33bb-5f25-b160-d469ae528bf6 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 0e0e260e-956d-5868-9980-e72827d4bdbe |  | note | – – – – – – – – – – – – – – – – –
label | ed3b0d4f-9598-5032-996b-974df8334f04 |  | note | CATEGORY: HP*
label | c55bbae1-6785-5516-a2d9-eda52994979c |  | note | – – – – – – – – – – – – – – – – –
label | c6363aab-1242-590b-83d6-6777b0d1b606 |  | note | RESPONSIBILITY: SE/PE/SPE
label | cad0c9ef-73d2-55da-ac12-52ed545703df |  | note | – – – – – – – – – – – – – – – – –
label | 4bfbc9f5-013d-51e5-9f0a-ef8a33671b8b |  | note | VERIFYING DOCUMENTS: This ITP
date | 91565af6-db4c-51b4-8e38-438c06e3bb00 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | deec6001-4370-5dee-afb7-6772d6434a7f |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 3bdbf6b2-7f8f-5c9f-8168-446f30ff36a0 |  | textbox | Name:
text | c1af949e-70b2-50c4-be2d-4a00185fc5fc |  | textbox | Position:
date | 8589f3c1-86ff-5bc8-abb4-197c6bb96fcd |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-093-Rail-CAMMS-Pedestrian Crossing Removal & Spot Tamping | itp |  |  |  | Yes | ITP-093-Rail-CAMMS-Pedestrian Crossing Removal & Spot Tamping Rev 0 | 68492a71-7ef8-41eb-ab68-2b0f9d9ae9c8
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 1f26799a-4307-5035-8025-3e9651f16f90 |  | note | Document Title: ITP-093-Rail-CAMMS-Pedestrian Crossing Removal & Spot Tamping
label | b14b337e-1d65-53c1-9184-702c92a405df |  | note | ITP Description: CAMMS-Pedestrian Crossing Removal & Spot Tamping
label | 2dcd2ba4-6643-5c3c-94a3-9e1a36d2e89a |  | note | ITP number:
label | efde42aa-1e84-5f8e-a7f3-f13f087c9b8e |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 6a9256a6-1aad-59f5-8cb1-a9ae9ef271f5 |  | note | Discipline (e.g. CIV/STR/RAIL): 093-Rail
label | 6850776a-4fa2-5ee2-9e97-877511f5059e |  | note | Revision Number: 0
label | 80bab366-91b6-5455-b9c1-73e65be2b963 |  | note | Revision Date: 4/09/2023
label | af8cd854-ecb8-5b9f-9ac5-562bbe2c1a3b |  | note | ITP created by: Jake Argentaro
label | 99189b79-1e09-5440-9426-ccc67d538fa5 |  | note | ITP approved for use by: Victor Mira
label | 325ef94b-5b79-5b14-a0c7-b30df631b55d |  | note | 1.1 Non Dependent
label | 1b1dc24d-04ba-50e2-8bae-2dc781fba55f |  | note | Reference: L1-CHE-SPE-316 Concrete Sleepers
label | c6f09485-36dd-5e95-9903-c35763ae5623 |  | note | 1.2 Non Dependent
label | 1e4dc4f5-ef0b-50d8-bfb6-99251e2d034c |  | note | Reference: L1-CHE-SPE-003 Heavy Rail Construction Tolerances
label | 1cd677e9-ed04-5056-8fe1-f8ba27460677 |  | note | 1.3 Non Dependent
label | 60358319-12bc-5007-9080-044ffb55273f |  | note | Reference: L1-CHE-SPE-064 Ballast Supply
label | aa101328-59d7-5dfe-be00-fe29c73819ad |  | note | 1.4 Non Dependent
label | 881c0d19-2849-54bd-b917-61524511d52d |  | note | Reference: L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
label | 990da862-99ce-59de-9eaa-1bed24a25380 |  | note | 1.5 Non Dependent
label | 90ee4cf3-16d9-5bcd-86fa-1c748af8ae96 |  | note | Reference: PTC Heavy Rail Track Construction Standards Drawing F598
label | 374244d4-56a5-53ce-81bb-0bb810971d8c |  | note | 1.6 Non Dependent
label | 233924c5-2bf2-5cf1-a9f3-1e46fb160d0e |  | note | Reference: Camms Road Package 52 Design Drawings
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.01 Obtain and submit Material Certificate of Compliance for Track Materials; Track Jewellery / Ballast 60mm Aggregate
label | 01f682f0-9c54-59b3-8b7c-91edcd2e3db9 |  | note | REFERENCE: IFC Drawing, Track Construction Site Mudmap, Bill of Materials
label | 3e970568-984c-531b-accf-7c935311bbd7 |  | note | – – – – – – – – – – – – – – – – –
label | daa559c7-6d96-5f13-8596-c42d8db0f544 |  | note | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration
label | 9d6bfd10-2321-5a10-b421-6c47cb08c2b4 |  | note | Attach: Manufactuer Certificates of Compliance
label | db22d78e-18b8-5374-9201-023d50236cc7 |  | note | – – – – – – – – – – – – – – – – –
label | eaa893d2-9a15-54ec-a0be-ebd2c2b3aedc |  | note | METHOD: Review Document
label | f9b2b8de-7160-517a-9d61-faadabd970c5 |  | note | – – – – – – – – – – – – – – – – –
label | ac38bae5-6f2d-5439-949b-0a394acc2556 |  | note | FREQUENCY: Once
label | f917dc4c-5dfb-5019-a1b4-54b943f3279d |  | note | – – – – – – – – – – – – – – – – –
label | e51247a2-762c-538c-b03b-e9aed05e2ce3 |  | note | CATEGORY: HP
label | e32b5f63-86ce-5301-ba47-660d925f9557 |  | note | – – – – – – – – – – – – – – – – –
label | f8028b45-e320-51ca-95aa-54c00528c7d9 |  | note | RESPONSIBILITY: Track Supervisor, Project Engineer
label | 5b45cbc3-c746-552e-a48b-a94324d44104 |  | note | – – – – – – – – – – – – – – – – –
label | 3355a46b-e005-5c8d-9b0f-ce7552232676 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | a4d05182-d3c9-5be6-8991-ff5cf12edaba |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 Submit Asphalt Cutting Plan
label | 635ba5e9-bb31-5831-9af8-78e193e9aa17 |  | note | REFERENCE: Track Construction Site Mudmap, Asphalt Cutting Plan
label | 30f6e68e-5640-5e2c-bd73-f9e7b765317b |  | note | – – – – – – – – – – – – – – – – –
label | 9a7e4c28-d8fc-52aa-93d4-66c9aea23f25 |  | note | ACCEPTANCE CRITERIA: Plant to detail cutting pattern for asphalt required for removal.
label | bf24534f-bf3f-5dde-a526-197668c73692 |  | note | ○ Asphalt to be cut to 150mm depth to provide clearance between cutting disc and concrete sleepers/rail jewellery
label | bc4cf755-881d-5485-9505-0f9f115e432c |  | note | – – – – – – – – – – – – – – – – –
label | 7b656baf-a4b7-5274-a48b-37dd6592f691 |  | note | METHOD: Review Document
label | 998d2811-e40d-5c2b-8a5c-0a648b4d8657 |  | note | – – – – – – – – – – – – – – – – –
label | 498ea975-0bcb-57cc-ada3-94d450361ee0 |  | note | FREQUENCY: Once
label | 0675bc2c-658d-5d42-afc5-b11108c5e07c |  | note | – – – – – – – – – – – – – – – – –
label | 66a885ad-757a-556b-a7a5-ccf9bb06a513 |  | note | CATEGORY: HP
label | d73fff91-7d16-5fd1-b59d-5398f03d416a |  | note | – – – – – – – – – – – – – – – – –
label | 90849dc2-be49-5a6a-a07c-86feac27c92f |  | note | RESPONSIBILITY: Track Supervisor, Project Engineer
label | aa7dcbc1-08b3-5968-924f-1febbf5a9f73 |  | note | – – – – – – – – – – – – – – – – –
label | 50bebc5e-0e90-5670-9b75-a7b0f5846b29 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | e4114312-6a18-5d19-8413-73ff27479611 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 Inspect supplied items upon delivery
label | 23227df2-b88c-59bf-ae3d-972ca8eb95bf |  | note | REFERENCE: IFC Drawing
label | 31a05b0a-6bb6-51a7-84cb-b10bcf11a2e0 |  | note | – – – – – – – – – – – – – – – – –
label | f6e550d6-77e9-5369-a634-22b673caf9f6 |  | note | ACCEPTANCE CRITERIA: No damage or rust on components
label | 36e764dc-2808-512d-b747-86f3e7be21dd |  | note | ○ Validate total number and type of components matches drawing
label | 154dcb05-c133-5553-ba1e-2f327b391b4d |  | note | Attach: Photos on site;
label | 286a1b2c-1df6-572f-808e-eedb98020f04 |  | note | – Track Jewellery
label | c4a20f9e-9505-51e6-96af-0630d77e7076 |  | note | – Ballast 60mm Aggregate
label | 4a8de085-ffc5-5d8f-bc92-1b37cf7c7fb0 |  | note | – – – – – – – – – – – – – – – – –
label | 7eb6df63-a8a4-5760-a52a-6484379422cd |  | note | METHOD: Visual Measure
label | 119667e1-760f-5040-860d-57c2c41c3465 |  | note | – – – – – – – – – – – – – – – – –
label | bf240934-8c2e-503b-a031-1a7eea040596 |  | note | FREQUENCY: Per delivery
label | 23d5203f-4ce4-5c6e-b435-115424eee0f8 |  | note | – – – – – – – – – – – – – – – – –
label | 80ec4580-8990-501b-bb91-179076260892 |  | note | CATEGORY: IP
label | 624b084e-93e8-5960-816d-18ab4daf5c75 |  | note | – – – – – – – – – – – – – – – – –
label | 130250d8-5269-55f8-a3e2-55dc4f995164 |  | note | RESPONSIBILITY: Track Supervisor, Project Engineer
label | 4d817a4e-bbb6-555e-b650-f48fa4f83265 |  | note | – – – – – – – – – – – – – – – – –
label | 7ac6e26e-e82b-5b04-b905-c2654b182d18 |  | note | VERIFYING DOCUMENTS: Material Inspection Report
date | 77d11e25-69ab-5588-9a2c-b5bb22bb73ee |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.01 Cut and remove asphalt, Clean track structure of loose asphalt and debris, remove contaminated asphalt as required
label | 1d42ac6f-175f-5869-ae0d-a7a2cd32c704 |  | note | REFERENCE: Asphalt cutting plan
label | a9a9907b-012c-5cad-8863-5024de1529cd |  | note | – – – – – – – – – – – – – – – – –
label | 24b570dd-27c4-522d-bc99-a70bb95e7ccf |  | note | ACCEPTANCE CRITERIA: Cut asphalt as per cutting plan, asphalt to be cut at depth of 150mm so as to avoid damage to rail and sleepers.
label | b53fcdb0-81ec-5c54-95b3-9cff490a6b2d |  | note | ○ Remove asphalt material, clean debris off rail and ballast, remove contaminated ballast as requried.
label | 54f5d971-39df-5d13-9c60-c5a85ce5c417 |  | note | – – – – – – – – – – – – – – – – –
label | 6cf31cd1-e5f1-5b1d-b8d8-44ebba20de3c |  | note | METHOD: Visual Measure
label | 4aa07b22-4f9c-55c6-98c5-e1ae83ca9a6c |  | note | – – – – – – – – – – – – – – – – –
label | dc9e630d-6722-5671-a234-07c3d5c3a099 |  | note | FREQUENCY: Once
label | 8949e415-f83c-5ae1-8619-40c08aee5824 |  | note | – – – – – – – – – – – – – – – – –
label | 3674f1c4-0cb7-5aaa-baf6-270ddff51a95 |  | note | CATEGORY: IP
label | 4fdb8b6c-d3b6-50d1-a361-f328af71d30e |  | note | – – – – – – – – – – – – – – – – –
label | 3d808efc-426d-5e70-8508-69106b6e2334 |  | note | RESPONSIBILITY: Track Surveyor, Track Supervisor, Site/Project Engineer
label | 8bf02ec1-1171-5a6f-819f-0db832fc0191 |  | note | – – – – – – – – – – – – – – – – –
label | 21e5e4d2-681d-53be-aeca-5a779bd64d9c |  | note | VERIFYING DOCUMENTS: This ITP
date | be160695-0f12-5ef9-aee7-7dbdc681a3d3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.02 Fastening replacement as required
label | 85189a59-a7b3-5458-b5ba-3f5fa87e2f96 |  | note | REFERENCE: L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
label | 20078840-473b-5128-b586-7ef2af4e3465 |  | note | – – – – – – – – – – – – – – – – –
label | fc01669b-0e9e-571d-b961-d582c786c57a |  | note | ACCEPTANCE CRITERIA: All rail sitting within Sleeper footing with correct sleeper insulators
label | 0bd21416-03df-535a-8557-7e9898424bc7 |  | note | ○ All rail fastenings installed
label | 25d1b79f-fced-5d02-8dd3-9e0261f78211 |  | note | Attach Site Photo:
label | 73faeb6c-d1b2-56ff-8e1b-29527b183199 |  | note | – Installed sleepers & fastenings
label | c29da72b-1f3f-5d32-800a-5b2d523c7257 |  | note | – – – – – – – – – – – – – – – – –
label | d9ccbfb9-4485-5a4f-8c60-f392c51d1db9 |  | note | METHOD: Visual Measure
label | 62f8c60f-44d0-599d-b7ad-cf38efd3cfb8 |  | note | – – – – – – – – – – – – – – – – –
label | fde433c9-7414-5d8e-8db3-24aa4d3c9519 |  | note | FREQUENCY: Once
label | 805d3d40-7ec8-59c0-b9bc-9244f04d67d6 |  | note | – – – – – – – – – – – – – – – – –
label | 6e89cf42-f608-56f9-99b4-068b4135625c |  | note | CATEGORY: IP
label | 0b334ee7-fab0-50bd-b7a4-45db51f2be7c |  | note | – – – – – – – – – – – – – – – – –
label | 0860407d-dd73-5aae-bc84-d24e8829a2a8 |  | note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
label | 7db0081f-33ea-5d70-944c-65d33e92a83a |  | note | – – – – – – – – – – – – – – – – –
label | 3f6697ae-171a-5000-b28b-2af54af95abf |  | note | VERIFYING DOCUMENTS: This ITP
date | d120b85f-4921-5b93-99fa-4ddfa5017d1d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.03 Track Tamping
label | 046744a4-8a7b-5ea0-b426-119d141fad5c |  | note | REFERENCE: Track tamping alignment as per existing
label | deaea297-6c30-5b1e-bfd1-9276c3e84003 |  | note | – – – – – – – – – – – – – – – – –
label | bc16cfba-9a91-53d4-852b-f1bba45f8353 |  | note | ACCEPTANCE CRITERIA: Track Excavator Tamped, Ensures Track Geometry Tolerances are not breached;
label | f02c40ad-d5a6-5b6c-b450-e5e9d8c4c7aa |  | note | ○ Gauge +3 / -3
label | 8cc3533d-20c8-5ae1-a0af-dcd6700b45b4 |  | note | ○ Gauge Variation in 2m 4
label | a5a6b05d-78f9-586c-90c8-6f1555c82353 |  | note | ○ Line (10m Chord) +4 / -4
label | 1885d887-635b-5161-9a31-c9c4d77e1b80 |  | note | ○ Twist (3.5m Chord) +2 / -2
label | 50c5a826-adf7-56e7-a291-01a2486eb608 |  | note | ○ Top (10m Chord) +5 / -5
label | 000b11c0-a5f6-5adb-8850-7c500cfae840 |  | note | ○ Cant +5 / -5
label | 2ec50e31-f4ba-5e04-8ca7-92aad56f9ffe |  | note | ○ General Alignment +15/ -15 (note, partial resleeper only requries track to be tamped to conform with local geometry, no survey requirement)
label | 237a92aa-b597-52d6-9a18-a3fd4a22ffa4 |  | note | ○ A minimum horizontal clearance of 3.0m from track centreline to structure.
label | 20750d01-06ad-5b1d-bd0f-9c08062d5f0a |  | note | ○ Height and Stagger readings of overhead wire to ensure minimum clearance of 4.61m is not breached
label | 0a6e8c90-1136-5d5e-8e12-d1fc1b378194 |  | note | Attach;
label | abd59798-6d79-5eae-ae4c-434c0bb50c65 |  | note | – Tamping Geometry Recording
label | 87ec04ac-ddfd-57c0-8b09-76a533d874e3 |  | note | Attach Site Photos:
label | 02e6116e-62d5-5327-a615-7ee330d1c450 |  | note | – Tamping Activity
label | 2616411a-0eef-5fe7-9b23-61ee0446bb3b |  | note | – Overhead measuring Activity
label | cb2cd83d-3c65-50de-8065-31a15b2c05f0 |  | note | – Structual Offset Measurement
label | ebd999f9-e115-58ad-b08b-2c0e7cc532bf |  | note | – – – – – – – – – – – – – – – – –
label | fbe87477-fb42-54cc-ac6a-e5189688f863 |  | note | METHOD: Visual Measure
label | 92ea9419-576b-5732-a1a1-e93bc05f5da5 |  | note | – – – – – – – – – – – – – – – – –
label | 0d52f431-2ebb-5076-adbb-a920f77d24e7 |  | note | FREQUENCY: Once
label | c746851c-2597-57c6-9d40-c2772aa42fa2 |  | note | – – – – – – – – – – – – – – – – –
label | e616a2f5-70a8-5b48-9628-463c33252a5c |  | note | CATEGORY: HP
label | ac3960f6-96d7-5459-b6dd-ccc6e65a4941 |  | note | – – – – – – – – – – – – – – – – –
label | 71221f33-0410-5589-80c0-4a795705ca42 |  | note | RESPONSIBILITY: Tamping Operator, Track Surveyor, Overhead Engineer, Track Supervisor, Site/Project Engineer
label | bc973526-a382-5e96-98b7-e2d0625ad861 |  | note | – – – – – – – – – – – – – – – – –
label | 67726ff3-b1e9-55da-9039-98712e0bbb19 |  | note | VERIFYING DOCUMENTS: This ITP
date | 4cc4b95f-1a6c-5113-94f5-e3df8594ba86 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 Regualting and Ballast Profile
label | 04e68190-22f4-554b-b45f-0fb2272092f8 |  | note | REFERENCE: L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
label | c5857e42-6337-5eee-ab6a-2e3ca9e1511b |  | note | – – – – – – – – – – – – – – – – –
label | 07c6637e-2257-5a49-a807-31a68487aa97 |  | note | ACCEPTANCE CRITERIA: Ballast has 400m width from outer edge of kerbstone with 1:5 crossfall thereafter
label | b767f457-1d97-5f4c-b9e1-70fe7b075528 |  | note | ○ No Ballast to be on top surface of sleepers or aorund rail Fastenings
label | 5452caac-f602-5d8b-8a50-682bfd77b72b |  | note | Attach Site Photos:
label | cc29b82f-e176-51c5-9513-e5fa3266ee17 |  | note | – Ballast Shoulder Measurement
label | f3d90e69-26c1-5e5f-a42f-f36a848cb1e6 |  | note | – Rubber Panels free of ballast materials
label | e11f47f0-d8a0-5853-bfb3-0c9713272c87 |  | note | – – – – – – – – – – – – – – – – –
label | e561b3fa-5d59-5ee5-95d6-ee7a6061f404 |  | note | METHOD: Visual Measure
label | 2df39b37-a80f-524f-9f5c-8c55a756e28b |  | note | – – – – – – – – – – – – – – – – –
label | 2e883289-ec3e-59fa-8c79-e5d5151b92d2 |  | note | FREQUENCY: Once
label | 71c7d1ec-b952-5f8e-932b-2b649f6d9cfc |  | note | – – – – – – – – – – – – – – – – –
label | f4d292b0-1ecd-5e6c-9be6-13799c249d83 |  | note | CATEGORY: IP
label | 2c62f4de-a62a-5da5-8f2d-f987c05bb131 |  | note | – – – – – – – – – – – – – – – – –
label | ab9012ad-4fcb-5a23-8376-2ce6e47838f2 |  | note | RESPONSIBILITY: Regulator Operator, Works Supervisor, Site/Project Engineer
label | fa6f1fc4-55cb-5cb0-9410-24068bcb4c27 |  | note | – – – – – – – – – – – – – – – – –
label | 75374d99-5fed-5eb4-ac2f-699e035c942c |  | note | VERIFYING DOCUMENTS: This ITP
date | 126ec64e-b266-52e6-b348-af4d6fba6c8c |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.01 Track Certification
label | 44a7fdb8-3986-5aeb-8bc6-c83ac7e0f9a3 |  | note | REFERENCE: MTMF020000-1 – Track Form A T, MTMF020000-2 – Track Form B
label | 19cbbdfe-9196-5487-b43f-a75e17ab975e |  | note | – – – – – – – – – – – – – – – – –
label | b4152570-cb1e-5c8b-b671-199f94d856bf |  | note | ACCEPTANCE CRITERIA:
label | 6e3e5d1b-0bb4-527c-b45a-ab42dd69c4f5 |  | note | Attach:
label | 37ceddf4-99ba-55c6-bb54-2b59d748431a |  | note | – Track Geometry Conformance Certificate
label | cdf38a20-4cf0-571e-9855-d601a9c9ecaa |  | note | – Track System and Component
label | 4d643ff4-5e54-5f9c-a00f-425a3fe6c4ec |  | note | Attach Site Photos:
label | a8fd7a23-0539-5867-84f4-9b855713bb08 |  | note | – Before/After Photo of worksite
label | 2d49814a-deea-53cd-82dd-1f687253c0a2 |  | note | – – – – – – – – – – – – – – – – –
label | cb636d66-d71e-5cad-829d-383d958932c1 |  | note | METHOD: Visual Measure, Document Reivew
label | 9a756883-9f27-5866-9927-49c6b1d7dae2 |  | note | – – – – – – – – – – – – – – – – –
label | d97692a1-cf02-5180-b34c-9035fc43103f |  | note | FREQUENCY: Once when all occupation works complete
label | fe0d38ec-6bce-540a-bd71-d33cabb7b261 |  | note | – – – – – – – – – – – – – – – – –
label | 9ec135f0-68ed-503e-ad93-332ff6a2d9e8 |  | note | CATEGORY: HP
label | b84474ae-ea11-5915-a8ed-db4b57bca988 |  | note | – – – – – – – – – – – – – – – – –
label | ed218176-c0b4-5a69-b2a4-26f65edf212b |  | note | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
label | 469a9991-3995-5657-9a46-8d43ba25ce0a |  | note | – – – – – – – – – – – – – – – – –
label | 4b55e9ca-63c8-5f83-8ba3-fb7deb8d2458 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 783dc45c-e786-5b1a-a4da-006d3cd96375 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 2c335f2b-a7e3-53fb-83be-e89b94edc38d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 763d319d-9093-5271-8627-5aca7b319f6b |  | textbox | Name:
text | 54c49bf0-1f2e-5ff7-af53-ffe3f227b924 |  | textbox | Position:
date | 4800fff3-b424-5186-9190-2457a669b644 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-003-CIV-Reinforced Concrete Pipe RCP-Material Inspection | itp |  |  |  | Yes | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | 68ba0c44-4839-4ace-8129-64d49bbb9e6a
checkpoint-status |  |  | checkpoint | CHK-003-CIV-Reinforced Concrete Pipe RCP-Material Inspection
label | 019b2fcb-282f-5c03-8510-431764122020 |  | note | Document Title: CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
label | 2e985c30-43bc-5d1f-af5a-ef4b3c6d7b66 |  | note | Check list Description: Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
label | 14dbd2be-5e2d-533b-9141-c209548ddeee |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 0408e18b-9ec2-530d-99a4-3f8dc49ded20 |  | note | Revision Number: 0
label | d57dfd10-cc6c-5046-8c38-83665359dcf2 |  | note | Revision Date: [Date of Approval]
label | ed9d2be5-138c-5841-84b7-05f0043e9d88 |  | note | ITP created by: Jon De Castro
label | b2cb522f-3dde-546a-b1ee-abc3ff3e45ae |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1 - Materials - Fabrication
label | a31d80e0-9e92-56ca-bba7-ff75790fa978 |  | note | REFERENCE:
label | 037a6c07-3cb9-5657-b97f-181c52d18494 |  | note | • IFC Drawings
label | 1fe6dbb8-e520-586d-bb55-62d99625d0b3 |  | note | • Section 620
label | 35d3ed0e-43bf-5b2b-ba5e-27e31b2ec9b4 |  | note | • Section 701
label | d71c2ef3-7063-581b-9742-4776ddfaa98c |  | note | • Section 705
label | 14d20d00-a26d-535f-8f49-fdb852033cb8 |  | note | ---------------------------------
label | 44be64df-c925-5801-8cb5-5561d61b9000 |  | note | ACCEPTANCE CRITERIA:
label | 96778c0b-9592-58f7-932f-665ec11547e4 |  | note | (1) Precast items manufactured in accordnace with IFC Drawings
text | 53b71c7b-85d6-595c-9feb-7e7f231bf898 |  | textbox | - Drawing Ref No.
label | 5f66c1fc-9bb4-5fc4-9dfa-e1aa5eda178c |  | note | ---------------------------------
label | d9d585b2-96b1-5120-b997-d81bec3533fa |  | note | METHOD: Visual Inspection
label | a8615e53-b4b9-5079-ba5c-a2789afb27db |  | note | ---------------------------------
label | 0ae9e1e1-876b-5ffe-a598-2ac5ea35bd2d |  | note | FREQUENCY: Each Lot
label | f2e5db36-0a4f-518e-b1d8-dd07387f53aa |  | note | ---------------------------------
label | 48a2a278-3c84-5831-88ab-eb30a62cc44e |  | note | CATEGORY: IP
label | 16c2965d-c577-5190-8e0f-565e9e4259ab |  | note | ---------------------------------
label | 980af84b-e4da-542b-a3cd-8f34e8e87de0 |  | note | RESPONSIBILITY: SE
label | 3a17464d-f6cc-5453-a034-f1a0e8c1a264 |  | note | ---------------------------------
label | 6a8760dc-a643-5df4-ba94-997d0593c3ff |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
label | 0372291c-020f-581d-a98e-7d2db3a921c5 |  | note | ---------------------------------
date | 101e42e4-3f6f-5b0e-8e35-9484ffdfe762 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Materials - Delivery
label | df8ecff6-40cd-5898-968f-f3d5615a8f4e |  | note | REFERENCE:
label | 1c89a5bd-8e5b-5145-8db3-bb6817e267ec |  | note | • IFC Drawings
label | 00dcc04c-df1d-5694-98c9-50bf90199517 |  | note | • Section 620
label | e36ae1bc-2cee-5516-b266-2c3b07c39ea4 |  | note | • Section 701
label | 46867914-f07f-5e53-bd41-ea570f0bcc41 |  | note | • Section 705
label | 8ca3d48d-c6bd-5cf0-b47e-3ed8458e9f5c |  | note | ---------------------------------
label | f9b0e62e-4560-5b96-8fb5-dcaa56ffa01d |  | note | ACCEPTANCE CRITERIA:
label | 58da26b8-caf0-574c-8c47-a3a67145807d |  | note | (1) Purchase Order and Material Description and Qtys matches
label | 8a3784fe-cf53-538f-a363-9cfd9c137025 |  | note | (2) Ensure precast concrete elements are as per IFC Drawings upon delivery and no damage evident.
label | 8a28b79a-c7af-555f-8b6d-b8440dfedd0f |  | note | (3) Lifting and Manufacture compliance certification provided
text | 8e0ed233-d02a-5c32-b320-e1483b893281 |  | textbox | - Purchase Order No.
label | c3872f8d-536b-5c19-a82d-8a35e4744197 |  | note | ---------------------------------
label | 46df0f86-5f7c-508c-b062-b794526e0990 |  | note | METHOD: Visual Inspection
label | b722609d-8305-571b-b3d3-06b6e045193b |  | note | ---------------------------------
label | daebe469-96b1-50e0-a603-239db95b7f45 |  | note | FREQUENCY: Each Lot
label | e30a5e47-bf68-5d59-ae52-6aae23cca778 |  | note | ---------------------------------
label | 503fc436-3ce7-57fc-a5d4-1c2e13c36622 |  | note | CATEGORY: IP
label | d67fdcf2-6170-5fdb-8872-affd95041ca3 |  | note | ---------------------------------
label | 7c27e44b-c16e-5563-92d5-66f0222aa4b1 |  | note | RESPONSIBILITY: SE
label | ef0aa3f1-61cb-503d-ae67-03e866d59025 |  | note | ---------------------------------
label | 8cf4a1be-1988-5874-8193-661c552774cc |  | note | VERIFYING DOCUMENTS:
label | 74fd841c-dd64-54ba-b810-24188d33b8c7 |  | note | • Material Delivery Docket
label | c323c157-8d44-52ed-9928-d4cd15766eb6 |  | note | • Purchase Order
label | 5163ea7e-abfd-500e-955d-aff06cee0d4d |  | note | ---------------------------------
date | 4e8776ab-e1cf-5116-87a6-346f4e2e6e36 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Materials - Manufacture's Certificate of Compliance
label | 8be78c5e-1f83-512c-b66c-3e80b63419fc |  | note | REFERENCE:
label | 142180f1-b30e-5a59-a162-6a1a88cab887 |  | note | • IFC Drawings
label | c12f060c-e2fd-5649-afcc-b0b79f950497 |  | note | • Section 620
label | cb8ad936-1a02-50ff-a1d1-bcd7db2d5188 |  | note | • Section 701
label | 1d684104-4992-5794-b8c1-3459fab12d4e |  | note | • Section 705
label | 27358ced-61e7-5e93-8c42-0f2f07a4a990 |  | note | ---------------------------------
label | 409c2c7c-a228-5b05-a42a-39e7cbfd9c50 |  | note | ACCEPTANCE CRITERIA:
label | 5b8f8a8b-48ad-5cff-93dc-ae0628bb2c0c |  | note | (1) Ensure Manufacturer’s certificates of compliance are received for precast RCP during delivery on site and min required strength is achieved prior to transporting.
label | e3a7be83-fc13-5eba-9344-a5903a61cc84 |  | note | ---------------------------------
label | 2b9ef523-10b8-5958-9841-0ef79d407c9c |  | note | METHOD: Visual Inspection
label | 92bfcef3-ce66-59f2-b945-08917f3f1b26 |  | note | ---------------------------------
label | 4ec5241a-87ca-58ba-8353-1493262c5e85 |  | note | FREQUENCY: Each Lot
label | dd536b47-d716-5f0c-a6de-87cdcf079a41 |  | note | ---------------------------------
label | c1afbc9d-668a-5d31-a055-791c969dc70a |  | note | CATEGORY: IP
label | 6b2f63a1-41d5-5e5c-af92-7893daaaa1a1 |  | note | ---------------------------------
label | d01c84e1-6e63-5748-ba62-b573715d2054 |  | note | RESPONSIBILITY: SE
label | 46d181a5-fba8-5abd-822f-bec41d47ed52 |  | note | ---------------------------------
label | dbc6a4e0-2688-51d8-9591-351cf9fd8366 |  | note | VERIFYING DOCUMENTS:
label | b4a335c0-7256-5ab6-afbd-dea24cf63dd2 |  | note | • Material Delivery Docket
label | 92808e45-ad04-5857-b09d-4e0736045f4c |  | note | • Compliance Certificate
label | 016dd470-72e9-5c87-b17e-298a7d55716a |  | note | ---------------------------------
date | d8d11084-342e-58a0-a041-66781c1842c1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Materials - Delivery to site & Storage
label | c273c18d-9d18-5a08-ae99-2bb21dc955de |  | note | REFERENCE:
label | 5f8aee41-7970-55fd-a421-9b1db3336337 |  | note | • IFC Drawings
label | 9ece20c0-c8f8-55ee-8263-648d3da2e947 |  | note | • Section 620
label | 279812cb-d761-585f-ace9-5703d8a81e26 |  | note | • Section 701
label | f62075c6-da2e-5421-b9c5-9dc1c4ccd367 |  | note | • Section 705
label | 3e176a84-b1c4-52f5-a4b2-fbf8e649d340 |  | note | ---------------------------------
label | 47e6d5a1-cc7c-5b82-b84c-e4952d840d9c |  | note | ACCEPTANCE CRITERIA:
label | c2e51c54-506b-557c-898e-8f1e13cd3375 |  | note | (1) Identification of product is legible (Stamp, Label, Etc) and should be marked on every precast element.
label | f6a5263f-4ff9-5149-a107-eda9b040687e |  | note | (2) Precast elements are unloaded and stored properly on site as per manufacturer's instructions.
label | c3ec9166-6bd4-5fc6-9049-38e20bf4b00d |  | note | ---------------------------------
label | 2b8cf4a5-5dfc-5d69-85d6-fadf78b7e987 |  | note | METHOD: Visual Inspection
label | c4da6700-7522-5aa5-930d-2ef07287d37d |  | note | ---------------------------------
label | a4ffb242-686a-56d3-8463-65ba0e2b8e42 |  | note | FREQUENCY: Each Lot
label | fc8ebf0b-29c2-535b-a58c-36c07ab499dc |  | note | ---------------------------------
label | a2f3ddc4-af3d-5ce6-a61d-86ecd3152613 |  | note | CATEGORY: IP
label | 4f73a631-a0dd-5159-b12e-059426b152c8 |  | note | ---------------------------------
label | 65188cce-f55c-5483-ac42-2577350a7015 |  | note | RESPONSIBILITY: SE
label | e32c9e73-fdf9-5e1b-a394-5d51cc585406 |  | note | ---------------------------------
label | 6757f880-f5b6-51b0-b688-0940bad0ba65 |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
label | 00750c6f-bed8-56bd-a67d-fb5864bcbb3b |  | note | ---------------------------------
date | ec97f1a7-cfa4-5dff-8c9e-fd14476f086b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Materials - Others
label | a5a52d65-933f-58a9-a0a2-5594403bf23d |  | note | REFERENCE:
label | 2da5bd4d-dc1f-5546-86c2-ae827027ec0c |  | note | • IFC Drawings
label | 231ec838-2e6a-5127-a238-be357e3034b6 |  | note | • Section 620
label | e1eda32d-9ef7-53fe-b645-0bca6fda293c |  | note | • Section 701
label | 729aee64-fbfb-51ca-9614-4ba01e4f7217 |  | note | • Section 705
label | a8f7a54f-0f32-5f90-9d32-d14c66a1d713 |  | note | ---------------------------------
label | 1fec4b7c-9e67-5197-8166-cdabea260a0d |  | note | ACCEPTANCE CRITERIA:
text | 60fe8f50-335a-5ab3-a4bc-3efb0c5d9753 |  | textbox | (For Additional Comments)
label | d19c29b2-2d3c-50fa-9133-9518edbccebe |  | note | ---------------------------------
label | 4ffd4269-e5dd-577d-8a52-8f922be7dbc5 |  | note | METHOD: Visual Inspection
label | 981c522a-e5b5-5cee-af7e-c5b906ab684a |  | note | ---------------------------------
label | 50ce190d-cf5f-5145-8b4f-e85c35653a5c |  | note | FREQUENCY: Each Lot
label | 6737c280-9192-5a0d-9ce4-867420b5503e |  | note | ---------------------------------
label | 3d0ae120-cb81-5ca1-b131-7ddde0554d4e |  | note | CATEGORY: IP
label | 7527edea-95c9-5e4b-869a-b4cc2fc033e0 |  | note | ---------------------------------
label | a335d91a-7ea0-5af1-8287-b1e7bbfdeca9 |  | note | RESPONSIBILITY: SE
label | aa0635d2-b4ce-5565-9e18-8b2dc5eb80df |  | note | ---------------------------------
label | a49f0d90-7151-5d75-9c4c-99ac18e20957 |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
label | 1151319a-4aa3-5c59-888c-131653459a07 |  | note | ---------------------------------
date | 779385c1-ffce-5ad0-bd63-f7e231414293 |  | date | Date Completed:
checklist-sectioned |  |  | checklist | ITP-051-RAIL-Camms-OHLE Installation | itp |  |  |  | Yes | ITP-051-RAIL-Camms-OHLE Installation Rev 0 | 719c114a-2d82-408a-a18b-050f89595db2
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | f148c6ff-1371-5f00-896a-01ddd5188889 |  | note | Document Title: ITP-051-RAIL-Camms-OHLE Installation
label | 57a56c1b-be2a-566e-b4fd-1b51e2526b28 |  | note | ITP Description: OHLE Installation
label | 511735c1-f04b-5e87-af97-73850b598a39 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 23e86770-576b-523c-8386-5533a894bf65 |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | 194179b7-caa6-54c1-9e68-924e4d1e26f6 |  | note | Revision Number: 0
label | 2079d6b1-5f4e-5347-b1c1-621a4a92ef84 |  | note | Revision Date: 26/06/2023
label | aea3f43b-51a2-596c-868a-e75295553369 |  | note | ITP created by: Nikhil Siram
label | 73abc8c6-195b-589a-b8bc-e192b47cd1c3 |  | note | ITP approved for use by: Victor Mira
label | 68bfffee-6160-59f8-94d7-664460539645 |  | note | 1.1 Overhead Line Electrification
label | dbbd69fc-51e7-5074-b454-28f5b1e7b977 |  | note | Reference: L1-CHE-STD-011(1) MEST 000002-02(1)
label | 4c1a583b-d586-533d-8e27-c10ba615122b |  | note | 1.2 Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | a658c7ee-7b38-55fa-aaed-9267d1eee959 |  | note | Reference: VRIOGS 001 AS 4100
label | 0fd157e5-fd78-554c-ba76-7da5ca42038a |  | note | 1.3 Electrical Networks Standard Electrical Networks Principles and Performance
label | 53dceb2d-9af7-5b9a-9c9d-05a050e1bb52 |  | note | Reference: L1-CHE-STD-015(1) MEST 000002-06(1
label | a931dbb5-bba7-585c-8076-12a524f8735f |  | note | 1.4 Fabrication of Steelwork
label | 5f466119-f37d-563f-9935-0f4258ae8b08 |  | note | Reference: VicRoads Section 630 January 2023
label | 60560439-0c0d-5013-9033-63abcf699c45 |  | note | 1.5 Electrical Networks Standard Electrical Networks Principles and Performance
label | fc9379e3-9248-554e-b653-590e39b92cee |  | note | Reference: Structural Steel Work - Fabrication and Erection
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Structural Steel Components and Fasteners
label | fbcb4dc7-0d3b-5a28-b086-060719619070 |  | note | REFERENCE: IFC Drawings
label | 689e7c0f-9889-500a-83c2-88331d011e52 |  | note | – – – – – – – – – – – – – – – – –
label | 01914ccf-9b51-50f8-a715-d351e1644e1f |  | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | 134c65e3-a25a-5c6d-bb78-0e9bbb0b58e6 |  | note | • Typically this consists of but not limited to:
label | d8b969d7-82a8-597c-8564-293f07cd0215 |  | note | i. Completed fabrication ITP
label | f1289c81-eefc-56b3-ac9e-e23a17e51ef8 |  | note | ii. Weld Procedure Specifications
label | 9771b0be-7328-5529-bac1-5daad79f3519 |  | note | iii. Weld Procedure Qualifications
label | 743f3d7c-4e8f-524e-9292-098c5f1cae3c |  | note | iv. Welder Qualifications
label | a310748b-4fb6-5a4d-a7b8-b0c039279d39 |  | note | v. Material Certificates
label | 73863369-df07-57a5-8517-75a1ac3e3d4e |  | note | vi. Coating certificate(s)
label | 113a0f26-ac7d-533f-aad6-5b5c58ad4f03 |  | note | vii. Non-destructive Testing (NDT) Reports (if any)
label | bbd7924d-945e-5952-aae0-2b538ca475a7 |  | note | viii. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | b76528ec-91fd-54da-89f6-6a049adbbf47 |  | note | • Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
label | 0ec8d898-212f-5f76-a7f2-d363b015e781 |  | note | • Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
label | 48e02010-9bee-5e9f-9af8-10275f018c49 |  | note | • All bolts nuts and washers are hot-dipped galvanized.
label | 3405b7b7-12b4-532b-8923-e95683be4a47 |  | note | Collate: Structural Steel Quality Assurance Documentation.
label | ef7ddfd8-b951-5ec0-920a-59a75b22c23a |  | note | Attach: Collated QA documents in ConQA
label | d897f512-fce3-57ca-a294-1ad344c6eab8 |  | note | – – – – – – – – – – – – – – – – –
label | 3bdf263d-938a-590e-8f92-663728735757 |  | note | METHOD: Document review
label | ecec0a85-d9c1-5d38-b965-4f17da5e2763 |  | note | – – – – – – – – – – – – – – – – –
label | 965f8ab6-c527-51cc-95a2-e60664c117be |  | note | FREQUENCY: Where applicable/ Each element
label | 9f499bc8-c6dc-5c99-b453-e0532fc93199 |  | note | – – – – – – – – – – – – – – – – –
label | f4c56df5-df3f-57bd-b693-cbfc80e31772 |  | note | CATEGORY: HP
label | 475f96d6-7c7d-5b6f-93c4-9680639578d1 |  | note | – – – – – – – – – – – – – – – – –
label | 0e033c6a-6cb3-5de3-b163-338726567399 |  | note | RESPONSIBILITY: PE
label | b4ab439c-041a-52fb-a261-e04b21918d6d |  | note | – – – – – – – – – – – – – – – – –
label | d0d701c7-1d59-508a-bb61-6ee89be7df36 |  | note | RESPONSIBLE PERSON: MRPA Engineer
label | ddf6ecc5-4fd1-5ebd-ab7d-90b20da17c89 |  | note | – – – – – – – – – – – – – – – – –
label | 75e6a616-cd37-5d84-978f-5202c621b2c1 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | cac6a215-631d-5d30-96ad-697b0b52eb56 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Bolted Connections Using Direct Tension Indicators (DTIs)
label | 73755e4c-b627-5510-80b3-3c9cc3b03efb |  | note | REFERENCE: AS4100 Clause 15.2.5.3 (a), AS5131 Clause 8.5.7 (a)
label | d0a1c30e-73e1-53d8-91e5-462446650c01 |  | note | – – – – – – – – – – – – – – – – –
label | 43035170-8f89-5c68-826c-ec60cf62cb5e |  | note | ACCEPTANCE CRITERIA: Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
label | 7d266c1a-f719-5325-aa94-4e87f1aa031e |  | note | i. technical data sheet or information on the product
label | a3330375-da55-57c7-8bf6-30328c342698 |  | note | – – – – – – – – – – – – – – – – –
label | 13c2ef29-5a29-5b22-9787-ecb42a160e15 |  | note | METHOD: Document Review
label | 7c59498b-4dff-5e33-bb90-bef8632dec4b |  | note | – – – – – – – – – – – – – – – – –
label | 4293e658-709e-58c7-a673-9531ad248baf |  | note | FREQUENCY: Where applicable/ Each element
label | ac36f416-c91a-5ed4-8e87-7ada1a00bbcb |  | note | – – – – – – – – – – – – – – – – –
label | f0d46cbc-7e49-5686-ba71-8070fba1076d |  | note | CATEGORY: HP
label | 191211d7-2799-51c7-9046-9b1ca880f381 |  | note | – – – – – – – – – – – – – – – – –
label | 5c8c52e2-878e-5e32-9aaf-e024803dbdae |  | note | RESPONSIBILITY: PE
label | 868a651e-e316-50b2-a596-e94755e76102 |  | note | – – – – – – – – – – – – – – – – –
label | f478616f-d9db-56a8-b7bc-735c0f49dbe3 |  | note | RESPONSIBLE PERSON: MRPA Engineer
label | ee88d529-a989-5ffb-80fe-c341d198910d |  | note | – – – – – – – – – – – – – – – – –
label | dc5e03f1-7df2-5266-b130-c472564ef1f3 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 2a668106-bca6-59ee-897b-2a6c5cf0dbaf |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Overhead Wiring Small Parts Steel and conductor wires
label | 93af7a57-5207-5377-9d52-122312b61b4f |  | note | REFERENCE: Relevant MTM Standard Drawings
label | ea77361f-98c0-5d14-82af-c2944d722fe2 |  | note | – – – – – – – – – – – – – – – – –
label | f6d22dc4-efd2-5617-aa0e-9a1e7ac15b1b |  | note | ACCEPTANCE CRITERIA: Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
label | 72e6e9e4-85be-5efb-818a-38c6d4929b6c |  | note | • Deliveries are to be inspected to match the purchase order
label | 0897717f-2b88-5624-b16e-37742b20d4a6 |  | note | Attach: Purchase order/Delivery dockets/Certificate of conformity
label | 60faeab6-56f2-5156-9798-a4e9ddf17257 |  | note | – – – – – – – – – – – – – – – – –
label | 53dad715-103d-5150-88c7-57466fcccb37 |  | note | METHOD: Visual Insoection and measurement
label | 17261e2e-e998-5b68-9d4c-5c23617fa7a6 |  | note | – – – – – – – – – – – – – – – – –
label | 26e5388a-9aec-528f-ac7c-0b0ddd1776a2 |  | note | FREQUENCY: Upon delivery
label | 4910e533-23f5-5897-8dce-cd47d8f9019c |  | note | – – – – – – – – – – – – – – – – –
label | 83b8c716-d5e8-5084-9abc-abbf208ca015 |  | note | CATEGORY: IP
label | 1b80cd0b-c51d-5a63-b2e0-89ccaf17c227 |  | note | – – – – – – – – – – – – – – – – –
label | 3dbb3ec0-b355-57e8-8dfc-865d1fdf51ad |  | note | RESPONSIBILITY: PE
label | 2744148a-5fa0-503d-adae-4c7216203bd6 |  | note | – – – – – – – – – – – – – – – – –
label | a4dba2b1-ada8-578b-917d-660b276de25b |  | note | RESPONSIBLE PERSON: MRPA
label | 931081bd-d8dd-54ef-8d5b-8083bc0576d4 |  | note | – – – – – – – – – – – – – – – – –
label | 661f4c24-259e-52d2-be4a-df367e29a8d4 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 00f5c0ac-dae4-53c2-96d1-dedf2c9e9340 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Grout
label | 9efad30c-0bcd-51c0-9967-9b4a43ace209 |  | note | REFERENCE: IFC drawings
label | 5d5beec6-fc92-5ff8-8f95-59137c06751e |  | note | – – – – – – – – – – – – – – – – –
label | 18706576-b524-57df-83d5-60dbd4c9a240 |  | note | ACCEPTANCE CRITERIA: All grout under base plates shall be CONBEXTRA C or equivalent as approved. Approved grout to be Flowable shrinkage compensated with minimum 50 Mpa compressive strength.
text | 07dd74a2-eb4a-5bfc-968b-702061477fc7 |  | textbox | Enter: Teambinder Material Approval number
label | 5839b8ff-97db-5c3d-a923-f32663d6c6e0 |  | note | – – – – – – – – – – – – – – – – –
label | 09faae26-bfd4-53b6-9525-5a8460c5d68b |  | note | METHOD: Document Review
label | 6d1f1d44-2c3a-5767-a09e-cc2f7ed1ad3a |  | note | – – – – – – – – – – – – – – – – –
label | c2233edb-2f69-5584-819d-88230534debe |  | note | FREQUENCY: Where applicable/ Each element
label | 5249284f-ec8b-5301-a18b-f305e0860218 |  | note | – – – – – – – – – – – – – – – – –
label | 54364178-b125-5bd4-afa9-d170b1aba8d5 |  | note | CATEGORY: HP
label | bd3c7478-4264-56b4-8291-1f5961dad0b7 |  | note | – – – – – – – – – – – – – – – – –
label | 7166194d-6ede-50c7-8fdb-579e7724535a |  | note | RESPONSIBILITY: PE
label | 5ba488c3-2df8-55ea-9b87-1cc148de1174 |  | note | – – – – – – – – – – – – – – – – –
label | 4befb3f7-cd23-50fa-aed5-c59834226522 |  | note | RESPONSIBLE PERSON: MRPA
label | 0e8ea198-6550-55c2-9893-ef4e0443bc31 |  | note | – – – – – – – – – – – – – – – – –
label | db6a9834-e1c7-5057-8a33-536277b9fc0a |  | note | VERIFYING DOCUMENTS: This ITP/Material Approval
date | ac51e167-87b0-5578-ba98-c6feffe8c861 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Installation Methodology & Works Method Statement
label | 26bce41e-0b0b-5366-9304-a1b3f7fc2db9 |  | note | REFERENCE: AS5131 Clause 11.2.3
label | 95d032b0-77a1-5163-8eab-50ccb699a010 |  | note | – – – – – – – – – – – – – – – – –
label | a80e3a95-4c89-52f2-be0c-5fe0ff8b5691 |  | note | ACCEPTANCE CRITERIA: Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
label | 4fe0dd0a-cb65-58eb-b618-b47c9ee37518 |  | note | – Transported to site;
label | 4d75f571-3e36-5ee6-b961-19caf5eb4b9e |  | note | – Handled on site;
label | d1cfd0db-5771-53a9-8f19-85093ed5a1ac |  | note | – Installation Procedure (subcontracor ITP's);
label | 4610eb20-1e43-5767-8940-41d1a4e31234 |  | note | Submission of Work Package Plan and MRPA approval and acceptance.
text | 473a9a18-bec2-5da9-a316-fc570c37a774 |  | textbox | Enter: WAP number
label | 28939581-06aa-56ed-a11a-748694479566 |  | note | – – – – – – – – – – – – – – – – –
label | 2f4067f1-15e6-5652-a8b7-51f0ec9d5484 |  | note | METHOD: Document Review
label | 3672f576-7d5b-55e9-a2b8-558b013fb6ed |  | note | – – – – – – – – – – – – – – – – –
label | e304c6b6-7282-5a91-809f-120edab2b961 |  | note | FREQUENCY: Prior to Works Start
label | 22199418-bf33-520c-a1d9-d7e30701a089 |  | note | – – – – – – – – – – – – – – – – –
label | 28e0598f-0ceb-5900-ae01-5f39182129c2 |  | note | CATEGORY: HP
label | e1488ac1-ad6e-5899-82d9-241f5cff888a |  | note | – – – – – – – – – – – – – – – – –
label | e7714f38-0729-57ef-a5d9-25e9e8a64840 |  | note | RESPONSIBILITY: MRPA/CAT5
label | 8822d25e-38eb-52a0-9ad1-4fb00815dd13 |  | note | – – – – – – – – – – – – – – – – –
label | a6db77e2-de64-503a-b21a-304ea3dffa4c |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | f154165b-abce-547b-82e5-6cf734e4853b |  | note | – – – – – – – – – – – – – – – – –
label | 78c248c3-729e-5c46-b28e-e7d57234b854 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | db3cd2fb-1baa-5f08-a773-7e3bba657520 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Approval of IFC drawings
label | 4aa35f90-22ca-5497-8cd4-4a09c8ffbf0e |  | note | REFERENCE: Contractor Design Management procedure.
label | 77203aa5-78b8-54d8-9cdd-77bbec0166cc |  | note | – – – – – – – – – – – – – – – – –
label | 5f2ee7ce-9938-51f5-b090-ab815fa3881a |  | note | ACCEPTANCE CRITERIA: Ensure correct and most recent revision of IFC design drawings are used for construction.
label | 306db17a-ca21-596d-9f80-e4062332d2a9 |  | note | – – – – – – – – – – – – – – – – –
label | 858967b9-7e26-53a9-b0e7-74724cc61304 |  | note | METHOD: Document/Drawings Review
label | a6cca0fc-98bd-5b5d-85db-8499d901b8da |  | note | – – – – – – – – – – – – – – – – –
label | 4b2f8bdf-6abf-59da-8f47-d79e840979aa |  | note | FREQUENCY: Prior to Works and at regular intervals.
label | a436c7b2-a7cc-5295-96b2-90ef1e63f773 |  | note | – – – – – – – – – – – – – – – – –
label | 51247041-412f-5151-9cd4-8fe8e2c9226d |  | note | CATEGORY: HP
label | 1a3a53c1-17a0-5162-b15d-ea9de48729a9 |  | note | – – – – – – – – – – – – – – – – –
label | f2826148-acc8-5824-9b68-7e1bd3cb1943 |  | note | RESPONSIBILITY: MRPA/CAT5
label | 1b8a17fd-bfbf-5453-8879-71b4f46f3bd9 |  | note | – – – – – – – – – – – – – – – – –
label | 293ac7c1-898c-5f37-841e-5c2684329322 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 9ae31d18-60ca-5317-a15c-3b3ba50dea5c |  | note | – – – – – – – – – – – – – – – – –
label | 71288c5e-272c-59f5-9390-2e281351d90f |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | d3fe8bce-b08a-5863-bfab-214a0340b178 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 Cantilever assembled.
label | 1389d1df-6c57-5b61-a96c-a25497729bc5 |  | note | REFERENCE: Cantilever assembled as per IFC design.
label | 27eb4424-b4e2-599c-b9bd-4fd24ec2418a |  | note | – – – – – – – – – – – – – – – – –
label | eb5aa959-dc44-56fe-a915-23c30885ed51 |  | note | ACCEPTANCE CRITERIA: Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | 1a7b6c77-20d0-501c-a71b-40027658cfa8 |  | note | – – – – – – – – – – – – – – – – –
label | ddc5b205-c19e-5039-944e-c564d825ecda |  | note | METHOD: Visual, Document Review
label | eac94b56-bff7-5b72-a433-73531e681880 |  | note | – – – – – – – – – – – – – – – – –
label | 7ae4b055-38b7-5ebd-b424-f28214fc45ad |  | note | FREQUENCY: Each Task prior to works start.
label | af5bbc08-f725-5b1b-b1f9-f4a6dc6c01b8 |  | note | – – – – – – – – – – – – – – – – –
label | 5f8ccff5-8401-5a20-903f-1fdd023644a3 |  | note | CATEGORY: IP
label | dd723a24-b898-5ec0-8e07-22c5c6e14aa3 |  | note | – – – – – – – – – – – – – – – – –
label | abf66213-317b-5701-951f-a848d82245b2 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 802659c6-cbde-5176-86fe-ad7a88346e64 |  | note | – – – – – – – – – – – – – – – – –
label | 153ad09b-90e0-570c-89de-3505271b8aac |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 67121522-1531-5a6e-9ff2-9a73eb2d26ee |  | note | – – – – – – – – – – – – – – – – –
label | eb21b2f0-1ccf-5091-b030-2507b6dea9ab |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | e805d018-bcb7-5c36-a328-5a3b29990fc0 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Mast Installation
label | 405d76c1-3e59-5ca4-b3f5-014f172f4202 |  | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | d76502ce-373d-52df-88da-07015569aba3 |  | note | – – – – – – – – – – – – – – – – –
label | 4b055cc3-11a2-5936-9327-88aae6515321 |  | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
label | d989fb05-dd8a-54d0-9f2b-6f9912f15a6b |  | note | – – – – – – – – – – – – – – – – –
label | 071583ee-58d6-5638-8046-d01d2769293e |  | note | METHOD: Measure, Visual
label | 347b0895-7e36-564a-9793-7c1faa9e4f8f |  | note | – – – – – – – – – – – – – – – – –
label | c32b5552-a311-5929-87a8-f2f7247696d8 |  | note | FREQUENCY: Each OHLE Structure
label | 5905c547-ac5b-58c4-8b0d-1ef257861dae |  | note | – – – – – – – – – – – – – – – – –
label | 99d98c80-a03a-5ace-b116-026607fe2084 |  | note | CATEGORY: IP
label | 50e42cba-f27e-5c06-97b3-17c3b92cc483 |  | note | – – – – – – – – – – – – – – – – –
label | 074dcde2-d08a-54f4-aa3a-55d726af960e |  | note | RESPONSIBILITY: CAT5/MRPA
label | 0bc79dc7-686d-5600-880c-e1ef2b0972c3 |  | note | – – – – – – – – – – – – – – – – –
label | 9b2b0d8a-7e98-579e-8e40-923d388a9054 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | bba3fd11-d728-5850-be46-97a6965dc24b |  | note | – – – – – – – – – – – – – – – – –
label | 777c05f5-dbc7-5c06-86ab-c3d11dc8f6f7 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 9bc542da-dd2f-558c-b61f-ca2c000aaa40 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Cantilever installed.
label | 78cab06d-60f6-5788-8cf3-424a7905b229 |  | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | f5637112-97ec-54c3-bd80-774a393e8ae3 |  | note | – – – – – – – – – – – – – – – – –
label | 705fa245-1412-5a32-af68-a129b39f75d7 |  | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
label | 9ddbfe73-c2f6-5e80-9e57-124af4f1d1f0 |  | note | – – – – – – – – – – – – – – – – –
label | bfe108db-2c56-5d1b-a10b-690c70654dba |  | note | METHOD: Measure, Visual
label | 56cee73b-e20a-5825-948f-1913cfe9293b |  | note | – – – – – – – – – – – – – – – – –
label | 2ec1631d-2493-51cf-aa87-cad2a1b137d3 |  | note | FREQUENCY: Each OHLE Structure
label | a74e4de1-e148-51cc-9b2c-ee062d768ee9 |  | note | – – – – – – – – – – – – – – – – –
label | f72c6957-cd26-50d7-b1e7-2a2e9046d0ed |  | note | CATEGORY: IP
label | 0eeb5c90-90a9-5f95-9847-29e973589cc4 |  | note | – – – – – – – – – – – – – – – – –
label | 032629e2-be66-5b66-bcda-37ffa29711d7 |  | note | RESPONSIBILITY: CAT5/MRPA
label | b698a03d-20bd-5dd4-8b6e-30aa48621839 |  | note | – – – – – – – – – – – – – – – – –
label | 36b4a5bf-a6c0-5a12-972a-b1ed1390f9cd |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 0eeb48cd-b313-51b4-9600-5b14c30f9beb |  | note | – – – – – – – – – – – – – – – – –
label | 6e237519-b156-5220-8607-c1a1e225794c |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 85d1c19c-7692-57aa-8ffc-b8fa09d08340 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Bearing type Joints TB Friction type joints TF
label | eb573cab-4d0d-5baa-a929-6381304a0bb2 |  | note | REFERENCE: IFC Drawings
label | 0c846858-ccee-5b07-b7c8-15c1bc472831 |  | note | – – – – – – – – – – – – – – – – –
label | 08045599-9dd2-5d9f-b647-4b334d8dc912 |  | note | ACCEPTANCE CRITERIA: BOLTS DESIGNATED TB & TF ARE TENSIONED AS PER AS 5131 and Table 8.5.6
label | 7c990232-5045-5f22-b9e9-d37bb60f36ed |  | note | – Bolt mark ups (in case of partial tensionening) should be visible for inspection
label | eed43c0a-d99d-51e8-bb26-5bdc700ad0e0 |  | note | – DTI squirts are to be visible for inspection
label | 594abf7b-c299-5e9e-86fe-06ac95d91509 |  | note | – – – – – – – – – – – – – – – – –
label | 815062d2-d587-5974-9f0d-1f40b15363c7 |  | note | METHOD: Visual
label | bfeae9b2-d572-5884-b543-1dc8b7371f9e |  | note | – – – – – – – – – – – – – – – – –
label | d5c11207-f1f5-57dd-b006-4d25810b05dd |  | note | FREQUENCY: Where applicable/Each element
label | d1e70388-7848-50f0-a0e6-3619ad63d1e5 |  | note | – – – – – – – – – – – – – – – – –
label | 8963735a-b63e-5a11-a41e-f4625010e145 |  | note | CATEGORY: IP
label | 4ff0be49-a62f-5a41-97be-aaa2500568e1 |  | note | – – – – – – – – – – – – – – – – –
label | 0510c9e9-87f4-56f4-830f-06359b9e314a |  | note | RESPONSIBILITY: PE
label | 91c2e4fe-a48f-57cd-a0ad-43d8462d60c6 |  | note | – – – – – – – – – – – – – – – – –
label | 39331307-fa75-584e-9523-0ac628d17d51 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | c11bab12-1484-5728-8be4-bd280a42c4b1 |  | note | – – – – – – – – – – – – – – – – –
label | ba4a3b93-7b83-573a-9111-7dc6ffd0308b |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 55dccc35-2544-5db2-9af1-38688e6cc31f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Install SPS to correct height / position relative to track
label | 58e02560-ac6b-5aa8-a740-d7e50d219c79 |  | note | REFERENCE: Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | 6243ac03-e5cb-5fc6-a25d-75052017aa66 |  | note | – – – – – – – – – – – – – – – – –
label | 9a5880a2-45ed-570d-ae30-9c08b2784042 |  | note | ACCEPTANCE CRITERIA: Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | e77214fc-0440-5b6d-94a9-1186e8ecaf6e |  | note | – – – – – – – – – – – – – – – – –
label | 75add6ef-704b-5e4f-a23f-abdeab4f91d4 |  | note | METHOD: Measure, Visual
label | 9521ff7d-d339-56eb-80ea-d359260bf3b6 |  | note | – – – – – – – – – – – – – – – – –
label | 6da6578c-c0a3-58bf-81bb-0bb584500b9c |  | note | FREQUENCY: Each OHLE Structure
label | c83cad90-5e06-5d89-8477-1dedc504fa7c |  | note | – – – – – – – – – – – – – – – – –
label | 8d63a6aa-1073-58e8-9154-543dad4acf69 |  | note | CATEGORY: IP
label | 8a55561e-ffc0-582e-9734-4cff9eb86375 |  | note | – – – – – – – – – – – – – – – – –
label | fe75da46-7b20-59f3-b9f0-58830ae47b29 |  | note | RESPONSIBILITY: CAT5/MRPA
label | b49e0d6d-4e0f-522c-8478-05f231360ec8 |  | note | – – – – – – – – – – – – – – – – –
label | a79f4fc1-7b97-5c95-9ba5-3fde5c4eb75d |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 9156d195-50f7-58e9-a0a5-aa6f4d48080d |  | note | – – – – – – – – – – – – – – – – –
label | 9900457c-57fd-5ef4-895b-d87c80f1d945 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 9b03d926-cf6e-5b47-9834-33388cab2165 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Cantilever checked once installed.
label | f57ddaa7-72be-5b54-8b44-a26b28a51478 |  | note | REFERENCE: Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet.CAT5/OHLE/CHK002
label | b062b12d-622f-5002-bb42-ed37da7693a9 |  | note | – – – – – – – – – – – – – – – – –
label | 706e6243-3eae-57a9-8d39-bd63f46bb8a4 |  | note | ACCEPTANCE CRITERIA: Supervision checking to ensure that equipment is installed correctly.
label | e7fcea10-91dd-53b1-b6b8-77240993bba6 |  | note | – – – – – – – – – – – – – – – – –
label | 27c97b9d-0bff-5223-bdef-047fba64f514 |  | note | METHOD: Measure, Visual
label | 3198d02a-4f31-5576-9be7-6ca1375b5b74 |  | note | – – – – – – – – – – – – – – – – –
label | b6261b59-8995-5fa9-95fb-d682b684a619 |  | note | FREQUENCY: Each OHLE Structure
label | 773699aa-2da1-5177-b2ed-09b204da4958 |  | note | – – – – – – – – – – – – – – – – –
label | 0239746e-0170-5aa4-a042-35ac132d8353 |  | note | CATEGORY: IP
label | c0cc045c-fa6d-571c-825e-9740846b6c35 |  | note | – – – – – – – – – – – – – – – – –
label | 63a2552e-ced6-54b1-991d-ebfcb7b89178 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 722c6851-f9b3-5a5f-8743-0654e6963549 |  | note | – – – – – – – – – – – – – – – – –
label | 5f988979-cb36-5947-bb00-ae56cbf9a796 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 7182c053-8397-5fe7-963b-2822b344e601 |  | note | – – – – – – – – – – – – – – – – –
label | 5dbc3395-106e-52fe-ba0f-1a8d02757909 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 1f0db19a-8b93-5c71-840d-dcc74883575a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Base Plate Grout
label | f7fa42b5-6fe3-5227-b83c-e8baf2cae45e |  | note | REFERENCE: IFC Drawings
label | bb5ddb38-a839-5a86-80b0-e83305d04bd6 |  | note | – – – – – – – – – – – – – – – – –
label | 120e633b-fa46-586b-afa0-f2e8e220da2b |  | note | ACCEPTANCE CRITERIA: Grout to be mixed as per manufacturer TDS.
label | 4f77e87b-c6f1-54bf-9325-cb4fe105f0af |  | note | • Grout to be poured under base plate as per IFC drawings. Grout over pour is to be 6mm and cover area with Nom 50mm offset around the base plate.
label | b3bde0b4-d973-5815-af9e-55d5301b3a28 |  | note | – – – – – – – – – – – – – – – – –
label | 336abeff-79c7-572b-8165-6c33fdff4d72 |  | note | METHOD: Visual
label | 851dfee7-b4c4-58f2-8d46-cc4bbaa5c512 |  | note | – – – – – – – – – – – – – – – – –
label | fdfaffdd-678e-5e63-a2bd-04bf3e74ec64 |  | note | FREQUENCY: Where applicable/Each element
label | 7ce796a7-4e61-503f-a994-42d9844605e5 |  | note | – – – – – – – – – – – – – – – – –
label | 692a7b97-c5e2-5bd5-8a0f-8f9d78f7fe2d |  | note | CATEGORY: IP
label | a5b61d7e-a612-523e-b9de-e7f04744c590 |  | note | – – – – – – – – – – – – – – – – –
label | 0b2a5793-e89d-5306-a5a3-6e8c93b37278 |  | note | RESPONSIBILITY: PE
label | 605a92bf-f14a-54ec-a34e-fd06c56bd70c |  | note | – – – – – – – – – – – – – – – – –
label | 648eacf9-478d-58a0-9b17-03471a0bdd61 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | f2822ab2-8703-5b79-8545-2ba873fdda6a |  | note | – – – – – – – – – – – – – – – – –
label | 9316538a-ccb8-58bf-b099-d4de0aaa7878 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 02ce2d65-008a-5fda-801f-2909c9a7d19d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Installation of wire supports at the correct height and stagger
label | f113f664-64da-5d7d-a878-13fada443392 |  | note | REFERENCE: Install as per design
label | f5e76fd5-559d-5af4-9550-3d6db871165a |  | note | – – – – – – – – – – – – – – – – –
label | bf9d0c99-8804-54a3-a026-92a4be1643a0 |  | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
label | 26675dd8-d7cd-532b-8cfe-21ad73a05e7b |  | note | – – – – – – – – – – – – – – – – –
label | 80eade78-5c33-5aac-9677-d52c1b7b91fe |  | note | METHOD: Visual
label | ebbc6076-35cd-5071-b6ef-e661f178df3f |  | note | – – – – – – – – – – – – – – – – –
label | 42b8390e-bce7-5ca7-bd7c-968939a83d2f |  | note | FREQUENCY: Each OHLE BWA Structure
label | 95176ab9-567e-55e1-8629-63dfadf7ca23 |  | note | – – – – – – – – – – – – – – – – –
label | 0d3d8e2b-c0c6-5024-a626-82f78e0364f0 |  | note | CATEGORY: IP
label | 0d3c7294-604e-5e78-bef8-606bab95ae38 |  | note | – – – – – – – – – – – – – – – – –
label | 86e30e2d-4a65-5bab-9353-13cd8b4ff333 |  | note | RESPONSIBILITY: CAT5/MRPA
label | cbc6ef85-8b9f-53d1-a7b5-9f52af6d7193 |  | note | – – – – – – – – – – – – – – – – –
label | f0e42900-b547-5316-b560-fc0c5c935292 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | b29de4b5-b532-57f7-93ec-a3604757462f |  | note | – – – – – – – – – – – – – – – – –
label | 9c052b69-cf6b-5b01-ae7e-13de4eb239c8 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 9a56bd0f-7c56-522f-964f-5a32d045838a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Install to correct tension
label | f225a121-cddc-5e67-adc2-e79d56966dc4 |  | note | REFERENCE: Install as per design
label | adb94fb9-40d4-5818-83a3-a8608620a2b2 |  | note | – – – – – – – – – – – – – – – – –
label | 662a84e8-0ffc-5acc-9fb9-e43222381975 |  | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
label | bc755784-79a4-529b-a587-12a200167dc0 |  | note | – – – – – – – – – – – – – – – – –
label | 86722245-2d6a-5459-9b66-c8e4dbd89629 |  | note | METHOD: Visual
label | 0469da7d-5b8f-5766-bb9f-1bd54c34e992 |  | note | – – – – – – – – – – – – – – – – –
label | 4f1a17d5-9d7a-515a-8170-6b685b150025 |  | note | FREQUENCY: Prior termination
label | 4308e12d-69e9-54b2-beca-c730555f494c |  | note | – – – – – – – – – – – – – – – – –
label | 2c234d91-7ed4-5048-bf4e-9b09ba37d6da |  | note | CATEGORY: IP
label | 50daf694-b027-51fe-82fa-4fa8403f0465 |  | note | – – – – – – – – – – – – – – – – –
label | 08a64f94-eb2e-5cfe-ac52-6ab17b72dda1 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 199be1ba-502a-5600-ab35-7d9c0a36de10 |  | note | – – – – – – – – – – – – – – – – –
label | 02665dd5-61f5-52a5-abb9-c5fb5a585da9 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 5c87e806-85fd-52d8-b1e3-9b8c2ed821d8 |  | note | – – – – – – – – – – – – – – – – –
label | d8fee63c-383c-57d3-827c-578dbbbf332c |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | e23f4b19-e5e6-5e71-8ea1-7b37609fe12d |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Defects/Temporary Works
label | 896b7b69-83b6-55a5-a14b-ea72c05f9bf1 |  | note | REFERENCE: IFC wiring layouts, cross sections and design drawings.
label | ad21956f-fc9e-55f4-a581-7901316634b3 |  | note | – – – – – – – – – – – – – – – – –
label | 598781b0-a20b-50e3-9898-60f719decc7d |  | note | ACCEPTANCE CRITERIA: Ensure all Defects/Temporary works are capture and closed out correctly.
label | 1d0f9b8a-9b16-5d99-92ac-c4d1ba93382f |  | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
label | b439b2ff-2ba7-522d-80e7-a62751d86c03 |  | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | 945d32c5-6154-5978-b06a-16610edaf2f7 |  | note | – – – – – – – – – – – – – – – – –
label | aa0ab4ff-df71-5777-bb61-1796050afea5 |  | note | METHOD: Document Review, Visual
label | 11792a19-935e-5a54-990c-debeba665871 |  | note | – – – – – – – – – – – – – – – – –
label | 30e138fd-b52a-5684-a5c4-35b42a4ab606 |  | note | FREQUENCY: Each OHLE Structure
label | a6427bcd-a952-58bc-9ab9-ac1b2871f499 |  | note | – – – – – – – – – – – – – – – – –
label | bd5338ca-3fc0-5491-90f0-b74b4f7bbc3c |  | note | CATEGORY: IP
label | 05badb6e-0de6-5c0b-b72d-6fc056638141 |  | note | – – – – – – – – – – – – – – – – –
label | d18df339-52a7-5f6f-8023-abb99a0511ce |  | note | RESPONSIBILITY: CAT5/MRPA
label | f748293f-f956-5ec9-ba18-aba23cead3e4 |  | note | – – – – – – – – – – – – – – – – –
label | 901f73ef-a722-5a2a-b79e-b81da98847b3 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 0e9d31e6-78a0-58aa-ae69-7034dc658158 |  | note | – – – – – – – – – – – – – – – – –
label | 547e0712-aebf-51c2-aaec-0d8abad4ef93 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 041ba95b-97ff-562a-8763-ee309cc1c601 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Relevant documentation readily available. (As-built Survey)
label | 4fd8a86e-5e05-57d5-becc-42d92991ad9a |  | note | REFERENCE: As built drawings and check sheets to accordance to MTM Design spec.
label | c4465d09-da87-54bf-8b26-bdf87ecd1dbd |  | note | – – – – – – – – – – – – – – – – –
label | 8af26945-d80e-5ad0-a926-a224dc15b9aa |  | note | ACCEPTANCE CRITERIA: Ensure delivery of relevant documentation to client.
label | 4e22902e-110f-5371-948e-83c6463996d9 |  | note | • As built drawings and check sheets. CAT5/OHLE/CHK/002 check sheets.
label | dbd918e7-d25d-58a0-83f4-ab64c1ae3202 |  | note | – – – – – – – – – – – – – – – – –
label | 71f4846f-20c4-5216-b529-58ec763f415b |  | note | METHOD: Document Review, Visual
label | c29bc638-5648-5396-9042-55ef111e8d11 |  | note | – – – – – – – – – – – – – – – – –
label | dcb19017-7fa1-56d4-ae02-d2b32690a7fe |  | note | FREQUENCY: Each OHLE Structure
label | 5851a3ff-100e-5573-9c86-84c5ac235891 |  | note | – – – – – – – – – – – – – – – – –
label | b8e7253b-2643-56ac-8a1a-522fea5d8096 |  | note | CATEGORY: IP
label | 445454ad-99dc-5373-844e-cea5f43c93cb |  | note | – – – – – – – – – – – – – – – – –
label | 3ff08a8e-3bb0-5b0d-a8fd-59a537013644 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 382cfcd1-10b0-5679-b16c-1aa878e7850c |  | note | – – – – – – – – – – – – – – – – –
label | 5cd59216-a59d-5928-9147-6d981ec52a2d |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | b851a33b-eee2-50d8-a985-1e61b213aef9 |  | note | – – – – – – – – – – – – – – – – –
label | bc4cd2c9-fc09-50e4-aa9e-9b075fbab064 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 411640f0-9872-58e7-8cc1-20ca9f86974e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | 68d3e125-9644-57c0-826e-14101f1b77af |  | note | REFERENCE: MTM Quality Management Plan
label | 63d29d17-91bd-5191-8975-58a563a16202 |  | note | – – – – – – – – – – – – – – – – –
label | 506b4b40-36b8-5904-9e12-495ad3e9607e |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 7206e493-44c1-5224-80f8-7b7d12529ff5 |  | note | – – – – – – – – – – – – – – – – –
label | bd1e0970-d2b4-58ed-90b7-9555aa6fc001 |  | note | METHOD: Document Review
label | 89df3e34-f660-5467-8523-fc3b09c27a4e |  | note | – – – – – – – – – – – – – – – – –
label | 05366cd7-4262-5e1c-8cbf-4e5565ac5f07 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 49c9c494-b917-563a-b6c1-317b558504b1 |  | note | – – – – – – – – – – – – – – – – –
label | 15975b89-420b-52d7-9532-e33b6b3e6d86 |  | note | CATEGORY: HP
label | db0b257c-0fea-5161-ad5e-657f50c098df |  | note | – – – – – – – – – – – – – – – – –
label | b3f724c3-efea-523c-b66e-ec53776b1849 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 3e0fb0c1-ddc0-5191-b962-aafe29ab77c9 |  | note | – – – – – – – – – – – – – – – – –
label | 9370e3e3-aa65-5d8b-aee3-8164a77e103c |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | d957aa5c-5fd2-5cfe-8397-9ed8eba542e6 |  | note | – – – – – – – – – – – – – – – – –
label | 41a607af-24d1-5809-aab7-2b72ee5faf88 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | fba7245e-e102-57fc-910c-849207081156 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | e4a8498f-5a32-577a-9f00-98cd5ef9e4ef |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 33c64d2e-eac9-59d8-b7c5-ba7e328cc64b |  | textbox | Name:
text | 70722abd-c6a2-554a-a640-9b5cb2bb81bb |  | textbox | Position:
date | 2ba33d73-94bc-5994-afeb-0cf1936027bc |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-070-CIV-CAMMS-Tactile Installation | itp |  |  |  | Yes | ITP-070-CIV-CAMMS-Tactile Installation Rev 0 | 7a9d969e-4d69-4f9a-8306-5453d0fbc3bb
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | c733fa19-a456-5a9d-8076-a7781f2a11b4 |  | note | Document Title: ITP-070-CIV-CAMMS-Tactile Installation
label | 30fff762-05fd-5d2b-a06f-21043da4b4f5 |  | note | ITP Description: CAMMS-Tactile Installation
label | 6a1efbc2-24ff-52db-a22d-a2e804e3ead5 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 5f1226f8-f440-5390-a41b-5af338a5e76a |  | note | Discipline (e.g. CIV/STR/RAIL): 070-CIV
label | 668f0f4b-5083-5e53-be74-f7bffc70d228 |  | note | Revision Number: 0
label | 700c4aee-7d84-5cd7-8015-e4670b410f57 |  | note | Revision Date: 28/02/2023
label | 7c6ae378-c324-5ee6-a762-cd181dc5232d |  | note | ITP created by: Chloe Mitchell
label | e98d67f1-17f1-58ec-b81a-528ed6211a9f |  | note | ITP approved for use by: Victor Mira
label | 24ff54dc-98a3-5ada-ab44-91a73924381f |  | note | 1.1 Non Dependent
label | 3345842c-4bec-5d1f-b812-97cb1c88e4cb |  | note | Reference: AS1428.4.1
label | e8838594-f812-5148-8e97-06e677095f63 |  | note | 1.2 Non Dependent
label | e7270e4b-52bf-5c88-86cf-21154eb77bdb |  | note | Reference: VicRoads Section 160.A9
label | be64603c-d276-5d3a-b109-562a825fdc7e |  | note | 1.3 Non Dependent
label | aeaa2e4d-d957-5c65-ba6e-ae4f70ab2f14 |  | note | Reference: IFC Drawings
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Material Conformance
label | 31ca4175-e8d8-5306-b2d3-adf62fb7d0df |  | note | REFERENCE: AS1428.4.1 Section 2.2 & 2.3.1
label | a806e2c4-0048-50f4-9726-e3637d809b12 |  | note | – – – – – – – – – – – – – – – – –
label | fdcb751a-f7fa-5b60-a009-1f310f449247 |  | note | ACCEPTANCE CRITERIA: Tactile Indicators must conform with the requirements of AS1428.1.1 Section 2.2 & 2.3.1
label | 515aed46-242f-5886-80aa-37bfd4f72cc6 |  | note | Attach: TeamBinder Material Approval Ref No
label | 1476f51d-9ccf-52d1-8b66-ac26b3af0be8 |  | note | – – – – – – – – – – – – – – – – –
label | 8f5b33cf-f5ce-5544-b5c6-92e1237bd712 |  | note | METHOD: Document Review
label | cddd59e5-121b-516a-b301-cfe2119dccfc |  | note | – – – – – – – – – – – – – – – – –
label | ca49ffff-2692-5f17-96fe-b78c2e2a244a |  | note | FREQUENCY: Prior to works start
label | a224da6a-c163-5437-b566-e7879d04ee5f |  | note | – – – – – – – – – – – – – – – – –
label | 26926e26-bf81-5989-9bb7-76b27541e928 |  | note | CATEGORY: HP
label | 7ef382c0-0d92-5963-b7d3-2c9f37603faf |  | note | – – – – – – – – – – – – – – – – –
label | e557fc58-5817-58b2-aa6c-69386859560b |  | note | RESPONSIBILITY: Nominated Authority
label | d8d5aeaa-2b8e-56a6-9177-a1409ff2058b |  | note | – – – – – – – – – – – – – – – – –
label | 004d19e7-93b4-50ec-9cde-cfc4a9bcda8b |  | note | VERIFYING DOCUMENTS: Conqa HP Release
date | 5c7ee6d7-29fe-5b64-80b7-4cae09b9ce3c |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Documentations
checkpoint-status |  |  | checkpoint | 3.1 Documentation Conformance
label | ed85f434-d8b5-5cd4-8ec1-749743b37ce9 |  | note | REFERENCE: DoT Handover Process
label | 293c6478-cfe7-5361-b00b-8cb7f4b25d07 |  | note | – – – – – – – – – – – – – – – – –
label | 770b5f09-cfc0-5ae4-b292-d8269490da85 |  | note | ACCEPTANCE CRITERIA: Tactile to be yellow in colour, VicRoads approved as per design note RDN 06-05 and DDA Compliant
label | 40b78f98-58f0-5eb2-abc0-58fd14f2670d |  | note | – – – – – – – – – – – – – – – – –
label | 185ed91f-6e17-5249-8eaa-cdab3e947558 |  | note | METHOD: Visual & Document Review
label | 679f1c34-36a2-5052-98ef-cc1ad7e61802 |  | note | – – – – – – – – – – – – – – – – –
label | d771f8ab-46e0-5158-9570-0e5c4c956b92 |  | note | FREQUENCY: Prior to works start
label | 6da6d27b-20f7-5fd7-ab3b-eb580ff526d9 |  | note | – – – – – – – – – – – – – – – – –
label | b40dbad4-9ad2-59e4-b385-8398865441ab |  | note | CATEGORY: HP*
label | 3a9731fb-ad1f-5120-88fc-80c9d020cea6 |  | note | – – – – – – – – – – – – – – – – –
label | 18257276-d617-5ce5-8459-fed020ede1d2 |  | note | RESPONSIBILITY: SE/PE
label | 8dd91f1a-3378-55e1-b718-e25077712322 |  | note | – – – – – – – – – – – – – – – – –
label | b36920cb-a780-5459-943e-b47c3fcda24e |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 0494256c-d021-562b-9366-d9ab046a1b7f |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out
label | ac28cfc8-f27c-5d5f-977f-7a810faa8444 |  | note | REFERENCE: IFC Drawings
label | dd8594fd-44d6-5fdb-ab8b-71a36a42a2db |  | note | – – – – – – – – – – – – – – – – –
label | d255d78f-3a6e-5061-9167-53c2422a1fe9 |  | note | ACCEPTANCE CRITERIA: The required positions of the tactiles are clearly set out by a surveyor as per IFC Drawings.
label | 55d33c67-e760-593b-922a-1941e73a37ef |  | note | – – – – – – – – – – – – – – – – –
label | ce67b873-1f09-5b30-aa4b-9fde95d7472f |  | note | METHOD: Measure, Visual
label | ff9ea518-4fce-536a-88e9-d92e7adfe2bb |  | note | – – – – – – – – – – – – – – – – –
label | 08489770-e22d-5ad4-bc66-85a6a6ebd6a9 |  | note | FREQUENCY: Per Lot
label | b69780de-0cf2-5ccc-aa8f-3bb95d300a94 |  | note | – – – – – – – – – – – – – – – – –
label | 7df3bbc3-02db-5c60-ba11-a5aa52a351bf |  | note | CATEGORY: IP
label | 23c20f8d-49d0-5d15-a2e0-cd944fa3602d |  | note | – – – – – – – – – – – – – – – – –
label | 877dcecd-551b-5574-ab59-75d7f618329b |  | note | RESPONSIBILITY: Surveyor, SE/PE/Site Supervisor
label | f4934133-7b6e-5ca9-8e13-0c1bd62c9420 |  | note | – – – – – – – – – – – – – – – – –
label | 1c799afa-8179-54c4-97c9-488e738ff489 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 297ddbce-3591-5be8-ad15-82c2ff33ff12 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Installation
label | d65d55d4-9753-5ac5-a94d-145475ba9879 |  | note | REFERENCE: AS1428.4.1 Section 2.3.3
label | c16f6f03-845a-5a0b-a399-87065246b4f6 |  | note | – – – – – – – – – – – – – – – – –
label | 05d78311-04b4-59dd-ad62-d91180b3d192 |  | note | ACCEPTANCE CRITERIA: Notify Nominated Authority prior to installation.
label | 7981d086-d9bf-5ecc-8cf6-729e8f48c54e |  | note | Warning indicators shall be installed as follows:
label | 62e36c22-a21f-50d2-b625-6ba514fc463d |  | note | (a) For the full width of the path of travel
label | 8d17e894-234d-5e9e-8f3c-8138a1cc57f9 |  | note | (b) Perpendicular to the direction of travel when approaching the hazard.
label | fac700da-4460-50c1-8224-a8416c600a78 |  | note | (c) Set back 300 +/-10 mm from the edge of the hazard except at railway platforms and wharves.
label | 000f3355-ee65-5c5c-a17e-2d944b79030f |  | note | (d) Where integrated warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below, over a minimum depth of 600 mm to 800 mm from the direction of approach.
label | cc3bc31d-3f2d-5af3-92c0-61c9730c0a0b |  | note | (e) Where discrete warning TGSIs are used over a depth of 300 mm to 400 mm, the arrangement shall be as shown in Figure 2.1 below with a minimum of 6 discrete truncated cones in the direction of travel.
label | 0b571e7b-e5db-5946-a7f4-6945d5bd94aa |  | note | (f) Where discrete warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below with a minimum of 12 discrete truncated cones in the direction of travel.
label | 0459d0ad-57b9-5cb4-8eef-eb13734c77e3 |  | note | Where required on a path of travel, warning indicators shall be located at both the top and bottom of stairways, ramps, escalators and moving walks
label | 1689c9b0-08d5-5e5a-9ab2-ef9ab21079b5 |  | note | – – – – – – – – – – – – – – – – –
label | 1066065c-6f7f-5dc0-bf08-b377dd7e8669 |  | note | METHOD: Visual/Site Inspection & Document Review
label | 7fe86f47-2b37-50e4-9589-8832f50bd97c |  | note | – – – – – – – – – – – – – – – – –
label | 0b817436-3dab-5d52-946d-6e3483c0ea69 |  | note | FREQUENCY: Per Lot
label | 5d0ce74a-ec2d-5935-81a8-2ac1903d0940 |  | note | – – – – – – – – – – – – – – – – –
label | e21e226a-9cb7-5f8f-8cf0-e59873ccdcbc |  | note | CATEGORY: HP
label | d1af7cda-48ae-5a31-99b5-e32ea2f3d45c |  | note | – – – – – – – – – – – – – – – – –
label | 44fa8693-c18f-530b-b393-dac8b88320a4 |  | note | RESPONSIBILITY: Nominated Authority
label | 9a58e888-8e2c-570d-b644-8f1a2d5c02ae |  | note | – – – – – – – – – – – – – – – – –
label | 35a40eb6-4ca8-5ffc-93ea-b89ed475c3ad |  | note | VERIFYING DOCUMENTS: Conqa HP Release
date | 0c82ccd9-d44e-5c07-b754-f0b6219f207f |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 Laboratory and On-site measurement of luminance contrast
label | 74803b6d-ae64-556e-92eb-73ca7b90e712 |  | note | REFERENCE: AS1428.4.1 Appendix E
label | 21dd4eea-d46e-57ad-9020-2d55065a883c |  | note | – – – – – – – – – – – – – – – – –
label | d0683c8b-5ac5-5579-bff3-055bfa29605e |  | note | ACCEPTANCE CRITERIA: Submit Test report to AS1428.4.1 E5.4: The following shall be reported:
label | e8acad4b-6f00-5986-83fc-711d74667344 |  | note | (a) Full description of the surfaces tested with product details where known.
label | d0c1eae6-6e3c-557b-af40-f5269f4f2523 |  | note | (b) The instrument being a luminance meter with a 1° measurement area corrected to approximate the CIE 1931 Standard Observer.
label | a144f2db-cc69-5bea-932b-1aaa09d25a1b |  | note | (c) The location of the sample, if on-site.
label | 3a720677-6b73-5c03-9350-d81a4d514517 |  | note | (d) The location of the sample of the measurements on the TGSI.
label | 378c63f8-39b4-58fb-9794-b595370a652e |  | note | (e) A description of the light source(s) illuminating the sample, including type, [e.g. fluorescent tube, incandescent, high pressure sodium discharge, metal halide, and colour (in general terms)].
label | 32a2e0c1-707b-5584-b331-380193496ee9 |  | note | (f) The mean luminous reflectance of the adjacent surrounds to the tactile indicator under the conditions set out in Paragraph E5.3
label | 4e7792b5-b586-5109-a143-5e6ca9026eea |  | note | (g) The mean luminous reflectance of the tactile indicator under the conditions set out in Paragraph E5.3
label | c929bfcf-ba51-5fa4-9a20-2fba56cdcd5d |  | note | (h) The luminance contrast with the surrounds on both sides of the tactile indicator.
label | c7e7956a-77f5-5559-aaf8-ab0c6b48f9c6 |  | note | (i) A reference to this test method, i.e., AS/NZS 1428.4, Paragraph E5, Appendix E.
label | 77ead668-0b33-569d-a744-914b8a8cf705 |  | note | Attach: Laboratory Test report
label | 63ddb05d-a246-5a1c-baf0-67dfa5c597e0 |  | note | – – – – – – – – – – – – – – – – –
label | 0826b067-3e60-5539-9c08-58916e0908e5 |  | note | METHOD: Visual/Site Inspection & Document Review
label | 11ea0dcb-c12c-5056-9b7f-f57389f0a84e |  | note | – – – – – – – – – – – – – – – – –
label | 6fa3be6b-b5a3-5a97-8475-42c505ec5b44 |  | note | FREQUENCY: Per Lot
label | 95ab54e7-39b4-503a-a1e0-eb64665ba35e |  | note | – – – – – – – – – – – – – – – – –
label | fa72a1dc-58c6-5e4d-bcc9-31ae52ba0977 |  | note | CATEGORY: IP
label | deb66514-be04-5283-b941-80a296f7e23a |  | note | – – – – – – – – – – – – – – – – –
label | be55a3cf-175c-5e66-9a27-41d31a9ab1b3 |  | note | RESPONSIBILITY: SE/PE
label | 8fc28aa4-ab7f-5b04-bf59-da2dc3befa43 |  | note | – – – – – – – – – – – – – – – – –
label | 03e19cc0-0605-56f1-9a3b-fdeee23cbb9b |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 91c078dd-4934-5a42-a2bb-a44f7746e198 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Distance between tactiles and sleeve
label | b6c8face-d300-5ca6-974c-c805f4606fb9 |  | note | REFERENCE: DoT Handover Process
label | 1303a600-fb61-51fc-b0a0-92e4cd0d5090 |  | note | – – – – – – – – – – – – – – – – –
label | c14c1057-4654-5ddd-8566-fc7831c8ab79 |  | note | ACCEPTANCE CRITERIA: Distance between tactile and sleeve to be a minimum of 300mm as per note 1 of the Handover Process
label | 05f437c2-3f59-5348-ac61-7f524549643c |  | note | – – – – – – – – – – – – – – – – –
label | 70358d96-6d39-5604-aef4-822c8c3ce42e |  | note | METHOD: Visual Inspection, Measure
label | 1727c2f2-fd34-5dc1-8fa3-b84756c41874 |  | note | – – – – – – – – – – – – – – – – –
label | 7654eaa1-ae8b-5b69-b431-10503d8557fb |  | note | FREQUENCY: Per Lot
label | df58170d-65c3-5c89-b7dc-8c7e79dc1e9d |  | note | – – – – – – – – – – – – – – – – –
label | 785078de-c119-5a8e-8d14-3513882a068d |  | note | CATEGORY: HP*
label | bf1a2327-9c71-5525-999a-007233f8b826 |  | note | – – – – – – – – – – – – – – – – –
label | f7b21c71-66c2-5f38-ad7d-589ed75712f7 |  | note | RESPONSIBILITY: SE/PE
label | 8e8ef00e-142c-5b1c-97f7-691579f6f42d |  | note | – – – – – – – – – – – – – – – – –
label | cad16a30-2a74-5e53-8c59-6187212f2068 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 16f9dae5-6a5e-5219-8be2-be0667389ea8 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey
label | 2652efb9-d5ca-58e9-9530-935039400f96 |  | note | REFERENCE: IFC Drawings VR 160.A9
label | 26f6c50c-adb5-5e6d-840a-672b19156a88 |  | note | – – – – – – – – – – – – – – – – –
label | 7ec7a44e-9662-5ccc-8265-4b7dd19055af |  | note | ACCEPTANCE CRITERIA: As-constructed’ information shall be progressively documented during the work under the Contract and shall be provided to the Superintendent in a neat and clean format Attach: Survey As-built / Survey Report
label | df5c2b57-7b23-5187-9256-3737be334436 |  | note | Attach: Survey Conformance Data/Report
label | d004d271-1097-59f7-bec5-6df400a24c4a |  | note | – – – – – – – – – – – – – – – – –
label | 80c3916e-a60a-50e2-a97f-789daca7eec4 |  | note | METHOD: Document Review
label | f6872ff7-94a2-52fc-8014-d8ad7c567585 |  | note | – – – – – – – – – – – – – – – – –
label | b720a6eb-8cb5-5d35-a50b-e6df6c81d9f7 |  | note | FREQUENCY: Per Lot
label | a0d0d52e-f9d4-5eab-bb60-84cc66efdc49 |  | note | – – – – – – – – – – – – – – – – –
label | 66e02289-c749-5c1b-8dc6-bc43314bbeea |  | note | CATEGORY: IP
label | be62df75-73f1-560a-83d6-e489b005df78 |  | note | – – – – – – – – – – – – – – – – –
label | 6bf2d1e7-c820-59fa-a160-e05075905c13 |  | note | RESPONSIBILITY: Nominated Authority
label | 5d9aed7b-86ea-513d-89a2-8b8e655a7e37 |  | note | – – – – – – – – – – – – – – – – –
label | 741bbbda-11b9-5da7-a559-4ca03b0f7cb5 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | a2a7c165-e340-59cd-a410-cc75b76404a7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | d0ce2057-970a-5baf-a43b-da3f683890fb |  | note | REFERENCE: MRPA Quality Management Plan
label | b82db9ce-09fa-5300-a569-aecb873ed5d3 |  | note | – – – – – – – – – – – – – – – – –
label | c3fd4ff1-4ffe-5285-8d7c-cb2d51d01824 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 007bd982-65dc-5753-bd99-87e672429493 |  | note | – – – – – – – – – – – – – – – – –
label | 84cfc80d-9347-5e5b-a556-ada3234dffd1 |  | note | METHOD: Document Review
label | 16806881-4875-5316-b672-968fb6ccc108 |  | note | – – – – – – – – – – – – – – – – –
label | b8d14232-54a9-5242-919b-50fbc10a783d |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | d3468596-5beb-5431-9f05-3e885674c2ad |  | note | – – – – – – – – – – – – – – – – –
label | 4a3872c4-d40c-56d2-bd36-dc2ffc2532b9 |  | note | CATEGORY: HP*
label | 30aeff51-71cd-57cb-a059-cbb74398f09e |  | note | – – – – – – – – – – – – – – – – –
label | 352c64a8-3a83-500c-ae59-70b9a7758acc |  | note | RESPONSIBILITY: SE/PE/SPE
label | 569b358a-10c7-526d-9b12-3807db662548 |  | note | – – – – – – – – – – – – – – – – –
label | b40576be-0d74-5e0f-ba9e-a75d46cd5c23 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | b1f0d192-6645-55b3-8092-e6ca80b15ff6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | b9485eea-8980-5ed6-b02c-4f2d69c6214d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | caee7128-bce5-591c-b7db-0f8ead648628 |  | textbox | Name:
text | 449ddbd0-c2ea-5e81-96db-158818d431f7 |  | textbox | Position:
date | 09265911-c550-5034-be99-3cd0a4bc5330 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-115-STR-CAMMS-Bridge Waterproofing Rev 0 | itp |  |  |  | Yes | ITP-115-STR-CAMMS-Bridge Waterproofing Rev 0 | 7ecd2c93-ba52-4407-9c94-282c224589b0
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Reference Documentation
label | 48c7ea56-89a3-5d6a-90d8-1c2cb7c267ce |  | note | Document Title: ITP-115-STR-CAMMS-Bridge waterproofing
label | bf0139b3-1dde-59fa-8bfe-36ccf277c08f |  | note | ITP Description: CAMMS-Bridge waterproofing
label | cca2741e-3ec6-5bab-8ef5-ac19a4209bdf |  | note | Discipline (e.g. CIV/STR/RAIL): 115-STR
label | 3007c6a3-af46-5a26-acec-e5b37d90bf67 |  | note | Revision Number: 0
label | e260ea69-4627-56e8-ac95-00ab34220b46 |  | note | Revision Date: 15/12/23
label | 5d981741-e1ce-5699-978e-703c44903060 |  | note | ITP created by: Victor Mira
label | c75f776a-a41e-5514-9bcd-f7a35fc2a180 |  | note | ITP approved for use by: Victor Mira
label | b45e2264-63d2-5bef-b617-37e83d5abc74 |  | note | 1.1 VicRoads Section 660 January 2018
label | 7b08064c-bc8c-51d3-bbee-7c22a704414c |  | note | 1.2 VicRoads Section 691 November 2018
label | 67a70455-454b-57b9-b8ab-4b54fa85df1d |  | note | 1.3 AC-AR Installation Guide
checkpoint-group |  |  | section | 2 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Waterproofing Membrane System Materials
label | e6443af9-6b1d-5386-b0ad-d90a2c86ef18 |  | note | REFERENCE - VR 691.05 VR 691.07
label | 8c1c4459-d36f-5cc5-b1b2-b486380f4ce0 |  | note | – – – – – – – – – – – – – – – – –
label | f4f85e0e-7452-5932-9c18-f224e915cfe0 |  | note | ACCEPTANCE CRITERIA - Certificate from the manufacturer in the form of a guarantee confirming that the waterproofing system and materials comply with the requirements of this section, including a guaranteed in-service performance of not less than ten (10) years from the date of installation. Submit Certificate of Conformity, including all relevant test results shown in Table 691.071 and Table 691.072, verifying conformity of the supplied materials for every lot/batch delivered, to be submitted for review to the Nominated Authority.
label | bb183dc5-c69f-5bc5-af8d-ad87a7413a37 |  | note | Enter: Teambinder Approval Number
label | 7a357e6a-9574-57ec-9b16-28292d2a5e8d |  | note | METHOD - Document Review
label | 32fcd06e-56e8-53a2-b152-9ebeb097d904 |  | note | – – – – – – – – – – – – – – – – –
label | 1c538609-fdf7-58b6-b100-2a6cf7991b28 |  | note | FREQUENCY - Prior installation
label | ffe93e42-25ca-5d7f-b2b2-f2c12c465b68 |  | note | – – – – – – – – – – – – – – – – –
label | c7ae826d-6e6a-513d-826e-4c1564fec24b |  | note | CATEGORY - HP
label | e96dc6b1-01f7-59c9-ad62-3094554cc57a |  | note | – – – – – – – – – – – – – – – – –
label | 7d045d9c-5287-5396-9348-da1af847c468 |  | note | RESPONSIBILITY - Nominated Authority
label | b37a9761-5b10-5f75-8ee2-4078b19c8305 |  | note | – – – – – – – – – – – – – – – – –
label | a1023d2d-59e0-5387-b315-659acfd201d9 |  | note | VERIFYING DOCUMENTS - This ITP
label | 43907e7f-cb4b-53e4-b8b0-dc991652d209 |  | note | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preliminaries-Procedures
checkpoint-status |  |  | checkpoint | 3.1 - Waterproofing System installation Procedures
label | ee1409e9-1537-5c02-8384-b94c4681a5f1 |  | note | REFERENCE - l VR 691.04
label | 5e5c1df8-797f-52e3-a827-1707b1c726a8 |  | note | – – – – – – – – – – – – – – – – –
label | 5cc8f2db-9c5f-5927-8552-0969425a97d9 |  | note | ACCEPTANCE CRITERIA - Details of proposed procedures and surface preparation in accordance with clause 691.08 to be submitted for review to the Nominated Authority. Waterproofing works shall not take place until the Contractor's proposed materials and procedures and surface preparation in accordance with clause 691.08 have been reviewed and accepted by the Superintendent.
label | 8526395a-3f3d-5394-823c-fda593eb18c1 |  | note | Enter: Teambinder Approval Number
label | 1c156aa2-2ac3-5cf7-b80a-2785ce723cc3 |  | note | METHOD - Document Review
label | edc5eaff-d3df-5da6-a677-439a98a4263f |  | note | – – – – – – – – – – – – – – – – –
label | c95149fb-8908-5192-b170-8c4252c0baf9 |  | note | FREQUENCY - Prior installation
label | f83b1b7d-7953-59b2-a09c-1211b9e3f9e5 |  | note | – – – – – – – – – – – – – – – – –
label | 70eec19e-ebe8-5256-ae30-86d49856ead6 |  | note | CATEGORY - HP
label | 1956e430-0b7d-5db9-8aa4-5f0c0447a8ff |  | note | – – – – – – – – – – – – – – – – –
label | 32feec4f-3345-5b14-81dc-3d713c606d83 |  | note | RESPONSIBILITY - Nominated Authority
label | 878f2618-5b0f-51fb-93af-7787483258f7 |  | note | – – – – – – – – – – – – – – – – –
label | b2479654-dff3-5be6-9b8d-b4d81b25995e |  | note | VERIFYING DOCUMENTS - This ITP
label | b922cfbe-5b89-592d-9ef9-f90e25dbf5f4 |  | note | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Material Handling and storage
label | 4d6bdd96-6e9a-55b3-b965-207919e13d0b |  | note | REFERENCE - VR 691.15
label | 5e362f8a-0497-5cf2-b6d3-d97da9ddd796 |  | note | – – – – – – – – – – – – – – – – –
label | 34826651-1ae5-5545-af7a-ec428b24359c |  | note | ACCEPTANCE CRITERIA - Where applicable the joint material including joint sealant shall match the drawings or be an equivalent product All material shall be brought to site in the original preformed rolls or unopened cans clearly labelled with the manufacturer’s name, product type, reference and batch numbers. The Contractor shall provide a certificate from the manufacturer for each batch of waterproofing membrane and primer material confirming:
label | c62fa845-830b-5852-b786-f902d5b006ab |  | note | (a) manufacturer’s name and address
label | dd6fc847-3dc3-5a2c-8b42-871e9ab1debf |  | note | (b) product reference
label | 9bb66074-fe1f-5d36-b271-6eaff473ec73 |  | note | (c) batch number of identification
label | 26447a34-3627-5476-be00-7955d53aacb3 |  | note | (d) quantity manufactured in the batch
label | 794b9a74-a3bb-50b7-a8d7-8430b2b323aa |  | note | (e) date of manufacture.
label | 0110890f-c389-568d-be87-1c824b185484 |  | note | All waterproofing membrane materials to be used on the works shall be free from contamination, gelling, drying out, heavy skin formation and severe segregation of ingredients. Attach Delivery dockets/Proof of purchase
label | 3a7e8e49-00ab-553a-9869-68491bed1a24 |  | note | METHOD - Document Review/ Inspection
label | 9faaad8c-4ca4-5a75-8614-24995ae1f4ca |  | note | – – – – – – – – – – – – – – – – –
label | 3fa476ba-ece6-5446-b32e-23dde58b05d4 |  | note | FREQUENCY - When applicable
label | 3ab64058-0cf1-5a04-9912-daddbb6d32db |  | note | – – – – – – – – – – – – – – – – –
label | b3ea5fb9-2693-54d9-965c-3e5111d2ba4a |  | note | CATEGORY - IP
label | 9b1a2089-fce1-5db0-a222-5acdc1241d47 |  | note | – – – – – – – – – – – – – – – – –
label | 53a7f1e8-b8bf-5e56-99ab-8b7f35384bb8 |  | note | RESPONSIBILITY - PE/SPE
label | d7326306-de2a-5f83-b5e2-3c72326e6814 |  | note | – – – – – – – – – – – – – – – – –
label | 5ed48405-969d-55b0-adfe-db6b0dc2c8a7 |  | note | VERIFYING DOCUMENTS - This ITP
label | c030fbe2-55c6-576c-bcc2-9368d10a7cf2 |  | note | Date Completed:
checkpoint-group |  |  | section | 5 - Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Surface Preparation
label | f195744f-ca35-5ffb-9ab1-df0a310e6339 |  | note | REFERENCE - 691.08 (a) and(b)
label | 3e21b186-c60d-5edc-bde3-65ada5595d00 |  | note | – – – – – – – – – – – – – – – – –
label | ed7adcb3-36f5-5fec-b7f4-a801255c9508 |  | note | ACCEPTANCE CRITERIA - The surface preparation shall be in accordance with the manufacturer’s recommendations for the waterproofing membrane system to be applied and as specified in this section. Concrete surfaces to which the waterproof membranes are applied shall be dry, clean, sound and free of dust or loose particles.
label | cb2d892c-f80f-5bee-bb87-69a07f3991b4 |  | note | METHOD - Visual Inspection
label | fd16e92d-21a7-5cd3-ac68-3e10569c7518 |  | note | – – – – – – – – – – – – – – – – –
label | 640acd5d-919c-501f-af31-13fae8fec7bc |  | note | FREQUENCY - Before Primer Being applied
label | 98cbf079-e6a2-5ac1-aa99-28d37971828d |  | note | – – – – – – – – – – – – – – – – –
label | 204ad66d-07bb-502e-90ab-11a5f00bedc4 |  | note | CATEGORY - IP
label | c69ccd26-7ce2-53a1-a369-0b4724c94ee1 |  | note | – – – – – – – – – – – – – – – – –
label | f0af1d6f-984c-5383-aba9-e1ccd9ce2570 |  | note | RESPONSIBILITY - SE/PE
label | e63dd89e-af0a-5024-bbe3-abae27cbe406 |  | note | – – – – – – – – – – – – – – – – –
label | 08c6664b-eb9e-59cc-ab55-35f3f2dc294d |  | note | VERIFYING DOCUMENTS - This ITP
label | 6af443ba-7721-50c1-b40e-c74ca168fbac |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Primer application
label | 7a048959-8987-59db-807f-a6542eddb2a3 |  | note | REFERENCE - 691.08 (c )
label | 408e83e5-c450-5a2a-8534-3ea06533cf45 |  | note | – – – – – – – – – – – – – – – – –
label | 08919e41-825d-5521-b083-6fb0ee84b67c |  | note | ACCEPTANCE CRITERIA - Primers shall be applied by brush, mop, broom or spray in accordance with the manufacturer's recommendations.
label | 2bf97d75-d0e8-5e50-9f44-f94f275e45fb |  | note | METHOD - Visual Inspection
label | cc1507be-ff7d-50db-a60a-8e725ee1b803 |  | note | – – – – – – – – – – – – – – – – –
label | 63235347-3c84-572d-8280-7fdb84683b0e |  | note | FREQUENCY - When applicable
label | 8834ddbb-b489-5230-a272-f6c56fc5e98a |  | note | – – – – – – – – – – – – – – – – –
label | a4e2e054-828a-5b2c-9fd0-36e7a80dcdbd |  | note | CATEGORY - IP
label | b8a81c6e-cb9d-52ad-8728-14391e86d687 |  | note | – – – – – – – – – – – – – – – – –
label | f22040e5-9ba0-5c9a-badf-9de6e6fc5520 |  | note | RESPONSIBILITY - SE/PE
label | 6a51dfc6-f190-59ea-8cda-dcebfd2d05be |  | note | – – – – – – – – – – – – – – – – –
label | 1f3b9291-b13d-5d8e-aeb6-ca0a57051486 |  | note | VERIFYING DOCUMENTS - This ITP
label | f8542b01-5514-5947-acc0-8a5849d38f70 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Environmental Conditions
label | 43ca527c-c742-57a6-ae36-52313ad6606b |  | note | REFERENCE - 691.14
label | 4eeb9282-15fd-59e0-80b6-4bed5e66070f |  | note | – – – – – – – – – – – – – – – – –
label | 77d321c2-83d4-512d-8ec4-8968e5221e88 |  | note | ACCEPTANCE CRITERIA - Waterproofing systems shall not be applied under any of the following conditions:
label | f21df389-39ec-54ef-90ed-c2591ada9f7d |  | note | (a)windy conditions where over spray and/or spatter may be generated
label | 7fdbe1cc-a62a-5d50-91bc-a159e7bcb6bd |  | note | (b)when wind-borne debris is likely to contaminate the uncured surface of the freshly applied membrane
label | 27fd0b91-8811-52be-bdc8-29bf2a081e2f |  | note | (c)when the ambient temperature exceeds 35°C or is below 10°C unless otherwise expressed in writing by the manufacturer
label | 8a38c3e0-01c5-57eb-b1df-99c220d92d1f |  | note | (d)when the relative humidity exceed 85% or where it may be expected to exceed 85% during the subsequent 12 hour curing period
label | 4f9d10cd-fd25-5b10-bfdf-5a2b02061b5e |  | note | (e)when rain spatter contaminating the surface and adversely affecting the adhesion to the substrate
label | 1763346a-5fb0-5c77-9ce0-84dadd57d45f |  | note | (f)when the substrate surface is wet or damp,
label | fe148a8a-c970-548a-a046-2957f548e61b |  | note | (g)the surface temperature of the substrate exceeds 40°C.
label | 8dccc056-09e1-515b-820d-15a98383c8d5 |  | note | METHOD - Visual Inspection Measure
label | 05061861-4b48-5e66-aff2-e5c9f4efaf20 |  | note | – – – – – – – – – – – – – – – – –
label | 2c97c706-b554-58ec-95d2-f01100469b36 |  | note | FREQUENCY - Prior installation
label | 629e8c59-0581-5a77-9536-6b898b8959fe |  | note | – – – – – – – – – – – – – – – – –
label | 7477b041-2e56-522b-8bc4-eeef520f22c1 |  | note | CATEGORY - IP
label | fd98d2de-b515-5c8d-aac7-8dfc3417a37d |  | note | – – – – – – – – – – – – – – – – –
label | 3e6a5089-00c0-5ac7-a26f-399f516cc081 |  | note | RESPONSIBILITY - SE/PE
label | 01623849-2033-540b-b6cc-a26002d64c43 |  | note | – – – – – – – – – – – – – – – – –
label | 0bd5c467-d50c-50e2-8e3d-b22dd99172bf |  | note | VERIFYING DOCUMENTS - This ITP
label | 2fdc72ec-8bd8-5ace-a05a-a7ab5e9f54f1 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Waterproofing membrane application
label | 8efdfba2-9e50-5a90-bb4d-53fb17c78c36 |  | note | REFERENCE - 691.09 (a)
label | c2eab467-67ea-53cd-8457-5b86af18b273 |  | note | – – – – – – – – – – – – – – – – –
label | e7954399-a525-539c-9fdf-0f9f01f1337e |  | note | ACCEPTANCE CRITERIA - All concrete surfaces to receive a waterproofing membrane shall be dry at the time of application. The waterproofing membrane system shall be applied within 24 hours unless otherwise expressed in writing by the manufacturer after the preparation of the concrete surface. The prepared surface shall be protected against contamination and rain or expected rain if the waterproofing is not undertaken within 24 hours.
label | f3dc652c-13d6-5cb1-800a-8dab47942100 |  | note | METHOD - Visual Inspection
label | e1b920cd-6097-5483-9e27-415e0c298139 |  | note | – – – – – – – – – – – – – – – – –
label | d72af173-da47-5774-a86f-71263b771603 |  | note | FREQUENCY - Prior installation
label | 46b1f223-0477-50dc-bacd-7a400f35232d |  | note | – – – – – – – – – – – – – – – – –
label | 78b6e667-a941-58f3-9ad7-ad1a18223a5a |  | note | CATEGORY - IP
label | 943678ba-814f-5b00-9e07-2d6a2d01607b |  | note | – – – – – – – – – – – – – – – – –
label | 803b88e2-196a-50e1-9cb0-87b8584d3f02 |  | note | RESPONSIBILITY - SE/PE
label | 5b0d4144-1c08-5d30-98d9-a4b1dcf4e9b2 |  | note | – – – – – – – – – – – – – – – – –
label | 4df19a08-c265-548d-ad0f-189c00667985 |  | note | VERIFYING DOCUMENTS - This ITP
label | 0c34ec48-4094-5f80-85a8-a64f6abe0c34 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Waterproofing membrane application
label | fcdfc4e7-6d5a-5d35-9c27-997b5055d3ef |  | note | REFERENCE - 691.09 (c )
label | 810ed977-ba61-54e6-938b-40570274e0fd |  | note | – – – – – – – – – – – – – – – – –
label | 51a9081d-1987-5e52-bcae-e4e37197385e |  | note | ACCEPTANCE CRITERIA - Placement of preformed sheets shall commence at the lowest section and proceed to higher sections, so that water does not flow into any joints during service. The Contractor shall ensure compliance with the manufacturer's recommendations for heating method, duration of heating and temperature of oxidised bitumen adhesives.
label | e2ca7d9b-93a8-5fdb-ba7b-379b12de46b9 |  | note | METHOD - Visual Inspection
label | 2a6063c0-a903-5d20-9535-7ed306d766aa |  | note | – – – – – – – – – – – – – – – – –
label | c88be4a1-9961-567a-9ff4-36faf5ff6bf6 |  | note | FREQUENCY - When applicable
label | 84610b04-60c6-510f-bfd7-c48ddf6a1115 |  | note | – – – – – – – – – – – – – – – – –
label | bd6f6de4-b908-5c87-bef4-941d25771d61 |  | note | CATEGORY - IP
label | 5525fe08-5d1b-5ea9-9fd6-35b766c3fa26 |  | note | – – – – – – – – – – – – – – – – –
label | b43a825f-df61-5bdf-bf5d-a0b50af91936 |  | note | RESPONSIBILITY - SE/PE
label | 4ea1c404-a368-541c-82e8-d495fdef584e |  | note | – – – – – – – – – – – – – – – – –
label | 887ada97-8867-5c69-a126-acf99b5fdc3c |  | note | VERIFYING DOCUMENTS - This ITP
label | 8d7043ac-a2cd-5f4c-a0e2-06c2df8222a0 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Waterproofing membrane application
label | d9d29d4f-9516-53a9-abdd-48d000722eac |  | note | REFERENCE - 691.09 (c )
label | 56291d00-fb92-5e8a-89c7-bebba007063c |  | note | – – – – – – – – – – – – – – – – –
label | 39d585ca-7bfb-566a-8702-43ffab4acdde |  | note | ACCEPTANCE CRITERIA - Self-adhesive membranes shall be rolled out and manual pressure applied immediately to ensure satisfactory adherence to the concrete deck.
label | 348852cd-f166-507c-a424-0db54bc5f4d5 |  | note | METHOD - Visual Inspection
label | b2733d5f-5dd2-50c2-8c24-b303445a2b54 |  | note | – – – – – – – – – – – – – – – – –
label | c20a5c37-4bea-5a72-b3be-a1ee69b3181c |  | note | FREQUENCY - When applicable
label | 7cecfc28-db91-5a30-9a8d-3023354469e1 |  | note | – – – – – – – – – – – – – – – – –
label | abe088c1-00fe-5ffc-8c65-3dd645d3474d |  | note | CATEGORY - IP
label | 68b6e2d0-dc7e-5fca-b971-407bded5b925 |  | note | – – – – – – – – – – – – – – – – –
label | a5cb2c59-9ddb-5288-bbc5-e7c6a610583b |  | note | RESPONSIBILITY - SE/PE
label | da073856-d554-5490-a93c-b55a5d07f254 |  | note | – – – – – – – – – – – – – – – – –
label | b1bbdfcb-cb70-5220-aef0-9bd4dfd8a2cd |  | note | VERIFYING DOCUMENTS - This ITP
label | 88af5f95-e040-54fd-9401-9e63f95e35f5 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Waterproofing membrane coverage
label | e5461363-a138-57ba-907a-8427b9cfda3c |  | note | REFERENCE - 691.09 (d)
label | 328bcaba-1ac7-55fa-bde8-70614cecee4f |  | note | – – – – – – – – – – – – – – – – –
label | 24204e89-e599-5038-bd9b-b4ccf1635a2a |  | note | ACCEPTANCE CRITERIA - Coverage of the waterproofing membrane must be continuous over the entire deck area, including service bays, between parapets, medians and kerbs. The layout of the waterproofing membrane shall be detailed such that water seepage beneath the membrane is prevented,
label | d45ea03f-b813-576a-8fd1-87fde1cfbcf1 |  | note | METHOD - Visual Inspection
label | eca5c1cd-f336-52c4-9211-233e211221f3 |  | note | – – – – – – – – – – – – – – – – –
label | d42527b1-f03a-5a82-97d7-149eb671ea99 |  | note | FREQUENCY - When applicable
label | 4439f640-c68e-5d06-b677-c347950c8a6f |  | note | – – – – – – – – – – – – – – – – –
label | cb33c131-f62a-5ae4-86c2-d62156ca0501 |  | note | CATEGORY - IP
label | 10bb935d-5dc4-5b1a-93c9-ceb10b2df247 |  | note | – – – – – – – – – – – – – – – – –
label | b93d44e8-b814-5290-9ee3-3956d8dbf704 |  | note | RESPONSIBILITY - SE/PE
label | b92174e4-6091-574d-9cae-4e4390f5c6a0 |  | note | – – – – – – – – – – – – – – – – –
label | befd4d9f-c14d-5cf8-bd7d-aac1def7a23a |  | note | VERIFYING DOCUMENTS - This ITP
label | 6d5a1a5b-4029-576c-bf86-4c112b8abe7f |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Waterproofing membrane coverage
label | 758412ea-8c10-5e38-be1a-c9a9345409dd |  | note | REFERENCE - 691.09 (d )
label | 5af724b8-4c5b-509a-8f04-bb6cc15c32a4 |  | note | – – – – – – – – – – – – – – – – –
label | a15a00cd-9349-5daa-9646-78e74b4f145f |  | note | ACCEPTANCE CRITERIA - At the junction with vertical concrete surfaces, the membrane shall continue up the vertical concrete surface, terminating at a level 10 mm below the top level of the proposed asphalt surface.
label | 5d47ff47-e8e5-5f9f-b67d-184df4a2dee3 |  | note | METHOD - Visual Inspection
label | 54d9c385-749b-5297-a75f-3c224cfc75cc |  | note | – – – – – – – – – – – – – – – – –
label | dcfc03c5-6e5c-5926-a30d-9cdb3eedcdb2 |  | note | FREQUENCY - When applicable
label | 6d0e38b1-e50c-5f5e-860f-638b45a55375 |  | note | – – – – – – – – – – – – – – – – –
label | ca8608e2-e51b-59b1-8f55-e25ebd9c3f31 |  | note | CATEGORY - IP
label | 89e45bbb-aa4c-5739-ac32-4490dfd9dd33 |  | note | – – – – – – – – – – – – – – – – –
label | 75aa2b00-f4ef-5d5c-aca8-3a8291ea84e1 |  | note | RESPONSIBILITY - SE/PE
label | bc24fa3c-fde2-590b-a6d2-db01c6447cba |  | note | – – – – – – – – – – – – – – – – –
label | 49a1fdb1-2751-5f96-b15d-65d200f7f044 |  | note | VERIFYING DOCUMENTS - This ITP
label | 0772e8e6-2bb5-5ed5-ba00-986a3b9e4f7a |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Waterproofing membrane coverage
label | 6f456984-b6ef-573e-be6f-f003fce30bb5 |  | note | REFERENCE - 691.09 (d )
label | 331610b2-7945-5483-800d-889cf44a3b36 |  | note | – – – – – – – – – – – – – – – – –
label | c8f3b857-2d9c-560c-8258-3732f3b12166 |  | note | ACCEPTANCE CRITERIA - The waterproofing membrane shall be applied with minimum side and end overlaps of 100 mm and 150 mm respectively.
label | f69da80c-6fd1-5592-98e3-ee182f238a46 |  | note | METHOD - Visual Inspection
label | 2a57c87d-106b-532a-b3de-ab0df69107e4 |  | note | – – – – – – – – – – – – – – – – –
label | f5650bab-ade6-572b-95c7-42476ee017a2 |  | note | FREQUENCY - When applicable
label | 107520f8-7ee7-5cd8-bea5-ce4400ee21fd |  | note | – – – – – – – – – – – – – – – – –
label | d400d518-3277-598b-b184-460aa7a17f96 |  | note | CATEGORY - IP
label | 16689f73-f602-5ad8-9335-363b189ac012 |  | note | – – – – – – – – – – – – – – – – –
label | 8a638e9b-b79c-5185-ab74-18fca019a582 |  | note | RESPONSIBILITY - SE/PE
label | 559ea325-9c70-5ddb-8788-77d22e470ae6 |  | note | – – – – – – – – – – – – – – – – –
label | 9dfc6bcd-c0f0-5d88-9e8b-3404f7fa1249 |  | note | VERIFYING DOCUMENTS - This ITP
label | 509b1b8d-1beb-5e45-8759-57ba3c7bb2f1 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 - Tack Coat
label | 4cb26a72-3ee9-533a-b9fe-bd7f35789986 |  | note | REFERENCE - 691.05 (f)
label | 511aa82d-1764-56d5-943f-228075439451 |  | note | – – – – – – – – – – – – – – – – –
label | 8292d6a1-189a-5ca9-b97b-339d7163f1ab |  | note | ACCEPTANCE CRITERIA - Tack coat shall be applied as required, in accordance with the manufacturer’s recommendations to provide adequate adhesion of asphalt to the waterproofing membrane over its service life. The tack coat shall be applied uniformly to the waterproofing membrane
label | 23e1c5ae-23a8-50a4-a7a1-99dd31e8ad00 |  | note | METHOD - Visual Inspection
label | 9d2f239a-c7fc-59a3-9382-01bc3779174e |  | note | – – – – – – – – – – – – – – – – –
label | 1c72c6ea-01f5-5a69-bb23-20a5c168ca5c |  | note | FREQUENCY - When applicable
label | 3b412336-3c4c-52e2-97f2-29b9f316021c |  | note | – – – – – – – – – – – – – – – – –
label | 9faad36d-e103-5bd6-a1c5-ea7764927707 |  | note | CATEGORY - IP
label | 9a965849-b8bf-564d-bbb6-f97eba0476bb |  | note | – – – – – – – – – – – – – – – – –
label | 248fd980-12d0-5344-ad5b-5ff0c435f391 |  | note | RESPONSIBILITY - SE/PE
label | 338ae3e8-dc19-5b67-8da6-9d420f699565 |  | note | – – – – – – – – – – – – – – – – –
label | 5f6b3431-0e93-5ec8-93c3-cbb6e0b25110 |  | note | VERIFYING DOCUMENTS - This ITP
label | 8bd69f07-0a09-5d2e-8ba9-e85fb97cace8 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Drying and curing
label | 746a5a04-8a78-55b8-b53e-dbec58db46e9 |  | note | REFERENCE - 691.13
label | 2145ae7d-6076-515e-a90a-6fa90210b869 |  | note | – – – – – – – – – – – – – – – – –
label | 6b9a2d93-98c0-5a8c-a3e6-5465bc3e133e |  | note | ACCEPTANCE CRITERIA - The Contractor shall adhere to the manufacturer’s instructions regarding drying and curing requirements, and overcoating time intervals, for the prevailing weather conditions.
label | 67f443d7-0333-587d-9588-5e61e216ebea |  | note | METHOD - Inspection
label | 7f1ab5f4-c2c4-5fb4-9c0c-d443f3aaff56 |  | note | – – – – – – – – – – – – – – – – –
label | 01bd4ddb-521a-55e8-a362-ae9b2469772d |  | note | FREQUENCY - When applicable
label | 546f0126-f97b-58e0-9940-219c5619c4a4 |  | note | – – – – – – – – – – – – – – – – –
label | a7ed359e-1fc9-5cdd-97c6-108d2245cd57 |  | note | CATEGORY - IP
label | 6289ca30-5201-5b2e-89ce-4491770b7bc6 |  | note | – – – – – – – – – – – – – – – – –
label | d9cb70cd-c706-5a93-8063-6816be9d245d |  | note | RESPONSIBILITY - SE/PE
label | 385e14ec-b920-51c0-8480-77c19f7f67f2 |  | note | – – – – – – – – – – – – – – – – –
label | e803ae87-b440-5ae5-8ed9-726b76e11d8f |  | note | VERIFYING DOCUMENTS - This ITP
label | 19d0841a-4af4-5c9b-a2b5-d21145d5e50e |  | note | Date Completed:
checkpoint-group |  |  | section | 6 - Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.2 - Subcontractor Product warranties obtained
label | 5f6d4d2c-bf1b-54ce-97b1-9b95ef9abadc |  | note | REFERENCE - 691.05
label | 9c5cfd5a-2469-59e0-8635-884e1a1cc3fd |  | note | – – – – – – – – – – – – – – – – –
label | 63464d89-78f9-5b52-9cf1-7e9565d2ee26 |  | note | ACCEPTANCE CRITERIA - Product warranties obtained and are compliant with 691.05
label | 2c3f4038-a28f-5811-9c15-92051eee9cd8 |  | note | METHOD - Inspection Document Review
label | f492aa48-794c-599e-94d4-57e8dc7d6cd9 |  | note | – – – – – – – – – – – – – – – – –
label | 43df31c2-7a82-5ea0-825b-ec8b5d21fd0e |  | note | FREQUENCY - Once per Lot
label | da9676b0-ae0a-5bf9-8199-2b38411e14ca |  | note | – – – – – – – – – – – – – – – – –
label | b523f155-a71b-5cf6-81ff-6f47dbbf86bf |  | note | CATEGORY - WP
label | 4915ff4a-17ff-5b60-9964-c3a4cd9af458 |  | note | – – – – – – – – – – – – – – – – –
label | a3d13c52-0793-5ec0-8dea-7e89f9b4fa29 |  | note | RESPONSIBILITY - SE/PE
label | 03ed346e-0d76-5902-8081-dc36c58f4b16 |  | note | – – – – – – – – – – – – – – – – –
label | 1b95e6ba-227c-5397-9862-035dca6cf978 |  | note | VERIFYING DOCUMENTS - Copies of product warranties
label | 87f57319-3989-5b79-a9e8-3abafe5667b1 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 4910e81a-5dea-5bff-97c3-ec03381d8e8a |  | note | REFERENCE - MRPA Quality Management Plan
label | 08978740-52e2-5913-91dc-5046f1b2750b |  | note | – – – – – – – – – – – – – – – – –
label | 4f236242-5c36-5283-b576-794940c39e87 |  | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 7164b3db-fc19-5d22-9c52-e54dc12fe09f |  | note | METHOD - Document Review
label | b9506bf4-24d9-5b94-9b5c-571708aae4a9 |  | note | – – – – – – – – – – – – – – – – –
label | 5ffddfea-d8dd-5521-bacc-7b634f672143 |  | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
label | 2e590f39-f5ae-59c6-a654-7a0f86598406 |  | note | – – – – – – – – – – – – – – – – –
label | d2d2e556-9aaf-5a36-8d03-d5dd4b87fb32 |  | note | CATEGORY - HP*
label | b7fc7882-0d43-5131-bccb-4121b760172a |  | note | – – – – – – – – – – – – – – – – –
label | a3102b2e-7b7f-5350-bdec-52416741c773 |  | note | RESPONSIBILITY - SE/PE/SPE
label | b4226b13-2508-5a75-b370-d10153a009ee |  | note | – – – – – – – – – – – – – – – – –
label | 7e8ea7c3-5054-58b3-a83e-8ac997f149e7 |  | note | VERIFYING DOCUMENTS - This ITP
label | b396923b-b87c-5308-9c79-41b458f70e21 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | ae63d049-2120-5cc9-87e3-a8a8a8cdfe56 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 0ce98d29-6219-563a-80ea-6048f3603a91 |  | textbox | Name:
text | 95c643f8-d5c6-5583-9326-19649ce6fdf4 |  | textbox | Position:
date | 9abcc4b6-9b63-5890-accb-b060db6215cd |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-RAIL-CAMMS-MTM-Stormwater Drainage Rev 0 | itp |  |  |  | Yes | ITP-RAIL-CAMMS-MTM-Stormwater Drainage Rev 0 | 858657f8-8819-4b23-8bb8-ae41a661d944
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | ee0f1665-f439-5778-8996-b6b588da05c3 |  | note | Document Title: ITP-RAIL-CAMMS-MTM-Stormwater Drainage
label | ca9d17f2-29ba-56a6-a100-99b7c3187e72 |  | note | ITP Description: Stormwater Drainage
label | c5036338-012b-5962-8959-6240580c8e7c |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | c12a1f08-325d-5c32-acf2-8dc238f4ab10 |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | 48cf106b-6259-51fe-8fec-09db1dc83b3a |  | note | Revision Number: 0
label | 43da4b3d-8fbc-5482-b586-7fdb3f1f0b43 |  | note | Revision Date: 12/08/2022
label | 125a0c32-8fd8-56e0-b84e-de1a002abd97 |  | note | ITP created by: Justin Kreinberg
label | e7f9fa0f-e51e-5b46-a0a1-6b9a6c6236aa |  | note | ITP approved for use by: Victor Mira
label | f873287d-6fc9-5473-9110-18a97e28102b |  | note | 1.1 - Non Dependent
label | 57c32a93-f63f-5b4d-a0cc-15b9afb69fb6 |  | note | Reference Documents: VicRoads Section 701 (May 2020)
label | 181c8fbc-13f1-5609-9e3b-0db7f720adde |  | note | 1.2 -
label | f0a42740-6b31-5210-aebe-63d601c37320 |  | note | Reference Documents: VicRoads Section 705 (June 2021)
label | 617ebc07-b510-5c91-8547-37f7078a7d94 |  | note | 1.3 -
label | f075b407-a6ec-589d-b9f1-9f66f76e49f6 |  | note | Reference Documents: MTM Track Drainage L1-CHE-STD-030 (July 2018)
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Drainage Pit - Supply
label | d35fb691-3fff-53db-bea9-7884543395ba |  | note | REFERENCE: Section 705.07
label | 0d0b8b81-2930-578b-b868-619f2eba9ee2 |  | note | ---------------------------------
label | 176605a4-5f4b-5859-9a35-d8e6e0ed4581 |  | note | ACCEPTANCE CRITERIA:
label | 93903a24-2529-53a1-bd19-468e350abb02 |  | note | Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with 705.07.
text | a1e4191c-14c8-5dce-aea0-2fbad92fe53a |  | textbox | Enter: Teambinder Material Approval number
label | 82f90c8e-c567-5de1-ba48-4262e22fa9df |  | note | ---------------------------------
label | eb02dd27-63d7-5270-a7b6-f5ee8f7b19ce |  | note | METHOD: Document Review
label | 2467cf1c-b48f-5939-9b2f-b2a6394163a6 |  | note | ---------------------------------
label | 4e22e45d-48b0-5f66-acc2-818538980ba3 |  | note | FREQUENCY: Each lot
label | 8f21f7a0-2955-5c26-b397-a13c1b32fd73 |  | note | ---------------------------------
label | 95b4b310-4a1f-5600-ba35-a3c69b7ab9cc |  | note | CATEGORY: HP
label | 53d0674a-f8e0-5f54-a473-cbaaf411c3dd |  | note | ---------------------------------
label | 45241d70-f4c6-513a-944c-4f344a98db8a |  | note | RESPONSIBILITY: SE
label | 83d6435d-017d-5d4a-b7d9-2d4a96b60086 |  | note | ---------------------------------
label | 117db91e-b88f-5232-8a54-6c7ec96ad22b |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 61929c14-d409-58f7-9a6b-737fc273c74f |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Drainage Pit - Step Irons
label | 249617d1-8ef7-5e60-9cb8-786b6e630206 |  | note | REFERENCE: Section 705.04
label | 50de1a42-c0a7-544a-988b-47e155dd8a5c |  | note | ---------------------------------
label | 58f05bb9-1346-598c-b5f0-a9a271765eca |  | note | ACCEPTANCE CRITERIA:
label | fb82c56e-b483-54f9-95b1-aa0c3c207379 |  | note | Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
text | ee380b23-2ffd-56ff-b927-3f5a5ceb6b5e |  | textbox | Enter: Teambinder Material Approval number
label | 6f39f51a-2563-5c52-8e0b-80b6c3fdf3cf |  | note | ---------------------------------
label | 4cf0af88-3aec-52c1-b44a-dabb111e76aa |  | note | METHOD: Document Review
label | b6b5dbc6-ad1c-572b-9ea8-601dedd3c4ff |  | note | ---------------------------------
label | 15e8221b-1426-552b-8499-1aa47a1a10cc |  | note | FREQUENCY: Each lot
label | fd0f4f98-4cb3-53ac-9e46-6dfdeec68874 |  | note | ---------------------------------
label | f5e6a3f1-c94b-5f3e-a29e-7395861221c2 |  | note | CATEGORY: HP
label | 1750a881-a46c-5f65-a02f-381ab14f87dc |  | note | ---------------------------------
label | 236066b6-fe84-5df8-9a9a-77f69e3afeb7 |  | note | RESPONSIBILITY: SE
label | 4aa57b68-c1c0-5bef-9f86-05416b63f0a0 |  | note | ---------------------------------
label | ad922f16-3afb-51f0-9abd-10cf7c77830c |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | aceccb1a-01ce-576b-89c4-934f5b503190 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Drainage RCP Pipes - Supply
label | 02b426b2-6280-5138-9d31-1d974aa874b2 |  | note | REFERENCE: Section 701.05
label | 6ae553c2-ca7d-510e-b4ef-086d45bae2f6 |  | note | ---------------------------------
label | f1562463-519f-5771-a3b9-65cb871d0347 |  | note | ACCEPTANCE CRITERIA:
label | 92522e6a-6e3d-5093-908b-743a712a1467 |  | note | Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with 701.05.
text | a39ffbe1-ed9d-5949-814b-5da898b8f444 |  | textbox | Enter: Teambinder Material Approval number
label | df99abc4-b95d-5c54-906c-92750fdd3741 |  | note | ---------------------------------
label | 6207baf8-56e7-58e4-8184-cf14f9f86f08 |  | note | METHOD: Document Review
label | 2165d4de-eb5e-504f-83f9-ba1c14d7025b |  | note | ---------------------------------
label | 7e4aecaf-0a5c-54d6-b596-2c88a5dcacb6 |  | note | FREQUENCY: Each lot
label | 75aace53-45e7-527a-8583-a84a87ce555a |  | note | ---------------------------------
label | 990262ed-a1a5-55b4-b27a-63b5abdb9756 |  | note | CATEGORY: HP
label | 8b365e65-5dc1-541f-982f-5b9d4a4913d5 |  | note | ---------------------------------
label | ccaedc50-6ca6-53c2-9f35-a3b9a5a6cd5f |  | note | RESPONSIBILITY: SE
label | 1c412879-2448-52f8-baeb-1773e5bf0897 |  | note | ---------------------------------
label | 6c6d4f30-73be-574d-a8ca-59d8c2ac4a9f |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | ee1235ea-b652-558c-8f48-0b46ef5a2a1b |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Drainage Flexible Pipes - Supply
label | 4b42108b-bf31-592b-8e17-97652c40353c |  | note | REFERENCE: Section 701.07
label | 4da5202c-e8ec-5532-bf70-65815c18aeac |  | note | ---------------------------------
label | fe25e9ab-1d57-5212-bad0-2f29a8538d68 |  | note | ACCEPTANCE CRITERIA:
label | f6a4e174-3ea4-53fa-8135-eab9b55f0220 |  | note | Flexible pipes shall be supplied in accordance with 701.07
text | 27aea3b7-46f8-527e-bcd3-f6c068614576 |  | textbox | Enter: Teambinder Material Approval number
label | 7569500f-bb36-507c-b721-b8f65c4cc06a |  | note | ---------------------------------
label | 38d7e840-2db4-542b-a60f-5ac5e9515f38 |  | note | METHOD: Document Review
label | 4661889e-d64c-5a1c-aa94-618eb16db1f1 |  | note | ---------------------------------
label | ea901287-1084-50a0-90a8-c8d234a1e1de |  | note | FREQUENCY: Each lot
label | a3b64976-3d0a-5777-8550-0dc9fd722961 |  | note | ---------------------------------
label | b898c484-87e5-5b6b-a547-2c638f7bf07c |  | note | CATEGORY: HP
label | 85f80947-c023-5afd-8ae8-d8df5e9cbc4b |  | note | ---------------------------------
label | 68fa8178-43a0-5486-91a8-27106d4d7277 |  | note | RESPONSIBILITY: SE
label | 7493a83d-224c-5e31-a842-6993245af300 |  | note | ---------------------------------
label | c3b6b87e-c570-5c8d-9a4a-861adf35a5dd |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | d9743002-2d19-5f48-b8f9-673ad851342f |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Drainage Slotted Pipes - Supply
label | 33f95161-186c-5789-945f-6a336aa441cd |  | note | REFERENCE: Section 701.07
label | a3d00c9c-932a-5ecf-89cf-cc6de5e9d23f |  | note | ---------------------------------
label | cbe915e1-e354-5f93-9600-51573dc520af |  | note | ACCEPTANCE CRITERIA:
label | 6ac404e0-569a-5b26-9eff-af9938e8ba1c |  | note | Subsurface drainage shall be supplied in accordance with 702.04
text | 68f97cd9-cf0f-5f2e-90dd-9e22805cf0df |  | textbox | Enter: Teambinder Material Approval number
label | 1e40e83a-21c3-5125-932a-80e84b28a7c6 |  | note | ---------------------------------
label | 7aab155d-dcf6-590c-89e1-05ff82809c62 |  | note | METHOD: Document Review
label | e5bbb8ee-9fb1-55ae-8a2f-f16bb71dbddc |  | note | ---------------------------------
label | 2215b88b-a7b2-5ff4-987c-04e43d33ae87 |  | note | FREQUENCY: Each lot
label | c31a3c15-1553-51f0-ac9a-9c9a433a48d0 |  | note | ---------------------------------
label | 35808bbf-8f0d-5fcc-96b7-991a9b51cfa9 |  | note | CATEGORY: HP
label | faa83399-21e5-5737-a783-11282fbf7d17 |  | note | ---------------------------------
label | f86e29e1-66df-5dcb-93ac-16dd13751864 |  | note | RESPONSIBILITY: SE
label | c88050b2-66f1-5bde-8be6-763aa2ecb0b4 |  | note | ---------------------------------
label | 4d812e67-d6e2-571d-b67e-d80ff80df937 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | b7b02ae6-ac82-5c96-83dc-9c8c2b7cdbd6 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 Drainage Bedding Material - Supply
label | ace21155-794b-5bf1-893e-a81c478fe97b |  | note | REFERENCE: Section 701.09
label | a2527941-f1e5-5843-bfa3-3ab3baab3108 |  | note | ---------------------------------
label | d6275d7a-a541-5cc7-b70b-b21401af8d20 |  | note | ACCEPTANCE CRITERIA:
label | 2fbe0a1f-37c4-51ff-b0ad-a6be070f56fd |  | note | Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | 8ee0743c-1bc0-55c2-82dc-fb6f444ee84a |  | textbox | Enter: Teambinder Material Approval number
label | 086bc06d-0161-59ee-baaa-21c60b9ada33 |  | note | ---------------------------------
label | 3916bbf4-dcc8-529e-8c57-dba79f5145d0 |  | note | METHOD: Document Review
label | 66613016-5666-5f13-9f1a-d2b8ae07d07a |  | note | ---------------------------------
label | 5b49b9f8-8222-54e8-9f6d-5252fad10de7 |  | note | FREQUENCY: Each lot
label | 25680218-bc2a-5253-956f-4ecaa0300424 |  | note | ---------------------------------
label | b17266fb-2460-5520-abe9-87facb2125d0 |  | note | CATEGORY: HP
label | d51816a2-a478-5edf-985e-e709e8a26bff |  | note | ---------------------------------
label | 0508c454-3218-58b3-9042-e32078a99195 |  | note | RESPONSIBILITY: SE
label | 3aeb1c7c-d631-5d97-8819-d0c6223faff8 |  | note | ---------------------------------
label | 86c7f31c-68a8-5d1f-b194-15e3c47ebda0 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | ff4507ed-bd7e-5e9c-90b6-3585d81b8ff1 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 Drainage Backfill Material - Supply
label | 9bc5fe82-03f3-509a-940e-59dd44fb6f1d |  | note | REFERENCE: Section 701.09
label | 0b1eacdd-5010-5ebc-b453-47775a5d26e0 |  | note | ---------------------------------
label | 3f280de6-d595-5b24-a8ad-3f4c06f73281 |  | note | ACCEPTANCE CRITERIA:
label | d7a64c0d-1737-5fd9-89f3-966cf49b7dae |  | note | Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | 0e0561bd-9ab2-5ea3-8c19-8d7d646d9f69 |  | textbox | Enter: Teambinder Material Approval number
label | 8372510e-f2c9-5039-8238-bee6df3270df |  | note | ---------------------------------
label | d5c9d286-69a6-5f1d-b649-ffa0c693d0b3 |  | note | METHOD: Document Review
label | 482b3714-4726-590a-99e9-4a357291a726 |  | note | ---------------------------------
label | f8a29500-fb49-5d1a-873e-bf098b0898fc |  | note | FREQUENCY: Each lot
label | 2b82f3f7-f1c5-594e-9f3b-9a11e86b4b39 |  | note | ---------------------------------
label | 9a6dcc54-9a09-5393-bf9d-456e6677edf4 |  | note | CATEGORY: HP
label | f7adff96-2203-5711-8ff5-0d8e2d374777 |  | note | ---------------------------------
label | f8fed124-ec9e-5a67-8eb6-dc99bbe46ce0 |  | note | RESPONSIBILITY: SE
label | eb8d0b49-4a13-58be-a048-40893a213697 |  | note | ---------------------------------
label | b3131080-e373-526a-bcf0-4a7d84758d6a |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 25716d88-2f9d-54ae-85ff-d1b3c0c735af |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Procedures
checkpoint-group |  |  | section | Pre Construction
checkpoint-status |  |  | checkpoint | 4.1 Survey Set Out-Pits
label | 24c3045e-d0ac-57b8-a766-93517d9a185c |  | note | REFERENCE:
label | 65d723e9-0a55-590f-8403-ec2bef2392fa |  | note | IFC Drawings
label | 1a1702aa-0e12-5527-969e-cbb197217b4f |  | note | Section 701.10
label | 972eb1d6-5ba6-5344-b116-31fc8701d517 |  | note | ---------------------------------
label | b3497c5e-d2d4-539c-b2cf-9cbdcc2fe8e3 |  | note | ACCEPTANCE CRITERIA:
label | 86b592cf-7026-5649-93e7-a109bb02d17c |  | note | Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | 26739f1c-d4c3-542f-8c6b-826eac4aba81 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | 3a8068e6-602d-5de7-a37b-2002ed28a5da |  | note | ---------------------------------
label | de790a75-201c-5785-b08a-61cb339dc1b8 |  | note | METHOD: Visual inspection
label | 1c0e42e0-a1de-5b89-bbd6-7e38d9244bb2 |  | note | ---------------------------------
label | e7cde081-9fec-5d90-a631-f15c57a2a455 |  | note | FREQUENCY: Each Lot
label | fb5c90ef-eda4-50a1-8718-701b43112cfe |  | note | ---------------------------------
label | 3c601cb1-ffcd-5fd6-8864-dc8c0f262ce4 |  | note | CATEGORY: IP
label | b04c4f49-4a19-5339-9327-7e74a4a5a892 |  | note | ---------------------------------
label | c5eb69db-c61c-557b-9fb3-65272332d919 |  | note | RESPONSIBILITY: SE
label | e32fb930-0599-5bb6-bf4a-89eeba3aaf47 |  | note | ---------------------------------
label | cb6a4a70-c046-511f-866c-d58b7e2a288a |  | note | VERIFYING DOCUMENTS: This ITP
date | bd7c1d2e-4cab-5814-9769-e86786a0bedc |  | date | Date Completed:
checkpoint-group |  |  | section | Construction - Pit Installation
checkpoint-status |  |  | checkpoint | 5.1 Pits-Pit Excavation
label | ed6be0ec-1c62-5653-bbcc-1662170f51af |  | note | REFERENCE:
label | 0cbfd44d-6c41-5300-b71a-96023c18dfc7 |  | note | IFC Drawings
label | 6f91ef1f-02a9-57b7-b581-0d95886f6416 |  | note | Section 705.05
label | 7d59e0c7-9b46-54a6-ac3d-9dc92a483be2 |  | note | ---------------------------------
label | e70ee95c-cb83-5058-b40a-6a3b8819985f |  | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
label | 42e95654-e866-5d86-a256-b9f74968f0d4 |  | note | ---------------------------------
label | b870fb0e-5e69-53da-9f32-451622b18cdd |  | note | METHOD: Visual inspection
label | 1bca50be-53d2-515c-9341-618d0522dff2 |  | note | ---------------------------------
label | c3b3cee9-6dcc-5db6-86e8-501ec35f8b5b |  | note | FREQUENCY: Each Lot
label | d4e2409f-58b1-5728-81de-b04cf8c4e791 |  | note | ---------------------------------
label | 457a7cfe-1e7a-5bbb-a987-5b90b0f9edec |  | note | CATEGORY: IP
label | ea2f9a3b-1671-5a11-928e-3679e3b749de |  | note | ---------------------------------
label | ebf56e51-8b16-5aeb-9c59-9125185090d6 |  | note | RESPONSIBILITY: SE
label | 4396d11b-1fa4-51dd-bf52-4435d138f09a |  | note | ---------------------------------
label | 72dfbe1c-c464-5ab7-9e02-90cf517933dc |  | note | VERIFYING DOCUMENTS: This ITP
date | 878ddb73-2b4b-5b25-8136-39ac23718970 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pits-Excavation Foundation
label | 85a96a73-ff5e-51e5-8c04-498f12d75018 |  | note | REFERENCE:
label | 712033fb-a9b7-510d-9ba0-75a0e52eda74 |  | note | IFC Drawings
label | e6765f0a-69f6-584d-a891-c7b32d8a7835 |  | note | Section 705.05
label | 2b69a6b9-5616-54d2-ab00-43c5f4e5d281 |  | note | ---------------------------------
label | dea16ed0-fab9-5a25-bb8a-7e40653cea9d |  | note | ACCEPTANCE CRITERIA:
label | c99e3955-7a04-57af-9ab9-cdf9cf4a88c2 |  | note | Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
label | 51b30dbd-0035-5670-bc46-0c9616282dd0 |  | note | > 80mm for clay foundations
label | 719e2db2-7a1a-5398-ad81-3b41cb511144 |  | note | > 150mm for rock foundations
label | 2ad43ef5-6811-59e4-a206-00826d7ca5cc |  | note | ---------------------------------
label | 89a9f105-91c2-5b76-8323-6684834864ab |  | note | METHOD: Visual inspection
label | 7cbe07a9-35e0-5895-9ae3-68a79e444fea |  | note | ---------------------------------
label | bdb00c1e-53ad-5f91-b651-a54eb35e4a0d |  | note | FREQUENCY: Each Lot
label | 2cdd8b35-d087-5a06-b886-dbb32e26a1ce |  | note | ---------------------------------
label | 3785669a-ca78-5783-8fb8-442984a0560c |  | note | CATEGORY: IP
label | 39eca24b-03c2-55a6-a77e-5150b245fcc1 |  | note | ---------------------------------
label | 331db0ad-de57-5f25-b239-ca91df89bb31 |  | note | RESPONSIBILITY: SE
label | 67471aef-aea3-5b9b-88a8-4b42a8411f7c |  | note | ---------------------------------
label | 355aa3c4-e68c-539b-9811-c66713209352 |  | note | VERIFYING DOCUMENTS: This ITP
date | b1505cc4-d68f-55a6-a09e-3092e2a737f5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Pits-Placement of Pit
label | 85cd7ea1-f306-5598-baac-98e19da6f39a |  | note | REFERENCE:
label | 8aa840b6-632f-593e-8217-138ba93d99cc |  | note | IFC Drawings
label | 15f8f898-e5b4-5f0f-8798-27c8f6596079 |  | note | Section 701.10
label | c9979c2c-a4e0-5335-a8da-0af05f98f9fe |  | note | ---------------------------------
label | af86d084-4940-5c57-8623-80fe428b100d |  | note | ACCEPTANCE CRITERIA: Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | 1e58d8a6-83d4-5a2b-b4e3-dffdb3d9898d |  | note | ---------------------------------
label | 2ab17e29-3d9c-5b41-9d58-f28634d9964c |  | note | METHOD: Visual inspection
label | 6d05f5c1-cd99-5369-b491-e03f61afd2ac |  | note | ---------------------------------
label | 08dedde9-ec63-5ab7-b1d4-fc819660bb7c |  | note | FREQUENCY: Each Lot
label | da02ae8d-1a26-54ea-9ff9-e097cf8bbb47 |  | note | ---------------------------------
label | 190d5bee-c547-52a3-bc31-885d27c1879a |  | note | CATEGORY: IP
label | 011e21d4-2545-5df7-9300-2c1705557a55 |  | note | ---------------------------------
label | 8c8d14e0-9dfb-5f68-b0fd-61f51a4c514c |  | note | RESPONSIBILITY: SE
label | af6f3432-07ec-5cce-abab-6f6cf54b4e49 |  | note | ---------------------------------
label | e713689d-4c80-5de9-ab9f-fb2c8965a9f3 |  | note | VERIFYING DOCUMENTS: This ITP
date | ea4acdd0-36ab-519d-a1e9-f31c9c7dac40 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Pits-Jointing
label | ee2d2e28-80eb-5773-b7ba-09baeb128dc1 |  | note | REFERENCE: Section 705.11
label | 45c67af3-d133-5e14-abfe-811500e85c84 |  | note | ---------------------------------
label | cab47e0d-ff4e-5bbb-b310-376ae61954f3 |  | note | ACCEPTANCE CRITERIA:
label | fc409264-d5e3-51d8-997c-d94ef0504e98 |  | note | All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
label | fc010168-a5d9-5b8b-bff5-45dce5f5b295 |  | note | Exposed reinforcement shall be coated with an approved epoxy treatment
label | ccac88dc-f7bc-540e-a702-01088c2b185f |  | note | ---------------------------------
label | 3405c58c-815c-5bab-bb1f-17b6565469e7 |  | note | METHOD: Visual inspection
label | cb4eeede-9b00-5493-8aa9-7d43160ef0f7 |  | note | ---------------------------------
label | 7f2b43c5-e363-589a-abf8-de0cfd7da6b1 |  | note | FREQUENCY: Each Lot
label | 36b96de6-5865-5abb-a344-73de24356c3a |  | note | ---------------------------------
label | eff48ed6-2fde-594d-ad41-beae05169333 |  | note | CATEGORY: IP
label | dfeeb822-af59-5341-ba42-82686d48fe10 |  | note | ---------------------------------
label | c17f67c3-a359-5294-ab6e-65228d6bd126 |  | note | RESPONSIBILITY: SE
label | 2939739c-59ea-56f6-9bba-3db4f00c14c1 |  | note | ---------------------------------
label | 0b681a28-75a2-567a-8dcb-ebbece4ad935 |  | note | VERIFYING DOCUMENTS: This ITP
date | c4624971-1b90-5473-9471-38530abe8fb2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Pits-Shaping of Floor
label | f10c35d8-65d7-5b92-b88f-2b0b8a889794 |  | note | REFERENCE: Section 705.13
label | 358daee2-973e-562b-b05c-9f7b337dc660 |  | note | ---------------------------------
label | 954953d3-5ae9-5175-a49a-3f037772fda4 |  | note | ACCEPTANCE CRITERIA: Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
label | 6e0ff7b7-fa57-5e66-91b6-a7f54abac9eb |  | note | ---------------------------------
label | 2a2a9c4c-adb1-53c9-b956-fda8fc13d969 |  | note | METHOD: Visual inspection
label | 35f00cd6-2c35-54b0-8434-ba50d0b89b85 |  | note | ---------------------------------
label | 70f73234-7ee9-548e-b13a-3467d0a96f30 |  | note | FREQUENCY: Each Lot
label | f2776a16-304d-5cb5-8010-fcb8eb989cc2 |  | note | ---------------------------------
label | a0f88a33-6483-5989-8d00-9cf80aab2300 |  | note | CATEGORY: IP
label | 1e636efb-65f9-5a77-8a9f-6ac9eb8549f1 |  | note | ---------------------------------
label | 898d930f-4604-51a4-aa55-f1e249e12137 |  | note | RESPONSIBILITY: SE
label | 1436ae27-0d2a-5a7b-9331-c8d89e8aefa5 |  | note | ---------------------------------
label | df0b565a-c79a-5307-a078-e700c99d52a5 |  | note | VERIFYING DOCUMENTS: This ITP
date | f07c80ba-e492-54f0-9464-83e2043a7f85 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Pits-Step Irons
label | 34ba0edb-b7fb-56f8-a7ef-92fccffc9f3e |  | note | REFERENCE:
label | 41cf660d-15e7-5d17-8e60-1df09ee8b895 |  | note | IFC Drawings
label | 75e0407d-f21c-57ad-bf13-1bbe6cf3ec81 |  | note | Section 705.12
label | 702f758b-25a9-58f8-b63f-ad7c542980f7 |  | note | L1-CHE-STD-030
label | 42e56a8d-e91d-5f9b-8948-5da4beccdd6f |  | note | ---------------------------------
label | eee614f4-ef23-5f0a-a8cc-d8197af6e1dc |  | note | ACCEPTANCE CRITERIA:
label | 12ccab27-0ecb-5273-8ed0-d8179133e26f |  | note | Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them.
label | 30bfe0b2-e752-51bc-b2ee-cf9444c83ab8 |  | note | Step rungs do not come within 50mm of the top of the riser
label | 85ee49ac-02a5-51fe-a1bb-ca12919d295d |  | note | ---------------------------------
label | 5aede39f-1bbb-5981-86c8-3a804a1193d2 |  | note | METHOD: Visual inspection
label | 28b12efd-242c-5c15-aab8-41dc5fd30cdc |  | note | ---------------------------------
label | eb92abd3-89cd-5b48-a02e-931929e290eb |  | note | FREQUENCY: Each Lot
label | 57ec8156-e8f3-515b-927f-684bc8bbc126 |  | note | ---------------------------------
label | e522f67c-fe93-5c71-9b6c-1c5a4749530e |  | note | CATEGORY: IP
label | 1f7f9f75-928d-5b58-8db6-9047f72f8d90 |  | note | ---------------------------------
label | ba6c9f5b-1945-56cc-afa1-66df031fb173 |  | note | RESPONSIBILITY: SE
label | 31584d5a-ad2b-5bc3-9e19-761b08481d97 |  | note | ---------------------------------
label | 8bc7e1eb-9f1e-546e-8d12-2fe9f503ddfd |  | note | VERIFYING DOCUMENTS: This ITP
date | f6913d58-b792-546f-af64-f18f2230fa76 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pits-Fitting of Covers
label | 4532c040-f590-5f96-af12-5b540a605a9d |  | note | REFERENCE:
label | 366c940a-d048-5408-bbc6-837fc95f0c06 |  | note | IFC Drawings
label | d94ee30b-c1b1-5c77-9dda-34bb847252d4 |  | note | Section 705.17
label | 7f92d463-5be4-5480-b2ad-bb74df9650c6 |  | note | ---------------------------------
label | 47fab317-27c7-5275-ad0f-498e03c331f7 |  | note | ACCEPTANCE CRITERIA:
label | 836d9c66-059c-5abd-bbda-3f0e3c925036 |  | note | Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
label | 89b65fa6-f352-57a8-9245-9eda18f45109 |  | note | Height shall be within 10mm of the design level
label | 34425cb7-da15-58d5-8f7d-752c8d051cac |  | note | ---------------------------------
label | 0c3fb92c-39cd-5705-a401-12a03faf0a5f |  | note | METHOD: Visual inspection
label | bba49c76-c8b2-5080-bb06-1ba7274dc845 |  | note | ---------------------------------
label | 486668c4-a7ce-5cc0-93d4-6bf7f24a6b39 |  | note | FREQUENCY: Each Lot
label | 603c3a49-7425-522e-a769-21a0d5355fa6 |  | note | ---------------------------------
label | 0dc9b661-5484-5700-9448-3ce8129872b9 |  | note | CATEGORY: IP
label | 0fd4bc91-5731-59da-bc9d-e26c5517b637 |  | note | ---------------------------------
label | 1755cce9-0031-5ec6-b6d4-b69a8f8900e9 |  | note | RESPONSIBILITY: SE
label | 2ba28105-3498-5d96-9761-6c1306fa07e4 |  | note | ---------------------------------
label | b557e12e-f2c3-56ab-848b-c325265dcbb2 |  | note | VERIFYING DOCUMENTS: This ITP
date | 7bb8eef7-adcc-5cf5-95f5-b18967eba967 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pits-Pit Lids
label | bd1098e3-8d44-5559-82a0-3ea0df6e5e4f |  | note | REFERENCE:
label | 34e7359d-b39e-5e61-bf4d-a6e84d0a2ade |  | note | IFC Drawings
label | 3d45db80-cc4a-5f63-b168-bf574e032831 |  | note | L1-CHE-STD-030
label | b6f9e720-43e9-5f27-a46d-3f7489714922 |  | note | ---------------------------------
label | c0e13d23-1d07-5c68-a38b-219d2bdcbc65 |  | note | ACCEPTANCE CRITERIA: All stormwater pits shall be provided with a locakable minimum Class D piit lid, grate or ballast cage in accordance with MTM L1-CHE-STD-030
label | 63d8f780-100b-557c-b451-1bfbf517a8fc |  | note | ---------------------------------
label | 2ffea3f0-1976-5939-82f0-363b23084255 |  | note | METHOD: Visual inspection
label | 142000b6-0432-59f7-b6cd-1e23f6216688 |  | note | ---------------------------------
label | 862c5908-7066-5c0d-b26b-7f7e839a3cc3 |  | note | FREQUENCY: Each Lot
label | 0b97a811-e93a-5668-a4cb-006c0a1eee67 |  | note | ---------------------------------
label | 808d5a99-9137-5304-9622-7fc18112d8a1 |  | note | CATEGORY: IP
label | 5e3aaac2-ca5f-55cc-be6c-e04d04eb59c0 |  | note | ---------------------------------
label | d0478c26-032e-5d2f-bc7d-3af33fe815f2 |  | note | RESPONSIBILITY: SE
label | f06db88f-84e8-59ea-9ac8-fb1f1bcc2c93 |  | note | ---------------------------------
label | 4c902db5-4669-5f40-97a3-6943b1e2dbf5 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2e61b87a-c2e7-5d5b-8d29-d3615917283b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Pits-Backfilling Around Drainage Pits
label | b06e7bd1-dede-5309-b6ee-6a1859ac5bf2 |  | note | REFERENCE: Section 705.18
label | 3a15db24-964f-57cf-b272-2571688601d9 |  | note | ---------------------------------
label | 699361dd-85cf-50e1-bc7e-fb2112dc57c9 |  | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
label | 86dcc65d-e469-5709-aef6-5f911079aa12 |  | note | ---------------------------------
label | eab1bfab-d8bf-5097-a482-588e7e1242fb |  | note | METHOD: Visual inspection
label | f7e471e8-eba0-5880-a3b7-45b8f10519d4 |  | note | ---------------------------------
label | fab3b738-ce7d-558d-80d5-aeac12f7ea36 |  | note | FREQUENCY: Each Lot
label | 326eb8ce-3168-58ff-8610-2bf2b173abca |  | note | ---------------------------------
label | dd63fe2f-f2a9-524d-8286-52d7894eb559 |  | note | CATEGORY: IP
label | 1869fd24-4964-5d0a-9e6d-f6028f91134d |  | note | ---------------------------------
label | ebd3f927-0fdc-594a-9c9c-56640fe49fea |  | note | RESPONSIBILITY: SE
label | 0f5dcba4-64be-5110-9284-b27ed2abe28f |  | note | ---------------------------------
label | 6321e96b-e970-5db7-8ec2-77404b531ef5 |  | note | VERIFYING DOCUMENTS: This ITP
date | bfe23dd3-021f-553f-8304-b4f985c23e3c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Pipes-Trench Excavation
label | 4d14f358-afa0-51c6-ac56-3ab0905bce8b |  | note | REFERENCE:
label | 5fd7bf4f-2ea0-53b4-bfe4-16091c76165e |  | note | IFC Drawings
label | 84365ac4-e233-573e-8080-3e5bd9fb58ac |  | note | Section 701.15
label | 949e2451-0807-555e-ae73-104ec26499fb |  | note | ---------------------------------
label | 37b6640e-54fa-507d-afdd-9cc6b18b13ab |  | note | ACCEPTANCE CRITERIA:
label | abd7a860-0881-524f-b8b9-f3c1ba0e51a6 |  | note | Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | 56256ba5-a5a1-5e50-81d3-47b8a2e78e65 |  | note | > 300mm, < 600mm for RCP
label | c546965e-3e80-5d1f-967f-ac998f4dd9e5 |  | note | > 150mm for Flexible Pipe
label | f9e0d5ea-ad14-5832-90f3-aff6f02a6244 |  | note | The base of the trench shall be compacted to refusal using mechanical plant.
label | c1bf97ab-121a-5a78-bef7-a03183fb6ff4 |  | note | ---------------------------------
label | 8dd74a29-f481-5ce3-b6ba-96237fa35cfa |  | note | METHOD: Visual inspection
label | 82a0d95a-553a-5761-a6e5-59f0ad44375d |  | note | ---------------------------------
label | ee5aec51-0f4c-517d-84ef-ef67b4ccf78d |  | note | FREQUENCY: Each Lot
label | bb052810-abda-5583-b528-84c166b2818d |  | note | ---------------------------------
label | e249fb66-6291-5961-b80b-6836d48035a4 |  | note | CATEGORY: IP
label | 2d017219-2582-5d0e-8edc-3c9f44fe6e82 |  | note | ---------------------------------
label | f5a3d236-3c4c-5420-b1c7-c9966d87c7f9 |  | note | RESPONSIBILITY: SE
label | 5b9a58f2-e2be-51a4-a7ce-9c633db9f004 |  | note | ---------------------------------
label | 2e68f86a-1561-5d5b-b7ed-8a687cdeca7e |  | note | VERIFYING DOCUMENTS: This ITP
date | 479691f4-0a47-55b6-9e35-e3ae7e0cfa89 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Pipes-Bedding Placement
label | b4e3f79d-f3d8-51d0-a352-f3a25736235a |  | note | REFERENCE:
label | 1f271d1e-9b55-532c-b7a8-4ac68366e507 |  | note | IFC Drawings
label | 08948b4d-71a5-5d7a-8d51-6cec79015c7b |  | note | Section 701.16
label | 293a7ef2-cb0a-51d2-8779-18da5a6f771f |  | note | ---------------------------------
label | 744abee5-8722-53c7-9751-32fa4d5be873 |  | note | ACCEPTANCE CRITERIA:
label | 06893c25-64c7-56f3-b8d4-02caec541940 |  | note | Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | a04833af-65d1-5772-8c0c-ffb40d41a80e |  | note | > 100mm where D<1500mm
label | 5f1d119f-42e0-5f45-a559-2d170dd2fa7b |  | note | > 200mmwhwere D≥1500mm
label | 00522a45-06d2-5053-a3ac-bae07e8398f3 |  | note | Bedding material shall be placed and compacted in layers <150mm loose thickness
label | e54a318c-cfd3-5a72-90e2-5ca0704b28eb |  | note | ---------------------------------
label | 0bd577d0-595f-5cfc-a9ec-44bfa92a6925 |  | note | METHOD: Visual inspection
label | 8660f428-3cd5-5e96-94b2-465452d8d5d5 |  | note | ---------------------------------
label | 2a0f0780-9f96-5589-b966-c29bd72f4e21 |  | note | FREQUENCY: Each Lot
label | d024a489-4f9e-51be-a76b-8056a91992fa |  | note | ---------------------------------
label | 4b17f5fb-4c37-5e7d-b702-345208d43042 |  | note | CATEGORY: IP
label | 2a3001f6-db6f-520a-96bb-88d22c1f1c16 |  | note | ---------------------------------
label | 32545f4b-a18e-5a92-9aab-913d6f8ba3ef |  | note | RESPONSIBILITY: SE
label | f2649f91-0bc4-5676-8240-f970d2f3c213 |  | note | ---------------------------------
label | 50d4adc4-dccf-5df1-8788-4c449f2aab26 |  | note | VERIFYING DOCUMENTS: This ITP
date | 03c6db59-6e3c-5036-890f-ad8c5710bb49 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Pipes-Placement of Pipe - RCP
label | 06e15bf1-5e65-5e63-af80-b67d4271856d |  | note | REFERENCE:
label | 9f159d52-ee9d-5fbb-bbdc-4a54e1a9de36 |  | note | IFC Drawings
label | f44ba8d0-a385-56aa-8c85-de23bc159514 |  | note | Section 701.17
label | 8cf575bb-c238-56f0-908f-8a8c6994c51a |  | note | Section 701.20
label | 44662b7d-def0-5dfb-a7a9-ee492f6dd3b3 |  | note | ---------------------------------
label | a99ae201-8a98-5d54-addc-ead713eb9813 |  | note | ACCEPTANCE CRITERIA:
label | f4fd9ed9-024a-5a61-b0da-9543402805df |  | note | Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
label | 8654a0c8-b700-54c2-8edb-a8d2c66b3407 |  | note | Gaps between spigot and socket are in accordance with the manufacturers specifications
label | aee5635f-d0bf-59d2-83e9-ec4db47117eb |  | note | The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
label | 480de007-bfcd-503b-9b7d-082368669b21 |  | note | ---------------------------------
label | 507f39b5-8b6c-5a78-bfd6-99116e59a4e0 |  | note | METHOD: Visual inspection
label | 9cb8386c-8df3-5a25-a701-9913139c7989 |  | note | ---------------------------------
label | 35149eb1-d841-5eea-85ec-c4b8892f168f |  | note | FREQUENCY: Each Lot
label | 536daa6b-9674-557c-a9ff-9269503e2375 |  | note | ---------------------------------
label | 3eb4e9b8-e95e-55ee-9d66-7f0b19ded748 |  | note | CATEGORY: IP
label | 33ba882c-5051-5202-95e8-c1bc814ba019 |  | note | ---------------------------------
label | 42178f99-3aa6-515e-b50d-a6be12f96044 |  | note | RESPONSIBILITY: SE
label | ed2fbf33-ebba-5c2c-b193-20212630fdc2 |  | note | ---------------------------------
label | cfe287d8-471f-53dd-8ef4-528b8197a0e4 |  | note | VERIFYING DOCUMENTS: This ITP
date | da98a8df-aba4-5824-8f36-5e3a62e3dead |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Pipes-Placement of Pipe - Flexible Pipe
label | 49ebfbdf-ea86-5e48-97a9-7aa8e060cf8e |  | note | REFERENCE:
label | 0e7a30f9-403c-51fd-ae6a-20c2bed782cc |  | note | IFC Drawings
label | 1aee6f40-17f7-5e18-aec9-4cd3f532cc92 |  | note | Section 701.17
label | 5ff76d14-24aa-5a63-9055-57ec70219988 |  | note | Section 701.22
label | 8e1d5d5a-ed66-5524-9ea8-3433af1c11f0 |  | note | ---------------------------------
label | 6d6ef945-6f31-577e-83bb-7b39aa103c90 |  | note | ACCEPTANCE CRITERIA: All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications
label | 37295e20-5c6f-5405-ac4f-a5355063dd7e |  | note | ---------------------------------
label | 0dcc0960-808e-5429-9466-a4731d1fc196 |  | note | METHOD: Visual inspection
label | 3328b9fd-3ec6-555f-b8c4-ae4d31393d18 |  | note | ---------------------------------
label | 75794902-c9cc-5dab-9027-0c8a077e46a5 |  | note | FREQUENCY: Each Lot
label | 66bd8ac2-2ccf-51d4-b6a3-80c3fc63d5d4 |  | note | ---------------------------------
label | 9a783f71-6ce5-5691-9119-639849057cfa |  | note | CATEGORY: IP
label | 318349bb-5ef0-5d7e-9c26-30ffaa446205 |  | note | ---------------------------------
label | 2b827bf6-0e65-5c73-abbd-a052d0bc6515 |  | note | RESPONSIBILITY: SE
label | 77e31f6b-35ff-59ef-9cbf-56e81a05b03c |  | note | ---------------------------------
label | 551188a0-ade0-541d-ba11-652b68c90708 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2f6c5883-845b-51bf-8a12-104979a91f0b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Pipes-Lifting Holes
label | 2220f9af-ff2f-52ed-aac9-d03bf5ec5de4 |  | note | REFERENCE: Section 701.18
label | a7b56b7a-123e-51af-8618-145a8c5003af |  | note | ---------------------------------
label | 252e31c8-5dad-5401-be4f-3878c055a07c |  | note | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | 3de0cf93-4362-593b-b593-93641fae2513 |  | note | ---------------------------------
label | ccc02da8-a08e-57c8-a380-56e37b105906 |  | note | METHOD: Visual inspection
label | 4a2ccdfd-6139-58a2-9999-485c8d456c07 |  | note | ---------------------------------
label | c14dadc0-c35a-5bcf-9759-eb06022489b0 |  | note | FREQUENCY: Each Lot
label | de0d2bf9-a228-5ac5-a8f2-d91cac94626d |  | note | ---------------------------------
label | ecbeb7b4-5103-5396-87c9-70597a14225e |  | note | CATEGORY: IP
label | 5432f01f-9e75-5a23-871a-a73fdf979b39 |  | note | ---------------------------------
label | bdec262d-f7e1-5339-9689-2f541b3202a3 |  | note | RESPONSIBILITY: SE
label | 2a8401d1-31fd-5ae0-9d26-640b92735419 |  | note | ---------------------------------
label | 1c6583f1-afdc-546b-a3fe-9aa045d97df5 |  | note | VERIFYING DOCUMENTS: This ITP
date | ccaff243-1589-576e-9b5b-c8026af8157b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Pipes-Survey Conformance
label | 4e3e046b-9436-548c-b924-18289542a040 |  | note | REFERENCE: Section 710.10
label | 66e43c9a-ccbe-50db-b93c-5bce25bea3f1 |  | note | ---------------------------------
label | 6efd62c1-a4a9-56c4-928e-aafe8e7826fc |  | note | ACCEPTANCE CRITERIA: Location of drainage shall be verified by a surveyor prior to backfilling
label | f03dd153-9848-5d65-914a-12f511503aba |  | note | ---------------------------------
label | 639ba107-f120-5a6e-b6ca-c4901be5343f |  | note | METHOD: Visual inspection
label | 113d97b7-2825-5408-baa4-aad946bbcdb5 |  | note | ---------------------------------
label | 27078ed7-3f69-5a5d-83f2-d33c83ceb0bc |  | note | FREQUENCY: Each Lot
label | b2d2ddd4-5524-54fa-9869-98e26432ebed |  | note | ---------------------------------
label | 23f4a3f7-ec1d-5e42-bc7a-f2852cdff7b9 |  | note | CATEGORY: IP
label | c7239f3a-7f1d-5f96-9ccc-563e86980d37 |  | note | ---------------------------------
label | 464423d7-c7c9-5c3c-8123-87285b55b87f |  | note | RESPONSIBILITY: SE
label | 7421cbae-8301-5726-a2aa-11518a8e3d5d |  | note | ---------------------------------
label | d9d24082-7013-5142-95f6-ee729c78e1b0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 74f8c082-903e-5b1a-934c-b3a374e4df6f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Pipes-Backfill Placement
label | b42df311-ea17-527f-b087-0d83dacdab2d |  | note | REFERENCE:
label | a417b9ab-ba11-512c-8f07-b8698f65b36e |  | note | IFC Drawings
label | b6f41a02-56ef-5f18-a78c-90032e2cb2ce |  | note | Section 701.16
label | 5ea19ec1-2b5d-5e18-b1ab-d891f0b64fa7 |  | note | ---------------------------------
label | 78dadb77-571e-5445-bf05-ce68e99dbdfb |  | note | ACCEPTANCE CRITERIA:
label | b3969438-529e-55d4-9872-f0f309c4dd9e |  | note | Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | 7484e7e9-2e5a-5648-a6d9-5f8a2ac5b138 |  | note | Filling shall not be placed within 2.0m of the open end of the pipe.
label | 8b8831d1-3c7e-5642-8bd7-be573629f0f8 |  | note | ---------------------------------
label | 4bb396d3-abdd-5658-9469-79c799c859de |  | note | METHOD: Visual inspection
label | f9e52bcf-5c66-56db-a804-c6c3260e2faa |  | note | ---------------------------------
label | b09237b9-9ffd-527b-9055-065485aa1c14 |  | note | FREQUENCY: Each Lot
label | 01e7a8fa-d452-5f31-a726-a7a0cf827946 |  | note | ---------------------------------
label | 444c49b4-ab69-56ce-a048-ce28628d2e59 |  | note | CATEGORY: IP
label | e7eb91c9-a28b-53b9-b6e8-84d92d0c4f6c |  | note | ---------------------------------
label | 6e252302-43b3-54ed-bd18-a89a96c204ce |  | note | RESPONSIBILITY: SE
label | 3983c04c-edd6-5ca4-9757-8992ac6a5dd1 |  | note | ---------------------------------
label | f6c8524f-d310-5322-8cd9-cb22fa72eda9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8517bf81-afe8-53d9-82c9-c0607b82626f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Pipes-Backfill Testing
label | 820058d3-598a-5434-9968-d4b1f215cdf3 |  | note | REFERENCE:
label | 97677478-e79b-5693-8f53-be7efd687af8 |  | note | IFC Drawings
label | 42458fb1-8e5a-5c1e-8e51-a220620d46ac |  | note | Section 701.20
label | d0a75b39-c421-5666-88a2-1fa0ead6f58d |  | note | Section 701.29
label | 87b5e65d-95c0-5548-bdc0-1f77a9ad0de7 |  | note | ---------------------------------
label | 5569456e-310e-52db-a278-9d5a6e4466c2 |  | note | ACCEPTANCE CRITERIA:
label | 637dd737-3b4a-5793-9646-695f771a8954 |  | note | Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | d9d2d235-8a02-51cd-9f31-5d84aa57d169 |  | note | Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 8d08768b-539d-51fa-a131-be2738015d1e |  | note | ---------------------------------
label | 62af36e5-d2a0-5361-b3a1-cbdb9449c428 |  | note | METHOD: Visual inspection
label | 2328ac16-5c30-5008-ba9e-9d8daaa8a648 |  | note | ---------------------------------
label | b506f5c2-df8a-5dc8-80c0-319a8c84eede |  | note | FREQUENCY: Each Lot
label | 0e0c2357-2bfd-543d-9023-e5e4bf97761f |  | note | ---------------------------------
label | 0c33bf99-cb2d-52ee-97b8-a1a8c1881168 |  | note | CATEGORY: HP*
label | 67ed0c34-517d-5ec5-a0d6-916fd1f3f499 |  | note | ---------------------------------
label | 3c8ae780-9e2c-55c3-a312-5b06b73e0638 |  | note | RESPONSIBILITY: Nominated Authority
label | f2ca7ecd-4d04-5125-a1aa-73f817a5fc55 |  | note | ---------------------------------
label | 6865ca43-0d59-516a-8ca4-27359b23bca1 |  | note | VERIFYING DOCUMENTS:
label | 2819332c-48d9-54c7-8b09-276e9dc4292a |  | note | This ITP
label | 7bd7c424-7165-5a55-be1a-337e02d2c2f3 |  | note | Attach record of test report
label | dd3786f4-0147-56bd-a8d5-d35a095fd7eb |  | note | Attach material delivery docket
date | b7040397-4b83-56c2-839a-a7ab5173d048 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Slotted Pipes-Trench Excavation
label | b5b245ef-a343-5534-b357-d5751cb70886 |  | note | REFERENCE:
label | fd9c6005-9307-5731-bee3-cbcaf2424f03 |  | note | IFC Drawings
label | 00f15a06-c160-5044-80ec-793490fb78c6 |  | note | Section 702.08
label | 7849dc5e-af99-5882-8e28-fb7cc3e2d3a3 |  | note | ---------------------------------
label | 46eca9e7-2dfd-59f4-8eac-f80d30592d4f |  | note | ACCEPTANCE CRITERIA:
label | 78dd904f-e15c-5237-a785-a6682f9d34f8 |  | note | Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of > 150mm for Flexible Pipe
label | 5cceb90b-6782-58c1-8c13-f6c38d7a8a3f |  | note | The base of the trench shall be compacted to refusal using mechanical plant and be <50mm below the specified level of the invert
label | 53574fcd-13a1-500f-b6cb-87955612b7e6 |  | note | ---------------------------------
label | d60d3d4c-f27e-5e4c-a57c-a77b58eb762f |  | note | METHOD: Visual inspection
label | 9eb1f72a-8b8a-5dbe-8ea2-23f9a13dd834 |  | note | ---------------------------------
label | 61a6f493-76e7-5758-b8f4-cc46820d6bfa |  | note | FREQUENCY: Each Lot
label | 6c8e0eb8-6fa8-5733-9f41-0f755974c27a |  | note | ---------------------------------
label | f2cc37ab-1376-5aff-9293-f31b6ad809b7 |  | note | CATEGORY: HP
label | c6884d8b-2da2-5951-b92d-662f96a4dba2 |  | note | ---------------------------------
label | c6ccdf9a-cd1f-5b08-8a2b-f32728e81ef6 |  | note | RESPONSIBILITY: SE
label | c7b18488-e8f2-5863-b340-30c60a8472c2 |  | note | ---------------------------------
label | 4203bdbb-7783-579a-90c7-093dd285340d |  | note | VERIFYING DOCUMENTS: This ITP
date | 38c7ce53-c0c4-5860-b190-eedfc9b24c89 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.19 Slotted Pipes-Geotextile placement
label | 05c5ab3a-2513-5cc5-890d-0a6ab7a5057a |  | note | REFERENCE: IFC Drawings
label | dd2eced2-721d-5ac9-b794-d486f193e8e0 |  | note | ---------------------------------
label | 33ad62bd-d418-5d95-b9a5-4b5cbae0655b |  | note | ACCEPTANCE CRITERIA:
label | 84be3a73-e262-50ed-a59d-098fb71ab197 |  | note | Trench to be wrapped with geotextile in accordance with the manufacturers specifications.
label | e90bcdda-7b4d-50f6-98ec-823a0e01bbf2 |  | note | All laps are to have 150mm lapped at the top of the trench
label | 68796600-c8b9-5a1b-abb6-f95efb7e6f17 |  | note | ---------------------------------
label | f4b72f64-aa07-5175-83da-1d97b970feb7 |  | note | METHOD: Visual inspection
label | c1609c5e-f9a8-576d-a45d-e754cb049829 |  | note | ---------------------------------
label | eb35193d-0047-5825-b6ca-427df50a6b63 |  | note | FREQUENCY: Each Lot
label | a6c68a3b-952f-58dc-9774-c97958253321 |  | note | ---------------------------------
label | 37a2a97a-3c03-5cd4-9dba-0e4ed8a731f7 |  | note | CATEGORY: IP
label | ae432d08-f7e7-5787-ac6b-4879877a5213 |  | note | ---------------------------------
label | bc84a794-f8b8-5370-8112-fe4c0f8c5147 |  | note | RESPONSIBILITY: SE
label | 997a0894-e01c-50e9-ba90-0f12d6cd874d |  | note | ---------------------------------
label | 757b103a-4a58-58bd-a299-039a4e8a0fe1 |  | note | VERIFYING DOCUMENTS: This ITP
date | b6d580f2-adcb-5e0f-8253-379690996400 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 Slotted Pipes-Bedding Placement
label | eb16a4d1-0372-5539-8fd3-6ad01a7534a5 |  | note | REFERENCE:
label | ece36646-006a-597a-8478-ed4385431db2 |  | note | IFC Drawings
label | 6a3f3ccb-54b4-5749-857e-7875d0c15018 |  | note | Section 702.09
label | 32561caa-4556-5965-a497-6bac3b254dca |  | note | ---------------------------------
label | 0f09302e-7ca9-5d2e-a52d-b1bf7807ffc3 |  | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | aa71f248-538f-5d28-b394-9d2310b0c95b |  | note | ---------------------------------
label | 046e77e6-5b32-52de-9f5e-b45cd8a9aefe |  | note | METHOD: Visual inspection
label | d02a8581-bf3e-5a0b-aeea-1036deb8a464 |  | note | ---------------------------------
label | 0acd30a6-ed9a-516e-9290-df75fe125c05 |  | note | FREQUENCY: Each Lot
label | a0412db0-c9a3-517b-8881-d3a975d16584 |  | note | ---------------------------------
label | e5ac17ec-613e-5265-8e6e-03cf9a0b2e40 |  | note | CATEGORY: IP
label | 71a615d4-c89a-5fc5-8970-170e20e73ebb |  | note | ---------------------------------
label | 1c4cc3d2-78b1-554c-88b8-6c706f11e7f2 |  | note | RESPONSIBILITY: SE
label | e6dbfb76-1f8d-58b7-86e2-62848202eb70 |  | note | ---------------------------------
label | 0a363582-3953-5b1d-b756-362161b53dcb |  | note | VERIFYING DOCUMENTS: This ITP
date | e843858f-db7b-5e7b-a95a-6c8c6aa05377 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.21 Slotted Pipes- Placement
label | cdd94068-ed09-5ee3-bc60-0c686f48ad0a |  | note | REFERENCE:
label | d9876986-0981-5c73-a942-0c1097f3b275 |  | note | Section 702.03
label | 66891bda-c8cd-569e-b93b-a5a2b2d98338 |  | note | Section 702.09
label | 608b563c-e99f-58cf-ac03-c89085233dda |  | note | ---------------------------------
label | fcd85316-eb06-5036-ab23-ac1bb154d9ae |  | note | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the opening in the lower half of the pipe.
label | d3e68be9-5e20-5774-81d8-4eadab521d5b |  | note | ---------------------------------
label | a9ebddb6-64a7-5337-bc82-9ad595313389 |  | note | METHOD: Visual inspection
label | 1eb6e129-a718-5c29-9169-52d7972bc473 |  | note | ---------------------------------
label | 98ee3056-7438-5ad5-95b7-e9b9134a51a7 |  | note | FREQUENCY: Each lot
label | 0601b374-12a9-5961-8a0d-004e0843e1a6 |  | note | ---------------------------------
label | e1aaba7a-b7b6-5c2a-b590-f958ff0a61fc |  | note | CATEGORY: IP
label | 3ab7e929-cce3-5e20-a89f-c8b07616abfd |  | note | ---------------------------------
label | 2bc8aa86-d197-59f6-a1e8-c6adf92bb499 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 58fc6651-3614-58e6-922a-a70bc3a2253c |  | note | ---------------------------------
label | 4addd832-5db7-57da-aa7c-e1224cb0aaac |  | note | VERIFYING DOCUMENTS: Sign ITP
date | a73b1f53-027f-564e-ada9-cdadb0bd57f9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.22 Slotted Pipes-Backfill Installation (Granular Filter Material)
label | 044baaac-a67b-5053-a032-56198d64febb |  | note | REFERENCE: Section 702.09
label | 238f0ae0-adff-566b-8172-0a2435c65c39 |  | note | ---------------------------------
label | 2fb73e0f-b078-55ec-b25d-d7f7044a1f38 |  | note | ACCEPTANCE CRITERIA:
label | efb7ee9f-8379-5ed9-b495-8cbb21ad66a6 |  | note | Material shall be placed moist and compacted in layers not exceeding 300mm.
label | f19bae9b-57a4-5d1c-aeab-30aeff2e650a |  | note | The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | 3829893a-134e-5fed-b37a-4b7185ab8440 |  | note | ---------------------------------
label | b746ee56-d877-5035-a2e6-b6fb2054c643 |  | note | METHOD: Visual, Doc. Review
label | b830b5d3-68ef-5c1b-960f-59946746042b |  | note | ---------------------------------
label | 198de62d-2057-5272-97ea-d5910c89f6a5 |  | note | FREQUENCY: Each lot
label | 3ba3f732-fd4a-5b4d-afbc-8f7ec22206fc |  | note | ---------------------------------
label | d13d54dc-28ce-58b8-ac47-c70104268209 |  | note | CATEGORY: HP
label | 1c5331c0-4470-584a-9539-4552b03267b1 |  | note | ---------------------------------
label | 94bc40c1-5bf0-56d4-a5aa-3f08a275debe |  | note | RESPONSIBILITY: SE, NA
label | 676a91d2-4a40-5786-9e7e-17f1aaf61242 |  | note | ---------------------------------
label | 939c8c1d-47e7-5668-92ec-a1001062189b |  | note | VERIFYING DOCUMENTS:
label | 42892726-ebc9-582c-b412-95ef849188f4 |  | note | Sign ITP
label | f4fd2f82-6ff9-5cef-9a23-81cc94471173 |  | note | Attach Backfill Delivery Dockets
date | 7a22b10a-6610-5d63-8233-605a8a6ca72d |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.23 Slotted Pipes-Backfill Installation (No Fines)
label | 974522fc-aa36-5435-a088-ecf04e9e91ac |  | note | REFERENCE: Section 702.09
label | 5e5fce74-fb8b-527f-8335-ac8db46896d1 |  | note | ---------------------------------
label | e7186fd4-c6dd-5211-9416-c889bbe23286 |  | note | ACCEPTANCE CRITERIA: All subsurface drainage shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
label | ae0dd1e7-3c62-596c-baf7-f8389fe2c0db |  | note | ---------------------------------
label | fda5e73b-5f11-5966-a540-fa5ce7b2dc08 |  | note | METHOD: Visual
label | a34c7f77-4614-5161-981d-804a502e7544 |  | note | ---------------------------------
label | 4eff83fc-9bb8-5066-8ce3-0821e1ccddb9 |  | note | FREQUENCY: Each lot
label | a97903e2-6362-591b-bf96-6d75e9ea9101 |  | note | ---------------------------------
label | 9cf93d9c-579c-56c7-8aa4-e624d5f230ed |  | note | CATEGORY: HP
label | b11b403b-e023-5d8e-aff7-00a60fe71cff |  | note | ---------------------------------
label | 304c56c3-f9cd-52bc-8f42-c73d22f08315 |  | note | RESPONSIBILITY: SE, NA
label | f7bc0362-c179-5e7c-9c7c-dce7873bb7fb |  | note | ---------------------------------
label | 20145e76-99ff-5337-906c-6e5a38042ed6 |  | note | VERIFYING DOCUMENTS:
label | 1900f08c-ba76-5f98-b5dc-384faed8a9f2 |  | note | Sign ITP
label | ad9d87d0-1611-58a7-bb3d-fb47f156b079 |  | note | Attach Backfill Delivery Dockets
date | 33adaa53-2897-5bb4-8338-fd1757b6eba6 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Flushing & CCTV
label | dc85a34b-ce40-57f4-bb58-ea98e113d82e |  | note | REFERENCE:
label | e702f4e6-55c7-5f80-aec2-51319c6a0ebe |  | note | Section 701.28
label | c6a499fb-665b-5a03-b480-1ad8a7e8278f |  | note | Section 701.30
label | c5217ef7-9f45-53c8-9a88-08d0db5345a1 |  | note | ---------------------------------
label | e43a0c02-be3c-5e1e-bd59-90b00d6ea889 |  | note | ACCEPTANCE CRITERIA:
label | b0a45514-25a0-5c0f-adca-0f449a05deb6 |  | note | All pipes shall be flushed clean from end to end on completion
label | 72ec1625-98ba-545b-9717-2be8a5c37679 |  | note | All drainage lines shall be inspected after completion of earthworks to subgrade level and prior to construction of the pavement layer by an independent testing organisation using CCTV
label | e4a53ddc-8a69-5e84-b2a2-4684abfa30ab |  | note | ---------------------------------
label | 5e895991-d071-5988-b5be-69fb39ec04ec |  | note | METHOD: Record Review
label | d1903101-56a4-5b73-a0e2-fe65df214dee |  | note | ---------------------------------
label | 90686740-0360-5e95-86a3-95d728fb5b7b |  | note | FREQUENCY: Each lot
label | ecd1f3bb-6f66-5caa-97cb-a63f63d6952f |  | note | ---------------------------------
label | 935734cb-3dfd-5130-be07-3b53c19c6589 |  | note | CATEGORY: HP*
label | 46ef9af9-cc1f-593b-a252-930f1d5f95a6 |  | note | ---------------------------------
label | c430aab2-af78-51d2-9a07-167000ee2e39 |  | note | RESPONSIBILITY: Nominated Authority
label | 249354c1-6db3-5e14-aff6-d033594a6a1f |  | note | ---------------------------------
label | 20e2c0c6-fec4-5643-9a2a-2d07330bbaec |  | note | VERIFYING DOCUMENTS:
label | a429cdb7-91ac-5952-bf05-eee6a2bac67d |  | note | This ITP
label | 3fcb9b40-a31b-56bc-adb5-036189305105 |  | note | Attach Inspection record
date | 2f98c48e-6edc-59d2-a7ba-87898266fe4f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 As Built Information
label | 48796809-da90-5ef8-b819-d095dab9c113 |  | note | REFERENCE: Section 701.10
label | 081ba7f1-0a9a-50e5-8e1b-cf589fbf98fc |  | note | ---------------------------------
label | 00141b82-678e-523e-8877-c7cc3efe2597 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage is within the tolerances specified in 701.10
label | bd8d4df5-e55d-5a75-b525-8a4aecfba789 |  | note | ---------------------------------
label | 7cc3b521-5216-5d8a-b287-597d3ad9e499 |  | note | METHOD: Document Review
label | 1ce55bc9-0394-538d-871a-83ca85a6d174 |  | note | ---------------------------------
label | 22c7c124-c0d8-565b-b961-a7b01e77d2ad |  | note | FREQUENCY: Each lot
label | 05da4a4e-c905-58e1-9ec4-6d182e89e495 |  | note | ---------------------------------
label | a61c2355-dd35-57eb-b4b6-c747d2e38e58 |  | note | CATEGORY: IP
label | b8965b1c-d73c-5990-ac40-858c00230bfb |  | note | ---------------------------------
label | 47950599-6932-53d6-920f-0b306013bbc6 |  | note | RESPONSIBILITY: SE
label | 4494bc3d-d4c6-5769-99ed-dcdb10c19075 |  | note | ---------------------------------
label | dd0c8171-f023-5c45-aefe-8cafbdb8b81e |  | note | VERIFYING DOCUMENTS: Attach Survey Conformance Report
date | 8193a011-7cf0-54bc-a7d8-54084df7c2a7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | 7282d987-74e1-598c-b48a-ac8e0d0d9fa7 |  | note | REFERENCE: MRPA Quality Management Plan
label | a0aa31ed-567e-549b-b6a9-6c9db4f99509 |  | note | ---------------------------------
label | 58939b71-f09f-5147-9df1-c2b6fa7aae66 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder
label | bd757316-40c7-520f-b8b2-b538e23b49b3 |  | note | ---------------------------------
label | faeac183-b317-53b4-93ce-10fa785b2b8f |  | note | METHOD: Document Review
label | 5725ff7b-27f6-5efb-8770-958fc629bf06 |  | note | ---------------------------------
label | 5d2e5fed-b16d-5b89-8561-7957647bf728 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 62d298c7-3a73-5a4d-8add-e422b03b5af9 |  | note | ---------------------------------
label | 08cc5676-d90d-55f0-ac31-4bdafac9b211 |  | note | CATEGORY: HP*
label | 7bc906e3-8b2d-5ba3-9575-90f35cbbe589 |  | note | ---------------------------------
label | 48846afc-24e4-56a9-8f11-99aae2179fd1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e8b09220-5dbf-53b0-a2ac-0a84d2cf6e69 |  | note | ---------------------------------
label | 7ff47de5-2b43-55ba-be2d-4a6c98c34d73 |  | note | VERIFYING DOCUMENTS: This ITP
date | d80159cb-e873-59e7-a5c6-d5c44bc799b7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | aaa886a7-9224-551b-83ed-a507a443a674 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | b6b1953f-c577-592c-95d2-7f1f15ea7bdf |  | textbox | Name:
text | 805d8c22-d1f8-5270-ac6a-526bd44ba46a |  | textbox | Position:
date | 1704ad4a-c42a-59f0-85a2-e5925c9d132c |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-074-STR-CAMMS-Precast Super T Installation | itp |  |  |  | Yes | ITP-074-STR-CAMMS-Precast Super T Installation Rev 0 | 875c7700-6946-41c7-937a-a7aa6ca0640b
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 0a48c983-0012-5e5c-9eca-219accacf60b |  | note | Document Title: ITP-074-STR-CAMMS-Precast Super T Installation
label | 505f944c-96bd-5461-a251-ac3a6d952825 |  | note | ITP Description: CAMMS-Precast Super T Installation
label | 225a5e9e-6c96-54eb-b2e0-1422828cfa71 |  | note | ITP number: 074-STR
label | dcc3cea2-45ca-506a-b09e-e5459ce9ae5c |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 018612b1-1239-574c-88a9-80f59cb46c3f |  | note | Discipline (e.g. CIV/STR/RAIL): 093-Rail
label | b6bd430a-cf3f-5d15-b5e0-63dc5f0b6f01 |  | note | Revision Number: 0
label | 218fdfbf-fe18-55f4-8428-0ab3e31228f3 |  | note | Revision Date: 5/10/2023
label | 0cc0675c-f8bc-5e01-9420-812b9bdfa5e7 |  | note | ITP created by: VM
label | 64144f84-d570-59ea-ab36-9d44ebba00b0 |  | note | ITP approved for use by: VM
label | c85d3989-e28e-53a5-a187-f278520cdc67 |  | note | 1.1 Non Dependent
label | 6ecc3324-7c05-5d14-8b1c-d92b08289fd2 |  | note | Reference: VR 652 June 2010
label | 9efc312d-1491-5101-b7e8-0ba20497450f |  | note | 1.2 Non Dependent
label | 9e95072d-d99a-5bd6-9187-a344f7d7abf7 |  | note | Reference: VR 656 June 2010
label | 21962194-f885-5142-ad65-190e90eb6516 |  | note | 1.3 Non Dependent
label | d98f51d4-349f-544c-8518-eabc34971400 |  | note | Reference: VR 610 February 2020
label | 33595337-f5f8-5ccd-a670-539ca1fd5ea1 |  | note | 1.4 Non Dependent
label | 9b8016ba-8c4a-5ae1-8471-078809773c68 |  | note | Reference: VR 620 May 2009
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Epoxy bedding
label | c8a78e47-0b86-5142-9f3e-93d75f4b6297 |  | note | REFERENCE: IFC Drawings MRP-052-C-SME-DRG-31-MPK-CBR-1112
label | e83a48b7-dcf7-5e34-af3b-c2c73402758b |  | note | – – – – – – – – – – – – – – – – –
label | 30c21991-8021-5605-9223-940409c193f0 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 14fcba68-87da-556c-b7fe-dc4ffaa01c11 |  | note | i. minimum compressive strength requirement as the Expoxy beeding is used to ensure the taper plate fullyengaes with the Girder.
label | cb9ac87d-dbd1-55d4-b830-b0a4136f24b1 |  | note | ii. Can be applied in IFC specified nominal thickness (1mm)
text | 9de36c8f-b7c6-506c-9bb0-956199e5f226 |  | textbox | Enter: Teambinder Material Approval number
label | 3e6742a6-281b-5036-a902-787e7c2a335b |  | note | – – – – – – – – – – – – – – – – –
label | 8c4d8bd7-7061-5b6c-8944-9ed3d73d08c3 |  | note | METHOD: Document Review
label | b1ab674a-3124-5406-acff-9b6e1056928c |  | note | – – – – – – – – – – – – – – – – –
label | ad3c3c33-98e3-5c44-9131-97793c03fb1e |  | note | FREQUENCY: When applicable
label | b997e147-a6f3-51d0-9d62-0a154effc41e |  | note | – – – – – – – – – – – – – – – – –
label | 71979815-0905-53dd-8d24-3e9473fa3566 |  | note | CATEGORY: HP
label | 5bf05e29-62ab-5182-9464-fc9c5ed03919 |  | note | – – – – – – – – – – – – – – – – –
label | b743c8c7-3b33-519a-83dc-a4145d158e40 |  | note | RESPONSIBILITY: Nominated Authority
label | 27d93f02-9f6c-58fa-854b-9e642606859e |  | note | – – – – – – – – – – – – – – – – –
label | 5e57d048-38d7-59ea-94df-c50ae06e3d3b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 627fc17a-e163-5f40-9ffd-7b1aff93a90a |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Bolts
label | c001dbd6-0fe6-5fd0-be1f-52702e897099 |  | note | REFERENCE: IFC Drawings MRP-052-C-SME-DRG-31-MPK-CBR-1112
label | de24fa5b-61b9-5d10-bc13-b47ed30e10d6 |  | note | – – – – – – – – – – – – – – – – –
label | e427ae9a-0401-5433-a2a7-4a68a2e6d723 |  | note | ACCEPTANCE CRITERIA: M16 property calss 12.9 Zinc Coated countersunk socket cap screw
text | 6102600e-3dc3-5465-9a5c-289afca6aa4a |  | textbox | Enter: Teambinder Material Approval number
label | 38583a86-de24-5007-934d-432347b384da |  | note | – – – – – – – – – – – – – – – – –
label | 58c98ef1-1460-5124-8da6-cb92e663f16c |  | note | METHOD: Document Review
label | fc819b19-3a6a-597c-a333-ef24ff3f8c6a |  | note | – – – – – – – – – – – – – – – – –
label | 2b89c10e-aeae-5578-8a41-38c7334fb1d8 |  | note | FREQUENCY: When applicable
label | 70192c26-51c7-5a19-a137-2885354b6085 |  | note | – – – – – – – – – – – – – – – – –
label | def26c24-b0db-5009-9eda-9f8c608d5007 |  | note | CATEGORY: HP
label | 81b2d21a-2cc8-5d61-bac4-f86e8779a07e |  | note | – – – – – – – – – – – – – – – – –
label | ea42b738-9fcb-59c9-be9b-00568fcb0968 |  | note | RESPONSIBILITY: Nominated Authority
label | 386918cf-24c0-5150-9192-58c4017205a6 |  | note | – – – – – – – – – – – – – – – – –
label | 8be3738b-b8fa-5861-96b0-174331d9f9b8 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 1638e4ad-8b9d-5b75-8b6c-9e28e4a10b0a |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Precast Elements
label | 61a754a4-890d-5d39-8553-edad3d1f6e63 |  | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.473 (March/June 2019) 620.03
label | adc2ce3b-658a-5f49-91a7-707f75082c66 |  | note | – – – – – – – – – – – – – – – – –
label | a239a3d2-52f3-591d-9060-1c4186442836 |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | dd97944d-3237-5ba7-9d2e-971dd597a456 |  | note | i. Certificate of Compliance / Birth Certificate
label | 60c8f89c-37f6-5c08-9eb7-f98319c6ca75 |  | note | ii. Compressive strength test results
label | a89c5718-b6b7-54fd-8f4b-53493343fc74 |  | note | iii. Precast Lifting Design
label | acb07057-98b4-5d9a-924d-9b20236264ba |  | note | iv. Pre-pour check sheet / ITP
label | 631f8861-789a-51fe-818f-7920fa1c34e1 |  | note | v. Pre-stressing check sheet / ITP
label | c2e0a0fb-9ffe-5c69-8415-35f4662e7758 |  | note | vi. Post-pour check sheet / ITP
label | 5fbd9c39-1ade-512f-9cbb-6c92cd2dd0ba |  | note | vii. Covermeter check record
label | 10226c72-cd91-5f1b-87e0-b8e088330303 |  | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
label | 27b9edca-12a4-572c-aa91-662ebe2d7b30 |  | note | Note: Different revisions of 610 have different clause numbers
label | 47215d29-d386-54ea-bec3-ad56cfee904c |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder
text | b2031e16-b7ce-5565-a057-d7bfd28ad60b |  | textbox | Enter: Teambinder MDR Lot number
label | 2d1b5125-9f8f-5019-b1ba-f89d68756d50 |  | note | – – – – – – – – – – – – – – – – –
label | da49aa55-d92a-53ff-b354-1c7ae918568f |  | note | METHOD: Document Review
label | 1c1448fb-a618-58e3-9ddb-9680bed03ba6 |  | note | – – – – – – – – – – – – – – – – –
label | 8570c1f5-a605-5398-879b-5518eb9fdb66 |  | note | FREQUENCY: Each element
label | bd71febc-420f-540f-862f-45e0e3eafd60 |  | note | – – – – – – – – – – – – – – – – –
label | d74623a6-9bc4-5973-aace-79155350e423 |  | note | CATEGORY: HP*
label | 0a438998-ff63-5237-bb20-96de6eceb3b9 |  | note | – – – – – – – – – – – – – – – – –
label | a2b2185a-6ed3-527a-b62a-31f7419a7553 |  | note | RESPONSIBILITY: PE/SE/SPE
label | 542a831d-5db0-541d-8978-06a90eac9ec3 |  | note | – – – – – – – – – – – – – – – – –
label | cfbeb12c-fc31-502e-a210-3b4cdcde4eda |  | note | VERIFYING DOCUMENTS: This ITP
date | 86668b69-de6c-5de0-9924-3b17762c399b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Elastomeric Bearings
label | 44960410-b221-5867-a83e-3be6ed3750b2 |  | note | REFERENCE: IFC Drawings 652.02, 652.03, 652.04, AS5100.4
label | 1f6ea7ef-b8d7-5af6-a86b-f98281298a52 |  | note | – – – – – – – – – – – – – – – – –
label | 5b359cd0-a984-5596-a528-d0199bfbc7cb |  | note | ACCEPTANCE CRITERIA: Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4.
label | bd7bc42c-43c2-5888-a047-82e62e1d466f |  | note | Tolerances:
label | 34c805d3-21d5-5c1d-81ec-2d01ab63dccd |  | note | ○ Dimensions in plan = +4mm, -2mm
label | cd062295-d35e-54c8-bc44-6483b85d115f |  | note | Thickness =
label | 2a919ac0-2c79-5800-834c-e368d26752c3 |  | note | ○ ≤100mm = ±2mm
label | efe2a1c7-052d-5860-9959-1a9efec41ab2 |  | note | ○ >100mm ≤ 150mm = ±3mm
label | 66ed1828-0ba8-50a5-9220-a24187279951 |  | note | ○ > 150mm = ±4mm
label | c22645fb-94b1-5920-be6b-37c843cd55d7 |  | note | Testing:
label | 8ce03773-2d7a-53f3-aab4-a1f02041a72e |  | note | ○ Each bearing tested under compression
label | c7fb565c-b45e-5bc6-8308-ca9ba90db540 |  | note | ○ Batch tested for shear stiffness
label | a8e8bf74-d052-5baa-9422-2455dd067d9a |  | note | Attach: Elastomeric Bearing Test Reports
label | bd4015e6-c72c-5427-9cd0-af03730044e4 |  | note | Attach: Elastomeric Dimensional Records
label | f08c0bff-2dae-5dae-94dc-1b0f4657b84f |  | note | – – – – – – – – – – – – – – – – –
label | e726e936-0931-5c56-b3c6-443322877257 |  | note | METHOD: Document Review
label | ca8b8a50-1783-5add-880e-e6b7a2fdca55 |  | note | – – – – – – – – – – – – – – – – –
label | e5d6ab36-9024-5f6f-bead-c4dd4e5cfa77 |  | note | FREQUENCY: Each element
label | b8ff6bb7-3c31-5a25-b02e-d5f5808d3546 |  | note | – – – – – – – – – – – – – – – – –
label | d7861cfa-5e09-56ff-87d4-3494e5df5a31 |  | note | CATEGORY: HP
label | a013569b-1fb4-52f9-a20a-51e62c2ceb14 |  | note | – – – – – – – – – – – – – – – – –
label | 8d1a5201-d740-595d-a60e-d924eabdb4da |  | note | RESPONSIBILITY: PE/SE/SPE
label | f4b22893-0583-5bb1-8c3b-2680ab6c0f04 |  | note | – – – – – – – – – – – – – – – – –
label | e2116f17-2e71-572c-b77e-055da46a14c5 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0f245200-fd54-554e-9a9b-39ecae23a5e3 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Tapper plates
label | 6970fa04-1d92-5d51-ab64-ddceeb9673ca |  | note | REFERENCE: VR 620.05
label | 9fd9abc4-3acd-5582-a3dd-fedb58a6d7f8 |  | note | – – – – – – – – – – – – – – – – –
label | 726b0ff1-a28e-56ac-91a7-ed2362a2e20d |  | note | ACCEPTANCE CRITERIA: Material for sole plates and bearing retainers shall be of structural grade steel complying with the requirements of AS 3678. All surfaces and edges of sole plates shall be finished smooth and bearing surfaces shall have a maximum out of flatness of 0.4 mm.
text | 928c7b81-eefc-5fde-8cb0-6a53011e1bfa |  | textbox | Enter: Teambinder MDR Lot number
label | 106c8145-9b27-55d9-8293-67e459b19341 |  | note | – – – – – – – – – – – – – – – – –
label | 14751350-4d30-55a5-b21d-1354ddd26ff0 |  | note | METHOD: Document Review
label | 916c72c7-258c-5715-9e78-e25efe2e6fb5 |  | note | – – – – – – – – – – – – – – – – –
label | 2ea2e69f-546d-59fd-bf1d-764aad9315cd |  | note | FREQUENCY: Each Plate
label | df5bf641-2a2b-5336-92de-0e73c765b031 |  | note | – – – – – – – – – – – – – – – – –
label | 0c97b1d9-3d41-5ed9-a4a4-9ab5566f8760 |  | note | CATEGORY: IP
label | 8cb26604-a3c5-5669-942f-a4a0a557fc78 |  | note | – – – – – – – – – – – – – – – – –
label | f9d3df92-2102-570d-8a7d-c3da9ef8857f |  | note | RESPONSIBILITY: SE/PE
label | 5be94bc8-2bfe-5c47-a4d7-e4c251145959 |  | note | – – – – – – – – – – – – – – – – –
label | a7a5a367-fcde-5e07-9d4e-cc0451458952 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3a0bba32-cf75-5c01-9444-ef41e005c016 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Bearing Plates-Check
label | 354a2592-1d8b-50a7-bbcb-c823524c643c |  | note | REFERENCE: IFC Drawing MRP-052-C-SME-DRG-31-MPK-CBR-1112 Note 3
label | c670975d-fb17-5cdd-b956-0bb8ab2a98bb |  | note | – – – – – – – – – – – – – – – – –
label | b988bfee-ef30-5ccf-bb27-2ecff99ce5b6 |  | note | ACCEPTANCE CRITERIA: Bearing Plates shall be inspected after fixing to girders and prior to the erection of the girders. Ensure the plate and plate orientation are correct
label | c42ae47e-415d-509a-b39e-5dd30bc2d2ed |  | note | – – – – – – – – – – – – – – – – –
label | 74ffc893-5c66-527a-b0fc-3b175f612ded |  | note | METHOD: Visual
label | 29124a02-6f5b-5344-8959-385473b15614 |  | note | – – – – – – – – – – – – – – – – –
label | c520c8a5-8a56-5ec7-98e4-2e1fc0cb463e |  | note | FREQUENCY: Each Tapper plate
label | 87b35cc6-8f7a-53ee-8909-9d081cff2bd1 |  | note | – – – – – – – – – – – – – – – – –
label | 047d08c3-4240-52f1-86bd-f9e86e13b802 |  | note | CATEGORY: IP
label | 48a40e2e-60a4-5dfc-94de-ae085e91bea2 |  | note | – – – – – – – – – – – – – – – – –
label | 05f8b1ae-4d60-5811-a38a-7b59cfc154b9 |  | note | RESPONSIBILITY: SE/PE
label | 9e82b9a9-fdd6-5299-88a1-b7b6d4081173 |  | note | – – – – – – – – – – – – – – – – –
label | 9355a67e-1b9c-5614-8ece-c50b1bb88338 |  | note | VERIFYING DOCUMENTS: This ITP
date | d8bdcdd0-6cb3-5ffa-ae5f-3aa4ae33ef69 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Crosshead / Pedestal Tolerances
label | b8ba50c1-eeac-5037-bdeb-2919ffc57876 |  | note | REFERENCE: Survey As-builts / Survey Report
label | e47ab6c5-d71e-56a0-94f7-e47d0069e789 |  | note | – – – – – – – – – – – – – – – – –
label | e86378fa-9b07-5107-bc26-dcbfc270b79b |  | note | ACCEPTANCE CRITERIA: Re-check that the As-built dimensional tolerances comply with the requirements below:
label | 98d105a3-eb10-5e3d-b279-784b795367c7 |  | note | ○ Reduced level ±2.5mm
label | a83610e5-7613-5611-9ea7-acd6e5a39825 |  | note | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | a4f14a2c-daff-546b-9f41-cc24994e8e71 |  | note | ○ Deviation from flat surface ±1mm
label | b47f6a54-5bbc-5241-87f9-3f2db00322e8 |  | note | – – – – – – – – – – – – – – – – –
label | ef6108cc-251f-5f3b-82fa-cb8e5887e9be |  | note | METHOD: Document Review
label | 50f07ba5-9567-5892-a4a4-911dd00c7fd5 |  | note | – – – – – – – – – – – – – – – – –
label | a14d45a3-b5ad-5d6b-b944-c10ce1bd3060 |  | note | FREQUENCY: Each element
label | f9d15ed9-25a5-52d6-ae47-6456f1270cfc |  | note | – – – – – – – – – – – – – – – – –
label | 0d3ad228-5884-5660-af03-d0df7d158c39 |  | note | CATEGORY: IP
label | f691f6fe-87ea-5ca9-a71f-bf756a37df11 |  | note | – – – – – – – – – – – – – – – – –
label | 915b74a0-da69-55fe-b0bc-a9331cb559bf |  | note | RESPONSIBILITY: PE/SE/SPE
label | c01f1a39-b5b9-54ff-a2a5-b159a501fa71 |  | note | – – – – – – – – – – – – – – – – –
label | ac16b116-a7b9-514d-b9ad-fddebf07af10 |  | note | VERIFYING DOCUMENTS: This ITP
date | 67128f34-7e65-5b42-a3fd-4be4614eb5f2 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Elastomeric Bearing Placement
label | fc709627-f934-5709-968d-b53f53910509 |  | note | REFERENCE: IFC Drawings VR 656.05
label | 9acb16e5-f5ec-5666-9062-f1bc6031d49f |  | note | – – – – – – – – – – – – – – – – –
label | fae6f011-485a-5255-b804-eaa0a16369ea |  | note | ACCEPTANCE CRITERIA: Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances.
label | b23a9770-300e-508d-98e4-9a8512a6033d |  | note | Tolerances:
label | 54a01722-6bdd-52ff-b772-427ef66c10aa |  | note | ○ Plan position: ±2mm in any direction
label | f0be4a87-a63a-5a19-9f5c-684bc0de463b |  | note | ○ Level: ±2mm
label | e5a1a7e5-6369-51ee-b33b-5def166dd409 |  | note | Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report
label | bfea7015-c45c-522f-a01d-2b361295d402 |  | note | – – – – – – – – – – – – – – – – –
label | 1e51e3ab-5413-5bf2-a1be-98fe09da0378 |  | note | METHOD: Measure, Visual
label | 3d7d27da-ffbe-5103-b664-66fbf8558aae |  | note | – – – – – – – – – – – – – – – – –
label | 4ff63eb9-b70e-5a3a-a68f-edd38b5f4df1 |  | note | FREQUENCY: Where applicable, each bearing location
label | b75c3a85-a313-5960-9e58-4187408e5730 |  | note | – – – – – – – – – – – – – – – – –
label | a1fc238d-cc98-57c0-8391-65fca452aeb8 |  | note | CATEGORY: IP
label | 85e96bf6-3c15-5b6c-85e0-225246d5ea3d |  | note | – – – – – – – – – – – – – – – – –
label | 5c4d3e50-0efb-506d-bd5c-27b6cd86f63f |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 6bdc7302-de1f-58ab-8461-13c26b8ec89f |  | note | – – – – – – – – – – – – – – – – –
label | 628049e4-c81d-58aa-b732-ebd29ff4ca74 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5e11e5e4-20a9-5c9d-8d0d-1d86a0f21010 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Restraining Blocks-HDPE Packers
label | 4b0f5a8b-966d-5dec-ae1d-8a01f3219e30 |  | note | REFERENCE: IFC Drawing
label | e8175e80-02b3-500f-ad35-868b7ba0136e |  | note | – – – – – – – – – – – – – – – – –
label | 91827ca7-ffbf-5472-85c4-15c49b94c8e1 |  | note | ACCEPTANCE CRITERIA: 200x200x35mm HDPE packers are to be installed in designated recesses on restraining blocks.
label | 74670c7b-635e-5bc7-b511-3513564783a9 |  | note | – – – – – – – – – – – – – – – – –
label | f986b19e-5ffa-5412-b1b8-2adeffa25628 |  | note | METHOD: Visual
label | 916b0d57-69d1-5c3a-9e07-7dd7e457a0db |  | note | – – – – – – – – – – – – – – – – –
label | 95217e9b-8e18-50de-89fa-89c33bace420 |  | note | FREQUENCY: Each restraining block
label | 7376e8dc-5efd-5bed-8205-20e44745ebbe |  | note | – – – – – – – – – – – – – – – – –
label | c27acb41-706c-5b96-8d36-2dde83afa740 |  | note | CATEGORY: IP
label | f702e2df-9aea-595e-bf0c-cae9947754b4 |  | note | – – – – – – – – – – – – – – – – –
label | 9be8fa0e-071c-5ace-add1-09b0005f0663 |  | note | RESPONSIBILITY: SE/PE
label | 71a020fe-1a12-56ee-a7a8-4fd7265aed2b |  | note | – – – – – – – – – – – – – – – – –
label | 6d2e5ab4-3e62-5af9-be05-3cf7b752ffd9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 325f6361-b268-5573-ae8c-b226d0780211 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Precast Handling
label | d282ec04-c672-559a-8d20-f786f13c01d7 |  | note | REFERENCE: 620.07 Crane Lift Study
label | 707adac6-5a2c-5d75-abba-f35701751378 |  | note | – – – – – – – – – – – – – – – – –
label | 216e8aff-3293-5a59-8a74-4bbd0eca3bf1 |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | 097dab8d-f319-5435-88ce-b03b991a0ed8 |  | note | – – – – – – – – – – – – – – – – –
label | da527464-9b68-5147-999e-28b54517de81 |  | note | METHOD: Visual
label | 2b27942b-cead-5252-9bce-3f6cfe6392fd |  | note | – – – – – – – – – – – – – – – – –
label | 44683602-ee0e-56b9-8444-573f82a144aa |  | note | FREQUENCY: Each element
label | c8aea3a4-a2dc-5df0-a609-df50877a2485 |  | note | – – – – – – – – – – – – – – – – –
label | cbd1360b-3759-5393-b217-90ccd6c9064e |  | note | CATEGORY: IP
label | 973db2b6-f180-59f3-a669-3ea4f34f2ebf |  | note | – – – – – – – – – – – – – – – – –
label | 1b97d93e-679e-5b4e-a935-1f279e622c8c |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4a488b50-2410-5578-af79-308006d584cb |  | note | – – – – – – – – – – – – – – – – –
label | 7ee23b41-88cf-52e3-9df5-57cf60fd2e18 |  | note | VERIFYING DOCUMENTS: This ITP
date | 24df1648-b3fc-593f-91a3-718c95360160 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Precast Placement
label | 53227dca-479c-59f3-8b33-28dfdfee169a |  | note | REFERENCE: IFC Drawings 610.27
label | 908cf177-5070-52b2-bb10-f9fef27ed0f7 |  | note | – – – – – – – – – – – – – – – – –
label | 553f2d31-4e51-5738-bd0b-0ce31533c3b4 |  | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | 71a5dca7-31b7-519c-b4a0-f36a6126d323 |  | note | ○ The nominal gap between elements is as per the IFC Drawings.
label | 21c1b393-9296-5ab0-b727-b9b8bca07093 |  | note | – – – – – – – – – – – – – – – – –
label | 01421581-6cf5-5baf-b2e8-2251ad05669a |  | note | METHOD: Measure, Visual
label | cbdc1f04-7fd0-5df4-b75f-6b196b7175de |  | note | – – – – – – – – – – – – – – – – –
label | d6ceeeb0-ac15-5293-b16f-9479b2b331c8 |  | note | FREQUENCY: Each element
label | 50ecec0e-0610-54de-956b-2c98082144ed |  | note | – – – – – – – – – – – – – – – – –
label | c08e153e-cbed-5487-b7b7-04164ce6e3a9 |  | note | CATEGORY: IP
label | a6a470c2-f18c-5f4e-8e4b-025ec29320ff |  | note | – – – – – – – – – – – – – – – – –
label | 8a347efb-108b-5e9b-bc0c-f1af66670237 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 57f16d85-d084-5f54-828c-61f2edc4a574 |  | note | – – – – – – – – – – – – – – – – –
label | d5116e4c-9bc1-5fb4-840b-5aab616b216c |  | note | VERIFYING DOCUMENTS: This ITP
date | d466ebe6-3594-59aa-8c97-de48e7f5d75d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Precast Traceability
label | beebb05d-f10e-54ba-9066-dfbfa3047085 |  | note | REFERENCE: 620.09
label | 6197bbc9-4dbb-5b37-89c7-a07646b2dce4 |  | note | – – – – – – – – – – – – – – – – –
label | 6158d772-7566-5612-b139-944f1064e602 |  | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | bd7464a4-8b6b-5093-a8f4-ea1b43de789e |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | d86df572-7bcb-551a-82ac-c65f429d6ffe |  | note | – – – – – – – – – – – – – – – – –
label | f711abdf-f89d-5166-9fa4-16880a963d3f |  | note | METHOD: Visual
label | 345f842f-b67e-582f-ae7c-1a0f8edd296d |  | note | – – – – – – – – – – – – – – – – –
label | 2dfb6fe3-6bd9-5c2f-b029-39fd32ab2318 |  | note | FREQUENCY: Each element
label | f6c5a16f-031e-5f20-8cf5-678e91d45b04 |  | note | – – – – – – – – – – – – – – – – –
label | 940c9414-a7ac-5413-9a6f-295910b235c1 |  | note | CATEGORY: IP
label | a6b2b72d-6628-5d27-9ad5-c64f07e3da7a |  | note | – – – – – – – – – – – – – – – – –
label | a303d35d-b4c7-582d-a97c-76070c2871cd |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1e2f7d9e-2717-577c-80a9-f72cddeafab7 |  | note | – – – – – – – – – – – – – – – – –
label | 0f851020-62db-583f-bf4f-e7b2e270d17b |  | note | VERIFYING DOCUMENTS: This ITP
date | 001aeed8-925b-52ec-b867-ce16e40f09b7 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey
label | 52557e39-e6c3-5876-a529-af58119849b6 |  | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472 (March/June 2019)
label | 0c12c109-db2b-542e-a33c-d61df342000e |  | note | – – – – – – – – – – – – – – – – –
label | fb907f0d-cfad-50b9-91d4-f45c6e35e1f2 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
label | 7f2293d0-8b77-5867-a9ea-c02d77a87c01 |  | note | Attach: Survey As-builts / Survey Report
label | 81fafe3b-47c4-5882-9da6-bc42324c2bfd |  | note | – – – – – – – – – – – – – – – – –
label | bfd68a2c-9d86-5f51-8781-dfdec26d6180 |  | note | METHOD: Document Review
label | 1e441e99-f36c-5050-ad3c-f14c6cb2885b |  | note | – – – – – – – – – – – – – – – – –
label | 347ba275-db3e-516b-bc52-2925fde1259d |  | note | FREQUENCY: Each element
label | e17583db-e593-5747-89aa-beb56117f52a |  | note | – – – – – – – – – – – – – – – – –
label | 423d193b-23fd-5384-9d85-53a27b48d12c |  | note | CATEGORY: IP
label | 75a3da20-afeb-553e-ba3d-c013f95d8a6e |  | note | – – – – – – – – – – – – – – – – –
label | 8df8623c-080e-523c-b54b-9914e7ac77d8 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | fd156e82-5b28-56f5-b98f-f4cacfebb1de |  | note | – – – – – – – – – – – – – – – – –
label | 4312c39e-0175-540f-9f7b-0af87260f68c |  | note | VERIFYING DOCUMENTS: This ITP
date | 8cc938d7-a239-5e0f-ab46-2b6c73f0a403 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | cf8c73ce-3923-5e13-9130-9bdd9e921717 |  | note | REFERENCE: MRPA Quality Management Plan
label | 883a9bfa-17bd-5c63-a8c7-10bec724d609 |  | note | – – – – – – – – – – – – – – – – –
label | 27ddc896-9aae-5c20-82ad-7ae4c37cfc26 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 55ef7643-b65d-5a2d-9906-170f96242ce0 |  | note | – – – – – – – – – – – – – – – – –
label | e8c82db2-54a9-5e57-8ae2-ed6b84807d92 |  | note | METHOD: Document Review
label | d865108f-a706-5a9a-bb61-b1025c2300a6 |  | note | – – – – – – – – – – – – – – – – –
label | bcc6c418-01df-5e09-865c-1ae42663c38e |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | b8c3dade-3628-5156-a4b3-356b68596b0d |  | note | – – – – – – – – – – – – – – – – –
label | 74f74944-a7ed-5247-bd34-957d1409e084 |  | note | CATEGORY: HP*
label | f86ceeac-fcad-5bb5-b046-4433d99df220 |  | note | – – – – – – – – – – – – – – – – –
label | 22b3693e-c0dd-5f85-9e94-a46db9b62bae |  | note | RESPONSIBILITY: SE/PE/SPE
label | 64ce0201-a076-5f30-88d9-7d1e1c6956c3 |  | note | – – – – – – – – – – – – – – – – –
label | 9df863a9-0dba-52f5-b782-6f15148bfd4f |  | note | VERIFYING DOCUMENTS: This ITP
date | 4c650473-af2c-5fd1-90c6-29b4292c0fea |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | cfe9e132-9d97-5e6d-9c8a-137e219eca53 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 291487b7-390d-5298-a013-6d683564322d |  | textbox | Name:
text | 1ddf4c17-c13f-50ed-a517-dc0016b83ed0 |  | textbox | Position:
date | 8cd8f80d-0aec-5053-a135-499fcdf61b14 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-105-STR-CAMMS-Bridge Expansion Joint Rev 0 | itp |  |  |  | Yes | ITP-105-STR-CAMMS-Bridge Expansion Joint Rev 0 | 87e87c72-a378-447f-a331-ec8cc154175e
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Reference Documentation
label | a8027ad4-9952-5bd6-8107-d4cbc35feb49 |  | note | Document Title: ITP-105-STR-CAMMS-Bridge expansion joints and waterproofing
label | c2efbaf6-9499-5e88-b7d7-e634710d7990 |  | note | ITP Description: CAMMS-Bridge expansion joints and waterproofing
label | 1ec4a8e1-b7a7-56e6-b9f4-851311de0056 |  | note | Discipline (e.g. CIV/STR/RAIL):105-STR
label | a8a79c90-f8d2-50fe-b3cb-da8ce29d83fa |  | note | Revision Number: 0
label | 26128c8b-992c-56ce-b621-9c863bc2bad0 |  | note | Revision Date: 10/11/23
label | 7809fe74-bec1-5b84-8159-f286efbf0038 |  | note | ITP created by: Isaac El Zayat
label | 281706c1-1c53-5c81-b834-02f447e544a4 |  | note | ITP approved for use by: Victor Mira
label | 604e9fd3-e314-5216-bb3d-b3b029f55880 |  | note | 1.1 VicRoads Section 660 January 2018
label | 6c5b92ef-4b13-5a00-9c25-7b8971133b16 |  | note | 1.3 AC-AR Installation Guide
checkpoint-group |  |  | section | 2 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.2 - Expansion Joint Components
label | f733d9a6-7c80-5af2-adb3-49830af0a9b4 |  | note | REFERENCE - IFC Drawings VR 660.03
label | 0d972b8e-f044-5407-b562-8e4d9a4c58e7 |  | note | – – – – – – – – – – – – – – – – –
label | fbece130-aa6e-5f5c-9516-27be5ff72fc6 |  | note | ACCEPTANCE CRITERIA - The Contractor shall supply all expansion joint components including joints, seals, inserts, anchorages, cover plates, waterproofing membrane, drainage system, bedding mortar, nosing, edging and all adhesives and sealants required for the installation of the joint system in conformity with the supplier’s recommendations.
label | a1a9ca1a-3a19-5910-8387-d8376e6fd746 |  | note | Attach Delivery dockets/Proof of purchase
label | 103963b3-3a7e-514a-91a6-f77fa1b75b21 |  | note | – – – – – – – – – – – – – – – – –
label | f6093d15-7359-58d1-aa84-db89d66efa03 |  | note | METHOD - Document Review/ Inspection
label | df7ce7f1-6675-5e72-bcab-8289f233b2bb |  | note | – – – – – – – – – – – – – – – – –
label | af13b5f7-093e-5420-b16b-d5a52e3ae2ad |  | note | FREQUENCY - Where applicable, for each element
label | 8548b200-5a80-5036-b122-e9be9c461977 |  | note | – – – – – – – – – – – – – – – – –
label | cc06f59d-7d28-5c92-ac15-4f631d4f25a5 |  | note | CATEGORY - IP
label | 81f747c1-db94-59e6-a55b-2a6e92076d03 |  | note | – – – – – – – – – – – – – – – – –
label | 41296d9a-5285-5501-b3ea-6ca923da8d31 |  | note | RESPONSIBILITY - PE/SPE
label | 933a2e13-8929-5044-b413-82e6ce1e6dc6 |  | note | – – – – – – – – – – – – – – – – –
label | 9be0df39-ee05-5bad-8ae4-b81b37d94f20 |  | note | VERIFYING DOCUMENTS - This ITP
text | 5e018f01-b8fc-5af5-a187-199638976a63 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3 - Preliminaries-Procedures
checkpoint-status |  |  | checkpoint | 3.2 - Expansion Joint Design
label | b2bde7ce-4df5-5e7a-8a05-ba108a703614 |  | note | REFERENCE - IFC Drawings VR 660.03
label | fda6eeef-f12d-56ba-856c-0886ead93648 |  | note | – – – – – – – – – – – – – – – – –
label | fca0eb2c-d307-5660-a4c0-6d6fc41cfeb2 |  | note | ACCEPTANCE CRITERIA - The expansion joint system shall match the drawings. Where applicable, the joint sealant shall match the Drawings and installation manual
text | fe990c05-4a5a-5c6b-bab2-bbd1a9b251ef |  | textbox | Enter: Specify the Joint type:
label | 70c33ce1-89e3-53f0-b758-c453495aca74 |  | note | AC-AR-125D for road P2-100D for SUP and Footpath
label | 8b718c1e-d645-54d3-bdda-139cc8d859db |  | note | – – – – – – – – – – – – – – – – –
label | e13b46be-ca92-54d7-946e-d7423291f8b5 |  | note | METHOD - Document Review
label | d8b3147c-cc06-5d21-a864-1c552c464113 |  | note | – – – – – – – – – – – – – – – – –
label | b650f351-2af8-5d4e-87d9-1b8fe83bceec |  | note | FREQUENCY - Where applicable, once, within 4 weeks of acceptance of tender
label | 27f121b5-cd64-54de-8774-8dd288ccf0e1 |  | note | – – – – – – – – – – – – – – – – –
label | 4c32be85-82e0-5e5a-abda-2a06ff19b679 |  | note | CATEGORY - WP
label | 2c6eace6-7fcc-53da-a218-4d18c4ad8061 |  | note | – – – – – – – – – – – – – – – – –
label | a548aa3d-f8b3-5d7c-ab95-699478e230a1 |  | note | RESPONSIBILITY - SE/PE
label | 1253f4e0-6419-5b95-b2a2-885ebe33199b |  | note | – – – – – – – – – – – – – – – – –
label | 1386e9c8-48ec-5e66-b888-4a237da3ec7c |  | note | VERIFYING DOCUMENTS - This ITP
text | 0e54caef-5b4b-5feb-9d46-54f89bfea5c4 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4 - Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Expansion Joint Installation Temperature
label | cfc555d6-92b4-5b44-9135-bf30b6b067fb |  | note | REFERENCE - VR 660.04
label | 6da5fb7c-931c-59ba-8636-da0876f1f6cf |  | note | – – – – – – – – – – – – – – – – –
label | 0087e04a-2bab-5e4d-8c8c-0b9246c396a1 |  | note | ACCEPTANCE CRITERIA - The bridge temperature shall be measured at the time of installation and where it differs by more than ±5°C from 20°C , shall be adjusted by the calculated values provided by the designers. Installation Temperature = [free text]
label | f09e5f8b-ab4d-5d71-9243-5e03f61cfcd3 |  | note | – – – – – – – – – – – – – – – – –
label | e0739bcb-a29f-548a-94ac-df4e39e4cd38 |  | note | METHOD - Measure
label | f720fe5d-94fe-5ba7-b230-f98efea553ea |  | note | – – – – – – – – – – – – – – – – –
label | 72492033-836d-59b2-9e0f-e3a39d562e68 |  | note | FREQUENCY - At the time of installation
label | 443395c4-d60a-54f5-9847-c412687af0c9 |  | note | – – – – – – – – – – – – – – – – –
label | cafe3d56-e13d-529c-9a3b-a9ab6938b1ef |  | note | CATEGORY - IP
label | 8fb0f596-73a0-53b3-9e5b-8de6ea6832b5 |  | note | – – – – – – – – – – – – – – – – –
label | fa5deae6-1419-5678-8046-27186cc1f4f2 |  | note | RESPONSIBILITY - SE/PE
label | 18499831-4aa2-5203-86fd-c3e30247648d |  | note | – – – – – – – – – – – – – – – – –
label | 114aa5ae-e10b-5d90-8ccf-ddf434eed91b |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 3ea2dd36-ff90-52dc-9bad-7a9650ca1bd3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Post-pour Inspection of Expansion Joint Bearing Surface
label | d4e4691a-d167-544f-8d3a-37e26577f3d9 |  | note | REFERENCE - VR 660.04
label | b877897e-495a-5962-b398-d3b6664d342d |  | note | – – – – – – – – – – – – – – – – –
label | b7bb47e9-0de2-5614-ae2b-5a51640dd6f9 |  | note | ACCEPTANCE CRITERIA - The faces of the concrete under the full length of the expansion joint shall be inspected for the presence of voids and other imperfections.
label | 8660e067-d11b-5df7-8c23-1c17462d59fa |  | note | – – – – – – – – – – – – – – – – –
label | b2ca34cd-2893-5de6-9499-3a09d5a237ba |  | note | METHOD - Visual
label | 8ec6810c-6914-5514-b9ce-d43db6332624 |  | note | – – – – – – – – – – – – – – – – –
label | 31afb989-ea0d-599f-95b7-55cf0f6cea9f |  | note | FREQUENCY - Prior to joint sealant (where applicable)
label | a443f14b-79e3-578c-8e94-7fa3760572fe |  | note | – – – – – – – – – – – – – – – – –
label | feabb7f5-6d26-5d6b-8c64-cf1911bdcb58 |  | note | CATEGORY - IP
label | 3a770eba-c925-56fa-9adc-30529ae12a4d |  | note | – – – – – – – – – – – – – – – – –
label | 4f35f135-63a1-52f1-b566-774bf5afeaf6 |  | note | RESPONSIBILITY - SE/PE
label | 0c49d853-26e6-5016-a385-cd81a4ecf0a9 |  | note | – – – – – – – – – – – – – – – – –
label | 01a6fad6-bfda-534a-b25e-133ca8469bcc |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | f3824843-adc4-53dd-ba58-7227a27fd811 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5 - Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Expansion Joint Placement- Anchor Bolts
label | 1034c829-8814-510c-9270-74b97e4ffc0a |  | note | REFERENCE - IFC Drawings AC-AR Installation Manual
label | a7861593-006e-57c1-8156-fbac0c28cc8d |  | note | – – – – – – – – – – – – – – – – –
label | ff8d0ccf-9242-5b1a-abf2-a4f643fc6159 |  | note | ACCEPTANCE CRITERIA - After concrete strength is in excess of 30MPa, the anchor bolts can be tightened via the snug tight plus part turn method or with a calibrated torque wrench. As per installation manual:
label | 52378a50-e26e-5267-9ecb-b26ce6502294 |  | note | Part turn method: Snug tight + half turn
label | 8a49e581-096d-5e1b-a496-04313b85f2db |  | note | Calibrated torque wrench: 400Nm
label | b22df80c-a271-5774-a879-67a8f04f85e2 |  | note | – – – – – – – – – – – – – – – – –
label | 9e64ed76-3f33-50db-8ffa-8b711c25b260 |  | note | METHOD - Measure Visual
label | 1e3b6839-8199-574e-8d57-eff9a77e0095 |  | note | – – – – – – – – – – – – – – – – –
label | e7bf25d4-3978-58c4-a752-62d9bde92ea2 |  | note | FREQUENCY - AC-AR 125D (Road section) joints
label | 0b4b3044-071c-5a58-818c-600176381cdd |  | note | – – – – – – – – – – – – – – – – –
label | ec5cbf2c-c82c-5d6e-aa9b-ef299143c3c5 |  | note | CATEGORY - IP
label | 728ff792-c1ec-5e56-abd0-51965d0fddba |  | note | – – – – – – – – – – – – – – – – –
label | ce2644ca-555f-5eb0-8708-f4c5c3733faa |  | note | RESPONSIBILITY - SE/PE/SPE
label | 8980c66b-7d85-577c-a424-90473ba5af59 |  | note | – – – – – – – – – – – – – – – – –
label | 67fb0abe-9d96-5af3-8f6c-fb7c821f69f7 |  | note | VERIFYING DOCUMENTS - This ITP
text | 1f032175-d8d1-52b4-b009-7fa10c56b409 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Expansion Joint Placement-Coverplate
label | 957539c2-4e66-5314-9f53-27bb4aebfb14 |  | note | REFERENCE - IFC Drawing
label | 295461e7-b4e1-5fdf-a9aa-17560e90d0b1 |  | note | – – – – – – – – – – – – – – – – –
label | b25d9ef6-8f10-5c41-bcb8-6bf5ba7a660f |  | note | ACCEPTANCE CRITERIA - Aluminium checker plate is installed with M12 Cuntersunk bolts as specified in the drawings
label | ab28af66-5e1f-5e0e-a76c-61fe6f706710 |  | note | – – – – – – – – – – – – – – – – –
label | d6beb434-ce53-5483-8f36-6bc0b30f3a3d |  | note | METHOD - Inspection
label | 9d1adc35-71b0-5b51-b568-92af7e1ab214 |  | note | – – – – – – – – – – – – – – – – –
label | 4508af31-03c9-54ee-85fb-9448fbfb04f0 |  | note | FREQUENCY - P2-100D (SUP and Footpath) Joints
label | 4fd58c8d-eff7-5450-b4e7-befb066d98ee |  | note | – – – – – – – – – – – – – – – – –
label | 35d98da6-edf6-5ebe-b0a5-bc81c137f2db |  | note | CATEGORY - IP
label | 784b8bb6-5f91-5a3f-9f9a-93585216b16c |  | note | – – – – – – – – – – – – – – – – –
label | 89376a9e-38c7-5ecd-aeec-8f8722833354 |  | note | RESPONSIBILITY - SE/PE
label | 47a81494-ca85-5339-b142-b5683d3e49b6 |  | note | – – – – – – – – – – – – – – – – –
label | 36205fc8-de65-50a6-a118-26e8350d47cc |  | note | VERIFYING DOCUMENTS - This ITP
text | 69ea79ee-2529-5605-a33b-758c949e3d96 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Expansion Joint Placement
label | cadf3000-2b21-5dbf-84f4-66cf87d18e9c |  | note | REFERENCE - IFC Drawings AC-AR Installation Manual VR 660.04
label | f3a8888b-28e8-5706-a5a8-018beb1b3fdb |  | note | – – – – – – – – – – – – – – – – –
label | 48b3e7de-b34a-5336-b147-fac8eb3ae6ed |  | note | ACCEPTANCE CRITERIA - Check compliance with the Drawings, installation manual and tolerances:
label | 8241ec59-96d6-51de-a13c-ad6079319d41 |  | note | Joint gap = ±3mm (38mm is specified on the drawings)
label | e7712e1e-471d-534f-928a-e7ca563b61bd |  | note | Deviation from plan alignment = 5mm max.
label | c5deb94f-cf3b-5839-bd2d-387734bc91d7 |  | note | Deviation of top surfaces (step) = 0mm to -2mm when measured perpendicular with a 2.5m straight edge
label | f2bcd940-5160-5196-9f9a-9cb6cdaed340 |  | note | – – – – – – – – – – – – – – – – –
label | d0407e5e-ba26-5f7f-bfbc-1183b19d0a40 |  | note | METHOD - Measure Visual
label | 8b7851f1-40ce-5c67-ab6b-832b3ba1225d |  | note | – – – – – – – – – – – – – – – – –
label | f1e18e9f-b3f7-5bca-a472-81081f4feed9 |  | note | FREQUENCY - Each element
label | 00b4fd4a-20a2-5aac-83d1-b10a2ac93c53 |  | note | – – – – – – – – – – – – – – – – –
label | 3e6c8bb9-3c8f-57e5-8cc2-e82f0ccfe70c |  | note | CATEGORY - IP
label | 0617d363-17c4-5012-90d0-b77790373a8a |  | note | – – – – – – – – – – – – – – – – –
label | da045b18-929a-524d-942e-f2796a80105a |  | note | RESPONSIBILITY - Surveyor SE/PE/SPE
label | c472bee6-6530-5219-8951-d01fc7506b9b |  | note | – – – – – – – – – – – – – – – – –
label | cc510cb6-3eb9-5dda-9b15-0b3825579edd |  | note | VERIFYING DOCUMENTS - This ITP
text | 59206f66-d5ef-58ab-8d44-ee21c7e796a4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Compression Seals, Inserts and Membranes
label | b0b5f6a7-ba4d-5371-8b66-7e39043ce02c |  | note | REFERENCE - VR 660.04
label | 68547c48-4260-5e32-b709-eac814ef1040 |  | note | – – – – – – – – – – – – – – – – –
label | 99f9ebcc-9a5e-571a-bd56-ad13f0e64a38 |  | note | ACCEPTANCE CRITERIA - Compression seals, inserts and membranes shall be installed in one continuous piece for the full length of the joint, inclusive of footpaths and barriers.
label | 42f73dfb-8bbf-5d32-90be-13bcaed6e8f4 |  | note | Completed joints shall be watertight.
label | b677c57f-d528-5d44-9723-4905a075e1bf |  | note | – – – – – – – – – – – – – – – – –
label | 833ac32e-0695-5307-8853-3c898b7ebdb7 |  | note | METHOD - Visual
label | eb23069e-713b-5bd3-857c-382b5f061150 |  | note | – – – – – – – – – – – – – – – – –
label | 0d462fd5-604e-5e2b-9214-186230e1c0f0 |  | note | FREQUENCY - Where applicable, each element
label | ded599c4-7e83-5d52-97cc-650086badf12 |  | note | – – – – – – – – – – – – – – – – –
label | c5ea1475-2fee-5c5f-88e1-4930fe420a54 |  | note | CATEGORY - IP
label | e3f9bac8-8516-5dc8-85c7-07d63d2f0486 |  | note | – – – – – – – – – – – – – – – – –
label | b52aca00-a073-5789-9317-228db85d7182 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 86d93929-1b9e-5a25-856f-f5897d39aa06 |  | note | – – – – – – – – – – – – – – – – –
label | 55f9cdd5-0af5-567a-a2c2-92b31c6a0c30 |  | note | VERIFYING DOCUMENTS - This ITP
text | a8c2edcc-20d0-5a32-8018-3e42ff5ba5aa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Final Inspection of installed system including all accessories
label | 7c9d9346-c031-50e9-ac9c-f52897ba6023 |  | note | REFERENCE - IFC Drawings
label | f3af8a1a-639d-54e9-a421-fd86666f0580 |  | note | – – – – – – – – – – – – – – – – –
label | ff929cef-b52e-5ed6-90cd-6bbddb03d7e4 |  | note | ACCEPTANCE CRITERIA - No visual damage to the installed system
label | 6f3d32fd-1414-51c6-90a1-71c1fd1c802e |  | note | – – – – – – – – – – – – – – – – –
label | 27eedf3b-de0d-5ed5-9d75-9a9400e0f164 |  | note | METHOD - Inspection
label | 30bf8a7d-28d9-589d-8f1d-f96509771531 |  | note | – – – – – – – – – – – – – – – – –
label | 35dfdf4a-4348-5d86-abff-9a57c0608f27 |  | note | FREQUENCY - Once per Lot
label | 43aa97aa-2127-57d5-8939-42ae52b96e35 |  | note | – – – – – – – – – – – – – – – – –
label | bf7a90b7-0094-5c78-ba32-f743e98152b8 |  | note | CATEGORY - IP
label | 8d1f73cd-83a6-5ac1-9600-24e45351ae8c |  | note | – – – – – – – – – – – – – – – – –
label | c3c28628-d61a-544c-a33c-1aeb9958fec5 |  | note | RESPONSIBILITY - SE/PE
label | b4c32e3f-62cc-5a67-bc23-b53e1d6d55d2 |  | note | – – – – – – – – – – – – – – – – –
label | 0e8320ce-7f6f-5d69-a9c0-fa8a94fa9d68 |  | note | VERIFYING DOCUMENTS - This ITP
text | 3cdfe8f1-7736-53c0-88af-b9bc64ba01b8 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6 - Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Trafficking of Joints During Construction
label | 0579cb90-1224-5062-834f-fe9635ba1f20 |  | note | REFERENCE - VR 660.04
label | 48d41b7b-c38c-5105-bfba-fef968c7ae60 |  | note | – – – – – – – – – – – – – – – – –
label | 7f4404ac-c537-5989-8c36-ca7d4e8728db |  | note | ACCEPTANCE CRITERIA - Joints, seals, inserts and membranes shall be protected from damage due to construction activities and the passage of site vehicles.
label | 88b794ca-1c17-5f24-b1dd-b46310061258 |  | note | – – – – – – – – – – – – – – – – –
label | 81610df2-b301-598b-a403-b24b5012539d |  | note | METHOD - Visual
label | 85be5565-d11a-533a-9649-0253fcdc0206 |  | note | – – – – – – – – – – – – – – – – –
label | 679001ff-9043-5080-9cee-48b27a54f176 |  | note | FREQUENCY - Where applicable, each element
label | 22c299f7-3979-5075-8b96-148e34e403c8 |  | note | – – – – – – – – – – – – – – – – –
label | 118206ee-343d-5758-b099-b2b328f08c0d |  | note | CATEGORY - IP
label | 3c023519-be2c-5efb-a8a6-2dc24b72369b |  | note | – – – – – – – – – – – – – – – – –
label | 5cfafe2c-cf32-5674-aa2a-cefd99c10080 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 976c5eb4-5510-5fab-aadd-5a9c2da52519 |  | note | – – – – – – – – – – – – – – – – –
label | 76bdc6cb-1c6e-5a8d-809a-e6918a4aec55 |  | note | VERIFYING DOCUMENTS - This ITP
text | 991bdc08-c61f-58cf-aee0-e790c4799d2c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - As-built Survey
label | 5c287ad8-fc46-5154-b635-0e155079744f |  | note | REFERENCE - IFC Drawings VR 660.04
label | 7c90c970-d210-5e20-8563-a9f34b532957 |  | note | – – – – – – – – – – – – – – – – –
label | f2a27bc1-76eb-581b-b7f5-6c5c8c97742f |  | note | ACCEPTANCE CRITERIA - Provide record of dimensional measurements to demonstrate expansion joints comply with tolerances as per 5.3 above.
label | 97338522-6174-5007-8e89-2a86ac20bba5 |  | note | Attach: Survey As-builts / Survey Report
label | 8a69bce4-48e6-552e-aea0-2145cba11181 |  | note | – – – – – – – – – – – – – – – – –
label | 40304be0-1049-50f1-a99f-e085ebaac4da |  | note | METHOD - Document Review
label | d00d89d5-8b21-5cd0-b1bb-a90ace16c221 |  | note | – – – – – – – – – – – – – – – – –
label | 8e4ba5b6-c644-5eab-a54b-d0e0a0c5a843 |  | note | FREQUENCY - Each element
label | dfe6015c-6654-582f-b772-f3002068cb24 |  | note | – – – – – – – – – – – – – – – – –
label | c4819624-df5b-5167-a236-3ca48c920886 |  | note | CATEGORY - IP
label | 401af768-e710-501d-8711-4de500a2a90a |  | note | – – – – – – – – – – – – – – – – –
label | 09d33f60-dff5-5784-92cd-b0b39952553a |  | note | RESPONSIBILITY - Surveyor SE/PE/SPE
label | 1f0399e8-6fbc-5bf5-a761-bd70d76b4d22 |  | note | – – – – – – – – – – – – – – – – –
label | 53c91829-5660-5c1b-a20b-06c1e78a629a |  | note | VERIFYING DOCUMENTS - This ITP
text | fa36db24-a12f-5152-a492-8e2c42d2e233 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Subcontractor Product warranties obtained
label | f918e8f4-08f9-58a2-bcac-3c51570ae5f5 |  | note | REFERENCE - Work Method Statement IFC Drawings
label | f7a2ba92-d4fd-5e39-8f39-63fc0889e93b |  | note | – – – – – – – – – – – – – – – – –
label | 2b9e2130-1c52-5eda-b380-2e3aa73d848a |  | note | ACCEPTANCE CRITERIA - Product warranties obtained and are compliant with what is specified in IFC Drawings
label | f3dbe5c3-e150-55b9-b19f-5f5119077c6f |  | note | – – – – – – – – – – – – – – – – –
label | e8265290-7c5f-5f6f-b878-b3dfe097994c |  | note | METHOD - Inspection Document Review
label | 366441c6-3deb-553e-8140-fd2093e1657a |  | note | – – – – – – – – – – – – – – – – –
label | 1d664a67-8d38-5011-9191-dbc5e75d5d7d |  | note | FREQUENCY - Once per Lot
label | c44e82ad-5af5-5ea2-ac77-c1d48ab42e81 |  | note | – – – – – – – – – – – – – – – – –
label | 17e0b05b-62f1-57e9-a522-ae9504970e70 |  | note | CATEGORY - WP
label | a88fa225-5c44-5a8e-b0df-c25eb0dec2df |  | note | – – – – – – – – – – – – – – – – –
label | fb070335-fa46-5683-9d6a-2696fa3a6528 |  | note | RESPONSIBILITY - SE/PE
label | 94ad8096-2ff9-55b4-8ee1-4b71b8f8d0e9 |  | note | – – – – – – – – – – – – – – – – –
label | 11a96251-98cc-5949-905a-ff7bf9d05267 |  | note | VERIFYING DOCUMENTS - Copies of product warranties
text | d4a040a2-6070-5647-86b2-f73ac1e3ae9c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Non-conformance Report (NCR) Closure
label | 0131e3bf-c6ba-5987-bff6-2fbbeaaef2bd |  | note | REFERENCE - MRPA Quality Management Plan
label | a1fd406f-5cfa-515f-8603-4d36783ce686 |  | note | – – – – – – – – – – – – – – – – –
label | 4d0c605f-d00f-51c1-9d02-67bda189e16f |  | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | b8b24f6b-65ab-5ed7-8b41-7fa6b417968b |  | note | – – – – – – – – – – – – – – – – –
label | 0be1861a-03de-5cee-9542-7ac3099ebace |  | note | METHOD - Document Review
label | 3c80fd14-c9c0-5bf3-a875-ef76989c1335 |  | note | – – – – – – – – – – – – – – – – –
label | 5e852f1b-6f67-52e6-80cb-cda6afee7cf5 |  | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
label | b34ce2cd-a8e5-5f3e-900f-0642d260f971 |  | note | – – – – – – – – – – – – – – – – –
label | 07618e5e-0817-5a60-ad38-b0d33ccb0113 |  | note | CATEGORY - HP*
label | 10956934-8963-58a1-b3d1-4ef337968ec5 |  | note | – – – – – – – – – – – – – – – – –
label | 17d76026-8276-5a63-bbfb-600ca0f2495f |  | note | RESPONSIBILITY - SE/PE/SPE
label | debcc40f-58ab-5510-8589-d119ac0fcdb9 |  | note | – – – – – – – – – – – – – – – – –
label | 6b4bc80a-7be8-50a9-9457-b38cf791ea54 |  | note | VERIFYING DOCUMENTS - This ITP
text | 33d32882-48f4-54f7-8b47-d361eedb63a0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 770703e9-75b6-5ff7-98b5-4e209529bee6 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c5a3f4a5-65bb-5ad5-b5d1-abf45c66c849 |  | textbox | Name:
text | d936ae23-e46f-575f-860b-386f461eeb80 |  | textbox | Position:
date | aaaeef21-5aaf-5605-bf33-3af9339e09f3 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-061-STR-Camms-Precast Barriers and Kerbs Installation | itp |  |  |  | Yes | ITP-061-STR-Camms-Precast Barriers and Kerbs Installation Rev 0 | 8ac872e8-5bd8-447d-9eae-c70dfc5acf01
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | a53da435-2360-53e2-8790-7ca167c0c5ae |  | note | Document Title: ITP-061-STR-CAMMS-Precast Barriers and Kerbs Installation
label | 387f4898-3833-5e7a-a99e-12602b82843f |  | note | ITP Description: CAMMS-Precast Barriers and Kerbs Installation
label | 53cd1d81-13eb-5331-9690-1599a96ed66f |  | note | ITP number: 061
label | df134883-4818-5df3-9dba-50316d4bbec0 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 4750af83-57ea-5404-86cc-3d274d1f526e |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 66482eac-d97c-5abd-844e-b5f3f9e26a20 |  | note | Revision Number: 0
label | bcbf1a26-7426-59e5-a4f6-776742bf7220 |  | note | Revision Date: 18/08/2023
label | d9f246f4-aeb6-5886-b1e4-02bdfeb6848d |  | note | ITP created by: Justin Kreinberg
label | bab5ea9a-1b7c-5dc5-b4f6-44b6352f37bd |  | note | ITP approved for use by: Victor Mira
label | 22037ef7-3527-5bc7-a68c-1e52c1e383da |  | note | 1.1 Non Dependent
label | 9461b3e0-4eef-5644-816e-90bd34f1349e |  | note | Reference: VicRoads Section 610 Feb 2020
label | a58cc799-3967-5cad-b8ca-50ae04ebce18 |  | note | 1.2 Non Dependent
label | 2462fe35-3d4a-5d31-970b-5299039d6fa7 |  | note | Reference: VicRoads Section 620 May 2009
label | 2422304c-0ebf-54ba-92d6-eeef4bb7b77f |  | note | 1.3 Non Dependent
label | f18fde9f-cbba-533c-b43a-1cbb67c40ebe |  | note | Reference: VicRoads Section 630 October 2013
label | cc42f35c-89fc-57a7-a607-a003e01af50a |  | note | 1.4 Non Dependent
label | 7df45a25-802c-5122-be91-bc310bb721a6 |  | note | Reference: VicRoads Section 670 October 2013
label | b70ab8a9-7833-5e45-ae49-56f55534649d |  | note | 1.5 Non Dependent
label | 4cd3551e-fb52-51c6-8607-c61743bf57d3 |  | note | Reference: VicRoads Section 671 October 2013
checkpoint-group |  |  | section | Preliminaries Materials
checkpoint-status |  |  | checkpoint | 2.1 Grout
label | 8c109616-f509-57d8-b38c-65bc9e3a015f |  | note | REFERENCE: MRPA Quality Management Plan
label | a3ee2c98-403e-5ca8-a7a4-02a5e2d0d049 |  | note | – – – – – – – – – – – – – – – – –
label | b5b3aaf0-d4a4-5224-b517-e27e484a2328 |  | note | ACCEPTANCE CRITERIA: Details of the grout to be placed between the precast elements to be submitted for review to the Nominated Authority.
text | 640bf39c-0850-5f74-8897-6536073deee9 |  | textbox | Enter: Teambinder Material Approval number
label | 255fbe77-f19b-571e-a6e8-0431522be29f |  | note | – – – – – – – – – – – – – – – – –
label | efa3d10a-9e40-5351-bd69-ecfe77e41236 |  | note | METHOD: Document Review
label | a91eaa03-ae65-55ea-b595-4337144fa04e |  | note | – – – – – – – – – – – – – – – – –
label | 602de65a-d0bf-5aeb-ae45-b71008ec07e4 |  | note | FREQUENCY: Once, for each product
label | 046c3c8b-9a5a-56e6-9f2b-5058b18ee090 |  | note | – – – – – – – – – – – – – – – – –
label | ff6b5795-425e-5a7d-99b1-285186c93c89 |  | note | CATEGORY: HP
label | 11050bc9-436f-502c-80fc-02c60897ba9a |  | note | – – – – – – – – – – – – – – – – –
label | 67938f7c-c8cc-5947-b720-55c4a0196020 |  | note | RESPONSIBILITY: Nominated Authority
label | 94f45fda-2b51-599d-ab85-8892ad2ca9e4 |  | note | – – – – – – – – – – – – – – – – –
label | bf341cf3-d35f-58a6-8c7a-d2873995bb76 |  | note | VERIFYING DOCUMENTS: This ITP
date | b348d65e-4336-589e-8ba0-84d75f6d3e7f |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Documents
checkpoint-status |  |  | checkpoint | 3.1 Precast Elements
label | 06bf8a18-fb9c-5f35-891a-bc90695c3ae1 |  | note | REFERENCE: IFC Drawings VR 610
label | 7b786dc7-c2f6-55d2-8f3e-bbaa875e7240 |  | note | – – – – – – – – – – – – – – – – –
label | 6c5200da-61e8-5ab7-90d9-a76bb4b0a19a |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | 65ceb7e2-c639-5879-a6a1-48aee334fc82 |  | note | i. Certificate of Compliance / Birth Certificate
label | 4c22fb57-448a-5086-9523-96394098e254 |  | note | ii. Compressive strength test results
label | b798917a-5cfa-5b7e-895e-d774b092e7f0 |  | note | iii. Precast Lifting Design
label | 43b4b220-d474-58aa-ae0a-0f4c18b3137b |  | note | iv. Pre-pour check sheet / ITP
label | 2f4d33b1-777b-5888-9c87-0cb10dea7069 |  | note | v. Post-pour check sheet / ITP
label | 0b0b189a-7a7c-504e-a033-9ee9a0697111 |  | note | vi. Covermeter check record
label | c2472efe-41ab-5255-b4dd-98c79cae9aed |  | note | vii. Record of dimensional measurements
label | bd11f0ce-c895-57a7-83f2-a54c074299de |  | note | These documents are typically stored in a MDR Lot in Team Binder.
text | 683dc3a6-188c-5e90-9365-834a9653eafd |  | textbox | Enter: Teambinder Material Approval number
label | 6d9d8323-b993-50c7-9c93-9e81c827c051 |  | note | – – – – – – – – – – – – – – – – –
label | f85dbc13-bbde-5fda-a70a-50b5b347a9f1 |  | note | METHOD: Document Review
label | bac69bfb-1773-5433-9a7c-1cc13e67956d |  | note | – – – – – – – – – – – – – – – – –
label | 14bc92fa-f4a8-52fa-bb35-aa81ba3a36ce |  | note | FREQUENCY: Each element
label | 37d83823-52e0-54a3-8dd6-b4d644a85904 |  | note | – – – – – – – – – – – – – – – – –
label | a39ae726-10d2-5aaa-8988-2762e986e44a |  | note | CATEGORY: IP
label | 044cde5b-3fc1-5b54-9eb3-058500235404 |  | note | – – – – – – – – – – – – – – – – –
label | 89217913-79ec-512e-86b1-fae29953330d |  | note | RESPONSIBILITY: PE/SE/SPE
label | 2434b1de-dd3b-55e2-85ea-f1e7a1c68d9c |  | note | – – – – – – – – – – – – – – – – –
label | e330fdaf-b31d-5b63-9f08-3ff67bf45164 |  | note | VERIFYING DOCUMENTS: This ITP
date | 48683fc4-4ede-57f8-aaa5-9905e1703651 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Bridge Deck / Foundation Compressive Strength
label | 5a512701-0192-50e7-9f9e-e73b54ba0fa2 |  | note | REFERENCE: 671.03
label | c846bc91-9a00-52ac-9847-f15e06f28f1b |  | note | – – – – – – – – – – – – – – – – –
label | 809d91e8-3400-522b-9efe-ac2e01bbedfa |  | note | ACCEPTANCE CRITERIA: For Precast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
label | 34dffbf5-57d7-53af-8fec-014b513d7a73 |  | note | – – – – – – – – – – – – – – – – –
label | 42700a9f-9429-59f9-8d45-91d1f0661488 |  | note | METHOD: Document Review
label | 059cef08-a668-5f9a-aec4-6b7b99c0746d |  | note | – – – – – – – – – – – – – – – – –
label | 9fa49d35-b210-521e-afff-2ddb9f8aefe0 |  | note | FREQUENCY: Each installation location
label | cb2c1480-db0a-526c-830b-d3ece49df9dc |  | note | – – – – – – – – – – – – – – – – –
label | 232d7792-beb8-56a2-9f60-fd7beff14504 |  | note | CATEGORY: HP*
label | 3e9f5f5b-8638-5de8-a902-bdfae75babf8 |  | note | – – – – – – – – – – – – – – – – –
label | d2347529-6bb1-574f-9415-378eff651d58 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a38df15f-f4cf-55c2-aefc-59b65526dca8 |  | note | – – – – – – – – – – – – – – – – –
label | 05598c8a-53f3-574b-9f90-ae0582063bdf |  | note | VERIFYING DOCUMENTS: This ITP
date | 3acefe46-5185-55bf-9a3b-c8fd8877911e |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out of Precast Elements
label | 11749285-9d9f-52c2-8b7b-8d313e9fb256 |  | note | REFERENCE: IFC Drawings
label | 5bfd533b-6ad7-5687-9eeb-0198b70aec08 |  | note | – – – – – – – – – – – – – – – – –
label | d3e5a89f-5f9e-51f3-9a46-463e47c4e038 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
label | 12eea823-fcce-505b-8146-cba09cac59a5 |  | note | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
label | 2eca082b-4bfc-5028-878b-10e3acd8b5ec |  | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
label | a7853e3c-19d6-5f5b-a56e-52e0381d8494 |  | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
label | f921a761-c84e-5833-87c5-4fc52645333e |  | note | – – – – – – – – – – – – – – – – –
label | df31871c-ce97-5b30-be73-95e039862ef1 |  | note | METHOD: Measure, Visual
label | ed3b83a9-0ed5-5332-ad31-65d66026b0b8 |  | note | – – – – – – – – – – – – – – – – –
label | 5e9fe89a-9189-5fb2-8e32-a14ee6eca202 |  | note | FREQUENCY: Each element
label | 5af914f8-e78e-5eb7-9f51-5dce6c037711 |  | note | – – – – – – – – – – – – – – – – –
label | 1b530d87-968f-542c-8af1-39aa10b3de53 |  | note | CATEGORY: IP
label | 60a19e11-5a06-5464-9cde-dccae4f3c961 |  | note | – – – – – – – – – – – – – – – – –
label | 666549d5-b60a-5173-bea3-7ec24650b8b0 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | e1d3bc2b-ff3b-5003-8efd-deac9029f25e |  | note | – – – – – – – – – – – – – – – – –
label | c573923c-fca3-5457-9478-f1a13fe3a7b4 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6da5fb78-8c57-5309-ab66-bb5e302273a5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Bearing Shims or Bearing Strip Placement
label | 39576289-6668-55ac-a0b5-ff948bc93c55 |  | note | REFERENCE: IFC Drawings
label | ef57a83e-3e4e-53f8-a298-0f6a985cbd0d |  | note | – – – – – – – – – – – – – – – – –
label | a5b11f86-119b-573c-9d19-2ea3b8fab857 |  | note | ACCEPTANCE CRITERIA: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
label | 99a35fb1-0ac7-5d3e-8acc-2e473c86e479 |  | note | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
label | 6f82a083-f7ad-5f1f-9c3c-e6477ad2c167 |  | note | – – – – – – – – – – – – – – – – –
label | 510779bf-9c0e-5098-b2f1-5fe03849b497 |  | note | METHOD: Measure, Visual
label | 43ee9550-b1bf-5032-b0cf-93453e0d7882 |  | note | – – – – – – – – – – – – – – – – –
label | 1f1afff9-bd38-5786-8f93-182643274e35 |  | note | FREQUENCY: Where applicable, each installation location
label | b1def477-f9d5-5805-ba5c-c8988af35a2b |  | note | – – – – – – – – – – – – – – – – –
label | 3f0f2170-b039-585a-b00e-c00c769fa046 |  | note | CATEGORY: IP
label | 3c9a2fcd-fe4b-5822-aa79-4339ae126869 |  | note | – – – – – – – – – – – – – – – – –
label | ab599359-e5b6-5882-a5db-fb33ab13a63d |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | bf26ebc8-7d7e-5764-8c1b-a0a0cded0699 |  | note | – – – – – – – – – – – – – – – – –
label | 6919c848-9c27-56da-9ada-8ff27c611c63 |  | note | VERIFYING DOCUMENTS: This ITP
date | 84331ca5-5ca7-5591-989d-0a30ae864d5c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Bitumen Board and Ableflex placement
label | fd5752b6-7438-5862-8a5b-c9bcd1516d70 |  | note | REFERENCE: IFC Drawings
label | 6b89d76b-59ec-5a9d-9152-344ebe8d88fc |  | note | – – – – – – – – – – – – – – – – –
label | a3970bd4-b8be-5529-b2d7-2fa1f92ab24b |  | note | ACCEPTANCE CRITERIA: Adhere any bitumen impregnated fibre-board and ableflex into the positions shown on the IFC Drawings and where grout or concrete ingress will affect the end use (such as around conduits).
label | 7b64eaa5-7001-52ae-af1e-89a9b6850ff5 |  | note | – – – – – – – – – – – – – – – – –
label | 33020c6d-f121-5bc8-9526-95ed3cce6385 |  | note | METHOD: Measure, Visual
label | c08b1034-056d-565c-bac1-a6a4c47b6b06 |  | note | – – – – – – – – – – – – – – – – –
label | 1411b4d3-5758-50ee-84ee-74b5feab7bff |  | note | FREQUENCY: Where applicable, each installation location
label | 41782e8a-9ca0-5214-9914-a0ef98b321d8 |  | note | – – – – – – – – – – – – – – – – –
label | 387550f3-9045-5978-bb89-13110d983e10 |  | note | CATEGORY: IP
label | 0f9c6633-bb06-52fe-a663-26c1ad4838a7 |  | note | – – – – – – – – – – – – – – – – –
label | bdfa6b67-d0a1-50d9-bbb7-944f80004a98 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 18f6cefb-7c30-599c-9975-f6be1f1ed684 |  | note | – – – – – – – – – – – – – – – – –
label | c8f63915-ec55-5a0c-9e97-75905e83ee62 |  | note | VERIFYING DOCUMENTS: This ITP
date | 955c1855-f42d-5946-8f1f-c9b7066c7ab5 |  | date | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Precast Handling
label | 17801aa4-ccfe-550e-884e-48fc4ebdfd9a |  | note | REFERENCE: 620.07 Crane Lift Study
label | c2de8f58-9fab-5389-8822-e6f7c28f8b07 |  | note | – – – – – – – – – – – – – – – – –
label | f016a1f5-05a4-5e80-be9b-a0258ff8d02e |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | 8e4a4a43-6534-54f8-8a49-d9c8fc7cdefc |  | note | – – – – – – – – – – – – – – – – –
label | 61aad7a8-fffb-5267-82ba-7e8281c362a4 |  | note | METHOD: Visual
label | 09b3e89f-ce8a-506e-bd92-f860c00fc740 |  | note | – – – – – – – – – – – – – – – – –
label | 08adf102-b6a2-5e8d-96bb-c7675a0d28f1 |  | note | FREQUENCY: Each element
label | b566878c-bf0e-5d6f-af76-3cdace14f25e |  | note | – – – – – – – – – – – – – – – – –
label | 6d4fcdba-254e-55a9-ad96-60d6ed30ee71 |  | note | CATEGORY: IP
label | 48f722c6-3848-5a58-838e-3b11a19e80b6 |  | note | – – – – – – – – – – – – – – – – –
label | d68684af-0392-5fdd-9b9a-27f5a276482c |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9ca49572-f29f-5434-a4e3-876521785dfc |  | note | – – – – – – – – – – – – – – – – –
label | bb707816-f36c-5a9b-833c-027173a932a8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 22c527a7-dff6-597f-abab-4ab967fbf240 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Precast Placement
label | f71cae77-2a2c-5054-9532-6d6b3ce58f9e |  | note | REFERENCE: IFC Drawings VR 670.05
label | cb2f0d46-e152-5619-adf5-5fddda73bf33 |  | note | – – – – – – – – – – – – – – – – –
label | 4a2baf9b-e5e2-56c6-bf54-2b9eb22f5afd |  | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
label | 617207a3-83c5-5206-bf2e-b4aa11c87ba2 |  | note | Adjustments to be made to achieve following tolerances:
label | 4e2e566e-d320-5338-8795-5bda66119466 |  | note | (a) Departure from plan position: 25 mm
label | 08d457fc-2998-5824-807e-679b6862b6c0 |  | note | (b) Departure from alignment: 5 mm
label | d01f2829-74ee-5723-94e2-147ef03cf0b6 |  | note | (c) Irregularities in alignment: 3 mm in 3 m
label | 4dfbad19-e3bf-561d-8bf8-c362150ebd90 |  | note | (d) Variation in joint gap width 3 mm
label | cfb19b34-e0c3-5345-8e58-f36bf6e00307 |  | note | (e) Verticality of posts, panels, balusters and openings: ±2 mm
label | 960e2afe-6d7d-5a23-a8fe-7af1c88f4b52 |  | note | The nominal gap between elements is as per the IFC Drawings.
label | a62d8384-5857-516f-9a81-8e246b8e211d |  | note | – – – – – – – – – – – – – – – – –
label | d8fcc950-3425-5320-a6fb-533bfd880c2d |  | note | METHOD: Measure, Visual
label | 95652cd5-85fe-5569-94d9-9755b84411a5 |  | note | – – – – – – – – – – – – – – – – –
label | 1f24db4c-183d-5318-9afc-4a06a2cc5ecf |  | note | FREQUENCY: Each element
label | fb91dcf9-dd73-51af-a64d-01240aac5a9c |  | note | – – – – – – – – – – – – – – – – –
label | 66dd3b20-21cc-55ab-9f63-c92af546a1a6 |  | note | CATEGORY: IP
label | 98bceba5-e94e-53fa-ba09-e5ed655edc42 |  | note | – – – – – – – – – – – – – – – – –
label | 1854a6c2-e821-5419-98d3-38dd5583bc24 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 90910fd9-8fe4-5cb3-8925-e4341a2a1cc1 |  | note | – – – – – – – – – – – – – – – – –
label | 596a819b-47f6-5edb-b1df-8bf6df9e8424 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6da4757b-db10-5c2a-920e-f7d3e8b7d354 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | 153428e4-35a9-57c8-84c9-3597b0787fd6 |  | note | REFERENCE: IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3
label | e2fd2540-59e9-5f47-8a5e-930f901fd842 |  | note | – – – – – – – – – – – – – – – – –
label | 33841e5c-aae3-5535-93d3-92fcac811df5 |  | note | ACCEPTANCE CRITERIA: Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
label | a95d5151-eb9e-5fc9-a9b5-d56974a992b2 |  | note | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | 6bbfa7f0-7469-55af-8701-73ebabde1eac |  | note | ○ Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | 7c3045cf-ac58-5adc-9320-ed2c66890dc0 |  | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | b50a7913-7e44-51ba-b912-40ac6bb4ea13 |  | note | – – – – – – – – – – – – – – – – –
label | 819e1ee6-6fa5-5c8f-85be-f230d0f8c8bb |  | note | METHOD: Visual
label | c77a6bf3-5f2f-5c6d-9f7a-a9f4bfac3ec4 |  | note | – – – – – – – – – – – – – – – – –
label | 2c915e5f-f464-51f0-a493-e6be2f5c55b7 |  | note | FREQUENCY: Where applicable, each bolted connection
label | 3cf3089f-3a5e-5d2e-9d13-c92548842ad4 |  | note | – – – – – – – – – – – – – – – – –
label | d2b55415-d0cf-5e36-b2ae-6f6af128407e |  | note | CATEGORY: IP
label | a0ed5873-8919-5130-aa2a-bb59da7c161f |  | note | – – – – – – – – – – – – – – – – –
label | d5660482-752a-558f-b563-c7ba01f219a0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3cff8e74-b4c3-5e47-97c7-27180eb2f575 |  | note | – – – – – – – – – – – – – – – – –
label | b00c5784-f4b8-55f7-b84a-cd8a9ec7ebc4 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0988da81-3a7a-53d2-9011-f3f5ff51d3f0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Precast Traceability
label | 2600e079-3507-5901-8243-2d484d1b8816 |  | note | REFERENCE: 620.09
label | 2e7d1c70-596a-5b1e-ba76-2753db3be0cc |  | note | – – – – – – – – – – – – – – – – –
label | 7e2b6a79-7115-57d2-9b5b-97524bfbcf10 |  | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | 2f1ae554-b19e-59c2-b40f-ba036144f344 |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | 0a1c574a-9960-56e1-95e0-162a259ff611 |  | note | – – – – – – – – – – – – – – – – –
label | b1b7f35f-1ca2-51f8-a46e-a4b49d75e332 |  | note | METHOD: Visual
label | 50e942d6-2224-56f2-9d5b-4927c98c037f |  | note | – – – – – – – – – – – – – – – – –
label | 3c3e3ddd-a744-5b6d-935a-7ddd6d06fe91 |  | note | FREQUENCY: Each element
label | a3554819-26b5-5030-b74f-3ddf9538569d |  | note | – – – – – – – – – – – – – – – – –
label | f6a8a767-0784-5e3c-a608-6e2041369ebb |  | note | CATEGORY: IP
label | ec70d828-3abf-535b-a5ca-209770a25853 |  | note | – – – – – – – – – – – – – – – – –
label | 92a04c7a-6d8c-503e-99b1-172ee02c6dd9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 236706bb-1250-5a6a-adbe-a58375b06d21 |  | note | – – – – – – – – – – – – – – – – –
label | 866ea223-7b43-56a6-8ec8-d4f29eb1a849 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2271ebfb-64ac-5ad8-8da9-6c7999a7f913 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Flowable Grout Pour
label | 8a2b9169-1802-5366-affc-63941dd94026 |  | note | REFERENCE: IFC Drawings
label | d2b87daf-f6a0-557e-b59e-dbb065bbc41e |  | note | – – – – – – – – – – – – – – – – –
label | 6001c0ae-569c-5e98-975e-3fbc8da57651 |  | note | ACCEPTANCE CRITERIA: Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
label | 40aca846-fbe1-59c2-ba14-cd74046eef09 |  | note | Complete: Grout Pedestals & Bearings ITP
label | 8dd8a388-3da7-5374-b10d-0e39f9ded3a9 |  | note | – – – – – – – – – – – – – – – – –
label | 27852465-69be-5a23-9b4d-0bd000b6b95c |  | note | METHOD: Visual
label | 6227237d-18e7-5f6f-873c-7c31a6a3fe35 |  | note | – – – – – – – – – – – – – – – – –
label | c3e66e18-ef61-57d0-8564-e5046b8cead6 |  | note | FREQUENCY: Where applicable
label | f9804177-dabd-5c73-9eae-4b5699fcf0ac |  | note | – – – – – – – – – – – – – – – – –
label | 93498ab8-5041-558d-9330-fb10147e06be |  | note | CATEGORY: IP
label | 181f6728-4d92-530e-bf26-b70bf4869125 |  | note | – – – – – – – – – – – – – – – – –
label | 3afced7d-6541-55ed-a005-e08cf13c6aea |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | b383cf26-54df-5bbd-af37-aa452ea85bf2 |  | note | – – – – – – – – – – – – – – – – –
label | ef98ad04-7b13-5672-894d-3e2005245f26 |  | note | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
date | 75bdad51-e4bc-51c6-9a01-f61079e2bc12 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 As-built Survey
label | 33022dcb-72c7-57e2-af35-b55345ee1fb2 |  | note | REFERENCE: IFC Drawings VR 670.05
label | f6cc26b6-8e5e-57b9-9e13-8c5fa39af823 |  | note | – – – – – – – – – – – – – – – – –
label | 4efee5ab-7f4e-5653-9651-c1711fb1f583 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per VR 670.05
label | a43ce4b7-5c8e-55e2-8db8-64aa39153a9a |  | note | (a) Departure from plan position: 25 mm
label | 69e01b93-bfdd-5ef5-a76a-7409549efc06 |  | note | (b) Departure from alignment: 5 mm
label | ff5aaa4e-f0c6-5071-88ba-1ed4d76d4b76 |  | note | (c) Irregularities in alignment: 3 mm in 3 m
label | 603a9d02-b0c0-539a-b862-d64a9ddbdfbb |  | note | (d) Variation in joint gap width: 3 mm
label | 17c7c613-3237-5b3f-b019-a25a3f0ca958 |  | note | (e) Verticality of posts, panels, balusters and openings: ±2 mm
label | 9bee831c-5e6c-5d0c-a911-c6607159d05b |  | note | Attach: Survey As-builts / Survey Report
label | 0aef35c2-b698-599e-ba79-f5cc4820a2e8 |  | note | – – – – – – – – – – – – – – – – –
label | a1c2f68c-111e-5b30-90d6-e88ce049f73a |  | note | METHOD: Document Review
label | b6e2fcfc-e52f-5d8e-8e99-3b2ab4473b2d |  | note | – – – – – – – – – – – – – – – – –
label | 336e1da6-39db-53df-b75b-c0356b61b0f8 |  | note | FREQUENCY: Each element
label | 78bbbd53-3f2c-5db2-9660-e906263234a4 |  | note | – – – – – – – – – – – – – – – – –
label | 60252a0f-3857-5f06-bb73-20e19fff98f5 |  | note | CATEGORY: IP
label | c03f5f11-26f9-59fb-a4d8-94e378713447 |  | note | – – – – – – – – – – – – – – – – –
label | 9f8f2fc2-47a9-5416-bdd0-b207d1848960 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 68ecacb5-7517-525c-8f90-41ee4cb878ec |  | note | – – – – – – – – – – – – – – – – –
label | 66c6e53a-d631-5f7c-afb9-e2d2fd5e031b |  | note | VERIFYING DOCUMENTS: This ITP
date | 098668b5-79d7-5acd-a958-9c2fac70c114 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | 572f0a77-d107-5517-8d78-b6e11cfe6b8e |  | note | REFERENCE: MRPA Quality Management Plan
label | abbe9589-f4c1-53de-9104-945dd1a09728 |  | note | – – – – – – – – – – – – – – – – –
label | 4fda35ff-c77d-5349-bcc0-1f0e71066e2f |  | note | METHOD: Document Review
label | a290f0ee-d079-5525-b5fa-1d4238e0e178 |  | note | – – – – – – – – – – – – – – – – –
label | 8d508aae-7152-5a7a-99e8-4e2f398a1682 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | bada74ce-e093-502e-a38f-d78cbfdd9010 |  | note | – – – – – – – – – – – – – – – – –
label | bea508f7-faa9-5699-877d-d1ef02720e53 |  | note | CATEGORY: HP*
label | 6d78880d-ae61-57c5-b64e-246670da2da0 |  | note | – – – – – – – – – – – – – – – – –
label | 7dcd1a7e-0b53-5857-8512-8a9136f01ee8 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2b6b026a-38a3-5ddc-a8c7-a0c3a76f3aaf |  | note | – – – – – – – – – – – – – – – – –
label | a4e2c0f5-0ca3-5480-a81c-6da91e31f7a2 |  | note | VERIFYING DOCUMENTS: This ITP
date | 260b0cfd-2b0f-509d-af29-f83693e2df26 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | b6aefe95-827e-5b44-9f9d-a27ed2c14d7d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 763de495-db05-5e3b-afa6-a5cfb2dea804 |  | textbox | Name:
text | b92a7c19-7ee9-5e85-9d27-7bbfa1d134a4 |  | textbox | Position:
date | 049fd50e-9460-5fb2-91b2-6867cc21af1a |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-032-STR-Precast Basin Retaining Wall Installation | itp |  |  |  | Yes | ITP-032-STR-Precast Basin Retaining Wall Installation Rev 0 | 8d59760f-bc7f-4b97-ae46-14bc49f97811
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | f19a5bea-ffe9-5a1b-b96d-90585c43fe1e |  | note | Document Title: ITP-STR-Precast Basin Retaining Wall (Supply & Install)
label | 31fd7494-51d8-5ab3-abdf-eab1afe2d52a |  | note | ITP Description: Precast Basin Retaining Wall (Supply & Install)
label | 64f9d2a7-1054-5e1f-a140-9070c2bd45b7 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ab831a3c-7097-570b-a2f1-ebc42615445c |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 26db247b-98b5-5987-9f15-c50a9cd0f89a |  | note | Revision Number: 0
label | afa21d57-61df-56ea-b944-44ab19a77e9a |  | note | Revision Date: 01/03/22
label | c639a0ef-3a6e-53a2-ba13-e2764d3c5409 |  | note | ITP created by: Michelle Lim
label | f05239c7-56df-5d7c-804c-ff2abaf24fa2 |  | note | ITP approved for use by: Victor Mira
label | ee862f36-a5d5-56f2-9310-29224f3060b1 |  | note | 1.1 Non Dependent
label | d7a549a0-177f-5deb-a44e-61a3e88f0bce |  | note | Reference: VicRoads Section 610 November 2018
label | d50e4509-71bf-5b5e-8f06-c783b2055a90 |  | note | 1.2 Non Dependent
label | 23aa4950-0b10-5040-bbfe-b3bac6e2d33d |  | note | Reference: VicRoads Section 610 June 2019
label | 463ce870-bc06-579b-9b88-19e94f72cbc7 |  | note | 1.3 Non Dependent
label | 1f3b7733-7fe6-56c5-aae8-7b309a78f8ac |  | note | Reference: VicRoads Section 620 May 2009
label | 96ca079d-6557-5e56-a60b-27f6371a005e |  | note | 1.4 Non Dependent
label | 8593b891-ebfa-587d-b599-0ce03358c557 |  | note | Reference: VicRoads Section 630 October 2013
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Joint Sealant
label | 184ef14f-c1d3-51d1-863a-05613bec8ae3 |  | note | REFERENCE: MRPA Quality Management Plan
label | ab7d4a12-236e-5f5b-a31f-2f5f2caa8592 |  | note | – – – – – – – – – – – – – – – – –
label | 343b5c6f-8666-5100-934a-24acfc0723f3 |  | note | ACCEPTANCE CRITERIA: Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
text | 7afee6ad-5d93-5bb0-a669-1802b7638430 |  | textbox | Enter: Teambinder Material Approval number
label | 72d865cf-5569-5c70-a7e4-f88a17b80eb2 |  | note | – – – – – – – – – – – – – – – – –
label | a40fd1e0-1b1f-5530-90c2-c0f848910b33 |  | note | METHOD: Document Review
label | b12e13ba-4cc0-5dd8-88ca-dfad3fa74846 |  | note | – – – – – – – – – – – – – – – – –
label | 0d4a3324-d181-59a7-9634-b62b3fce98b5 |  | note | FREQUENCY: Once, for each product
label | 650bbf81-8f51-5321-bbbd-8c9103c81779 |  | note | – – – – – – – – – – – – – – – – –
label | b6250dac-03f1-552c-93ca-d6ae9e5e9cf9 |  | note | CATEGORY: HP*
label | 94ee090a-4411-5376-bc1b-ad0f39b6fa5f |  | note | – – – – – – – – – – – – – – – – –
label | e47d259b-2bc3-59b5-bcbc-4e2438c8ec57 |  | note | RESPONSIBILITY: Nominated Authority
label | e42176ef-6ed3-50c9-b618-3eb80b0ff9f1 |  | note | – – – – – – – – – – – – – – – – –
label | abf500b9-db4a-5868-b97a-61b3435e1c0d |  | note | VERIFYING DOCUMENTS: This ITP
date | 987bee62-f99a-5bbc-8bee-61fa437e7cee |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Subsurface Drainage
label | f3dc55ce-95f9-53fd-ad32-76299d7e75db |  | note | REFERENCE: IFC Drawings
label | 13ac5831-5225-5788-9918-2ad4f6bbb41f |  | note | 702.03
label | eb7edaf0-0c63-5946-91d6-38e330dee722 |  | note | 702.06
label | f899a567-b823-5b77-8f8b-91516a2fba32 |  | note | 702.07
label | 43ca9e63-8238-5f3c-94c8-e1ac65dc8c56 |  | note | 702.09 (f)
label | 5bde9cfa-a1b5-573d-ad1a-1b5f3fbdbccf |  | note | – – – – – – – – – – – – – – – – –
label | 6bd0596a-b737-5559-a4c9-d1794ba0b87b |  | note | ACCEPTANCE CRITERIA: Details of subsurface drainage as per IFC drawings
label | 30761698-70d0-56ce-b0da-19c2b5ef0ec6 |  | note | 100 dia slotted subsoil drain
label | 7382d35a-b575-52b1-8bae-ed8861a83012 |  | note | Category 1 (Class 1000) perforated plastic pipe. Perforations max width of 1.5mm and min length of 150mm per m2
text | cef3fa75-1d26-57e1-a376-4f154d5eb40c |  | textbox | Enter: Teambinder Material Approval number
label | be94d185-9e3c-5e11-90cf-f4279522b255 |  | note | – – – – – – – – – – – – – – – – –
label | 136b9afa-bd20-5ae2-b4a1-88ae2ae40176 |  | note | METHOD: Document Review
label | 7c57cbf6-c3cd-5c18-8bfb-534bfdcec103 |  | note | – – – – – – – – – – – – – – – – –
label | f2da7b21-29d6-5cec-8ecf-5a995efb750d |  | note | FREQUENCY: Once, for each product
label | 8b0055ea-120f-5099-8082-9f0eb6a8db83 |  | note | – – – – – – – – – – – – – – – – –
label | 667dac93-0a38-51f5-8844-60f84989b3ac |  | note | CATEGORY: HP*
label | 39d4ce80-109a-5082-8b42-390d84cdd181 |  | note | – – – – – – – – – – – – – – – – –
label | d8c5893b-6ba5-532c-add2-6dc672d0d9ce |  | note | RESPONSIBILITY: Nominated Authority
label | 503d4210-05d4-53cc-bfe9-87a93b2d24f0 |  | note | – – – – – – – – – – – – – – – – –
label | e257653d-41ef-55e9-bccd-fd13eafd2ca9 |  | note | VERIFYING DOCUMENTS: This ITP
date | ffc6d78c-f8f7-5b22-b2fe-629ec1ea0eb9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 No Fines Concrete
label | 0a10082e-25aa-534f-a569-23c65fbde7cc |  | note | REFERENCE: 702.05
label | d16a948e-d5ac-5391-ab6f-687c1fbc550a |  | note | – – – – – – – – – – – – – – – – –
label | 4ef37b3c-f257-532f-b486-595f32432ef4 |  | note | ACCEPTANCE CRITERIA: No Fines Concrete to be used as backfill in geotextile A64 around subsurface drainage.
label | 4e104c4e-fae4-51ba-9cb8-84449b247534 |  | note | No Fines to comply with 702.05(e)
text | c7b461a1-c793-536a-bd5e-39c60613b006 |  | textbox | Enter: Teambinder Material Approval number
label | 2345958b-b69a-561e-91b9-6c7e538e9f9c |  | note | – – – – – – – – – – – – – – – – –
label | d7b1d20e-0bea-5bc3-bfa1-643bc0f7fc6b |  | note | METHOD: Document Review
label | 50b9ba84-8dc7-5678-b4c6-83f3df9e9a3d |  | note | – – – – – – – – – – – – – – – – –
label | c0656b71-d9a5-562d-8c74-48428a77be1f |  | note | FREQUENCY: Once, for each product
label | 90a46967-d31f-5119-a73f-381a4433d7f4 |  | note | – – – – – – – – – – – – – – – – –
label | fa30766e-c0c3-5f9b-8e3d-b041d5eb9745 |  | note | CATEGORY: HP*
label | 076fad31-cba1-5b17-9da1-63c15a6119f0 |  | note | – – – – – – – – – – – – – – – – –
label | 668d5ea0-d7e7-501c-b147-bd28d182ba3a |  | note | RESPONSIBILITY: Nominated Authority
label | a005bc92-587d-5df7-9282-419b6a9a395a |  | note | – – – – – – – – – – – – – – – – –
label | a95cd34a-75f1-5c87-ac86-7b4c90f99b5d |  | note | VERIFYING DOCUMENTS: This ITP
date | 00c21368-6222-58b8-a1e3-b36f26d716ef |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures and Documentation
checkpoint-status |  |  | checkpoint | 3.1 Precast Elements
label | 951629e8-159a-54d7-b287-a8f87fff715a |  | note | REFERENCE: IFC Drawings
label | 8e7930f5-780b-5a68-933a-32cbd3a10ab3 |  | note | 610.46 (a), Table 610.463 (November 2018)
label | b2b64610-96a2-50ea-a3fb-6f43b1e684f9 |  | note | 610.47 (a) Table 610.473 (March/June 2019)
label | f3aa9cd4-45bd-505e-958b-7762c7b89bc7 |  | note | – – – – – – – – – – – – – – – – –
label | 98d455a1-1274-5dcb-ac77-ea6acfc34d26 |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | 8d751498-e66e-54d9-9d0e-af09ce8b1591 |  | note | i. Certificate of Compliance / Birth Certificate
label | b2ce0dbe-ee81-5e8f-a77c-ace836bd0fc3 |  | note | ii. Compressive strength test results
label | b2d12680-309b-5dda-b987-53ca8108042c |  | note | iii. Precast Lifting Design
label | 97d10148-9fc5-5e08-909c-810c31d3a522 |  | note | iv. Pre-pour check sheet / ITP
label | 77f88446-394d-5c2d-ad3e-040e52c0cb12 |  | note | v. Post-pour check sheet / ITP
label | e7cf40e5-0b17-56eb-859d-53e6aed85ee7 |  | note | vi. Covermeter check record
label | e4c32231-a7aa-5ef5-9cfd-2b38dbc16416 |  | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
label | f25c0e18-e919-57f3-8600-3b11c14a20f4 |  | note | Note: Different revisions of 610 have different clause numbers
label | 6292e597-90b2-57de-9178-7f144bec3482 |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | ec63dcd8-8c4d-5196-a9b5-0d5b16c5424e |  | note | – – – – – – – – – – – – – – – – –
label | 1866371e-ca26-55fc-bfd2-0bf7311d507b |  | note | METHOD: Document Review
label | e456f3f1-1528-5f6d-b319-215d2b8648d9 |  | note | – – – – – – – – – – – – – – – – –
label | d7db8e7b-fd70-5975-b98e-5fff2ab98966 |  | note | FREQUENCY: Each element
label | 7f174dce-1e84-54ac-b7f2-e68ab56805b5 |  | note | – – – – – – – – – – – – – – – – –
label | b2b7556e-c48a-5e97-9140-034d23512a9c |  | note | CATEGORY: HP*
label | bef86d83-8b8f-5da3-936c-5e29a2a07982 |  | note | – – – – – – – – – – – – – – – – –
label | 6c6e35fd-1209-5ff9-8eac-3ce4d6c273af |  | note | RESPONSIBILITY: PE/SE
label | 1860f806-336a-5fd5-9cad-b4444ddca148 |  | note | – – – – – – – – – – – – – – – – –
label | 17d651db-3a8c-5b7b-beeb-00136eec89ab |  | note | VERIFYING DOCUMENTS: This ITP
date | 1acaa4e7-58d8-5d84-88e5-f57a3e5b50c7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Precast Base Slab Founding
label | 1376081f-7348-5c17-b630-09264c91808f |  | note | REFERENCE: IFC Drawings
label | b88bf13f-ddda-5639-8d63-d45ad5da2e77 |  | note | Temporary Works Design
label | ab2a1ed0-ee48-595f-94ba-b5eb5f0f78fa |  | note | – – – – – – – – – – – – – – – – –
label | 0ed97020-05e0-5ecc-b6e3-4296776e72ac |  | note | ACCEPTANCE CRITERIA: Foundation material beneath the precast wall shall be inspected onsite by a qualified geotechnical engineer to ensure that soil conditions meet the following material parameters:
label | 5ded682f-e04d-5555-98cd-70c015abb8c1 |  | note | – Minimum undrained shear strength 80kPa
label | d42eb96c-6833-51d4-bf9b-194d39bcec67 |  | note | Attach: Test report or Geotechnical report
label | 2468cb9d-43df-558d-a455-b31ac77a9688 |  | note | – – – – – – – – – – – – – – – – –
label | 4732c0c8-4224-5eed-8585-7a1b38e68716 |  | note | METHOD: Document Review
label | 5a9b807a-6251-5678-b660-7e87de5b984d |  | note | – – – – – – – – – – – – – – – – –
label | e82e5c60-c1e6-5c55-81b9-842263c3c731 |  | note | FREQUENCY: Each installation location
label | 016f9013-9f62-531a-8095-486b77806b36 |  | note | – – – – – – – – – – – – – – – – –
label | f83ccb5d-b78c-5e10-bd8f-e266388800f3 |  | note | CATEGORY: HP
label | 381d0485-fa67-5fa9-b190-c5bcd88d7786 |  | note | – – – – – – – – – – – – – – – – –
label | 6a218258-cd7a-5843-8b25-43d36eb59642 |  | note | RESPONSIBILITY: Geotechnical Engineer
label | 54f0837c-dc2e-539b-b858-85be85cadbcd |  | note | – – – – – – – – – – – – – – – – –
label | 2685e8c3-d707-5807-a8a1-d95ed4ce7cfe |  | note | VERIFYING DOCUMENTS: Attached Report
date | dc3a2e6f-e13a-5935-8062-91122731d68b |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Materials Inspection Checklist
label | b4eb9e43-b93f-52d0-975a-a7f320cd5f66 |  | note | REFERENCE: 620.06
label | 136cffcb-abe6-53e7-a400-fdb6711d0430 |  | note | 620.07
label | a182bc4d-4a2f-5280-9a12-945f0a590791 |  | note | MRPA Quality Management Plan
label | 07e67926-1e64-56cd-83dc-71a3ed65cd43 |  | note | – – – – – – – – – – – – – – – – –
label | f1367bac-4e9e-5f0a-b001-ac9b94e39a60 |  | note | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
label | abd73fb7-b2e1-5d71-a72d-5e607d37a92d |  | note | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
label | 90fc60a5-daae-559d-ab06-cf45b2c4eefc |  | note | Elements shall have unique identification and orientation marked (if applicable).
label | 681afc7d-f7c4-5368-822c-a99f48ed7475 |  | note | Complete: Materials Inspection Checklist in ConQA
label | 02d29602-1760-51fe-8f36-8a2a35679e32 |  | note | – – – – – – – – – – – – – – – – –
label | 200c11e9-ea33-51b4-909b-fe9f8b40b9ae |  | note | METHOD: Measure, Visual
label | cca2496e-6b00-557b-b1e8-6f189a1376d8 |  | note | – – – – – – – – – – – – – – – – –
label | 095e1ee2-92d0-53a8-9bb5-1b954194c976 |  | note | FREQUENCY: Each element
label | 26c7f4d2-4a40-50c5-ae51-8be236512ddd |  | note | – – – – – – – – – – – – – – – – –
label | f8e1adab-9123-56b5-8669-dd5d7391b899 |  | note | CATEGORY: HP*
label | ed95de94-f6b5-512d-a2c1-8d13a4af114b |  | note | – – – – – – – – – – – – – – – – –
label | 3a2c61ff-bc8f-5945-9cf6-c068dd414bca |  | note | RESPONSIBILITY: SE/PE
label | 9c8f4862-5655-522f-8f4c-74049f5c55b8 |  | note | – – – – – – – – – – – – – – – – –
label | 39fea7c9-f5d7-581d-93e9-717cdf763546 |  | note | VERIFYING DOCUMENTS: This ITP
date | 062ec990-8cd8-5e30-a99a-babbcdf49953 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out of Precast Elements
label | 7f72a1f9-a347-57ef-8015-f7335d805239 |  | note | REFERENCE: IFC Drawings
label | 7357b2c0-136c-5954-aff2-bbdf93e65a4c |  | note | 610.46 (a), Table 610.462 (November 2018)
label | 179ecec0-a38e-526b-ac75-6a049d3269ef |  | note | 610.47 (a) Table 610.472 (March/June 2019)
label | a62ffe8d-fbfe-5b51-8c59-18ab857505f0 |  | note | – – – – – – – – – – – – – – – – –
label | 79e18867-4b90-5f49-8539-618fd481a922 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
label | ac4e6d8e-5087-5573-9ada-306f3e2f16ae |  | note | Where anchor bolts or steel posts are cast in to the concrete, ensure that these are within tolerance.
label | 3fe73320-2f29-5207-a51b-3e3ee48964c0 |  | note | If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
label | c4314fde-79eb-5c68-9590-f9a8d15b25c0 |  | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
label | ae46bd99-b16e-5d41-9d61-b6cbfb43862f |  | note | – – – – – – – – – – – – – – – – –
label | c5084a96-3e40-5752-81fc-2fa40323f9c2 |  | note | METHOD: Measure, Visual
label | b6991dfb-22e1-581c-8e12-a4db213bc5f2 |  | note | – – – – – – – – – – – – – – – – –
label | abb9a71e-27fd-5a12-8fe0-f34e03f2c390 |  | note | FREQUENCY: Each element
label | 9fd7fcfe-c2d2-50d7-b2ac-a35579c76735 |  | note | – – – – – – – – – – – – – – – – –
label | 96442538-8304-5ca6-81b0-10e3c5606702 |  | note | CATEGORY: HP*
label | 34d2baab-a6d0-53b6-aedc-f5eaa25c62ad |  | note | – – – – – – – – – – – – – – – – –
label | 2cc3dfcd-0e1f-519f-9e63-d517fa1d5d6e |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | d6ba67ea-ad89-5406-9c41-e53599cef23d |  | note | – – – – – – – – – – – – – – – – –
label | 677fa826-cca9-569b-92ad-945813c63687 |  | note | VERIFYING DOCUMENTS: This ITP
date | 4dc27164-d227-590c-ac71-317f5787fadc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Shims Placement
label | 565a6c5e-02a1-5f20-b15c-0654c20dae14 |  | note | REFERENCE: IFC Drawings
label | 077a1912-a82b-5340-a980-af9aefae6f4e |  | note | – – – – – – – – – – – – – – – – –
label | a7f2a801-31fb-5af0-a4c4-837a3131cc0c |  | note | ACCEPTANCE CRITERIA: Place the shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
label | 801f7fac-10d4-516a-804e-f8663a594bbd |  | note | Packers to allow for 50mm grout under the precast elements
label | 20e37649-db95-5f38-84fd-22cfd47e37be |  | note | – – – – – – – – – – – – – – – – –
label | 6dee86c7-ea95-54bd-b869-2277b03b807f |  | note | METHOD: Measure, Visual
label | 9223a16b-7b52-5aa2-b141-dc725d88f74d |  | note | – – – – – – – – – – – – – – – – –
label | 1362e66e-cc6a-5f00-84ec-3acb5503f14c |  | note | FREQUENCY: Each element
label | 849893fb-2e1a-5088-9521-2e16bf6c00ed |  | note | – – – – – – – – – – – – – – – – –
label | fe0a829f-4686-5803-bc75-62f92b562082 |  | note | CATEGORY: HP*
label | 3f35dd8f-1fa0-531b-99f9-a56c9ca62fbd |  | note | – – – – – – – – – – – – – – – – –
label | abcd392f-c2e9-5616-b7ed-1920dda163b6 |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | 5d2e16f8-2734-5702-8457-2d34b839a973 |  | note | – – – – – – – – – – – – – – – – –
label | 40a998f8-be62-5d4f-935b-d44ba103f09d |  | note | VERIFYING DOCUMENTS: This ITP
date | 32d5a3fb-da6a-54dc-86ca-e22568e6d057 |  | date | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Precast Handling
label | 0e0afcfd-dc6e-5993-b9b6-d9041771151a |  | note | REFERENCE: 620.07
label | c9356e38-4ac5-5d6a-9d07-9d4d20751042 |  | note | Crane Lift Study
label | cc1b23be-c860-517c-b755-c16736b94c10 |  | note | – – – – – – – – – – – – – – – – –
label | 0c2294d3-a53c-535d-bccb-ce45a82ee105 |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | b3fb9570-27bd-5852-a2ac-97f579a114d7 |  | note | – – – – – – – – – – – – – – – – –
label | 554a2b28-3807-56af-93d5-680ac9bbc51f |  | note | METHOD: Visual
label | b54bc579-86c3-5c27-9469-01463813d581 |  | note | – – – – – – – – – – – – – – – – –
label | e8acac12-d917-52e4-85e3-bad31a0c9e38 |  | note | FREQUENCY: Each element
label | 5c80aac6-5d39-53a4-8651-2fe910e6f3f0 |  | note | – – – – – – – – – – – – – – – – –
label | d27f619d-037f-5495-9455-bbad484fd357 |  | note | CATEGORY: SP
label | df665423-0aef-5a56-93ff-9744add549e7 |  | note | – – – – – – – – – – – – – – – – –
label | e6863670-c970-5243-a66a-71bed764b16a |  | note | RESPONSIBILITY: SE/PE
label | c19bbefc-1954-548b-90c3-928746a92f5e |  | note | – – – – – – – – – – – – – – – – –
label | ca759824-bcef-5558-876a-ac6cc74c0e37 |  | note | VERIFYING DOCUMENTS: This ITP
date | ab46ba79-75f2-53c8-8ec1-75cc5a8ae03e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Precast Placement
label | 44fd0900-704e-5541-9020-4ea17495c315 |  | note | REFERENCE: IFC Drawings
label | d9675d00-a031-5e9a-9e48-ed53685356cf |  | note | Temporary Works Design
label | 3488480d-3437-5c6a-9124-91ae897ddb2b |  | note | 610.27
label | 812d998a-b3a3-5220-8f41-133dd8447c88 |  | note | – – – – – – – – – – – – – – – – –
label | 62dbbe55-0a37-5653-b81c-a39ed9e22fd0 |  | note | ACCEPTANCE CRITERIA: Precast elements shall be placed into location and not released from the crane until any adjustments necessary by lifting the unit and adding/removing shims or adjusting the connecting bolts so that alignment between units, minimum end bearing, overall height and position remains in tolerance.
label | e637305a-4063-5d85-ae59-4569504fed35 |  | note | The nominal gap between elements is 20mm as per the IFC Drawings.
label | b77b3f9e-d6e6-59f5-a0ee-e7f6f924d249 |  | note | – – – – – – – – – – – – – – – – –
label | d45dbab3-82a9-5d02-ad0e-4cc0663f27b1 |  | note | METHOD: Measure, Visual
label | 0889b0a0-e43d-5d9a-8dd0-87c2e3318a57 |  | note | – – – – – – – – – – – – – – – – –
label | 87988d68-5697-568b-b1e9-47dfd8b21613 |  | note | FREQUENCY: Each element
label | d0e1c109-178c-5255-b270-2ec88991e019 |  | note | – – – – – – – – – – – – – – – – –
label | 7d731c6f-706f-591b-b9e2-eaa303548144 |  | note | CATEGORY: SP
label | 4f95dd5a-eb16-5ef3-8aca-0e24be7e696e |  | note | – – – – – – – – – – – – – – – – –
label | f430929e-1a22-58f1-88a8-4a8637e9a6d6 |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | f7488ad8-535a-5f1f-927c-38bf87a67925 |  | note | – – – – – – – – – – – – – – – – –
label | 45efa3b1-d19b-597e-ae39-a4424d2226ea |  | note | VERIFYING DOCUMENTS: This ITP
date | 59ea4000-f378-503f-9017-873d4e481064 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Waterstop Seals, Compressible Seals & Isolation Joints Application
label | eb2700f0-32f7-5dfe-a170-a378cd19a7c5 |  | note | REFERENCE: IFC Drawings, Product TDS
label | ece3d4a1-06dc-5ea7-ab53-0da76564f0d8 |  | note | – – – – – – – – – – – – – – – – –
label | f7859c53-4e3a-50d8-a3a7-8dd496310435 |  | note | ACCEPTANCE CRITERIA: Materials shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
label | d0f46c6b-bbb0-545b-8b89-eba6d372b78f |  | note | 300mm wide Bituthene placed centrally over joint. Bituthene to cover retained height of upstand and extend 100mm along top of base slab.
label | 196d301a-32e4-5aea-bece-2db2f90d5a31 |  | note | Compressible filler with backing rod to be installed on both faces
label | b4d1b93c-141b-55bf-8516-3afb7f989cd5 |  | note | Fabric Geosheet CS15F or equivalent to be installed over retained area of upstand, and over the 300 wide granular backfill for subsurface drainage, as per IFC drawings.
label | c8c57cc0-59f9-5358-9b61-cbf74c87e95a |  | note | Adhere any waterstop seals or expansion materials full height of the structural element(s) and located as per the IFC drawings.
label | e6c8c303-92e0-5e8e-98bf-0b67077ec0dc |  | note | – – – – – – – – – – – – – – – – –
label | bb008825-bbe2-5cc2-9aeb-9d14783d26c0 |  | note | METHOD: Measure, Visual
label | 44e58812-0f3b-5c62-8662-71efa6ca0427 |  | note | – – – – – – – – – – – – – – – – –
label | ce8d1abb-6da6-5dc8-ab88-3b2f59f28229 |  | note | FREQUENCY: Where applicable, each installation location
label | 7842fc77-1f6d-53b2-99b3-a5cbfeec3bd2 |  | note | – – – – – – – – – – – – – – – – –
label | 454cc3ac-cdc2-53fc-b1f4-c9d272788f86 |  | note | CATEGORY: IP
label | 187c1d65-3e89-5893-90ce-b3f831f3ae00 |  | note | – – – – – – – – – – – – – – – – –
label | dc7b59e7-ded0-5f56-84f7-43917f8e11ca |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | f5778d6a-2c0d-50b2-b3cf-436df39fb137 |  | note | – – – – – – – – – – – – – – – – –
label | 74c2f94b-e958-57e6-8580-459aab2153ab |  | note | VERIFYING DOCUMENTS: This ITP
date | 678d9c04-76a6-5f98-bfd6-99b15079fcfd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Joint Sealant Application
label | 48d9701d-55f4-53bb-9fe7-3687dcb3985e |  | note | REFERENCE: IFC Drawings
label | 0f25d8e1-10b3-55ff-a89a-f9fa55103b4b |  | note | – – – – – – – – – – – – – – – – –
label | 2ff843b5-c0ad-5818-b7a8-b8694572363f |  | note | ACCEPTANCE CRITERIA: Compressible filler with backing rod to be installed on both faces.
label | e7f2e7ad-bee1-5a9c-a818-77213a001c98 |  | note | The gap between each precast element on the retained side to have 300mm wide bituthene placed centrally over the joint. Bituthene to extend the retained height of the upstand and extend 100 along the top of the base slab
label | 3d41f669-f263-51c0-8c87-0ff3ace7ca81 |  | note | – – – – – – – – – – – – – – – – –
label | 2d909ed0-03f4-5cfb-b005-e25d8000867b |  | note | METHOD: Visual
label | 5d7edd37-aaed-5329-8f3d-5bdb19508727 |  | note | – – – – – – – – – – – – – – – – –
label | 1074150e-3c7e-5304-8cca-a225da68ed1e |  | note | FREQUENCY: Where applicable, each element
label | cd7dc012-a109-5a55-846c-40c2ab8c47bc |  | note | – – – – – – – – – – – – – – – – –
label | 259a388d-7aa5-5e93-99d5-0ce47d936294 |  | note | CATEGORY: IP
label | 101d3244-4bb6-500b-85ba-757ae33039ca |  | note | – – – – – – – – – – – – – – – – –
label | e0216b6d-c593-5ae0-b289-ed986b480e36 |  | note | RESPONSIBILITY: SE/PE
label | b2ef51ad-8900-5cbf-92ba-21fc5406b77a |  | note | – – – – – – – – – – – – – – – – –
label | 5afa04bc-fd1c-570c-9527-0a3fed73991f |  | note | VERIFYING DOCUMENTS: This ITP
date | d23be74d-4cfe-540b-96f6-219c503bcc4a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Subsurface Drainage
label | 4ad14a4d-4abd-5b18-a01e-c41df16f2d80 |  | note | REFERENCE: IFC Drawings
label | 043d0a07-6f1f-59ef-be4b-2cffca8b2350 |  | note | 702.03
label | be5d5f8a-c44c-58b7-8e7a-d1dd8b80893d |  | note | 702.06
label | 1368083f-ac49-5956-aaef-6353af1c8ea5 |  | note | 702.07
label | bb1f10ff-2feb-505b-b4c6-dceb2671fc22 |  | note | 702.09 (g)
label | 164f30f6-1548-5aec-a231-09239fa86243 |  | note | – – – – – – – – – – – – – – – – –
label | 8b2ad0f4-aa31-515a-b14a-31b2cf32fcba |  | note | ACCEPTANCE CRITERIA: Subsurface drains shall be the type nominated on the IFC drawings - 100 dia slotted subsoil drain.
label | c8cae151-9c3b-59f8-9f4f-c6018d092f64 |  | note | The drainage shall be backfilled with 300mm wide No Fines Concrete in Geotextile A64 as shown on the IFC drawings. No Fines Concrete to be compacted within 1 hour of mixing
label | 872c2881-354e-509b-a06d-7dfc092edf7d |  | note | Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
label | a5b88326-b436-59c6-93c5-2fe8f51373ca |  | note | Weep holes shall be checked for obstructions.
label | 0c509faa-c576-5fde-8dc9-2e5c04f9f8b6 |  | note | – – – – – – – – – – – – – – – – –
label | 03cb299b-cc49-5cdf-a47b-3ed6e2c0dc20 |  | note | METHOD: Measure, Visual
label | 15fa05f7-5564-513f-a45a-bb0b0f5190a8 |  | note | – – – – – – – – – – – – – – – – –
label | 6cc06d88-6af0-5763-8398-13ab66258a16 |  | note | FREQUENCY: Where applicable, each installation location
label | 5e5e1f88-7508-5f4a-8583-b379f0a76e74 |  | note | – – – – – – – – – – – – – – – – –
label | 3dd48f4b-441e-5cb0-bb00-347a78945021 |  | note | CATEGORY: IP
label | 2b3e241d-b7a2-57dc-94e4-81c15415a7fd |  | note | – – – – – – – – – – – – – – – – –
label | 57f85a23-e056-5132-996d-9ed8c8b37f7c |  | note | RESPONSIBILITY: SE/PE
label | 7f759b35-4d49-5897-bcb0-354393c8952b |  | note | – – – – – – – – – – – – – – – – –
label | cbe358fb-8387-569c-b8a7-f5f89974742a |  | note | VERIFYING DOCUMENTS: This ITP
date | b2116ad8-270f-5ef0-a153-40a9454a9ab4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Flowable Grout Pour
label | f165213a-c790-5040-8d90-72782a00b864 |  | note | REFERENCE: IFC Drawings
label | 9eaa1c84-526d-522b-91cd-794888731d37 |  | note | – – – – – – – – – – – – – – – – –
label | d5daefc0-8fbe-58c6-bc69-06992e9dbd00 |  | note | ACCEPTANCE CRITERIA: Grout shall be poured in the gap between the bottom of the precast element and blinding layer below. Utilisiing shims to ensure 50mm thick of grout.
label | 2094e041-d448-54aa-9907-c87ede6a2086 |  | note | – – – – – – – – – – – – – – – – –
label | b5988ba5-6f3e-5e34-a054-ff0c2f06ed4e |  | note | METHOD: Visual
label | b455e59e-a3f3-5c33-8b94-135c341dfb17 |  | note | – – – – – – – – – – – – – – – – –
label | eb216b0c-ad94-5778-ab36-dfb54b2636c9 |  | note | FREQUENCY: Where applicable, each element
label | cbedf4b0-5056-5ff3-a50b-2dff549d695f |  | note | – – – – – – – – – – – – – – – – –
label | 8124068f-7eb9-5be8-b9f6-c70eba220426 |  | note | CATEGORY: IP
label | b4ebb81a-a7d1-5bb5-8058-a11dec49f95f |  | note | – – – – – – – – – – – – – – – – –
label | 116cfe0d-b8e9-5789-b504-74b127e3a854 |  | note | RESPONSIBILITY: SE/PE
label | 4b4c8f4e-25f9-58d2-9fa9-3de97fa308e1 |  | note | – – – – – – – – – – – – – – – – –
label | 11761de4-612d-5537-a55e-a6733c52438f |  | note | VERIFYING DOCUMENTS: This ITP
date | 23c9e9ce-b504-5cf6-bbf6-34b7c5799c8d |  | date | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey
label | f029ed52-8b9d-5336-b442-db08868929ad |  | note | REFERENCE: IFC Drawings
label | 8d6192cd-b9c5-5189-b497-562f22fe816a |  | note | 620.09
label | f4a3c3fa-4ae0-5b95-8e6c-f509c92dce0a |  | note | – – – – – – – – – – – – – – – – –
label | 34e27a33-7e5c-5eb3-967b-27a291c3e12f |  | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | c92d4366-3f67-5556-bb8c-9e6d4759f58c |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | 64ff28c4-993d-5e08-9366-4c4d6f6f16d7 |  | note | Attach: Survey As-builts / Survey Report
label | 3a49f297-4e27-5518-b6c4-3e145df74447 |  | note | – – – – – – – – – – – – – – – – –
label | 1726f8c3-edb4-5e57-a14d-8410871d9450 |  | note | METHOD: Measure, Visual
label | 387ee268-d140-5abc-b080-a135d61ff35c |  | note | – – – – – – – – – – – – – – – – –
label | 5ba1d262-2647-54a1-9e56-8258d2a8a090 |  | note | FREQUENCY: Each element
label | 2d2fe9be-f9cf-54dd-9bb7-ab735970f217 |  | note | – – – – – – – – – – – – – – – – –
label | 0517266b-7989-5718-ac0d-e81cb2833aea |  | note | CATEGORY: HP*
label | 170aba6e-b589-533a-bc75-8e2967430875 |  | note | – – – – – – – – – – – – – – – – –
label | e1d13410-eed2-56a4-88e5-be6a957a0502 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | e7e536c2-f887-562f-92fb-507b73555523 |  | note | – – – – – – – – – – – – – – – – –
label | 7f7b38cb-89a6-5fd6-8c10-5ff30d7ed626 |  | note | VERIFYING DOCUMENTS: This ITP
date | a60e349a-86a4-5009-80d0-976b728d55ec |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | c48c67d3-2eeb-5f6e-a419-baf1bdacfb43 |  | note | REFERENCE: MRPA Quality Management Plan
label | bdca0272-ccc6-5f20-be48-e54a56336443 |  | note | – – – – – – – – – – – – – – – – –
label | 173b9883-098a-5baa-9d0e-32cce59333f2 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | a140084f-7316-55d9-99b6-acfdab4fa3fd |  | note | – – – – – – – – – – – – – – – – –
label | 4ae278e8-54ff-5968-b6d3-2fcf08843e5d |  | note | METHOD: Document Review
label | 51fcf64a-1300-5698-840c-ef6f8b82d92b |  | note | – – – – – – – – – – – – – – – – –
label | 9301b6a3-e7f6-5f85-8dbd-f175163492ed |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 222328c0-976c-5756-9ba0-1ac9a5c610d9 |  | note | – – – – – – – – – – – – – – – – –
label | d192fe65-afd1-5e1a-ab51-d86367e370c2 |  | note | CATEGORY: HP*
label | 130d8069-d0fa-51ac-879b-eded4ffab1a5 |  | note | – – – – – – – – – – – – – – – – –
label | a126c0e3-2a54-5061-ab8e-70599084706d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0fad674f-7ef3-52e0-8b4d-f33d970021eb |  | note | – – – – – – – – – – – – – – – – –
label | 3ecf732a-bc58-5dea-be05-b26634f0ac57 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5dcfc125-234e-55a5-94ba-7e132f6e78ff |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 2dd42f16-9df5-53c5-b183-39b920c5bf45 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 3989c7f3-620d-50c4-a4ab-ec768fd813ae |  | textbox | Name:
text | 5f52c0c8-ce50-5e2e-8b0a-a4aaa53b2aef |  | textbox | Position:
date | 3c110bac-b190-5424-b753-49abd7f24c4d |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-034-STR-CAMMS-Precast Crosshead (Supply & Installation) | itp |  |  |  | Yes | ITP-034-STR-CAMMS-Precast Crosshead (Supply & Installation) Rev 0 | 9ea3dbe5-2268-4e1f-b814-2658ef3b787c
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | c5c03ab1-d197-5303-8d19-5138e0ce08ba |  | note | Document Title: ITP-STR-CAMMS-Precast Crosshead (Supply & Installation)
label | 94aabaec-4876-5a81-8cb8-1e7b6df8b3b8 |  | note | ITP Description: CAMMS-Precast Crosshead (Supply & Installation)
label | 7d41edda-a077-5082-a619-c6044d6f1c19 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 8b952032-83c7-5bf1-878a-376f25513f48 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 3363a0e5-dec5-5f20-8900-523f8990de6b |  | note | Revision Number: 0
label | 3f22834d-592d-5461-9841-c4e94a8d8c34 |  | note | Revision Date: 17/05/2023
label | 0081e997-b10d-51f8-b892-98c51b3544c2 |  | note | ITP created by: Isaac El Zayat
label | a33b731e-1780-51c4-9429-67f7091d70f0 |  | note | ITP approved for use by: Victor Mira
label | fe804b0c-1742-57b1-a9ca-0a6ab74757bc |  | note | 1.1 Non Dependent
label | 8e11113a-7ace-5f5b-8ebf-73412ea7f4e0 |  | note | Reference: VicRoads Section 169 July 1993
label | 563eaa2a-42b8-565f-af1e-5c48307dc185 |  | note | 1.2 Non Dependent
label | a4a011d3-d9b4-5d9f-b2d5-93a148f1aaeb |  | note | Reference: VicRoads Section 610 March 2019
label | c2474c16-16a4-5597-9b19-5912a226c91c |  | note | 1.3 Non Dependent
label | 4e66217b-a240-5701-a012-0ae7cdbdc80e |  | note | Reference: VicRoads Section 611 November 2018
label | a379f600-47fb-5d9c-bf81-7ada16def388 |  | note | 1.4 Non Dependent
label | c572895e-3637-599f-b837-2661a7955530 |  | note | Reference: VicRoads Section 613 June 2017
label | d84de799-748b-5c25-a532-3222fb8cdb8f |  | note | 1.5 Non Dependent
label | 84a99e07-49a3-5dfb-9952-3d6da75c992f |  | note | Reference: VicRoads Section 620 May 2009
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Grout - Product Selection - Epoxy Grout
label | 8c4a8ea5-5a55-5874-952a-ab7686e29566 |  | note | REFERENCE: IFC Drawings
label | 0d5d2544-8714-554d-96a5-8b056adcb265 |  | note | – – – – – – – – – – – – – – – – –
label | a244e292-0b8b-5335-809a-76205411535f |  | note | ACCEPTANCE CRITERIA: Details of the materials and the proportions of grout mixture shall be submitted for review. Product to be selected based on the following criteria:
label | 3d4c2e3d-ade8-5cad-903e-3147688799bb |  | note | i. have the required strength at 28 days as noted on the IFC drawings.
label | b3d1c5f6-faaa-5cdd-bf2d-b150a057cf2c |  | note | ii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
text | 8afcd50d-daae-58b9-b197-f29e68867c89 |  | textbox | Enter: Teambinder Material Approval number
label | 4e5fbfed-020d-585c-a83f-ee44a94577cf |  | note | – – – – – – – – – – – – – – – – –
label | 06f193b4-eb8e-5081-95e8-139fb49f3565 |  | note | METHOD: Document Review
label | 589084bf-9c9e-5b64-8e14-44a8a4a07e9a |  | note | – – – – – – – – – – – – – – – – –
label | cdef794f-d6b4-563b-a50a-93bad80bca64 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 593556b7-90cc-541b-9b36-6d9811669fcc |  | note | – – – – – – – – – – – – – – – – –
label | c374ffe1-33ae-58ce-bf14-ef40e2373863 |  | note | CATEGORY: HP
label | ed978fed-09ca-5b66-90a8-c6ee140da117 |  | note | – – – – – – – – – – – – – – – – –
label | fa63254c-f3e6-51dd-9c16-144054c675a3 |  | note | RESPONSIBILITY: Nominated Authority
label | 20a649c6-88c3-563c-bfb5-148b1bb5f15d |  | note | – – – – – – – – – – – – – – – – –
label | ef534fe1-5fb2-5f13-b40d-3826349b9033 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0a0932c1-71f8-5815-b5a1-77db349223a1 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Precast Elements
label | d296d252-da59-566c-8fe6-0589e56b8781 |  | note | REFERENCE: IFC Drawings 610.47 (a), Table 610.474, 620.09
label | 2e521ea3-33a1-5e16-a2e7-3df9c79fd114 |  | note | – – – – – – – – – – – – – – – – –
label | dae11110-fbc0-5cdf-b217-53286208dde6 |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | d891c980-def3-5d90-8085-0ca605ccfa3a |  | note | i. Certificate of Compliance / Birth Certificate
label | 8d69f072-0e07-51c6-aa21-5f2ef22118ca |  | note | ii. Compressive strength test results
label | 99df3633-7285-51cd-b854-23eb0451ff8d |  | note | iii. Precast Lifting Design
label | 6581e9e8-23f0-5fa6-9565-d42b6faa13fd |  | note | iv. Pre-pour check sheet / ITP
label | daed7544-369b-50c5-b01e-cdf61211881a |  | note | v. Pre-stressing check sheet / ITP
label | fd081031-2d1d-5b5d-a272-5e5c2082160c |  | note | vi. Post-pour check sheet / ITP
label | 7d79754d-ad46-58a4-8361-891601dac273 |  | note | vii. Covermeter check record
label | 609cb606-8d2b-546e-8eef-7c78b9ffee68 |  | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (where applicable) shown on table 610.473
label | 84716f81-b50f-5fbf-a817-9394a9fd2821 |  | note | Note: Different revisions of 610 have different clause numbers
label | ba025fd8-6c0c-513d-8a12-aca34806b8ec |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
text | e93fba8c-2cfd-50b1-8ee7-d3eeae7a7807 |  | textbox | Enter: Teambinder Approval number
label | e4a30398-3116-50a3-95f4-a00a6209aec4 |  | note | – – – – – – – – – – – – – – – – –
label | eeb934fb-74cc-5ea1-88a4-baf59bb7008e |  | note | METHOD: Document Review
label | 08107416-5592-5801-9a94-7f62f08bf19c |  | note | – – – – – – – – – – – – – – – – –
label | ae85dfb7-be4f-540b-bffa-5eebde1c7221 |  | note | FREQUENCY: Each element
label | e77a7bec-2874-5f5e-8bf8-afa20fc1f814 |  | note | – – – – – – – – – – – – – – – – –
label | fbabd57a-d931-5e83-85cf-17f04a7aa1ff |  | note | CATEGORY: IP
label | d5be34a9-0ebc-573d-b10f-fe0a2dc229d6 |  | note | – – – – – – – – – – – – – – – – –
label | 89a562ae-eb8e-5b3f-b1d7-90e1678d2e6a |  | note | RESPONSIBILITY: PE/SPE
label | 9df77762-f3fe-5906-95a9-1a2b5f910e76 |  | note | – – – – – – – – – – – – – – – – –
label | fe3f1964-ec95-5c93-a181-3f3020fadede |  | note | VERIFYING DOCUMENTS: This ITP
date | 88e94eb4-f63d-5869-b128-23d31158b984 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Precast Element - Minimum Concrete Compressive Strength
label | d39222f4-cf50-5256-a014-6bbabe9a8516 |  | note | REFERENCE: 620.03, Ancon Lifting Design
label | c3549342-c8cc-573a-bb83-5b38a170ffc1 |  | note | – – – – – – – – – – – – – – – – –
label | f92bada4-02cd-585e-85d3-8a0d7b6a95ab |  | note | ACCEPTANCE CRITERIA: Lifting of precast units to be minimum concrete compressive strength of 20 Mpa.
label | b4d08ed9-bd39-529e-8170-57992a108c13 |  | note | • Ancon lifting design requires minimum concrete compressive strength of 30 Mpa.
label | 11148c5e-044f-5083-942e-ac1d143ed340 |  | note | • Verify compressive strength test results prior to lift.
label | a159e537-f6a8-5b86-bbd9-397eb5c81e0b |  | note | – – – – – – – – – – – – – – – – –
label | 58266641-9009-587a-8d46-d4a2e299e595 |  | note | METHOD: Document review
label | cb892667-2451-5cd1-a483-12ba3442eed3 |  | note | – – – – – – – – – – – – – – – – –
label | cefe0045-a6b0-5522-9c95-7eb2547d71bc |  | note | FREQUENCY: Each element
label | 78b71789-a00a-5633-a0ce-93c18ad6953f |  | note | – – – – – – – – – – – – – – – – –
label | 69dc8b75-8158-5b79-856c-87a03b3f1bba |  | note | CATEGORY: HP*
label | d01c7fa7-e6df-545a-bb1c-270b495a51bb |  | note | – – – – – – – – – – – – – – – – –
label | 7aeb2797-ec2c-5cd3-8240-5a21db583c3d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7ac7de11-d179-545e-ba72-1039a926e77e |  | note | – – – – – – – – – – – – – – – – –
label | 9c0175a0-b980-57c9-983c-91d00c139bac |  | note | VERIFYING DOCUMENTS: This ITP
date | 384af615-d192-5f0d-9981-e0d7266a2a28 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 IFC Drawings
label | 99a589af-b18c-5c22-bcfc-ba6918eb32b8 |  | note | REFERENCE: MRPA Quality Management Plan
label | e39fc129-0e4f-5a51-a0a6-19c7143797a4 |  | note | – – – – – – – – – – – – – – – – –
label | 847f5b42-9ceb-59b3-bed9-90de7dae63c6 |  | note | ACCEPTANCE CRITERIA: Revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 4f70ada3-82c7-5b1d-a286-82064fb8273f |  | note | – – – – – – – – – – – – – – – – –
label | 404da320-83fa-5e00-bef0-395b369af30f |  | note | METHOD: Document Review
label | 5dc36d1d-b131-52a6-918a-f870a201ce4a |  | note | – – – – – – – – – – – – – – – – –
label | c89cef88-c667-51eb-afba-e38026814c4a |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | c8a621b1-6bff-5906-a3ba-7c4c35a88e74 |  | note | – – – – – – – – – – – – – – – – –
label | d48c2366-31d4-5692-8709-280f1403aba9 |  | note | CATEGORY: HP*
label | d32fd8e4-d7f9-54e8-b233-86f19ae14be7 |  | note | – – – – – – – – – – – – – – – – –
label | 5e6b0251-71fa-55e6-8f49-471902cc519f |  | note | RESPONSIBILITY: All
label | 9494412d-7d84-572c-be76-5032da4c697c |  | note | – – – – – – – – – – – – – – – – –
label | d0c6f342-1000-5c22-b5de-d3b6c99e8762 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8c66c683-60b6-55e0-a417-f5adf7a66dd2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Survey Set-out of Precast Elements
label | 7e1a5490-785d-5a35-9f15-266066decbaa |  | note | REFERENCE: IFC Drawings 610.47 (a), Table 610.472
label | e51c8805-37bc-5bd7-afa1-2132e509283c |  | note | – – – – – – – – – – – – – – – – –
label | a5cb3588-6a5b-5d8d-8880-16399c2a6408 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the Table 610.473 as applicable to the element.
label | 2ae5a4fd-454e-52e0-b851-3f5923de2b70 |  | note | – – – – – – – – – – – – – – – – –
label | 2593f2e1-a90f-5083-bf16-826a240d3111 |  | note | METHOD: Measure
label | 0e7e5e26-298a-5410-b612-af13d8e9b53d |  | note | – – – – – – – – – – – – – – – – –
label | 701f7acb-5fdc-509a-af03-2c25c69fbbb7 |  | note | FREQUENCY: Each element
label | fed068fb-f4ef-5887-af2e-4c88937f31ad |  | note | – – – – – – – – – – – – – – – – –
label | 0d4bad25-723c-5e7f-a609-7a7aa5f892f3 |  | note | CATEGORY: IP
label | 65b1c31f-1619-56cb-8778-2dcee6c5636d |  | note | – – – – – – – – – – – – – – – – –
label | 358ed924-1337-5216-bce7-d94a41bada14 |  | note | RESPONSIBILITY: Surveyor, PE/SPE
label | 3f0637a2-5541-5022-8d27-05feef5e726d |  | note | – – – – – – – – – – – – – – – – –
label | d0c11c34-6d7a-534d-886b-831117bfafb0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1cdc370f-3054-59f9-b0c0-d43a381b3daf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Scabble (Green Cut) Column
label | b9d412cc-d8d7-59d3-99fd-a0d4e5192bc2 |  | note | REFERENCE: 610.2
label | 77d12098-446b-5ca0-8b1c-da6307dd591a |  | note | – – – – – – – – – – – – – – – – –
label | 0f013922-ee8c-556b-88ed-dfc2de91ae2c |  | note | ACCEPTANCE CRITERIA: Construction joints shall be prepared to produce a well-bonded interface between hardened concrete and freshly placed concrete.
label | 615d8057-2596-5cee-ba4f-f300a121d213 |  | note | • 3mm of coarse aggregate to be exposed.
label | ae7d6831-388f-5faf-861c-a3b2a538d3de |  | note | • Surface to be moistened, with excess water removed.
label | 8a6be621-9a78-5439-84b2-5f94a2a7a853 |  | note | – – – – – – – – – – – – – – – – –
label | 406f0d35-226e-5956-b934-ebc1294c5770 |  | note | METHOD: Visual
label | 990ab891-9bae-5873-91fa-233bec362875 |  | note | – – – – – – – – – – – – – – – – –
label | 8d973082-4b42-59be-93e8-6f8ad7196b44 |  | note | FREQUENCY: Each element
label | d1c40093-0639-5e58-9f5d-b6d50d81c223 |  | note | – – – – – – – – – – – – – – – – –
label | 40867c07-b56f-5b65-ab14-fa99834b1235 |  | note | CATEGORY: IP
label | 437f1c68-5174-573e-b12f-386b1e959d49 |  | note | – – – – – – – – – – – – – – – – –
label | a5fbcd78-bce5-551d-a8a6-c5f5d65378e9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7c322145-be8d-59be-96e6-7454aaff03f6 |  | note | – – – – – – – – – – – – – – – – –
label | c4a6b9b6-54e3-5dda-aa0e-7c3435bba564 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6b77e98d-999b-5f27-bb50-3f4cf3389d51 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Install Packers
label | f11a361c-7490-5526-985d-6a22bbe3404c |  | note | REFERENCE: IFC Drawings, Temporary Works, Table 610.472
label | 49af8700-17db-5054-b485-d6b0580bfeb1 |  | note | – – – – – – – – – – – – – – – – –
label | c0125aab-37df-5ecc-840e-a01db73e8dbc |  | note | ACCEPTANCE CRITERIA: Place packers to the survey marks at each column in accordance with approved temporary works and tolerances.
label | 0a3c7220-0148-52a2-a4c0-36a1d8a1099c |  | note | • Scabbled surface to be levelled where packers to be placed.
label | 020f8aea-eb79-5911-8077-ddd389d3dc01 |  | note | • Packers to be checked for survey tolerance of crosshead reduced level. (±10mm for reduced level for piers as per 610.472 (ix))
label | f35b2a44-c186-547e-aa3c-2d69cfb5da3a |  | note | – – – – – – – – – – – – – – – – –
label | 64e59584-a421-5b33-baec-4d8bfa69028f |  | note | METHOD: Measure, Visual
label | 98e06c92-8cda-5953-a26a-945dde4f66f5 |  | note | – – – – – – – – – – – – – – – – –
label | d76ead67-6097-5500-ae80-6fc89de36a32 |  | note | FREQUENCY: Each element
label | 286b6afc-b3c4-5998-aed8-203a4558558d |  | note | – – – – – – – – – – – – – – – – –
label | ffe8b812-2578-5043-9e71-37b223cc1b4a |  | note | CATEGORY: IP
label | 4c7fd559-d990-578e-8e16-6106e9e572fe |  | note | – – – – – – – – – – – – – – – – –
label | d85a0f23-f8b3-5851-8b4d-4f6c7cf102cb |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | febb8ad9-00fe-5424-8025-d3831ded24e7 |  | note | – – – – – – – – – – – – – – – – –
label | 2985e565-a0f7-5ea1-a9ff-bc4c06169d8f |  | note | VERIFYING DOCUMENTS: This ITP
date | c5b96d23-f4e2-5d5d-ac20-5e3507649f31 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Bleed tube
label | 85819e6a-a8a4-552a-89c5-c802960684a6 |  | note | REFERENCE: IFC Drawings
label | 2b76e5c2-3706-58fc-802e-6125b581b0e8 |  | note | – – – – – – – – – – – – – – – – –
label | 33df8160-94cb-54fc-b8c8-55ef268500fd |  | note | ACCEPTANCE CRITERIA: Minimum 3 No.Bleed tubes per pile are installed
label | ac3cda62-b969-5eef-be13-2a858dd787a2 |  | note | – – – – – – – – – – – – – – – – –
label | f577052d-a4ab-528d-91ca-7a2feca23e64 |  | note | METHOD: Visual
label | 71dcaded-d13d-5a53-977c-e2c553f450e3 |  | note | – – – – – – – – – – – – – – – – –
label | a7a28e55-340a-5046-9de0-c7d9ba1cc946 |  | note | FREQUENCY: Each pile
label | 85f75a82-a6ef-56cb-b431-3244a50fa784 |  | note | – – – – – – – – – – – – – – – – –
label | 0005b791-e6cf-539a-9cfb-4bd7cd7c8249 |  | note | CATEGORY: IP
label | 984563db-66c8-5476-8b5e-e4088af277db |  | note | – – – – – – – – – – – – – – – – –
label | 2e62b3bc-345b-5e06-94f5-043f84fe0026 |  | note | RESPONSIBILITY: PE/SPE
label | 45bd67c6-d421-58b5-ae8f-91b69ee992a8 |  | note | – – – – – – – – – – – – – – – – –
label | b96cd6c7-2c8e-5ba0-bb3c-7d8cd107f2ed |  | note | VERIFYING DOCUMENTS: This ITP
date | 001177f5-74b9-5a44-a684-f75deffcec7d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Sealant & Bleed Tubes
label | 7c11c951-10f2-50a7-bd21-9de2f5fa4047 |  | note | REFERENCE: IFC Drawings, Product TDS / Application Guide
label | cd1e28a3-5cbe-5aba-89db-311c4d1e66d7 |  | note | – – – – – – – – – – – – – – – – –
label | b0589bc8-8104-509d-aea9-b537d07376fc |  | note | ACCEPTANCE CRITERIA: Seal perimeter of column, excluding 3 No. min bleed tubes per column to be equally spaced.
label | 0fb43ddf-f925-527d-a03a-0dd97379ccde |  | note | • Thin layer of wax compound to be applied to forms to minimise grout sticking.
label | 6e53a636-6cc6-5441-baca-743f837a1f90 |  | note | • Do NOT pre-soak when using resin based grouts.
label | 7734465f-7b1a-5b66-8db0-22fe905feb60 |  | note | – – – – – – – – – – – – – – – – –
label | c18ac9d8-55cb-57aa-8dcd-1e2551dd9049 |  | note | METHOD: Visual
label | 8b17dab8-a3e1-5aaa-a382-54d12e973e4d |  | note | – – – – – – – – – – – – – – – – –
label | 5d5a94ae-7d6f-5d73-91f4-7abb5a62b7f8 |  | note | FREQUENCY: Each element
label | 124a14e5-3ac6-5e8d-802e-29fc30278f7f |  | note | – – – – – – – – – – – – – – – – –
label | 12122738-d667-5efa-b79d-f70a2545a7ed |  | note | CATEGORY: IP
label | fb3d3d8b-ff19-58cd-9581-76d03922e452 |  | note | – – – – – – – – – – – – – – – – –
label | 4822f1e5-b6f8-5918-9907-8b6d20798315 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f579e0e0-5dc9-5873-9333-6a56d3c3138e |  | note | – – – – – – – – – – – – – – – – –
label | 87141861-4e08-5cf0-b768-cd1001058df0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 338a7c3c-0db9-58fa-b8cf-2128feeefa16 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Grout tubes
label | 86c6fb2d-787a-577f-aa51-d42ef7bed24e |  | note | REFERENCE: IFC Drawings
label | 8d2c75cd-93f9-5fb9-955d-009e55153d04 |  | note | – – – – – – – – – – – – – – – – –
label | 9f851ae8-5677-5690-b362-fae50a334eb0 |  | note | ACCEPTANCE CRITERIA: Grout tubes are inserted to the bottom of the corrugated sheath (Duct)
label | 88d7ab24-1106-5df1-a605-7b47c1a863f6 |  | note | – – – – – – – – – – – – – – – – –
label | c30ca5db-eef7-5415-948d-8cf94aedd524 |  | note | METHOD: Visual, Measure
label | a3933093-c785-5dc2-98fd-6e393cfc53e9 |  | note | – – – – – – – – – – – – – – – – –
label | 2357cc05-a66b-524e-b32c-3383dfd91dbb |  | note | FREQUENCY: Each Duct
label | 44809ac7-3708-5cbd-a25a-ab56304d979f |  | note | – – – – – – – – – – – – – – – – –
label | 7b6ac86b-b4b8-5a21-9f9f-e11fececf3cb |  | note | CATEGORY: IP
label | fc7b5b5e-db51-5319-b917-537ee88e1235 |  | note | – – – – – – – – – – – – – – – – –
label | eea0f3c1-4f33-5119-8942-9a671a65d511 |  | note | RESPONSIBILITY: PE/SPE
label | c5ae3c3f-1731-5b3c-9db3-2d2f48998560 |  | note | – – – – – – – – – – – – – – – – –
label | 1bfdd34c-4eea-5b3d-8a92-d7d1e77475a0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1e29e203-a40e-58a7-a44a-e38e8c1fed13 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction/Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Precast Handling
label | 9d9dcd92-b440-5ce2-b13c-5dc6c3e9158d |  | note | REFERENCE: 620.07, Crane Lift Study
label | 6f27fa8b-ba7a-5342-8618-9f8aac31f422 |  | note | – – – – – – – – – – – – – – – – –
label | 3df147d0-2e38-51b4-8e79-3df73075a008 |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | c877b6c0-8b80-552e-8443-912d9b48aac4 |  | note | – – – – – – – – – – – – – – – – –
label | 83c1624b-edd6-5156-a888-e11a890a732d |  | note | METHOD: Visual
label | d754bd79-ff60-5673-8f14-a48d47eb47da |  | note | – – – – – – – – – – – – – – – – –
label | 675cab33-2cdb-5b63-9130-8d79a7aefcd5 |  | note | FREQUENCY: Each element
label | 12b24854-ecc6-5255-92e7-539edef6b461 |  | note | – – – – – – – – – – – – – – – – –
label | 91e1c0e0-4446-5a4e-9462-ddd1421edc3b |  | note | CATEGORY: IP
label | f3694a8f-bb18-542f-9935-bcc6826b0278 |  | note | – – – – – – – – – – – – – – – – –
label | d150f188-5958-587c-b04d-7bdb85b2e838 |  | note | RESPONSIBILITY: PE/SPE
label | be91df35-10af-568d-8830-bd6c505d403d |  | note | – – – – – – – – – – – – – – – – –
label | 717f2b50-02c0-5a42-a328-af62679e1693 |  | note | VERIFYING DOCUMENTS: This ITP
date | de8c720d-0a1f-50d8-b2f6-36033a9365c9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Precast Placement
label | fa8468ce-a9fe-50e8-be7e-ef747890a287 |  | note | REFERENCE: IFC Drawings 610.27
label | 3856bf33-f765-53ba-82af-ab2568173fc9 |  | note | – – – – – – – – – – – – – – – – –
label | 31e30e80-39fb-5ea4-805b-73bb5d009e15 |  | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | e8c40e8b-2a3d-55e7-8f99-a2b08cd7047d |  | note | ○ The Gap between precast crosshead and pile
label | 6f5060d2-15d7-51b3-a1f5-0f28be4e6b7c |  | note | • Min 15mm
label | 0c964363-a53a-5ce2-a099-f93756056e3a |  | note | • Max 30mm
label | caca5ccd-0913-58f6-aa78-0177617225da |  | note | – – – – – – – – – – – – – – – – –
label | 7710aa4e-25f4-5778-a119-ffa55fb731f7 |  | note | METHOD: Measure, Visual
label | 02d0c886-edc6-5a96-90e3-aa01761da8cd |  | note | – – – – – – – – – – – – – – – – –
label | 5990e65e-4442-5e35-b987-4af084e051b3 |  | note | FREQUENCY: Each element
label | 94008207-59fe-5db7-b416-dfaa08aea734 |  | note | – – – – – – – – – – – – – – – – –
label | a04ac06d-d3cb-53ea-89d7-c8b58d22b564 |  | note | CATEGORY: IP
label | de18b2eb-41d5-5c2d-874d-5c5eeddf0f1a |  | note | – – – – – – – – – – – – – – – – –
label | 72f3fb77-685d-53f5-97aa-09ea61f77a77 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | eba68601-cfde-5b5e-81d1-ff0bc45b4655 |  | note | – – – – – – – – – – – – – – – – –
label | c183db0b-ff29-5927-82b7-1f0e79e1ce30 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6eefb79f-65ff-5ce2-8882-aebc0e3cadbe |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Grout mixing
label | d67740d1-7e86-5ff5-9ad2-e1089f8f785b |  | note | REFERENCE: Manufacturer Instruction, Product TDS / Application Guide
label | dc4e60a8-d1ba-50ce-908f-39f92b8d9303 |  | note | – – – – – – – – – – – – – – – – –
label | 1b98d2c6-e197-5b4c-b79f-1f5cc6827074 |  | note | ACCEPTANCE CRITERIA: Pour the entire contents of the hardener pack into the base container. Mix the hardener slowly into the base using a slow speed heavy duty mixer.
label | d9a08801-d611-58f6-a876-51cb1cadd738 |  | note | • Once combined the product should be mixed at 350 to 400 RPM for 2 to 3 minutes until a uniform mix is obtained.
label | 7e29bf9b-26f5-537b-8ed6-89a11e573316 |  | note | • Pot life @ 20 degrees celcius: 30mins
label | 36b8ff31-2bea-55b8-a005-bf40cace68ed |  | note | – – – – – – – – – – – – – – – – –
label | ab6207a0-50ac-5cd7-a773-926968740bc5 |  | note | METHOD: Visual
label | 706e74dd-451b-54c5-afd8-9629185eb1b1 |  | note | – – – – – – – – – – – – – – – – –
label | e95bba7a-ae18-5d04-8690-daf02a3814db |  | note | FREQUENCY: Each duct
label | fb8a13f5-cf27-5328-9859-d74bfe348473 |  | note | – – – – – – – – – – – – – – – – –
label | 0381cfdf-50b0-569b-a93c-5b4b218d138a |  | note | CATEGORY: HP*
label | 852c8463-1366-5ef6-b61c-fdfc30de16ed |  | note | – – – – – – – – – – – – – – – – –
label | 6d1db5aa-5e1d-5b2c-a99e-1e4b9b7bfcda |  | note | RESPONSIBILITY: PE/SPE
label | a4c5c95c-8636-5244-ac1e-ff7157507ad3 |  | note | – – – – – – – – – – – – – – – – –
label | 4d8878a7-3b73-5310-95f1-5cde75ad41f0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 57849088-b8a8-5ee1-b190-f13a6c00af74 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Grout injection - Bleed tubes
label | 24c8e96c-c128-56f8-9489-8241b88ab6c3 |  | note | REFERENCE: IFC Drawings
label | ed4034d0-b9ed-5952-a104-a732bd7915f0 |  | note | – – – – – – – – – – – – – – – – –
label | 176d24f4-3b30-5906-b0d4-11c74d9aea17 |  | note | ACCEPTANCE CRITERIA: Grout allowed to flow until all bleed water is expelled and grout flows freely from each bleed tube. Then lock off bleed tube.
label | 626af2ea-4c65-5984-b163-ed8bfae1623d |  | note | – – – – – – – – – – – – – – – – –
label | afeeb3a0-4f22-52e9-ad2a-b1260e6d1760 |  | note | METHOD: Visual
label | ad88ac73-df8f-5b19-9738-cc172ca05fd0 |  | note | – – – – – – – – – – – – – – – – –
label | 5411c318-ca78-5962-9482-218422213b08 |  | note | FREQUENCY: Each duct
label | 9a259ca9-27cc-51b1-8ec8-246eabe67f01 |  | note | – – – – – – – – – – – – – – – – –
label | 66b76ed3-80e9-57a2-b1e1-0838e4af2235 |  | note | CATEGORY: HP*
label | a6c21cd3-3c83-5778-9182-7cd2adac26b7 |  | note | – – – – – – – – – – – – – – – – –
label | 3f4145b6-ce67-5cf7-89fb-25bd4828aa1a |  | note | RESPONSIBILITY: PE/SPE
label | f04dc13f-2db7-57dc-a2bc-274e907d8dea |  | note | – – – – – – – – – – – – – – – – –
label | e07ea46a-8ddc-50b2-9c73-06d57c5cd6dd |  | note | VERIFYING DOCUMENTS: This ITP
date | d6d7a425-594f-58a4-85a6-4ac6be9b018d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Grout injection - Ducts
label | 9f6e1714-1955-591a-bb79-127f55b9b21d |  | note | REFERENCE: IFC Drawings
label | 4d58d944-e990-569e-8b4c-7fdc7772da79 |  | note | – – – – – – – – – – – – – – – – –
label | 706ac581-4a36-549e-b563-6f07bcbb7a93 |  | note | ACCEPTANCE CRITERIA: Grout injected in a continuous pour until grout emerges from the top of all ducts
label | 6674cde3-c688-501f-a8f3-79a81344bfdc |  | note | Attach: Completed Grout Pour Checklist
label | aa2b8c1e-4c3c-57fd-a061-b9b842357898 |  | note | Attach: Completed Grout Pour Record
label | fdc0aa96-ae23-5ec9-b548-628b0ebc74b8 |  | note | – – – – – – – – – – – – – – – – –
label | c41e1350-e00e-57a3-a9b5-009744953de1 |  | note | METHOD: Visual
label | 347e91b1-daeb-5ab0-83ef-442f9d4e8d65 |  | note | – – – – – – – – – – – – – – – – –
label | ccef69b9-889e-55a6-8e2e-8eb86edff793 |  | note | FREQUENCY: Each pile
label | b28e81f4-7f18-529d-a7ff-1e673c244b25 |  | note | – – – – – – – – – – – – – – – – –
label | a07380b5-ce0b-5961-8301-8a05000c28bd |  | note | CATEGORY: HP*
label | c1062077-ba45-5ef9-b2b8-bafb5fe5ef3e |  | note | – – – – – – – – – – – – – – – – –
label | 0a066296-a0ab-5b62-a2b7-6aeab36c4cd5 |  | note | RESPONSIBILITY: PE/SPE
label | 6f7a98d5-7a6c-5b34-a4b6-19d78ae28e4a |  | note | – – – – – – – – – – – – – – – – –
label | 96783f2b-6709-52a9-926a-8ef6692a606c |  | note | VERIFYING DOCUMENTS: This ITP -Grout Pour Checklist
date | 28e89b86-454b-5e34-a463-129269e8eaf0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Testing - Sampling Frequency
label | 58c35a9e-693b-5ef9-a71a-39c09c435e3f |  | note | REFERENCE: IFC Drawings 610.28, 610.33
label | 739ca2c1-a46e-5293-8e65-a5e1549b88ce |  | note | – – – – – – – – – – – – – – – – –
label | 2d081cd9-0010-5245-8931-3cf934d8a23b |  | note | ACCEPTANCE CRITERIA: Three (3) 75 mm test cubes shall be taken from the first batch of material mixed.
label | 42fb201c-a5c6-5f82-84b8-16cd21c873c7 |  | note | • Three (3) 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength.
label | f49dcfcb-dd4e-5007-bb78-e92b7dd3fda0 |  | note | • The cubes shall be cured for seven days under laboratory-controlled conditions
label | ac55cc8e-f0d8-56ba-92f5-00b6e731ed5a |  | note | • Test cubes shall be made in rigid steel moulds, cured and tested in accordance with AS 1478.2.
label | b18955af-0834-5b5e-ac49-c612babf4e8f |  | note | • The contact face of the concrete shall be flat and have a surface roughness between an amplitude of 0.5 mm to 1.5 mm, with a surface presenting similar to Grade 40 grit sandpaper.
label | d00ee945-61ca-51c8-9f6d-06bfa44d83b7 |  | note | – – – – – – – – – – – – – – – – –
label | 3adb51a1-b6ea-56b5-aa0a-6d15c72bdc88 |  | note | METHOD: Measure, Visual
label | 152873ae-bcd3-5d21-a181-89b0e1c05853 |  | note | – – – – – – – – – – – – – – – – –
label | aae3787f-d3cb-5919-8e41-129809c79de5 |  | note | FREQUENCY: Each element
label | f47298d3-d3e9-5687-b4e3-f5e3abac3e51 |  | note | – – – – – – – – – – – – – – – – –
label | 381099f0-d099-5de9-9aaf-d0fb4856cceb |  | note | CATEGORY: IP
label | 2dd0706a-9147-55d0-81de-d26a35e9b6d1 |  | note | – – – – – – – – – – – – – – – – –
label | 8907d6dd-e021-5d64-a761-9ced6764b613 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a6659eee-912f-5734-ac0c-2e234dece909 |  | note | – – – – – – – – – – – – – – – – –
label | 7c12f06a-62d3-5d02-bcbb-4cef810a0b4d |  | note | VERIFYING DOCUMENTS: This ITP
date | dd302582-aa87-58a9-aabf-0ae456d7dace |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction/installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Grout Compressive strength test results
label | b989a703-14f7-557d-bbc8-05c0f2b6f516 |  | note | REFERENCE: IFC Drawings
label | c7230165-e3c1-5d2a-af03-7deeaf6a1b96 |  | note | – – – – – – – – – – – – – – – – –
label | e845b254-1f4f-5b73-b900-77700eef9c61 |  | note | ACCEPTANCE CRITERIA: Two (2) cubes shall be tested at seven days and the third cube at 28 days to confirm compliance with the minimum compressive strength requirements.
label | 3198c39f-974e-575f-914b-f79184224f4f |  | note | • The minimum compressive strength of test cubes shall be50mpa At 28 days.
label | b4040cfc-874c-568c-be48-7d1a0ec3af04 |  | note | ATTACH: Complete Test Results
label | f227546c-06cd-59b5-82fa-397eadb8c6f9 |  | note | – – – – – – – – – – – – – – – – –
label | 4e02c2ef-587a-51b3-92ec-6429702b57e9 |  | note | METHOD: Document Review
label | dba90b80-568e-5a05-ad67-dc40722f9bbe |  | note | – – – – – – – – – – – – – – – – –
label | 65cf630a-974d-5dcd-9833-7d2ebc5188c6 |  | note | FREQUENCY: Each element
label | a1b1c34e-c4e6-52d5-8c02-5ade7b6e8118 |  | note | – – – – – – – – – – – – – – – – –
label | e8812486-0d18-5657-86e0-bfae10ca9463 |  | note | CATEGORY: HP*
label | bcd90af3-2005-5a72-b94c-9ce09c2f0c5c |  | note | – – – – – – – – – – – – – – – – –
label | f7ffa0f4-b5dd-577a-9dab-26f1a4f9ffb7 |  | note | RESPONSIBILITY: SE
label | ae7553b9-001e-5546-b804-2f1488e59038 |  | note | – – – – – – – – – – – – – – – – –
label | eb3a10b1-a73f-52f6-872a-35c31f3f2811 |  | note | VERIFYING DOCUMENTS: This ITP
date | 93ca194c-de39-5e82-acb6-64480f86fa91 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 As-built Survey
label | 5cf89e1a-a8a7-5f5e-96b4-7a171adb8d6e |  | note | REFERENCE: IFC Drawings
label | 3a4040c1-9870-5685-bc1c-2e2288e46652 |  | note | • 610.46 (a), Table 610.462 (November 2018)
label | dca5c941-5d04-5c98-8901-31ec4fb0c701 |  | note | • 610.47 (a), Table 610.472 (March/June 2019)
label | aea10af9-31a9-52b8-b23e-0a784abc5369 |  | note | – – – – – – – – – – – – – – – – –
label | faa2aebd-7763-507c-b05b-2c89536febde |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
label | 3d85a6f8-e327-54f9-a042-581a3a3c4cab |  | note | Attach: Survey As-builts / Survey Report
label | 8b900112-b4a2-51f6-989e-7ee4ef341785 |  | note | – – – – – – – – – – – – – – – – –
label | 94dfe17a-6a63-52ba-8eb2-f4d1a72e74b9 |  | note | METHOD: Document Review
label | 8bf5cbd8-a9cb-5aad-a390-e77c0f4ff13d |  | note | – – – – – – – – – – – – – – – – –
label | 9f776141-3265-511f-a502-3800e4ce6a98 |  | note | FREQUENCY: Each element
label | 3ccd45ef-e0f7-50b3-b6e9-4d4783637ff5 |  | note | – – – – – – – – – – – – – – – – –
label | 58f1f571-5cba-53e6-8e32-21ad272a8f08 |  | note | CATEGORY: IP
label | 85020d8e-4c8a-5222-a330-9559dd1606f3 |  | note | – – – – – – – – – – – – – – – – –
label | 28e0af10-c6c6-5ca8-b20c-30b329e94510 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | ace9e20b-76c4-5ca1-b927-ce461877c975 |  | note | – – – – – – – – – – – – – – – – –
label | 716ab93a-bb9e-59f6-a105-02429afe219e |  | note | VERIFYING DOCUMENTS: This ITP
date | 372432c6-91b3-5fe8-9f1a-bb0b395d62a4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | 78fd717d-d2a2-5685-a1e2-1a16fa3eaac0 |  | note | REFERENCE: MRPA Quality Management Plan
label | 249a8c7e-71ae-5bcc-8142-5daf55eaed92 |  | note | – – – – – – – – – – – – – – – – –
label | 1eeb387e-a55f-5e71-9b49-a98d35da8030 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 038a3026-e42c-55cf-a268-301e2a71d336 |  | note | – – – – – – – – – – – – – – – – –
label | f688388f-7c68-576a-86d5-ec497a7166ed |  | note | METHOD: Document Review
label | 968e25a7-1fad-5095-b6fc-fc45fdd12c01 |  | note | – – – – – – – – – – – – – – – – –
label | 27884cb6-be06-52d5-b369-d1e80b1a8b3e |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 739facba-695c-546d-9941-01fe7cd59ab7 |  | note | – – – – – – – – – – – – – – – – –
label | 4c42d02f-d747-552c-ac8a-5fcf449f3359 |  | note | CATEGORY: HP*
label | ed9464ce-3b8e-5124-b89a-51bdba8677c3 |  | note | – – – – – – – – – – – – – – – – –
label | c616ce7e-2243-5f87-9404-3eab4db549bb |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4402b19f-92bb-5105-aed7-8f992899393c |  | note | – – – – – – – – – – – – – – – – –
label | dedf9533-a88e-59d0-82b0-a890bedecde0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8eeefe2e-b238-59f9-be3b-fded92f800a8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 78537981-6868-5a70-a4d7-7031bc1e39d3 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 01d412ab-087d-5c77-980f-4d0951e3892f |  | textbox | Name:
text | 783b58c9-ab04-5282-9d0b-52cee7e9c7e1 |  | textbox | Position:
date | 1e6593e6-7780-5b9a-b9a6-19ac8ceec9b2 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Ausnet Conduit Bore Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Ausnet Conduit Bore Rev 0 | ab7ef30d-9104-43f1-81a8-85781b69b393
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1 - Referenced Documentation
label | a26e48ca-b62c-51ca-8723-7ab126cffe3e |  | note | Document Title: Ausnet Conduit Bore
label | 30c8b4d5-4fe9-5295-adc4-47450294b45c |  | note | ITP Description: Ausnet Conduit Bore
label | 9c308e30-e4b0-5a8d-b7af-3b006641a8d9 |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | 91b37566-1552-5d58-8638-cde75f95933b |  | note | Revision Number: 0
label | e41ffb9f-bd40-5eaf-ba98-7acedefbf593 |  | note | Revision Date: 29/07/22
label | dda31d16-1b1e-5b22-85cc-2f96ce9ce57c |  | note | ITP created by: Michelle Lim
label | 99dbeb7e-3aeb-50ef-90d3-381b7810fa29 |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | bc9916e0-20c6-59a2-87b6-1615ffd8efdd |  | note | Reference - IFC Drawings
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependant
label | 0b9f5de9-b824-5e8e-9daa-e5f959b24395 |  | note | Reference - AS 4799-2000
checkpoint-group |  |  | section | Preliminary Works/ Materials
checkpoint-status |  |  | checkpoint | 2.1 - Electrical Conduits
label | 2343d2fe-2fbf-58f3-a170-3631321a40fc |  | note | Reference - IFC drawings
label | da2bd1ba-c775-5868-a730-b8caf76a41de |  | note | Acceptance Criteria - Conduit crossing railway to be heavy duty PVC 150mm Id/180mm OD Grade PE100, SDR 13.6
text | 6964125a-a17b-57b2-84af-b8d4d02f7345 |  | textbox | Reference:TeamBinder Material Approval Number:
label | 29590f1f-f2bc-5bde-b12d-3a36f06a6472 |  | note | Method - Document Review
label | e6b2bc50-f99b-5912-8303-16252bef7a44 |  | note | Frequency - Prior to commencement
label | fd5d8759-b47e-5c94-b6f8-58e28e24d3ae |  | note | Category - HP
date | 92bc40ef-ca10-5d7b-b318-4b26bb007cf8 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Grout
label | 75c1fa61-6377-5e69-8af8-4659f9163703 |  | note | Reference - IFC drawings
label | 91bc332c-dd2d-5b3d-8967-3b49547074e7 |  | note | Acceptance Criteria - Cement based grout shall be flowable, self leveling and non-shrink
label | 93c779a7-ea85-576e-a5d1-eb8db5984434 |  | note | Grout of the minimum UCS of 2Mpa at 28 days shall be used to fill the abandoned conduits
text | 850d6ace-d689-570b-91f9-ac9d9bd4cc53 |  | textbox | Reference:TeamBinder Material Approval Number:
label | 9b099fd6-ff6f-5cf4-ac7f-3055ee1d302a |  | note | Method - Document Review
label | 9c5d70ed-4d41-5f33-87ae-825287748566 |  | note | Frequency - Prior to commencement
label | 8735742d-2fa8-5080-81a5-f1777e90bbd3 |  | note | Category - HP
date | 05b7f63c-347b-567c-b685-c82a50a43146 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminary Works/ Procedures
checkpoint-status |  |  | checkpoint | 3.1 - Check that current revision drawings are being used
label | 99777746-3b6b-54a3-bdbb-5ad15a4628cd |  | note | Reference - IFC drawings
label | 81a0fcc0-4396-5285-a79b-d6fa80110be2 |  | note | Acceptance Criteria - Drawing revison must be confirmed with the design manager
label | 2defc7ca-d5fc-5ab8-b41b-a9fcc8176091 |  | note | Method - Document review
label | 79e90360-dd08-530d-b5b5-c04977b7b082 |  | note | Frequency - Prior to commencement
label | f29d6c3c-0a33-56f9-9361-350e1492698a |  | note | Category - HP*
label | b2f0579c-60ad-59ca-ae41-4b2db75f9614 |  | note | Responsibility - SE/PE/SPE
label | d6e9d375-5f03-5a22-8960-ca2e2df1acb2 |  | note | Verifying Documents - Design drawings.
date | 3feb5f7a-9a2a-5c70-b6c8-79e073e96022 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Grouting Procedure
label | 9b1e0cd3-546d-596b-92b3-ba8e567ce26c |  | note | Reference - IFC Drawings
label | 05580c18-232e-55aa-9fe8-68ec00e9c65f |  | note | Acceptance Criteria - Volume of abandoned conduit to be calculated to determine amount of grout to be used. This should match the grout delivery volume.
label | 2db1fbcf-be2c-57bb-a754-95c08875e417 |  | note | Method - Measure
label | 211d07da-bd4a-5128-8ffd-82449ca17a82 |  | note | Frequency - Prior to commencement
label | 5056b12d-511a-53d5-a0d3-02a9bc9bbde4 |  | note | Category - HP*
label | 04bc4de1-a3b9-55ea-bd47-96122e0b65fd |  | note | Responsibility - SE
label | 9a1906bb-0cfa-587d-902c-5eb73958eb8b |  | note | Verifying Documents - Calculated grout volume used Grout Volume
date | d3faaeb5-1f84-5558-8a1f-3e8fa4fded80 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - PE Welders Qualifications
label | 6b508fe2-235e-5971-97ab-47d23ec6882b |  | note | Acceptance Criteria - PE welders are to be pre-Qualified
text | ab0b19f9-77e8-539e-8e18-99440450cf9a |  | textbox | Reference:Teambinder Hold point release number:
label | 72bba6b6-e4c5-5670-b070-aaf34aa7ae41 |  | note | Method - Document review
label | c73974b3-ecba-5fa8-84e8-7b573c53de2a |  | note | Frequency - Prior to commencement
label | 9c03e138-3a75-5f29-a298-4095de4a49c0 |  | note | Category - HP
label | 23c5c349-ea8c-521d-9726-da87ebea809d |  | note | Responsibility - SE/PE
label | 8ed28ce6-9254-52a8-a0ba-cf3f32d5c972 |  | note | Verifying Documents - Teambinder approval number
date | b7e8583b-73e1-54a5-9da3-7b52dd9e2ac3 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | 4d6d00cd-1a01-5b44-9945-0dd8607a6d9f |  | note | Reference - IFC Drawings
label | f249b66e-5d8f-5788-8871-e67414f2d4f4 |  | note | Acceptance Criteria - Set out line and level of drilling works.
label | 02910dca-3067-5f70-82b2-0523a89d3633 |  | note | Survey to mark out existing services.
label | b0c5b90a-4c27-5b3c-9c43-b3d4694a941c |  | note | Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
label | 69deff03-f4a2-5285-bb54-5b86de012ee1 |  | note | Method - Measure
label | 91f73fa2-671d-5a44-82b3-485aa0e8f5f9 |  | note | Visual
label | c6f46eeb-67b1-53a0-a4c2-bcee233a7f9b |  | note | Frequency - Each element
label | 02905057-281d-566f-968f-1c7cae60bf66 |  | note | Category - IP
label | 3f05978f-76bb-58ed-95f9-27ac8619ab35 |  | note | Responsibility - Surveyor
label | 126ec3c0-349d-5607-9068-6df1851d725b |  | note | SE/PE/SPE
label | a1e9020e-a5bd-5fe8-966e-f984c6c8c817 |  | note | Verifying Documents - This ITP
date | d2086e41-55f3-534d-9576-c20ca3859822 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Draw ropes
label | 6d3e25d7-025e-560b-8480-0acf9a509a32 |  | note | Reference - IFC Drawings
label | 73bda0f5-5ae9-5693-806c-87416ccc126c |  | note | Acceptance Criteria - All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
label | cbd2af81-e826-5ba5-bbd5-3dbd8fcccabf |  | note | Method - Document review/ Visual
label | 26212195-c1d9-5fb1-9766-41f88c2dd09d |  | note | Frequency - Prior to commencement
label | 84b81427-ee06-5a10-8160-08eb8ee9e258 |  | note | Category - IP
label | a832c7b7-007a-5650-a43b-df369ddd79b7 |  | note | Responsibility - PE/SE
label | 49499d03-92e7-5ebb-9ee7-f9a5568bb9c6 |  | note | Verifying Documents - Material compliance certificate
date | bc6c886e-89fe-5bc1-b561-dcf84650d8e7 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Conduit welding
label | c3b66b0c-5a24-50d8-8f23-8ebaa0c35d91 |  | note | Reference - IFC Drawings
label | 671ee394-5dc3-5bf9-bfcd-965aca18d7c0 |  | note | Acceptance Criteria - Joints are to be butt welded.
label | fb84f130-03eb-534e-a955-20be59a268ae |  | note | Weld map to be supplied and identify unique joint numbers.
label | e87e08b8-b525-50f5-ada6-a48cd434f201 |  | note | Butt Welding records to be supplied.
label | db525af3-789a-5e09-9fc6-153329a1b2b1 |  | note | Method - Document review
label | e07eaae2-e233-56c0-94dd-fd703e7fb766 |  | note | Frequency - All Joints
label | 6e99f878-ca45-5faf-86f9-38cb9ddc036d |  | note | Category - IP
label | 2fb0f31f-5cc7-5864-81ba-78322019f59a |  | note | Responsibility - SE/Site Supervisor/Survey
label | bd29357b-b484-5b32-9454-870ce5308fb5 |  | note | Verifying Documents - Sign ITP
label | 40b1a6f4-32c8-53e9-a817-ab803ae438f2 |  | note | Butt Welding Records
date | 8dac538c-6b2c-5ba4-8720-d05d1aa50e01 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Drill rig setout
label | 4098c95a-3395-5fcc-a36c-9add0022ab74 |  | note | Reference - IFC Drawings
label | 7d7c5e7e-d616-55bc-84b1-2880e0694fed |  | note | Acceptance Criteria - Location as per current Drill shot plans
label | a64fceae-7330-5ca4-a8d6-953006539b35 |  | note | Method - Measure
label | 10cd76ca-f90f-559c-8ff9-d1449e4a1d18 |  | note | Visual
label | 90920f94-88c3-5b67-b189-480585af60f1 |  | note | Frequency - Prior to commencement
label | 80aeab88-0469-596e-8b7b-80f8b6387cba |  | note | Category - IP
label | 9ad8a52c-8435-5db3-8468-311ab2c10cdf |  | note | Responsibility - SE
label | d322de80-7236-5626-8d09-1e7422253894 |  | note | Verifying Documents - This ITP
date | 28999c4f-5db2-544d-b7f4-aae8207efa5d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Installation of Pipeline (Trenchless method)
label | 11a7b036-bbee-544c-9b00-139e1d0ae2f4 |  | note | Reference - IFC Drawings
label | b31777de-dcf3-56a0-9a19-cc38e40d8c7c |  | note | Acceptance Criteria - Drill to be installed as per the survey setout.
label | ab965dd5-897a-54ef-b784-0411f61a3288 |  | note | Bore longs to be supplied.
label | 72f20a54-b9fa-57b1-b2ac-e21047fc946b |  | note | Method - Document review
label | 7693b7d1-ef10-501c-a9c2-b3d4b3732e23 |  | note | Frequency - During pilot bore
label | 2e3312e3-9d41-5849-a95c-1fea3b9a483a |  | note | Category - WP
label | c6b0fb06-fddc-5358-a26f-d59a948ad16d |  | note | Responsibility - SE/Site Supervisor
label | 73e9d0e3-4f5c-5763-af0e-984a32dbe654 |  | note | Verifying Documents - Bore logs
date | fa82014c-5479-5938-8afa-e3e877e461d0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Plug pulling
label | 67f5321e-e58b-521d-8eae-2c9c05f05f90 |  | note | Reference - IFC Drawings
label | 448d2c5c-314a-5475-97d7-1c648eae780a |  | note | Acceptance Criteria - Mandrel with 90% of the pipe diameter to be pulled thrugh each conduit to ensure the conduit hasent been compressed.
label | d10307e6-3b31-5cf0-b366-e5858a6bb272 |  | note | Method - Record and Review
label | 5560ebe8-4de2-5e36-b15b-e252a20519f2 |  | note | Frequency - All Pipe
label | a6fbabd7-bf5e-580b-af0a-a01135cc6b9f |  | note | Category - HP*
label | 7bf43e90-98df-527b-9154-fb601e10256d |  | note | Responsibility - SE/SPE
label | 890a60bf-8cfb-5fb1-87c3-8f9df3b7072b |  | note | Verifying Documents - Sign ITP
label | 53c6dd31-ef14-518d-8464-fdf775628d66 |  | note | Visual of pipe pull pictures.
label | 1640019e-6d9b-5d24-bd9e-a90b077ecb29 |  | note | Subcontractor Test Record
date | 58f5e790-4501-56e2-91cd-31f4a1756074 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Draw rope
label | b60f5da9-c484-5def-b9e9-bd848fc23ff7 |  | note | Reference - IFC Drawings
label | 2db17aed-df56-5901-97d3-0dc4ba4c5b44 |  | note | Acceptance Criteria - All draw ropes must be continious between shafts and have 2m slak in the shaft.
label | f77b750d-6503-5bf3-865f-93b0983ef0c8 |  | note | Method - Visual
label | 4703f643-d2f9-55fd-90ec-b0c366ce3931 |  | note | Frequency - All Pipe
label | 784f2e5a-bb8c-5386-bb57-682cbe52f1de |  | note | Category - IP
label | 4ddb5923-708a-52b8-bfd4-8e53553979be |  | note | Responsibility - SE
label | 2d192fba-4d1f-5c96-83fc-d926e03cb8fd |  | note | Verifying Documents - Sign ITP.
date | 017d9f02-16e0-5095-b649-7944757032b1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Mixing of grout
label | 33bca5f9-8c19-548f-9c1e-0843ed57fa40 |  | note | Reference - Grout TDS
label | e3174267-d1d6-50f4-91ec-7ae1fe41da08 |  | note | Acceptance Criteria - Mixing and proportioning of grouting to take place as per Technical Data Sheet provided with product.
label | 7d017c6c-cd41-55ce-afff-3c833e68be01 |  | note | Only whole bags of product shall be used.
label | 3e7838de-f2b5-5102-9f72-a4bc59952aec |  | note | Grouting shall not commence when temperature is below 5 degrees Celsius or above 35 degrees Celsius
label | c57a6119-8002-5cc5-a4c7-775dedbc23a9 |  | note | Grout mixture should be mixed adequately and free from lumps
label | e0a4d736-3cd9-5744-b7af-61cab2096126 |  | note | Method - Document review/Visual
label | 02bf9f2f-4570-567d-afbe-28e330e303ee |  | note | Frequency - All pipe
label | 5dd592b3-4981-5454-8583-1f19572746b8 |  | note | Category - WP
label | 484bd8b6-481d-5b7c-b187-0b5bbad93164 |  | note | Responsibility - SE
label | c3407150-afe6-5fac-b05f-5a8fc72d052f |  | note | Verifying Documents - Sign ITP.
date | 467f5742-9aab-5f32-9a0d-fa8444800224 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Clean surrounding faces and remove excess grout
label | 7d159a76-5ccb-573b-bcf9-4e1fed385f2f |  | note | Acceptance Criteria - Area free of excess grout and spillage
label | 44756d61-da04-5d1f-a669-e3ccce601413 |  | note | Method - Visual
label | b95396d1-334c-51c4-8c10-58a34f14c510 |  | note | Frequency - Each shaft
label | 5eee597c-182d-519f-a626-f06a1ec9c7c7 |  | note | Category - IP
label | 4b3167c9-cf1d-50d3-879a-e5d03bc233ef |  | note | Responsibility - SE
label | b848cd5f-223a-5d60-bbec-97cb8482ae19 |  | note | Verifying Documents - Sign ITP
date | 1baffb45-d45c-59ae-b08b-ebb98944ec4a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Curing
label | c9e83b02-cda0-5a4f-8eae-22f910b11ffb |  | note | Reference - Grout TDS
label | 4751d2aa-1264-5796-94ae-f4db9f43bea6 |  | note | Acceptance Criteria - Curing in accordance with TDS
label | 8446b435-dca4-5569-b002-4dcc0731e346 |  | note | Method - Document review
label | 39b2d2fe-5f02-560e-a968-af210f08a29b |  | note | Frequency - All pipe
label | a4aca60f-2214-528e-bda0-47fe8d83ac1e |  | note | Category - IP
label | f39f19b0-54b1-574a-86e0-4aa03c6b0860 |  | note | Responsibility - SE
label | ba62e377-a91e-5c52-bbab-14dcdadffbaa |  | note | Verifying Documents - Sign ITP
date | 55a08de3-95ff-5a85-b1ba-0d433d677674 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Auditing
label | be960d36-283c-5a4c-be82-7c453f88155b |  | note | Reference - IFC Drawings
label | 38a2d4c6-15e3-5ab9-968f-ca7fa741f20a |  | note | Acceptance Criteria - Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts.
label | 594c9a1e-da59-576f-ba81-8d3943958334 |  | note | Method - Record and Review
label | ea463cb6-db40-5926-9b78-5b93ff4a426a |  | note | Frequency - Alll Pipe
label | 224fa96f-e660-5c4e-b6c6-359ce014a9e3 |  | note | Category - HP*
label | e4c878c2-1584-591d-840c-7671f7965be9 |  | note | Responsibility - SE
label | 7b68420c-237e-5107-96d5-0b38fcbe484b |  | note | Verifying Documents - Sign ITP
label | 8c85c847-9d91-5aea-be5c-a1edfc54d0ad |  | note | Auditing Report
date | 70fa33c0-fa63-5290-b98b-e4e5d97d6902 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Reinstatement
label | 986a0bdc-25d6-5888-b53b-a702b80a2957 |  | note | Reference - IFC Drawings
label | e88720c5-dfa4-5968-b168-c01b060d14b0 |  | note | Acceptance Criteria - Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified.
label | 40624830-4c05-5bc6-b15f-7dc3609c2e4f |  | note | Method - Visual
label | 3c18a4f0-5b03-56c6-82a0-a3fe6fc19287 |  | note | Frequency - Each shaft
label | 69948410-d81b-5fe9-85d5-35f6165c513f |  | note | Category - IP
label | 3e2bc950-50d9-567b-807f-ccb1b71b1aff |  | note | Responsibility - SE/Site Supervisor
label | 4b9b6efc-ac94-5535-a08e-1ef5750f70c6 |  | note | Verifying Documents - Sign ITP
date | aa62c1e9-16d8-587c-98f8-14aec683f009 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Subcontractor ITP
label | c1b762ff-1a2e-5df1-b4ec-fd671dd3729d |  | note | Reference - IFC Drawings
label | 564480c5-0d56-5cbe-ad97-ef798bde1201 |  | note | Acceptance Criteria - Acceptance and closeout of subcontractor ITP
label | c0389e95-f04f-55a5-bbc3-f47146a7810b |  | note | Method - Document review
label | 5dfead6d-e45f-5af8-9b3f-183e9ebaf84c |  | note | Frequency - Each element
label | 1146556a-28c6-5c6b-84e2-492fc57c0e6e |  | note | Category - IP
label | a298705d-17be-57ed-b2ef-afb11a8d12ef |  | note | Responsibility - SE/SPE
label | 1b9ec0e2-cac7-5c2b-b1b6-63b865f70fd5 |  | note | Verifying Documents - Sign ITP Completed
date | 96db5df5-7f33-588b-9ea1-e7c7872f41f6 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | 348b2a25-5039-597c-9699-2aa5d2a30ee0 |  | note | Reference - IFC Drawings
label | a9d7fa61-bb74-54fc-8231-537a2d4e9b34 |  | note | Acceptance Criteria - Survey as built report to be compiled.
label | 9a095dbc-ba18-5551-b2cc-0cd949ad2606 |  | note | Borelog obtained from subcontractor
text | cf4e5a54-ec7e-5fc5-a3fe-e1ab49731c18 |  | textbox | Autocad and PDF reports are to be supplied to:
label | 0f2c3fa9-23cc-57a7-b494-75aba86ea02d |  | note | Method - Document Review
label | 81fb97b8-995e-5363-8073-3a52cf383ab7 |  | note | Frequency - Each element
label | 9e9a1be8-4a74-5bad-befe-ee7280db1635 |  | note | Category - IP
label | a6c4ec19-0368-54f0-bbdd-1740c092f052 |  | note | Responsibility - Surveyor
label | 610ee70e-50a0-5857-8aad-8709b47697fb |  | note | SE/PE/SPE
label | 065d12b0-da05-5bfd-b234-981e87aa3ba9 |  | note | Verifying Documents - Survey As Report
date | 12c70a45-bb1f-5047-b37f-1f6748b6e3be |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Red-line / As-constructed IFC Drawings
label | c4e1e79c-55f6-56a0-aa00-3bfdd7afc265 |  | note | Reference - MRPA Quality Management Plan
label | 016e02f4-3aba-5a66-b2a6-169febb19de8 |  | note | Acceptance Criteria - All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
label | 65d9017c-bfda-5921-9b43-babf38628b85 |  | note | Method - Document Review
label | f5f691a9-f57d-5d5e-a9a1-5d7d7910b352 |  | note | Frequency - Once, after construction of the design package
label | 444930bf-552f-5370-aa75-2dea667f9582 |  | note | Category - WP
label | 34c105df-0c16-590b-a086-ae04a82ee1bf |  | note | Responsibility - SE/PE/SPE
label | 87844509-bd55-5f80-a132-2fe060fe870e |  | note | Verifying Documents - This ITP
date | fecc2c39-f85f-5f31-ba6d-773102a51b5e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 709657aa-b366-535c-8439-714812c4f713 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | cc5c7067-1a4e-5d4e-878c-c6a4c50777be |  | textbox | Print Name:
text | 2d9c35a5-327f-5d55-8ddf-e84f32b9c8b5 |  | textbox | Position:
date | e29a3a6e-769b-517a-a391-fbd26a88c279 |  | date | Date:
checklist-flat |  |  | checklist | CHK-004-STR-CAMMS-RSS Walls-Fill Placement Rev 2 | itp |  |  |  | Yes | CHK-004-STR-CAMMS-RSS Walls-Fill Placement Rev 2 | af562932-84b5-4288-adf4-16194af816d1
checkpoint-status |  |  | checkpoint | CHK-004-STR-CAMMS-RSS Walls-Fill Placement
label | f09d8581-968b-5ebb-91a5-ec4733760071 |  | note | Document Title: CHK-004-STR-CAMMS-RSS Walls-Fill Placement
label | ff2f1dfc-c707-56af-8940-a33a95804df9 |  | note | Check list Description: RSS Walls-Fill Placement
label | f93827aa-5f2a-5183-b039-5ff4f7c0c0fe |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | e9fe9be7-ee90-5e63-93ec-7d7d0b14c2ea |  | note | Revision Number: 1
label | eb6091fa-366d-571d-98d8-eb588320a5a9 |  | note | Revision Date: 1/05/2023
label | 8c769145-28ea-5413-a24e-5e4af301970e |  | note | ITP created by: Victor Mira
label | b913fbf1-480f-56c6-b52d-d3f484877bcd |  | note | ITP approved for use by: Victor Mira
checkpoint-status |  |  | checkpoint | 1 - Soil reinforcement - Straps
label | 7145b6e2-1edf-55a1-8672-f46c45ba76ef |  | note | REFERENCE: 682.08
label | 6921ae79-8b53-552e-b12f-2c88b8ede1ee |  | note | – – – – – – – – – – – – – – – – –
label | 674ef257-686e-57d9-8607-2e0f99a50e12 |  | note | ACCEPTANCE CRITERIA: Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
label | 60db4c1c-67c3-5c79-9ac1-4e45fc2a1845 |  | note | • Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
label | 27952fff-5844-5c88-9968-2dcc197f5c49 |  | note | – – – – – – – – – – – – – – – – –
label | 3613b641-7548-593e-81dd-e0a97b203682 |  | note | METHOD: Visual
label | 8d6ed4e6-c105-5776-bb12-4b002969891e |  | note | – – – – – – – – – – – – – – – – –
label | 8d23641d-bb9e-5c98-9871-1d7461737912 |  | note | FREQUENCY: Each strap
label | 8098612b-c6db-54a6-86a7-1b4cf514bac4 |  | note | – – – – – – – – – – – – – – – – –
label | 3f2f10bf-6e90-5997-b83f-4d45ac61fcea |  | note | CATEGORY: IP
label | dd0d09c7-a305-58c0-8048-0800ccd2b7c3 |  | note | – – – – – – – – – – – – – – – – –
label | 3feaa987-1a8f-5f1e-ab11-9bab45bde0b9 |  | note | RESPONSIBILITY: SE/PE
label | d6380a00-25f1-5857-a043-1bb9e3b0abd5 |  | note | – – – – – – – – – – – – – – – – –
label | b37964c4-a57d-5326-9a8b-47d6d9f145a0 |  | note | VERIFYING DOCUMENTS: This Checklist
label | f655dc6b-ff88-5913-b284-1caa2f3f9950 |  | note | – – – – – – – – – – – – – – – – –
date | 455a7e86-06e4-5583-896d-b74a61502540 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Soil reinforcements - Connections
label | 175aa34a-8782-534b-bdbb-e2221c298aa7 |  | note | REFERENCE: Installation manual
label | 6482701c-0cf2-5e42-acf3-6edf63cd13b2 |  | note | – – – – – – – – – – – – – – – – –
label | 29fee35a-709c-5c4e-acdf-67b3ce2b8ac6 |  | note | ACCEPTANCE CRITERIA: Correct number of reinforcing element shall be attached to each panel
label | 5bec1816-c907-5641-b60c-b4a1118f3ad4 |  | note | – – – – – – – – – – – – – – – – –
label | 7ac5921f-d588-5683-9358-9fa94d19c185 |  | note | METHOD: Visual
label | f7245198-c4cc-535a-bc51-5aae0637a4af |  | note | – – – – – – – – – – – – – – – – –
label | d8ea75b4-01ea-56a9-b01b-e48169e212ac |  | note | FREQUENCY: Each panel
label | 6b206ee2-7c1e-5ec0-af5f-2fa86a20eb18 |  | note | – – – – – – – – – – – – – – – – –
label | 1e44d1a8-b178-5937-bdba-19df53664476 |  | note | CATEGORY: IP
label | 11f76b4e-46da-55bf-a445-f4558699164d |  | note | – – – – – – – – – – – – – – – – –
label | 83a95c6a-f3dd-5087-88f8-c4f7c70d0ce8 |  | note | RESPONSIBILITY: SE/PE
label | 0461e92b-9aa1-56b2-b96a-7611935714ca |  | note | – – – – – – – – – – – – – – – – –
label | cb1b2e0c-2509-561d-aa25-32530d80928d |  | note | VERIFYING DOCUMENTS: This Checklist
label | 7376e96e-a45d-5de5-b774-81e0afc78215 |  | note | – – – – – – – – – – – – – – – – –
date | e75643dc-1e29-5598-b3c0-f7bdcfd40737 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Soil reinforcements - Connections
label | 28995cbb-4e08-5d56-b8f2-6c275a2fc82c |  | note | REFERENCE: IFC Drawings
label | 94bd2838-b311-53ac-8991-a83cb3721bac |  | note | • Schedule of lengths: MRP-052-C-RFL-DRG-33-CBE-CSW-1302,1403,1503,1602
label | d158a99f-dde8-5485-9010-120bf62123c9 |  | note | • Connections arrangement: MRP-052-C-RFL-DRG-33-CBE-CSW-1901
label | 616c46a6-bda1-54f1-9d58-387116c411ab |  | note | – – – – – – – – – – – – – – – – –
label | c2812fad-ab10-58f7-bd21-007931a32328 |  | note | ACCEPTANCE CRITERIA: Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
label | f9fe02c9-0f4d-53b2-92e9-5a31a3629ea2 |  | note | – Bolts are to be snug tight.
label | a289d7c8-8420-56c6-ad8f-e07e91400823 |  | note | – – – – – – – – – – – – – – – – –
label | 17378304-f599-5759-b8d5-9b1da00bc5e8 |  | note | METHOD: Visual
label | 93aab342-02db-575e-bf81-7a921026ae57 |  | note | – – – – – – – – – – – – – – – – –
label | cdb56cca-c94a-5c79-9766-cdb6d52b75ce |  | note | FREQUENCY: Each fill layer
label | 7142199e-c6b7-5c7c-ad29-32d9b7474088 |  | note | – – – – – – – – – – – – – – – – –
label | 28ffe264-bd0b-5195-a551-9373dace9771 |  | note | CATEGORY: IP
label | 50391a3a-ef31-51f7-85e8-8aa3f9a05164 |  | note | – – – – – – – – – – – – – – – – –
label | 078f3f30-88e6-5cde-9aa3-22a0538f0cb4 |  | note | RESPONSIBILITY: SE/PE
label | 10053f46-fead-5204-928b-b1ff0ac04e6d |  | note | – – – – – – – – – – – – – – – – –
label | 04e59617-aa8d-5346-8406-508164173134 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 137f3b78-f408-5b4b-968f-104e5b597b72 |  | note | – – – – – – – – – – – – – – – – –
date | 9dfa4ba0-3aed-5d1d-a871-e9a523f4a562 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Soil reinforcements - Plan arrangement
label | 46653a12-e04e-5407-92fd-3272fdaa0501 |  | note | REFERENCE: IFC Drawings
label | 6646ba90-5421-5dfe-972f-73d7c72c4f73 |  | note | • Arrangements: MRP-052-C-RFL-DRG-33-CBE-CSW-1102 to 1104 VR682.06
label | c774b250-7a59-5c31-b6c3-8f381fc79d6e |  | note | – – – – – – – – – – – – – – – – –
label | 102c12b5-6700-554a-b221-c928e69e24c3 |  | note | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
label | 6fbe2224-508d-544b-b0c1-12499447439c |  | note | – Grid Strips shall not overlapped
label | d4f78391-03e8-582d-a03b-cfc2848fb629 |  | note | – – – – – – – – – – – – – – – – –
label | ed345ddb-13ea-5487-a20f-047aa3f876d1 |  | note | METHOD: Visual
label | 039bd368-4d89-52c6-a323-8a39748dfdb1 |  | note | – – – – – – – – – – – – – – – – –
label | f79a10ce-5062-56c6-8885-cbf43ef9a606 |  | note | FREQUENCY: Each fill Layer
label | 3d14fe45-9e69-5fb0-9d18-2f65bed391af |  | note | – – – – – – – – – – – – – – – – –
label | bfca1f20-7796-55ac-9075-b4a2537c5d55 |  | note | CATEGORY: IP
label | aa0c9e63-df8d-5132-8de1-857890293d45 |  | note | – – – – – – – – – – – – – – – – –
label | 39a50441-7a97-5c4a-a0b1-c6ba65c04955 |  | note | RESPONSIBILITY: Surveyor/SE
label | 3998075a-97c3-5aa8-8414-ca74f371ce30 |  | note | – – – – – – – – – – – – – – – – –
label | a0b09398-b041-598a-936e-da3c111c52d7 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 5d3942eb-4d33-5b07-9435-d23c095fa75a |  | note | – – – – – – – – – – – – – – – – –
date | 5acd1804-f7d5-5b1e-8bf5-20f2b54c9b01 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Soil reinforcements - Plan arrangement
label | 7ff34b47-f741-514d-99fc-88f4e0370acd |  | note | REFERENCE: IFC Drawings
label | 1bcd5609-50b3-54e2-a21a-af9d7ff2c633 |  | note | • Arrangements: MRP-052-C-RFL-DRG-33-CBE-CSW-1102 to 1104 VR682.06
label | 7f5a5a2a-df1e-5e9a-992c-2f510daed94f |  | note | – – – – – – – – – – – – – – – – –
label | 4a55fdfb-034f-52aa-b5af-f100534bbffa |  | note | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
label | 7742eca1-54a3-52bb-b06d-65e7f6ce0444 |  | note | – Grid Strips are not to pass over pile cap. RSS used in conjunction with a bridge abutment shall be independent of the bridge structure.
label | 7372f4cd-b2de-55f2-a467-ce27a7e15714 |  | note | – – – – – – – – – – – – – – – – –
label | 34a187d7-8b01-5f4a-884d-67b83676e4ab |  | note | METHOD: Visual
label | fa8b2bb3-cb4e-5b55-8c48-0ea3b57f2ae6 |  | note | – – – – – – – – – – – – – – – – –
label | ea6e4c63-2ef1-52a7-af37-efee2b74f01f |  | note | FREQUENCY: Where applicable
label | 06445b96-05ea-5eca-90fc-185a6701ce8f |  | note | – – – – – – – – – – – – – – – – –
label | 7d947383-b0ff-563d-95b1-b936e29d7ba0 |  | note | CATEGORY: IP
label | 7a359fad-57d8-525e-89c6-78510a178b71 |  | note | – – – – – – – – – – – – – – – – –
label | 00b27943-828e-5e8e-99f1-47ed7c2b7479 |  | note | RESPONSIBILITY: PE/SE
label | 7de4ae58-ff68-5b67-ad83-24ff67da92ad |  | note | – – – – – – – – – – – – – – – – –
label | dbd3fc26-be60-53f6-ab77-ff456e0f92f0 |  | note | VERIFYING DOCUMENTS: This Checklist
label | af8a67b1-2c57-5e6e-a03e-5f029e4e55f7 |  | note | – – – – – – – – – – – – – – – – –
date | 828a7438-85de-57a6-ba76-790676c09709 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Soil reinforcements - vertical deviation
label | 738bb264-0697-5808-a42e-9595efd05e20 |  | note | REFERENCE: IFC Drawings
label | f35225db-8285-5359-90f2-c35d1589f465 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1702
label | 947fe590-a02e-5a80-9415-7853f4cf2111 |  | note | – – – – – – – – – – – – – – – – –
label | 35399e68-7cc4-5002-aa68-88d4fc55e9a1 |  | note | ACCEPTANCE CRITERIA: The vertical deviation of the soil reinforcement shall be within +1% upwards and -0.3% downwards of the soil reinforcement length, relative to the connection height.
label | e7391f73-f90c-5d7e-b8d5-92fda2ce9690 |  | note | • Avoid clash with drainage as directed in IFC Drawings.
label | b41badc4-4b91-5baa-8e71-73f866b9e403 |  | note | – – – – – – – – – – – – – – – – –
label | bb5952cc-51c7-5a49-958f-e39dc3770699 |  | note | METHOD: Measure, Survey
label | 87939e79-50fa-5e40-a5ef-3beec099c4e6 |  | note | – – – – – – – – – – – – – – – – –
label | da7cd5ff-2193-501b-b4e1-2e42ceba3149 |  | note | FREQUENCY: Each Fill Layer
label | 07a0b286-d5dc-5ae0-8f5f-763f96cddc72 |  | note | – – – – – – – – – – – – – – – – –
label | 6254f418-85d2-5b68-a012-abf9bb7fe98c |  | note | CATEGORY: IP
label | d307c9ee-00eb-55c8-ba37-04ea7d7b3750 |  | note | – – – – – – – – – – – – – – – – –
label | b76b8973-ac5f-5772-858c-9bd38ebcfdc9 |  | note | RESPONSIBILITY: Surveyor/SE
label | c5a29645-b72e-5729-8cb0-f5029f3b5121 |  | note | – – – – – – – – – – – – – – – – –
label | 1c7f7396-d7f4-5a59-883f-127f96444861 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 5510e6ac-eca1-542a-8850-fbb8b105bc21 |  | note | – – – – – – – – – – – – – – – – –
date | 8672f831-352e-58cb-a771-4bb4ba885883 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Fill - Pacement
label | a887c2ea-c7d1-5c0d-a1e2-3ae4b148b16f |  | note | REFERENCE: 204.10
label | 61a0b1d6-ea29-572f-a0df-cd7e3c30d3b8 |  | note | – – – – – – – – – – – – – – – – –
label | 849c7c91-9dd8-5a27-95de-d4ec3d6a0a70 |  | note | ACCEPTANCE CRITERIA: Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm
label | ae9347ce-2f63-54e1-a781-869765186b5b |  | note | • All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps
label | 6cf33a3c-0b97-5542-a26a-6f27353e023d |  | note | – – – – – – – – – – – – – – – – –
label | 18bae2a4-541a-50b0-883b-29dc77134982 |  | note | METHOD: Measure, Visual
label | 27140bc5-1016-5273-b339-14e66e593737 |  | note | – – – – – – – – – – – – – – – – –
label | eb9ca134-5af8-5732-878f-97f019f5e66a |  | note | FREQUENCY: Each Fill Layer
label | fc087ffe-87a2-58c8-8219-e62e841c8577 |  | note | – – – – – – – – – – – – – – – – –
label | 1440a0a4-3476-59a2-b0e5-1ee970c30c3e |  | note | CATEGORY: IP
label | 132436f3-1484-5b2c-bbbc-b36f23d9885d |  | note | – – – – – – – – – – – – – – – – –
label | 2bc97323-895c-5459-a5c2-f6595cafa5f3 |  | note | RESPONSIBILITY: PE/SE
label | ce3812bb-b9b0-5950-96ec-8e7bb90b89cd |  | note | – – – – – – – – – – – – – – – – –
label | 26b70fa8-92fe-5018-9521-159fcd3c6e4c |  | note | VERIFYING DOCUMENTS: This Checklist
label | 0350b649-2290-5ab4-a443-a8ae92ada642 |  | note | – – – – – – – – – – – – – – – – –
date | 330011a7-7384-58ec-b8e7-322976b257aa |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8 - Select backfill - moisture content
label | ede30106-cae1-542d-813d-3bdab8518974 |  | note | REFERENCE: IFC Drawings
label | 9b4a8a79-7f32-50b2-90be-c65577ab7f95 |  | note | – – – – – – – – – – – – – – – – –
label | af06be78-e907-580a-8a9c-22b5fe0fadb7 |  | note | ACCEPTANCE CRITERIA: Moisture content of the backfill shall be maintained evenly at all times.
label | ff3588a3-01c3-5475-886e-9c32282e4785 |  | note | • Moisture content shall be within 0% to -2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content, must be allowed to dry
label | a3daf6af-ff31-551e-821e-707d26ee3750 |  | note | – – – – – – – – – – – – – – – – –
label | f8932425-58cb-5188-b6de-8c79c61c45ce |  | note | METHOD: Measure
label | 5b3d40f1-bc21-5707-b298-c71e649a8f41 |  | note | – – – – – – – – – – – – – – – – –
label | 20d46102-9dbf-5ad5-bfc2-a03ed164021d |  | note | FREQUENCY: Each Fill Layer
label | 3bcd07a3-2556-5080-bd66-a4ce941ac36d |  | note | – – – – – – – – – – – – – – – – –
label | 58976da2-6e3c-5ae9-b117-f98f50467a3a |  | note | CATEGORY: IP
label | 13be8b0b-8451-58e3-9aff-6d5ce0a05b22 |  | note | – – – – – – – – – – – – – – – – –
label | 059c2a88-6403-591e-9e33-4b96eefa3d08 |  | note | RESPONSIBILITY: PE/SE
label | 7c7d1f5a-66d5-58a4-a4ca-afcdf3d9e0ed |  | note | – – – – – – – – – – – – – – – – –
label | 59a2d17b-4811-5c3e-a963-55f82f32ca93 |  | note | VERIFYING DOCUMENTS: Attached Test Results
label | 68122c44-6a62-5762-a4cc-0d9a203937e8 |  | note | – – – – – – – – – – – – – – – – –
date | 11eac5c8-f279-510f-943c-350352a477af |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Select backfill - placement
label | e2198e41-b84a-5c98-a8ee-587d920cd7f5 |  | note | REFERENCE: IFC Drawings
label | b03893f6-b0a4-5b8a-86d8-0e6d1f3d0ddb |  | note | – – – – – – – – – – – – – – – – –
label | e356bdb1-9e78-58ea-accf-969d8e4e4bfb |  | note | ACCEPTANCE CRITERIA: Select backfill shall be placed in accordance with Vicroads section 204 and compacted to 98% of standard proctor density.
label | 044eb40a-d686-5f56-9155-51cb3a1bd88f |  | note | • Compaction within 1 meter of the wall face shall be achieved by a light weight (Hand Operated) mechanical tamper roller or vibratory system.
label | 10f2fe50-57af-5669-91b5-f36860339fd2 |  | note | • No large compaction equipment shall be allowed in this zone.
label | 9c63149f-d594-5e3a-b073-5c575d8e907f |  | note | • Compaction beyond 1 meter of the wall face shall be in accordance with the table VR 204.111
label | fbfa8ce1-c169-5546-86ce-dff583d8783d |  | note | – – – – – – – – – – – – – – – – –
label | 168128bb-5ef6-5e87-8812-de991581970c |  | note | METHOD: Measure
label | 894e5d23-baa8-5147-a87e-aead2286d289 |  | note | – – – – – – – – – – – – – – – – –
label | 5aefcd75-246e-5224-a265-fde28b1cc65f |  | note | FREQUENCY: Each Fill Layer
label | 74958cc1-7c03-58ea-a413-d5f4126acdff |  | note | – – – – – – – – – – – – – – – – –
label | e6bb156d-49fb-5f91-b4bf-a9871072f424 |  | note | CATEGORY: HP*
label | addc152b-e22d-5de6-b006-56fdc6d78cc5 |  | note | – – – – – – – – – – – – – – – – –
label | 8984b784-004d-5fd4-9728-70fa90416144 |  | note | RESPONSIBILITY: PE/SE
label | 9822ebfa-88f6-51e1-b0aa-08d614a18b2d |  | note | – – – – – – – – – – – – – – – – –
label | 8f358c40-7704-5444-ad2e-52d88474c284 |  | note | VERIFYING DOCUMENTS: This Checklist
label | e1727d11-2b92-5083-92cb-30480b43c08f |  | note | – – – – – – – – – – – – – – – – –
date | 3d28c19a-b510-58b5-ac2a-0f69138812e6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 10 - Select back fill - reduced frequency
label | f25fd5c4-9bbf-555c-b7f8-d08222bf4214 |  | note | ACCEPTANCE CRITERIA: After three consecutive lots of like material have achieved the specified requirement, the contractor may seek the superintendent's agreement to reduce the frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
text | 5948d8f3-2b8d-5f58-badc-7ea2dc1ee324 |  | textbox | Three Consecutive Lots tested to satisfy this requirement.
label | 2cd364eb-2bc9-5aa8-b550-5b1fe9358ec2 |  | note | – – – – – – – – – – – – – – – – –
label | dd7a4e45-366e-558f-ae81-241cfa5e6eb8 |  | note | METHOD: Document review
label | ce1b6a2e-2bee-5910-bb24-28976170b074 |  | note | – – – – – – – – – – – – – – – – –
label | e52f9a69-51b2-5a4c-ac2f-2a795fa30b9d |  | note | FREQUENCY: Each Fill Layer
label | 23b61b1c-c22f-528f-8dd2-dbb2fb3b42b7 |  | note | – – – – – – – – – – – – – – – – –
label | 7dea4c32-7146-5a43-a3af-fb22ec861117 |  | note | CATEGORY: IP
label | 22044160-494c-5cba-9b52-a0c84d0df6b4 |  | note | – – – – – – – – – – – – – – – – –
label | 4a28a8ee-4cd2-5736-b5ec-8df179c5e908 |  | note | RESPONSIBILITY: Nominated Authority/PE
label | c84962f1-2926-5fda-b3fb-fea5cda2f5c2 |  | note | – – – – – – – – – – – – – – – – –
label | 55b5a02f-4bed-5ba5-aeef-be91065bb52b |  | note | VERIFYING DOCUMENTS: Referenced Lots in This Checklist
label | b18cdc07-fe70-57eb-818d-c7c17ca886b0 |  | note | – – – – – – – – – – – – – – – – –
date | 3e911f0b-23d5-53bb-97dd-eaa439b44ac1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 11 - Select Backfill - Testing frequency - acceptance
label | 57dbaf15-de85-5140-aa1e-da92b1d33339 |  | note | REFERENCE: IFC Drawings
label | 8dc757c0-7ad8-595b-8b4f-6b3d793befbd |  | note | • VR 204.14
label | c8e2be7c-72f6-5030-be52-301c49ef7ef8 |  | note | • VR 682.16
label | b31963e7-b85b-5563-9239-38612839bb7f |  | note | – – – – – – – – – – – – – – – – –
label | 6ced8d17-3f81-54f9-95c7-f9894bc1ede3 |  | note | ACCEPTANCE CRITERIA: Testing frequency shall be in accordance with Vicroad Specification section 204.14
label | cf1b8b52-0a2c-5a5f-b958-d84191f6174a |  | note | • The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance.
label | f5ff93ac-701a-52bb-9284-248c3c914ae1 |  | note | • No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted.
label | 1efcc395-b96b-52a9-a973-538a08858648 |  | note | • If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed
label | f39bfa44-b11b-5e9d-b70e-c9f76d8224a3 |  | note | Attach: Compaction test results
label | 3c373fcd-a86a-53bc-92b4-4dc2b6bf63f2 |  | note | – – – – – – – – – – – – – – – – –
label | 00d473b1-be36-5923-9a8d-b25f11113f7b |  | note | METHOD: Measure
label | ff14c97b-389d-5c00-a66b-4316648f26a7 |  | note | – – – – – – – – – – – – – – – – –
label | ddeb4e93-fca7-550e-bdfa-8d01c81203d0 |  | note | FREQUENCY: Each Fill Layer or every second layer as agreed
label | 6cb3f4f3-e083-5df0-b220-7310fd6def99 |  | note | – – – – – – – – – – – – – – – – –
label | 49338b8a-b957-5999-94c7-4f3c7b921b03 |  | note | CATEGORY: HP
label | d26d0c70-fe29-58d7-bd20-884d5d47e5ec |  | note | – – – – – – – – – – – – – – – – –
label | dbd7f3c2-4c3d-56a4-bf7c-a5785821f522 |  | note | RESPONSIBILITY: Nominated Authority
label | 39860132-9cb1-58b8-bee1-250d4a436e7d |  | note | – – – – – – – – – – – – – – – – –
label | 15d218fc-7eb3-5eac-801f-e5e0259d9f45 |  | note | VERIFYING DOCUMENTS: Attached Test Results
label | 1f199daa-e988-57fd-af32-e73a92e77d43 |  | note | – – – – – – – – – – – – – – – – –
date | 7d89d082-8989-5099-8a51-36bbb88148f7 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Select backfill - acceptance
label | a50b0bf2-6e68-56d7-9f7f-d27f107d79fb |  | note | REFERENCE: VR 204.12
label | 19cc1df1-5a66-5ca5-ab33-de2083919a8c |  | note | – – – – – – – – – – – – – – – – –
label | 4c171616-140f-5923-a452-8c015a005c99 |  | note | ACCEPTANCE CRITERIA: All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
label | a70d745b-98fb-501e-be50-7a847b50832d |  | note | – – – – – – – – – – – – – – – – –
label | 69b8225d-dee3-5c7e-88c1-e95a60bc5754 |  | note | METHOD: Visual
label | 9e15648d-952f-5013-90bd-456ca4dd74fb |  | note | – – – – – – – – – – – – – – – – –
label | 56933712-8e7c-569a-ad4e-e31fc8395c9b |  | note | FREQUENCY: Every Fill Layer
label | 1014b2f7-89d4-5486-8229-e450fab3807a |  | note | – – – – – – – – – – – – – – – – –
label | ac281ddd-7dcf-5018-b20c-7796e096ae50 |  | note | CATEGORY: HP
label | 9489232f-8c9d-5144-9d17-ce01f0a8cc50 |  | note | – – – – – – – – – – – – – – – – –
label | fbc3663e-d909-5d97-9896-8ad6b0bd4e0b |  | note | RESPONSIBILITY: Nominated Authority
label | 89471f88-0f26-5b6c-8c93-6eb080c31db0 |  | note | – – – – – – – – – – – – – – – – –
label | 723109f4-3db9-526f-ae72-cd483f86216f |  | note | VERIFYING DOCUMENTS: This Checklist
label | c6d3def0-8f19-5a1d-aee1-99d58372850e |  | note | – – – – – – – – – – – – – – – – –
date | a006d01a-2b5e-56f4-85bf-7e56f7c0122c |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7276f07f-cf0a-52a7-a222-4bf26062a688 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | bb339f41-e53c-579c-bf82-8caf2e5df9ba |  | textbox | Name:
text | aa9702ab-4795-5221-9cf4-d1d06923b4f7 |  | textbox | Position:
date | e39a4561-bc61-57d4-80f7-e93be278f832 |  | date | Completion Date:
holdpoint |  |  | signoff | Signature
checklist-sectioned |  |  | checklist | ITP-073-CIV-CAMMS-Lighting-MTM Carpark Rev 0 | itp |  |  |  | Yes | ITP-073-CIV-CAMMS-Lighting-MTM Carpark Rev 0 | b065e794-ac15-42bc-800f-5b03260c90b8
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | eebf3119-9204-55a2-bbaa-55b233db08f0 |  | note | Document Title: ITP-073-CIV-CAMMS-Lighting-MTM Carpark
label | 46897a91-5fc4-568b-a5c5-ed5bc63748ae |  | note | ITP Description: CAMMS-Lighting-MTM Carpark
label | 1296070e-1795-5036-af68-7b7f9e510b41 |  | note | Discipline (e.g. CIV/STR/RAIL): 073-CIV
label | a25a1004-e8f8-5893-9aca-1c16be781e99 |  | note | Revision Number: 0
label | 59c9b91a-f228-5d2f-83c1-d0b437314a4e |  | note | Revision Date: 8/11/23
label | 84ac5183-8bac-55c2-93ba-cadf52713be1 |  | note | ITP created by: Romualdo Magpantay
label | 411e1881-a842-52c8-a6b1-a8789401345d |  | note | ITP approved for use by: Victor Mira
label | 6f5e811e-09b1-58a5-96d9-6fb10f329c4a |  | note | 1.1 L1-CHE-STD-059
label | 7c002317-6ce7-5440-8840-87c79b1126f1 |  | note | 1.2 L1-CHE-STD-035
label | f6c12c68-d15f-5d88-bbb4-f3121a129744 |  | note | 1.3 L1-CHE-SPE-155
label | f6c8f615-fc1c-5f97-b3d1-91d62326f75f |  | note | 1.4 AS/NZS 3000
label | fc27b167-d9ab-5c52-8c31-6f1bab0b06ad |  | note | 1.5 AS/NZS 1158.3.1 (2005)
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - Obtain and review manufacturer documentations for the supply of materials
label | b8820342-9a35-54cf-8485-70511fe86cf0 |  | note | REFERENCE - AS/NZS 3439.1 L1-CHE-STD-035 AS/NZS 2053 IFC Drawings
label | c38c3674-b30e-58f2-92ce-ac438da1240f |  | note | – – – – – – – – – – – – – – – – –
label | 2151626d-7c26-5919-a77f-bae03cf223ec |  | note | ACCEPTANCE CRITERIA - Materials comply with MTM Engineering standard Lighting and Powerrelevant specifications.
label | 95fb78f7-e473-56c0-9167-13a2759f4857 |  | note | All materials shall comply with the standards and specifications shown on the drawings. All structural steel, associated components and welding consumables shall be manufactured by companies that hold quality systems certification to AS/NZS ISO 9001.
text | 21457737-8fa7-555c-804f-1d08231e6eec |  | textbox | Enter: Teambinder Material Approval number
label | 20d14040-6033-540d-8a98-878cd351ae07 |  | note | METHOD - Document Review
label | ce992482-fb93-5430-9e82-0e9b7f4bf5d9 |  | note | – – – – – – – – – – – – – – – – –
label | c29f26c0-3b8f-58d5-92ee-d1b5d002fb4f |  | note | FREQUENCY - Per Source
label | d3107bce-101a-5729-a596-ec2b70cacc38 |  | note | – – – – – – – – – – – – – – – – –
label | 3e1a8907-3cde-5df9-a0b7-d0b5c9aa4f82 |  | note | CATEGORY - HP*
label | f488924d-6d3a-5659-8ac4-18085cd6d4e3 |  | note | – – – – – – – – – – – – – – – – –
label | 19cbb5d6-780c-512b-853b-6404f8057d26 |  | note | RESPONSIBILITY - Nominated Authority
label | aeff485c-3854-5fd1-8dbd-3623cf314363 |  | note | – – – – – – – – – – – – – – – – –
label | 7b753784-754c-589a-8098-3a98b626cc28 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 4b7ada1a-1815-56ea-b887-2e0aef05837f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Inspect supplied items upon delivery
label | b980dfa7-a9f5-506c-9c0a-e7c2b7e1f41b |  | note | REFERENCE - QMP L1-CHE-SPE-155
label | 29432bb4-8185-5a25-8042-00f574ebbd9b |  | note | – – – – – – – – – – – – – – – – –
label | 6dffdd7f-d0e1-5711-8d1f-321061df4074 |  | note | ACCEPTANCE CRITERIA - Supplied items are to correct spec, class, size and undamaged
label | d58df246-673f-5206-8055-7011d71b7b83 |  | note | Luminaires: At the time of delivery, the supplier shall provide three hard copies of the following:
label | 74f01c0a-b957-5bb1-9b4e-d1e57df9e9e4 |  | note | Installation Instruction Manual
label | ed9b08c4-2eb2-59ab-a237-72f5df0d1ee0 |  | note | Operation Instruction Manual
label | 8c1bc061-3aa0-51e9-bb7d-7e55d65d119c |  | note | Storage, handling, loading and off–loading instructions
label | 57dd28f8-b6ff-558a-94aa-c951affa9275 |  | note | Test Certificates
label | ed7055c5-f4f3-5fab-91a9-a96a7568dfd3 |  | note | Warranty Information
label | 4f24bed5-39cc-5ff4-99ac-c2bd0dd8314d |  | note | METHOD - Visual /Site Inspection & Document Review
label | 8a88bee9-3d66-5d9b-95c5-db4b5c04b728 |  | note | – – – – – – – – – – – – – – – – –
label | 1b1ea5b4-b7d3-5437-9dbb-2bca9869bfd0 |  | note | FREQUENCY - Per Delivery
label | 32b2a44b-79b1-5985-b7d1-d117f3a29315 |  | note | – – – – – – – – – – – – – – – – –
label | c11451eb-028f-5961-aef2-febb981792a3 |  | note | CATEGORY - IP
label | f069aea1-6450-5cd5-91c0-05bc287c10e7 |  | note | – – – – – – – – – – – – – – – – –
label | a19eac7f-d26f-536a-8040-708dcc319685 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 618b71b9-d776-5a87-b785-a88ce606649c |  | note | – – – – – – – – – – – – – – – – –
label | 0fde758a-7ef2-5119-ba27-523156d35eef |  | note | VERIFYING DOCUMENTS - This ITP Attach records required
date | bede554b-b558-5add-80f5-de2e7e763787 |  | date | Date Completed:
checkpoint-group |  |  | section | Civil Works
checkpoint-status |  |  | checkpoint | 3.1 - Conduit & pit installation
label | dca5ec3e-8ce5-51fd-8017-93d456104e66 |  | note | REFERENCE - L1-CHE-STD-035 IFC Drawings
label | 662b2652-b1ca-507e-b0bb-72d22a084d58 |  | note | – – – – – – – – – – – – – – – – –
label | 9e88aacd-8c60-580f-a928-fa55016126f8 |  | note | ACCEPTANCE CRITERIA - Conduit and Pit Installation works are to be recorded under ITP-CIV Pit and Conduit (Supply and Install) - MTM Car Park Lighting ITP in addition to Subcontractors Checklist.
label | b8b7d60e-a5fd-58ad-ac1c-db19d585b038 |  | note | METHOD - Document Review
label | cf67ea94-81d9-52a1-8302-504b046c94ea |  | note | – – – – – – – – – – – – – – – – –
label | eeee1963-ab45-58e6-9420-f7d34bfe093d |  | note | FREQUENCY - Per Lot
label | 05d957e3-1a9f-5a97-bc97-9d53e97a5246 |  | note | – – – – – – – – – – – – – – – – –
label | 5d7df0df-f5b2-5cc9-92d0-aba3dd17dc3e |  | note | CATEGORY - IP
label | 42882d18-d86e-5c82-a5e3-199ad901ffcd |  | note | – – – – – – – – – – – – – – – – –
label | bba6282c-7b49-53b4-b0ab-e13f38947a84 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 2291e569-f86f-5b48-9a1c-391e50e3ccfd |  | note | – – – – – – – – – – – – – – – – –
label | b6476eb2-83c9-56f6-909d-e8f0a2fc2436 |  | note | VERIFYING DOCUMENTS - This ITP Attach Subcontractor Checklist
date | 13be4867-96de-5e66-9dc7-6ed65b2b4d46 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Prepare the plinth foundation(Excavation & levels)
label | 859b0ba9-bb27-56ff-8bdd-f22f0124e15d |  | note | REFERENCE - Drawings IFC
label | dbae7f27-9676-5d10-a8a1-d5fe9c2cddd0 |  | note | – – – – – – – – – – – – – – – – –
label | 853399f7-4876-5e15-9475-69f729df29e8 |  | note | ACCEPTANCE CRITERIA - Check levels conform to relevant drawing depending on type of pole to be installed.
label | 70db9191-5faf-56a2-8404-b46b42e627f9 |  | note | METHOD - Visual Survey
label | 4ab569d7-2a06-5099-893d-874b374daf4a |  | note | – – – – – – – – – – – – – – – – –
label | 377d7dc7-ab8c-56a4-be41-b54cdbbbda6b |  | note | FREQUENCY - Per Lot
label | b5187bfa-3cfc-5032-b36c-77d33802c300 |  | note | – – – – – – – – – – – – – – – – –
label | f4ad1ca6-cd15-591f-893a-f3a0bcda5799 |  | note | CATEGORY - IP
label | 242e16e9-7080-52fa-a4a8-581bffd7db1f |  | note | – – – – – – – – – – – – – – – – –
label | 2ed617f9-8eaf-51be-9550-1b402da13a8c |  | note | RESPONSIBILITY - SE/PE/SPE
label | e4719457-cd41-595d-82e7-8d6008542449 |  | note | – – – – – – – – – – – – – – – – –
label | e5415c68-14f3-50e5-8a6d-2435b71213a0 |  | note | VERIFYING DOCUMENTS - This ITP
date | 01911fa1-7611-5239-bbe7-d281d9a8ecda |  | date | Date Completed:
checkpoint-group |  |  | section | Light Pole Works
checkpoint-status |  |  | checkpoint | 4.1 - Installation lighting pole bases & columns
label | cd4fed9d-18f7-5698-816d-a1b8ba0382fe |  | note | REFERENCE - IFC Drawings L1-CHE-STD-035
label | 697b0ce1-2adb-5d55-8439-2f11eb8608b2 |  | note | – – – – – – – – – – – – – – – – –
label | e8cf8e4b-388f-5904-966f-8e33f1f761c7 |  | note | ACCEPTANCE CRITERIA - Free standing platform lighting poles shall be at earth potential as mounted in ground or on structure. Light fittings shall be earthed by the earth cable from
label | a2a4b046-a2c3-5ddc-a6e9-31eea8196b97 |  | note | Concrete and metallic poles at all new installations and station extensions that support low voltage equipment shall be earthed by an underground conductor that is connected to the earth at the origin from which the circuit is supplied in accordance with AS/NZS 3000.9.5.2
label | 78142869-6c3e-5e19-9786-10e85a89485f |  | note | Lighting installations shall be LED and comply with L1-CHE-SPE-155
label | cbfd6035-35ec-5cd5-8ab3-b62f93c93bbe |  | note | Car park poles shall be located as per IFC Drawings.
label | 24feab04-7bc5-59de-8546-83984a44fd52 |  | note | Pole access hatches shall be orientated to allow unobstructed access.
label | 6caea65b-5baa-5e55-816e-28305e4704e6 |  | note | Level formed ground shall be at each pole for access by ladder or EWP.
label | 6a510997-1e66-5354-9ee5-47e3d6b1bede |  | note | METHOD - Visual /Site Inspection & Document Review
label | 380c2bb0-b422-5032-8f90-a9b80f2e5392 |  | note | – – – – – – – – – – – – – – – – –
label | 5360ec91-2472-5ad2-9843-d76ee22550c0 |  | note | FREQUENCY - Per Lot
label | 1a4d31a8-86f4-5ab0-a501-7c9a5a07f307 |  | note | – – – – – – – – – – – – – – – – –
label | 0909a656-c784-5663-8226-03682ecae352 |  | note | CATEGORY - IP
label | 91dca009-9438-52c6-aaf1-d36ed4e1a57c |  | note | – – – – – – – – – – – – – – – – –
label | 5158c810-664c-5fe0-9b63-a6c27b9bb692 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 15ee7560-83f0-57e3-b0e1-36f1db737fe7 |  | note | – – – – – – – – – – – – – – – – –
label | ada2a212-0a9e-5aec-9d1b-4f2a0ec5becd |  | note | VERIFYING DOCUMENTS - This ITP
date | bc0475d1-0dff-5e5a-813b-8bef66dbfd15 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Assembly of outreaches and luminaires
label | ffdb096c-0c17-5d13-bef7-889280a5a463 |  | note | REFERENCE - L1-CHE-STD-035 IFC Drawings
label | fd46bd6f-447e-51eb-bebe-60f215d84cb7 |  | note | – – – – – – – – – – – – – – – – –
label | 19993395-b2e3-56e1-bdb8-1fcda0977ed1 |  | note | ACCEPTANCE CRITERIA - Outreach bracket to be installed to the pole spigot using the clamping bolt assemble
label | aad082f4-7299-59ce-86d4-3e36d58948b1 |  | note | Bracket and luminaire to align at right angles to vehicle path on road
label | 74266131-a769-5f11-9d4c-bddcf3de31b1 |  | note | – – – – – – – – – – – – – – – – –
label | c1e69849-94f7-5dc7-ba73-09bb3abf37da |  | note | FREQUENCY - Per Lot
label | c3653656-4c2a-5144-849b-a680f9ad58e3 |  | note | – – – – – – – – – – – – – – – – –
label | 0dd64302-fd28-5a25-b9b2-e4280997a946 |  | note | CATEGORY - IP
label | 592a078a-19db-5cfd-beee-f6fa5aaee3a9 |  | note | – – – – – – – – – – – – – – – – –
label | dae6b6b5-7b19-5f64-967b-7f6bb1cb9d20 |  | note | RESPONSIBILITY - SE/PE/SPE
label | f5f1ad86-f0a7-5499-84ee-54ea8c06effe |  | note | – – – – – – – – – – – – – – – – –
label | 1728d4f0-52ac-5489-bbc0-24e7bc4606f4 |  | note | VERIFYING DOCUMENTS - This ITP
date | 32b11e46-42f8-5788-86ae-3df8636bc76b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Installation of lighting distribution cabinet
label | 1a160110-387b-5444-ab1e-222a6c1a3bca |  | note | REFERENCE - L1-CHE-STD-035 IFC Drawings
label | 209a5f46-039c-5c6c-b301-cbbb6429df8b |  | note | – – – – – – – – – – – – – – – – –
label | c519e058-ce7a-5da5-be05-f2185343686f |  | note | ACCEPTANCE CRITERIA - The switchboard or distribution board shall be designed and manufactured from suitable materials appropriate to the location in accordance with AS/NZS 3439.1.
label | b4cca84f-c1c3-5736-ab19-b4c2643af683 |  | note | METHOD - Visual
label | be738e11-5402-5b7c-86c8-94af76945342 |  | note | – – – – – – – – – – – – – – – – –
label | 97c89c3c-3cea-5631-a553-cf54f3010cff |  | note | FREQUENCY - Per lot
label | 86abc145-3528-5ea7-a4c8-94c6bc99932d |  | note | – – – – – – – – – – – – – – – – –
label | 9358c237-b4b4-5be0-86b5-8d75254e9e34 |  | note | CATEGORY - IP
label | b94d4324-539f-5f41-b54d-b365fda2b259 |  | note | – – – – – – – – – – – – – – – – –
label | 412ca0ba-2119-5cc8-94fc-cd7b6aeed8fa |  | note | RESPONSIBILITY - SE/PE/SPE
label | a26e00fc-f873-5455-8944-c12022bdf0a1 |  | note | – – – – – – – – – – – – – – – – –
label | cca8ce08-ee53-5fbc-81e6-0f6a319c8746 |  | note | VERIFYING DOCUMENTS - This ITP
date | 91c9b8ec-31ea-519e-9965-c59e23a49f8b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Installation of cabling
label | 3d93c18f-4a39-59a9-b83e-38800d2d1b2c |  | note | REFERENCE - IFC Notes
label | 6dec2d8d-5a2c-5452-9f6a-f331c3fbcf2d |  | note | – – – – – – – – – – – – – – – – –
label | 0c4e553d-f015-5d4d-bd04-ec7bb14182d9 |  | note | ACCEPTANCE CRITERIA - All electrical cabling to be in accordance with the requirements of AS/NZS 3000: (Australian/New Zealand Wiring Rules) Each pole to be cables from the pole circuit breaker
label | 878ccd0c-cbb6-5f6a-9185-55bdf50925fa |  | note | METHOD - Visual & Document Review
label | 9821cdef-42ed-5fc8-a479-12893d7e232b |  | note | – – – – – – – – – – – – – – – – –
label | fb444b6c-c669-533f-b3d1-476f4c11f9c0 |  | note | FREQUENCY - Per Lot
label | efe8e37c-79da-5f41-bb80-8480685aa80d |  | note | – – – – – – – – – – – – – – – – –
label | dabdbe37-51b5-58fa-b342-fa152606c4b5 |  | note | CATEGORY - IP
label | a5c4ec2f-24b1-5f4b-bb61-fedfb3204189 |  | note | – – – – – – – – – – – – – – – – –
label | 1bb2e4ca-cac5-5729-a7c8-0a4052ee0a1c |  | note | RESPONSIBILITY - SE/PE/SPE
label | fe2a1a06-d152-5cd0-8a00-ff62d2909d04 |  | note | – – – – – – – – – – – – – – – – –
label | 865187f7-9a2a-53c9-bd93-f80c9d5892b5 |  | note | VERIFYING DOCUMENTS - Test Certificate This ITP
date | 35f6210e-57fa-5f16-9450-afd35e2e53be |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 - Commissioning & testing
label | e50a1276-33df-53e8-866e-582669e1b27e |  | note | REFERENCE - L1-CHE-STD-035
label | 4e9b07e0-3466-5923-a991-d33eccb6859e |  | note | – – – – – – – – – – – – – – – – –
label | 247bb616-a1e1-5429-b910-5affa75285c2 |  | note | ACCEPTANCE CRITERIA - Upon final acceptance, the Contractor shall switch on the lighting installation at the distribution cabinet in automatic mode, and record the time, date and meter reading for contractual, warranty and power supply purposes and supply this record to the Superintendent within 48 hours
label | c6819bba-8f67-50e5-9e48-0d295bba70d8 |  | note | METHOD - Commissioning & testing
label | 522c8e71-4768-5404-88fe-94497229ee4b |  | note | – – – – – – – – – – – – – – – – –
label | 91003672-e3ca-5759-ad7f-0aa5a68f15e3 |  | note | FREQUENCY - Upon completion of each section
label | 7db24f36-b760-531f-9da2-4a41c07a4c5b |  | note | – – – – – – – – – – – – – – – – –
label | 1568ef2a-fa58-583e-9d22-a1d9f835dccf |  | note | CATEGORY - HP*
label | b3a9f90f-d8b3-5931-96d4-41dc12c29ff3 |  | note | – – – – – – – – – – – – – – – – –
label | f3318008-416d-531e-aa56-a0a366eaec66 |  | note | RESPONSIBILITY - SE/PE/SPE Services Engineer
label | 2ad3b6a6-652b-5f5f-afec-6b5bda87ac76 |  | note | – – – – – – – – – – – – – – – – –
label | 0b958ff5-8adc-5042-a6eb-9f13fdcba9a5 |  | note | VERIFYING DOCUMENTS - This ITP Attach Certificate
date | f2aed501-6eca-5752-aa80-bb7af3db8f9d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 - Labelling of Assets
label | 8163cdc8-52a0-5098-85e1-8f3717aaff32 |  | note | REFERENCE - L1-CHE-STD-035 MTM Standard
label | f813db0a-c243-5adc-9e0f-0b075b6b7af8 |  | note | – – – – – – – – – – – – – – – – –
label | 01311221-425b-5844-b8cd-6b48d718b2c4 |  | note | ACCEPTANCE CRITERIA - Labels fixed to poles as per MTM standard. Pole numbering
label | 5a616424-94a5-51d1-87b8-45c182271ec7 |  | note | Labelling of switchboards, distribution boards, circuit breakers, RCDs and all control devices shall be labelled as per Appendix B in MTM standard.
label | 688ccdfa-5de8-5f15-a198-5758d6638087 |  | note | Indelible Labelled drawings shall be permanently displayed at the point of supply. Permanent field markers shall clearly identify the extent of the EPZ locations.
label | 6fbf1d9e-1ae3-5289-b6c2-eee88759ddda |  | note | METHOD - Visual /Site Inspection & Document Review
label | 389e4cb2-5301-5744-a1b2-c156f78dac61 |  | note | – – – – – – – – – – – – – – – – –
label | 69aa4ac4-3dc4-5e31-a73c-1f2e38b01272 |  | note | FREQUENCY - Per Lot
label | d4817ebe-1006-5cad-9d3a-ac772575ec6d |  | note | – – – – – – – – – – – – – – – – –
label | 1570d591-cc76-52ce-99fa-bede94ce50d7 |  | note | CATEGORY - IP
label | a3acbee2-32bf-5bcc-8ed8-7ebda9f58031 |  | note | – – – – – – – – – – – – – – – – –
label | bcff4920-e2b3-5a18-bf8c-ccbaa544bfc7 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 8cebabb9-152b-5416-9f45-0d5035d25846 |  | note | – – – – – – – – – – – – – – – – –
label | c03dfeb1-aeb1-5401-89b8-3784fdb372aa |  | note | VERIFYING DOCUMENTS - This ITP
date | d90168ed-8873-5cc1-9ce4-dcc4015388aa |  | date | Date Completed:
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | 5.1 - Attached and verify Subcontractor conformance records/signed ITP including relevant verification sheets
label | bb3884f5-af59-5ccc-bbb4-3806143c6ab9 |  | note | REFERENCE - IFC Drawing Note
label | 49c699a3-2934-5f5a-a6a2-5ee9af4df68b |  | note | – – – – – – – – – – – – – – – – –
label | e7ddf352-bc21-5362-b2b3-f94a9b04b394 |  | note | ACCEPTANCE CRITERIA - Check conformance report against project conformance criteria
label | 6adba040-ed7b-5094-9b5f-088aac6b4fdf |  | note | METHOD - Doc. Review
label | dd5d1724-d2f1-54e8-8cbd-84c0641acf64 |  | note | – – – – – – – – – – – – – – – – –
label | fa72ebe9-7288-548f-9a4b-e40bcf590ff5 |  | note | FREQUENCY - Each lot
label | 871b61ad-3c77-5ae0-831e-33138c481294 |  | note | – – – – – – – – – – – – – – – – –
label | 42a8b04f-59bb-5530-943c-859bbc8bdc6b |  | note | CATEGORY - IP
label | fe686fe0-46a6-5373-bb3c-7e0bea8b89f1 |  | note | – – – – – – – – – – – – – – – – –
label | e052d7c5-3274-585d-bac9-82893a017c46 |  | note | RESPONSIBILITY - SE/Site Supervisor
label | 22e82484-eb78-52ba-ab75-b2d44f269707 |  | note | – – – – – – – – – – – – – – – – –
label | 2bb8946f-f7de-5563-bff1-a6b667f6b04f |  | note | VERIFYING DOCUMENTS - Sign ITP Attach documents
date | 981feaa4-cc81-5b69-ae3c-78299a61cc9a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - As-Constructed Plans
label | 29f31834-77ce-5818-bb09-7b771a96f25a |  | note | REFERENCE - IFC Drawing Note
label | 9f8d3e01-967d-5e2c-a4ad-be890ec9dcb6 |  | note | – – – – – – – – – – – – – – – – –
label | 7ec4cbcf-98f3-59f7-a9b3-c8f598fb7e8a |  | note | ACCEPTANCE CRITERIA - The Contractor shall supply to the Superintendent two copies of ‘As-Constructed’ plans along with a USB drive or other approved storage medium containing the CADD drawing files, and the same shall be supplied by the Contractor to the local distribution company if appropriate.
label | 506866e6-74fa-5c8d-8a64-d15c5b8ef69c |  | note | METHOD - Document Review
label | 6aa47160-fd19-5910-b9ef-98d6caa05b2b |  | note | – – – – – – – – – – – – – – – – –
label | f834b3c1-016f-5155-9a39-65e748b41c95 |  | note | FREQUENCY - Upon completion/ Work area
label | 92c3f69f-02e0-5f35-9506-e5b2f90cd5d5 |  | note | – – – – – – – – – – – – – – – – –
label | 84304048-0fb8-5e54-9077-418ec88baeec |  | note | CATEGORY - HP*
label | 88adc4c8-a45f-57ff-b385-2f0bc0fdac70 |  | note | – – – – – – – – – – – – – – – – –
label | d6f55510-fa0d-53b5-afa6-998d305be29e |  | note | RESPONSIBILITY - SE/PE/SPE
label | d09eb47c-b240-5d27-b83e-368261a9c428 |  | note | – – – – – – – – – – – – – – – – –
label | cfc24c80-443e-5c1a-97c1-20e926010186 |  | note | VERIFYING DOCUMENTS - Sign ITP Attach As Constructed Plans
date | dcd423b9-a665-5861-b980-e6b5a0918072 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Non-conformance Report (NCR) Closure
label | 4a20ec9f-5dde-5b22-8c2c-ad213219074e |  | note | REFERENCE - MRPA Quality Management Plan
label | ad05bd0f-c5f5-5143-ae9b-98bc26adc424 |  | note | – – – – – – – – – – – – – – – – –
label | f5501924-2d3c-599f-b9b9-bc083d115e72 |  | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 2476944c-f8ff-500a-bee1-0289c0d698fc |  | note | METHOD - Document Review
label | 66e78546-a80f-5643-848a-2b7df4148b14 |  | note | – – – – – – – – – – – – – – – – –
label | ace47f07-4d94-522a-8443-ba3a4cdd8d59 |  | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
label | c0006926-2ffb-5c77-a0f4-1582b0528cf5 |  | note | – – – – – – – – – – – – – – – – –
label | 297c8f1a-7c0d-521b-8efe-2dc1a8495181 |  | note | CATEGORY - HP*
label | bd8bc239-8f7d-551b-884a-c9d8c8c036dd |  | note | – – – – – – – – – – – – – – – – –
label | 48e3d0f0-0c33-5fb5-9c36-b60db9769b42 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 16dfad08-66ed-52d6-bae2-27c219e3f970 |  | note | – – – – – – – – – – – – – – – – –
label | a64a7712-71a5-5ce0-a2b5-ef76eb545aba |  | note | VERIFYING DOCUMENTS - This ITP
date | a2b17e77-4ac6-5144-8aa7-3d54006c3398 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | c3b13b89-bc47-5377-8c80-af0e417bec52 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 7f5b4465-9bb3-507a-b049-2d49876114e0 |  | textbox | Name:
text | 0227ae78-9564-576a-83e3-4809e942891d |  | textbox | Position:
date | f2b65c71-2ece-5e53-85d0-4c792133fb79 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-101-STR-CAMMS-Concrete Coating Rev 0 | itp |  |  |  | Yes | ITP-101-STR-CAMMS-Concrete Coating Rev 0 | c5b33fb1-59d3-4399-822c-bd36a9a0fb13
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 8916acaf-485e-509b-ac5e-fb246aa42d9a |  | note | Document Title: ITP-101-STR-CAMMS-Concrete Coatings
label | 3d9d2bde-4e2d-5ea9-b80b-5fc82e6d278c |  | note | ITP Description:CAMMS-Concrete Coatings
label | b4c0b32b-e4e8-541e-b087-a656c6ca3717 |  | note | Discipline (e.g. CIV/STR/RAIL): 101-STR
label | 9f2836c8-b616-5e98-a487-e6d006dadf85 |  | note | Revision Number: 0
label | d031c039-3c8e-59a0-a53f-d60f8aa4ddb4 |  | note | Revision Date: 45238
label | f2e3b3c2-2048-54ac-9667-c9dd1b089f21 |  | note | ITP created by: Mike Freeman
label | cfc7899b-0f41-5290-945d-be4540609b36 |  | note | ITP approved for use by: Victor Mira
label | d8657910-40b1-5b7a-9dd8-e9af9e331c47 |  | note | 1.1 VicRoads Section 685 November 2018
label | d996486f-ce73-52e9-94d9-92126089b7be |  | note | 1.2 VicRoads Section 686 November 2018
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - Anti-graffiti System Selection
label | b4ead549-0c26-5a38-ab89-88ad575069f2 |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (e)
label | fb1930f0-d13f-5141-b516-144b6c6355af |  | note | – – – – – – – – – – – – – – – – –
label | 608c9251-fa03-5794-9a90-5b0cd85cd0da |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 879cbaee-f077-5004-85fd-5ad4dae88f52 |  | note | i. be either a film-forming or a penetrant system
label | 3d327b96-ce02-53f0-ab8d-6759ccc687c1 |  | note | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
label | 22e0f057-ab36-5553-adad-aee5000e94ed |  | note | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
label | 3b8a6087-ef1f-5662-85d2-228aa8f07980 |  | note | iv. be non-yellowing, colour-fast and not subject to fading
label | 6d5b8d89-d468-5758-ae3f-4e045bc783b1 |  | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | f55c158a-a4d4-5ecb-a2f7-1623a66d21f4 |  | note | vi. application thicknesses (film-forming):
label | 529866ce-408d-5bca-beef-91364b33bd4f |  | note | WFT total = 175µm min. OR
label | 62ffdbe5-5c25-5bc8-993f-d2f6a49f4718 |  | note | WTF per coat = 88µm min.
label | 4e12ee63-751f-5ae1-aa0e-8c6996a0d95c |  | note | DFT total = 100µm min.
label | fc3c0f60-5942-5820-9357-dfc52bfd0302 |  | note | vii. adhesion to substrate (film-forming):
label | 0d45d7e1-05ad-5217-9762-e4f4cd1b7808 |  | note | 0.75MPa min.
label | 01d1ed79-3f9e-50d2-a8a8-a4fe5d963daf |  | note | viii. application rate (penetrants)
label | c2bd2c88-ebc6-5bb3-a31d-06f48faba935 |  | note | as per the minimum thickness on the manufacturer's TDS
text | e3087bbf-be01-5700-adc1-a2a48f3f2572 |  | textbox | Enter: Teambinder Material Approval number
label | c75f5bc9-dc1b-5825-9d7c-fff984960843 |  | note | METHOD - Document Review
label | 73ca61e3-ee07-54a4-946e-af648f240fe3 |  | note | – – – – – – – – – – – – – – – – –
label | ca0cd941-86d0-5596-a3e7-fdad604be1fa |  | note | FREQUENCY - Once, for each coating system, 14 days prior to application
label | 6bb0d270-b05e-5212-a614-118576b8186a |  | note | – – – – – – – – – – – – – – – – –
label | 42654b02-1438-5ffe-a7ab-e2805f4fe50b |  | note | CATEGORY - HP
label | ee99aec9-b85b-5e28-9dcb-35ddf8bdebb3 |  | note | – – – – – – – – – – – – – – – – –
label | b3d0f4c6-043c-5756-984c-df10d75a97c6 |  | note | RESPONSIBILITY - Nominated Authority
label | 5839d469-6fbd-5eb6-8d1f-b4c778ef420b |  | note | – – – – – – – – – – – – – – – – –
label | afe4e622-9a99-535c-836c-5b4295d318b1 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 717b81ea-274f-5fd2-8df5-b85255d77d4d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Decorative & Anti-carbonation System Selection
label | 51f59276-4947-581c-9db6-04de8c2fc854 |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 686.04 686.05 (a) & (b) Table 686.051
label | 9eb820d8-e976-5029-9278-4cb0187d5c86 |  | note | – – – – – – – – – – – – – – – – –
label | e8b016d4-a9e0-5b22-b3f8-59398bbffa38 |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 4c715686-50f7-5397-9ff2-7c088573adb3 |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | 6730c009-55dd-5faa-bc50-63c27300ee9b |  | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | 7b83b536-c62c-5522-af0a-5945840b7cfc |  | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | f9a6c902-13d8-5862-b81f-ccff87b09531 |  | note | iv. be non-yellowing, colour-fast and not subject to fading
label | 220b27e0-08b8-50bc-8379-5ba1df6dea66 |  | note | v. be guaranteed to last for 10 years of outdoor exposure
label | 3d3e7275-30c0-56b3-8da2-66652e10cf68 |  | note | vi. application thicknesses:
label | a338418f-fe20-5f44-b341-d178541ca1c5 |  | note | WFT per coat = enough to achieve the total DFT
label | c46e2aea-fa86-5b8b-b8a9-ab9dc7c51ef7 |  | note | DFT total = 150µm min.
label | f73917d6-b9af-5a98-b83a-20d014f48cdd |  | note | vii. adhesion to substrate:
label | 9df4889e-83b9-50d1-979f-00eb4f629022 |  | note | 0.75MPa min.
label | 85102f78-dc10-5d26-9797-09763aa5e7a9 |  | note | viii. able to bridge cracks up to 0.3mm wide
label | 6d9f4a3e-df9f-5fc9-a899-3f83bdcdb83d |  | note | ix. able to be re-coated within 24 hours
label | 8e199736-cdd4-548a-a9d0-5ea18d4927d8 |  | note | x. have a minimum pot life of 1 hour
label | 440343e2-72b7-525d-92b4-cbb4ca77bc59 |  | note | xi. compatibility to an alkaline surface
label | 74cbdc47-ced0-5d40-96ff-78ea421c4824 |  | note | xii. equivalent air thickness >150m
label | 4bfd1985-9564-559a-820a-f045d86e7187 |  | note | xiii. equivalent concrete thickness >450mm
label | 7fd8ae5c-99c5-5dfe-89f4-0b8b6ee01218 |  | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | 44720dc7-33a2-5c60-9890-6109643e90f2 |  | note | xv. Water vapour equivalent air layer <4m
text | 665e2310-1e49-51a9-b81a-f46770bf3053 |  | textbox | Enter: Teambinder Material Approval number
label | cd25079c-37b5-597d-b685-f757501cd413 |  | note | METHOD - Document Review
label | 1b79a6af-e2c6-59bf-a630-72b1de7cc70e |  | note | – – – – – – – – – – – – – – – – –
label | aca5bc10-4766-5f53-ac29-8af39d626aa3 |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | bbe8eda8-9cf3-5e09-a195-5f7af1c684d4 |  | note | – – – – – – – – – – – – – – – – –
label | e84cda6e-2e8a-5427-aa74-6ecafba5d099 |  | note | CATEGORY - HP
label | 0b25ef89-7351-5263-868f-72283290ea5e |  | note | – – – – – – – – – – – – – – – – –
label | cf3809c5-5ed8-52cd-966a-b57db0f30d59 |  | note | RESPONSIBILITY - Nominated Authority
label | e2cd0db7-9731-5297-bca5-820483e50693 |  | note | – – – – – – – – – – – – – – – – –
label | 757afefd-2767-5c6f-b4af-cdd5f4b68dff |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | f33d5315-b81f-57c7-a98c-620e6484f757 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
label | fd5c6150-c569-51be-809c-f8352f6cbc08 |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051
label | cd064036-d5a7-5a2e-bcfe-710c6ce89194 |  | note | – – – – – – – – – – – – – – – – –
label | 37413969-09da-56e9-b49f-0d37df6f0edc |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 6bbb44e7-8c05-5914-b142-2320eef1dfc8 |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | 16c8347a-40e1-5601-9a41-9dd1f9288748 |  | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | 9177cae6-dcb9-5d01-8ad9-9b2714b8cb48 |  | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | 4f05bff2-f06b-5e60-99cc-23dfb5bc295a |  | note | iv. be non-yellowing, colour-fast and not subject to fading
label | 06762084-4878-59c2-a8eb-c2d9ce45756c |  | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | a82acbee-81bc-5832-8d66-f68e19229f83 |  | note | vi. application thicknesses:
label | 4f063c50-dda0-54a7-bc0f-f8699bc1beec |  | note | WFT per coat = enough to achieve the total DFT
label | 604dc424-7488-5740-9eeb-e08c9a39c39b |  | note | DFT total = 150µm min.
label | 25ee83cb-32b8-5a45-b8de-83609d4d7c94 |  | note | vii. adhesion to substrate:
label | 76c4a09a-8d2d-5eca-95eb-3823e4877589 |  | note | 0.75MPa min.
label | 20ab8b28-f717-5fe6-9eeb-4d393bac4a56 |  | note | viii. able to bridge cracks up to 0.3mm wide
label | 5d454a19-bc0b-580a-82ff-7bfa4dc4a664 |  | note | ix. able to be re-coated within 24 hours
label | 29c9f71d-439d-5c03-9e75-9fe3dcd93f1b |  | note | x. have a minimum pot life of 1 hour
label | d9f9e549-b551-5c85-bb81-bb4039c3b063 |  | note | xi. compatibility to an alkaline surface
label | 6dff8198-77fa-52c5-a17d-fbee7d9bbeef |  | note | xii. equivalent air thickness >150m
label | 3750bcf5-04e8-5053-ac00-9a0e76c395a7 |  | note | xiii. equivalent concrete thickness >450mm
label | a2788d37-40f2-5da6-be62-1451abbd3830 |  | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | 48459e82-06ab-5eb7-a57b-51bd0edc5711 |  | note | xv. Water vapour equivalent air layer <4m
text | c71babab-119b-5127-9aa3-905e672ab88d |  | textbox | Enter: Teambinder Material Approval number
label | a45682ea-dea4-56e4-bc35-7d49df49ec2f |  | note | METHOD - Document Review
label | f6fd6967-a5f0-5c98-877e-bf535c9f912c |  | note | – – – – – – – – – – – – – – – – –
label | fbcd7513-4f63-5d44-b35b-7cbc1f3a3b6a |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | 51c8ac38-7ebf-5cd2-a2ba-2b61c1bfe2ad |  | note | – – – – – – – – – – – – – – – – –
label | 6af6da10-27b8-5f2f-96aa-082de4fa4115 |  | note | CATEGORY - HP
label | d3ee3bd2-54bc-5f3e-95c9-d3710a36d42f |  | note | – – – – – – – – – – – – – – – – –
label | 7b9ecb26-eac4-5592-b2eb-d2c8ebe4f931 |  | note | RESPONSIBILITY - Nominated Authority
label | ccb0dc19-2c1f-5231-8a69-84d9b581a9cd |  | note | – – – – – – – – – – – – – – – – –
label | 1df5e442-6516-5282-b785-1c7236977e60 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 9b98baa3-0cae-514d-8c3b-b85f2e07ac61 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
label | 8a0c4451-9837-5099-9d6f-0349de68c952 |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051 686.05 (c) (i) & (iii)
label | fef91574-9953-515a-ad12-dd910ef0f3fe |  | note | – – – – – – – – – – – – – – – – –
label | 96634cc9-65c5-5610-884e-de0cf44c017a |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | d9438ece-5611-5bc8-9990-e673353cf205 |  | note | METHOD - Document Review
label | e47ca166-2280-5d09-8f42-d7e06f6f2ead |  | note | – – – – – – – – – – – – – – – – –
label | c3065801-9190-566d-8d9f-ed317fec9c5a |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | fe183c38-13fa-5f19-84cc-97cb855bdc0c |  | note | – – – – – – – – – – – – – – – – –
label | 9dd6a60f-7baa-5b4e-a5b7-38d197a44428 |  | note | CATEGORY - HP
label | 0891b304-35e2-5eb4-af94-e7c851e668fb |  | note | – – – – – – – – – – – – – – – – –
label | 3e9188ea-75c7-592c-9a91-43ec8a535fa1 |  | note | RESPONSIBILITY - Nominated Authority
label | b1122cc7-8cd3-5e06-bb95-1a9c62683233 |  | note | – – – – – – – – – – – – – – – – –
label | a7e96e17-7b9e-5a4d-9e3d-d91d76f1d431 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 6d87ca6e-6956-5b20-95de-8cec4c17f45e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Work Procedures
label | 16d65438-f75d-5e45-8c16-dea4a1350d86 |  | note | REFERENCE - 685.05 686.04
label | 2828785c-b435-538a-a5b8-37f6a6e6a6f0 |  | note | – – – – – – – – – – – – – – – – –
label | 90f7083e-e229-5cf7-852b-b11cc7ba0fa3 |  | note | ACCEPTANCE CRITERIA - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
text | 46713e36-2f5f-5e1b-b86f-a284cb737ed8 |  | textbox | Enter: Enter: Teambinder Hold Point number
label | e101a4f7-c842-5b19-ab42-1313a3017de7 |  | note | METHOD - Document Review
label | eccf481c-fc21-5b71-af5a-bd05310d5a0a |  | note | – – – – – – – – – – – – – – – – –
label | 38eee1a5-f3d2-5b36-baae-72841e153e41 |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | ed94faf6-76e0-50cd-8eab-ba4120f463ce |  | note | – – – – – – – – – – – – – – – – –
label | d19ece13-3d27-5d9f-99ae-f2aafcb96e43 |  | note | CATEGORY - HP
label | 58015e80-9610-520a-89ca-19e4edd397f9 |  | note | – – – – – – – – – – – – – – – – –
label | 227ef28e-d6d4-53a5-9483-7cb836cf8ea5 |  | note | RESPONSIBILITY - Nominated Authority
label | a3f74d71-3711-5b77-b1a5-c4f08eec6348 |  | note | – – – – – – – – – – – – – – – – –
label | 7f244d21-1e96-57d5-825a-cbb2f77fc82b |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 9338dee2-72f7-58e2-b204-b52c4ce8ceaf |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Coating Personnel & Equipment
label | 4ebb8834-c8af-5f93-a898-7861c71dc419 |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.16 686.18
label | 57ffe212-802b-5396-9d2e-2c2add93d79b |  | note | – – – – – – – – – – – – – – – – –
label | 0f049848-72a6-5f46-a50c-74595bfd5e34 |  | note | ACCEPTANCE CRITERIA - The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques.
label | 21ae3a89-98b6-5ae6-a61f-43a031fe20a9 |  | note | Application personnel require 2 years minimum experience.
label | cdae4b8f-6eb6-522d-9eb9-2e81ce466232 |  | note | The supervisor shall remain present at all times.
label | 695bf44a-dcd6-5696-9544-d9a0549d14c4 |  | note | Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
label | 19485621-4487-5568-9393-a86a50078c83 |  | note | METHOD - Document Review
label | 43730dac-d145-55c1-bcb6-48999c72633f |  | note | – – – – – – – – – – – – – – – – –
label | 1d347752-d9be-555c-91fa-3ee4c0cb0406 |  | note | FREQUENCY - Once, prior to application.
label | 6eea68b2-30ab-54bb-ad1a-8eba9cab95ae |  | note | – – – – – – – – – – – – – – – – –
label | 6392c2bd-6fdb-5df9-b13a-069817dc6c82 |  | note | CATEGORY - IP
label | f0b07153-2c7e-5612-a69c-7ba9a10f2395 |  | note | – – – – – – – – – – – – – – – – –
label | 162410ae-75fe-5c0b-9a38-c82cdc386092 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 23fabf97-dc7e-5532-897e-24833c8bd887 |  | note | – – – – – – – – – – – – – – – – –
label | fd7e27b3-0ac8-5d5d-9b47-a6f13c3c30f7 |  | note | VERIFYING DOCUMENTS - This ITP
date | c983613b-215b-596d-8bb2-2337820f6f6e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Protection of Adjacent Works & Property
label | 1cb29f2f-21ea-5d96-849b-ed3629faad4f |  | note | REFERENCE - 685.17 686.10
label | d6db4952-6ca1-5890-b89a-581097142dda |  | note | – – – – – – – – – – – – – – – – –
label | 018f8158-4727-51a5-9856-d66d27664df8 |  | note | ACCEPTANCE CRITERIA - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes.
label | 8b36626a-4544-569d-9418-af244f245bfd |  | note | No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place.
label | e2686a16-dcb1-5b12-b26a-90a0fbb0f921 |  | note | Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
label | a0f63288-f033-5b9b-afdd-abdc2c4fe292 |  | note | METHOD - Visual Document Review
label | 6de821dd-19d5-5136-93c1-5213c30e485a |  | note | – – – – – – – – – – – – – – – – –
label | 1cc5227c-0055-5e73-bd51-85195f7130be |  | note | FREQUENCY - Where applicable, 2 days prior to application.
label | 39e48054-5b7e-5fd0-ac3a-212440693d23 |  | note | – – – – – – – – – – – – – – – – –
label | e1b86a0f-341b-50cb-a1b3-92b5632c2452 |  | note | CATEGORY - HP
label | a68abdbb-dca6-5026-ae7f-6e258b60e929 |  | note | – – – – – – – – – – – – – – – – –
label | 4f4f7d97-fde7-5842-9f90-49952c376f33 |  | note | RESPONSIBILITY - Nominated Authority
label | 2a72bca7-84e1-5566-8fb8-bb1bdc97c16f |  | note | – – – – – – – – – – – – – – – – –
label | ce507fc6-ffff-5a8b-9d63-519c3a0be2f7 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | 29cc1bb4-63dc-58e2-8963-ad2bd68794b3 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Minimum Concrete Curing Period
label | 56f4afe2-8973-500a-8b12-77fe84194ec0 |  | note | REFERENCE - 685.08 686.16
label | 164bc062-c4e1-5829-aea5-6c73fdbc5e93 |  | note | – – – – – – – – – – – – – – – – –
label | 072dc550-36da-576a-b3c7-616d309dea60 |  | note | ACCEPTANCE CRITERIA - Concrete shall not be coated until the minimum concrete curing times have elapsed:
label | a122bf96-730e-56ae-adfc-734af0530c47 |  | note | Standard cured concrete = 14 days & moisture content less than 10%, or 28 days
label | 3a42ad69-72c9-5c22-848e-7e3fa9bc4800 |  | note | Accelerated cured concrete = 14 days
label | 397c0b50-6149-5b4a-83b6-95accf0dbb0e |  | note | Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
label | 1ed6c277-0309-5271-ab39-7539a1441bc8 |  | note | METHOD - Visual Document Review
label | bd37459f-08fd-524b-9a65-de7675f96c74 |  | note | – – – – – – – – – – – – – – – – –
label | b900dc2f-a486-5b32-989f-0b3f87711142 |  | note | FREQUENCY - Once, prior to application.
label | 6604ef06-498f-5878-aa20-43d54fa7e4a4 |  | note | – – – – – – – – – – – – – – – – –
label | b2239c03-843d-5544-9924-71ae4fad87e5 |  | note | CATEGORY - IP
label | acf5e8f9-65ca-5501-86de-70dffa58143d |  | note | – – – – – – – – – – – – – – – – –
label | 27e87c1c-bfa4-5825-ab34-41a57c05f909 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 3298cf6d-ea14-55ae-b42e-d317ff3b7aaf |  | note | – – – – – – – – – – – – – – – – –
label | dba4c6e2-8acf-5c6b-8e13-1625c77c280e |  | note | VERIFYING DOCUMENTS - This ITP
date | ae8b927f-8ac9-537c-9914-3fc537eccf95 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Trial Application (or Past Performance) Inspection
label | b9f44233-254b-5296-a469-606ee668cc20 |  | note | REFERENCE - 685.11 686.13
label | b348a5f9-a974-54cd-b343-b7989d484199 |  | note | – – – – – – – – – – – – – – – – –
label | 635c7055-0a4e-5e98-84bd-657fb415483d |  | note | ACCEPTANCE CRITERIA - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate.
label | 1ff071a2-819e-53e5-9b2d-c24c1c9721a2 |  | note | Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
label | 1cb683ec-8597-5fae-bcff-85708e647d76 |  | note | Attach: Inspection Photographs OR
text | 692c9471-ce06-5d86-8d49-1c1e845f37e3 |  | textbox | Enter: Teambinder Hold Point number
label | a05f8e3d-a191-53d4-b995-bc51d7b0bd7b |  | note | METHOD - Document Review
label | 2e73ece9-0a2a-5b77-a9ec-347bf32772af |  | note | – – – – – – – – – – – – – – – – –
label | abc3704b-e7a5-5b24-a7a7-30c29df2bb67 |  | note | FREQUENCY - Once, for each coating system, 7 days prior to full coating application
label | e1ab11ee-08e6-581d-9904-01ab380f2bb1 |  | note | – – – – – – – – – – – – – – – – –
label | 4606d8cc-d3ce-52da-b985-1fc545752402 |  | note | CATEGORY - HP
label | bd37af7e-5ae2-50cc-9da8-51eded9e1068 |  | note | – – – – – – – – – – – – – – – – –
label | 7ac74573-2e31-5e86-9ce0-a33d2682d610 |  | note | RESPONSIBILITY - Nominated Authority
label | 19f3ddb3-9994-58d0-9ed9-eb9e2be85070 |  | note | – – – – – – – – – – – – – – – – –
label | de8e292e-fa43-5f70-86cb-11d33da43673 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
date | e6f23566-58ef-520c-8d27-f5dce96921eb |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-application Activities
checkpoint-status |  |  | checkpoint | 3.1 - Material Records
label | 6b098a2d-5d63-5513-a1b2-738fa5b3980a |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.10 685.12
label | 7109fbf7-891d-5a59-9edf-65c7ac34315c |  | note | – – – – – – – – – – – – – – – – –
label | 29f354aa-af39-564d-a95d-1ce4b7940a0b |  | note | ACCEPTANCE CRITERIA - Materials shall be brought to site in unopened, sealed containers, clearly marked with:
label | 139c1af0-4c12-54dc-88d3-db72a6bc4f32 |  | note | the manufacturer's name & address
label | 13ced07f-8066-52ed-9924-cd6608337f1c |  | note | product reference
label | e1ad6875-b013-55af-977a-1913208ccdcf |  | note | batch number
label | 94a08809-ad89-5171-82d7-8e48f64ef200 |  | note | quantity manufactured in the batch
label | 801679d8-a9de-5c36-998b-a23b90e3faba |  | note | date of manufacture
label | 4bfb1057-9079-59a4-a9b0-c34161826581 |  | note | Product beyond the manufacturer's shelf life shall not be used.
label | 31531eda-cb9d-5eef-bd63-8a2e5ea1144b |  | note | Each product shall be traced to final location.
label | c5b15c8a-0f17-5116-9b3c-72f08cea947b |  | note | METHOD - Visual
label | 14bdd21d-025d-57e2-b00b-13f5ec4a5ea5 |  | note | – – – – – – – – – – – – – – – – –
label | 768821db-5ca0-589d-82f5-7d59ddfd6c64 |  | note | FREQUENCY - Prior to application
label | 8e44d889-b159-5791-b98a-a2d1568c511b |  | note | – – – – – – – – – – – – – – – – –
label | 08a36fd7-43d3-5a88-ac8d-5e4ad1e31f52 |  | note | CATEGORY - IP
label | f6cee039-074a-5d7d-90eb-5277c0558234 |  | note | – – – – – – – – – – – – – – – – –
label | 6d5149a9-f830-5fe6-8092-0deb6c5e0297 |  | note | RESPONSIBILITY - SE/PE/SPE
label | d053cd0a-0c77-534d-8c2c-c612cef6b230 |  | note | – – – – – – – – – – – – – – – – –
label | edec7399-6c6b-52fe-a0ba-483e8fdbe73c |  | note | VERIFYING DOCUMENTS - This ITP
date | 2b5deec9-b5b0-5ea8-ad32-c361084a090d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Weather Conditions
label | ed219a1a-a555-5847-90e7-0daec43f4de2 |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.09 685.12 (a) 686.11 686.14 (a) (iii)
label | 7f785d0d-b758-51e8-ba41-7e05be1896d9 |  | note | – – – – – – – – – – – – – – – – –
label | 3156beeb-b749-51be-8ddb-dd7bf3fa397d |  | note | ACCEPTANCE CRITERIA - Coating systems shall not be applied under any of the following conditions:
label | 225dc430-ce05-5e28-a578-f6eaec46aa6b |  | note | i. windy conditions where spray/splatter may be generated
label | 5895360a-5b3a-5921-b2f0-79767aae1036 |  | note | ii. when wind-borne debris is likely to contaminate the uncured surface
label | c1e37edc-7381-5573-91bb-efb456d77628 |  | note | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
label | 15f31b15-5da1-5e12-9f57-f52bfae9f3bc |  | note | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
label | 3ef83ccc-7374-5bc6-9a4e-2b5ee6d2d360 |  | note | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
label | 2336aeb2-d1a1-5275-ae2a-0eb7c61ddfbd |  | note | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
label | e4f14428-d735-5c0c-a73a-8733f158244f |  | note | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
label | 646d5423-927b-559a-a80d-a2b6ecf24481 |  | note | Weather conditions are to be recorded.
label | ee097803-bba3-5c5a-83e8-f13ce2295cd3 |  | note | METHOD - Visual Measure
label | 2d64f54d-9ed5-5d93-9939-dcbc79b8951d |  | note | – – – – – – – – – – – – – – – – –
label | ee6fddcb-3657-5246-951c-e189ab006730 |  | note | FREQUENCY - Prior to application and every 4 hours per shift
label | d2deb1e2-2588-5946-a6cd-2a04c835406f |  | note | – – – – – – – – – – – – – – – – –
label | 7a2eca93-4935-5170-bf83-b0c5811be53f |  | note | CATEGORY - IP
label | 7ca5d210-3ad0-5e06-ab9e-6647f822f102 |  | note | – – – – – – – – – – – – – – – – –
label | 635742d3-c2fa-5b25-ac39-0c56785214a6 |  | note | RESPONSIBILITY - SE/PE/SPE
label | db032e4a-1d09-5a9f-ae0b-a6ab19a9b4b6 |  | note | – – – – – – – – – – – – – – – – –
label | d90e02f2-d45d-56bd-8786-9d96fb44f9da |  | note | VERIFYING DOCUMENTS - This ITP
date | 698aa470-15be-5b4b-a811-4395adc511c7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Surface Preparation
label | 312430ab-4b1b-5f60-8386-c963112e83b9 |  | note | REFERENCE - Surface Cleaner TDS Coating System TDS 685.05 686.06
label | fccbe39e-b029-5fa1-ab6b-97e79cac8602 |  | note | – – – – – – – – – – – – – – – – –
label | fc1951b5-ac0a-55eb-82fe-b5c0b9f15af6 |  | note | ACCEPTANCE CRITERIA - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means.
label | 0b792b5c-b716-57a3-b157-3a021f6e376d |  | note | The surface shall then be flushed with water.
label | 304bef1c-7230-5887-9486-95f99038800d |  | note | Any concrete defects exposed during the surface preparation shall be repaired accordingly.
label | 484156a1-f6bc-52d6-b875-89369717db62 |  | note | METHOD - Visual
label | 9ceef4ed-d88a-542f-987e-8b5a3e97ac63 |  | note | – – – – – – – – – – – – – – – – –
label | b5fccb9f-07b5-5f2f-a104-1c8f4e1fa0bf |  | note | FREQUENCY - Once, prior to application.
label | 1b21da9f-3e46-5821-bcc3-a836f1bbacee |  | note | – – – – – – – – – – – – – – – – –
label | 1ed41a6c-a9ac-5200-b620-bb84b035fcb5 |  | note | CATEGORY - IP
label | 2979c127-0cd6-5f3a-b36b-5490e6f37146 |  | note | – – – – – – – – – – – – – – – – –
label | 053d4ba6-dcf2-53a3-b63d-86dc61eec93b |  | note | RESPONSIBILITY - SE/PE/SPE
label | 6c9cd3a7-bdcc-5355-a0de-f5ea3762905a |  | note | – – – – – – – – – – – – – – – – –
label | ddebdbd9-9721-51b6-8308-9920ab53699a |  | note | VERIFYING DOCUMENTS - This ITP
date | 9ad137ed-3a19-5c9b-a75f-38c42576367d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Surface Moisture Testing
label | acf5e39c-4bbd-58dc-917d-60c4e395cbae |  | note | REFERENCE - 685.12 (a) 686.14 (a) (iii)
label | f939d28f-b90e-5bb8-8ecc-f135ad8ecb12 |  | note | – – – – – – – – – – – – – – – – –
label | ceaa3c80-589e-5e1e-9910-7ee8c9ed7904 |  | note | ACCEPTANCE CRITERIA - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS.
label | e727f87a-096c-53c6-94bc-27d7859ff314 |  | note | Surface moisture conditions are to be recorded.
label | 6343c793-782a-5767-b7f4-971662f302fe |  | note | METHOD - Test
label | 458f2fe7-8c0e-5be1-82ac-0e5817d3568d |  | note | – – – – – – – – – – – – – – – – –
label | 4f584bd1-e5cf-53db-b730-df514c35c395 |  | note | FREQUENCY - Immediately prior to application, 1 no. test every 50m²
label | 6b32fd79-481d-542c-a54a-a91326af2d94 |  | note | – – – – – – – – – – – – – – – – –
label | 51bcb0ec-57d1-511b-81d9-c880ca3707c5 |  | note | CATEGORY - IP
label | 06ffc42c-b6c3-5473-87f0-f51af857df54 |  | note | – – – – – – – – – – – – – – – – –
label | baf21de4-e6b1-536f-ae7d-3c9d28fbd73e |  | note | RESPONSIBILITY - SE/PE/SPE
label | bb53599f-75b1-557a-935c-7aa391c1518e |  | note | – – – – – – – – – – – – – – – – –
label | 3b89f386-09db-5f98-8ce5-4725c788710d |  | note | VERIFYING DOCUMENTS - This ITP
date | b4fdf5ed-0bf4-54f3-a0e7-70341304833a |  | date | Date Completed:
checkpoint-group |  |  | section | Application Activities
checkpoint-status |  |  | checkpoint | 4.1 - Method of Application
label | fe0fd949-e71a-5b2c-9fa6-6c1b3bec1e51 |  | note | REFERENCE - Coating System TDS 685.07 686.07 686.09
label | b7d31f54-898e-50fc-8e61-b9a700538a82 |  | note | – – – – – – – – – – – – – – – – –
label | 3f4dcdd6-3b3f-5c37-9185-9917df1fcb37 |  | note | ACCEPTANCE CRITERIA - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved.
label | 13b22c91-a245-53c1-b8bd-d1cbc5c45fc5 |  | note | Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified.
label | 78309429-c4ae-5797-b9f0-ebb707229c48 |  | note | For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application.
label | d5600b94-56f8-5b8f-aadf-02e8a02e50ab |  | note | Times of coating(s), material names, locations coated and volumes used shall be recorded.
label | 770870ed-78c5-52d7-8978-91d158f3f0bb |  | note | Attach: Coating Application Record
label | 1e6cf814-416b-5cf2-8e2a-5558fefb2094 |  | note | METHOD - Visual Measure
label | fed1d79e-dec5-5fbf-a325-4a99a38562d4 |  | note | – – – – – – – – – – – – – – – – –
label | 94a2d588-7053-5f1b-be6a-56deb39b7c1e |  | note | FREQUENCY - Each coat
label | d1b97df6-9af7-526f-b38e-51e57eca70a9 |  | note | – – – – – – – – – – – – – – – – –
label | 1ffe2354-fb4f-5495-89ec-5ce8c533e87f |  | note | CATEGORY - IP
label | 9e24d606-1484-5859-bb02-ae3f46e6b634 |  | note | – – – – – – – – – – – – – – – – –
label | 02ed7ab2-a091-5287-87a8-75246ab29f58 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 8f6bd13e-693f-5631-aa07-8c67c01d7731 |  | note | – – – – – – – – – – – – – – – – –
label | e8df90df-e454-5284-92f9-f0498a3fb825 |  | note | VERIFYING DOCUMENTS - This ITP
date | 065a8c5b-4fe6-5e11-8cd0-7c60922cedcb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Wet Film Thickness (WFT) Testing
label | 5e22c590-f9e3-5a0f-b073-ad7bf02e7d83 |  | note | REFERENCE - Coating System TDS 685.12 (b) (ii) 686.14 (b) (ii)
label | 97b18963-0144-5efc-b931-6c5459bebfb1 |  | note | – – – – – – – – – – – – – – – – –
label | ae30ef65-0255-5d57-a508-2da202e876b5 |  | note | ACCEPTANCE CRITERIA - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
label | c2cc001b-bfce-581a-94cb-dc9d527f7a0a |  | note | Attach: WFT Test Results
label | ceafa2e9-023c-5675-8428-337674655aeb |  | note | METHOD - Test
label | 1c3fd5e1-b37c-54b5-a4c0-1df94ce6c7d3 |  | note | – – – – – – – – – – – – – – – – –
label | 20c08b37-adf5-593b-aa08-1c4bc1e3973d |  | note | FREQUENCY - Where required, 1 no. test every 50m², 3 tests minimum
label | 0a6683e8-c8ea-58be-8bce-455dde368976 |  | note | – – – – – – – – – – – – – – – – –
label | 1bbc3605-ebe2-52d1-a1ce-6c182c338f66 |  | note | CATEGORY - IP
label | 31b6dfd2-4168-5899-b265-595fdfe99ce7 |  | note | – – – – – – – – – – – – – – – – –
label | ef59f538-2f8a-5a28-a3d3-cef637710a9a |  | note | RESPONSIBILITY - SE/PE/SPE
label | e99b67a5-9f99-5808-9f20-fd32e5dd556e |  | note | – – – – – – – – – – – – – – – – –
label | 4ad05700-3932-5e29-ba54-48e8550cbe1c |  | note | VERIFYING DOCUMENTS - This ITP
date | 61c64df9-825f-56d5-9e15-b34ddef95c76 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Inspection & Defect Identification
label | 9b09bc43-fafc-5591-8c4d-3928732c8283 |  | note | REFERENCE - 685.07 685.13 (d) 686.07 686.15
label | c05c15b0-555b-524b-bbe9-6f79fbfd7da4 |  | note | – – – – – – – – – – – – – – – – –
label | 286bd12e-bb08-571e-8d2f-50e551a82f6e |  | note | ACCEPTANCE CRITERIA - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats.
label | e8865e4f-483f-5a23-a44a-0feab06235a6 |  | note | Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
label | 2ae01cb1-3f56-505a-8cab-ad6a29b78d53 |  | note | METHOD - Visual
label | 4371bcfa-f0e0-5f80-acd3-13bf8578cc49 |  | note | – – – – – – – – – – – – – – – – –
label | e216cf8f-b3d4-535b-98ca-388e4bd73716 |  | note | FREQUENCY - After each coat
label | 49ffa3d1-e82d-5178-b878-67e41eae7f10 |  | note | – – – – – – – – – – – – – – – – –
label | 429223fd-5c46-5d3e-94ff-bec2ff53a390 |  | note | CATEGORY - IP
label | 37b4ebae-f3a2-5b0d-a17f-6b5f3525951a |  | note | – – – – – – – – – – – – – – – – –
label | 53ebe7cb-f73d-59e7-808a-58332022f141 |  | note | RESPONSIBILITY - SE/PE/SPE
label | dd77daa0-5919-5002-b051-1c6eb5061a8e |  | note | – – – – – – – – – – – – – – – – –
label | b2875f66-e503-52d9-b82e-28f8f5b64255 |  | note | VERIFYING DOCUMENTS - This ITP
date | c5cc7544-90f5-5b9f-9aa0-6e97f5e17aed |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Drying and Curing
label | 0fc4b746-5dd1-584b-acc5-8491e1515c7d |  | note | REFERENCE - Coating System TDS 685.17 686.10
label | 6582ef00-4ea1-5b44-8f13-49d707b8ce9f |  | note | – – – – – – – – – – – – – – – – –
label | 0f733304-47fd-572b-ae84-bc3e76004ec7 |  | note | ACCEPTANCE CRITERIA - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
label | de888d0a-9293-5238-9e35-049c6466b36d |  | note | METHOD - Visual
label | 7ff590a2-a686-526e-9d67-a051362b41e7 |  | note | – – – – – – – – – – – – – – – – –
label | 4d605e34-736d-5b06-bc83-870ea06eeaa5 |  | note | FREQUENCY - After each coat
label | ed6106b4-1b23-5c6b-a378-0f45cb5ea5b4 |  | note | – – – – – – – – – – – – – – – – –
label | efd0c9cc-b98d-5a8a-86b1-9c03ca060ae4 |  | note | CATEGORY - IP
label | ebcd18f1-04ba-5a42-90fb-f32654a0f634 |  | note | – – – – – – – – – – – – – – – – –
label | 626e979d-50e1-5ecb-8a26-7f392e5f09bc |  | note | RESPONSIBILITY - SE/PE/SPE
label | b956ad82-b174-51c8-bdc9-5432e7035fac |  | note | – – – – – – – – – – – – – – – – –
label | 41d52740-e3e2-5588-84bc-63dde18ce951 |  | note | VERIFYING DOCUMENTS - This ITP
date | c00c38e7-ffa2-55a5-9a91-8424314c4779 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-application Activities
checkpoint-status |  |  | checkpoint | 5.1 - Clean-up & Waste Disposal
label | 3bc63e85-9d86-52ac-8fbe-feb9d2243408 |  | note | REFERENCE - 685.09 (c) 686.10
label | 6a4471aa-1bd4-597f-a46b-9c69bc127e50 |  | note | – – – – – – – – – – – – – – – – –
label | 491c234c-1a05-5eef-9e72-e55311093d3f |  | note | ACCEPTANCE CRITERIA - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
label | 51502a97-9ccc-5829-b415-15dcdb4cc54b |  | note | METHOD - Visual
label | 045b317e-db67-55e9-9578-b3eb41caed1f |  | note | – – – – – – – – – – – – – – – – –
label | f8e46d7b-c88f-52dc-8b06-59fde0d8919a |  | note | FREQUENCY - At completion of Works
label | 4285900d-3395-56e7-ae03-ae7d71e5bfe0 |  | note | – – – – – – – – – – – – – – – – –
label | 84549586-24e6-5a09-9ae9-d7c3096f84fa |  | note | CATEGORY - IP
label | 36393cb2-acc4-540f-900c-8d5d593b545d |  | note | – – – – – – – – – – – – – – – – –
label | 2acb000e-3a91-545b-b73b-4e5caaef2410 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 53bd4c4e-80b0-513a-b131-1bdff214ba68 |  | note | – – – – – – – – – – – – – – – – –
label | 4ab433f4-1a59-573d-be8f-36c70170ddf8 |  | note | VERIFYING DOCUMENTS - This ITP
date | 3d636e15-136a-589d-8c01-40188eabb98a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Dry Film Thickness (DFT) Testing
label | fe03938b-24c9-56e7-b8bf-6af5b7b453aa |  | note | REFERENCE - 685.12 (b) (iii) 686.14 (b) (iii)
label | 47fe56df-9153-5200-b384-6de422213c70 |  | note | – – – – – – – – – – – – – – – – –
label | e1298cb1-7eb5-5914-a9c8-8896d84b80c7 |  | note | ACCEPTANCE CRITERIA - The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
label | e4062379-7368-5f3e-a17f-0785111591bc |  | note | i. Anti-graffiti system = 100µm
label | 5f005a3d-1206-5886-bf5c-ec7aa867eb63 |  | note | Ii. Decorative & anti-carbonation = 150µm
label | d17e4272-528b-5ae5-af9f-ed3eda81feaa |  | note | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
label | aa055f11-b8de-55e6-9f31-74d03952a973 |  | note | iv. Atmospheric & splash zone (dual protective) = 200µm
label | 455f3568-37da-5206-8057-74f18f857f15 |  | note | No more than 15% of the readings shall be less than 90% of the required thickness.
label | 4d475e8a-207a-5d02-912c-9547fdbf8b05 |  | note | Attach: DFT Test Results
label | 79f7c98f-3857-5554-bbe5-a0f5df389e3b |  | note | METHOD - Test
label | 2a65fcd5-6d5b-5c55-9c17-8cbdd257f98d |  | note | – – – – – – – – – – – – – – – – –
label | aa80b24d-0af2-54b0-b6ac-17968b3d003b |  | note | FREQUENCY - Where required, 1 no. test every 50m², 3 tests minimum
label | 3046bbc7-0519-589d-a56f-62c5676a9e0f |  | note | – – – – – – – – – – – – – – – – –
label | 1f291aa6-6e84-511b-8db0-88a2eca05da1 |  | note | CATEGORY - IP
label | 4d601762-257d-5b7e-a488-fb4c327289bf |  | note | – – – – – – – – – – – – – – – – –
label | c722cc6b-f69a-574e-89b1-17028dcdd2d6 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 8fff6794-9d78-5b2b-ac2b-88e2c5c1e59b |  | note | – – – – – – – – – – – – – – – – –
label | 843fc2af-f4cc-5422-ac52-28616a51e842 |  | note | VERIFYING DOCUMENTS - This ITP
date | 53c79991-eaaf-5e85-aee1-1a05c62fcb00 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Adhesion Bond Strength Testing
label | 8f443fe1-e56f-544b-bfe9-f772abb28c97 |  | note | REFERENCE - 685.12 (b) (i) 686.14 (b) (i)
label | abc0570d-ff25-59d0-9868-a9e9ff1e50a9 |  | note | – – – – – – – – – – – – – – – – –
label | 6c300cd0-4be8-58de-b4f5-8f34d320a854 |  | note | ACCEPTANCE CRITERIA - A minimum of 14 days after application, the bond-strengths between:
label | ac3cf5e1-b43b-5047-b5ce-adad3376bb9f |  | note | i. the coating system to the substrate, and
label | 3f77816b-934d-5022-ad95-f7408a6bde05 |  | note | ii. Separate coating layers
label | 9a848a44-6e7f-52da-bc69-06089598122e |  | note | shall be tested using 50mmØ aluminium dollies.
label | 71462617-7555-544c-bd52-9673ca6dd384 |  | note | The subsequent results shall be greater than 0.75kPa.
label | 71a4212e-3670-5a38-adcf-556a2634b2ae |  | note | Attach: Adhesive Bond Strength Testing Results
label | 54a573b4-dc34-5940-8cb9-7e1571f64896 |  | note | METHOD - Test
label | 1fb98e75-1b11-5dab-b484-690bd4b3c1ea |  | note | – – – – – – – – – – – – – – – – –
label | 0b4f1cd0-f60e-550a-862f-4a62d90df8cd |  | note | FREQUENCY - Where required, 1 no. test every 50m², 3 tests minimum
label | 14e1b01b-1e31-5dc0-8f3f-e3c3c2ab7098 |  | note | – – – – – – – – – – – – – – – – –
label | 8e470121-2c12-5cc6-a44d-2ef5eb08e341 |  | note | CATEGORY - IP
label | 0c101dcd-3315-5c67-963d-f543c7ca74f7 |  | note | – – – – – – – – – – – – – – – – –
label | 64942d5b-3b17-5dcf-ad0c-2ecd0a508f7a |  | note | RESPONSIBILITY - SE/PE/SPE
label | 95cb01eb-f3cd-549d-898e-4c2ccf55508a |  | note | – – – – – – – – – – – – – – – – –
label | b0c52580-8905-5f24-ad3d-b47dab9f57d1 |  | note | VERIFYING DOCUMENTS - This ITP
date | 5996bbd8-0cb9-5ca1-85a6-92d923873449 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Penetration Depth Testing
label | 25e88ad6-d76f-57aa-9a3e-98f38babb8ef |  | note | REFERENCE - 685.12 (b) (v) 686.14 (b) (v)
label | 17d59154-f41a-59be-b6a1-23b1b308467b |  | note | – – – – – – – – – – – – – – – – –
label | 51fad38a-4050-50cb-b661-74a82676ba12 |  | note | ACCEPTANCE CRITERIA - Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration.
label | b652d69b-8771-5c70-96d6-24d7bb608d6d |  | note | The subsequent results shall be:
label | 6d257bed-4edd-5b3a-bad2-a7da365d58b8 |  | note | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
label | 94d64a33-a933-51b5-a05b-7fb99037d155 |  | note | ii. Silane, Solid Silane or Silane Cream = 5mm min.
label | 7c6cfb2e-a2c5-513e-851a-b12d5c193013 |  | note | iii. Silane-Siloxane or Siloxane = 3mm min.
label | 47e317b3-4aaa-55bb-9311-050c77e4ad8c |  | note | Attach: Penetration Depth Testing Results
label | 4d401968-0742-5662-a436-4c5a3241987f |  | note | METHOD - Test
label | 29060a1c-bd69-5391-91b8-70c411bfaf71 |  | note | – – – – – – – – – – – – – – – – –
label | 14c98c5d-b364-560f-835b-45c6377e7fce |  | note | FREQUENCY - Where required, 1 no. test every 50m², 3 tests minimum
label | e485e153-a2c5-56cf-a38d-0fd4e6d4e6e1 |  | note | – – – – – – – – – – – – – – – – –
label | a408687f-a06a-5b56-a2e4-dc702ef44b10 |  | note | CATEGORY - IP
label | 2640a37c-ab66-5f3c-80c0-6bf22b630b87 |  | note | – – – – – – – – – – – – – – – – –
label | 69846bb6-3b66-50e6-8e5d-d05a73ba9a19 |  | note | RESPONSIBILITY - SE/PE/SPE
label | b607f895-5df7-53f8-8266-5802c59629b8 |  | note | – – – – – – – – – – – – – – – – –
label | 7b87f7ca-2b48-57e7-8a01-bb678b2de70f |  | note | VERIFYING DOCUMENTS - This ITP
date | e9365851-f524-50bf-885b-86ecf382ef27 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Non-conforming Coatings
label | d7a34510-771c-5a73-9cc0-9c17e63400b8 |  | note | REFERENCE - 685.14 686.17
label | b3d68538-eec3-5bd3-8f26-5a7c9f52e4c4 |  | note | – – – – – – – – – – – – – – – – –
label | 70cc79ae-bece-526e-b15d-0e598614e2f2 |  | note | ACCEPTANCE CRITERIA - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
label | 70b8aed4-6505-5f79-97ff-c5a873bfb2b3 |  | note | METHOD - Visual
label | 1cc9a861-046e-580d-a165-9cbb67ddf8e9 |  | note | – – – – – – – – – – – – – – – – –
label | 134ca011-7332-563d-9adf-d52dbfad5a8b |  | note | FREQUENCY - Where required
label | dfdfcfd7-3fdf-5eae-9f98-ecb10fcf93a3 |  | note | – – – – – – – – – – – – – – – – –
label | 5b20a5d9-9203-5c78-ad7a-fb9b1469ca04 |  | note | CATEGORY - IP
label | 9f0278a7-d981-5047-9240-cca16bf10434 |  | note | – – – – – – – – – – – – – – – – –
label | 4efcfa9f-7182-5273-8fad-8739cfec143a |  | note | RESPONSIBILITY - SE/PE/SPE
label | 7570800a-6457-526b-b431-ec2c9eb9431e |  | note | – – – – – – – – – – – – – – – – –
label | bab21829-b0b1-5b40-9470-bde4aa3776ea |  | note | VERIFYING DOCUMENTS - This ITP
date | c8597128-da19-566d-9292-0facd2afca1a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Coating Application Guarantee
label | 84b275a1-f108-5b10-9708-788982e5bd7e |  | note | REFERENCE - 685.06 (b) 686.05 (a)
label | 3367b534-f689-5553-9c19-8349787eebfb |  | note | – – – – – – – – – – – – – – – – –
label | aa1dfa44-3ae8-5761-bad5-ec25f77c15f5 |  | note | ACCEPTANCE CRITERIA - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application. Attach: Coating Application Guarantee
label | 44d84224-5414-587b-bd86-f82687c92a9b |  | note | METHOD - Document Review
label | 1f58faa4-8716-50e3-bc89-045a96444022 |  | note | – – – – – – – – – – – – – – – – –
label | be4efd42-b62a-529b-ad51-58c408b10dc5 |  | note | FREQUENCY - At completion of Works
label | 8426f002-bcf7-5347-8a95-4cf12ec87b4c |  | note | – – – – – – – – – – – – – – – – –
label | 8d89f470-ef10-5117-b785-2c1468cb0ca1 |  | note | CATEGORY - SP
label | 0ffc7516-d23d-5ad6-b33c-8197adb6f242 |  | note | – – – – – – – – – – – – – – – – –
label | b747ca1a-0365-5d4c-b8b5-55deeb1e6997 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 499708d8-706d-5f91-979d-b916cbac10e8 |  | note | – – – – – – – – – – – – – – – – –
label | b0daf211-5b5b-5e8e-90c7-5879a709e006 |  | note | VERIFYING DOCUMENTS - This ITP
date | 1be9c8a0-5703-5007-88cc-c2148932bd55 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Repair to Damaged Coating
label | 239a3315-6626-53ab-9c67-4a634dd6df60 |  | note | REFERENCE - 686.17
label | f3270985-c685-5320-8db7-a83cd394c97f |  | note | – – – – – – – – – – – – – – – – –
label | 757d9ea9-a546-5265-b583-c5b1052ffd52 |  | note | ACCEPTANCE CRITERIA - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
label | 38351f96-42c0-5570-98a4-35c6dd9a45db |  | note | METHOD - Visual
label | 0945739b-3d09-5ca6-b84c-43aa88237d8f |  | note | – – – – – – – – – – – – – – – – –
label | ca6eda3e-9ead-5a6d-8846-da1a1ae7b954 |  | note | FREQUENCY - Where required
label | 794c427f-13a1-5e45-bd5b-07363caca510 |  | note | – – – – – – – – – – – – – – – – –
label | de4b93fd-89ef-5731-bb7f-1ee786ffca0d |  | note | CATEGORY - IP
label | 52d462aa-5d8a-5f2b-8915-defe3f3df7ef |  | note | – – – – – – – – – – – – – – – – –
label | 300d104e-1e6e-5e4d-96cd-c8a18f4d3b98 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 591815dd-9be5-5fd1-858f-14f18950120a |  | note | – – – – – – – – – – – – – – – – –
label | 6ce3ebf9-374b-5d57-94cf-72a8082249ef |  | note | VERIFYING DOCUMENTS - This ITP
date | e03c2b79-e968-5276-8832-1d1985aa27e2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Non-conformance Report (NCR) Closure
label | 7c8e4468-700f-53de-88df-eeda502873d6 |  | note | REFERENCE - MRPA Quality Management Plan
label | b81fa867-4a3c-5aa7-8c43-4f3781f50638 |  | note | – – – – – – – – – – – – – – – – –
label | a4f5b7f0-1bf6-5d4d-95e8-61842c039279 |  | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | a5d1a2db-87cb-527d-82ab-7352a768c63f |  | note | METHOD - Document Review
label | 7c5a58cb-4944-5153-9bf1-e8632661ac9c |  | note | – – – – – – – – – – – – – – – – –
label | 664ec7c3-6b65-59c9-aae9-8cb4faedba85 |  | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
label | 4f50dbc8-94d4-53fe-ada5-e0c54bc6579f |  | note | – – – – – – – – – – – – – – – – –
label | 168dad84-4a80-5a00-8280-7da3327face6 |  | note | CATEGORY - HP*
label | 1c694b51-d40c-5f25-8678-c2d79f83de96 |  | note | – – – – – – – – – – – – – – – – –
label | 4b129659-1bd6-5231-9902-2ff6f000b443 |  | note | RESPONSIBILITY - SE/PE/SPE
label | ffc26814-91bb-539f-b217-9e967ebb2d14 |  | note | – – – – – – – – – – – – – – – – –
label | b26d9351-7c8e-566c-92c2-7a7a5dced69b |  | note | VERIFYING DOCUMENTS - This ITP
date | c4bd3358-c144-5969-b4f0-68424abcae30 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | b8f5b572-51a1-511c-bcb2-3dad9ff54434 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 2a69210d-6e5c-590d-b731-68b5fa190349 |  | textbox | Name:
text | 84db1487-ede8-5101-a92b-c1dac3cfd9d2 |  | textbox | Position:
date | 99d803fa-e42e-5d18-b0ee-d3a983b1e9d6 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation Rev 2 | itp |  |  |  | Yes | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation Rev 2 | c62ef726-2c3b-40cb-90d2-0cf77d810730
checkpoint-status |  |  | checkpoint | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation
label | c5a16d14-8fd7-5673-bcb3-40b769e5a9fa |  | note | Document Title: CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation
label | c75fad33-c825-5fc3-b1a5-85a4c10ea66b |  | note | Check list Description: RSS Walls - Panel installation
label | b3c32878-4e5f-59a4-ad27-88b6feb26cc9 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | e7a9bc07-bcb4-5d32-9bea-b42261067476 |  | note | Revision Number: 1
label | c2c7b40d-ed5f-52eb-8402-abbdd9652bf2 |  | note | Revision Date: 1/05/2023
label | 1b0525ee-efc0-59ab-bdd6-c9b9f80f2da2 |  | note | ITP created by: Victor Mira
label | 1d513f23-5118-5fba-bee2-65d3ed1b530e |  | note | ITP approved for use by: Victor Mira
checkpoint-status |  |  | checkpoint | 1 - Panels - survey set out - Tolerance
label | 23a66d11-c81b-5d90-8e2b-b135187d2f60 |  | note | REFERENCE: IFC Drawings
label | 8ca8be64-881e-5af3-8b23-f28b4653ee4b |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | b4e7572c-c98d-583e-a095-f1ce60c84a9e |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | 038f8606-35b9-530d-982f-6b45e1c9867e |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | fe60598e-c3bc-5543-96c7-c143300dbb67 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | 0dfdb242-2f10-5432-8aad-a055d29038ed |  | note | • VR 682.20
label | f4e0c35b-6fea-592e-b448-acfbf39b7989 |  | note | – – – – – – – – – – – – – – – – –
label | e03fc02b-1069-523c-ac53-64060ecc39b2 |  | note | ACCEPTANCE CRITERIA: Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | 26f9d85c-38d3-5362-8932-318223282810 |  | note | – – – – – – – – – – – – – – – – –
label | 832fb03c-9168-5749-bb32-70252f5a244e |  | note | METHOD: Measure
label | e1439810-e913-505c-ae91-edb6e762be58 |  | note | – – – – – – – – – – – – – – – – –
label | 71cef091-ed70-5fbf-abd5-e70c270a09d7 |  | note | FREQUENCY: Base course panels
label | f7502225-9b4b-5f83-a84e-540d1f32ae99 |  | note | – – – – – – – – – – – – – – – – –
label | ee31311e-f205-567c-b8c8-6f6deedce921 |  | note | CATEGORY: IP
label | 791942bf-a635-5e77-88f6-7060067b5998 |  | note | – – – – – – – – – – – – – – – – –
label | 9fee023b-d43e-5aa0-b994-f9a12671b491 |  | note | RESPONSIBILITY: Surveyor/PE
label | 4fd7f7b8-3241-577d-86f3-afd6889a9e61 |  | note | – – – – – – – – – – – – – – – – –
label | b91051c5-4bde-50dd-b600-030774884652 |  | note | VERIFYING DOCUMENTS: This Checklist
label | cbebf9bb-ce4f-5d17-bd1f-900d572369d0 |  | note | – – – – – – – – – – – – – – – – –
date | f867021f-bd1f-5a7d-ac79-6312478e3492 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Mark - up panel for construction team
label | a54d2561-18b6-5022-a718-d6bb791389ce |  | note | REFERENCE: Construction Manual
label | 7ec78dc3-4d0d-583a-9266-dfc4aab028d9 |  | note | – – – – – – – – – – – – – – – – –
label | 22d6852d-7f91-58ae-b765-473405f0442d |  | note | ACCEPTANCE CRITERIA: Mark number of strips per row on the back of each panel.
label | 282449de-19ee-5f4d-b45b-5de8214b18ea |  | note | – Mark design locatoin (Wall number, row and column) as per elevation drawings on the back of each panel
label | 27579e98-933b-53a6-9fb0-d2b7f30e8776 |  | note | – – – – – – – – – – – – – – – – –
label | c4eb7d05-e586-5302-9c0e-eae30c7cf0b7 |  | note | METHOD: Visual
label | 242fb79a-02da-5db4-a65b-2ee08ff8e15c |  | note | – – – – – – – – – – – – – – – – –
label | d03ee3f5-d262-5d30-9186-3881bc24450e |  | note | FREQUENCY: Each panel
label | 45530eb1-08c9-5fa3-97a4-5ee25a4f7ffe |  | note | – – – – – – – – – – – – – – – – –
label | 8c6685e2-bb21-5a48-a85f-97c38567385d |  | note | CATEGORY: IP
label | 68df1298-b827-57c1-ae4a-e2dccedf6bcb |  | note | – – – – – – – – – – – – – – – – –
label | 00f9fe8a-066f-5da0-a875-4c476b75d62c |  | note | RESPONSIBILITY: SE
label | b1e0247f-d109-5e17-8d32-717788774de4 |  | note | – – – – – – – – – – – – – – – – –
label | 17879788-7f09-50d8-b4c8-c02bd278a32a |  | note | VERIFYING DOCUMENTS: This Checklist
label | 559ad51c-656f-5dc0-b9e9-91380e8d71df |  | note | – – – – – – – – – – – – – – – – –
date | 39d430eb-aa71-5ae1-a8a4-4ea4ee83fcf0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Panel installation
label | 3bb41032-8098-57a8-9358-95587937464a |  | note | REFERENCE: IFC Drawing:
label | 70042d7f-219d-5ea2-9d9b-c20cd6177eea |  | note | Schedules:
label | 1a36cd5a-7bdd-5cfc-8b07-2dc802e09f9a |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1302
label | dfa2be3a-44e7-5f7d-af19-fe42b8e0e147 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1403
label | 73568bb3-4275-59ba-aeb0-69b9fd1c42ca |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1503
label | c17619f3-e33f-5883-ad05-39d6332890ec |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1602
label | c2683d72-2447-5110-b19c-9489fa4dcae2 |  | note | Instructions:
label | 23582b7b-6ce2-59cb-9ce3-a205fd753569 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1803
label | 5f2cd94c-fad7-55f3-99de-cab4ce4061c6 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1804
label | a3a56a56-696b-5840-9a30-873283f6ee90 |  | note | – – – – – – – – – – – – – – – – –
label | 1aa0c1a1-e396-5b99-adb1-e03490c1011c |  | note | ACCEPTANCE CRITERIA: RSS Panels are to be installed as per IFC Drawings and specified schedule.
label | 5a26c661-5401-53fd-9715-bff9dc8adc82 |  | note | – Check for correct architectural pattern
label | f6785c57-ba34-5309-8f68-6e2d59d9aa67 |  | note | – Check for Weephole Locations
label | dd703921-8cb5-5cf1-a235-587bdf628e8d |  | note | – Check the 19mm nominal gap to be maintained
label | 8be10dc3-03a5-5b1a-843e-24060261fd35 |  | note | – Check the 1 in 40 slope is to be maintained
label | d6ce6772-94ba-5fbb-aef0-76257a03688c |  | note | – – – – – – – – – – – – – – – – –
label | 26593c92-68cd-5827-be75-42e69ec0bbab |  | note | METHOD: Visual, Measure
label | 5ff37e92-53c4-5780-9c94-a85d26af8920 |  | note | – – – – – – – – – – – – – – – – –
label | 99bf4faf-956f-5254-9b37-7247e89578f2 |  | note | FREQUENCY: Each panel
label | f0058788-3752-5c57-883a-6283c26e490f |  | note | – – – – – – – – – – – – – – – – –
label | 4bf0c283-d54a-5ed9-8ca6-ad4d11db1b6f |  | note | CATEGORY: WP
label | e0b962bf-3cc6-5bf3-b987-d2e425d33dbb |  | note | – – – – – – – – – – – – – – – – –
label | 2a7ba18e-7ffd-5d77-b239-f5f0c07186c0 |  | note | RESPONSIBILITY: SE
label | bec01d8d-8ba6-5543-b859-617be33d3068 |  | note | – – – – – – – – – – – – – – – – –
label | e71af293-7ba3-582b-b38a-d877034fe306 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 53081d18-7b90-5479-994a-4bc944d31504 |  | note | – – – – – – – – – – – – – – – – –
date | bceee11e-ed48-57e8-be45-7b61245b5543 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Panel installation - Abutment interfaces
label | 2c00f9b7-a277-5a5a-9979-906dd2f60fbf |  | note | REFERENCE: IFC Drawings
label | 113edc7b-ba49-565f-9ce3-86129a1015ff |  | note | • MRP-052-C-SME-DRG-32-MPK-CSW-2052
label | 4243c3ea-5376-5c7b-b8ca-42289e40de8e |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1105
label | 2df9a8c9-87c6-5069-ae4c-3cb63348ed01 |  | note | – – – – – – – – – – – – – – – – –
label | 46a0b2af-cb0e-53ad-ba03-2073f7e52f39 |  | note | ACCEPTANCE CRITERIA: 20mm nominal gap between panels and Abutment wall is to be mainatined
label | a049662c-6ed1-5d74-8853-85ecb9822682 |  | note | – 300mm wide x 6mm thk Galvanized plates fixed to abutment wall and Adjacent panel as per IFC drawings.
label | 645b9f2e-a6d1-5e87-a43b-891536103985 |  | note | – 600mm wide BITAC tape installed
label | 1a06227d-f000-5d97-8cb5-05ccca847277 |  | note | – – – – – – – – – – – – – – – – –
label | 3f5728c2-4931-5a04-9b64-8c4631b5a11e |  | note | METHOD: Measure
label | 854221ed-1c1d-59fd-8929-45014b576f5e |  | note | – – – – – – – – – – – – – – – – –
label | 00bc96da-19c1-5a03-be89-3bebdec8f539 |  | note | FREQUENCY: Where applicable
label | f7f6cb3c-5b1e-5e46-b248-e5b95252b556 |  | note | – – – – – – – – – – – – – – – – –
label | 112e3be3-57ba-5ae6-a766-7f5e2f26112f |  | note | CATEGORY: IP
label | b8b8f520-8cfd-57da-bf35-71244ea36ac4 |  | note | – – – – – – – – – – – – – – – – –
label | b3d29da7-2407-5666-9586-d72a51b0a39c |  | note | RESPONSIBILITY: SE/PE
label | adebb367-c6a9-512c-b0b4-797a9281291c |  | note | – – – – – – – – – – – – – – – – –
label | f995fa8a-ec76-5429-8895-d4c4aeac0f23 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 07c25085-be13-5a73-b96b-b4b702d4a9e1 |  | note | – – – – – – – – – – – – – – – – –
date | bbcba258-d29d-5aeb-bed9-79727ad13d67 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Filter fabric - Installation
label | 281be809-1b15-5f9a-bc4c-ec54fd160ee8 |  | note | REFERENCE: IFC Drawings
label | d363558f-439b-56a4-a45d-95619b20e490 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1803
label | ef4b2a75-ed23-52a5-ad07-99cb43b0c6a2 |  | note | – – – – – – – – – – – – – – – – –
label | 1b80d513-f2b5-5491-93aa-daef5aca2cd2 |  | note | ACCEPTANCE CRITERIA: Install Filter Fabric against all vertical and horizontal joints
label | 7dfc11c0-65fe-567c-8153-ba44ad8b764f |  | note | – – – – – – – – – – – – – – – – –
label | c4ab92b0-f224-5ac4-826c-ea008d13bf6a |  | note | METHOD: Visual
label | 94fbf997-5af3-511e-a2ff-dbad3d294a07 |  | note | – – – – – – – – – – – – – – – – –
label | 3639bd1c-1e2b-5470-89ff-17765d7f79a2 |  | note | FREQUENCY: Each course of panel installation
label | d61f508f-a64f-50d0-8de6-cd9ddf7270e2 |  | note | – – – – – – – – – – – – – – – – –
label | 713a07ee-45ae-55c6-8d24-33aaa945fe9b |  | note | CATEGORY: IP
label | 45bb1b74-a748-50e0-bc12-5bfd2a2ac905 |  | note | – – – – – – – – – – – – – – – – –
label | aaad321a-36e0-5865-b287-18fa5b93e550 |  | note | RESPONSIBILITY: SE
label | c122cb0e-b52d-524b-bb15-0e771aac1719 |  | note | – – – – – – – – – – – – – – – – –
label | 1cb0367e-75ac-531a-a225-06f0145a0612 |  | note | VERIFYING DOCUMENTS: This Checklist
label | da3def15-225f-573d-a30a-951dff2f1327 |  | note | – – – – – – – – – – – – – – – – –
date | 995c35a2-83d2-508c-a200-6405354f61b2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Drainage - Strip Drain
label | fcf0237d-865a-535d-bef0-835964fe099e |  | note | REFERENCE: IFC Drawings
label | f760aa20-4a10-532e-ab80-6e3a4d1bbe7a |  | note | • MRP-052-C-SME-DRG-32-MPK-CSW-2053
label | b60a1d07-d40c-5e85-b16e-52d2e35c4093 |  | note | – – – – – – – – – – – – – – – – –
label | 313e0339-b68c-50ce-a767-0809db8f23f2 |  | note | ACCEPTANCE CRITERIA: Install 150mm wide vertical strip drain "PRODRAIN PD20"-at every vertical joint between panels in RSS wall.
label | 24701114-612b-52fb-8bf8-742e241251e9 |  | note | • Ensure no gap is formed between strip drain and RSS panels
label | cd929267-b18f-50e1-85c8-6deb08780e2d |  | note | – – – – – – – – – – – – – – – – –
label | e11fe419-c661-51f3-aa0a-2cfbb23ee8fe |  | note | METHOD: Visual
label | a5e6c454-ee7a-5734-9261-f678ce57ebad |  | note | – – – – – – – – – – – – – – – – –
label | 8b788e96-b93f-5fbf-a41d-1f4f667fecc9 |  | note | FREQUENCY: Each course of panel installation
label | 7d6b27ca-c00d-5858-b4ed-88437f568e2a |  | note | – – – – – – – – – – – – – – – – –
label | 9c0a3cf5-859f-5559-b03a-fe6e5fe952fb |  | note | CATEGORY: IP
label | d2d2d06d-a816-589a-8036-b12314f36ba9 |  | note | – – – – – – – – – – – – – – – – –
label | 2e50e39d-ef35-5c28-8477-ec3eeb9dc472 |  | note | RESPONSIBILITY: SE
label | 3d4f2ee8-41f7-5d30-9445-28421c960c15 |  | note | – – – – – – – – – – – – – – – – –
label | a1ebe31d-74ba-572a-b1b4-69323b723678 |  | note | VERIFYING DOCUMENTS: This Checklist
label | b47cbb4c-4478-50c1-8254-829fc7acf869 |  | note | – – – – – – – – – – – – – – – – –
date | fb72623a-fee8-543c-a9fb-b0754cee2519 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Panel installation - Survey reference points
label | 48d1a665-1dba-5775-8b3a-6b28f1e67168 |  | note | REFERENCE: VR 682.21
label | 159d2442-aa54-5d5c-9809-4b489ed7c04a |  | note | – – – – – – – – – – – – – – – – –
label | 8b6802dc-2272-5a1a-ae70-27231607bfe3 |  | note | ACCEPTANCE CRITERIA: To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | daf5e89d-dc58-508f-8da0-503c108ca91c |  | note | – – – – – – – – – – – – – – – – –
label | c99ca691-ce5d-5108-b838-8ea48d438c19 |  | note | METHOD: Visual
label | f79900df-f42c-5035-8a84-bc041a78cba2 |  | note | – – – – – – – – – – – – – – – – –
label | eb2bf11f-1213-526c-8a3e-33e69033076f |  | note | FREQUENCY: Each course of panel installation
label | 281daa7c-906f-5110-b6dc-773ae41d4247 |  | note | – – – – – – – – – – – – – – – – –
label | e65ecf24-a9c4-57a9-921b-6109dc114bd9 |  | note | CATEGORY: IP
label | cb2244eb-1d84-5f23-a3e6-45e21c8c36a2 |  | note | – – – – – – – – – – – – – – – – –
label | 6f41e742-6059-580f-9857-730660639c15 |  | note | RESPONSIBILITY: Surveyor/SE
label | 62328cc8-f116-5c9e-b8c8-446ba5905296 |  | note | – – – – – – – – – – – – – – – – –
label | 466a9442-cfaa-5995-a4eb-b23e1a37b9ab |  | note | VERIFYING DOCUMENTS: This Checklist
label | 2a576ff9-381b-52b5-9ecf-ba9f53132f67 |  | note | – – – – – – – – – – – – – – – – –
date | 551cfb7f-4c7f-5c3c-a866-e15eaaf13e5d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8 - Traceability of precast units and records
label | bd727285-11da-53b5-88dd-2b764151b902 |  | note | REFERENCE: VR 620.09
label | 98be84e8-6df8-51f9-82a3-88bf7b6b9e3d |  | note | – – – – – – – – – – – – – – – – –
label | 64bbadfc-874b-5477-8f99-70b519bf7d45 |  | note | ACCEPTANCE CRITERIA: Unique ID of precast panel is recorded.
label | fd6a1188-53df-5d83-bb74-4e703b833d7e |  | note | ATTACH: marked-up elevation drawings or installation record with reference to panel ID
label | a995fa8b-9aea-5cbe-92bf-e6ecb887c660 |  | note | – – – – – – – – – – – – – – – – –
label | f5cc8514-439a-50bf-910d-c6f33bcc4c3c |  | note | METHOD: Visual
label | 59506b47-d793-57e2-9c84-4073f30ec51e |  | note | – – – – – – – – – – – – – – – – –
label | 4b9440c5-212a-5aed-a944-461a6fbe407a |  | note | FREQUENCY: Each panel
label | 3d2df8de-46a0-540f-8361-f9b53a555afa |  | note | – – – – – – – – – – – – – – – – –
label | 9fd8b91a-16db-5451-8f4f-f7c964819960 |  | note | CATEGORY: IP
label | 694ff59b-540c-5560-80b5-8780db689b93 |  | note | – – – – – – – – – – – – – – – – –
label | 4155fdff-9f4b-56de-9add-2f8357f06060 |  | note | RESPONSIBILITY: SE/PE
label | 45999bd0-ed74-5ad7-9f60-733c317e8721 |  | note | – – – – – – – – – – – – – – – – –
label | e19a2e14-9aec-561b-bca0-bee8f1c8a88e |  | note | VERIFYING DOCUMENTS: Attached marked-up drawing or installation record
label | c10942d9-3dd2-599b-9d98-c955ce5f667d |  | note | – – – – – – – – – – – – – – – – –
date | fc5753dc-1827-59ac-8f5b-a3defb45b30b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Panels installation - Conformance Survey
label | 34695902-daef-565f-8a0d-11d76cd6a904 |  | note | REFERENCE: IFC Drawings
label | a76089db-bf8f-5a6a-ae28-f22870447ac0 |  | note | • VR 682.06
label | 146879ee-cbd0-5a79-a56b-68163137e8ad |  | note | • VR 682.17
label | db762e8d-4dc8-550b-af25-9402b87ed03b |  | note | • VR 682.20
label | 915275e6-93ba-5e14-8b24-cf4e47ad226d |  | note | – – – – – – – – – – – – – – – – –
label | 2bb74069-5a67-5793-9faa-359b5f2b1a82 |  | note | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
label | 0b37c4bd-4413-5d31-8c3d-2d52aece63ec |  | note | The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | 66103a84-1cb4-5c84-bbca-a9d9fb554471 |  | note | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | c47addd8-9c5c-5b4c-b7d7-6f61d054bafc |  | note | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | 9d25e40b-6223-5544-843e-ca967a9438a7 |  | note | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap
label | 9669028d-5d99-5761-bf4b-0417137ab185 |  | note | – The wall level shall not deviate from the specified level by more than ±20mm
label | 87926d59-23bc-58f5-833a-f01d8e090317 |  | note | – The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | 1391a4fc-9ff2-5542-b8ac-a640ee0792a6 |  | note | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
label | 0c36ec03-8e7c-5cfd-ae5d-65b453ac0dcf |  | note | Attach: Survey Report
label | f48aaade-39c8-5bd4-9ecc-fa557f64db0b |  | note | – – – – – – – – – – – – – – – – –
label | 73d267c6-6390-5ad9-9975-0ed0cae2bc96 |  | note | METHOD: Survey, Measure
label | a2fc2eb5-0fad-561a-ac4d-378643cce10d |  | note | – – – – – – – – – – – – – – – – –
label | 071ee6e6-7590-5fb9-9d92-05c8b3700572 |  | note | FREQUENCY: Each course of panel installation
label | 084205dc-4bb1-5870-9ba3-a07fa1ef83f1 |  | note | – – – – – – – – – – – – – – – – –
label | 5687f847-696c-5521-a64f-6856122dd8f5 |  | note | CATEGORY: HP*
label | 0a376d96-b85b-58e0-9117-202852facf02 |  | note | – – – – – – – – – – – – – – – – –
label | 98c678c4-c945-5fa5-b461-fe8e6d6890c6 |  | note | RESPONSIBILITY: Surveyor/PE
label | a419bbda-b98d-5f53-9571-e42871ac7ea7 |  | note | – – – – – – – – – – – – – – – – –
label | 9900df89-8f4c-511b-801c-9068d001d398 |  | note | VERIFYING DOCUMENTS: Survey Report
label | 7223d2e3-0094-5359-8325-c5ab91fe6757 |  | note | – – – – – – – – – – – – – – – – –
date | 2cbfe2bc-8754-55ac-83f6-c0d5ff05b907 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | db45e4b2-f016-513e-bbe7-7e6d09735799 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 704cba7f-2aa6-532f-867c-e92bc9cd18fb |  | textbox | Name:
text | d1d6d11c-db25-58e4-bf48-5a2acdd76150 |  | textbox | Position:
date | 1b0e467b-937c-5048-85da-8dc77932e3c6 |  | date | Completion Date:
holdpoint |  |  | signoff | Signature
checklist-sectioned |  |  | checklist | ITP-012-STR-RSS Wall-Main | itp |  |  |  | Yes | ITP-012-STR-RSS Wall Main Rev 1 | cff17963-117f-4710-9ec3-3daf3faa28a7
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 5a3c858d-f28d-5a26-a500-cc3ccd289b49 |  | note | Document Title: ITP-012-STR-RSS Wall-Main
label | 81e6080e-17b6-50a5-9007-811886e5a1b0 |  | note | ITP Description: RSS Wall-Main
label | 10c7818b-bed6-5b3c-ae83-424d6ac42aee |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ea799ef0-a113-59a5-8e54-c79b86433a9a |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 498af1db-14e3-52ff-b944-57a29aa971ed |  | note | Revision Number: 1
label | 6242921e-876c-544e-9f2f-ac537052c48f |  | note | Revision Date: 1/05/2023
label | 79df7bf9-0549-59c1-ae10-a0131f8a60bf |  | note | ITP created by: Victor Mira
label | 2f2c2240-1f4b-5584-aea4-e76720b09432 |  | note | ITP approved for use by: Victor Mira
label | 147c6ce6-a448-540b-81b2-8b6396f4ed00 |  | note | 1.1 Non Dependent
label | 00a30657-d2d0-5182-9580-e3f1bf8c454d |  | note | Reference: VicRoads Section 682 November 2018
label | 48faceb2-6dcc-538c-93b4-9b862336b697 |  | note | 1.2 Non Dependent
label | 84d4e5dd-f2d2-5b91-9285-cc8ec4df3022 |  | note | Reference: VicRoads Section 204 December 2015
label | 8c45244a-453f-5f98-a4de-7c839e660b6a |  | note | 1.3 Non Dependent
label | 0003dad2-c909-5638-8e58-cc337f9b5d93 |  | note | Reference: IFC drawings
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete-Leveling Pad
label | ac6e6da8-dfc7-5fbd-a5c6-cd5ea2b452e2 |  | note | REFERENCE: IFC drawings
label | e52c053b-6646-56c9-871e-246989d9df76 |  | note | – – – – – – – – – – – – – – – – –
label | 2e3e43b6-0a5b-520d-86a6-ddf81de9207f |  | note | ACCEPTANCE CRITERIA: CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS;
text | e1d913ef-72e0-5001-b24e-90a1ad47f37b |  | textbox | Reference: Teambinder MA number:
label | cf8e5207-4ebd-5eca-842f-ed0f7ed8716e |  | note | – – – – – – – – – – – – – – – – –
label | 17dbc5f6-89f3-5d41-b45c-2f473438863d |  | note | METHOD: Document Review
label | 3bd87415-233e-53e2-bf41-8c7984c80b71 |  | note | – – – – – – – – – – – – – – – – –
label | 1763229c-2a85-5470-b43f-b0326ad14288 |  | note | FREQUENCY: Each element
label | e4f72307-66d6-5faa-b854-22111c158f44 |  | note | – – – – – – – – – – – – – – – – –
label | dc07650c-b347-5554-b8fe-159901d40fee |  | note | CATEGORY: HP*
label | eb483f7a-ba76-5f7e-8f68-50b77cd21337 |  | note | – – – – – – – – – – – – – – – – –
label | dda970fc-b7d7-5411-8e43-aea331a03894 |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 6ccf35c6-a5b8-580b-9c04-69e75857281d |  | note | – – – – – – – – – – – – – – – – –
label | 7d1711a2-562b-53f5-b318-f95c160839d7 |  | note | VERIFYING DOCUMENTS: Material approval
date | 839571de-373e-58e8-b39b-01735f0d9355 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Select fill
label | a16c16e1-651e-5f63-aa99-33a4a8f863db |  | note | REFERENCE: IFC Drawings
label | b60f344e-a05f-57fe-a3cb-cfa5b801b74e |  | note | – – – – – – – – – – – – – – – – –
label | 9e6acb6b-967a-5087-a334-f1a4a9a055ec |  | note | ACCEPTANCE CRITERIA: Select fill shall comply with the requirements of the RSS designer:
label | 1ce20ea9-aaa3-576b-9d14-db784fad7e0c |  | note | • UNIT WEIGHT: 22 ± 2 kN/m³
label | de3aada8-5ab9-5fd8-a6f0-906678e2834e |  | note | • INTERNAL FRICTION ANGLE ≥ 34.5°
label | 7c436b6a-d2d0-51df-8fb5-7cca9f406982 |  | note | ○ Gradation:
label | 529f86fd-741c-5f05-bc70-5f1b4f17845f |  | note | • 150mm: 100% PASSING
label | 1484a270-60e7-5e3f-9d3e-80064e9d0c35 |  | note | • 37.5mm: 60 TO 100% PASSING
label | 4f7d50dd-4d92-5e18-b4d8-212213b5b50c |  | note | • 9.5mm: 25 TO 100% PASSING
label | e0f62b97-6261-59fb-af81-afda8d770742 |  | note | • 2.36mm: 15 TO 100% PASSING
label | 13475b85-6a63-59e0-9a6d-8d4ce6ae4371 |  | note | • 0.6mm: 10 TO 100% PASSING
label | 9951afd5-575d-56c8-b319-1afa017119fd |  | note | • 0.075mm: 0 TO 15% PASSING
label | baab5bfe-bfaa-5698-85db-1e831a6de5a7 |  | note | ○ Electrochemical Properties:
label | d97e3a73-7176-5426-b13c-39562a7248cf |  | note | • RESISTIVITY >1000 Ω-cm
label | 057062b8-cab0-5792-9a75-375923fd3104 |  | note | • CHLORIDES <200 mg/kg
label | d310a8ed-d230-5a05-b540-5ce5bfd7ae7e |  | note | • SULPHATES <200 mg/kg
label | e0002a05-caf5-530a-8e87-e39ace8b8f70 |  | note | • ORGANIC CONTENT 0%
label | 24bf6a1f-9cb2-5048-9572-82a9466c9df1 |  | note | ○ Structural Properties:
label | c446fcb9-2056-59c8-abe2-f2fbe4de6926 |  | note | • COEFFICIENT OF UNIFORMITY ≥ 5
label | 2f69d07d-e8a3-5af6-a12c-da001c7a6597 |  | note | • LIQUID LIMIT ≤ 30%
label | 395b2a51-bcf3-5c99-a950-b62a1738aca1 |  | note | • PLASTICITY INDEX ≤ 12
label | 10daa424-35a9-5070-bff5-47c50c6bc3c5 |  | note | • The select backfill must meet the minimum requirements of Vicroads Type A filling
text | 5ff27ccd-6ed0-5f2b-9bbc-62043614a8cf |  | textbox | Reference: Material approval in Teambinder
label | 76697044-1b1f-5854-9fb7-c6f3d398c50f |  | note | – – – – – – – – – – – – – – – – –
label | 1848b70e-4d6f-5cc6-b353-5daaffb7ba0e |  | note | METHOD: Document Review
label | de263bd7-ecdf-54cd-a93b-6fcd7acc0782 |  | note | – – – – – – – – – – – – – – – – –
label | c59a7622-d7c7-5e60-8495-daacd4b9b9e1 |  | note | FREQUENCY: Each material specification
label | a6d902ba-0fb7-54a0-8b54-1d6890ce558f |  | note | – – – – – – – – – – – – – – – – –
label | 40bf56a7-78ac-589e-bc6f-e910b25059ec |  | note | CATEGORY: HP
label | 20e58292-a9a5-5365-80ef-32c028bf3631 |  | note | – – – – – – – – – – – – – – – – –
label | d5d9791c-fd78-50cb-b9ce-5b29c0abe554 |  | note | RESPONSIBILITY: Nominated Authority
label | 33088e73-7560-5967-97af-115e80542c20 |  | note | – – – – – – – – – – – – – – – – –
label | fc955469-8f6f-5597-8640-b930ec4ebbeb |  | note | VERIFYING DOCUMENTS: Material approval
date | d7c56057-a830-5666-ae5d-97c026ad739b |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 General fill
label | 8bd0d95d-de6d-557b-ae31-aa170b2bfb27 |  | note | REFERENCE: IFC Drawings
label | a2ffb24c-edc3-5382-83db-adedfff4ccb8 |  | note | – – – – – – – – – – – – – – – – –
label | 1619791e-09e6-5487-a4a3-e89a5c8c09b8 |  | note | ACCEPTANCE CRITERIA: Backfill behind the reinforced block shall be Vicroads Type B or better and:
label | caee2742-4dac-5dc7-9e9b-13d254fa6b77 |  | note | pH > 5.5
label | 0369705b-3524-5854-9dac-30ebe695c128 |  | note | CHLORIDES < 2000 mg/kg
label | 3f48facc-31ef-51cf-bfb2-7ad2cb2ea2c6 |  | note | SULPHATES < 1000 mg/kg
label | 9a98bb7b-fdc9-5d16-9297-da997a66f075 |  | note | Reference: Material approval in Teambinder
label | 784da485-ce68-55b9-9cac-cf107e270242 |  | note | – – – – – – – – – – – – – – – – –
label | 1918d7ee-963a-5ff3-92a6-b436b089037d |  | note | METHOD: Document Review
label | 7ad90829-ace8-591d-847e-ff9bc01f3f8e |  | note | – – – – – – – – – – – – – – – – –
label | f94a0441-5b95-5798-b7d9-1e402aa50895 |  | note | FREQUENCY: Each material specification
label | 6a2ed8ff-c4ad-5095-8575-e21352b65d93 |  | note | – – – – – – – – – – – – – – – – –
label | c5a24104-ab2b-501c-aadb-e0266ef2c4a7 |  | note | CATEGORY: HP
label | 11a077ff-d8c1-51c5-9084-d8cbd4fe0c4e |  | note | – – – – – – – – – – – – – – – – –
label | 3d762842-defc-5300-addf-f7d55e10149d |  | note | RESPONSIBILITY: Nominated Authority
label | b70eb4ec-9d67-50b4-8581-63a1fcfd10cd |  | note | – – – – – – – – – – – – – – – – –
label | a143be08-120f-538a-8312-ebee7a90059e |  | note | VERIFYING DOCUMENTS: Material approval
date | 9956eb0c-575e-566c-ae88-1416f3de1c6f |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Perforated Pipe-material
label | 34745e42-9122-53c7-aba6-3ba3dae16027 |  | note | REFERENCE: IFC Drawings
label | 055b6ec5-b85a-5b32-a021-2ec8a6cbcd68 |  | note | – – – – – – – – – – – – – – – – –
label | 85875f8f-e864-50c5-b385-e7cb2c4028f9 |  | note | ACCEPTANCE CRITERIA: Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
label | aa570f89-96a0-5e8d-96bc-481c17d9d795 |  | note | Reference: Teambinder MA number:
label | a7981b7b-e1fd-5f92-8286-b7a6c77c9e3a |  | note | – – – – – – – – – – – – – – – – –
label | 07b63b0f-11b5-5d6a-ab6a-31d871f0fe81 |  | note | METHOD: Document review, Measure
label | 84ae4048-9931-5224-92d4-f3dc050cafc3 |  | note | – – – – – – – – – – – – – – – – –
label | ac56a61e-1e8b-56a1-a39e-495388e16b50 |  | note | FREQUENCY: Each wall
label | 4412f8c2-1804-5c79-b964-f313d1f28a8f |  | note | – – – – – – – – – – – – – – – – –
label | f3c92df9-6dfd-5063-83b1-30eac54119f5 |  | note | CATEGORY: HP
label | 128f450f-203a-51cc-9b25-427473450dbe |  | note | – – – – – – – – – – – – – – – – –
label | 73b7424b-105f-5004-955d-724f8ba6532b |  | note | RESPONSIBILITY: Nominated Authority
label | f45aaa6e-707b-5946-a17d-2074f6bab417 |  | note | – – – – – – – – – – – – – – – – –
label | 9d9da0c2-59bc-5230-9b5d-3575ae1c8922 |  | note | VERIFYING DOCUMENTS: Material approval
date | 8a6d41c9-c2a8-552f-baf0-b160bf4dbfbd |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 RSS Panels
label | 32247d12-6be9-5589-9cd7-84c7aae0906c |  | note | REFERENCE: IFC drawings
label | be4bfe9b-84f7-5a8a-a42f-ced2dd881ac9 |  | note | – – – – – – – – – – – – – – – – –
label | 3d3d1746-65c6-5b46-804e-e27bf32b419a |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | 15f0200b-6a0e-571f-a552-80dae142aecf |  | note | i. Certificate of Compliance / Birth Certificate
label | e8f0da02-ec27-5cd8-a702-d75be59cbc16 |  | note | – 1. Concrete strength;
label | b56f33a3-8b71-55c5-819b-ffe2a9d1e291 |  | note | – 2.Date of manufacture;
label | 21f1bf95-5259-5cd4-8103-b29e59c67816 |  | note | – 3.Unique Identification number;
label | 40238426-c029-5689-8a7c-c429e543fe92 |  | note | – 4.Mass;
label | 79c9c8dc-ad1a-5800-a2ef-c680360a58c5 |  | note | – 5.Confirmation of number, type and capacity of lifting inserts;
label | a8977833-4791-502f-9a3b-40d7ea05c71e |  | note | – 6.Quality assurance sign-off.
label | f55f1066-9d4f-5cd4-929b-bcdcfdb60178 |  | note | ii. Compressive strength test results
label | 2c2c9c90-6f5a-514c-bb9f-365642de7bca |  | note | iii. Precast Lifting Design
label | bba556cf-3786-5bd5-b705-d85461031403 |  | note | iv. Pre-pour check sheet / ITP
label | 0689a20a-e77e-55f9-a41b-5e304d8483c1 |  | note | v. Post-pour check sheet / ITP
label | af4e7666-ee88-5604-9925-b222b91612e8 |  | note | vi. Covermeter check record
label | 551ed00c-228f-5d0f-9ac6-a56c70eb49e8 |  | note | vii. Record of dimensional measurements
label | cc596442-105a-5107-a40b-bc7b5e38b50a |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
text | 7e7a0789-2525-523c-a951-d1b2aecbab77 |  | textbox | Reference: Precast panels MDR Lot in TeamBinder:
label | 50a4513f-98de-5163-8848-106a86d43fbb |  | note | – – – – – – – – – – – – – – – – –
label | d9050164-57b0-53f3-87a6-5060e7cc2cd4 |  | note | METHOD: Document Review
label | bb13552e-f9a5-5e3d-b26d-433a2e085f03 |  | note | – – – – – – – – – – – – – – – – –
label | 176d88de-5335-567c-8408-dae1374d6788 |  | note | FREQUENCY: Once for each type of panels
label | a2a02159-5c33-54e0-be53-0d42106781f8 |  | note | – – – – – – – – – – – – – – – – –
label | 4fc2306f-7aa4-55c3-911d-87dcea54a83b |  | note | CATEGORY: IP
label | 2b794935-44fb-51c6-8fff-2d9535904f64 |  | note | – – – – – – – – – – – – – – – – –
label | 917b70dd-dbfd-526f-a24d-66d601dfbef5 |  | note | RESPONSIBILITY: PE
label | c1f25768-fe07-5207-91d7-0f03b3f5247e |  | note | – – – – – – – – – – – – – – – – –
label | 0c875e0c-c87d-5fc6-8978-240a71c0caf1 |  | note | VERIFYING DOCUMENTS: Precast panels Birth certificates and MDR Lot
date | 1fd39627-ef5c-5955-b8a1-8240a47782d8 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Foundation
label | a0116b19-efcf-5193-9f0b-674f6c6c9975 |  | note | REFERENCE: IFC Drawings
label | 0b8bbfc6-110f-57e9-aa97-51c6010d9241 |  | note | – – – – – – – – – – – – – – – – –
label | 90729cf3-3e42-54a2-92c1-69296a130c58 |  | note | ACCEPTANCE CRITERIA: The foundation material beneath the RSS fill shall be inspected on site by a qualified geotechnical Engineerto ensure that the soil conditions meet the assumed material properties:
label | c9924684-2e56-5aac-8f6d-785b8036f286 |  | note | • Description: Stiff Clay or better
label | a3d2c97e-63cc-5b5c-8998-da70d2015ece |  | note | • Unit Weight: 18 kN/m3
label | 327b9dbf-d987-50f1-99ad-2761b6ba3945 |  | note | • Effective friction angle: 28°
label | cadcbeb8-0849-5ead-8579-b8cff1010c40 |  | note | • Effective Cohession: 5 kPa
label | 0f9bf4c9-71fa-5bff-a88d-3152eb10eeb1 |  | note | • Undrained cohesion: 80 kPa
label | d3f838b6-3448-5ddd-99a8-56bf1c8bc011 |  | note | – – – – – – – – – – – – – – – – –
label | 6963087f-69dc-5414-a611-5be62b59b877 |  | note | METHOD: Test, Document Review, Visual
label | e5edea3c-6829-5319-afb3-990ad355647f |  | note | – – – – – – – – – – – – – – – – –
label | b787244a-fc10-5992-8fd8-615da0224c05 |  | note | FREQUENCY: Each retaining Wall
label | ec63b8b0-eef6-5141-a4c1-2b1651600bf0 |  | note | – – – – – – – – – – – – – – – – –
label | 9bb756bb-a71a-54e2-8e2e-abb4addfc25c |  | note | CATEGORY: HP*
label | dbcc25bb-09a0-52ec-9587-2cd37d354019 |  | note | – – – – – – – – – – – – – – – – –
label | 7f12c942-89e2-5285-a7dc-5b446ab0a6dd |  | note | RESPONSIBILITY: PE/Geotechnical Engineer
label | 0eb432e6-2d06-5809-973d-ef727e5a48ab |  | note | – – – – – – – – – – – – – – – – –
label | 09401ba6-f5b6-5e74-a9a1-07a8cee9d635 |  | note | VERIFYING DOCUMENTS: This ITP, Test results
date | c402da48-1e79-52c4-8ad4-e034e4bf0126 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Foundation
label | c2882d09-ab08-53ab-9cec-4d27b5a2ffe1 |  | note | REFERENCE: IFC Drawings
label | e80b350f-e6fe-525d-bc51-1df4e8af971d |  | note | • MRO-052-C-SME-DRG-32-MPK-CSW-2053
label | 889bde63-e6f1-5442-a6f7-bb81b1814e43 |  | note | – – – – – – – – – – – – – – – – –
label | fde2dcc0-0b73-5add-a2cd-2b36abce5dca |  | note | ACCEPTANCE CRITERIA: Where the foundation material does not meet the assumed material parameters, the existing ground shall be replaced with VR Type A fill Compacted in accordance with VR 204
label | 07cb888d-c6d5-5f0a-a924-32ee9cef53da |  | note | – Ground improvement works shall be keyed into surrounding material at minimum 200mm Bench width
label | 25432280-bf9a-5154-9f4a-91e2a2af9e6e |  | note | – Ground improvement works shall extend beyond either side of bridge approach to detail show in IFC drawing
label | 97f29d86-0967-52f9-96bb-60f06153ceef |  | note | – – – – – – – – – – – – – – – – –
label | c99a64c9-08fd-535a-b85c-797da0c5bbfc |  | note | METHOD: Visual
label | 685c0492-c679-59a6-a366-e4956e2296c3 |  | note | – – – – – – – – – – – – – – – – –
label | e2a1985a-3c98-5e55-900d-b3c8f7a196bf |  | note | FREQUENCY: Each retaining wall
label | c569b4b3-075a-5874-b83d-351b53fadc00 |  | note | – – – – – – – – – – – – – – – – –
label | 448205d6-3368-51e4-a989-1cadee3ef3f0 |  | note | CATEGORY: IP
label | a96a9a70-e490-554a-bd2d-cd41f82874ff |  | note | – – – – – – – – – – – – – – – – –
label | 6e74f9cb-c918-55cc-ac52-af1ad8bfd33e |  | note | RESPONSIBILITY: PE/Geotechnical Engineer
label | 61f422fe-2e0f-5baa-802e-e2507b0b678e |  | note | – – – – – – – – – – – – – – – – –
label | 695ee52a-e9a6-5c37-9d3f-69dd77791e70 |  | note | VERIFYING DOCUMENTS: This ITP
date | b6aa5dcc-a326-5932-9616-3b68c945de63 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Foundation
label | a640911d-32c8-558c-9a10-0b496616c3d3 |  | note | REFERENCE: VR 204.12, VR 204.11
label | ada6a7cb-a1cf-5ad0-af3e-1562470f82ec |  | note | – – – – – – – – – – – – – – – – –
label | 421593ff-bb51-56d6-a025-6ea89a603ced |  | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
label | f87f56a2-9e16-5dd6-b0bb-351f5496eeab |  | note | • No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
label | 980b81b4-cf88-5706-914a-54d98bc5b0b0 |  | note | – – – – – – – – – – – – – – – – –
label | 38a4faca-74c7-5c08-9913-c0bc694e6b00 |  | note | METHOD: Visual
label | 6a9e4e1e-7438-5a9b-b7be-0a58bc639c33 |  | note | – – – – – – – – – – – – – – – – –
label | 075201d1-cbe8-5e48-92c7-3dea21af538d |  | note | FREQUENCY: Each retaining Wall
label | 3ce740a0-9d6e-53c5-9c37-e48158166573 |  | note | – – – – – – – – – – – – – – – – –
label | 5bf2a16a-2326-5fbd-968a-68c178b876c1 |  | note | CATEGORY: HP
label | 1216795e-0818-5d92-94f0-d8e92507756e |  | note | – – – – – – – – – – – – – – – – –
label | 7985e3e2-6b80-5ea0-a8ba-b3c16e485301 |  | note | RESPONSIBILITY: PE/Nominated Authority
label | c6c8f491-f6a0-5748-a82b-8b584242ddcc |  | note | – – – – – – – – – – – – – – – – –
label | 1447e74f-604a-5325-b99c-903353bb33b6 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3355bb81-8a17-50e0-ad98-903a8eeb852d |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 Levelling Pad-Survey Set out
label | fa0a5fc6-09b3-5cbf-99c5-7a514c9ac2c5 |  | note | REFERENCE: IFC Drawings
label | 374a8b6e-b695-535e-9bc0-ac9ae1e1fc97 |  | note | • VR 682.20
label | aeecf6bc-72c0-5134-8d0c-a2f6ff585c98 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | 13560fd3-6c04-5b95-83b1-27cb13f2c73b |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | fe9f9ebb-3219-5f47-a7d8-c38aad92668c |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | c5206c13-6690-51c9-b57b-75b03ff8c144 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | b947a681-cd4d-59b0-8384-68a0ca404c20 |  | note | – – – – – – – – – – – – – – – – –
label | fe923ac7-d6bc-5344-82c7-d338178660cb |  | note | ACCEPTANCE CRITERIA: Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the tables in IFC Drawings and Vicroads Specification
label | 6bfedb58-3733-54e0-8069-c9c018f43486 |  | note | – – – – – – – – – – – – – – – – –
label | 06e1e88e-40f5-58cd-baef-ced02a9de161 |  | note | METHOD: Measure, Visual
label | f5cd6d09-1606-5883-8087-37595bda66b7 |  | note | – – – – – – – – – – – – – – – – –
label | 8438e244-b059-528b-b909-3f7567091c50 |  | note | FREQUENCY: Each retaining Wall
label | 5ea2c970-54c3-5422-acd1-ad505d7dcb16 |  | note | – – – – – – – – – – – – – – – – –
label | bd3b15de-dd87-520c-a01e-198623a2ec80 |  | note | CATEGORY: IP
label | ab817e67-2d53-5513-805e-39cde127abaf |  | note | – – – – – – – – – – – – – – – – –
label | f074bb4e-1e08-5ad1-a4af-c99587baed7b |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | 76aa1f8f-852a-52d7-8b50-794788f40763 |  | note | – – – – – – – – – – – – – – – – –
label | baa4d394-b0c5-5ecd-9064-fbfcad8c2df8 |  | note | VERIFYING DOCUMENTS: This ITP
date | a19b1cb9-4669-5d06-8775-2d3bd60cf0ff |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Form Levelling pad
label | 7e641105-3464-5a1c-827e-b9894205c7ef |  | note | REFERENCE: IFC Drawings
label | 6cabbf5f-bb96-5732-959c-8936ad0717cf |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | 97579fea-1412-566c-b684-35e371f865e3 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | a54055f3-47df-5470-ba51-212351af451d |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | 8dcabae1-db21-5434-8ba4-64d0c79f49b5 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | d712c7b3-3490-5ec7-9015-508339083ce8 |  | note | – – – – – – – – – – – – – – – – –
label | 04ae5e2a-c425-5d70-b5db-64f9fb71e469 |  | note | ACCEPTANCE CRITERIA: Form timber shutters to edge of levelling pad
label | 339841b0-c61a-5ff0-b731-dce35db3f202 |  | note | – Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
label | 55ac77f5-fe6f-5eab-a846-1217983c8eef |  | note | – The leveling course level shall NOT deviate from the specified level by mor than ±3mm.
label | f71a9181-33c1-5fb3-a5c9-c416921ad48e |  | note | – 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
label | 48493c3a-9ddc-5753-97d3-78eecd78c939 |  | note | – – – – – – – – – – – – – – – – –
label | 9ecf6c46-9040-53f7-908c-2fa028d8cfc3 |  | note | METHOD: Measure, Visual
label | 48f071cf-3a9c-5d33-be73-538d8a44bd82 |  | note | – – – – – – – – – – – – – – – – –
label | 0b59787a-82b1-5ebd-b80f-a28077cc9e65 |  | note | FREQUENCY: Each Lot
label | 4cda596e-30b0-57c5-9c2b-629cdd4208c8 |  | note | – – – – – – – – – – – – – – – – –
label | 9daf4cbf-659f-5af1-8a14-bc21e2517e5f |  | note | CATEGORY: IP
label | 5c541a1a-c1cc-57e6-a6ed-7cad5d7587d0 |  | note | – – – – – – – – – – – – – – – – –
label | 245af2d0-6c47-5a22-b821-dcd3608fcf14 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 5d9c6c54-7c1a-5b76-bfd4-8a71ed870153 |  | note | – – – – – – – – – – – – – – – – –
label | ee0a0ea0-d38b-5369-bedb-9eb0d23e2856 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2e8cbf88-4a69-5850-affd-f0ff8f7f01e2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Leveling Pad Concrete Pour
label | 4ad6e7f0-6939-5c8a-a97d-6a2f0e69c832 |  | note | REFERENCE: IFC Drawings
label | ddd4b9a0-7b4e-5675-98eb-d6648889da21 |  | note | – – – – – – – – – – – – – – – – –
label | 30052cf0-7fb5-593e-a76f-354f6d9328ef |  | note | ACCEPTANCE CRITERIA: Concrete to be placed in accordance with 610.
label | e9f69702-1518-517f-935f-18c3a7c89364 |  | note | Attach: Concrete Delivery Docket
label | 50242171-8918-5689-a34d-b9b4c91bae28 |  | note | – – – – – – – – – – – – – – – – –
label | 18858e5a-0c5b-58d0-9f5d-79d72cd99c8f |  | note | METHOD: Visual
label | 0db85466-c697-5498-a8dd-5172848a613e |  | note | – – – – – – – – – – – – – – – – –
label | c75f7239-ec12-5cde-bacb-ed1fe25148b0 |  | note | FREQUENCY: Each Lot
label | 4e0f21ab-ee4e-57df-879f-09ce0b9f9f47 |  | note | – – – – – – – – – – – – – – – – –
label | 807eb993-e420-5357-aaee-e8d956a46c09 |  | note | CATEGORY: IP
label | 1ebaf005-a5cd-5b25-9164-6b818b4aca2e |  | note | – – – – – – – – – – – – – – – – –
label | db108f6c-6da1-54f0-9968-485ea898db77 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c138ed25-d184-5e36-8ed0-207befefbd12 |  | note | – – – – – – – – – – – – – – – – –
label | 49078a7a-7594-5e47-8ab5-e9a9af83209d |  | note | VERIFYING DOCUMENTS: Concrete Pour record
date | 5a6bc732-33e4-5b38-a2dc-d7a99cc5402e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Leveling Pad Concrete Testing
label | 40835630-7066-508f-ae44-3657d2de9b5d |  | note | REFERENCE: IFC Drawings
label | 5f754176-89ec-57c0-89d2-8a51d9cd5dee |  | note | – – – – – – – – – – – – – – – – –
label | 7542ec66-472c-5d94-879d-964648cb4705 |  | note | ACCEPTANCE CRITERIA: Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
label | 09ab71a0-c7cf-5036-a148-8306153f5b07 |  | note | Attach: Concrete test report
label | 6bb78d82-069b-561e-92d6-a950d140d858 |  | note | – – – – – – – – – – – – – – – – –
label | 62841cdf-66d9-5f82-a718-d0441a35a57a |  | note | METHOD: Document Review
label | eff81849-1ed3-5636-bc0d-9d3d4b0b15e6 |  | note | – – – – – – – – – – – – – – – – –
label | 4b3b08b6-08c0-5c56-82ca-cc2c21614dde |  | note | FREQUENCY: Each Lot
label | 203b1545-faee-5ec2-bf05-497c826998cf |  | note | – – – – – – – – – – – – – – – – –
label | 7bf2a98c-d573-5a15-9caf-276fc978e521 |  | note | CATEGORY: IP
label | b9be637a-a672-5491-aa4a-448394ba9097 |  | note | – – – – – – – – – – – – – – – – –
label | e997eda9-485c-5b0a-aef2-7e21d4f18e30 |  | note | RESPONSIBILITY: PE
label | a0eed67c-9c56-5e9c-854f-5916f292793d |  | note | – – – – – – – – – – – – – – – – –
label | dc691f4b-7dcb-5734-b6bf-0a27a4e4f49d |  | note | VERIFYING DOCUMENTS: Attach Concrete Test Report
date | 5b1d8a29-e4cb-5d28-abfb-dd0a07fd8e51 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Levelling Pad-Post Pour Survey-Levelling Course
label | bc47cd65-126b-5bf8-af56-a6b2a3e606d1 |  | note | REFERENCE: IFC Drawings
label | 178e5558-9471-56a4-ad21-66d0fa3094b6 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | 0b7130e7-d3bb-5ead-8187-17360f9de90e |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | 80e93925-d849-5ca0-8852-dfbd29201ef9 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | bc154f4b-cbc1-57fc-862f-a1407b72ee98 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | 6be26861-25bd-5ff8-aa39-1254121aea02 |  | note | – – – – – – – – – – – – – – – – –
label | 55c2f01e-6aeb-5518-813a-8c300dbbb433 |  | note | ACCEPTANCE CRITERIA: Levelling course level shall not deviate from the specified level by more than ±3mm
label | dd89458a-8a86-584c-b1ff-c894f3182bd0 |  | note | – Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | 90f9e0e3-5c38-5971-837b-7c14f456f161 |  | note | – – – – – – – – – – – – – – – – –
label | b77e9577-7573-5f47-9ce8-25f738c2b1ea |  | note | METHOD: Measure, Visual
label | b24b6d71-9126-55fe-b392-5ac09947e8bb |  | note | – – – – – – – – – – – – – – – – –
label | fbb379d9-0f54-56e1-9179-c35e1c5dcc5f |  | note | FREQUENCY: Each retaining Wall
label | 626dc986-f16d-52a3-bd8a-71e664ad5dda |  | note | – – – – – – – – – – – – – – – – –
label | 24061947-9d5d-5705-b44f-c58fa5625f7b |  | note | CATEGORY: IP
label | 5fc0959c-0b6a-527f-a95d-05dbfd8579eb |  | note | – – – – – – – – – – – – – – – – –
label | 355fffa2-45b9-5b02-b424-2cadced7b4b7 |  | note | RESPONSIBILITY: PE/Surveyor
label | 35a85de8-2c23-558d-9d6e-604a1f5e872f |  | note | – – – – – – – – – – – – – – – – –
label | 4f4a9085-14aa-56ca-97bc-5522e46f44c0 |  | note | VERIFYING DOCUMENTS: Attach Survey Report
date | 54bdddde-d885-5400-8b82-4d16cb73f187 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Wall Panels Installation
label | d9430ba7-885f-539d-b270-e9847d08f538 |  | note | REFERENCE: 682.17
label | 29f834ab-cade-5d88-98c1-da5295932b1c |  | note | – – – – – – – – – – – – – – – – –
label | 55da4019-4819-5c7d-9189-e1874c00f279 |  | note | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
label | ed24a67c-b1b0-5d23-83dc-d6510dfee4fb |  | note | • The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | 6ef96ee9-dab7-58eb-80df-71d5658a0c1b |  | note | • Refer to checklist for each course of panels
label | 5a9ffbba-f84c-5391-8318-e93f0ad4340d |  | note | Attach: Lot map
label | e7782e90-bddc-50cc-867e-1ff3d29e791f |  | note | – – – – – – – – – – – – – – – – –
label | 7597ab4d-e3a7-5f03-98aa-434b0e4b4595 |  | note | METHOD: Visual, Measure
label | 84006bc2-141e-5f51-b37f-b42076a90d73 |  | note | – – – – – – – – – – – – – – – – –
label | cbdf47da-ba6e-5b4b-aa6c-e27cda7b59c9 |  | note | FREQUENCY: Each course of facing panel
label | 85b88bb7-cc04-5134-b699-5f3d006af61b |  | note | – – – – – – – – – – – – – – – – –
label | 963cc402-d37c-544a-b44d-01812c6bf8dc |  | note | CATEGORY: HP*
label | b78ce687-534b-5e65-84f5-574b7f19168a |  | note | – – – – – – – – – – – – – – – – –
label | 49d7644e-b6cf-5b48-a03e-a4e4a8ee266a |  | note | RESPONSIBILITY: PE/SE
label | a9a8c962-1293-5d25-b595-1ba9e9aff0e2 |  | note | – – – – – – – – – – – – – – – – –
label | d87fa261-895f-5401-8e2c-3f7b73b09147 |  | note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Pre-cast panel installation
date | 1244326f-fcd3-5ff3-b48f-65252f65a27a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Drainage-base of the Wall
label | a9f67426-017c-5cfe-991b-ca37f59149fa |  | note | REFERENCE: IFC Drawings
label | 676d306b-8c88-5c29-bbd0-bdca0292e3fe |  | note | • MRP-052-C-SME-DRG-32-MPK-CSW-2053
label | ffa1f531-7716-5121-b457-d0c079f3a6a2 |  | note | – – – – – – – – – – – – – – – – –
label | 7e37173e-6c59-5fd7-bd38-076a3087fa01 |  | note | ACCEPTANCE CRITERIA: To install 300mmx300mmGranular backfill in Geotextile BIDIM A64 around 100mm Dia. Perforted plastic pipewith 0.5%min fall to 50mm Dia weepholesin RSS panels.
label | 83761097-6d35-55e8-b4bf-34c543f1c923 |  | note | – Geotextile BIDIM A64
label | b22197c3-69d4-5415-a581-e1097f9165bb |  | note | – 300mmx300mmGranular backfill
label | 68a4fca3-4152-5edc-9f48-5b37768561b3 |  | note | – 100mm Dia. Perforted plastic pipe
label | 06a3ece2-31d4-52aa-85cd-21d3c16dd995 |  | note | – Perforated pipe to have 0.5% mnimum fall to 50mm weepholes in RSS panels
label | 7397ad7b-58aa-565e-98dc-5b0185e152ae |  | note | – – – – – – – – – – – – – – – – –
label | 9c916166-feb4-58e3-b2c2-1b9d1e11a2e9 |  | note | METHOD: Visual
label | f7588021-a980-5947-b4b3-60986a9b74b4 |  | note | – – – – – – – – – – – – – – – – –
label | b917d173-5bae-526b-8685-0662ec5b5183 |  | note | FREQUENCY: Each wall
label | d842f95e-ef12-5c76-82dd-da783d56c3b2 |  | note | – – – – – – – – – – – – – – – – –
label | e8171655-f4a4-5000-9c19-6182ed846395 |  | note | CATEGORY: IP
label | 60d2347d-610d-55c4-a671-4a8e459de077 |  | note | – – – – – – – – – – – – – – – – –
label | bdcb89a3-679b-5e0b-adf1-5b7a73925208 |  | note | RESPONSIBILITY: SE/PE
label | fb52f4ef-ad85-51ca-b89e-761be1bab63d |  | note | – – – – – – – – – – – – – – – – –
label | a2ed0717-c4d9-5b6b-857a-2b54e203b23d |  | note | VERIFYING DOCUMENTS: This Checklist
date | 809e944c-b42f-50ce-ae14-7f1b148e807c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Fill
label | 62a62d9d-a43e-5f0b-8eaf-f26a6a565b42 |  | note | REFERENCE: 682.16
label | cfcc6013-5450-557a-a800-4b92ae353a39 |  | note | – – – – – – – – – – – – – – – – –
label | 7873cbd7-4fb1-584e-bc36-1469fb2f81a5 |  | note | ACCEPTANCE CRITERIA: The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance.
label | b6f21b1b-c19b-57de-99eb-614bb37f3e4e |  | note | • No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted.
label | da899c96-65cb-52ae-bd0e-662ec6ef66d3 |  | note | • If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
label | a06f36a1-4e57-5511-a4bf-4f59189f7171 |  | note | • Refer to checklist for each fill layer
label | 7770c051-0934-5439-9bb8-26c8f5499b91 |  | note | Attach: Lot map
label | 01f0f818-1c24-5d7f-af94-ec373d5883a8 |  | note | – – – – – – – – – – – – – – – – –
label | 4d583ce4-ad4f-5081-a55c-a2486f9c2cff |  | note | METHOD: Visual, Test, Measure
label | 19a1c731-7e2e-5c7c-81fa-a4a1446a158e |  | note | – – – – – – – – – – – – – – – – –
label | 81e06d14-1fba-50a6-a552-e8750dc97ed3 |  | note | FREQUENCY: Each layer of fill
label | 297279d1-57ef-5521-b083-42139c61669c |  | note | – – – – – – – – – – – – – – – – –
label | 1cb477cd-eaf4-54cc-8bd5-2f702cb84048 |  | note | CATEGORY: HP*
label | 09047e11-9ee6-5d3a-bcfe-36cb451a38d4 |  | note | – – – – – – – – – – – – – – – – –
label | 4008c3e9-7e09-51fd-ba49-6d13196efda5 |  | note | RESPONSIBILITY: PE/SE
label | 7f8805b4-5c53-5deb-89a3-4d0a48c0c470 |  | note | – – – – – – – – – – – – – – – – –
label | 27819e84-2558-5d82-88a8-0af7a0aee03f |  | note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Fill installation
date | 34c523ee-1d2e-55f6-bd56-6ae3c1bbb4ea |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey
label | f83ed84f-2e6a-531c-811f-b58c7563695f |  | note | REFERENCE: MRPA Quality Management Plan
label | 6208878e-cb65-58ff-a435-f36915a0f7f8 |  | note | – – – – – – – – – – – – – – – – –
label | c2071648-ce3e-51ca-a778-7f29bebe27d7 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
label | 1d26bd10-ed46-5430-9343-f01ba0b6b871 |  | note | Attach: Survey As-built / Survey Report
label | e24d4d9f-a889-5d65-87f8-d5be6da63b5a |  | note | – – – – – – – – – – – – – – – – –
label | b38d854b-fb04-5726-bef6-3e29b153773a |  | note | METHOD: Document Review
label | 6fd74c38-bcc1-58a1-9829-5a8b1b69f46e |  | note | – – – – – – – – – – – – – – – – –
label | dea735bb-d47f-54b5-be90-758c58d1bd78 |  | note | FREQUENCY: Each element
label | 7497ce90-9022-53a7-82bd-cbd81a798ac7 |  | note | – – – – – – – – – – – – – – – – –
label | 6482d1e5-37c4-52b0-a586-b964d538d652 |  | note | CATEGORY: IP
label | 206fc87c-fae2-5769-8eba-ba8f95b57359 |  | note | – – – – – – – – – – – – – – – – –
label | 29405fa9-4ebb-5f18-b05d-12f9e34e6b18 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | f14d97a9-1919-59cc-b931-7b7ecc3185c5 |  | note | – – – – – – – – – – – – – – – – –
label | 8755cc80-2527-5762-877c-76d7530135b9 |  | note | VERIFYING DOCUMENTS: Survey Report
date | 67d840cf-0a4f-5037-b7b7-6404a7de116d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Wall Post construction monitoring
label | a65625bf-aee8-5f6c-a0e8-16d5e7e37325 |  | note | REFERENCE: VR 682.20, VR 682.21
label | 7605cae5-6cda-5f7f-87fc-7fab84685eb1 |  | note | – – – – – – – – – – – – – – – – –
label | 75ababa4-0ab2-595c-ab04-62800855845c |  | note | ACCEPTANCE CRITERIA: The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
label | cb253744-4a57-5836-9c84-83d755130676 |  | note | (a) plan position shown on the drawings, at base of wall shall not exceed ⌖15 mm;
label | 704a83af-c296-5167-8062-da057ef3b838 |  | note | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
label | c25e087f-2af1-5ce3-853e-5b738c371d6f |  | note | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
label | 2096018b-5787-5109-a0fd-ad6c7b28c623 |  | note | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
label | cd5ec6ec-2bd8-5f1f-b746-cf291d3f8d6f |  | note | (e) the wall level shall not deviate from the specified level by more than 20 mm;
label | 4c935e00-e4cc-503d-b65d-8e280e55fb59 |  | note | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
label | d0a1af76-3611-5e5a-9d72-805fd9450879 |  | note | The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey.
label | e5701a2e-f0b2-53f5-b38d-72c2dda9afb1 |  | note | – – – – – – – – – – – – – – – – –
label | cdc88886-3d45-58d3-a007-0403ec48085b |  | note | METHOD: Measure, Survey
label | 131c124c-495f-5070-8986-712a6940380a |  | note | – – – – – – – – – – – – – – – – –
label | 644dc79a-c2d7-5ac5-84d7-79a0665127b8 |  | note | FREQUENCY: Each wall
label | 378ba654-eac0-592f-a94d-427915658754 |  | note | – – – – – – – – – – – – – – – – –
label | bb280a9b-d99f-59bc-8ac1-299a25015455 |  | note | CATEGORY: IP
date | 876e4f1f-b69f-540a-8f53-4f2f2c8ac740 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | d0d71591-0d61-57b5-8ad1-536ea2dadc8c |  | note | REFERENCE: MRPA Quality Management Plan
label | 47386c30-b6c4-56c2-be26-6e9285c64137 |  | note | – – – – – – – – – – – – – – – – –
label | 811205d1-d5e7-5956-bfb8-98186ab259d0 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 1544313f-2e81-55c8-86d5-c43a9c69e0db |  | note | – – – – – – – – – – – – – – – – –
label | 1a33c899-2f58-5f5f-b30f-edaa774cbe8c |  | note | METHOD: Document Review
label | 3aac46f6-e882-5ca4-8171-06f61272cb63 |  | note | – – – – – – – – – – – – – – – – –
label | 8482e1d0-934e-53c5-b891-77cbd9c38e64 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | bd4b41cc-9927-51ea-bc53-f0a5ae629755 |  | note | – – – – – – – – – – – – – – – – –
label | bcc35338-726a-5bd0-8aa1-ddffdb0d0d43 |  | note | CATEGORY: HP*
label | c3526f81-803a-50ec-a41b-c47c8c8ad9c2 |  | note | – – – – – – – – – – – – – – – – –
label | 99aefe98-0b66-555e-87f1-d1318c0c8bef |  | note | RESPONSIBILITY: SE/PE/SPE
label | aafa504a-eb8c-5d3c-90b6-069bde4e1c72 |  | note | – – – – – – – – – – – – – – – – –
label | 7820860c-cafa-5691-99d5-73247d373abf |  | note | VERIFYING DOCUMENTS: This ITP
date | 9ee3d3d5-9fdb-5e2d-b3d1-54160afe7997 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 6b7e3044-01da-5c12-a8c8-1d03dd83d8d0 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 6bffcc49-da08-5266-a16c-bf686edaf980 |  | textbox | Name:
text | ee7ac50a-fa59-52bb-8199-cb595d7936b6 |  | textbox | Position:
date | 90ff8abf-e3d5-5df0-88a2-b4e3489783e4 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-033-STR-Grout Pedestals & Bearings | itp |  |  |  | Yes | ITP-033-STR-Grout Pedestals & Bearings Rev 0 | d0373c2e-faa9-453f-b57c-058673c5d718
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 60a3a4e8-3beb-5718-b371-56264f827a0b |  | note | Document Title: ITP-STR-Grout Pedestals & Bearings
label | d1168e38-c2e7-5f3a-8fac-c333e2751345 |  | note | ITP Description: Grout Pedestals & Bearings
label | 90a315a4-f44c-5782-a0e6-60d7b774bede |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | fafcfd14-ea4c-500d-8c98-2d32347c28b5 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 22152999-5668-5155-80ec-876ddec9337e |  | note | Revision Number: 0
label | 2955195d-8190-54dd-8cca-6a053e2df598 |  | note | Revision Date: 14/04/2020
label | 97a6216c-3776-521d-b7a1-bac2021cd415 |  | note | ITP created by: Mike Freeman
label | 526c565d-0f9e-5f6b-8013-badc02aa04f3 |  | note | ITP approved for use by: Victor Mira
label | 439412bb-3375-5fb6-8edf-db9bffbd6671 |  | note | 1.1 Non Dependent
label | 2e687fe8-9045-59fb-a978-c2e201bb6d39 |  | note | Reference: VicRoads Section 610 November 2018
label | 4d3ba989-5bd7-5f10-b3f4-a0244d33fced |  | note | 1.2 Non Dependent
label | 2470da3b-cbe4-5d14-b0d3-b644f96ca697 |  | note | Reference: VicRoads Section 610 March 2019
label | 6e3c39d7-afd1-5de7-868f-273238f2617d |  | note | 1.3 Non Dependent
label | ed1977dc-2075-5e72-8eaa-2859c103d838 |  | note | Reference: VicRoads Section 610 June 2019
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Product Selection
label | 8af14082-b525-5f70-abc9-069d565d8164 |  | note | REFERENCE: IFC Drawings 610.28 610.33
label | 6004356d-2d8b-5f56-bc11-6de99949180a |  | note | – – – – – – – – – – – – – – – – –
label | dcd18a39-6f6c-58c8-9374-ea0c8ab5b9b9 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 07abeef9-5936-5812-858b-4fb01a89b9df |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
label | 1cdb140a-9d28-53ea-9848-0abe88a80b9c |  | note | ii. have the required strength at 28 days as noted on the IFC drawings.
label | 65369d41-255c-559c-b1c3-a6f365edde69 |  | note | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
label | b0b751ab-9fe6-575f-a5c3-2bba95fbc612 |  | note | Note: Pedestals 200mm or greater shall be constructed from concrete - use ITP-STR-Structural Concrete instead
text | 48bb5756-e9a2-5329-917e-792e8a3aab1b |  | textbox | Enter: Teambinder Material Approval number
label | 2a5bf788-b729-5510-8b63-df6f461192e1 |  | note | – – – – – – – – – – – – – – – – –
label | a54fdd5b-07e3-549e-965d-b19fcdeae5f5 |  | note | METHOD: Document Review
label | ec201b45-453c-5e75-8a88-4d3b65c2bb89 |  | note | – – – – – – – – – – – – – – – – –
label | 31df7d49-e534-5fcb-93ff-c4ea8715cc9d |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 7f566be2-c785-5b39-92ce-40996d03dcb2 |  | note | – – – – – – – – – – – – – – – – –
label | da3161eb-e9e4-5cd6-a1ba-307be4c724c0 |  | note | CATEGORY: IP
label | 78a2478b-c08a-5e12-a65a-4af74f3aa1a4 |  | note | – – – – – – – – – – – – – – – – –
label | d3b4a431-b022-5415-ab46-2210f5c0bc26 |  | note | RESPONSIBILITY: Nominated Authority
label | 593c610d-bcb7-5687-8600-bb5a265957f1 |  | note | – – – – – – – – – – – – – – – – –
label | e909fd7d-9fa8-5d61-ae81-e6a7624a7b83 |  | note | VERIFYING DOCUMENTS: This ITP
date | bbf5c02b-a019-572d-a067-5bb1af0aeb3e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Curing Compound
label | 3b6592b3-6efe-5009-bf6f-8f61c5e5d55a |  | note | REFERENCE: 610.23 (d)
label | 338adf53-3e21-5419-b3fd-f8197c2da158 |  | note | – – – – – – – – – – – – – – – – –
label | 91ab0ee2-abbb-573b-84f7-ae99702a36ee |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 7186e716-1199-588f-a1dc-f87ecaa4ca1d |  | note | Note: This may be the same product used for the concrete curing
text | 528d281e-92e4-57df-89e0-0a7959d81243 |  | textbox | Enter: Teambinder Material Approval number
label | 88e61c4d-525c-5098-a3cc-1fd27aa0d593 |  | note | – – – – – – – – – – – – – – – – –
label | 2415156d-4930-52c0-bf6c-f41ff825db26 |  | note | METHOD: Document Review
label | 5fef31d3-bc4b-5e5b-8aaa-e045b7a95632 |  | note | – – – – – – – – – – – – – – – – –
label | fcf8c8e3-8c25-515e-aeee-3d3c64da44ef |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 4cf1a894-a5dc-5eaf-aee1-b8e9250ffd65 |  | note | – – – – – – – – – – – – – – – – –
label | cd3a0525-399f-574a-beed-0239e18018d1 |  | note | CATEGORY: IP
label | bc3a835e-32e3-5249-a516-3b59c633c573 |  | note | – – – – – – – – – – – – – – – – –
label | 63722781-833c-5c1e-b712-13fa9bdb7f7a |  | note | RESPONSIBILITY: Nominated Authority
label | ee61bcae-850c-5088-8842-745870285757 |  | note | – – – – – – – – – – – – – – – – –
label | d9c388ac-4ef9-5992-a7c6-7f593bb04fe5 |  | note | VERIFYING DOCUMENTS: This ITP
date | c245cc8f-5a13-56df-ae88-153733e78ba7 |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Curing Methodology (for Concrete, Grout and Mortar)
label | 4d3cb866-f017-5da9-ae57-264298a06db8 |  | note | REFERENCE: 610.23 (a)
label | c87f6e56-bf91-53a3-8561-276fb7f3be7b |  | note | – – – – – – – – – – – – – – – – –
label | e3874b67-7419-5cbd-8806-4031f1154e1d |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | 81e85b09-7e5c-578d-8b0b-2188849f834c |  | note | Note: This may be the same document used for the concrete curing.
text | 233923bb-6be3-560a-a8d1-496c59f220b0 |  | textbox | Enter: Teambinder Correspondence Approval number
label | b548907a-575b-5dd0-9afc-13459b70c529 |  | note | – – – – – – – – – – – – – – – – –
label | 270f76d4-ad9d-5fb9-8e76-6269f092114a |  | note | METHOD: Document Review
label | f7b4dd78-036b-5a8c-b4ce-e1f9c63ba788 |  | note | – – – – – – – – – – – – – – – – –
label | 08fc678d-b012-5cae-8b27-1e7247e485b6 |  | note | FREQUENCY: Once, 4 weeks prior to placement of product
label | dfef7a16-7ef8-5466-a8b3-cf2eba653aae |  | note | – – – – – – – – – – – – – – – – –
label | 5c344477-9f9c-5cf0-a7e6-275261acec64 |  | note | CATEGORY: HP
label | d5f8e221-88b1-58aa-a308-0ee54e91491b |  | note | – – – – – – – – – – – – – – – – –
label | 6bb9ed21-92b9-5989-bc05-c0a4653de4c1 |  | note | RESPONSIBILITY: Nominated Authority
label | de1d971f-9db6-5439-a695-6089dbfc9aae |  | note | – – – – – – – – – – – – – – – – –
label | 4abc0eda-9b62-5b2a-af70-3aff1dc21d79 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 3fc89285-50f5-54d6-adfb-b256c581f3b2 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | a46b9502-6417-562e-9ac6-08b617ba76d6 |  | note | REFERENCE: MRPA Quality Management Plan
label | 9cc20bcd-d032-5f3d-a26b-69cd72fb78f6 |  | note | – – – – – – – – – – – – – – – – –
label | 8abc2fff-6f0a-56e3-80a1-373ae005a606 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 16a38ffa-473b-5704-a12a-85e6d78db485 |  | note | – – – – – – – – – – – – – – – – –
label | 11c8299a-2648-549a-b1bd-ce326bb06e85 |  | note | METHOD: Document Review
label | 18957363-436c-5d76-b9f8-6865fc1ffc67 |  | note | – – – – – – – – – – – – – – – – –
label | a72591f5-aaa7-5146-9d6f-ad6d2b6f17fb |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | b88d318d-9ce9-59d8-9d81-c47c7251ace2 |  | note | – – – – – – – – – – – – – – – – –
label | b8818fed-10c6-5f09-a7d2-74d045f476d4 |  | note | CATEGORY: HP*
label | f6f6cf4a-168e-511b-b08f-aed805003584 |  | note | – – – – – – – – – – – – – – – – –
label | 84ee339a-25a7-565d-a023-2297dddf0112 |  | note | RESPONSIBILITY: All
label | a1b16513-2cc8-590e-b2d3-e1656b0628ca |  | note | – – – – – – – – – – – – – – – – –
label | 2eecb76e-8f74-5be9-a033-547f17292afb |  | note | VERIFYING DOCUMENTS: This ITP
date | f05a9f26-d3f6-5ab3-9e32-05ce928b290a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | f3a1dccf-4f49-5049-9061-955dd902c0f3 |  | note | REFERENCE: IFC Drawings
label | 2fbba19d-d917-55ea-a0b7-ed53b80cf43c |  | note | 610.46 (a), Table 610.462 (Nov 2018)
label | 28d3fdde-4d70-5556-8c3e-9428ca0e5f92 |  | note | 610.47 (a) Table 610.472 (March/June 2019)
label | 27f28553-2334-5bc4-9ad9-522b5cce456c |  | note | – – – – – – – – – – – – – – – – –
label | 1de93eb7-e4c0-5fd3-bdba-58fdc8a137ba |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
label | 9982f677-59bd-53d2-bad4-0a429801230f |  | note | Note: Different revisions of 610 have different clause numbers
label | e5d40ff6-9a89-5180-835a-5d82b28313b0 |  | note | – – – – – – – – – – – – – – – – –
label | d166c60a-a110-5b03-bba5-6ede5d4c662c |  | note | METHOD: Measure, Visual
label | d0204710-7615-5f5b-8aae-a908a0438b50 |  | note | – – – – – – – – – – – – – – – – –
label | c209b9c8-7d83-58a3-b35b-06df7ffc1aa2 |  | note | FREQUENCY: Each element
label | 616a974a-7295-5e22-808a-081fb54df511 |  | note | – – – – – – – – – – – – – – – – –
label | e79edd80-d6b7-586f-8a34-27c5b9e70f32 |  | note | CATEGORY: IP
label | 69eed20e-85da-5012-a834-a9a6a80bcef8 |  | note | – – – – – – – – – – – – – – – – –
label | 8cbc50ad-4556-5e5a-b525-207d1c98e3e7 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 50442971-f077-5328-a8f7-15d81e535a61 |  | note | – – – – – – – – – – – – – – – – –
label | 96c36ee8-ceff-561c-84e7-7d2de47ea4d8 |  | note | VERIFYING DOCUMENTS: This ITP
date | a040fdf4-1422-52a6-8ce0-2c3de8659fc8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Construction Joint
label | ef08e578-0632-5032-ade9-569a5f56e3d9 |  | note | REFERENCE: IFC Drawings 610.20
label | a1362b2e-2ce2-507f-b4d0-1dddc4c00dd5 |  | note | – – – – – – – – – – – – – – – – –
label | 57678532-ea3b-571b-afff-901a741d1e5e |  | note | ACCEPTANCE CRITERIA: Existing construction joint rebate is roughened / scabbled and set to 20mm minimum below top of the crosshead / abutment.
label | ceefce32-94c6-5583-bbff-927a1415f85a |  | note | • Concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
label | 45d613a8-507a-5655-bb95-819f005cff06 |  | note | – – – – – – – – – – – – – – – – –
label | a8e861c8-291d-5e7c-9915-2de99f0e918a |  | note | METHOD: Measure, Visual
label | 9c400e0d-14f1-55a0-bccf-6757e9148276 |  | note | – – – – – – – – – – – – – – – – –
label | 45a4d496-b2a9-59f3-a6e7-9020563c3730 |  | note | FREQUENCY: Each element
label | 4d1c8dcd-36b1-5574-8a92-02da8b0b79a2 |  | note | – – – – – – – – – – – – – – – – –
label | f35dd333-207f-5a23-9315-4ff49eacf01d |  | note | CATEGORY: IP
label | b39bd908-a46c-5cb1-8f1d-fca27d2e207c |  | note | – – – – – – – – – – – – – – – – –
label | c6ebc091-0fd3-5912-9d53-a99261e8f8b0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e6f824a3-ea98-5e92-b074-80ca2e5e0219 |  | note | – – – – – – – – – – – – – – – – –
label | bde9b8b4-e898-5bfe-9280-abeb442c9639 |  | note | VERIFYING DOCUMENTS: This ITP
date | 27311040-529c-5119-a8a2-6aa2d501a209 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Formwork Construction & Placement
label | ece8280d-0823-573f-9771-e67abede504b |  | note | REFERENCE: IFC Drawings
label | dccd40d2-9555-55c8-9de9-4dafc8619b08 |  | note | – – – – – – – – – – – – – – – – –
label | f4c3c1fa-1e64-5be3-8c31-9178e43d7ac5 |  | note | ACCEPTANCE CRITERIA: Dimensions in plan as per drawings (typically +50mm all around).
label | 7805b2a3-44fc-5ec3-899a-b16111ee9862 |  | note | • Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
label | 18597e88-929c-5cd5-bb0b-b9a99cad1caa |  | note | • Any cast in componentry (ferrules, conduit etc.) secure.
label | 4c7b5a71-894c-5d40-802f-664abe8822b3 |  | note | – – – – – – – – – – – – – – – – –
label | de2f1649-8845-5cf5-a2f9-c7d04e70e56f |  | note | METHOD: Measure, Visual
label | 0a183a37-8f38-50dc-bf29-7b69e5f4f8f0 |  | note | – – – – – – – – – – – – – – – – –
label | 0569928d-109a-5fd2-9798-47f4ea57800e |  | note | FREQUENCY: Each element
label | d678338d-1ef3-5a44-993e-933b6498fde1 |  | note | – – – – – – – – – – – – – – – – –
label | e2f9c196-4bbe-5c60-b5de-ac11dd7dd7de |  | note | CATEGORY: IP
label | 0194e909-46fd-5579-8627-48cf892d20d7 |  | note | – – – – – – – – – – – – – – – – –
label | 6aede03f-f1fd-501e-bf87-30e87e60e197 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3512fe93-1094-5c3d-96cf-aff104b5797f |  | note | – – – – – – – – – – – – – – – – –
label | 41fd0194-ce24-5e08-83be-e96dd0221e84 |  | note | VERIFYING DOCUMENTS: This ITP
date | ccaf94f0-9f1d-53cc-ad91-09211da46c5e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pre-pour Inspection
label | 2943e191-dae6-58be-b1c7-72a1d51e4099 |  | note | REFERENCE: IFC Drawings 610.20
label | 93911069-4a5e-5ffa-a2d4-9b75309e95f9 |  | note | – – – – – – – – – – – – – – – – –
label | d4f9c232-4146-5d62-bdbb-31c2b05b9194 |  | note | ACCEPTANCE CRITERIA: Formwork location and RLs comply.
label | 307dd6d3-62b4-5546-a9ab-f89fefb83b65 |  | note | • Any reinforcement has the required cover.
label | 2f1dac6d-a255-5de7-9fd4-fc4ddb71c5cb |  | note | • Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
label | f526c809-0aa3-5b0a-a207-2b8d3e84dc2e |  | note | – – – – – – – – – – – – – – – – –
label | 78bd615c-a9bd-5074-a66a-fab105b74ac8 |  | note | METHOD: Measure, Visual
label | 996ed0f1-b078-5d82-874a-cb15133d6b98 |  | note | – – – – – – – – – – – – – – – – –
label | 3db24b42-af13-510f-b090-0ed7f21b914a |  | note | FREQUENCY: Each element
label | 26457328-27a8-5f51-954f-d84ed014e34d |  | note | – – – – – – – – – – – – – – – – –
label | 9d8f6174-01a2-5d5a-ac26-41d7f061335b |  | note | CATEGORY: IP
label | 43e5846d-c624-5761-b953-d473b52e72ef |  | note | – – – – – – – – – – – – – – – – –
label | 58ef245c-90a8-5be0-9ae6-294c4c5db2f8 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c8c3759c-99e7-5e0a-9d81-e01a61bcb441 |  | note | – – – – – – – – – – – – – – – – –
label | 4085c8a9-2558-533e-ae76-dd57e33fe731 |  | note | VERIFYING DOCUMENTS: This ITP
date | 66552718-a67b-5434-80bf-6a39c2dbc57a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Weather Conditions
label | 9f420ec8-9a0c-5031-a979-514890f75710 |  | note | REFERENCE: 610.17, 610.17 (a) & (e), Table 610.171
label | 995de2eb-bdc3-556f-82dc-8c9a4b056c66 |  | note | – – – – – – – – – – – – – – – – –
label | dcc16b88-8a59-58e1-86ec-2a1eff45a7f9 |  | note | ACCEPTANCE CRITERIA: All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | e8520d58-a89a-5315-a896-b1c9fb8d7bca |  | note | • The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 19ef1bda-d86f-5c08-ae44-87bc2fa41bb6 |  | note | Record: Required information on the Grout Pour Record.
label | 71b2461b-38c1-5e73-a61b-59ffa98806da |  | note | – – – – – – – – – – – – – – – – –
label | 7d9dcba0-8812-5413-9b48-911019357d28 |  | note | METHOD: Measure, Visual
label | 0621ad08-317a-5795-968a-91e80732e9b2 |  | note | – – – – – – – – – – – – – – – – –
label | 5d750814-546d-5c34-a0f4-6a821ef9ae4d |  | note | FREQUENCY: Each element
label | 2f8a9453-9e6b-508c-841e-ea8139035c41 |  | note | – – – – – – – – – – – – – – – – –
label | ae94bf5d-8a3b-5ccb-9afa-3050155a2f6f |  | note | CATEGORY: IP
label | 53837178-32cf-5c4e-a521-f119678cb610 |  | note | – – – – – – – – – – – – – – – – –
label | be532401-6bdc-5164-a545-f4b6fb5dbce9 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 7ab0f61d-46bd-5c4f-804a-b4eaf9bd2a6a |  | note | – – – – – – – – – – – – – – – – –
label | 050361c0-32f6-5833-a637-ea42d7899f00 |  | note | VERIFYING DOCUMENTS: This ITP
date | cd6fbf60-327d-5bc6-9b3f-6f07b1c0fefb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Mixing Product
label | 30d87baa-4a66-5e8b-9b2c-b8d6ca185f83 |  | note | REFERENCE: Product TDS 610.28
label | 639cf6a8-5f36-58b6-b6ff-905f2bca7ca1 |  | note | – – – – – – – – – – – – – – – – –
label | ce9783d8-b7da-5a4d-b5b8-db16c24d25cf |  | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | d97917a3-1c41-5a2b-b55b-b37907f9e25c |  | note | • Only whole bags to be mixed with potable water.
label | a036c255-a672-5c35-91dc-c7cfd5239ac3 |  | note | • Volume of water matches the required amount for flowable consistency and accurately measured.
label | 7a92148f-776c-58c0-a514-502d60d2e2d6 |  | note | • Product poured into the mixer slowly.
label | 4cf06414-117a-5101-8f14-2facecf89e64 |  | note | • Mixing time as per TDS so that a smooth, even consistency is obtained.
text | 4079fd16-54c3-5e42-82e1-6226a63d2615 |  | textbox | Enter: Required information on the Grout Pour Record.
label | 393007c6-34f9-5798-8db6-eff10b7b53a0 |  | note | – – – – – – – – – – – – – – – – –
label | 2bdfd8fe-5076-5bed-a8b1-7877c5275ca6 |  | note | METHOD: Measure, Visual
label | d9b3c1b4-74f1-534b-b5e3-c6bc6096b886 |  | note | – – – – – – – – – – – – – – – – –
label | 2e918aff-d0b5-5514-91a6-9972f7833fff |  | note | FREQUENCY: Each batch
label | ab97406b-2d4a-5506-827e-029fe265c451 |  | note | – – – – – – – – – – – – – – – – –
label | db1350ca-4c9d-5bde-9a83-db7aae96314b |  | note | CATEGORY: IP
label | 9d510b93-73b9-500e-87ef-8795033c9de8 |  | note | – – – – – – – – – – – – – – – – –
label | 12deb436-60db-5e47-a979-d4669635e30c |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3fefd126-57a8-54ae-a21c-1e8aa4449f19 |  | note | – – – – – – – – – – – – – – – – –
label | 461207cf-78dc-545d-90fc-38142d51c439 |  | note | VERIFYING DOCUMENTS: This ITP
date | d39bff96-334a-5c31-99b1-f017268750b5 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities (Continued)
checkpoint-status |  |  | checkpoint | 5.5 Product Testing - Compressive Strength Cubes
label | 94c74fff-eb13-53e3-a3ae-8f0efc3a62c5 |  | note | REFERENCE: 610.28, 610.33
label | c8350169-c21f-5f24-a15b-dd718450531c |  | note | – – – – – – – – – – – – – – – – –
label | ae3ca094-b8c0-5923-8e79-dcb935f70929 |  | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | d475c6bb-be3f-529b-bfd9-642c23c441d1 |  | note | • Testing is be in accordance with the following frequencies:
label | 20785c39-5e28-505e-acef-7a492bbed24c |  | note | • First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 716fe519-3b02-58d5-bb51-a76c5e042e84 |  | note | • Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
text | e8f49cdb-5a0d-52f2-9a83-87dab094ecad |  | textbox | Enter: Required information on the Grout Pour Record.
label | 4b22c361-5a80-5f8a-8ceb-21ed3e1487e3 |  | note | – – – – – – – – – – – – – – – – –
label | 9f2bbe0c-f1c2-5254-a1aa-ae77c1270c99 |  | note | METHOD: Test
label | 608db77c-af8e-5b8f-8cb3-3562f5c3c051 |  | note | – – – – – – – – – – – – – – – – –
label | 1168c84f-9d56-5d00-b95f-848fbd2862dd |  | note | FREQUENCY: Each element
label | d09cb06a-b7d4-5318-bc9a-391a2b391ea3 |  | note | – – – – – – – – – – – – – – – – –
label | bdbc0bc3-b504-534d-b70c-1b48e43a549c |  | note | CATEGORY: IP
label | 9d1d9990-77e6-578f-8aa9-d7aae39bee5f |  | note | – – – – – – – – – – – – – – – – –
label | 04653a17-5dc4-5cd6-95e8-b20326fd1987 |  | note | RESPONSIBILITY: Tester, SE/PE/SPE
label | ef802324-87e0-5038-838c-cf8b20e8af40 |  | note | – – – – – – – – – – – – – – – – –
label | a94dd1a0-eb61-5115-b26e-08579215ea33 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1cb9111b-4629-5ecb-b676-4dcf72ce919d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Placement & Compaction
label | cff3d42a-71b5-54d8-9871-913271d0b93c |  | note | REFERENCE: Product TDS
label | d0037862-25cb-5216-ba31-dc57332915c7 |  | note | – – – – – – – – – – – – – – – – –
label | ebf39aa0-6b09-5d2d-a2e9-a87c34d52d57 |  | note | ACCEPTANCE CRITERIA: All batches are traceable.
label | c7cd77fc-2a44-5af0-a1c7-dc5095661e10 |  | note | • Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | 8dbb0b89-b330-5880-8a9f-54faded9f32e |  | note | • Product should flow to all areas and self consolidate.
label | e53f90e5-39f8-5a5d-a19f-4b3bfa2eca67 |  | note | • Product that stiffens or is showing signs of stiffening shall not be used.
text | 876fecba-9f71-5669-8837-7ab64d1f5591 |  | textbox | Enter: Required information on the Grout Pour Record
label | 3b4b1931-ada5-5f42-91df-face82777f10 |  | note | – – – – – – – – – – – – – – – – –
label | 46b85755-0f79-527e-a578-2bc8fc1e0171 |  | note | METHOD: Visual
label | 9a6ab97c-cc0f-59cb-8e68-d70858333539 |  | note | – – – – – – – – – – – – – – – – –
label | 11a80116-81a9-5681-9ac5-f774ae05c47e |  | note | FREQUENCY: Each element
label | ec2e9329-796e-5057-b899-c8750899880a |  | note | – – – – – – – – – – – – – – – – –
label | 9372a69e-3dff-532a-8080-c0806db4b1df |  | note | CATEGORY: IP
label | be1e70e7-87b7-5f7b-ac03-c50c7dc7e0da |  | note | – – – – – – – – – – – – – – – – –
label | 86adf0ff-a528-595f-a286-911b2781e8d2 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 5e4d1ae2-7c70-57e1-bca3-dcb6cd424389 |  | note | – – – – – – – – – – – – – – – – –
label | 7a4ae0b0-ebd8-574e-9e73-00034e4af551 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9ee5179e-8367-546e-8db6-51bc5db2a74c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Surface Finishes
label | 044ce5cc-1231-51b7-8b06-9596651140ed |  | note | REFERENCE: 610.28
label | b4126b99-8155-5916-9eaa-676b2380c4ab |  | note | – – – – – – – – – – – – – – – – –
label | 765feedf-1ed0-5781-a381-0022abcea9fb |  | note | ACCEPTANCE CRITERIA: Surface finish shall be flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper.
label | 1353faad-ae48-5a77-b8ce-d5b3327d0e5b |  | note | – – – – – – – – – – – – – – – – –
label | ce04472b-0c19-5f7d-8bec-9e74c339b3de |  | note | METHOD: Visual
label | 5e015469-5804-52cd-8234-bc7389a4a53a |  | note | – – – – – – – – – – – – – – – – –
label | 7f77954f-f019-5ffc-9cf6-90bcbca7ad09 |  | note | FREQUENCY: Each element
label | 4332d488-1cce-5310-b290-d72540895f5c |  | note | – – – – – – – – – – – – – – – – –
label | c680e972-3225-5a47-9953-e24da8bb80c4 |  | note | CATEGORY: IP
label | caf613d0-0499-5e17-b459-c7ee215738ed |  | note | – – – – – – – – – – – – – – – – –
label | 8878c60d-6a27-5761-98b0-0c0388a68621 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 970c0260-50ca-5321-872e-e3d8b88bdda2 |  | note | – – – – – – – – – – – – – – – – –
label | 181cccf8-5f91-54d1-ac69-ca391b7c33b7 |  | note | VERIFYING DOCUMENTS: This ITP
date | 77f8d9cf-d248-50fd-bbe4-978843977d61 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Curing
label | a019c691-387e-5066-8f33-1f5e8cdf5ee1 |  | note | REFERENCE: Curing Methodology 610.23 Table 610.231
label | baf9616e-8d7d-5ba1-a3a2-53e4754c0833 |  | note | – – – – – – – – – – – – – – – – –
label | 77fca5b4-a6ae-5e2b-bb5c-6822c239e2cf |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | 409c4f4c-5477-5f9c-aa8d-eeba749fc03f |  | note | • Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | a0f9c48d-e88d-5b52-862a-733d29044c25 |  | note | – – – – – – – – – – – – – – – – –
label | 9aeab052-985c-52dc-89a9-76fd71adadc8 |  | note | METHOD: Visual
label | a6853d3d-b0eb-5b29-be9f-fee72f0fc466 |  | note | – – – – – – – – – – – – – – – – –
label | efa3e3db-d6b1-53f1-8d06-a357b7c02c66 |  | note | FREQUENCY: Each element
label | e426b241-80c8-51b1-8203-6c2e21be4331 |  | note | – – – – – – – – – – – – – – – – –
label | c765c6eb-ea58-5275-ab6f-7b50fa7fe8dc |  | note | CATEGORY: IP
label | 54eeb532-e543-5920-8faf-4ebd5275ded5 |  | note | – – – – – – – – – – – – – – – – –
label | 5e675f13-1bf4-567e-92ef-e068d103ebcb |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 831d65d0-fa20-5639-8700-0c9d452eb8a1 |  | note | – – – – – – – – – – – – – – – – –
label | f591089c-c7f9-5fba-862f-003962721734 |  | note | VERIFYING DOCUMENTS: This ITP
date | e7b3d232-893e-5cf4-91f3-4eeb992328e0 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Compressive Strength Test Results
label | adf115c0-390a-5a86-a0e4-80d4ea9e86fe |  | note | REFERENCE: IFC Drawings, Product TDS
label | 64f15634-dce7-5ed0-98ad-d22b9c1437ce |  | note | – – – – – – – – – – – – – – – – –
label | 6c117eea-a6fa-58dc-827b-8cd735b5c88f |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | e882b0cd-fac1-51f3-aba6-3bbe992eb51f |  | note | • 28 day compressive strength per sample comply with the design strength.
label | 8b718294-e284-5377-ae6f-e9bfcfbc6527 |  | note | Attach: Compressive Strength Test Results
label | 2fb7b1cd-1b96-5176-8107-d19848a50f66 |  | note | – – – – – – – – – – – – – – – – –
label | 058c80b5-001a-5667-a383-85e20d8e8bbb |  | note | METHOD: Document Review
label | 77c91b55-710e-51fd-8b8a-1c52e98ddd47 |  | note | – – – – – – – – – – – – – – – – –
label | 64cef770-ba91-5827-8fc5-02616a6b7198 |  | note | FREQUENCY: Each cube
label | cce49b0b-1fe6-58bb-9446-9bfc0ea72732 |  | note | – – – – – – – – – – – – – – – – –
label | f089ff72-fad8-5937-936c-7b08c49811c8 |  | note | CATEGORY: IP
label | 652deb9e-5195-5851-bad9-01a09686d9a4 |  | note | – – – – – – – – – – – – – – – – –
label | 3909cd7c-716b-542a-9df5-715ff4bcc9bf |  | note | RESPONSIBILITY: SE/PE/SPE
label | 6800cc0a-c416-53e1-aeb5-8ad2c4ac6b18 |  | note | – – – – – – – – – – – – – – – – –
label | 1d2e07e7-0033-54eb-aa92-bf86d31eb91c |  | note | VERIFYING DOCUMENTS: This ITP
date | 972a6dc6-068d-5d3c-89a4-56374c693d04 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 As-built Survey
label | 022bf9b8-5160-56a8-95e2-b7bf4bfbea50 |  | note | REFERENCE: IFC Drawings
label | 50e2bd30-11c6-5f53-a51f-be010569db4a |  | note | 610.46 (a), Table 610.462 (Nov 2018)
label | e911221a-33d6-5a5a-8991-136b0e058964 |  | note | 610.47 (a) Table 610.472 (March/June 2019)
label | f55d9a99-771d-56bc-899a-227715b106b3 |  | note | – – – – – – – – – – – – – – – – –
label | 4aceba84-89af-500a-b8ad-67602355d714 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below:
label | 5edaf789-d07f-5f8a-8384-822f337771e5 |  | note | • Reduced level ±2.5mm
label | f516f56a-f189-5603-b06b-451aa60b2d54 |  | note | • Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | 29e67264-4b36-5181-8c33-dc72cdeb6f8e |  | note | • Deviation from flat surface ±1mm
label | 41330aa1-6692-593c-be39-8fcc0a8961ac |  | note | Note: Different revisions of 610 have different clause numbers
label | dc911d99-cc25-57be-862d-9a497710a5db |  | note | Attach: Survey As-builts / Survey Report
label | dbfdc535-9558-50e2-8619-76f9b014c744 |  | note | – – – – – – – – – – – – – – – – –
label | ef649933-c86c-5d32-b540-10e913fa72d0 |  | note | METHOD: Document Review
label | 9cb88343-58a2-5f3d-9880-94c58b09e138 |  | note | – – – – – – – – – – – – – – – – –
label | c8617aca-2f90-5bfb-acc3-393b0c887e70 |  | note | FREQUENCY: Each element
label | 3ec7b393-c262-5ed9-bcd0-874125fa2952 |  | note | – – – – – – – – – – – – – – – – –
label | 3201e900-0549-5a83-a262-1f0f7316503f |  | note | CATEGORY: IP
label | 5a1b1e71-250c-56bc-9423-1839ccbb9b8f |  | note | – – – – – – – – – – – – – – – – –
label | dd6480ab-4f19-5886-85e6-223d377c1a74 |  | note | RESPONSIBILITY: Surveyor, PE/SE/SPE
label | 738787b9-e1fa-5c15-bd0a-4d0951a0cbbc |  | note | – – – – – – – – – – – – – – – – –
label | ecaa4bdf-3a6a-5db9-ae67-1c6f03dcb266 |  | note | VERIFYING DOCUMENTS: This ITP
date | 38620732-ff49-5f14-919a-d13ccaf184bb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | 58b3ebe0-00fe-58b5-a7a9-d04ea6ce0c61 |  | note | REFERENCE: MRPA Quality Management Plan
label | 280cd43a-bcb1-54cd-a4a7-9af4c5b9f9fb |  | note | – – – – – – – – – – – – – – – – –
label | 5a7911f1-7fd1-5677-8855-8492dc815206 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 24035e1a-0f3d-5a1f-8ab7-5c767d365262 |  | note | – – – – – – – – – – – – – – – – –
label | 7d60f900-ac2c-598b-85ed-8eb04b6e87dc |  | note | METHOD: Document Review
label | 93d604f9-4332-5c0d-abfd-7efaf67dc51a |  | note | – – – – – – – – – – – – – – – – –
label | 2b70a4d0-f470-5309-bad8-4e6fdb1986fe |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 6e2eaa47-3538-5a2f-8215-6cfefcd79eea |  | note | – – – – – – – – – – – – – – – – –
label | fa13a7b8-1c29-52c1-aeb5-be9fcfbe4b43 |  | note | CATEGORY: HP*
label | db43960e-73ff-5148-8399-cd62cb435b57 |  | note | – – – – – – – – – – – – – – – – –
label | 5f40ccc9-7ed8-5554-b880-5671091cff50 |  | note | RESPONSIBILITY: PE/SE/SPE
label | 91539dd8-dd82-58ef-b55c-e8e28c77f684 |  | note | – – – – – – – – – – – – – – – – –
label | 4c598597-0244-5874-9efe-2e86298d33d8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0af0e0ba-c65f-55e4-b6b5-b0f1ada7765f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 24ec4667-573d-5b7d-beb5-e703902b02a2 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 291f208d-34f1-554e-a274-0b1d2f22455c |  | textbox | Name:
text | 48424a93-ea07-5f53-8283-a5491f3c716d |  | textbox | Position:
date | 6f6c2d08-de72-5a0c-984b-f576bdfafa27 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-069-CIV-CAMMS-Signage Installation | itp |  |  |  | Yes | ITP-069-CIV-CAMMS-Signage Installation Rev 0 | d2c17ea2-3d76-4d14-a0a2-bec3f21a5f11
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | e1b7dad7-b65a-5b5d-92f0-1df183efa6e8 |  | note | Document Title: ITP-069-CIV-Camms - Signage installation
label | 30520f0f-10ec-5433-ba36-ce095da02b36 |  | note | ITP Description: Camms - Signage installation
label | e1c71045-1a6a-5874-bf3b-587793180ade |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 6cc3422c-8440-5638-9503-f2863720a016 |  | note | Discipline (e.g. CIV/STR/RAIL): 069-CIV
label | aacaea4c-3188-55e2-a459-67ad164bc17a |  | note | Revision Number: 0
label | 870d7a49-ad73-5976-b1d7-315ccf4fb4c0 |  | note | Revision Date: 22/11/2023
label | 2ce6a507-f5e4-5ef9-89f4-49d023b5d3b5 |  | note | ITP created by: Chloe Mitchell
label | 2c2d8919-5a98-5d2f-b9a9-73fd0a52d977 |  | note | ITP approved for use by: Victor Mira
label | 540f628f-e9cf-51dd-9558-5794536fe11a |  | note | 1.1 Non Dependent
label | 9e29beaf-05df-57f7-8ba3-5c8b47ffa0cb |  | note | Reference: VicRoads Section 860 (Feb 2023)
label | 4e448a71-08ca-58ca-9fc4-93b603114ff7 |  | note | 1.2 Non Dependent
label | fa79f239-2dce-5dd0-b203-a0a079a18416 |  | note | Reference: VicRoads Section 714 (Feb 2023)
label | f9c7fa17-1460-5dda-80ff-fe3737da8896 |  | note | 1.3 Non Dependent
label | 2f724b04-3d62-5ad5-9979-f378e58c7adf |  | note | Reference: VicRoads Section 703 (Aug 2021)
label | 30c9fb75-98d9-5da3-b6be-7e929f107a84 |  | note | 1.4 Non Dependent
label | f76d1053-56b2-5808-b39c-4023b1a954e8 |  | note | Reference: IFC Drawings
label | f8f2da67-1385-51b5-970a-88197eaf8d64 |  | note | 1.5 Non Dependent
label | a89fefa9-d5e1-546b-995f-2f10b5c90488 |  | note | Reference: AS 1742.2:2009
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Manufacture & Supply of Signages and Posts
label | 2a946d72-c75a-57c9-98ad-d07e12eb5445 |  | note | REFERENCE: Section 860, Section 860.06, Section 860.07 Table 860.071, Section 714.03, Section 714.06 IFC Drawings
label | b28c0b03-1a37-5d81-93a1-5ade25c3842b |  | note | – – – – – – – – – – – – – – – – –
label | 48dde61a-2c4a-5e63-ade9-6c7065cbd7e6 |  | note | ACCEPTANCE CRITERIA: Signs are to be manufactured in accordance with Section 860 and IFC Drawings
label | 61680c4a-aa11-59e8-bb7f-09f37666a2b1 |  | note | ○ Warranties for the Signboard and Components, Sign Face Material, Giving of the Warranty and warranty Claims to be in accordance with Specification 860.07 and Table 860.071.
label | 51d3ce2a-9720-589d-937c-80c4ee29e333 |  | note | ○ Packaging and Storage of Sign to be in accordance with Specification 860.06.
label | 6aec8159-26bf-5892-a41b-96348887975f |  | note | ○ Signs and components shall be handled and transported so as to prevent damage.
label | 9edf1967-6208-5633-95cb-bf48a68ededd |  | note | ○ Signs shall be stored vertically in such a manner to prevent damage to the sign face, edges or components, taking into account any recommendations of the sheeting manufacturer.
label | 44f72774-6cad-5e98-b5b0-e98444ae387c |  | note | ○ Post details shall be as shown on the Sign and Post Schedule and in accordance with the VicRoads Traffic Engineering Manual Volume 2. Steel posts shall be either:
label | ad980fca-ee78-54ba-8db4-2da2bb2f00d4 |  | note | – Hot dipped galvanised; or
label | 5dae1bf3-846d-5a4e-ac67-34965bbd75ae |  | note | – Pre-galvanised prior to forming
label | 2e5e844c-aad6-58a2-b72b-d5f74e8b0825 |  | note | Attach: TeamBinder Material Approval Ref No
label | 35a5e061-ca83-5c62-a37b-20ebb164f27d |  | note | – – – – – – – – – – – – – – – – –
label | d0948653-e3c4-5d89-859c-24c825a52687 |  | note | METHOD: Document Review
label | b8a09b72-9c27-59a3-8841-1ed59898c1ed |  | note | – – – – – – – – – – – – – – – – –
label | 7c75c70b-1634-5517-8f1e-8c541092f5ed |  | note | FREQUENCY: Prior to works start
label | e2983112-fa3b-5e24-9ec9-0e0088c6a9c2 |  | note | – – – – – – – – – – – – – – – – –
label | 45c419f9-4f9c-5227-95d4-36dff3b8bb4b |  | note | CATEGORY: HP
label | 47098fb4-e4fe-596b-b80a-849dbca7cd19 |  | note | – – – – – – – – – – – – – – – – –
label | b8f2535b-e1bc-5307-97cf-3a335b260dc5 |  | note | RESPONSIBILITY: Nominated Authority
label | 5b735dd1-ec5b-5861-80f8-449d879090f8 |  | note | – – – – – – – – – – – – – – – – –
label | e7ed22e9-3c4b-5610-b9a6-3a5a91ea5190 |  | note | VERIFYING DOCUMENTS: Conqa HP Release
date | f4e554e9-c508-5873-b3f5-bb2f2491df61 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Check for correct documentation
label | 8e18d433-150c-55c8-aeae-d1240b559510 |  | note | REFERENCE: IFC Drawings
label | ae01264a-6ce1-59c3-862b-2f1b34da7e0d |  | note | – – – – – – – – – – – – – – – – –
label | 3e71a3fa-9c7e-5797-ba8c-2b0d2952c9e4 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and sub contractors are:
label | d8fab467-bb13-5ff7-8682-6851e753b898 |  | note | – Using the correct and complete set of drawings
label | f106d45a-704b-54bd-9597-539127178a57 |  | note | – All drawings are the latest version
label | 47195a30-6608-5b75-a4c1-eb94d4714c65 |  | note | – – – – – – – – – – – – – – – – –
label | cebf2be8-e835-5020-bc2a-9e5e05b5ff62 |  | note | METHOD: Visual inspection
label | 830529ba-62eb-5e8b-a998-8d45c176d59d |  | note | – – – – – – – – – – – – – – – – –
label | 3810a001-7a05-5fdf-9767-811ca3993eae |  | note | FREQUENCY: Prior to commencing any activity
label | 2544ea1a-75e7-5ff0-9924-96caae0ec439 |  | note | – – – – – – – – – – – – – – – – –
label | 5663266b-5f82-50af-a606-c40a08bea47d |  | note | CATEGORY: HP*
label | 294eafef-0a22-52c8-943b-f38c79ece060 |  | note | – – – – – – – – – – – – – – – – –
label | b48a7ecb-b06c-5f84-8922-66dde0545393 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8e772085-4dd2-5684-a281-b795de1a1b50 |  | note | – – – – – – – – – – – – – – – – –
label | 9454c309-2067-53d1-953f-a94743094a08 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | eee33e4d-6a80-5830-98f4-38d0707061dc |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Setting Out - Position of Posts and Signs
label | 1a415743-1ac8-5030-9150-5537e6ccb90c |  | note | REFERENCE: Section 714.06 IFC Drawings
label | 67a0cd94-9266-5211-ac8e-1e3e22602c13 |  | note | – – – – – – – – – – – – – – – – –
label | 179cf41a-221b-5313-82a9-10cb198e2e0f |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with IFC Drawings. The required positions of all posts and signs shall be checked and confirmed by the Supervisor before the erection of posts
label | ea120cef-cdea-5d4d-8c24-e951ab2e2024 |  | note | – – – – – – – – – – – – – – – – –
label | 8956b383-f261-5b6f-ad00-8fa19fbddabb |  | note | METHOD: Verify
label | 55783f20-a7f0-5abf-88ce-57140d51e43c |  | note | – – – – – – – – – – – – – – – – –
label | e92fab16-0c01-5a34-9934-6a3cc4692cdb |  | note | FREQUENCY: Prior to start
label | 157a8469-457c-5e0a-8120-37184a55f029 |  | note | – – – – – – – – – – – – – – – – –
label | 4a6de858-5e9c-5766-9765-7c572fb87a7f |  | note | CATEGORY: HP*
label | bd2669b1-14a7-5f3d-b014-4f7c73a9e966 |  | note | – – – – – – – – – – – – – – – – –
label | 35818a1d-2ab1-58cb-847e-d8d0c8bd07b2 |  | note | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | 05c4ae3a-b8c5-5fbf-a20e-ff19f3cfcb1c |  | note | – – – – – – – – – – – – – – – – –
label | 0a3b623a-3010-56b5-bf3b-c00a3571ad93 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 934256a5-593d-5a0a-930b-bc44791c74c3 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Foundation
label | 93a0c478-b858-564d-9ddc-28489e9a074d |  | note | REFERENCE: Section 714.06 (c), Section 703
label | 92d2787c-1b99-5ebb-867d-15ff06f03d4c |  | note | – – – – – – – – – – – – – – – – –
label | 8a7f4083-eb56-5cfc-9ba6-5ed86b67e30e |  | note | ACCEPTANCE CRITERIA: All posts shall be set in concrete foundations to depths shown in the Sign and post Schedule and have hole diameters as per the below:
label | 40a82617-d317-572b-be95-38f3a2bb3935 |  | note | ○ Post sizes 32mm and 50mm nominal bore steel = 225mm diameter
label | 66b174b9-f52f-5d75-8b0a-8505464f58cf |  | note | ○ Concrete shall be 20MPa and complying with requirements in Section 703.
label | 3e30a115-979b-5428-9e22-f93568fa8972 |  | note | Attach: Concrete Delivery Docket
label | e7ec3d88-36d6-5c6d-8c40-45e97cc0dde8 |  | note | – – – – – – – – – – – – – – – – –
label | d4e02714-7432-5536-92ba-46591cd96b5d |  | note | METHOD: Measure, Visual
label | 8482c214-13cb-5ade-9bf2-21be237f73b0 |  | note | – – – – – – – – – – – – – – – – –
label | c2ddd00c-5b71-5638-bf45-99e0a8c6da0d |  | note | FREQUENCY: Per Lot
label | 33a4d6a3-57f5-5c04-8ee1-44d23b95c3de |  | note | – – – – – – – – – – – – – – – – –
label | ea109c6b-8d1f-5714-a101-003ead505bf3 |  | note | CATEGORY: HP*
label | 9cc5c84b-ebb7-5659-9ce2-81ae31b08d81 |  | note | – – – – – – – – – – – – – – – – –
label | 70b21519-ab8f-5606-a7d1-d8efa24c80cd |  | note | RESPONSIBILITY: SE/PE, Nominated Authority
label | df30e450-10fc-5bd6-b5eb-3fae03c0123f |  | note | – – – – – – – – – – – – – – – – –
label | 10fb4d21-9421-5eea-b6da-00ef28351338 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 6da86c2e-2af5-57a6-b593-3ed05364fd25 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Post Installation in Sockets
label | 92ef9999-a7c4-57d3-9a8e-ff6265e7cb73 |  | note | REFERENCE: Section 714.06 (d) Table 22 of AS 1742.2:2009
label | 9006beec-cf90-5095-93e2-788749d6c474 |  | note | – – – – – – – – – – – – – – – – –
label | 24916c87-a0f1-5fd6-9138-db7d15580cb2 |  | note | ACCEPTANCE CRITERIA: For Post Size 50mm Socket size to be 65mm Nominal Bore Tube
label | 941f0d92-d17d-5793-8d54-f852016d4f39 |  | note | ○ The socket should protrude 50 mm above an earth surface or 25 mm above a paved surface.
label | 440cb27a-20e1-515d-b280-3be49f16d537 |  | note | ○ The sign post must penetrate a minimum 450 mm into the socket.
label | 9f1de52b-c5a8-5ecc-8b61-eca298b1badd |  | note | ○ Depth of the socket should be as per Table 22 of AS 1742.2:2009.
label | 3c29dc76-f3ce-571b-a91e-ec3a1c496fce |  | note | ○ The sign post should be securely fixed into the socket by an approved vandal-proof method.
label | a7d9a955-df51-5969-a288-9e2d712ef403 |  | note | – – – – – – – – – – – – – – – – –
label | 5f6928de-e3f4-5c08-a73e-70bf922e8e19 |  | note | METHOD: Measure, Visual
label | 3083117e-716e-5063-9dcd-cea1eab36fd8 |  | note | – – – – – – – – – – – – – – – – –
label | 69d61862-4df4-59cb-b959-537ac2321af8 |  | note | FREQUENCY: Per Lot
label | 3e2f0ec5-67fe-5b2c-b5ca-beb64d3e73a3 |  | note | – – – – – – – – – – – – – – – – –
label | cd554459-72c1-52e8-86e9-7940ae950c01 |  | note | CATEGORY: IP
label | a6abc405-a993-546c-a1bd-df664d6eaa83 |  | note | – – – – – – – – – – – – – – – – –
label | 43033069-c873-5bcd-b06c-28c26592808c |  | note | RESPONSIBILITY: SE/PE
label | b72c6aaa-51a7-5f0f-b5cf-a1b8b890648e |  | note | – – – – – – – – – – – – – – – – –
label | debb8004-8b21-5f5e-967f-d052f12ab5bd |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | bd9e67be-05a7-54a8-9f99-b265bf59f99e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Backfilling of Post Holes
label | ce744252-6b8b-53e8-8f99-f95c5d6990fa |  | note | REFERENCE: Section 714.06 e
label | 222c274a-570d-5466-83ba-0f446239a835 |  | note | – – – – – – – – – – – – – – – – –
label | d9e3de0d-13e5-5563-9235-0ffe93dcfea0 |  | note | ACCEPTANCE CRITERIA: Only relevent where cast in sleeves have not been used.
label | 460792e1-6976-5f90-b73a-099e526e43ad |  | note | ○ 32 and 50 mm Nominal Bore Steel Posts
label | feaf4ade-5d6e-5336-9d65-eeccd2689d39 |  | note | ○ Posts holes shall be back-filled with concrete with a nominal strength of 10 MPa.
label | 1cec09c6-3f9c-5ee1-81c7-e0770e4b3ab0 |  | note | Attach: Concrete Dockets
label | 77d6ba71-347b-5774-8a86-59bf6f7394b2 |  | note | – – – – – – – – – – – – – – – – –
label | a0fb35c9-610e-549f-a47e-635b26e56d28 |  | note | METHOD: Verify
label | 0eddec3d-a8de-5d03-b4e8-35bf89367853 |  | note | – – – – – – – – – – – – – – – – –
label | 87f5a8cb-3195-53b6-b8d1-4bed8c9665cc |  | note | FREQUENCY: Per Lot
label | 3e1df541-8f09-55c2-bf82-ab5135f31070 |  | note | – – – – – – – – – – – – – – – – –
label | 4c6ad430-e98b-5930-9f7e-9aac950599c7 |  | note | CATEGORY: IP
label | 47b073c8-4d4e-5f7a-a6b7-35901d82cb90 |  | note | – – – – – – – – – – – – – – – – –
label | bbe5ca3b-0745-5908-9592-d5d18241cccd |  | note | RESPONSIBILITY: SE/PE
label | ebf76f9f-dec6-5553-98e2-32305d53d440 |  | note | – – – – – – – – – – – – – – – – –
label | b8ca546f-a7dd-5ae7-a1a0-f63bfbbd1f66 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 3e913563-7269-5948-8da2-33ec68a5a018 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Sign Fitting
label | 34b1d939-eedc-5bb7-b9e8-364ed2695fce |  | note | REFERENCE: Section 714.07 Design Pack 11 - Signage and Linemarking (IFC)
label | 68f9bb7b-03e7-585b-81c8-61a0a3e79635 |  | note | – – – – – – – – – – – – – – – – –
label | 43364fc9-9491-57e3-8156-fb37297aab3b |  | note | ACCEPTANCE CRITERIA: Signs shall be attached to the post or structure using the type and number of fittings as specified in the Sign and Post Schedule, or as follows:
label | a9873a39-e880-5d8d-a2b4-7ae12ce93a55 |  | note | – Signs up to 200mm in depth – one fitting per post
label | d0e2c5b7-68e4-5ff2-95d6-c8544bc2bad3 |  | note | – Signs 201 to 900mm in depth – two fittings per post
label | 4e1542a8-997a-5146-8d93-6786b8055de2 |  | note | – Signs 901 to 1200mm in depth – three fittings per post
label | cb55145c-a923-5150-b4e4-bcbd5f3cd457 |  | note | ○ One extra fitting provided per post for each 400mm increment or part thereof above 1200mm.
label | 41416618-7705-514f-bb0b-4dee2cdb8f3b |  | note | ○ For braced signs, the sign shall be attached to the post at every intersection point between the sign bracing member and the post.
label | 2f895054-195a-524d-90d4-bcfccc895b1d |  | note | ○ When a sign assembly consists of two or more signs, the signs shall be moubnted in accordance with the sign assembly drawings.
label | 3bd3205f-390c-5959-9e57-beac59a007de |  | note | – – – – – – – – – – – – – – – – –
label | d8703382-01c3-58db-a0f3-4b5620fc921a |  | note | METHOD: Measure, Visual
label | 2707f58c-353f-5f67-a27c-4ad3d118e3d3 |  | note | – – – – – – – – – – – – – – – – –
label | 7e71114f-23b4-59bb-836f-ce689c3ae2d1 |  | note | FREQUENCY: Per Lot
label | 205ebe4b-ca3b-58ee-8847-71950173ab47 |  | note | – – – – – – – – – – – – – – – – –
label | 200d1852-f36f-5dc9-b269-002598a131a3 |  | note | CATEGORY: IP
label | 9306948c-8dff-5544-9ddd-bd2311ffe75b |  | note | – – – – – – – – – – – – – – – – –
label | a6af418c-4bc3-5b1f-be12-617d937f2d2e |  | note | RESPONSIBILITY: SE/PE
label | a431757e-4371-5896-8b45-9838a6b3747c |  | note | – – – – – – – – – – – – – – – – –
label | 8aa55225-0ca9-53c9-980c-612c93bcb81e |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 72e662a1-1b57-5abb-ae44-3b0da98b112d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Mounting of Signs
label | 9154fa87-0ad6-5558-84df-99ce3615e390 |  | note | REFERENCE: Section 714.07 (d,e,i) Design Pack 11 - Signage and Linemarking (IFC)
label | b6d1e79c-20f9-51cb-94c4-9e02a9a8fbce |  | note | – – – – – – – – – – – – – – – – –
label | fe6fbcba-63e2-5494-827c-8aa25e57b1b3 |  | note | ACCEPTANCE CRITERIA: Nominal Mounting Height for all signs in 2m from Road level to bottom edge of sign except keep left signs (R2-3) located in median islands, which are mounted 0.5m above ground
label | 525fc7e5-9906-5e18-8dc8-48406e67514b |  | note | ○ Signs shall be positioned in accordance with the following tolerances:
label | a5e43a98-a1f0-589b-925d-8aa0e2543d04 |  | note | (i) +/-40 mm of the height specified in the Sign and Post Schedule measured from the bottom of the sign or sign assembly to the lip of the kerb or edge of shoulder nearest the sign;
label | f51f1809-265b-58d7-bcb9-5822915cc2a9 |  | note | (ii) +/-100 mm of the pegged sign location or specified location.
label | ab28f283-9c2d-5600-ba6f-c1220c8fcb09 |  | note | ○ Sign shall be installed such that the sign face is rotated away from the approaching traffic to avoid direct reflection (approximately 5⁰), with the exception of signs mounted on structures over traffic lanes.
label | f6930d41-38fd-53e8-8263-b769ae1f2201 |  | note | ○ After erection of each sign all stiffening bars are to be removed.
label | 6807df85-cd4f-514c-a817-95e0e7f85c57 |  | note | – – – – – – – – – – – – – – – – –
label | f776d3eb-7995-5443-a2ee-a302818c91e9 |  | note | METHOD: Measure, Visual
label | 98a05ba5-a9b3-516f-a630-3ce558d72f50 |  | note | – – – – – – – – – – – – – – – – –
label | f26d3fd7-df9a-5d1b-b45c-1bcaa2683f8e |  | note | FREQUENCY: Per Lot
label | 14c36d26-b0ef-590f-8600-e47063dd3e5b |  | note | – – – – – – – – – – – – – – – – –
label | d5de924e-100d-5953-9b28-b7b8898ea7ab |  | note | CATEGORY: IP
label | b419d5f6-adf7-5b85-9248-6e01bf5764aa |  | note | – – – – – – – – – – – – – – – – –
label | f537aad5-a347-5ae8-ae8f-85a3ac15d143 |  | note | RESPONSIBILITY: SE/PE
label | 80912003-e0ac-59ac-986c-e58be27508ce |  | note | – – – – – – – – – – – – – – – – –
label | 9d858a49-61dc-5a99-aec1-591b297f4ad9 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 98252ea0-01c3-58f5-94a9-9bf9258755a5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Masking of Signs
label | e65551f3-2101-5341-98a8-68a1e6bc5b21 |  | note | REFERENCE: Section 714.08
label | e8d7ff8d-4b31-5807-91ba-2d391fe0fb41 |  | note | – – – – – – – – – – – – – – – – –
label | 2aa550f1-9d44-5bca-918c-7b075e2f5095 |  | note | ACCEPTANCE CRITERIA: Where indicated in the schedule, the Contractor shall mask the nominated sign(s) by placing a porous cloth or similar covering that conceals the sign text under both wet and dry conditions and does not void the sign material warranty. The masking material shall be held in position by wire mesh over the sign.
label | 4e91b11b-ac16-578f-abd9-8130e9410039 |  | note | ○ Adhesive material shall only be applied to the masking material and not be applied to either the front or rear face of the signboard.
label | d9d08f9e-5f78-516c-a5d9-500218d46ea4 |  | note | – – – – – – – – – – – – – – – – –
label | bdcd0bfe-ab0c-56b6-98ed-30f325292280 |  | note | METHOD: Measure, Visual
label | 9e8d67b9-3faf-5ab4-9182-724210b56e3e |  | note | – – – – – – – – – – – – – – – – –
label | 533e2c0b-a95f-5201-a2da-609459c5cfbf |  | note | FREQUENCY: Per Lot
label | 23f2a269-1bbb-564f-8c08-1b7295807be5 |  | note | – – – – – – – – – – – – – – – – –
label | 6002769b-08af-5d76-ae38-52c7ae9a36f1 |  | note | CATEGORY: IP
label | 8cf83949-768b-5d40-8c84-289c4da05be1 |  | note | – – – – – – – – – – – – – – – – –
label | 858ae014-b643-5424-8568-7d8a48069b4a |  | note | RESPONSIBILITY: SE/PE
label | b1ca3128-2233-58c2-9716-fbe3c4791e68 |  | note | – – – – – – – – – – – – – – – – –
label | 98cb856a-6dfe-5522-bccd-c4bf56f2cdcc |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 6d2a78ce-fa7c-5b55-be1f-dd4854465f85 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey
label | 3b5814d3-f96e-5b3d-8229-e7aec15eab84 |  | note | REFERENCE: Section 714.05, IFC Drawings
label | 3ea18a99-dde8-5a27-855b-28dd63a87218 |  | note | – – – – – – – – – – – – – – – – –
label | 80e7e99c-b4f6-5285-a1d1-0159c63155e7 |  | note | ACCEPTANCE CRITERIA: Survey activities carried out to validate correct construction of signs, components and posts as per IFC Drawings and Section 714.
label | c35ecfb5-2787-5bb7-a09f-75f6c365665a |  | note | Attach: Survey Conformance Data/Report
label | 9eac2586-9179-5c63-acc7-b3a39f4061cc |  | note | – – – – – – – – – – – – – – – – –
label | fd696389-15bc-5534-955f-aa9acb9c498b |  | note | METHOD: Document Review
label | d08be245-b37b-5d8c-aab3-6333709722a7 |  | note | – – – – – – – – – – – – – – – – –
label | 6894e8dd-4f79-52e5-a60c-19833d541d40 |  | note | FREQUENCY: Per Lot
label | 6c4fb05a-7290-53b0-bc46-2a441dbad9e2 |  | note | – – – – – – – – – – – – – – – – –
label | a3426c78-860b-5cf5-8158-5b250ccd25d0 |  | note | CATEGORY: IP
label | 041c6ac1-a939-54f6-8c84-62103e6e26bc |  | note | – – – – – – – – – – – – – – – – –
label | b274f34b-15b9-59e5-acd8-900bf4c1ff25 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 2fd343df-7b5b-538a-82da-18260dcf69dc |  | note | – – – – – – – – – – – – – – – – –
label | 737f5c7a-fd1a-530b-818a-146dc9ee1953 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 2495ef49-f303-5eef-8d66-2b3a85352700 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | c7c569de-50b3-5c7e-8be5-0a94d66c30f3 |  | note | REFERENCE: MRPA Quality Management Plan
label | f9d5e760-ec71-5646-9e21-ac749eaddfb5 |  | note | – – – – – – – – – – – – – – – – –
label | 59ac7a05-256f-5c89-8de4-1195d6a2e457 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
label | 07097de5-e5a5-5e6a-b556-ba04528c238e |  | note | – – – – – – – – – – – – – – – – –
label | e0ce2253-078f-5f2a-842b-abd8fd8a4745 |  | note | METHOD: Document Review
label | 330b8780-e88e-5695-b790-bf3233321a61 |  | note | – – – – – – – – – – – – – – – – –
label | 7ec6cf6b-fd07-518e-b9c8-5a695be4094c |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 8edf5b96-2ff9-5a25-8557-a7ee0bd113eb |  | note | – – – – – – – – – – – – – – – – –
label | de4f718a-4334-56df-b3a8-2380be263973 |  | note | CATEGORY: HP*
label | 95c9abfa-2afb-5391-81fc-07b9637287e2 |  | note | – – – – – – – – – – – – – – – – –
label | 9737f4c3-9ff1-504d-92d4-e573c8e1e910 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1108ccb3-c220-55d0-85d4-1c50bd4d98d7 |  | note | – – – – – – – – – – – – – – – – –
label | 68517ac5-7a63-5025-a90a-fc4b707c3747 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 1b13be30-d3fd-5f9d-aac1-1d85d963dcef |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 06bf0452-acf4-5d14-baad-aa7c167a5e1a |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 627afe22-7391-5b83-92d5-8066521a71e2 |  | textbox | Name:
text | 3bf7c564-2f7f-53d2-8396-8337be9ff6ee |  | textbox | Position:
date | 5933fc94-df91-5e1e-97c8-79c4129694fa |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | itp |  |  |  | Yes | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | d5963e0e-ff74-4ae6-a8f1-89193596998a
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Reference Documentation
label | ebf62cfd-6169-55bb-b642-47cde6574b8b |  | note | Document Title: ITP-STR-Concrete Coatings (Protective &/or Decorative)
label | 0d6f147a-6889-5476-90f5-b7b2375f4e24 |  | note | ITP Description:Concrete Coatings (Protective &/or Decorative)
label | 08d94395-4086-5c1a-ad4f-268718a4d92f |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 21c9acf4-cb51-5929-8c11-06abd7bdd3b7 |  | note | Revision Number: 2
label | dbef52d2-5964-5a24-9fc1-9b1f5ba0bd2c |  | note | Revision Date: 11/12/23
label | ed27cd5d-0871-50db-88e1-325bbee9162e |  | note | ITP created by: Mike Freeman
label | 5e4f72f9-0335-5833-b6e7-1a7bdd412fa6 |  | note | ITP approved for use by: Mike Freeman
label | 651479ce-4ae6-506b-9713-362bfb5dc4ed |  | note | 1.1 VicRoads Section 685 November 2018
label | 628cb3da-fa4d-5290-a4ef-de7dc7a3f9b2 |  | note | 1.2 VicRoads Section 686 November 2018
checkpoint-group |  |  | section | 2 - Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - Anti-graffiti System Selection
label | e3356397-e9ae-5fdf-a29a-094b4664308e |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (e)
label | 1013ee35-52fc-50a7-b685-40932484d08b |  | note | – – – – – – – – – – – – – – – – –
label | 22f215bd-1368-5ac4-a0eb-c9c1a74ad7b0 |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | d037cfec-e65f-580a-8641-14f0de76aa8b |  | note | i. be either a film-forming or a penetrant system ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification) iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses (film-forming): WFT total = 175µm min. OR WTF per coat = 88µm min. DFT total = 100µm min. vii. adhesion to substrate (film-forming): 0.75MPa min. viii. application rate (penetrants) as per the minimum thickness on the manufacturer's TDS
text | 64356883-472a-5cf4-84e7-aeccec806c3a |  | textbox | Enter: Teambinder Material Approval number
label | 0a8baa96-f4b6-50e0-a239-7432af5d2902 |  | note | – – – – – – – – – – – – – – – – –
label | 917c101a-6ac0-59b2-818c-ed539f7f0f7c |  | note | METHOD - Document Review
label | 06b5efa7-1fe9-5f35-93ec-cffbee415eb8 |  | note | – – – – – – – – – – – – – – – – –
label | ca88bda9-2bd0-5457-b8b5-53d5447abef3 |  | note | FREQUENCY - Once, for each coating system, 14 days prior to application
label | bff12959-c556-578a-b022-6d88b260a2a8 |  | note | – – – – – – – – – – – – – – – – –
label | 608d0b73-551e-5f3a-bb9a-62429b1f00a5 |  | note | CATEGORY - HP
label | 27d26cea-13cc-50ff-866a-812c94dad374 |  | note | – – – – – – – – – – – – – – – – –
label | f11df0d6-cf94-55d3-82af-cb5e278d28f4 |  | note | RESPONSIBILITY - Nominated Authority
label | d9ef5ea7-c0c1-5273-984e-aa493e4b6950 |  | note | – – – – – – – – – – – – – – – – –
label | 426d507a-7999-525d-9f76-7bed362e410e |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 326b82a6-9a1f-5f76-a7da-0c710d513d70 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Decorative & Anti-carbonation System Selection
label | 9ba097e3-c0b0-5a0a-8594-0e29776d14e0 |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 686.04 686.05 (a) & (b) Table 686.051
label | ec62a386-26cb-54eb-9d92-5583d2373c0b |  | note | – – – – – – – – – – – – – – – – –
label | b08bef56-299e-591e-9918-e1b2d2ba303a |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 99ff4637-77c9-5605-a46f-c101120dee52 |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
text | 00eca1c6-321d-5e65-b4af-a4341cd72905 |  | textbox | Enter: Teambinder Material Approval number
label | 0b2a1fb2-eaae-5f46-80ba-97a4af8bae4e |  | note | – – – – – – – – – – – – – – – – –
label | 5f3aae9d-b414-5436-a3d8-62e16043dbde |  | note | METHOD - Document Review
label | 9200d8a4-5584-5b8c-91c5-ebf4ed962768 |  | note | – – – – – – – – – – – – – – – – –
label | f70d6eea-7569-512f-9110-2e02298478fe |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | 1c684f1f-75d2-5af5-8bf4-7d9835f96a31 |  | note | – – – – – – – – – – – – – – – – –
label | 665acc0c-9c65-56f2-b803-25e2a45a6436 |  | note | CATEGORY - HP
label | 474b5895-860b-59d7-b23f-6832ed5e8b00 |  | note | – – – – – – – – – – – – – – – – –
label | 0248b879-d0c2-5445-be97-1a8bb729f908 |  | note | RESPONSIBILITY - Nominated Authority
label | ccd657d7-a608-5160-ba92-07948cb5eecc |  | note | – – – – – – – – – – – – – – – – –
label | d5ae6aa4-49df-5327-9776-5f5e1f36c00c |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | ea5c3d04-e594-53a7-aa30-f980313d7e62 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
label | 6ed310b0-84ca-5f25-8a29-3194df5fe308 |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051
label | cb3ca86f-cebe-593f-89ce-483165f1be23 |  | note | – – – – – – – – – – – – – – – – –
label | 3f377b2c-8281-5c45-a205-93991e02ab91 |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 5f3bbb48-bdca-5a3f-aa6e-72f2f72d93ea |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
text | a527c540-8ff4-5f71-a90b-dd049d78c9dc |  | textbox | Enter: Teambinder Material Approval number
label | 984b6d5d-7f48-5653-b456-511a327b133b |  | note | – – – – – – – – – – – – – – – – –
label | cc588d9d-71b3-5ec7-badc-1ec4295a4a37 |  | note | METHOD - Document Review
label | de693d16-872f-5e85-bbe5-384f32c08957 |  | note | – – – – – – – – – – – – – – – – –
label | b3bfd4b4-58ad-5fcb-becd-0cda4f0e7145 |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | 5e3c65c1-cf5a-5a8d-a2cf-923e15d1d166 |  | note | – – – – – – – – – – – – – – – – –
label | 94b5a294-0d04-5bee-9d01-9d7f3982f0e2 |  | note | CATEGORY - HP
label | 5551e8c1-b6e1-5eab-aa78-502568be24bc |  | note | – – – – – – – – – – – – – – – – –
label | 022cbee2-6857-589a-8690-bf9f37e12d26 |  | note | RESPONSIBILITY - Nominated Authority
label | d39cc64e-c258-5971-8691-939f50aacc64 |  | note | – – – – – – – – – – – – – – – – –
label | 53046865-466c-5a5f-aba1-4e41cab5a4eb |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | f8d790b4-0c2f-57a6-aada-9adec6f440fe |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
label | 4f4ad9e0-62ae-541f-a677-80b09bd14782 |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051 686.05 (c) (i) & (iii)
label | 3ae5ea70-fc1c-5d82-bd4a-ca7e5bd288f1 |  | note | – – – – – – – – – – – – – – – – –
label | 9ef16377-105e-59c5-80cc-3a54e01577ef |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 2ca7603e-f1b0-5187-9edb-09e5879ca409 |  | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat ii. all coats to be compatible with each other Penetrants: iii. active ingredients: Silane = at least 95% Solid silane & silane cream = at least 80% Silane-siloxane & siloxane = not specified iv. application rates: Silane = 2 applications of 0.3L/m² min. Solid silane & silane cream = 1 application of 0.4L/m² min. Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS Film-forming coat: v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) vi. to be water or acrylic based, solvent-free vii. to be non-yellowing, colour-fast and not subject to fading viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure ix. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 200µm min. x. adhesion to substrate: 0.75MPa min. xi. able to bridge cracks up to 0.3mm wide xii. able to be re-coated within 24 hours xiii. have a minimum pot life of 1 hour xiv. compatibility to an alkaline surface xv. equivalent air thickness >150m xvi. equivalent concrete thickness >450mm xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s xviii. Water vapour equivalent air layer <4m xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
text | 23178a56-041a-5b91-81e8-928ab8948818 |  | textbox | Enter: Teambinder Material Approval number:
label | 635386c1-93db-5483-bd0d-f580b51758b8 |  | note | – – – – – – – – – – – – – – – – –
label | 7dba8bc9-8271-5250-835c-1e12ea8b84d3 |  | note | METHOD - Document Review
label | 133b289d-060d-58e2-a83c-3fcb99babfb1 |  | note | – – – – – – – – – – – – – – – – –
label | cc97afc4-2b39-5df9-b205-6fe40abf7cce |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | 30ac2cee-24d0-50df-b85a-0cf35a67ef8f |  | note | – – – – – – – – – – – – – – – – –
label | bbb59dd1-10df-5d31-8970-6140bc46fb5f |  | note | CATEGORY - HP
label | f2bf8a94-7986-59bb-9885-a236ab30d332 |  | note | – – – – – – – – – – – – – – – – –
label | cbc1bcad-959c-5c7b-a13d-4de8518ed94d |  | note | RESPONSIBILITY - Nominated Authority
label | 84b3dacd-f7e0-5371-98ee-71a6af21d0c3 |  | note | – – – – – – – – – – – – – – – – –
label | e1da6992-0193-5bbf-890d-3b7baeb3e094 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 92e4bbb4-97c8-5ad3-a317-84c600f34c33 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Quality Documentation
label | eae5d80b-c016-599f-ab51-78cc9f346ea8 |  | note | REFERENCE - 685.05 686.04
label | fdf409f7-735a-5710-906a-ad912b494477 |  | note | – – – – – – – – – – – – – – – – –
label | 79a87b4f-46ad-5236-9208-a1353bde9942 |  | note | ACCEPTANCE CRITERIA - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
text | 763949da-25a0-5ac1-8262-9daf23903dd3 |  | textbox | Enter: Teambinder Hold Point number
label | cde6674f-c008-5a9f-9ce0-9b648f14b724 |  | note | – – – – – – – – – – – – – – – – –
label | f0925e50-f1ec-5299-a070-523a7dda4335 |  | note | METHOD - Document Review
label | 8fdf4e23-3b3c-5df6-a6e5-35cb68377cbd |  | note | – – – – – – – – – – – – – – – – –
label | 6931745a-41ef-500c-8315-036afb590d55 |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | 75f359a2-5648-59cb-9f82-3f8e40885f00 |  | note | – – – – – – – – – – – – – – – – –
label | fb476e5c-2283-50d4-a977-24cd548e2997 |  | note | CATEGORY - HP
label | 8ec4e513-1c7a-5e3d-bef5-30d1733d1174 |  | note | – – – – – – – – – – – – – – – – –
label | bc7da4b3-2e81-5b96-9f95-3f8af8ecf8d3 |  | note | RESPONSIBILITY - Nominated Authority
label | d98573ec-7e23-5c81-8a0b-e18df476deb6 |  | note | – – – – – – – – – – – – – – – – –
label | abd3847c-ba4e-5fd8-bed4-2a4b1d3dd52c |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 30a2d5a5-5749-5728-9045-67e54593b853 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Coating Personnel & Equipment
label | da9ee805-125f-581a-87e6-effdd85085ed |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.16 686.19
label | ff494f7e-2345-5244-8e34-cb08b5e2a66d |  | note | – – – – – – – – – – – – – – – – –
label | 746621e0-0e2c-5612-9b2f-b3e55810a06e |  | note | ACCEPTANCE CRITERIA - The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques. Application personnel require 2 years minimum experience. The supervisor shall remain present at all times. Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
label | f274aec6-2b08-5445-b4fd-3005a5b2c970 |  | note | – – – – – – – – – – – – – – – – –
label | acf2a470-0c74-53ab-b093-80472a93990f |  | note | METHOD - Document Review
label | 9a5da869-c48c-5264-9ee2-195a1b9ab3bd |  | note | – – – – – – – – – – – – – – – – –
label | 2586c726-1433-514d-be39-c525a6d6d64f |  | note | FREQUENCY - Once, prior to application.
label | 5e9fa58b-11e4-5b56-a160-02b3e76709d1 |  | note | – – – – – – – – – – – – – – – – –
label | 02ecbe53-e72d-57fa-99d2-81ba73e41ff4 |  | note | CATEGORY - IP
label | bafa73c1-1104-5612-90e6-29d97fa45e8e |  | note | – – – – – – – – – – – – – – – – –
label | 59376cc0-9ba1-5c6f-b66a-2521eb38a572 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 4c49042b-e27c-5b92-8b06-1f4312593e6f |  | note | – – – – – – – – – – – – – – – – –
label | ea197588-2222-57ff-9026-643e12d2f976 |  | note | VERIFYING DOCUMENTS - This ITP
text | 5d6fe0bf-9bf4-54f5-b741-a1d553a6cd2b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Protection of Adjacent Works & Property
label | 0ceaccd8-9400-574e-a6a9-9c042388e22b |  | note | REFERENCE - 685.17 686.10
label | 79de4c34-49e0-5d71-84b5-86da45e6b898 |  | note | – – – – – – – – – – – – – – – – –
label | 044182c5-4bd4-57c6-bdfd-48ac6aeb7771 |  | note | ACCEPTANCE CRITERIA - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes. No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
label | 941f732c-dce5-5dd0-95e2-31bb19efecf8 |  | note | – – – – – – – – – – – – – – – – –
label | 3fbed370-8cdd-515b-b92c-19abf892b7b1 |  | note | METHOD - Visual Document Review
label | 0ee11e8b-bde3-5286-915e-9259df20de95 |  | note | – – – – – – – – – – – – – – – – –
label | 27e8a024-dc73-5e20-b30d-aa2df7d387af |  | note | FREQUENCY - Where applicable, 2 days prior to application.
label | c25e0d71-1a52-59fb-8418-59fcb053bf4f |  | note | – – – – – – – – – – – – – – – – –
label | 767449d0-bcb7-5450-87a6-cfcc82eec914 |  | note | CATEGORY - HP
label | 5157a25b-b894-583f-8d59-cd702dafb84a |  | note | – – – – – – – – – – – – – – – – –
label | 93ea71ad-c38e-5bba-b351-791bcfbd3e7f |  | note | RESPONSIBILITY - Nominated Authority
label | 0dd3069d-504b-5025-bd58-e11354951403 |  | note | – – – – – – – – – – – – – – – – –
label | ab4c458c-33e4-5623-817f-8ba794b27850 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 5aedbd96-2f32-5d39-83d9-a540bd7b612c |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Minimum Concrete Curing Period
label | 60811e2c-403e-5fde-b078-4144c18e67c6 |  | note | REFERENCE - 685.08 686.16
label | 77e16cc1-e830-5e9d-a548-0c0347ccb22a |  | note | – – – – – – – – – – – – – – – – –
label | 9c014dfd-4244-53d4-9274-32902f674198 |  | note | ACCEPTANCE CRITERIA - Concrete shall not be coated until the minimum concrete curing times have elapsed: Standard cured concrete = 28 days Accelerated cured concrete = 14 days Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
label | e32e7401-21ad-5025-b50e-8d9077fe4aae |  | note | Note: All durations may be reduced by 50% if the moisture content is less than 10% when measured with a moisture meter.
label | d3e11755-02b0-5df9-b04f-35df9a29a774 |  | note | – – – – – – – – – – – – – – – – –
label | de2c25a3-5ecf-5283-adb7-bb9a197a6f49 |  | note | METHOD - Visual Document Review
label | 7c3330e7-75ac-5de5-ae51-802a2712a593 |  | note | – – – – – – – – – – – – – – – – –
label | 518f294a-00bd-5846-a481-3978d227aa9a |  | note | FREQUENCY - Once, prior to application.
label | 3da45566-95a5-53ab-bdcc-1c43424e236e |  | note | – – – – – – – – – – – – – – – – –
label | 57dfd387-7151-59bb-bbc9-8dbb0329a7fa |  | note | CATEGORY - IP
label | b577f13a-d0cd-59b4-8a9c-76d878cbe201 |  | note | – – – – – – – – – – – – – – – – –
label | 60783966-fa20-5a69-abda-504bc465716b |  | note | RESPONSIBILITY - SE/PE/SPE
label | 295b4fc9-5de6-5d83-8d0c-e12bb223feaf |  | note | – – – – – – – – – – – – – – – – –
label | 4710e1a3-f9c3-55cc-84df-a953b929b1b5 |  | note | VERIFYING DOCUMENTS - This ITP
text | 42a8e490-ac6e-53d0-9a65-f51363c90024 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Trial Application (or Past Performance) Inspection
label | b181a02b-c5dd-57ab-99dc-631841ea09ec |  | note | REFERENCE - 685.11 686.13
label | 58d31442-4380-5e4a-80c0-54de8735ed3d |  | note | – – – – – – – – – – – – – – – – –
label | bf4ffda2-3251-5a5f-8208-fbbe84ff3a4f |  | note | ACCEPTANCE CRITERIA - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate. Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
label | 5a19ec67-7fe3-5b6b-a540-0fd8f91684f2 |  | note | Attach: Inspection Photographs OR
text | ee39c334-0cb0-53c7-b1b2-872b41ba5967 |  | textbox | Enter: Teambinder Hold Point number
label | a819c9c7-3b1d-5e48-8297-b28350a4e7aa |  | note | – – – – – – – – – – – – – – – – –
label | 5ac32b70-75c6-540b-8108-3ae65d1431b2 |  | note | METHOD - Document Review
label | 3effc6f8-f925-569f-9001-261403b91032 |  | note | – – – – – – – – – – – – – – – – –
label | eb9d364d-3185-5a6e-bfd5-9dc4352e67f1 |  | note | FREQUENCY - Once, for each coating system, 7 days prior to full coating application
label | c4160185-ed20-5843-8826-66a805cfb2a8 |  | note | – – – – – – – – – – – – – – – – –
label | 4cef1ff7-ed16-58bb-bad0-16e642d46fac |  | note | CATEGORY - HP
label | 1ad865ec-66c4-5435-b9e3-652162153887 |  | note | – – – – – – – – – – – – – – – – –
label | 971eedca-4b32-58a0-a9ee-e8ecee3acddd |  | note | RESPONSIBILITY - Nominated Authority
label | 764f1439-0a02-5908-9b51-50e77acab72f |  | note | – – – – – – – – – – – – – – – – –
label | ffc9108f-8904-56e1-8efe-6e68f883f75a |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 2a8a08db-3d71-51c5-89ef-6f89188c37d8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Pre-application Activities
checkpoint-status |  |  | checkpoint | 3.1 - Material Records
label | dbb45701-19bd-5b30-8137-74ff002e12d8 |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.10 686.12
label | 469e2e3c-3ef8-59e0-850f-eeb5fa0be05e |  | note | – – – – – – – – – – – – – – – – –
label | 3256b853-35cf-5152-b4fe-7fe4c9c38524 |  | note | ACCEPTANCE CRITERIA - Materials shall be brought to site in unopened, sealed containers, clearly marked with: the manufacturer's name & address product reference batch number quantity manufactured in the batch date of manufacture
label | 9fc3bfb9-9756-568b-b412-ca31a4241d21 |  | note | Product beyond the manufacturer's shelf life shall not be used. Each product shall be traced to final location.
label | 477ed76f-f724-566c-9eb4-675b542bddc8 |  | note | – – – – – – – – – – – – – – – – –
label | 7f60e6b2-96d7-5575-85d2-24f15ad847cf |  | note | METHOD - Visual
label | c2d1f819-c67d-5f04-8e4b-904186bcda83 |  | note | – – – – – – – – – – – – – – – – –
label | 3657c5f7-0a3e-568c-a4a0-20b8613cb352 |  | note | FREQUENCY - Prior to application
label | 1662024e-67f5-5576-99ec-c4809b60d7d4 |  | note | – – – – – – – – – – – – – – – – –
label | 512fa0fb-29fd-5aa1-8f6e-356a8b5d6809 |  | note | CATEGORY - IP
label | 1912f92a-78a4-5d9c-8029-2529d3cc2d7a |  | note | – – – – – – – – – – – – – – – – –
label | 9f3e0404-629e-5518-895d-6fd61089d6a4 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 3ca75a3e-d842-5106-a23b-5e52d6e99a71 |  | note | – – – – – – – – – – – – – – – – –
label | 1c195274-2b83-5e11-a804-b2b68115901f |  | note | VERIFYING DOCUMENTS - This ITP
text | e2e18451-4933-5b3d-9be3-661c9ea534c8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Weather Conditions
label | 91cf58f1-fe83-5a4f-937b-e1406a3dbfc7 |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.09 685.12 (a) 686.11 686.14 (a) (iii)
label | 17ef4f56-d449-53bd-b3d6-93badb06cb3e |  | note | – – – – – – – – – – – – – – – – –
label | 17a31810-9c02-5073-9cd7-9d8bc245209d |  | note | ACCEPTANCE CRITERIA - Coating systems shall not be applied under any of the following conditions:
label | 8792d8f9-24bf-563f-8431-6f06812d2b7e |  | note | i. windy conditions where spray/splatter may be generated ii. when wind-borne debris is likely to contaminate the uncured surface iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate vii. when the substrate surface is wet or damp (unless it is required for the coating system)
label | 2c07e0c4-8eb1-5c28-88d8-eafad960667e |  | note | Weather conditions are to be recorded.
label | 8395e254-842e-5249-92bd-ebeaf0aa2346 |  | note | – – – – – – – – – – – – – – – – –
label | 965ab86e-8a85-5d3e-933a-05b40fd690c5 |  | note | METHOD - Visual Measure
label | ba36040b-db19-5f4d-b72c-bd8ace72bc01 |  | note | – – – – – – – – – – – – – – – – –
label | 03f089f8-29aa-52da-b45c-580badd91e61 |  | note | FREQUENCY - Prior to application and every 4 hours per shift
label | eb9e92e0-19c7-57d2-bddf-0952accc7980 |  | note | – – – – – – – – – – – – – – – – –
label | d89789d8-a331-5f7e-aa78-d456a7f2739e |  | note | CATEGORY - IP
label | 56dba6e8-b928-56ce-a88c-784849e5f124 |  | note | – – – – – – – – – – – – – – – – –
label | 9e7702ef-e28e-59c4-b582-c9f0eea222d2 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 1bcd2c80-9f0f-5edd-8545-ce84d973dd2c |  | note | – – – – – – – – – – – – – – – – –
label | acc01882-972e-5efa-a02f-17ef37715fe5 |  | note | VERIFYING DOCUMENTS - This ITP
text | 9a222357-4454-50b4-b8c5-e86af8c7cce2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Surface Preparation
label | a0861294-29e0-573a-9117-90d432b7c5f9 |  | note | REFERENCE - Surface Cleaner TDS Coating System TDS 685.05 686.06
label | 11aa7912-d515-5eec-892a-d789c82bb49d |  | note | – – – – – – – – – – – – – – – – –
label | c51cdf6f-b661-5293-96a6-f8cccc909676 |  | note | ACCEPTANCE CRITERIA - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means. The surface shall then be flushed with water. Any concrete defects exposed during the surface preparation shall be repaired accordingly.
label | 67ea195f-1ece-5920-8c4e-47516cc5db66 |  | note | – – – – – – – – – – – – – – – – –
label | 728d02a3-5b21-5ed0-b994-8eaa4d21562f |  | note | METHOD - Visual
label | eb2e5ffd-3b75-5a6e-8d84-47a934ea0718 |  | note | – – – – – – – – – – – – – – – – –
label | 43f0c3b6-0fba-5cda-84e0-d4e9a5b5da95 |  | note | FREQUENCY - Once, prior to application.
label | 56522e0a-b2e8-5a7f-8700-7373ff40817f |  | note | – – – – – – – – – – – – – – – – –
label | b119e8a4-ea63-5018-b6ea-6d227d37843d |  | note | CATEGORY - IP
label | d9e32f01-c4b0-5619-94bb-24d890037a9a |  | note | – – – – – – – – – – – – – – – – –
label | ec88d075-1e14-5e87-b0f5-7cb14b7b360d |  | note | RESPONSIBILITY - SE/PE/SPE
label | ef9616cc-b4f6-5a4e-90e6-269628e52771 |  | note | – – – – – – – – – – – – – – – – –
label | 0d23c258-8c4f-5d2b-b693-e63d716ee12b |  | note | VERIFYING DOCUMENTS - This ITP
text | 756f9760-aa36-52ef-8d9e-8cecfd6d1389 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Surface Moisture Testing
label | 9e6e8517-c0b6-5c0e-8d02-b55925476163 |  | note | REFERENCE - 685.12 (a) 686.14 (a) (iii)
label | b2fb9fa7-ef51-5f0f-a376-fe327deeba02 |  | note | – – – – – – – – – – – – – – – – –
label | 4a804b47-75a1-59dd-8635-77f0e094ea1f |  | note | ACCEPTANCE CRITERIA - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS. Surface moisture conditions are to be recorded.
label | 16bc95a2-fe14-506e-bf01-683e13af7913 |  | note | – – – – – – – – – – – – – – – – –
label | 44b2591f-386d-552e-bf8c-2abd74c2b545 |  | note | METHOD - Test
label | 0ce87e8e-585c-5007-9898-33412f677051 |  | note | – – – – – – – – – – – – – – – – –
label | 0c7120f8-b073-5f1d-b2e7-6e86b67fc4e1 |  | note | FREQUENCY - Immediately prior to application, test 1m²
label | 65651eaa-a477-5618-8686-584c3891ef9e |  | note | – – – – – – – – – – – – – – – – –
label | 5849f456-0d1a-5301-bf33-4378edcd7e1c |  | note | CATEGORY - IP
label | a1cbb57e-cc10-5d48-9369-7b3e78e29953 |  | note | – – – – – – – – – – – – – – – – –
label | b68ce990-0675-5029-b8ee-31444ea4efee |  | note | RESPONSIBILITY - SE/PE/SPE
label | f96eea1c-6d0b-5070-8e84-aed237763259 |  | note | – – – – – – – – – – – – – – – – –
label | fb64a259-316b-5f66-871e-39da593a0b4a |  | note | VERIFYING DOCUMENTS - This ITP
text | 1ec699d9-3dff-5c86-9afb-c9cc8233e7a5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4 - Application Activities
checkpoint-status |  |  | checkpoint | 4.1 - Method of Application
label | 493c5481-3454-5270-b99a-4923ce213f83 |  | note | REFERENCE - Coating System TDS 685.07 686.07 686.09
label | 92b4489c-2b77-55fe-b4c9-ecbbf9eb2eb3 |  | note | – – – – – – – – – – – – – – – – –
label | aca9fd02-980a-595e-86b8-07cc8781b645 |  | note | ACCEPTANCE CRITERIA - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved. Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified. For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application. Times of coating(s), material names, locations coated and volumes used shall be recorded.
label | e3bf83ef-cc01-59e3-bda8-cd38ddb1911d |  | note | Attach: Coating Application Record
label | 966c27c4-5a2f-50e5-8170-19297308b7d0 |  | note | – – – – – – – – – – – – – – – – –
label | c387fa8c-6601-514d-a181-e9afdce3b81a |  | note | METHOD - Visual Measure
label | 37e2892d-e71d-5951-88d2-321dbe3935ab |  | note | – – – – – – – – – – – – – – – – –
label | abe8ecad-6a2b-57d2-98e8-b4cccb47d65e |  | note | FREQUENCY - Each coat
label | 33413501-fde7-5e10-964e-aec2dca9ca25 |  | note | – – – – – – – – – – – – – – – – –
label | ac334a34-2bd7-5bca-bd30-30bf3d95829c |  | note | CATEGORY - IP
label | 46c2a7b6-e84f-563a-a538-e23023059039 |  | note | – – – – – – – – – – – – – – – – –
label | 1634f20b-ea3b-56c2-8cb1-c30d6789a9b0 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 5855c5a4-e45b-5c27-8c44-dc846ac4c98f |  | note | – – – – – – – – – – – – – – – – –
label | 6bd3e9ed-68a6-548a-b7de-ff2d626f6326 |  | note | VERIFYING DOCUMENTS - This ITP
text | 4622d820-5305-5d2c-a8dc-9fcb5709f34d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Wet Film Thickness (WFT) Testing
label | c2484e73-74ff-5c0a-8c27-af55def2a297 |  | note | REFERENCE - Coating System TDS 685.12 (b) (ii) 686.14 (b) (ii)
label | 61217586-d406-54da-ab95-c0f2fabe9dc6 |  | note | – – – – – – – – – – – – – – – – –
label | aafe61df-e962-56a8-979b-fcfe275a9dda |  | note | ACCEPTANCE CRITERIA - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
label | dbcdcd73-48bc-5bcf-bc61-de4ea8c938a4 |  | note | Attach: WFT Test Results
label | 61a37b79-1b46-5729-a89c-4a71d51925c7 |  | note | – – – – – – – – – – – – – – – – –
label | 1b84cf64-320f-56b4-8e40-1719b1f0a5db |  | note | METHOD - Test
label | d20d2c2e-f88a-594c-ba23-51dbf5c7fe12 |  | note | – – – – – – – – – – – – – – – – –
label | d33d033e-7233-5e0a-a2a8-ef68bd1101b6 |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | 9db04385-207b-570c-880b-aa0e5e4dbbc9 |  | note | – – – – – – – – – – – – – – – – –
label | 54679a0e-d241-5009-a12c-4d9e153fb2d9 |  | note | CATEGORY - IP
label | 8364df07-d2bf-536c-9346-f640d7c1d20b |  | note | – – – – – – – – – – – – – – – – –
label | fda03b6e-fc33-5151-8e01-abbcc7b22ff0 |  | note | RESPONSIBILITY - SE/PE/SPE
label | ac1d1725-bdbf-5de0-bafd-a7c06731f96b |  | note | – – – – – – – – – – – – – – – – –
label | d97e53d6-9dda-5ddd-9cb2-a6554fde0e8c |  | note | VERIFYING DOCUMENTS - This ITP
text | 59ef425c-975c-55c1-ae27-b7d18277948f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Inspection & Defect Identification
label | 045fc696-ec66-56fd-9dcf-527c9555e151 |  | note | REFERENCE - 685.07 685.13 (d) 686.07 686.15
label | e6def57b-7769-5397-ba19-18dcd17fa0ca |  | note | – – – – – – – – – – – – – – – – –
label | 2683f890-8126-50b5-836d-a37dbeafb2e8 |  | note | ACCEPTANCE CRITERIA - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats. Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
label | b32a8a74-b0e9-5c30-a0b4-56f3259f8720 |  | note | – – – – – – – – – – – – – – – – –
label | c93ffceb-6f3b-5c95-8471-42520d3ab61e |  | note | METHOD - Visual
label | 40b268f2-7dff-56fe-94ac-0b78706f2c60 |  | note | – – – – – – – – – – – – – – – – –
label | 60cc7c0c-9958-5f3e-b626-bc5c6db878bd |  | note | FREQUENCY - After each coat
label | 8f533a4a-6d1a-5781-806e-3cffd2028872 |  | note | – – – – – – – – – – – – – – – – –
label | e8b5a3e3-55ba-5e8f-b384-f63d0498b85c |  | note | CATEGORY - IP
label | 672032f5-7e77-5e6d-b2d9-337bc2bd5a55 |  | note | – – – – – – – – – – – – – – – – –
label | 57f69bab-6ee5-5b22-aedd-8e15a8d18cdc |  | note | RESPONSIBILITY - SE/PE/SPE
label | 5b99632a-c850-502a-abd3-18b42fdb98d9 |  | note | – – – – – – – – – – – – – – – – –
label | 1a543f16-eb46-5422-bc59-890a5ea52535 |  | note | VERIFYING DOCUMENTS - This ITP
text | 84789195-df65-5cba-ba37-802f1aa02141 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Drying and Curing
label | 3b60a252-24bd-518b-b316-c75cd11e2f85 |  | note | REFERENCE - Coating System TDS 685.17 686.09
label | f10fd9ae-e36d-5290-9598-997cb34fbb8c |  | note | – – – – – – – – – – – – – – – – –
label | 01ec810c-8fdf-5eef-8c38-eaa1fd9c20f3 |  | note | ACCEPTANCE CRITERIA - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
label | ea086422-f0f1-5f88-b84c-5fff82246828 |  | note | – – – – – – – – – – – – – – – – –
label | aae7cf4a-bf08-525b-8e35-6522fbe1744d |  | note | METHOD - Visual
label | fc26c1b8-7e53-587e-814d-8531dba0d210 |  | note | – – – – – – – – – – – – – – – – –
label | a9aa629f-b760-51b8-b886-71ca57fa1c80 |  | note | FREQUENCY - After each coat
label | 276d476c-3d9d-5b3f-8437-0ae4ed4b0ea1 |  | note | – – – – – – – – – – – – – – – – –
label | 9b9023ef-1272-5811-8006-37ba5087be21 |  | note | CATEGORY - IP
label | 4426b201-95ea-5a7b-9f88-6abd0bcad051 |  | note | – – – – – – – – – – – – – – – – –
label | 10fd4f1e-9e64-5a74-a704-9b6b28a130c5 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 254c2ba1-456e-5511-8cb4-781148309966 |  | note | – – – – – – – – – – – – – – – – –
label | d9914f22-1a8c-592f-b632-1da2ed8271e8 |  | note | VERIFYING DOCUMENTS - This ITP
text | 73975a62-6aec-5b39-8da3-be50684692cd |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5 - Post-application Activities
checkpoint-status |  |  | checkpoint | 5.1 - Clean-up & Waste Disposal
label | 473e405a-20eb-5c4b-ac82-2a290e85cec9 |  | note | REFERENCE - 685.09 (c) 686.10
label | 4734833d-9c14-592f-b526-d3b8dea8fe14 |  | note | – – – – – – – – – – – – – – – – –
label | 15c157f6-58eb-52a9-b5cf-4f3034537b97 |  | note | ACCEPTANCE CRITERIA - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
label | 0c45d18d-5bf6-521a-b7e7-702afa286aba |  | note | – – – – – – – – – – – – – – – – –
label | 43c74474-91b0-5c4f-83df-89add1f6b013 |  | note | METHOD - Visual
label | 75fa2b6f-96a9-5319-850f-0d93f5a3bc74 |  | note | – – – – – – – – – – – – – – – – –
label | 1bb7079f-8edb-5927-b18d-2ddf49cf55b2 |  | note | FREQUENCY - At completion of Works
label | af871e42-bf54-5a24-92ae-bca103009850 |  | note | – – – – – – – – – – – – – – – – –
label | 6cd2f5f1-7fcf-5ec9-812a-21d6c5340fa6 |  | note | CATEGORY - IP
label | 3141fe15-a1f1-5e89-bcc6-ef2d73129934 |  | note | – – – – – – – – – – – – – – – – –
label | 80fa7851-d227-5a4e-be0c-07384a652261 |  | note | RESPONSIBILITY - SE/PE/SPE
label | e241ba86-a026-523f-96de-5eedb8cad2b8 |  | note | – – – – – – – – – – – – – – – – –
label | 7e50fc2d-42cf-53b6-8eeb-f254ca3b77fc |  | note | VERIFYING DOCUMENTS - This ITP
text | 35f49e62-9c4a-53ed-8682-cdb3500c6300 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Dry Film Thickness (DFT) Testing
label | b4d95241-ab1d-58dc-bd02-dc92da8a60f4 |  | note | REFERENCE - 685.12 (b) (iii) 686.14 (b) (iii)
label | c9aa2334-90f1-5053-beab-299312a1289d |  | note | – – – – – – – – – – – – – – – – –
label | 578867eb-714e-5951-b2f6-c37a41d2a604 |  | note | ACCEPTANCE CRITERIA - The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses: i. Anti-graffiti system = 100µm Ii. Decorative & anti-carbonation = 150µm iii. Decorative, anti-carbonation & anti-graffiti = 150µm iv. Atmospheric & splash zone (dual protective) = 200µm
label | e5f03341-acca-5e69-9415-a4e81262b4f4 |  | note | No more than 15% of the readings shall be less than 90% of the required thickness.
label | 0e25e303-d7ac-5b95-9047-863aad871dc8 |  | note | Attach: DFT Test Results
label | 301155d6-6e39-58cf-b4c3-ec8d006bf330 |  | note | – – – – – – – – – – – – – – – – –
label | 4b6340d6-1114-570b-816f-24879f664d2e |  | note | METHOD - Test
label | b9666331-f0b1-5b48-8cd0-ac3e17145b35 |  | note | – – – – – – – – – – – – – – – – –
label | 1d4b4d06-e09a-5ba7-b14e-ed8a0ab2b041 |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | fd4a64c5-46de-5338-a441-644aea8ed24c |  | note | – – – – – – – – – – – – – – – – –
label | 410a50a9-c2f1-522f-9f52-91867ded2558 |  | note | CATEGORY - IP
label | c033cf2f-ad9c-5ccd-b2c6-dae20a1dcd46 |  | note | – – – – – – – – – – – – – – – – –
label | 1f1f16d2-3dd8-5f91-b421-19359d19af2c |  | note | RESPONSIBILITY - SE/PE/SPE
label | 3f15e846-b49e-5198-b69a-f7b4d49491e6 |  | note | – – – – – – – – – – – – – – – – –
label | b1521897-8449-51c3-b349-eabf49469f27 |  | note | VERIFYING DOCUMENTS - This ITP
text | a5752485-592e-560e-b4e4-440c7a03ae93 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Adhesion Bond Strength Testing
label | 1cc8a1cc-d9e4-58b4-aeae-35e6192166d8 |  | note | REFERENCE - 685.12 (b) (i) 686.14 (b) (i)
label | 15a7621e-5b73-5eb9-ac86-58e43c9a254a |  | note | – – – – – – – – – – – – – – – – –
label | 30ce2657-d516-50d2-8eb2-cd9b5bb701cc |  | note | ACCEPTANCE CRITERIA - A minimum of 14 days after application, the bond-strengths between: i. the coating system to the substrate, and ii. Separate coating layers shall be tested using 50mmØ aluminium dollies. The subsequent results shall be greater than 0.75MPa.
label | ce65e6ff-a59b-5e82-8a27-f2bcee847253 |  | note | Attach: Adhesive Bond Strength Testing Results
label | c72a6af2-eab1-5382-b403-d198f07a6bc8 |  | note | – – – – – – – – – – – – – – – – –
label | 78737d27-a026-529b-93a9-a423bcddc735 |  | note | METHOD - Test
label | 21d4d6ae-51ea-55cb-b261-e35826482503 |  | note | – – – – – – – – – – – – – – – – –
label | b01ba31d-abce-50e0-bd87-96401dab7481 |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | b004a044-fcd8-55fd-9276-f281b959f88f |  | note | – – – – – – – – – – – – – – – – –
label | 362b7693-bfaf-5769-a4a0-962726d6585b |  | note | CATEGORY - IP
label | 1f68e5e7-a671-5f34-8b67-39fd0a655672 |  | note | – – – – – – – – – – – – – – – – –
label | c4788c27-f31d-56e8-af07-25eec8d6fc88 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 3eb96a4e-a6f3-5c63-a02f-4c4ebcda3b95 |  | note | – – – – – – – – – – – – – – – – –
label | 1a01eff8-3327-514b-a952-233a094308c1 |  | note | VERIFYING DOCUMENTS - This ITP
text | 2e2e4312-cd8b-5e7d-891e-d2090f4a7dff |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Penetration Depth Testing
label | 4fe028dd-88ee-5cca-979c-3f68dce44181 |  | note | REFERENCE - 685.12 (b) (v) 686.14 (b) (v)
label | d4042058-032b-5646-b0c3-393b347f057f |  | note | – – – – – – – – – – – – – – – – –
label | 267f2b83-7fd0-53fa-a809-362270042a2e |  | note | ACCEPTANCE CRITERIA - Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration. The subsequent results shall be: i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible) ii. Silane, Solid Silane or Silane Cream = 5mm min. iii. Silane-Siloxane or Siloxane = 3mm min.
label | 8199a1bf-d5f2-5bed-8ece-c757d5221f3e |  | note | Attach: Penetration Depth Testing Results
label | c39d3396-4a56-57c1-a567-9cacaf224e4f |  | note | – – – – – – – – – – – – – – – – –
label | b159afae-0b45-546d-a847-a891789cb79b |  | note | METHOD - Test
label | 484b122f-fbad-580d-ba1b-ca410595d24e |  | note | – – – – – – – – – – – – – – – – –
label | c1c3a16a-1e2e-533d-87f8-1554b0c1ccfc |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | 958e048a-0c53-5663-940b-b4189dcffb8a |  | note | – – – – – – – – – – – – – – – – –
label | 02a5938b-ce9d-5250-bf5e-175939293c1b |  | note | CATEGORY - IP
label | df99a23b-0ce8-5ba1-83e3-62491b8ba81c |  | note | – – – – – – – – – – – – – – – – –
label | 68e34a94-8fb1-572c-90ba-6a739000f30a |  | note | RESPONSIBILITY - SE/PE/SPE
label | fe4f6064-41a4-5bff-9fb4-e9daadcf1931 |  | note | – – – – – – – – – – – – – – – – –
label | 12f4b5bf-1a9f-50e0-b282-108afc2478b0 |  | note | VERIFYING DOCUMENTS - This ITP
text | 7c4b9238-4cc0-58ad-be93-70db1f246fbc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Non-conforming Coatings
label | 6aa7b1d8-9ce9-570f-b7b8-6370e2a68587 |  | note | REFERENCE - 685.14 686.17
label | 63bea1c1-2dae-5261-887a-a76c5e68dcd2 |  | note | – – – – – – – – – – – – – – – – –
label | 50105fd3-1cf5-5a61-bdef-e024e1d2012f |  | note | ACCEPTANCE CRITERIA - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
label | 141fbbea-51dc-509e-a03e-922b8fe38b01 |  | note | – – – – – – – – – – – – – – – – –
label | 34885b3e-ec35-5c8e-9d30-c49bf89888f5 |  | note | METHOD - Visual
label | 46ff7232-98c1-56dc-845e-40c5bc695a7f |  | note | – – – – – – – – – – – – – – – – –
label | 4c8872b2-06c2-5e95-a727-861fd62e0355 |  | note | FREQUENCY - Where required
label | c9f1d184-9b61-5632-a346-cc8de0f54afb |  | note | – – – – – – – – – – – – – – – – –
label | 9c25a048-b0c7-566f-ad9d-9a09d466e096 |  | note | CATEGORY - IP
label | a4e6f890-9cc9-5f4d-9ec3-af3af64b29bb |  | note | – – – – – – – – – – – – – – – – –
label | e3840cbb-d3f2-503a-ac5d-c691180d0ddb |  | note | RESPONSIBILITY - SE/PE/SPE
label | c4350e51-8160-51f0-9ea3-d0f30caca280 |  | note | – – – – – – – – – – – – – – – – –
label | 3c2d33c7-e313-5525-ac95-7fe1232cd588 |  | note | VERIFYING DOCUMENTS - This ITP
text | c57155cf-395c-5602-ae23-ae13e7a698cd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Coating Application Guarantee
label | c740d635-aedb-5da5-8d35-8b8e60036957 |  | note | REFERENCE - 685.06 (b) 686.05 (a)
label | a2627019-e402-5db2-a271-648674d9ce20 |  | note | – – – – – – – – – – – – – – – – –
label | ee567e39-f047-503b-acae-c0006682546f |  | note | ACCEPTANCE CRITERIA - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
label | 8cd1d607-848f-54ef-a3eb-02f1121437c2 |  | note | Attach: Coating Application Guarantee
label | aca2d8cb-95fa-5470-a923-45485d3ea1f2 |  | note | – – – – – – – – – – – – – – – – –
label | 9d5acca7-425e-5cc6-9bc5-9e7a1c13c584 |  | note | METHOD - Document Review
label | c4451e71-e74c-505b-b16a-264d3e5d31f0 |  | note | – – – – – – – – – – – – – – – – –
label | 0eed5967-f08b-56c6-9476-908c24ec22c5 |  | note | FREQUENCY - At completion of Works
label | c295bd02-188d-597a-8f1b-6446ef498c08 |  | note | – – – – – – – – – – – – – – – – –
label | 7fdd6492-2329-51ec-88ba-cf48222ecd6a |  | note | CATEGORY - SP
label | 4d6b1565-bffc-5954-ad1a-504cfe44f0bc |  | note | – – – – – – – – – – – – – – – – –
label | 3b7f020f-bf99-596d-a796-9a8785be0b5c |  | note | RESPONSIBILITY - SE/PE/SPE
label | e6439bd8-c4cb-57b3-a802-3c0f2491264a |  | note | – – – – – – – – – – – – – – – – –
label | 4e35a047-41f5-5929-bf44-0576752c407f |  | note | VERIFYING DOCUMENTS - This ITP
text | b0e2b2cd-fa8c-548b-a325-7b01887ca1ae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Repair to Damaged Coating
label | 104fbacc-83aa-57c8-b160-765656b81e7a |  | note | REFERENCE - 686.17
label | 57e3c17e-af64-5b63-885f-76007668cbd1 |  | note | – – – – – – – – – – – – – – – – –
label | 658cb35d-d8d9-5a59-8021-f7a017995127 |  | note | ACCEPTANCE CRITERIA - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
label | beb7446e-5eef-5df0-ad55-103ab2e0e5d1 |  | note | – – – – – – – – – – – – – – – – –
label | c03ca874-609c-576f-b502-e7a3b8e760b6 |  | note | METHOD - Visual
label | 4bb9af53-8dd3-5ee8-9c38-ad0e5822a748 |  | note | – – – – – – – – – – – – – – – – –
label | acddf7e2-624c-527a-83ee-13c9905c405c |  | note | FREQUENCY - Where required
label | d04d5b3c-1615-51a6-a18f-dfcc7e5b2312 |  | note | – – – – – – – – – – – – – – – – –
label | 8a14dfd4-2296-5d2f-89fb-33615b8535b4 |  | note | CATEGORY - IP
label | 4651b042-8214-5adc-8e43-2bb78571c025 |  | note | – – – – – – – – – – – – – – – – –
label | 8ae865ca-9967-516f-ab30-ada1b05b618e |  | note | RESPONSIBILITY - SE/PE/SPE
label | bae5b287-f0f5-588a-bcc0-d9a2a6d33903 |  | note | – – – – – – – – – – – – – – – – –
label | c87d1edb-6cff-5d14-9bca-b03ac162c0c5 |  | note | VERIFYING DOCUMENTS - This ITP
text | f89feb87-c616-5054-8442-368c903192d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Non-conformance Report (NCR) Closure
label | c19fad57-1657-5898-a510-3c9223c64d57 |  | note | REFERENCE - MRPA Quality Management Plan
label | 8771e612-84d8-59f7-bffa-528dc4f9ac3f |  | note | – – – – – – – – – – – – – – – – –
label | a5fc614e-8566-569a-af0c-d0d845a97e76 |  | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 5e95408c-7f7d-5373-b862-1522c53f50ce |  | note | – – – – – – – – – – – – – – – – –
label | 73140741-d967-5042-8f12-03c31bb5004e |  | note | METHOD - Document Review
label | 0a313b75-158a-5cd4-b1fd-5ba2a92dd95d |  | note | – – – – – – – – – – – – – – – – –
label | 45477ddc-125a-5e7c-9260-540cc7643539 |  | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
label | c806393b-a76a-5f94-a312-6a44790df7db |  | note | – – – – – – – – – – – – – – – – –
label | de1f2f89-bf03-5247-a58e-d8d1a9913496 |  | note | CATEGORY - HP*
label | 0b1ff173-4e90-5c10-936f-599a41934a91 |  | note | – – – – – – – – – – – – – – – – –
label | b5ac22ad-6e4b-518d-a70c-6164d8ac1fb1 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 85639dc2-b2b6-5543-806c-752600e4a63e |  | note | – – – – – – – – – – – – – – – – –
label | 380c109a-8e34-5b01-8acd-807fec48b1da |  | note | VERIFYING DOCUMENTS - This ITP
text | ac4f66b6-35c2-5f57-a13c-e4c192f76a29 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7787f32a-6c07-524b-949c-994e033d0e07 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 930e4186-d63a-5b6e-a291-2670cee01321 |  | textbox | Name:
text | 94a27d18-b517-52c4-8376-9087814d945e |  | textbox | Position:
date | c2ddc0bb-7bbb-5e09-95b7-ce714c7a28ce |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-010-STR-CFA Piling | itp |  |  |  | Yes | ITP-010-STR-CFA Piling Rev 0 | d8587987-3159-4ec7-9010-ae91619766bf
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 7549e2a7-1046-5128-a10e-91343c2ab068 |  | note | Document Title: ITP-010-STR-CFA Piling
label | 829cd9ce-68b2-539f-bd23-7273ed749c30 |  | note | ITP Description: CFA Piling
label | a3e3891f-72ab-5dfc-b908-3fedcbcc4552 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 8e8590a4-c64b-5d15-bf0f-a420007c3b73 |  | note | Discipline (e.g. CIV/STR/RAIL): 010-STR
label | c5911cd5-c847-5547-958a-7e4825ce43a6 |  | note | Revision Number: 0
label | 78db8539-cc84-5649-873d-b352bad32f0e |  | note | Revision Date: 11/10/2022
label | abb17e33-687e-593d-b213-c4041b71f4bc |  | note | ITP created by: Victor Mira
label | c242f2c1-1528-5b71-a194-0bb14f860a5b |  | note | ITP approved for use by: Victor Mira
label | 77484c8e-bf5b-5b2c-b2bf-0c5b5ba8d1b8 |  | note | 1.1 - Non Dependent
label | 59903b61-657c-5520-86ad-4b5d8e5af298 |  | note | Reference Documents:
label | ca51b91d-f563-54b3-a14f-b6cee83fa8c4 |  | note | • VicRoads Section 607 March 2015
label | efcbe3d1-50ef-565b-b0b4-348dc112157e |  | note | 1.2 - Non Dependent
label | f4f5672e-d3fe-5b82-874c-ab470595ee4e |  | note | Reference Documents:
label | e3de9717-deca-5fe9-afd6-02f2ac36dbb2 |  | note | • VicRoads Section 610 June 2019
label | 09f1c815-3e13-5fbb-821d-1eada10827d0 |  | note | 1.3 - Non Dependent
label | fbff4bf4-31be-5584-b573-34de19f19bb5 |  | note | Reference Documents:
label | 31361a17-c6c3-55c9-8b0d-452eeb8f4114 |  | note | • VicRoads Section 611 November 2018
label | 773d1ca9-1320-5171-a5ba-71c18a413b25 |  | note | 1.4 - Non Dependent
label | d0e3994c-93c5-5748-ac34-2551e78da040 |  | note | Reference Documents:
label | 0df5e3fc-2b03-5075-beed-b6af53357e8c |  | note | • AS2159-2009
label | 951518e2-4968-5861-b015-7025143d9606 |  | note | 1.5 - Non Dependent
label | b56863f1-0ffd-51fd-9b92-94d63cd35dbb |  | note | Reference Documents:
label | 159afbb0-dea8-5732-8b69-92184f00a514 |  | note | • AS3810.1-2015
label | be4ee8f6-d48f-5d9b-b5c9-26cb5c187e4d |  | note | 1.6 - Non Dependent
label | 5b912002-b8dd-5e32-9cc2-27ae2f27caff |  | note | Reference Documents:
label | 3f031999-60a0-5bdb-a900-b6dba9a8ac1f |  | note | • AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | e6b6fce8-8da4-5f27-9dac-7d581aebe422 |  | note | REFERENCE:
label | 02941778-7648-57a5-bad2-4cbd16e9b864 |  | note | 610.07
label | 42c5aa25-d29d-5f23-a7ed-da4bc9625e28 |  | note | Table 610.071
label | 64a869c8-35b2-58b9-bd99-0ff242dc7642 |  | note | – – – – – – – – – – – – – – – – –
label | 546cccf6-cdc6-5877-b01d-8314042ecf6a |  | note | ACCEPTANCE CRITERIA:
label | e2f9dcc9-f355-563f-b89a-d7db6a8fcfdd |  | note | • Concrete Mix is Registered with VicRoads.
label | aa449da5-e992-5a3c-b05c-0824be9fa509 |  | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 40674fce-2247-529a-9d9b-d8ae2978d410 |  | textbox | Enter: Teambinder Material Approval number
label | c917990f-dcc3-5504-85d1-904b7f40480b |  | note | – – – – – – – – – – – – – – – – –
label | 34d4fda3-c9fc-51ad-b45e-ba78a947de10 |  | note | METHOD: Document Review
label | f4ca3ea2-1add-58b7-a6e1-10964205b9e1 |  | note | – – – – – – – – – – – – – – – – –
label | 1ab6d61e-9f1e-5719-8806-73d71c5d042b |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | af7e8ea7-ab53-5f7d-bc9b-2ace8f41c185 |  | note | – – – – – – – – – – – – – – – – –
label | b8b10749-405d-5dbe-abf8-14c8f3557e03 |  | note | CATEGORY: HP
label | 7e7ff1a0-777d-5406-bb6d-0e7de37abe4b |  | note | – – – – – – – – – – – – – – – – –
label | 84431e09-2bde-555a-a438-a3015a221fba |  | note | RESPONSIBILITY: Nominated Authority
label | c93fcd6f-d5c3-5a6a-ad8a-1ddc7d21c29a |  | note | – – – – – – – – – – – – – – – – –
label | ee09559e-e1eb-5692-a710-921644c91d82 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 1497753e-057f-5c45-8e00-1932fab86c0d |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | e00671e0-1948-5f86-9fcc-1f5ff19f0367 |  | note | REFERENCE: 611.05 (a)
label | e6173f55-4793-5248-a24f-81a30a57b07d |  | note | – – – – – – – – – – – – – – – – –
label | 5c2674fc-8ef2-5115-847f-65b682c56f16 |  | note | ACCEPTANCE CRITERIA:
label | 0af97f76-e186-58c3-8c66-78ecef6e71f2 |  | note | • Current ACRS certification for materials and for bar processing.
label | 0fb03936-aa0b-5e00-b8e3-c9ed45d7e5a0 |  | note | • Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | ef8d0620-11a0-5fc5-8489-df2e86b07120 |  | textbox | Enter: Teambinder Material Approval number
label | 414f97df-6ec3-539c-86b1-72c1571d7b18 |  | note | – – – – – – – – – – – – – – – – –
label | 06558eee-7b16-5813-894e-39e2c70a0598 |  | note | METHOD: Document Review
label | 9c5eb10c-8f34-5480-adb0-e11f2d19e0c1 |  | note | – – – – – – – – – – – – – – – – –
label | 6ea7afa9-8409-5ed6-849b-8eda0f7a1325 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | 04faf56f-8c61-5ed4-a741-6c76f78a4866 |  | note | – – – – – – – – – – – – – – – – –
label | 48683286-273e-597b-9115-159b85f1de26 |  | note | CATEGORY: HP
label | 57dc0cb8-dc62-56bf-b862-93123f6e84a2 |  | note | – – – – – – – – – – – – – – – – –
label | 8d5ccd10-21c1-5512-9c77-c04ecc209be2 |  | note | RESPONSIBILITY: Nominated Authority
label | a10933ed-0e5b-55a9-9b82-c521805a1238 |  | note | – – – – – – – – – – – – – – – – –
label | 2ae4b7dd-05d2-56cd-81a3-b4959357545c |  | note | VERIFYING DOCUMENTS: This ITP
date | 7173f7db-60a6-53ca-86d6-1e6bf23f2c46 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 12f1996f-cb7a-589a-85e2-6c11ba309f94 |  | note | REFERENCE: 610.26 (a)
label | fdf85ddb-bfd8-5559-8ccb-94c1659fab56 |  | note | – – – – – – – – – – – – – – – – –
label | 5fbf9ae7-b5a1-5a89-9d0b-9c8b8a507392 |  | note | ACCEPTANCE CRITERIA: Wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
text | d2b74115-73f5-5714-9e28-f69e32b28f92 |  | textbox | Enter: Teambinder Material Approval number
label | 0ead1d8b-fb44-5b4e-87fa-71f1d2c48685 |  | note | – – – – – – – – – – – – – – – – –
label | 14f684e5-883b-5588-9e3e-d7b358bfabf9 |  | note | METHOD: Document Review
label | 1d233384-d965-52a8-962f-47aea34b081e |  | note | – – – – – – – – – – – – – – – – –
label | 59a50cae-9b3c-542d-b223-a16f7f22e9ae |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | dedbac89-6650-5063-8daf-fdb2d546d721 |  | note | – – – – – – – – – – – – – – – – –
label | f16e7fd2-3ea4-5e06-b980-564138849cf8 |  | note | CATEGORY: HP
label | abee02ab-0f3a-5c21-ba1e-defa015e9e7f |  | note | – – – – – – – – – – – – – – – – –
label | bed15107-a396-51f6-829d-5c4b222f6b2b |  | note | RESPONSIBILITY: Nominated Authority
label | c612f2e9-85df-5798-811a-9b6dcc8f6148 |  | note | – – – – – – – – – – – – – – – – –
label | d19337af-80fd-58d3-b3cf-14c26487cba1 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3edca008-bacf-5ee6-9060-52819c5b42e1 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Working Platform certification
label | e0b63556-ee4f-5dd1-909a-7fd4bd7b35bb |  | note | REFERENCE: Piling platform design
label | 5a106df2-c6f1-5174-88c8-32124664bc0d |  | note | – – – – – – – – – – – – – – – – –
label | 214ffec4-6820-5070-bc8e-e8267d1f572c |  | note | ACCEPTANCE CRITERIA:
label | 44fdf388-06b9-5e03-960b-4ec2dc59db2b |  | note | • Satisfies minimum plant bearing pressures requirement.
label | 792d43a4-53df-5de3-b108-4ec5cff74a39 |  | note | • ATTACH: Piling Platform Certificate
label | 6128419d-85ba-5d7e-87d5-aecae35a0797 |  | note | – – – – – – – – – – – – – – – – –
label | 961f24a5-0351-5da3-b38a-7f5a7c841b3f |  | note | METHOD: Document Review
label | 2bc93b80-e817-5206-b8ba-af4a731dc38d |  | note | – – – – – – – – – – – – – – – – –
label | 02e59985-2f1b-5776-a993-3fde57ee35f2 |  | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | 7e764fb0-a55a-57cd-9907-5875431a9916 |  | note | – – – – – – – – – – – – – – – – –
label | e2f3d338-13da-5ce8-bd6a-6159cf530f26 |  | note | CATEGORY: HP
label | 1ad651c9-1d37-5668-acbc-5acb6784ddfe |  | note | – – – – – – – – – – – – – – – – –
label | a41a5ade-8cf5-5b25-80d2-ddfdfe82316b |  | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | e5f9177b-58ee-5685-abe4-ab7963f606d9 |  | note | – – – – – – – – – – – – – – – – –
label | a3ce368e-59a0-5e28-ac94-d82a53627289 |  | note | VERIFYING DOCUMENTS:
label | 37ea9857-b872-5922-bc6e-de9ef7d376b5 |  | note | • This ITP
label | cc0ce12c-e583-5eb7-866b-f8905449b72e |  | note | • Platform Certification
date | 2fc8c7ef-5774-5379-9fe9-5e9e6b1f0711 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Concrete CFA Pile Design
label | 53a75d3d-f1c6-5dee-abc7-388e5d7bfdd2 |  | note | REFERENCE:
label | 00f1d1fe-3661-5068-9bd7-290d01f937d2 |  | note | 607.01
label | bb9f2e02-c05a-5a0d-9e7c-8009bd251bee |  | note | IFC Drawings
label | fc651d42-9301-57be-9427-3eaf45a39240 |  | note | – – – – – – – – – – – – – – – – –
label | ad95baa6-a171-58bc-93c8-1999e2fec21b |  | note | ACCEPTANCE CRITERIA: Concrete CFA piles shall not be used in foundations for bridges and other structures on or over roads without the approval of the Superintendent.
text | ddf46129-1132-5f78-a3f4-86b1812d5c46 |  | textbox | Enter: Teambinder Approval number
label | 28aefae1-8796-5f80-94c4-9228e921094a |  | note | – – – – – – – – – – – – – – – – –
label | 44a96bea-390d-5db1-a08d-45462ee47421 |  | note | METHOD: Document Review
label | 1876c45b-02ea-5f58-a12c-e8cab2baed4a |  | note | – – – – – – – – – – – – – – – – –
label | 8c14a288-abf9-5db1-9977-35fae1c122fa |  | note | FREQUENCY: Where applicable, once, 4 weeks prior to the commencement of piling
label | 12ae9c6d-a1f6-5277-9c87-540380c09663 |  | note | – – – – – – – – – – – – – – – – –
label | 41e1dfb2-1c62-515e-93fa-6c7feae7b993 |  | note | CATEGORY: HP
label | 6ca52adc-0c29-5097-ab25-005d7b5353ab |  | note | – – – – – – – – – – – – – – – – –
label | 8306cf6a-121d-523d-9eb7-f5e6338f9743 |  | note | RESPONSIBILITY: Nominated Authority
label | 8c9ed939-9394-5a54-8dd2-073b4c57ad4c |  | note | – – – – – – – – – – – – – – – – –
label | 8001036e-30b9-5f83-8487-9c09751669f4 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1dcaeaa8-5cdd-5d26-a411-3deb430bf052 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Piling Operations Work Procedure
label | 8dd3e6f7-8991-5693-9b27-9c5f60863dde |  | note | REFERENCE: 606.03 (a)
label | c16a0ca2-612a-5133-b870-13cffb87b9ba |  | note | – – – – – – – – – – – – – – – – –
label | 4be58bac-163f-5738-aab5-9c94eb51b47c |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | 5709bc97-c884-5e50-b3e9-7e084d6ee105 |  | textbox | Enter: Teambinder Approval number
label | 1fc6d3c0-f428-54a2-948e-a80423d7f794 |  | note | – – – – – – – – – – – – – – – – –
label | fe88073e-d76a-5107-b03d-a74ee544f63f |  | note | METHOD: Document Review
label | c770750d-a667-596a-9007-274f2670a892 |  | note | – – – – – – – – – – – – – – – – –
label | 0bb7a3fb-b6fd-58c7-adf9-bbac79d099ba |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | 6ef99a5f-23ad-5f4b-9644-f094ff3b551b |  | note | – – – – – – – – – – – – – – – – –
label | 3a3b6efc-b3c6-523c-96a6-2b763c4f21bc |  | note | CATEGORY: HP
label | e26958c6-d2c8-59c1-9d88-9fb9bacc4dbe |  | note | – – – – – – – – – – – – – – – – –
label | b6cbead7-f9c4-5b58-a3bc-9099571995e4 |  | note | RESPONSIBILITY: Nominated Authority
label | dc823df7-22ec-52aa-907f-1cb488d8a5f9 |  | note | – – – – – – – – – – – – – – – – –
label | 0bffaff7-8973-593e-b0e1-146d84be7c72 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 0585a0ad-e8c9-52f4-981e-4e9fe0c70729 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Casting Under Water Procedure
label | adaf1930-341c-5ca4-aa2a-6581b9aa7d42 |  | note | REFERENCE: 607.04
label | 9a1c2593-ebbb-5334-bf20-c452ff1806a1 |  | note | – – – – – – – – – – – – – – – – –
label | cbdadcf4-eb9c-5551-ab74-975a8c5405d3 |  | note | ACCEPTANCE CRITERIA:
label | f29f9d68-5cba-5430-a784-abe61fdfbe33 |  | note | • Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority.
text | 3c12781b-39c1-5b38-ada5-b08d6ff04aa4 |  | textbox | Enter: Teambinder Approval number
label | 5dee6dcf-9002-5513-80de-8c2c2add1375 |  | note | • Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 450fd102-b4ce-52f4-b67f-b4f135ca325f |  | note | – – – – – – – – – – – – – – – – –
label | 0c81f093-6e12-5053-9bf4-4ee5b6385bb1 |  | note | METHOD: Document Review
label | ef53942d-a378-5beb-a227-a864254c0de1 |  | note | – – – – – – – – – – – – – – – – –
label | a1f18d49-71c4-51bc-aad4-5abbcf398daf |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | 4b38b0ac-45a7-5fa1-b0a0-2744f18a225b |  | note | – – – – – – – – – – – – – – – – –
label | 41647c13-2d4a-5b1f-9615-f939d2f9a73b |  | note | CATEGORY: HP
label | 3479660c-dbe8-5c79-83d2-2c93bd051e93 |  | note | – – – – – – – – – – – – – – – – –
label | 01acfe2e-152e-5878-a759-e3f95c7b014e |  | note | RESPONSIBILITY: Nominated Authority
label | a8e1112a-4101-5a9f-943a-4a604cc54f71 |  | note | – – – – – – – – – – – – – – – – –
label | 87275e00-5a93-5f2a-aa3f-a5a7ef3e324f |  | note | VERIFYING DOCUMENTS: This ITP
date | 32edc87a-f08a-5bbd-be24-918f3226e1a7 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Dynamic Pile Testing Procedure
label | fa11e898-2ae0-56cc-898a-46e23bac7d2e |  | note | REFERENCE: 607.07
label | 2236c0cb-63ea-5f63-8e20-39dd269e474b |  | note | – – – – – – – – – – – – – – – – –
label | 10b00ece-f10e-5d05-8500-dc8f8d6a3c53 |  | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | e50c1d6b-7844-5e7d-8b7b-0b7d8ce03d80 |  | textbox | Enter: Teambinder Approval number
label | e5e8ed85-cb67-5e0b-9e00-dc079188247a |  | note | – – – – – – – – – – – – – – – – –
label | e53c48e9-5dda-5eee-a48f-7cfd31d41e26 |  | note | METHOD: Document Review
label | ab393b26-b5b4-52d5-adf0-e2c299fcc187 |  | note | – – – – – – – – – – – – – – – – –
label | a07d0533-3df3-5940-bc33-b1857116021d |  | note | FREQUENCY: Once, prior to testing
label | 5fc58fa0-0d79-5cc8-8909-903a5d73759a |  | note | – – – – – – – – – – – – – – – – –
label | 14024248-73a9-5b55-b1cc-b5a667484b3e |  | note | CATEGORY: HP
label | 956394d3-c147-58ba-bc49-157d15d17515 |  | note | – – – – – – – – – – – – – – – – –
label | 29f4143e-b62b-57c6-89f3-710b4e65ef32 |  | note | RESPONSIBILITY: Nominated Authority
label | 189d1a13-889c-5173-9e94-7808cd796671 |  | note | – – – – – – – – – – – – – – – – –
label | 1ddedc7c-9105-5a8d-9c60-fb26ae9aedee |  | note | VERIFYING DOCUMENTS: This ITP
date | 07522865-dbb1-5abf-aa9b-568ec56ec1a4 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Pre-qualified Pile Testing Consultant
label | 788ada95-27c5-50fa-80b8-be6b7e910288 |  | note | REFERENCE: 607.07
label | b611765d-7bc3-5e72-ae1b-938cea159663 |  | note | – – – – – – – – – – – – – – – – –
label | aadc1e89-c5d8-5cbe-b030-da7da2fa1db9 |  | note | ACCEPTANCE CRITERIA:
label | b994803f-5670-5693-85ef-f4201023b125 |  | note | • All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | 9c6e8a25-6619-5f8f-b2f3-d9b1a19d530a |  | note | • Details of the consultant to be submitted for review to the Nominated Authority.
text | c3f4bf77-9642-559d-8740-77dc39203aca |  | textbox | Enter: Teambinder Approval number
label | ec7c5367-0e11-5164-b8d7-215a69cc0561 |  | note | – – – – – – – – – – – – – – – – –
label | 6170bf87-b6b0-521e-8ccf-da8d3a5affe1 |  | note | METHOD: Document Review
label | 251bbea5-bd4e-577f-904e-a5c36f270897 |  | note | – – – – – – – – – – – – – – – – –
label | c00e152c-344c-55fd-91bc-59fa67316b4a |  | note | FREQUENCY: Once, 2 weeks prior to testing
label | 9c915265-5db8-57e4-8624-c93b1780917c |  | note | – – – – – – – – – – – – – – – – –
label | 4c3db164-5867-5277-896f-aae60d1ceab6 |  | note | CATEGORY: HP
label | 89877b47-2eb7-5b85-903d-d2f185984bc5 |  | note | – – – – – – – – – – – – – – – – –
label | 242621d7-0878-5ae4-a2b4-73570b82f38b |  | note | RESPONSIBILITY: Nominated Authority
label | 8f40897b-59cd-53a2-b7da-c5e8022fbc1a |  | note | – – – – – – – – – – – – – – – – –
label | afac3d60-ceaa-5b63-b3cc-8a1ef53b6eff |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 38d8f895-c53f-5f3a-aa81-4b9217ab7be3 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Reinforcement Welding Specifications & Qualifications
label | c2a6103e-1117-54c3-bd3f-b8fe70b3435d |  | note | REFERENCE:
label | 06e7d05c-b184-5ead-8c0f-accc386321ad |  | note | 611.13 (a)
label | 2e171c67-7a17-5a87-b666-81a320090ee8 |  | note | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
label | 59a3a6f4-4409-5862-a5e3-99dadabe1cb1 |  | note | 611.14 (b)
label | 65848c5f-4b3a-5aaa-a9d9-c0c49122c2e6 |  | note | – – – – – – – – – – – – – – – – –
label | 0b58663d-6fef-51eb-a786-6471378d3894 |  | note | ACCEPTANCE CRITERIA: Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
text | ccced383-60ec-5b49-adc4-f7d22c788287 |  | textbox | Enter: Teambinder Approval number
label | 873c70f6-c2dc-5a45-94a7-4137745aba81 |  | note | – – – – – – – – – – – – – – – – –
label | d2d3f91b-11db-5d4d-8658-7e2bdde03b51 |  | note | METHOD: Document Review
label | 835d64a5-8630-54a5-a85e-5855838d8f4d |  | note | – – – – – – – – – – – – – – – – –
label | 294fdc0e-1f51-59b2-a30d-1c25244e5e4a |  | note | FREQUENCY: Where applicable, once, prior to welding
label | 5a1e1f0b-94b0-5150-bee5-664e1d16b662 |  | note | – – – – – – – – – – – – – – – – –
label | 9b30ba64-c36a-5aab-b38d-54fe892a62c5 |  | note | CATEGORY: HP
label | d3b5a346-f8a8-50b7-a42c-3cb8db26281d |  | note | – – – – – – – – – – – – – – – – –
label | 36cc2f55-76c2-5cdc-b635-5fba2488c564 |  | note | RESPONSIBILITY: Nominated Authority
label | 4090a053-f7dc-5d42-be19-4df2dd34d1fc |  | note | – – – – – – – – – – – – – – – – –
label | f913e472-edbb-57fd-83d7-5b4b071516c4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 879c350f-bd62-5d59-b298-8421f286ca8c |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 8302eeab-9c92-5ed5-aeb4-ad268bc74c40 |  | note | REFERENCE: MRPA Quality Management Plan
label | 599df973-8d56-5efb-8b4e-93ed11d1805e |  | note | – – – – – – – – – – – – – – – – –
label | 068d7f47-7473-59f2-b6de-8f3752d6e8d3 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 15120bad-5da1-5e76-92ad-a7d1f16a8f3d |  | note | – – – – – – – – – – – – – – – – –
label | 3261dd6c-dfa0-5f52-9ae0-d7c20841c2c1 |  | note | METHOD: Document Review
label | 82f5eb63-6921-5d57-9e33-bb28552db41b |  | note | – – – – – – – – – – – – – – – – –
label | f6a7ebd8-2678-5bff-9e02-0f77d8003b96 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 046db6e5-928c-5627-84a5-933a82e81cf9 |  | note | – – – – – – – – – – – – – – – – –
label | f447ce0e-70f9-5e08-ae38-611530345a27 |  | note | CATEGORY: HP*
label | 669ad4e8-2bad-5c43-a00b-de0bed470544 |  | note | – – – – – – – – – – – – – – – – –
label | 58173127-3081-5a2e-bd67-e18abaec5173 |  | note | RESPONSIBILITY: All
label | 4cbd6afd-9620-5694-9999-65b06c0c08b9 |  | note | – – – – – – – – – – – – – – – – –
label | 780bb735-8028-5925-8d1a-150e92689f5b |  | note | VERIFYING DOCUMENTS: This ITP
date | 5bb6c783-3c40-5756-aeff-daeb30fc283c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | b45bbb32-07c0-5931-bd7a-23f0a6bc9cc8 |  | note | REFERENCE:
label | 306f490f-d869-5a1a-aa5b-be8c803a2af3 |  | note | IFC Drawings
label | 6b1a2e93-114e-59b2-af65-affbf445eff4 |  | note | 607.06 (a )
label | e0d1a6dc-605a-560c-bf01-a2a5c851e5c1 |  | note | – – – – – – – – – – – – – – – – –
label | 3779384e-9434-5ed1-a5d6-a04890ff7c94 |  | note | ACCEPTANCE CRITERIA:
label | 576b9328-dc02-5d89-aa90-9cd579096680 |  | note | • Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | 0624a16b-e9a8-573f-a295-3df8f000d1ad |  | note | • Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | 76cd3dde-d7d6-5cb2-8960-cef5e53d086a |  | note | – – – – – – – – – – – – – – – – –
label | f10a042e-df12-5d84-9eab-5a16fee74acb |  | note | METHOD:
label | 8292fd6f-1447-51a6-b7d6-ad5c4f65dc1e |  | note | • Measure
label | 96419738-7015-5f15-9c04-124beb25dc0c |  | note | • Visual
label | bd720192-a0ee-5a03-992b-2e9ccada0a51 |  | note | – – – – – – – – – – – – – – – – –
label | 5ed23c66-a65f-5365-9515-198c571bd089 |  | note | FREQUENCY: Each pile
label | e3d52180-e50e-55c6-bbf2-80a4198abf20 |  | note | – – – – – – – – – – – – – – – – –
label | 2c6ae7a2-1650-5df1-ba02-dede6b1839f7 |  | note | CATEGORY: IP
label | 4d5bf8c0-bcc6-5657-b4d7-da4c1b230ab7 |  | note | – – – – – – – – – – – – – – – – –
label | b16c38a4-292a-59fe-99c0-2d87190d771e |  | note | RESPONSIBILITY:
label | 3ed2cd5f-dc8a-51c5-84e6-bac46553656b |  | note | • Surveyor
label | 1ced7f52-19a7-5f2c-b0ce-283c39697543 |  | note | • SE/PE/SPE
label | 231182e8-6dd0-5ed5-8820-7b3ad7abb97a |  | note | – – – – – – – – – – – – – – – – –
label | d2581f63-3ecc-57b2-bb05-58b70c304167 |  | note | VERIFYING DOCUMENTS: This ITP
date | 01c03029-12ba-5faa-ae92-b7abf547f174 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | 1d64cdb3-027e-58b8-9ce9-9e226690c2ee |  | note | REFERENCE: 607.05
label | 8c6ccfc8-8e6e-5505-9a10-3476eaa84cb3 |  | note | – – – – – – – – – – – – – – – – –
label | 6b6c829e-eac7-5762-b7c4-7f9c1a1da551 |  | note | ACCEPTANCE CRITERIA:
label | d2bd5f92-2320-54e4-98d2-aaff52067904 |  | note | • Pile construction shall not result in damage to adjacent newly cast piles due to ground vibration.
label | 677f2e83-3b76-53cd-9099-33464305d338 |  | note | • Pile excavation shall not commence within 2 metres or three pile diameters (whichever is the greater) of a newly cast pile until the concrete in the newly cast pile has attained a strength of 15 Mpa
label | 064456fb-daf5-52fd-833c-a040b008b4a1 |  | note | – – – – – – – – – – – – – – – – –
label | c45d1635-3ace-5877-9b23-229fbc11c967 |  | note | METHOD:
label | 960a68d3-c459-5044-871d-1f96e7a4ec79 |  | note | • Measure
label | 43cef934-a07d-5754-b6bd-a42cc10fe0ca |  | note | • Visual
label | 3ae0e3a7-4b22-5e8f-8f30-971ceca5f721 |  | note | – – – – – – – – – – – – – – – – –
label | 393ca6d8-87bf-5655-a8c2-b8da1ae9cf2e |  | note | FREQUENCY: Each pile
label | 44d5ac73-4fbd-5c64-a805-d7a44cf9b98d |  | note | – – – – – – – – – – – – – – – – –
label | af307444-7c0c-5039-8e7c-09f632fd1bd1 |  | note | CATEGORY: HP*
label | 7bc8e781-1b23-557b-9516-e7eb2c67357d |  | note | – – – – – – – – – – – – – – – – –
label | 52a498e0-b698-5458-9036-ad20ce22944f |  | note | RESPONSIBILITY: SPE/PE
label | 96a733bf-171d-532a-b4bb-ce1abb3391b0 |  | note | – – – – – – – – – – – – – – – – –
label | a9639976-9f8b-53cf-a4b2-3bb7df2d0c6e |  | note | VERIFYING DOCUMENTS: This ITP
date | 8b44bc78-4df6-52b8-b782-398c7a243648 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Reinforcement - Inspection
label | a317cc07-4c31-5101-8a6a-a5bf585088a4 |  | note | REFERENCE:
label | 704ee794-d7ff-5e36-9047-aa68723ccd0f |  | note | IFC Drawings
label | 58d841e4-4b6f-5f48-9257-79151c34ecd3 |  | note | 611.06
label | c4679b0b-9d4a-5849-b149-3d9bbd61dc1b |  | note | 611.09
label | 7afb3a5f-68d7-52e8-b770-09dbc2127557 |  | note | 611.10
label | 75a4e45c-2be6-538f-9918-4788142c1743 |  | note | 611.11
label | 7969bbc6-e371-5872-b839-fa26491ca880 |  | note | 611.12
label | 434c010f-434f-5148-9805-51442ba596ff |  | note | – – – – – – – – – – – – – – – – –
label | 6cd9e403-507c-5074-b814-e99f2f197d60 |  | note | ACCEPTANCE CRITERIA:
label | d79f2ba9-c416-5fb8-b024-846142230387 |  | note | • The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | b9e4b6c3-9cc5-5cf6-acd2-5f399feb3446 |  | note | • Projecting reinforcement is the correct length and location.
label | 4f0c5ec8-4a96-5a82-a970-17eee18de989 |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | e4d48e21-acf3-5a3b-8cd7-d22e3e6184d5 |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | e56cc545-3984-5dd1-bcc6-05bf2c76a436 |  | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 85e20c21-4d32-59c6-be4c-a900970b705c |  | note | • The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
label | 71c484d9-91c6-59a7-913d-e2492505d438 |  | note | – – – – – – – – – – – – – – – – –
label | 8ad2d9d0-9182-5e30-9dca-7617a26c82c7 |  | note | METHOD:
label | d8a382c7-449a-54c3-b8e2-6b0ba800754b |  | note | • Measure
label | 39976510-4255-5558-b19b-c465a462ab99 |  | note | • Visual
label | 6435c942-cd71-526b-bef7-536ec966e38b |  | note | – – – – – – – – – – – – – – – – –
label | 4c9ad975-cdfb-5d54-92cf-e9c1272483a2 |  | note | FREQUENCY: Each pile
label | 0388204d-35cc-57ef-a3bd-cd408d589426 |  | note | – – – – – – – – – – – – – – – – –
label | 15b82808-81d1-5dca-bb33-f661da694f3b |  | note | CATEGORY: IP
label | f355eb71-a635-50e0-9886-f2b44fa0e411 |  | note | – – – – – – – – – – – – – – – – –
label | 6259d671-7169-53d9-bc36-e3b3f4d14a76 |  | note | RESPONSIBILITY:
label | c8128fde-d471-5210-b1d6-e1be535beeb0 |  | note | • Foreman
label | ef2bec1b-521c-5a95-9e78-65802320f696 |  | note | • SE/PE/SPE
label | 63f5b36b-2022-591f-8b1d-48b692f03997 |  | note | – – – – – – – – – – – – – – – – –
label | 6e83879b-9c0c-520e-a16c-67c18f9dec3b |  | note | VERIFYING DOCUMENTS: This ITP
date | 68a3f965-218e-5569-98d1-8d302f04b79d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Reinforcement - Electrical Continuity
label | 4691d0bc-5b63-5918-af84-88b4ed8da2bd |  | note | REFERENCE:
label | 48bf9f5e-bb57-5865-910c-d744546060ff |  | note | IFC Drawings
label | 3a9b409f-899d-5f98-b589-3b6dd566fa11 |  | note | 610.29 (d)
label | 376d8ef0-ba56-5ce8-a22a-16608553e4f4 |  | note | 610.43
label | f34a45c0-afa9-5595-99bf-46a8991d7456 |  | note | – – – – – – – – – – – – – – – – –
label | d79e96bf-da9e-5e68-8d4e-e0373f384fc0 |  | note | ACCEPTANCE CRITERIA:
label | 5556b74b-3f04-5894-8679-d068339da059 |  | note | • Pile reinforcement cage to be made electrically continuous by:
label | 5e525698-dc16-5e9c-8dfa-ee118dc60d55 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 3333ecbf-d145-5721-a4ca-ed5de17a6f6e |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | c2762147-3a6a-5ce0-b476-04991b2763b2 |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | bbcc0550-5479-52ad-92b7-1e8b6c9aa05e |  | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | e25fa60c-b638-5ceb-82af-b03ff06aafaa |  | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | 23a77bff-413d-5b97-b49d-d40713df65b3 |  | note | – – – – – – – – – – – – – – – – –
label | 00c94f15-caf3-5996-8bb0-3960297a154f |  | note | METHOD:
label | 45c3bde8-cf59-5cee-b0f2-c34ff6a756e7 |  | note | • Measure
label | 993feaa7-7e0b-5897-86ea-d697c78de124 |  | note | • Visual
label | 866f4884-915d-50b8-83d6-ee331c6de02e |  | note | – – – – – – – – – – – – – – – – –
label | 901807b6-6971-5dfb-855f-236595a6cc2a |  | note | FREQUENCY: Where applicable, each pile
label | 263f00de-a20b-564c-9e6a-2b94f0f412f3 |  | note | – – – – – – – – – – – – – – – – –
label | d7ef6155-f64f-5c7c-9221-b8a91801b9b3 |  | note | CATEGORY: IP
label | 8fb3cbd3-6182-5e9c-bf1d-9259426dd22b |  | note | – – – – – – – – – – – – – – – – –
label | fbbb9d26-a6d1-5a45-a4fa-68c1e8467161 |  | note | RESPONSIBILITY:
label | 4e1235fa-bf8e-5dc7-9117-19db9b262676 |  | note | • Earthing Engineer
label | 7adb1e9c-23f0-53e4-ad9c-e1e001767198 |  | note | • SE/PE/SPE
label | f7809c77-b2b2-513b-a5b9-587ae7a08cbb |  | note | – – – – – – – – – – – – – – – – –
label | 5ab7dbbf-22cb-51f4-8512-c86672c88137 |  | note | VERIFYING DOCUMENTS: This ITP
date | 471af065-cc9f-5c03-8aed-2eeae4f6a89b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Augering Operations
label | a921fdb3-e9e5-5e9b-8398-c01208c3524c |  | note | REFERENCE:
label | ca7cb904-6bdd-5c31-bc20-cdea9c869343 |  | note | IFC Drawings
label | d7d5d020-c066-5f71-9e5b-905205b0aa8a |  | note | 607.04
label | 3ba9bdd2-0f8e-5d7d-944e-16cf846aa29b |  | note | – – – – – – – – – – – – – – – – –
label | 3d9f7769-4cd7-5513-8a3c-f450fada6116 |  | note | ACCEPTANCE CRITERIA:
label | 220d0c7e-4b01-50f1-acd5-3aa16e278270 |  | note | • Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | 56e19195-e209-53d7-a8b9-ac86e0f18c63 |  | note | • The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process.
label | 622069a3-6c0c-5d1a-85df-0517e8e464aa |  | note | • Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
label | f34c9a33-0137-5a77-bb87-3ffdaacbf6c9 |  | note | – – – – – – – – – – – – – – – – –
label | 027f3f2f-861e-5a69-a282-bba3f7459a62 |  | note | METHOD:
label | aedfa89c-77ea-5dcd-80c0-464606d812c4 |  | note | • Measure
label | 7e15b893-83dc-51e4-bb02-961a2a6af3e9 |  | note | • Visual
label | cc8e3298-63c2-5175-a250-2b1920713499 |  | note | – – – – – – – – – – – – – – – – –
label | b59de282-e015-574a-af72-8964e7789b43 |  | note | FREQUENCY: Each pile
label | 85c956ef-d04a-5636-a6cd-02095e6c9487 |  | note | – – – – – – – – – – – – – – – – –
label | ef471b89-63f8-50a2-8489-0c6c11543e3d |  | note | CATEGORY: IP
label | 2ad93007-4bee-5794-b13f-9f9a20d54e25 |  | note | – – – – – – – – – – – – – – – – –
label | ee20b9a7-762c-54db-a4a7-4890b62538a7 |  | note | RESPONSIBILITY:
label | f93ed0fb-1f9b-55b7-a48e-3e641a519a3e |  | note | • Surveyor
label | 594bafd6-b6b9-54db-8af2-21bd1c532211 |  | note | • SE/PE/SPE
label | 4e23f366-151c-5d4f-a24b-b79f0964a8e1 |  | note | – – – – – – – – – – – – – – – – –
label | cfb57e13-c643-5bde-a158-4fb6e48335e3 |  | note | VERIFYING DOCUMENTS: This ITP
date | 984ffcac-1de4-51db-88fc-c22bec98d789 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Inspection of Excavated Material
label | 5a83c3f2-49ed-56b8-9044-e2cff5ce3fdc |  | note | REFERENCE: 607.04
label | 9dac00db-3dbc-5882-8ec3-91e2dcece376 |  | note | – – – – – – – – – – – – – – – – –
label | 66351ea9-0f28-5615-9ac6-3f97cdeb1e8d |  | note | ACCEPTANCE CRITERIA:
label | 2611c619-80c5-5a16-8c0d-13fc4327db44 |  | note | • Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | 2ebd6efd-8e9c-57d7-a2fa-83b3016df793 |  | note | • Attach: Geotechnical Field Sheet or Report
label | 27eed6a3-96cd-5299-8acc-e12ccc20bd76 |  | note | – – – – – – – – – – – – – – – – –
label | 458ace61-0fa4-52ad-9552-fcc92387bd34 |  | note | METHOD:
label | 198dd56e-b7ac-52d7-98ab-6677eb617627 |  | note | • Measure
label | 4144e958-a656-5202-8589-b6b62f0aa1ce |  | note | • Visual
label | 09c5a053-74d1-58c1-8b65-06858d0f5795 |  | note | – – – – – – – – – – – – – – – – –
label | d6e09971-9e10-50b1-aec3-ecdef1a8b876 |  | note | FREQUENCY: Each pile
label | fdf1a5f4-f2cc-5ec2-8480-e214fc993887 |  | note | – – – – – – – – – – – – – – – – –
label | 8b7aff69-9e5c-5b73-9640-13f76b650c5b |  | note | CATEGORY: HP
label | db2c8fa2-650b-52b9-9670-e61b5d149377 |  | note | – – – – – – – – – – – – – – – – –
label | e65617e9-14e0-5bf5-bea2-8fc44fb49219 |  | note | RESPONSIBILITY: Geotechnical Engineer
label | 402e9f50-f852-58cd-ac4c-42de7230be31 |  | note | – – – – – – – – – – – – – – – – –
label | df67e5d8-1536-5322-bf03-021aebf78b8a |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 4c17856c-adb2-5176-bf86-00f6d91fac47 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 Increase in Depth Beyond Design
label | a855b737-51fc-5b03-9fa9-342834f74eee |  | note | REFERENCE:
label | 71c7e04e-219f-5dd7-b9fd-38e962698242 |  | note | 607.04 (a - d)
label | 25eeb2aa-76cb-5f6c-a39f-fdbde7ac1f4c |  | note | Piling Operations Work Procedure
label | b5ac6dce-1073-5653-b08f-bae7037c0cf5 |  | note | – – – – – – – – – – – – – – – – –
label | 3f6a9713-4ac9-5269-a6b1-280f887ba7f1 |  | note | ACCEPTANCE CRITERIA:
label | 369ce681-dbd0-5a93-8575-c5fad3402ba8 |  | note | • Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity.
label | 576383c3-35d6-5223-b606-2acd065600ee |  | note | • A full account of the changes shall be submitted for approval to the Nominated Authority:
label | bcf8c6ed-018a-5ac5-8d43-8122c1f91de1 |  | note | • Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
label | 4d45158b-59ad-579c-98cc-06228cceae80 |  | note | – – – – – – – – – – – – – – – – –
label | 2e037ad5-f085-5a02-9771-2cebebdf4241 |  | note | METHOD:
label | 7fe612b5-c064-530c-9c7a-7984070cf3e7 |  | note | • Measure
label | 6ce4b377-19af-5925-8a21-c5f7245347d5 |  | note | • Document Review
label | 632bc1dd-7505-58e2-9569-64dc570b3475 |  | note | – – – – – – – – – – – – – – – – –
label | 184d1af8-8201-5cbe-9706-f8baa8932722 |  | note | FREQUENCY: Where applicable
label | 87f69df9-003a-5c35-8ba7-b8aa41ea3ade |  | note | – – – – – – – – – – – – – – – – –
label | b778d35e-7f6d-5712-a9b7-dfb7bd71b18f |  | note | CATEGORY: HP
label | a3cfc03a-813a-5b34-b832-faf00a80e306 |  | note | – – – – – – – – – – – – – – – – –
label | 0f075fb2-8eb4-55a2-a1b2-da052abd3f10 |  | note | RESPONSIBILITY: Geotechnical Engineer
label | 13b37d69-50b0-591c-90db-10dd95c560d2 |  | note | – – – – – – – – – – – – – – – – –
label | 5797aefa-a794-56d7-8e7d-e9f4d9b7c6c8 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 62f1e31e-48a1-593c-8304-0cbf06cfb97e |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Weather Conditions & Evaporation Limits
label | ae0c29d3-aa4e-5418-b8f8-c866285802f8 |  | note | REFERENCE:
label | 1e4423e9-f903-5bbf-a21e-9562dffe212a |  | note | Hot and/or Cold Weather Concreting Procedure
label | 5c8cb70e-b527-5173-803f-f63af5af7fec |  | note | 610.17
label | 5066f9bb-29c2-5d14-aa39-e32287a06c0f |  | note | 610.17 (a) & (e)
label | 5c7a8d98-9e18-5e47-85a2-62c4abbf8639 |  | note | Table 610.171
label | 8cd017f2-7721-5d92-a380-41d8fcedae2d |  | note | – – – – – – – – – – – – – – – – –
label | 6ca1427a-264d-5aeb-ab1d-3681881d5c2d |  | note | ACCEPTANCE CRITERIA:
label | 439ccf99-836b-5a20-854d-61a0e6e35d8c |  | note | • All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | eb303a5b-5422-5766-8bdb-69be56a1991c |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | c75d1bd1-94c9-5462-9d47-a9e1e125dbd9 |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | fd01ecd5-8240-5d64-bd71-aa45525d3ab4 |  | note | • Record: Required information on the Concrete Pour Record.
label | 2c83067c-601b-52c2-bac4-75d1e7a041cc |  | note | – – – – – – – – – – – – – – – – –
label | 5912be87-7efe-5580-82d2-833fad139b0e |  | note | METHOD:
label | 39f932e5-5bbb-5db7-9d37-7ad9ff9060dd |  | note | • Measure
label | 4ad23dc0-0a6f-5d48-97a1-d0641d57d432 |  | note | • Visual
label | 1f584f6f-72b3-58a7-8df7-7409bf28883c |  | note | – – – – – – – – – – – – – – – – –
label | fabded33-5ef7-5195-bc39-16b7567e3a49 |  | note | FREQUENCY: Each pile
label | 519358c4-953c-514c-81cc-487036dc626f |  | note | – – – – – – – – – – – – – – – – –
label | b00227e8-f367-5790-856c-ae4bbe45af68 |  | note | CATEGORY: IP
label | 7ef9aa49-1211-53b1-9700-c61614103741 |  | note | – – – – – – – – – – – – – – – – –
label | bdea8d1a-6c5a-5269-bbd0-17df9e119840 |  | note | RESPONSIBILITY:
label | 23150932-2c09-5134-8794-fe04d1e14037 |  | note | • Foreman
label | 745eda9d-ad46-5cae-a503-e089c7bfa6a7 |  | note | • SE/PE/SPE
label | f238c93c-132c-567a-859f-3e5bb595d1c9 |  | note | – – – – – – – – – – – – – – – – –
label | 5b0f68cf-9085-5f13-a72d-7ae9ebbc4887 |  | note | VERIFYING DOCUMENTS: This ITP
date | f5f62cf1-d161-539b-9b74-50a2b94a626d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Concrete Testing - Sampling Frequency
label | 7967d8be-3f57-5bb9-8a06-b25832a3f251 |  | note | REFERENCE:
label | 56b5cb11-2918-5c6b-a7fc-e6ad049322e4 |  | note | Site Sampling & Testing Procedure
label | 19f965dd-fff0-518c-8f30-fd0a30393a22 |  | note | 610.16 (b)
label | 2bd06326-37a1-50b0-bb63-590b22db6db8 |  | note | Table 610.161
label | 475ffe7f-8364-5409-938c-2d82ec3190de |  | note | – – – – – – – – – – – – – – – – –
label | c68e842d-3664-5d16-8fc4-51c863ec9908 |  | note | ACCEPTANCE CRITERIA:
label | f2710a07-d46f-539b-8f14-2d9ac7a7d5f1 |  | note | • Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 2b40e9b9-19ab-52c0-99d5-b7be9e4e86b3 |  | note | 0m3 to 10m3 = 1 sample
label | 0986ea46-fe81-55bf-bd4c-4986160cf962 |  | note | 10m3 to 25m3 = 2 samples
label | 71e54ada-afcf-55d7-98f9-148fbd472c63 |  | note | 25m3 to 50m3 = 3 samples
label | 63ebf705-414d-52e1-b3a3-5c4d1f2f01f8 |  | note | 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
label | 1d9daf79-4272-5e23-bfec-1ee823b5e453 |  | note | ○ For each additional 50m3 and additional sample shall be taken.
label | f305a696-c919-5881-965b-ecc06059f342 |  | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | 54012a0c-cd2d-5767-a760-1ed21fdc5dff |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 2198f436-e4ef-514b-87ed-0d1f4c542b75 |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 32d2e0c7-3bb9-5d3a-b769-5c3eaaaa9220 |  | note | • Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 77dad52a-d886-538c-aa71-8e81f0dfaea5 |  | note | • Record: Required information on the Concrete Pour Record.
label | c2df939c-cf73-56b9-99a6-6aca6d1bb0f5 |  | note | – – – – – – – – – – – – – – – – –
label | 374909e6-96f7-5f5a-93dd-e86e4e731e3a |  | note | METHOD: Test
label | 5161e2c5-b1c6-5f6b-b4e4-eea719c5a3b2 |  | note | – – – – – – – – – – – – – – – – –
label | be6f720a-2f56-5f56-be82-db8c958e57e9 |  | note | FREQUENCY: Each pile
label | 54a7c94f-8e47-50ea-b87d-9299f00fdaf4 |  | note | – – – – – – – – – – – – – – – – –
label | e52a3e8c-c948-5cd0-af47-9159e5c38d4d |  | note | CATEGORY: IP
label | 0640c8fc-8741-59a2-a798-dcdafeb1b2eb |  | note | – – – – – – – – – – – – – – – – –
label | ac3f5774-7c35-52a1-8d52-4cfd022d587f |  | note | RESPONSIBILITY:
label | 097df871-4080-58fa-aebf-8f521c535b67 |  | note | • Concrete Tester
label | 5953449c-b379-5857-ae53-07984ab93ad0 |  | note | • Foreman
label | 1831fdba-04ed-5c95-8f2e-0655c217d0f7 |  | note | • SE/PE/SPE
label | edeb24c7-0be0-58f3-bdff-f21bc6ced4e3 |  | note | – – – – – – – – – – – – – – – – –
label | 159f0875-3416-574e-b2c9-6d81d410c560 |  | note | VERIFYING DOCUMENTS: This ITP
date | a667bdd8-f43f-5732-a346-e6f18416a77c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Concrete Testing - Spread, Passability & Viscosity
label | d5e355c3-22f9-52cc-b809-f4c1ed76585f |  | note | REFERENCE: 610.13 (b)
label | ecff2e8d-026c-5151-b80f-eadcf3e8e0fd |  | note | – – – – – – – – – – – – – – – – –
label | bd0de7cb-a5c8-5c1d-a884-230cf704e170 |  | note | ACCEPTANCE CRITERIA:
label | 00d2db4e-4341-5b13-aafa-b6e42e952acc |  | note | • Spread range = 550mm to 750mm
label | 000c2286-64c6-577d-b251-38b809c434e9 |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 28021447-fb10-5e4e-9c56-65c4e2377f7b |  | note | • Passability = ≤10mm (aggregate height differential)
label | 7db46fee-0622-51dd-b812-7911d526f4bc |  | note | • Record: Required information on the Concrete Pour Record.
label | a0520175-9d5b-5b14-868a-c5d981fabe8d |  | note | – – – – – – – – – – – – – – – – –
label | 815c7f3c-9344-51fb-bfa8-8c77b8a38f8a |  | note | METHOD: Test
label | 8a77633e-1840-57fb-b887-7a9f8d6f2973 |  | note | – – – – – – – – – – – – – – – – –
label | 02ae2ee9-286a-5b4e-b4ad-4d78f3fee441 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 192bdff0-8e4d-5c7c-b4ee-de4c3f958cf8 |  | note | – – – – – – – – – – – – – – – – –
label | 0bb5974c-1f0b-520b-a18f-84d4225344e1 |  | note | CATEGORY: IP
label | 93a69d61-fe63-5291-9ce0-e7ab74f5b682 |  | note | – – – – – – – – – – – – – – – – –
label | bb6ddc24-8bde-585f-a7a5-26530198548a |  | note | RESPONSIBILITY: Concrete Tester
label | 6d6ed1b8-77c2-5de8-af6d-dd676abfb44f |  | note | – – – – – – – – – – – – – – – – –
label | d16bbabb-4f8e-5517-8d5c-e42af874dfb5 |  | note | VERIFYING DOCUMENTS: This ITP
date | eb3c5250-7317-5a0d-92bf-f543cb7b2ebb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Compressive Strength Cylinders
label | f596f955-3d1d-5182-a9f2-1ec1b1a1ec83 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16
label | 939ed0e4-4e99-5dff-8c7a-b0a72bd34979 |  | note | – – – – – – – – – – – – – – – – –
label | 197a5ff2-cf1c-5fd4-90d4-7a40c462c3ad |  | note | ACCEPTANCE CRITERIA:
label | 4d932947-d527-57e9-9da5-db917263027e |  | note | • Correct quantity of cylinders manufactured per sample.
label | d79dfd7e-9754-5db1-8a42-f030f2283c3d |  | note | • Record: Required information on the Concrete Pour Record.
label | 5190d5ec-7672-531a-a00a-110b3923f9d4 |  | note | – – – – – – – – – – – – – – – – –
label | c7bb4aed-9674-5ac1-9f77-9c55233c5843 |  | note | METHOD: Test
label | c0d861aa-f6af-5172-b64a-6968078be6ee |  | note | – – – – – – – – – – – – – – – – –
label | 7c003c06-7956-570a-90ff-4b098f85e492 |  | note | FREQUENCY: Each sample
label | 998e5ad6-c4f6-5a73-9779-a21aa679162b |  | note | – – – – – – – – – – – – – – – – –
label | 63e066a4-f27e-5f2b-bced-524794556e33 |  | note | CATEGORY: IP
label | 87aea465-b9dd-5ecf-8850-50e98fc6156d |  | note | – – – – – – – – – – – – – – – – –
label | 463d5e38-b224-56b1-872b-e07e4886072f |  | note | RESPONSIBILITY: Concrete Tester
label | d203b627-5522-5180-949f-81877647550f |  | note | – – – – – – – – – – – – – – – – –
label | b2f49e6a-fd81-5e13-a44f-c2958c239f66 |  | note | VERIFYING DOCUMENTS: This ITP
date | 37d4856a-e143-5915-98f5-cf558e8f5175 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Placement & Compaction
label | 0ec5fa26-0da7-576c-a858-0edf998d907d |  | note | REFERENCE:
label | f69b9d2e-1f89-5db6-aa87-081193826c69 |  | note | Piling Operations Work Procedure
label | bf071714-e565-5fb0-8088-0b66570c0553 |  | note | 610.18 (a) & (b)
label | f53fdbf8-af6c-545c-ad04-d9842e93eed9 |  | note | 610.18 (d) (i)
label | 25fc0217-47d9-51b7-b802-aeee4060c0a4 |  | note | 607.04
label | 6e77fbc1-8ecc-59cd-95a4-f3472516e993 |  | note | – – – – – – – – – – – – – – – – –
label | de388217-acb1-58cb-94e3-3e19f1615c31 |  | note | ACCEPTANCE CRITERIA:
label | f7e0cff1-0e3e-5d75-bfc1-50f2cd45e3cd |  | note | • All concrete batches are traceable.
label | 9a1956c3-2f9d-5f1a-91cc-0874b5bbd9f7 |  | note | • The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted.
label | 8382a9b7-75ca-5c1a-a3ec-992d41afca41 |  | note | • The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions.
label | 4fe5445f-badb-5a55-a9ee-be5829addf33 |  | note | • Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete.
label | c7fe3dd3-4f0b-57bd-9386-5560e4817e37 |  | note | • Concrete shall not be dropped freely from a height exceeding two metres
label | d84088ac-76bb-5f96-9af1-18459bafaac4 |  | note | • Record: Required information on the Concrete Pour Record.
label | 0c7a8c59-20b8-5787-bedf-853edbac8a57 |  | note | • Attach: Concrete Pour Record
label | cd33c132-d30a-5130-bec5-c9da5e8c790c |  | note | • Attach: Concrete Dockets
label | 86051b19-70c2-5fbd-8837-dacbf5805d98 |  | note | – – – – – – – – – – – – – – – – –
label | e70d4b0c-4533-56f5-8ec3-a3336341bbd1 |  | note | METHOD: Visual
label | a4754f56-37db-5641-9b61-34529fc7eab7 |  | note | – – – – – – – – – – – – – – – – –
label | 8b8e45c9-3473-5e9b-8ecb-32130947876c |  | note | FREQUENCY: Each load
label | 8723953f-eda8-5384-baca-943f459af1a1 |  | note | – – – – – – – – – – – – – – – – –
label | 47efc508-9a07-5895-9800-e2b354fe070c |  | note | CATEGORY: SP
label | 60ac7446-428c-5ca7-9370-b1d8b6fbd9f7 |  | note | – – – – – – – – – – – – – – – – –
label | ab6a4a8d-5808-58f4-8ddf-cfa713d6834f |  | note | RESPONSIBILITY:
label | 337cd787-cc13-5f3b-aff6-130e48442ea7 |  | note | • Foreman
label | 1a53db02-61bb-5abb-a3f2-f51cb8cc411f |  | note | • SE/PE/SPE
label | ea4972cc-9421-5951-94ef-831ef1594ef7 |  | note | – – – – – – – – – – – – – – – – –
label | 4c6bf13d-c485-5b23-b1d2-00a41cc02e14 |  | note | VERIFYING DOCUMENTS: -
date | 3cf4ff1a-7a68-53eb-ab7b-ef8495a2bf4d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Reinforcement - Placement
label | 1cb698d0-16ea-5d2b-87d5-f76d74477aad |  | note | REFERENCE:
label | afb08fd3-376b-5bc0-80af-bb238b3acd20 |  | note | IFC Drawings
label | 9e680f1a-666c-5edd-ace5-7da0068e2c6c |  | note | 607.04
label | 43faab1a-d765-595e-b929-d02705d875c8 |  | note | – – – – – – – – – – – – – – – – –
label | 8b7560fa-31dc-525c-b042-e696c8c8a96c |  | note | ACCEPTANCE CRITERIA:
label | dcc03959-ee8e-5c56-8744-7067baacdeb6 |  | note | • The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
label | 1407a344-42aa-5c25-8faf-00ff1c2a9786 |  | note | • Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
label | 38726d7f-acdb-5baf-a2fb-3d0432b17f2e |  | note | • If the cage cannot be positioned into its final level, the pile shall be rejected.
label | 1c6a29d5-8c62-58b5-a325-8ed459f1e8fd |  | note | – – – – – – – – – – – – – – – – –
label | 8e376135-1b57-5307-b7c6-51c39fb85741 |  | note | METHOD:
label | 4d48fdfc-5ef5-573e-ac53-fafb82903dd7 |  | note | • Measure
label | baae46b1-becd-592c-85b3-ccc05352b4c9 |  | note | • Visual
label | 5ce2e790-b230-5e4a-863c-f02b75b87509 |  | note | – – – – – – – – – – – – – – – – –
label | 7e20dbd2-3bfd-5d2a-b698-1f68f31c9453 |  | note | FREQUENCY: Each pile
label | e763bbfd-2310-5b6b-8ae8-bd00496ecd94 |  | note | – – – – – – – – – – – – – – – – –
label | 8f3341e3-2116-560d-aadb-24ced8b28117 |  | note | CATEGORY: IP
label | f6a43967-6328-5305-8292-50a77b05c2e5 |  | note | – – – – – – – – – – – – – – – – –
label | 0d9c4cb2-59c2-5a89-83be-4796dffb1218 |  | note | RESPONSIBILITY:
label | 5c5c9e9a-55b8-5d3a-b085-3ba808850a84 |  | note | • Foreman
label | 1386bda7-f2fa-5c01-a23f-a07b3cc6fd68 |  | note | • SE/PE/SPE
label | 752d8156-2365-5770-a14d-d43a93afbff5 |  | note | – – – – – – – – – – – – – – – – –
label | 706b675f-1c2d-5c4f-9ca8-05b627b41991 |  | note | VERIFYING DOCUMENTS: This ITP
date | 012ab89c-3272-5e94-b7e3-ef40ba19c058 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Cast-in Items
label | e7de76c3-770d-505a-ab50-d7510b8078b6 |  | note | REFERENCE:
label | 2c6525f8-507e-5303-9172-5399a2b5f742 |  | note | IFC Drawings
label | ceca86a3-8a3a-546f-a48e-17833f75c57a |  | note | 610.46 (a), Table 610.462 (November 2018)
label | 7732b4c7-df30-5179-8416-1d80bb625441 |  | note | 610.47 (a), Table 610.472 (March/June 2019)
label | c01f0ec0-9ed3-5e72-8753-4eb4770b795b |  | note | AS3810.1 Table 3.3.6.2
label | c4320404-6aa6-5ade-b36f-f3287bd6e3fd |  | note | – – – – – – – – – – – – – – – – –
label | ef1bd43a-2ab8-5f02-9c85-74e51ebfb455 |  | note | ACCEPTANCE CRITERIA:
label | 483dcf48-f027-5bb2-b11d-0b52f3391436 |  | note | • All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement.
label | 9e49a545-a47d-5f02-842e-4d62bab7798e |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 7c04f32e-a147-5dd6-858f-d561ee43ed1e |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 5cf0d91d-a586-50ab-9524-561c751d683e |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 93d31c42-4e0c-5518-aa0e-5e5cc0641806 |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 98c9cca6-cb96-504b-ae76-0891c577acdf |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 0bb35c35-6759-5dc6-9adc-901f77c2bb7b |  | note | ii. Running dimensions of a group of the above = ±6mm
label | f53fb823-f6b8-5a0f-b67f-b7e3bf1aeedd |  | note | iii. Ducts and conduit location = ±12mm
label | e4298a1a-ab6f-545f-9902-1d7783f06bed |  | note | iv. Diameter of ducts and conduits = ±3mm
label | a6936804-f4ed-5473-aefc-c65774bdca8f |  | note | – – – – – – – – – – – – – – – – –
label | 751b549e-703a-51aa-8e13-08be24130edd |  | note | METHOD:
label | ba874f29-db59-50e6-bce3-6ead5058d2f2 |  | note | • Measure
label | 72682f0e-1ad2-5ab2-a3ff-c62041b02bbb |  | note | • Visual
label | e08d3602-c4c7-5da6-986c-02894d8170d2 |  | note | – – – – – – – – – – – – – – – – –
label | 0fa2d6ba-dbfc-5629-8a6a-4a67a26b168d |  | note | FREQUENCY: Where applicable, each pile
label | fb74863b-f70d-508d-90df-3ee6c2276316 |  | note | – – – – – – – – – – – – – – – – –
label | 9a9bf514-3be1-59f9-b699-57652e9e0eac |  | note | CATEGORY: IP
label | b47689bd-1883-5307-929f-19e439b6ea13 |  | note | – – – – – – – – – – – – – – – – –
label | fd0694e6-3eea-560e-9682-bea2a2d8c5f0 |  | note | RESPONSIBILITY:
label | 22a32e95-d2e5-5170-929c-a554cee3b332 |  | note | • Foreman
label | da9e6e84-0196-5740-87d3-0863871d1169 |  | note | • SE/PE/SPE
label | 94eac999-fda0-5b0b-9171-22cf13eaaa83 |  | note | – – – – – – – – – – – – – – – – –
label | b39b4ce0-c3f6-5f8b-a33c-6cd09b23ea38 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6c11d63e-9f75-57c5-832b-db96418f0277 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | 82bd880c-d9d8-5726-bc10-4e2056cccfa1 |  | note | REFERENCE:
label | 09c73800-63b6-5979-81cb-fd961726ec01 |  | note | IFC Drawings
label | a0593b7f-2020-59b8-a675-3d5d7f640b8e |  | note | AS2159 Clause 7.2.2 - 3
label | ae7a6d23-16d7-5faf-8638-230052fcd703 |  | note | 607.04
label | 456ec6b1-b425-5fbe-918c-6ca2e78f9547 |  | note | – – – – – – – – – – – – – – – – –
label | 8f5d9a85-d326-5c47-8d42-4ed7fbe0d5a9 |  | note | ACCEPTANCE CRITERIA:
label | cac0dff9-e1c6-58f0-8136-7f8f03a69cf1 |  | note | • Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | b8739967-9753-50ba-9594-b43ac82a52de |  | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | 36a10a42-fd7b-51ee-97ec-4af28f9d2010 |  | note | • Any weak or damaged concrete shall be removed back to sound concrete.
label | 9cfe4231-2910-53f2-a551-922c902229b8 |  | note | – – – – – – – – – – – – – – – – –
label | aed9b7a5-9984-5943-b633-8da9c090b4f1 |  | note | METHOD:
label | b6473fc2-0fed-5146-ac6d-5c50748905c8 |  | note | • Measure
label | 5717891c-854d-5e1b-8463-72ffdd11dd4d |  | note | • Visual
label | 7e41eb21-2ed8-5980-9478-5263b982c540 |  | note | – – – – – – – – – – – – – – – – –
label | ea1e29a3-cbd2-58db-a5eb-724bf6af3959 |  | note | FREQUENCY: Where applicable, each pile
label | 6de5062c-d9ad-5a68-a589-bfccb1116ed9 |  | note | – – – – – – – – – – – – – – – – –
label | 5e874c96-15f9-5624-88e4-219fb6441073 |  | note | CATEGORY: IP
label | cb994f1b-605d-5d9f-99e9-165423037d48 |  | note | – – – – – – – – – – – – – – – – –
label | 6a2fa62f-a4b8-5b89-8ec1-cb14517e7ac5 |  | note | RESPONSIBILITY: SE/PE/SPE
label | b154257a-7e4d-5063-aaa5-ba8bf72b8aa5 |  | note | – – – – – – – – – – – – – – – – –
label | 9ccc8c54-15dd-5677-9b89-aeaeff2be9fa |  | note | VERIFYING DOCUMENTS: This ITP
date | e47ea150-51f9-5b35-8901-9103d6a4bdad |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | af471017-df3b-55fc-bb09-d3733561516b |  | note | REFERENCE:
label | 8aa23041-53ac-5c97-bb49-124338dcc74a |  | note | IFC Drawings
label | 0d86b191-5a16-5e8c-879d-fe7837973f31 |  | note | Table 610.05.051
label | 304c27d0-0b95-57c6-a35b-ea4dede68dae |  | note | 610.16 (g)
label | 7b28e8a1-22c6-5081-9303-1cac6a1bd853 |  | note | – – – – – – – – – – – – – – – – –
label | c19fc38f-5c20-5a94-a8a8-f398d926036d |  | note | ACCEPTANCE CRITERIA:
label | 851ada47-8a1c-5c56-a0c2-a0b3041f90a9 |  | note | • 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | d2a784cb-a72d-5067-924c-b213c66cd269 |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 0b898c91-f3ef-54f4-85e6-11c0a05a2deb |  | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 25d4360f-d89c-507b-936c-5b3a9d37a5f6 |  | note | • Attach: Compressive Strength Test Results
label | f5499451-bde1-5ff5-9e1a-078e878edd14 |  | note | – – – – – – – – – – – – – – – – –
label | 259189d0-0fdb-58c2-98ca-264e69165285 |  | note | METHOD: Document Review
label | e9d6b5d2-8932-5b32-8eea-38012180606d |  | note | – – – – – – – – – – – – – – – – –
label | a024356d-8df6-558e-b2e6-93b7d2faa7a3 |  | note | FREQUENCY: Each cylinder
label | b8beb025-c470-51f6-a44d-820373d33c93 |  | note | – – – – – – – – – – – – – – – – –
label | 8a727588-8b73-5612-90e1-a98d2bee2a81 |  | note | CATEGORY: IP
label | 728ec606-f936-5c99-9de5-0c56e82e6ed8 |  | note | – – – – – – – – – – – – – – – – –
label | d9e5d656-9705-5c70-a046-0e0b580ccf53 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 878055bc-3262-5ccc-88b3-e73c3ea8ed0f |  | note | – – – – – – – – – – – – – – – – –
label | 6f283d6b-dcca-59c6-8369-26a49bd8be87 |  | note | VERIFYING DOCUMENTS: This ITP
date | b7f264fd-0351-5b40-9639-e49be0dd80d0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 30c45b8f-4c5a-5e70-a883-c1a898c9c447 |  | note | REFERENCE:
label | 00431c98-bcaf-5f0f-9860-2f9b78659d26 |  | note | 607.07
label | 6880e675-d994-5d1d-a7b6-499c606f4095 |  | note | AS2159 Clause 8.8
label | 5bf6e88c-2144-54e4-93e1-5d78dd0eae3c |  | note | – – – – – – – – – – – – – – – – –
label | bfc8d353-f54e-57ff-b59d-bd28db43c2a3 |  | note | ACCEPTANCE CRITERIA:
label | fab6b7e3-3799-5beb-8f0c-fb7a494f40aa |  | note | • Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | 607e08b6-49e5-5cd6-82ea-6349b9e1f0fb |  | note | • Cross-sectional area = ≥90%
label | c048a9a2-8f67-5b85-8a53-261150a30f10 |  | note | • Attach: Pile Integrity Test Report
label | b8852c2f-7b5d-5251-b42c-7a9afb9406d9 |  | note | – – – – – – – – – – – – – – – – –
label | 46d54237-8b21-59a2-9d9d-82a381f092ce |  | note | METHOD: Document Review
label | c20bcba8-985c-5880-a6c4-e6fb1886a48d |  | note | – – – – – – – – – – – – – – – – –
label | 1700e520-132c-596b-9bc2-5788819b453f |  | note | FREQUENCY: Each pile
label | a9abe824-a6b8-57e8-91ca-8722002243fb |  | note | – – – – – – – – – – – – – – – – –
label | fbe72c67-5ae6-530d-a709-544e29c81e6d |  | note | CATEGORY: IP
label | 2c9f90ed-153d-53db-a146-2aa8afdb0751 |  | note | – – – – – – – – – – – – – – – – –
label | 2f72e8fb-47ad-5203-a678-7583b7b88b57 |  | note | RESPONSIBILITY:
label | 4de2e63e-19f2-585e-b3d8-5e59b378f715 |  | note | • Testing Consultant
label | 20870682-b9fc-58f4-8729-025ec2ca561b |  | note | • SE/PE/SPE
label | eb1bbf41-a752-5e22-afe9-b25d0d3aefc0 |  | note | – – – – – – – – – – – – – – – – –
label | 281b6870-8f1a-584a-acbc-306d653b9dc8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 66a6190f-ef54-5ce9-9e8c-c5b7d5b48f42 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Dynamic Pile Testing
label | aa903e34-0384-5d85-a1c1-0f5a6430e7b5 |  | note | REFERENCE:
label | f45c19bd-6f7a-534b-b4a5-0b22e6132d18 |  | note | 607.07 (b)
label | 0854a456-1f17-5a0e-91df-9ecf92038b3a |  | note | AS2159 Clause 8.7
label | 25001f79-e485-5a05-a0a4-4b89f29c0995 |  | note | – – – – – – – – – – – – – – – – –
label | 62e6ba13-8957-5fa0-9f19-7ee099d6beab |  | note | ACCEPTANCE CRITERIA:
label | 3e545087-18b5-5aa7-a538-bfb39339c126 |  | note | • Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | 0487dfe9-407a-5d9f-bd92-875aa88186d9 |  | note | • Measured Ultimate capacity = ≥ values on IFC drawings
label | 5046b69a-46a1-51c7-9320-081169d2cac9 |  | note | • Attach: Dynamic Pile Test Report
label | 0abba7d0-f500-59ba-93a9-7d0e3a1aaab6 |  | note | – – – – – – – – – – – – – – – – –
label | 7aa6f84f-7dc7-5730-b491-7b43518b172d |  | note | METHOD: Document Review
label | ac22590a-22dd-5a55-93d0-22f5078b1bf4 |  | note | – – – – – – – – – – – – – – – – –
label | 02c066a4-e840-5f9c-97cf-77923de04da8 |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
label | b31bf7e8-e774-5171-a0d3-3d97eb77de40 |  | note | – – – – – – – – – – – – – – – – –
label | 18f101cf-e60d-5372-987a-d1c294fdf636 |  | note | CATEGORY: IP
label | 147e0887-49e8-5bd6-b7ae-cd0e87e6ce6f |  | note | – – – – – – – – – – – – – – – – –
label | a6087886-a7f8-5c16-9a7a-ce559df1fe73 |  | note | RESPONSIBILITY:
label | 30d10fd0-a141-5567-ac6c-2e0c4ca75c7a |  | note | • Testing Consultant
label | be709147-ef28-55ef-ad49-c1c827eec6c9 |  | note | • SE/PE/SPE
label | 70258f9a-ceb5-54de-b55f-482873159124 |  | note | – – – – – – – – – – – – – – – – –
label | 0c7ee861-30d1-57a2-91d2-b757c48dd30b |  | note | VERIFYING DOCUMENTS: This ITP
date | 3618b106-4261-55e8-9489-62de5a72142e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 As-built Survey
label | 65f3a90e-3c25-5cfe-9935-a5f6d5795ebf |  | note | REFERENCE:
label | d2dfc16a-f709-5b69-b5a7-a0723a84b310 |  | note | IFC Drawings
label | f03a8b4e-6279-5634-87fa-579b1957ea70 |  | note | 607.06 (a & b)
label | ec00adde-b345-57a4-8348-c227fe87db75 |  | note | AS2159 Clause 7.2.2
label | c98eec6b-a9e6-5880-8a5b-36050df736af |  | note | – – – – – – – – – – – – – – – – –
label | b073c97b-be1b-5b1c-901b-618f69e74aca |  | note | ACCEPTANCE CRITERIA:
label | a2d39406-9e8f-57a9-9a3f-0efefc977e55 |  | note | • The following tolerances apply to piles:
label | a8fd3f9b-3f05-59e0-aae8-b0da18f722ed |  | note | i. Centre of pile head plan location = ±75mm
label | f34313fa-b0e7-535b-a868-24b7c4541478 |  | note | ii. Variance from vertical or rake = 1:50
label | 41a28fc2-957a-51c6-a7c1-c2e9c95a6d91 |  | note | iii. Irregularities in straightness = 1:100
label | 8b861926-1af4-5f19-a48b-5e6095321bbe |  | note | iv. RL = ±25mm
label | 879cc518-6e2d-5be5-bf00-c8fa3e70234c |  | note | • Attach: Survey As-builts / Survey Report
label | e060c0f8-72c8-5dab-81be-e3318b31e6d8 |  | note | – – – – – – – – – – – – – – – – –
label | 3d42751c-3195-5c0f-9ae5-8182f9fede7f |  | note | METHOD: Document Review
label | f0d64098-e671-500a-85fd-1f4c889948f7 |  | note | – – – – – – – – – – – – – – – – –
label | 5c86c900-0e2a-5b59-8c76-979a7bb5d039 |  | note | FREQUENCY: Each pile
label | 1a578bc1-377a-5290-86bf-db86e51906cc |  | note | – – – – – – – – – – – – – – – – –
label | 188fe300-e28d-5ba1-87d2-5e0042b9f5ba |  | note | CATEGORY: IP
label | 30ce56f9-a385-5336-86a5-1b14770601d3 |  | note | – – – – – – – – – – – – – – – – –
label | ab248bcc-1a96-53a7-b5b0-3f05c4bc26e1 |  | note | RESPONSIBILITY:
label | 51de8547-3225-5b03-9544-a05d867bb37c |  | note | • Surveyor
label | 8c18e31f-5592-55ef-907a-f58227e2d8e9 |  | note | • SE/PE/SPE
label | 99faf69c-25f8-5cfa-ae74-923b2c3b9ae0 |  | note | – – – – – – – – – – – – – – – – –
label | 3af3cb09-72eb-55ae-a720-52a817d4f23a |  | note | VERIFYING DOCUMENTS: This ITP
date | 7e8f2162-2ed5-51d9-99de-1c61a367f2d8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Non-conformance Report (NCR) Closure
label | 829edf49-6b0c-598c-8902-b25319af2de3 |  | note | REFERENCE: MRPA Quality Management Plan
label | ded89642-63c9-50be-9d48-b140c230e69a |  | note | – – – – – – – – – – – – – – – – –
label | 7895ba42-8f35-5704-b18a-2473ec8099e0 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 2e97aa56-cda3-5655-afc6-f3345854e92b |  | note | – – – – – – – – – – – – – – – – –
label | ae9a14d9-5f16-51d5-a836-4d0dafd82530 |  | note | METHOD: Document Review
label | 92f01a70-f1b7-5e18-8f52-5dcff51e4ab9 |  | note | – – – – – – – – – – – – – – – – –
label | 46603636-1513-5519-9f06-e1fbae93f456 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | d2db17aa-dd73-5915-beaa-a4f86c9cb8b6 |  | note | – – – – – – – – – – – – – – – – –
label | ff1361ef-3f08-536a-a8b9-c2950301dc16 |  | note | CATEGORY: HP*
label | 407241dd-58cc-591a-8153-b735b9a69352 |  | note | – – – – – – – – – – – – – – – – –
label | cac8e338-73fd-5e96-adf0-d5d24b861094 |  | note | RESPONSIBILITY: SE/PE/SPE
label | fd36a17b-065a-568e-b715-7c7a5728e5ac |  | note | – – – – – – – – – – – – – – – – –
label | 11e821e2-4a07-5ae5-a47c-db419cdbb221 |  | note | VERIFYING DOCUMENTS: This ITP
date | f731fdbe-b344-57ff-9c58-7838c5848fed |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | e1420f2c-78d3-5b3b-ba7a-1cdd08d7d278 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 6ad3d4db-5758-5799-adc6-c68a1311ebe6 |  | textbox | Name:
text | d67a933e-3ebf-5859-8190-fb9719da2fb0 |  | textbox | Position:
date | ffd24bed-16b9-57e3-a900-431932d2e06d |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-RAIL-CAMMS-MTM-Conduit and Pit-Temporary Rev 0 | itp |  |  |  | Yes | ITP-RAIL-CAMMS-MTM-Conduit and Pit-Temporary Rev 0 | e26fd899-d5df-4826-b4bb-9b9e8026dd3a
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | bf90ed8b-6c22-519d-98d8-06d4df0cfe66 |  | note | Document Title: ITP-RAIL-CAMMS-MTM-Conduit and Pit-Temporary
label | e3efe4a6-a8b7-5484-9057-58bf1a511256 |  | note | ITP Description: Conduit and Pits-Temporary
label | 9686f80d-a5e2-5138-8a00-3ab5dd783b0d |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 6c8425a7-21f0-561d-9158-afc2f2989546 |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | 7eab6f97-9dad-50c8-9632-1071756b7ca0 |  | note | Revision Number: 0
label | fe3bb6eb-4410-54c3-9394-d28273527773 |  | note | Revision Date: 30/08/2020
label | 3249d04b-26cd-5581-8099-8f4c10be896f |  | note | ITP created by: Isaac El Zayat
label | 81da3fe3-0c6c-5be1-9106-1549665c1658 |  | note | ITP approved for use by: Victor Mira
label | 37fd94cf-db1d-5775-a897-842b57534db7 |  | note | 1.1 - Non Dependent
label | 9189eda9-272b-52f3-b609-fe0a91081196 |  | note | Reference Documents:
label | 0e598221-7b94-5b4c-8740-58f974e03f18 |  | note | IFC Drawings
label | 8ed73d3c-20d4-5533-a29c-5177f63830be |  | note | L1-CHE-STD-043 (VRIOGS 012.2.1)
label | 985b610d-0718-5160-b307-2efd6ad9cfeb |  | note | Australian Standards
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Conduits
label | 1f566cf8-66d2-5744-8945-097202548107 |  | note | REFERENCE:
label | 282c901d-82ba-54c5-b505-094c4790234b |  | note | Comms Conduit: AS/ACIF S008:2006
label | abe96299-4472-5374-b1b8-7615d62d8fdb |  | note | LV Conduit: AS/NZS 3000 - 2000.
label | 10c3dfbc-4d42-59fd-8026-7676d8b33d17 |  | note | L1-CHE-STD-043
label | f1548a03-bc0e-5c54-b6ad-c707827be01d |  | note | ---------------------------------
label | 4e945a6d-57bf-5d36-baae-63498a59ca54 |  | note | ACCEPTANCE CRITERIA:
label | f94a93fa-ee2f-5b71-8a07-1a645b80cf38 |  | note | Comms Conduits: 100Ø (114mm OD), PVC White comms conduit 4.6mm wall thickness
label | 86667eb5-a06b-563d-aff8-c0e8d5a6648a |  | note | LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
label | a2c16ffd-39a1-5a13-b155-3b85b5e7691d |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 32ac31d5-d38d-5171-a784-90a1039dca7e |  | note | ---------------------------------
label | a6bb60ac-bb24-5634-bf00-c145d8fadd49 |  | note | METHOD: Document Review
label | 3408d780-0cc4-528f-b921-188f279bec93 |  | note | ---------------------------------
label | 83524a85-5cdf-58c6-a0ae-d708788496cb |  | note | FREQUENCY: Each Material Type, Each Delivery
label | c708a368-4c2c-585c-b115-6ff70f20037e |  | note | ---------------------------------
label | a67b8cee-6be4-5715-b82f-363c69c23bbb |  | note | CATEGORY: IP
label | 83b42dec-5bd9-569e-a56e-a5600b021000 |  | note | ---------------------------------
label | 290ddaac-b44d-5343-8c16-24e54a88fce3 |  | note | RESPONSIBILITY: SE/PE
label | eae9e3da-6a95-5ae5-8ce3-517c8825c2cd |  | note | ---------------------------------
label | cd8af18e-5501-538a-a330-0043d79c0a95 |  | note | VERIFYING DOCUMENTS:
label | 4687bd63-6601-523f-b498-106e471de7bc |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | 28827953-f9e5-573c-bdca-f8596c754335 |  | note | Attach delivery dockets
date | be89af8b-ed39-5fc2-8378-136f21032f66 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Pits and Pit Lids
label | 6d506818-b57a-5bb3-b548-2116ce2d3926 |  | note | REFERENCE:
label | 3235a2fe-c980-5ab4-ba37-5405e5663256 |  | note | IFC Drawings
label | d03300ee-348b-5310-8a35-7b9141bb86a6 |  | note | L1-CHE-STD-043
label | 00e0f5eb-ccad-54a3-88f1-c0f12e287045 |  | note | ---------------------------------
label | 1e27fb79-1634-51a8-a53a-49ef2ce02832 |  | note | ACCEPTANCE CRITERIA:
label | 0b76269e-13f6-56d5-bc7d-fe1658e49bde |  | note | • Pits: Concrete Pits to be made as per AS 3600
label | b3b28c53-38d6-56e3-9903-5649947518c2 |  | note | • Pit Lids: Pit Covers shall comply with AS3996-2006
label | 7a9ad78b-9283-557f-982a-21e3fe5ff662 |  | note | Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
label | 7b92b1e1-d438-524a-bbec-a2a2b15aba7b |  | note | LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
label | 068d700f-8048-58fb-b7d7-f612d8a75da0 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 182797c4-8ed7-5b01-8a0e-ecd6cb77f3e2 |  | note | ---------------------------------
label | 60fc863d-0931-5c85-af09-85cc1d34d025 |  | note | METHOD: Document Review
label | 86f14eb0-ab1f-58e3-8061-d2831001d0cd |  | note | ---------------------------------
label | af73d79d-4717-5dac-a8e6-4183eadeb155 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 47e3cbba-3db0-5389-a34e-b277a1a8e7cd |  | note | ---------------------------------
label | cf60397e-6755-5484-9997-432723e9a66e |  | note | CATEGORY: IP
label | ab79d8cc-260b-58ae-8d4d-9b6cce91bc38 |  | note | ---------------------------------
label | d61f3992-2d52-566e-92ab-22e02ab16b16 |  | note | RESPONSIBILITY: SE/PE
label | c28b82e3-cf53-5ebe-9660-8e00dcafe351 |  | note | ---------------------------------
label | ca609459-7050-50eb-94ca-6a4116066f4e |  | note | VERIFYING DOCUMENTS:
label | a7d8627c-fbee-5c90-8ea7-88ea1afe0ec1 |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | a701adbb-9f0c-5634-a171-f957317ddd9e |  | note | Attach delivery dockets
label | e7dd3031-e21a-5a79-a196-3e65bf00d58e |  | note | Attach Precast Birth Cert
date | 572096ac-5605-5c68-b5d2-ea29d7c8d8f3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Warning/Marker Tape
label | ef80df02-bb70-5ce4-b2e1-48046e974050 |  | note | REFERENCE:
label | a558872b-0457-5402-941a-237de154f372 |  | note | IFC Drawings
label | 9d15a2f1-e17d-5c10-b4ec-8536003986c6 |  | note | L1-CHE-STD-043 6.4
label | 16abf6ed-ec92-56aa-9bba-0b2d3407c14d |  | note | ---------------------------------
label | beba12a2-a3f2-50a8-87d6-082df0d52645 |  | note | ACCEPTANCE CRITERIA:
label | 5d9674b3-844d-5104-9988-e7eadb4f2318 |  | note | • Warning/Marker Tape:
label | 7ad77e8d-dc13-5d9b-8abf-d3987edc894e |  | note | • Above LV:
label | 9122fcfc-5c60-5356-92c7-03c8573a0bcf |  | note | 150mm minimum wide orange coloured PVC
label | 82f14355-0f0c-5582-978a-b06ff970a0a9 |  | note | ‘DANGER RAILWAY SIGNALLING CONDUITS’
label | 1e1ff94c-76d9-5a39-bcf7-bf4512db72bf |  | note | • Above Comms:
label | ae642106-478d-55d8-a443-abeb26f32317 |  | note | 75mm minimum wide white coloured PVC
label | 11bb940e-c8bc-5c73-93ac-04d20c93a7b3 |  | note | ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire
label | 2c07dbc7-ae07-54e5-a2f4-d61959f6dbf2 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 049fddd8-d588-5f29-850e-13dfa7712cb8 |  | note | ---------------------------------
label | a7e6e58a-fb40-5063-8e1b-5d8916d9e34e |  | note | METHOD: Document Review
label | d8441dd9-e4fc-513d-bc50-c3a0627eec46 |  | note | ---------------------------------
label | 784215b3-63ea-50a1-b30e-ca0caf4322a4 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | f1c19371-0429-54eb-b25f-b164a6194878 |  | note | ---------------------------------
label | 1907ae65-a1ea-50d9-b939-022f9d6c2d7f |  | note | CATEGORY: IP
label | 89ad9da6-1ed3-5e89-ad47-a8b776453c70 |  | note | ---------------------------------
label | 8b54635c-e91b-5adb-a720-23a50c6a77be |  | note | RESPONSIBILITY: SE/PE
label | 97e4a208-9f01-5fdf-b835-974c12b4d71b |  | note | ---------------------------------
label | 66335cde-18b2-51d0-b536-679628d3cd90 |  | note | VERIFYING DOCUMENTS:
label | 8547a0f4-7c1a-5096-b508-1b4f09fa9ccf |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | 92767350-2ec3-5157-9df7-70b234f3bd4b |  | note | Attach delivery dockets
date | ce026a42-24bb-52f7-94e0-e6aefe9fe6b0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Protection Barriers
label | b042269e-e45b-50fc-b8b6-20f65c79cafb |  | note | REFERENCE:
label | 1dfd535c-2e07-5259-817c-48321860f8cf |  | note | IFC Drawings
label | 449631db-a1c3-547f-ab65-16a1ce1f6372 |  | note | L1-CHE-STD-070
label | 059a40c5-88ec-5b8b-9dfe-bde3a632c876 |  | note | ---------------------------------
label | 0a34e599-0b22-5877-824b-6eb488830854 |  | note | ACCEPTANCE CRITERIA:
label | f989f733-a357-5557-bc30-86c68ac56296 |  | note | Approved plastic protective orange strip (Vinidex or type approved equivalent)
label | 8d94fd48-c6c6-5b6c-a823-b8be72cd9c79 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | cb59e849-3839-55eb-a626-aee09676f8e4 |  | note | ---------------------------------
label | 717a769a-1d87-50fb-b360-0a73b132c901 |  | note | METHOD: Document Review
label | c2dd9435-54d0-5945-8fc7-e73a6c307961 |  | note | ---------------------------------
label | 2b81e876-dee1-574b-a336-4ecf8e1a497d |  | note | FREQUENCY: Each Material Type, Each Delivery
label | f9a18784-9607-5401-9038-bd671ad71655 |  | note | ---------------------------------
label | cc1d6462-2b04-5d15-903d-35eecf86599f |  | note | CATEGORY: IP
label | 7a09221c-dd4e-59bd-abc5-90029e0aa7c6 |  | note | ---------------------------------
label | d3c0ed0c-a95d-58d8-98e7-547708c2d16a |  | note | RESPONSIBILITY: SE/PE
label | cb752997-6860-51e5-8416-d53563f024a7 |  | note | ---------------------------------
label | 0cc4748e-d2e2-5752-9f6f-d3ebd6a3da96 |  | note | VERIFYING DOCUMENTS:
label | 2f2cc158-06b2-55b2-bd94-4c67ebf3e9e9 |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | e8900088-dc30-5df7-a895-0ae044188b34 |  | note | Attach delivery dockets
date | df81d17d-cad3-58d8-b553-ec4e99c5a97a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Backfill Material
label | 03eb518f-ace3-55f4-bc20-e8b810177cec |  | note | REFERENCE:
label | 838df13f-e840-5bc5-bb05-faadffa5f714 |  | note | IFC Drawings
label | 15f91c3a-0175-5294-97ff-7427f2952281 |  | note | L1-CHE-STD-043 Section 2 Table 1
label | 6308ac7c-1685-58b0-acda-d0e81b82e6b8 |  | note | ---------------------------------
label | b025d7eb-4640-5dbe-9a53-66d2397081a1 |  | note | ACCEPTANCE CRITERIA:
label | ea95a501-1842-5cfd-9f41-34667839c1ac |  | note | Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could dmanage the conduits.
label | 31b6cb02-023e-5a79-9019-5839320eb9d3 |  | note | Inspect backfill material.
label | 8a8b0042-2c7e-5b84-a6df-b012b678c55f |  | note | Attached delivery dockets (if applicable).
label | c3af4524-c51b-5921-b28a-93b1fd70d4b1 |  | note | ---------------------------------
label | 14dd357d-5503-5292-83fa-bcddcf4e64ea |  | note | METHOD: Document Review
label | e7928602-2739-5e84-946b-fcada7bc34ca |  | note | ---------------------------------
label | 8d88bf2b-5fb2-5b45-983f-3ef9ec0f1195 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 630c937d-5108-53a9-a43a-dd68eeb1e00e |  | note | ---------------------------------
label | c6b6f3cc-6567-5a93-bb79-d68315d2637e |  | note | CATEGORY: IP
label | 75b76b75-3a0e-5efd-9afb-b71d8d0d6b1d |  | note | ---------------------------------
label | 9592a3d1-7ca6-5dd6-98ef-f8bc469a0ec0 |  | note | RESPONSIBILITY: SE/PE
label | 3c25ed44-dcd0-5b49-91d5-b649d8939368 |  | note | ---------------------------------
label | ee551379-aab1-55a9-bb57-b35da3aa72ce |  | note | VERIFYING DOCUMENTS:
label | 27b21db6-3fc6-5ee0-adb4-fb7a68206a1b |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | 7e433f6e-525b-5b6a-92a2-9e625392a5c6 |  | note | Attach delivery dockets (if applicable)
date | 0da65980-8b39-5cd1-ac59-6d480c0565e3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Bedding Sand
label | 7da71428-837b-5761-bd45-269b5bab3529 |  | note | REFERENCE:
label | d67a3be5-04f7-5c12-bd4f-8527d703d753 |  | note | IFC Drawings
label | 4e787d3a-aff5-5933-a2f3-611a7140a188 |  | note | L1-CHE-SPE-313
label | 1dd76df1-9c0f-5423-bd86-c6614a9c5cf5 |  | note | ---------------------------------
label | a5841c79-993d-5a25-8163-8748818db088 |  | note | ACCEPTANCE CRITERIA:
label | 8fb67725-85ab-5828-ab24-9e997bd961dd |  | note | • Recycled Glass Sand shall be free of any perishable matter
label | bfbb350d-6de4-5085-9000-b1676ca896d2 |  | note | • Bedding material and embedment material shall comply with the following grading requirements:
label | 3b148c46-0553-5628-bc14-eec0924065d2 |  | note | 4.75mm passing 100%
label | 5a3f4c5b-7e30-571a-b0a1-b42c5ad42451 |  | note | 2.36mm passing 75-100%
label | 0133516b-237d-5149-b379-4f12a5bc9c6b |  | note | 0.075mm passing 0-5%
label | 67ba5836-cdbb-5d64-90ad-f1b8b66fd21d |  | note | ---------------------------------
label | c84fc911-e01a-5ac0-8a0a-1e261ac460f0 |  | note | METHOD: Document Review
label | d6982ad0-4a0f-5af9-b5da-3f733e2bb82e |  | note | ---------------------------------
label | d3f6e490-5e29-5a55-a79f-228fd4d848e4 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | d989b824-47fb-5e45-9ad4-c871f45b43a8 |  | note | ---------------------------------
label | 0ab1f44b-624e-57f0-b477-cfaef3f8b5ea |  | note | CATEGORY: IP
label | b04e0233-465c-5333-9dd7-a727030bd051 |  | note | ---------------------------------
label | a6a2349f-f907-5257-9efb-0bc0adaa6006 |  | note | RESPONSIBILITY: SE/PE
label | d79ecb9f-ea0c-5ee3-b481-165f3f00495c |  | note | ---------------------------------
label | ec226a2d-6d4e-53c4-bb1f-b569b0ae4887 |  | note | VERIFYING DOCUMENTS:
label | 68d56421-39ea-522a-bd4b-7c67110cbe75 |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | c4500129-608b-5f03-a212-5891d92df0c8 |  | note | Attach delivery dockets
date | 8a2545b8-d09b-5c5e-8938-8fb7aec74f5e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Draw String
label | 62316771-d111-517d-a239-8100ae90e581 |  | note | REFERENCE:
label | 62195fa0-f41d-5d02-b396-6013661914ef |  | note | IFC Drawings
label | 4c557bc7-d6e9-52eb-8170-86148dc41832 |  | note | L1-CHE-STD-043
label | 0eb575cb-c5ba-5300-9722-a0e79a9f9514 |  | note | ---------------------------------
label | 3ac33559-cc2e-542a-aa7d-b8511dcb3386 |  | note | ACCEPTANCE CRITERIA: 6 mm diameter polypropylene blue/yellow
label | d0884ccb-f866-5520-933d-a20debd8ef32 |  | note | ---------------------------------
label | b4528542-249a-59fb-8ca6-b78b61278a87 |  | note | METHOD: Document Review
label | 3a7563ab-c157-57b0-b3f2-1faf79167672 |  | note | ---------------------------------
label | 848e59a1-0bc6-5986-8852-9a549fcb09c6 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 93b503e3-5807-51db-91d0-d466af4cb78e |  | note | ---------------------------------
label | 2c0700bd-f442-51ce-93c8-c1ac9a99285e |  | note | CATEGORY: IP
label | 467a4688-1cba-5bb6-98c6-447fdbcf3675 |  | note | ---------------------------------
label | 3d8ee86e-473e-522a-bf64-5ccaeb1e1566 |  | note | RESPONSIBILITY: SE/PE
label | 52761bb0-692b-53b3-983a-055dc0368311 |  | note | ---------------------------------
label | 95ce23d8-602f-5482-af0f-36febbc649ba |  | note | VERIFYING DOCUMENTS:
label | 0a1c78d7-ef25-5dfd-adc7-eb30db1ee5d3 |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | e9a7cb62-1225-5ee9-88b9-0958f64322b4 |  | note | Attach delivery dockets
date | 68ba1ec1-f067-5aab-b569-2fdcfecbb8e4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 Markers and Marker Posts
label | e605ce09-81e4-52d0-a204-d6c8a8a44ffd |  | note | REFERENCE:
label | 711c6409-3ae3-5c29-9aa2-b19e19e87ee0 |  | note | L1-CHE-STD-043 13.2
label | b9329ba1-2096-51ca-854d-f7a50f7c1d0c |  | note | AS 4799
label | 238fd729-2340-5742-9718-fc34e304cefa |  | note | ---------------------------------
label | eb65e49e-a034-504f-ba31-0f3b12a06774 |  | note | ACCEPTANCE CRITERIA: Markers and Marker Posts are to be manufactured in accordance with AS4799.
label | 2bd4db00-64c6-5102-b8e3-08ca9a15b43b |  | note | ---------------------------------
label | e1f31c35-a5b8-53d9-b0c9-b06389055b72 |  | note | METHOD: Document Review
label | fe32ec1e-a3bd-515f-995f-162d847e643f |  | note | ---------------------------------
label | ec0a976f-e6eb-5f40-a685-b3b236fc7af5 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 68d1a97b-c9a6-514a-9cf4-8f0f42b881de |  | note | ---------------------------------
label | 7995bc0b-dbd9-5e56-b684-3e1446187c2a |  | note | CATEGORY: IP
label | 4b8bd95f-1cd1-526c-be21-0cab09654bc5 |  | note | ---------------------------------
label | 83373d6a-8f40-5859-8786-7e0c9c31ee5f |  | note | RESPONSIBILITY: SE/PE
label | 445d8569-a71c-50ed-9365-5690e3aeccd3 |  | note | ---------------------------------
label | 0ef611c4-7935-5107-8f81-4dd25c181c66 |  | note | VERIFYING DOCUMENTS:
label | 0f9d709a-141b-5157-8641-73c5695ca12f |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | 73229cdf-0a05-5a0a-8e64-9d4dddd912c0 |  | note | Attach delivery dockets
date | a849f194-a044-5df0-892d-d6f6de1616d5 |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries-Procedures
checkpoint-group |  |  | section | Pre-construction
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out
label | 06f68b60-3771-5bc4-af5b-937b2c71f861 |  | note | REFERENCE: IFC Drawings
label | e0aeb3fc-390d-5319-bc26-eb702f28fe79 |  | note | ---------------------------------
label | a52e8b70-167a-5ecb-bc4c-95896c8b2c2f |  | note | ACCEPTANCE CRITERIA: Survey to set out trench alignment and pits, and establish construction control (alignment and level).
label | ff9bc54a-afaa-533a-afa9-cd41b31f936f |  | note | ---------------------------------
label | 7484a3c0-2d02-5504-976e-c84099794196 |  | note | METHOD: Measure, Visual
label | 116c97c4-1d48-50f2-a01f-9a9b57a8f8d3 |  | note | ---------------------------------
label | e0197d6f-6d3f-505f-b871-5499b2157419 |  | note | FREQUENCY: Each element
label | c23c9a0f-05fb-5f4a-ab7a-e957379d37ce |  | note | ---------------------------------
label | 9d9b8f00-5abd-538c-9a64-9ca3a5b3501e |  | note | CATEGORY: IP
label | cf34b04d-b6b1-5a45-8707-66ba90c175c1 |  | note | ---------------------------------
label | 4969e812-3ce0-548a-8d37-4062bbaedfa5 |  | note | RESPONSIBILITY: Surveyor, SE/Site Supervisor
label | bce4d969-e8ea-527a-9166-8f71c40bb421 |  | note | ---------------------------------
label | 85954051-6ee0-5ac5-9920-de16c2220a84 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5b16e36a-3145-5fce-a8a5-0f6e82b8f91e |  | date | Date Completed:
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 5.1 Trench Excavation
label | abf0684a-a6ae-5de0-9650-5db6da13934d |  | note | REFERENCE:
label | 5f704c55-69fb-59c4-b946-ba73613568d0 |  | note | IFC Drawings
label | f7161ea1-cd2d-55aa-9fbc-8215f1cdafb2 |  | note | L1-CHE-STD-043
label | 4f69e87d-61a3-570e-bd0a-63525e979bda |  | note | ---------------------------------
label | ffa29e0d-f66a-5070-8519-23c9bef6f3b8 |  | note | ACCEPTANCE CRITERIA:
label | 7d563da8-6a23-5a00-9b56-99448b787f10 |  | note | Trench profile and depth as per IFC drawings.
label | 692616c9-2dfa-5c99-8afb-f8737472dc99 |  | note | The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
label | 92330e20-d6cd-5822-80b5-f3de7b3b3d4e |  | note | The floor of the trench shall be level and free from all loose sharp objects; such as stones or rock of any type, or size, or rail ballast.
label | c0e6f3b5-0070-51fd-8eb9-1c68623bbccb |  | note | ---------------------------------
label | a4847ad8-a464-5523-a088-218df4067a1b |  | note | METHOD: Measure, Visual
label | 6c6c635d-50d7-5389-8554-552f96124ab8 |  | note | ---------------------------------
label | d8a06271-513d-5321-ab28-6bc369098aa7 |  | note | FREQUENCY: Each lot
label | e848d48a-4d07-5936-8e9f-09313c753d91 |  | note | ---------------------------------
label | 65188492-cd61-5d53-91c7-c059feb371cb |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 95e703a0-e9fc-5ffa-844b-04ea252a080d |  | note | ---------------------------------
label | 60e3b842-42da-5cb7-971b-07d0f23721bc |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 226772e8-30bf-54a6-bc9b-a8d8c40c4ced |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Trench Stability
label | d7a00b18-a3c0-5e83-be8f-16300ec12764 |  | note | REFERENCE:
label | 688aa16e-4f27-56c4-95bf-c2ad48695967 |  | note | L1-CHE-SPE-070
label | 8480fa36-e475-50ac-ba54-0fd6a47c1cea |  | note | L1-CHE-STD-043
label | 76030813-cbdb-5fe0-9910-b74ea55076e8 |  | note | L1-CHE-STD-070
label | e8269ead-d349-5491-ae6d-7401bb05d3d6 |  | note | IFC Drawings
label | 8da17f0f-5d46-577b-8ad2-c7c8c7b87ba9 |  | note | MRPA standards
label | d603c5d9-72ef-5ca4-a1b5-fef736485928 |  | note | ---------------------------------
label | 5e3146ac-52de-5094-967e-79b0b5925208 |  | note | ACCEPTANCE CRITERIA:
label | aff49d7d-69e1-55fe-88c9-61ff3663e3d6 |  | note | Trench stability check:
label | 1a346432-87fe-5e4e-9f26-be525cdc1362 |  | note | – Shoring,
label | 8715a2f4-3885-598a-8437-b76d7ec48859 |  | note | – benching
label | 300eec64-38c0-5b27-8403-a46d2589af61 |  | note | – geotech signoff
label | b8c441cc-b004-5fb0-8801-6f5d4f1709d6 |  | note | ---------------------------------
label | 0d29295e-e21e-5d64-bc3f-2c8e235b7446 |  | note | METHOD: Visual, Document Review
label | 5422e6e9-fc9c-5128-b033-6ec827a9c7a2 |  | note | ---------------------------------
label | e7964096-a528-5833-a9ca-5f9e842ec8d9 |  | note | FREQUENCY: Each lot
label | 759e1232-ae97-56a4-914b-3493dfd1ab64 |  | note | ---------------------------------
label | 8f348d03-a637-5d64-8fe5-8c2f65e7c88c |  | note | CATEGORY: IP
label | 1a39db78-83a0-5915-bb33-5adc6cafad30 |  | note | ---------------------------------
label | 93da1aa2-8248-5be3-810c-ea83b04e710e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ae7bca71-465c-55cd-b03b-1269a2373f01 |  | note | ---------------------------------
label | d147143c-0b28-5152-8be2-81bc8bdac88b |  | note | VERIFYING DOCUMENTS: Sign ITP
date | b6dcb368-7230-5831-a849-e62c986472ae |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Conduit-Bedding Sand
label | cf2b6b15-f6bd-5d2a-b3de-058134edf203 |  | note | REFERENCE:
label | b634d083-9662-5a0f-b78b-48dc838b5cd5 |  | note | IFC Drawings
label | 1ff8437d-9064-504d-a7d8-fb75813c6e3d |  | note | L1-CHE-STD-043
label | eddf0766-01f0-57c9-bc30-2b70409c9077 |  | note | ---------------------------------
label | 9fd422a9-c208-571c-a697-96ae08c821dc |  | note | ACCEPTANCE CRITERIA:
label | 11469c94-07ce-57d5-bef7-f5c2c99cc385 |  | note | 50mm bedding sand to be placed at base of trench in accordance with IFC drawings
label | 0620345a-1c6b-5d95-9e4b-397280b08f11 |  | note | In areas where rock is encountered, the cables shall be laid on a clean bed of sand 100 mm thick
label | 04fe0384-1557-5aa5-b4d2-71dc1452a60b |  | note | ---------------------------------
label | 3da0d8d3-8302-5e9c-9fd9-961f566932c8 |  | note | METHOD: Measure, Visual
label | 727d51c6-7108-5254-85e1-bed19eedcac9 |  | note | ---------------------------------
label | 3c692a17-929f-54f3-ac65-077567bb390b |  | note | FREQUENCY: Each lot
label | 08286d5f-05a5-56d9-bfa0-97e550f1664c |  | note | ---------------------------------
label | 9825b245-9776-5a3f-9a2b-16b344b69e07 |  | note | CATEGORY: IP
label | d464aa5d-2c6c-5035-afe1-9904803265ca |  | note | ---------------------------------
label | 37933f8b-4c8d-5684-841a-245ae5c818e2 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 246d259d-f75f-53d6-a806-20faa06aee0c |  | note | ---------------------------------
label | d47c0cbb-c854-51db-9bc5-cce94d9c65a2 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | ff45ae51-2360-51e2-9a72-723857307539 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Conduit-Configuration
label | b4cd4b47-e276-5edb-85fc-ecb76075ace8 |  | note | REFERENCE:
label | 1e9f751f-ac13-5d14-afad-40e65cfa4b19 |  | note | IFC Drawings
label | 12050097-ee97-5276-abae-b638f0a287c2 |  | note | L1-CHE-STD-043
label | 4975c10b-07a5-5c25-b8eb-6bf3a291c6a5 |  | note | ---------------------------------
label | 281ca41a-ae20-51f3-bda2-def1b9d494f4 |  | note | ACCEPTANCE CRITERIA:
label | 78df08b1-6ad2-53b2-aef1-7645321e8f7e |  | note | Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
label | ecfdfdf2-1477-5735-b492-02fc02cd4b86 |  | note | Min Cover
label | ec0b3e71-dab2-530b-88f4-747831df89ae |  | note | – Natural Ground: 800mm
label | e8a42497-84f9-5c77-bf23-314d31aa1e0f |  | note | – Under Road: 1200mm
label | 87b1b8a4-58dd-591b-8256-23e2782a53d2 |  | note | ---------------------------------
label | c96cc1d2-5761-5e4a-99a6-0ae1056c1f52 |  | note | METHOD: Measure, Visual
label | b4c0195e-3bc9-5587-8033-bbc8bdc61f94 |  | note | ---------------------------------
label | 8aca18a1-3eee-5dc1-bf32-391f42d348de |  | note | FREQUENCY: Each lot
label | 49c88edf-0cb2-5d72-ba1c-fb9634f04e2a |  | note | ---------------------------------
label | b4335057-e6c6-5160-98e3-3f3d78371aa8 |  | note | CATEGORY: IP
label | e8bd8dce-f9ee-5a04-b156-ee8f085ac23a |  | note | ---------------------------------
label | 22f2088f-5440-5063-b8f5-3a8f459dcf25 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4a1e6c9e-5453-5d3e-8aa4-8d9fb590d88a |  | note | ---------------------------------
label | 64622c39-a841-5731-b192-dddb25c67e4e |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 93f02c49-934f-5813-9933-2067599ab70e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Conduit-Separation of Services
label | ea206090-e14d-5745-9b90-856c85cc0a7a |  | note | REFERENCE:
label | 261afc55-cbcc-5635-a372-ae82d42de17e |  | note | IFC Drawings
label | 57c41735-5ea2-5940-bb53-7b9c91bbbb3b |  | note | TS-SP-013
label | 179b690f-157b-5ea4-bead-a7e5644c1c59 |  | note | L1-CHE-STD-043
label | aad012e0-8b28-50ac-a2f4-0b0ef4bbb92a |  | note | ---------------------------------
label | 1a590a8b-0156-5594-b517-18eb8e106632 |  | note | ACCEPTANCE CRITERIA:
label | ff4f208d-8e57-5149-adaa-4ef11bc8f3a9 |  | note | Separation of services
label | 33dfd4a9-601a-5421-b067-f81befd7e1ca |  | note | – HV: Min. seperation distance between HV conduits at least 50mm
label | f238ca11-4457-57b8-9854-87e9a40aa6eb |  | note | – VicTrack: 100mm from HV
label | 6a9ad61b-56db-5e70-9518-8035fbf29543 |  | note | – Utility: 300mm to utilities
label | a07e4341-2844-5c69-a88a-6d6550dd5afd |  | note | ---------------------------------
label | c1743fa5-6eb5-564c-90dc-81bb3f54b011 |  | note | METHOD: Measure, Visual
label | f7764138-ca03-5741-a4ec-81d837d01292 |  | note | ---------------------------------
label | a16b683f-114e-5c45-b935-f078df941f40 |  | note | FREQUENCY: Each lot
label | add440a5-93e7-5822-8f44-8304ca8814da |  | note | ---------------------------------
label | 2a9290b8-ff55-53b8-9522-03077780d23e |  | note | CATEGORY: IP
label | 531af432-2b39-5ac7-9092-ea5731a80a7d |  | note | ---------------------------------
label | 464c931b-0392-5302-a0fd-a33a307fe07f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 43b603ba-930c-565e-a35b-80af0ec5d1c8 |  | note | ---------------------------------
label | b8b35e5b-d976-5141-900f-4916300a6301 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | fc037328-b131-5937-b322-5a2f8443a4ad |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Conduit-Joints
label | 18ab26f9-1948-5509-bb71-2ab41064de1e |  | note | REFERENCE:
label | d32d4fd6-05eb-55c9-b25c-5d2a83907488 |  | note | L1-CHE-SPE-070
label | 54eeb862-131a-543d-922f-b4cfa0b1b5c8 |  | note | L1-CHE-STD-043
label | bdde8f06-57f5-53e8-9490-b83321b98c53 |  | note | L1-CHE-STD-070
label | 4560bd08-d7bf-5a9c-8111-8ef590f33da1 |  | note | IFC Drawings
label | e878650f-bdab-51e7-b4f7-4faf6b66a8b6 |  | note | ---------------------------------
label | efcaa11f-9cc1-5a45-a4ee-4a97f0c959fc |  | note | ACCEPTANCE CRITERIA:
label | 47327ba9-abc1-5523-9ea7-37b243ac7af1 |  | note | All conduit joints shall be made by utilising the spigot and socket ends.
label | 91dd5dcc-a228-525d-98c6-a500aeb7a5d5 |  | note | Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer.
label | 75e8db83-b4cd-5145-83f6-34a5be7e5b2f |  | note | The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer.
label | c903aa47-a824-5007-808a-9cc3909f8629 |  | note | Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
label | eeb8beb1-5ffa-5a2d-9c2f-97cde8a28a37 |  | note | ---------------------------------
label | 670ea1b3-ebe7-5d6f-883a-2393ff554f53 |  | note | METHOD: Visual
label | d299352b-b97d-5e22-8f28-7aeda4ef2226 |  | note | ---------------------------------
label | c8dad3cc-e76d-556f-ba8d-3afb07812bc0 |  | note | FREQUENCY: Each Joint in each trench
label | 90c9334b-4719-5d32-8ba9-fdfbe981e355 |  | note | ---------------------------------
label | 0c25b74f-2bf5-533a-94b3-09146697115d |  | note | CATEGORY: IP
label | 2ccc600f-7a55-5836-903b-61070d0c7f1f |  | note | ---------------------------------
label | dae017fe-ee80-5e55-bc4d-6d341aadefab |  | note | RESPONSIBILITY: SE/Site Supervisor
label | e1d23bd6-e7bc-5988-bb50-a8d70e2e8823 |  | note | ---------------------------------
label | 1b8456c2-7510-5787-8f6f-705d66014256 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | d9142768-86b5-5dce-ab2a-62317c4add93 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Conduit-As Built Pick Up
label | 41b024ba-3db1-5b38-a0a1-58e7b23a6f91 |  | note | REFERENCE:
label | d52aa1a7-11e1-5fe4-acd8-4527a7679d4c |  | note | IFC Drawings
label | 05d7e3fc-ce18-5017-85b8-cfc02e60fcfd |  | note | L1-CHE-STD-043
label | b35d9a0d-dbc6-5a3f-a8b2-3e4cde281e7d |  | note | ---------------------------------
label | b8186c16-440e-5a29-9026-aff17afd8ca2 |  | note | ACCEPTANCE CRITERIA:
label | de66e833-8abb-5415-8423-8a49e59d16a2 |  | note | GPS co-ordinates to an accuracy of ± 0.5 m shall be recorded every ten metres for the entire length of the cable route / trench, and at all changes of direction.
label | d6c4444a-1ede-5131-a7d6-dcb52789f451 |  | note | This method shall also be utilised to capture all;
label | 73aeb6b9-e528-54ec-be2b-0abf90546f73 |  | note | i. Cable joint locations.
label | db31078f-2120-58d3-84a5-04a213cb21a8 |  | note | ii. Cable pit locations.
label | 746ba369-f704-5ce4-a9b0-d513d04415e6 |  | note | iii. Under line crossings
label | cfd072e8-a967-55fd-b87b-c7ab2836547f |  | note | iv. Under road crossings
label | 4a782ea7-7d66-5abb-afc8-4a8ebea3acf9 |  | note | v. Other significant points of the cable route
label | 0d2ee097-ef27-5ba9-a663-d24b42584402 |  | note | ---------------------------------
label | 0e46f47b-25de-5f3c-af82-ba0aceaaf23b |  | note | METHOD: Measure
label | 97db20ae-bf19-5b6c-a2a9-232784c59c69 |  | note | ---------------------------------
label | c4113f93-e06f-54a4-80a3-f582d4c9b166 |  | note | FREQUENCY: Every 10m
label | 83b9bc32-301e-51d7-991c-38bda7f24b3a |  | note | ---------------------------------
label | e17584ef-9030-535f-a2d3-ca747d41eda9 |  | note | CATEGORY: WP
label | c18a924a-a58f-5139-a9c5-3dfa7d6775d1 |  | note | ---------------------------------
label | a222d086-36a9-5580-b240-0ff7f11a3dcd |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 0a122641-408a-51ac-a6fa-0a42fe8d2076 |  | note | ---------------------------------
label | 712cb3c1-4142-5f56-99fd-73bcb6e55fb4 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 479f6f26-2525-5937-8685-27579cef359b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Conduit-Bedding Sand Installation
label | a5ecba00-6076-54e7-a966-d53e2745512f |  | note | REFERENCE:
label | 5a860324-69f1-516e-9689-933c07cfb88e |  | note | IFC Drawings
label | feac06ca-d86a-507f-8e5d-79334f1a8540 |  | note | L1-CHE-STD-043
label | 3e7b36a9-21e0-542e-80c6-1756c5415d1c |  | note | ---------------------------------
label | badc9c44-2a6d-52ee-a7e7-ed52da07671d |  | note | ACCEPTANCE CRITERIA:
label | 91af2717-813b-5835-a890-dfd758802a6b |  | note | Bedding sand extends 50mm past edge of conduits.
label | 1cb2a618-c2bc-5c5d-8b38-336e8d741d69 |  | note | Bedding sand extends 100mm above conduits.
label | 03b0b93f-8b13-5f85-b7b1-185c16ddb5bd |  | note | ---------------------------------
label | d07b6f02-af0e-563b-b9d8-01dd0323752d |  | note | METHOD: Visual
label | 7112f32d-e385-5d5f-9fd1-b93f1d2c033e |  | note | ---------------------------------
label | f36c44fc-758b-556e-b86c-326c2fcfd1ce |  | note | FREQUENCY: Each lot
label | d3156323-4283-5abe-a2c3-b5aef3842eff |  | note | ---------------------------------
label | 342a9b99-9471-5118-847d-27c698ff0dd7 |  | note | CATEGORY: IP
label | b389f3a0-2e6c-5c90-92c0-7c9bcc08727e |  | note | ---------------------------------
label | ee910d60-3f45-522f-bac4-7acd7054b6fc |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3bed6293-3378-5b58-bd07-6a9ef37dafe4 |  | note | ---------------------------------
label | 484d3571-26a7-54b7-8066-2d7410d8f416 |  | note | VERIFYING DOCUMENTS:
label | edc1e544-033b-5dd0-bb57-62f2920f3ebf |  | note | Sign ITP
label | 4cc9b037-8c25-5941-93b2-064c3e841faa |  | note | Attach Delivery Dockets
date | fe0ef891-b01d-5cd5-92cf-2b5a0871e23c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Conduit-Protective Cover
label | 73311859-1540-5bc8-a7c9-d6692521e149 |  | note | REFERENCE:
label | d21c26e9-74ba-51ca-967d-fdec85fd8389 |  | note | IFC Drawings
label | 30b862d7-fd1b-5df6-8364-0e05ecad348b |  | note | L1-CHE-STD-043
label | 7edc8764-c30d-583f-a150-028c35b39c7c |  | note | ---------------------------------
label | bcdace18-0d59-5fad-86d1-5b01816d5dba |  | note | ACCEPTANCE CRITERIA:
label | 16bc11a9-4ce6-5246-aa75-ebc7662b3a3e |  | note | The cover strip shall be placed on top of the cables and overlap the cables by not less than 50 mm on each side
label | 9f069712-ca4e-5116-be2a-b25bd91b5bd8 |  | note | The protective cover shall be no closer than 75 mm above the cable/s
label | a6db99d9-4669-5af6-846b-fbe32800ac2d |  | note | ---------------------------------
label | c35ef9e2-6e7f-56f4-b1eb-c5a196c78141 |  | note | METHOD: Visual
label | 78292c70-90d0-59c7-8f65-fd55c23df731 |  | note | ---------------------------------
label | 1dffe008-9c4b-5c00-a14f-bc996f3d255b |  | note | FREQUENCY: Each lot
label | be72ca41-8387-544f-ade1-d7d2909265d5 |  | note | ---------------------------------
label | 27f04208-1318-539a-800e-53fbe047c6f8 |  | note | CATEGORY: IP
label | 8f4316fc-37dc-5a4d-bc9b-4794ea2deb7a |  | note | ---------------------------------
label | 95fdb6dd-8b3d-58a7-93cb-45b19c7a647f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1391ee5f-0155-5cae-a61b-69cea58de81e |  | note | ---------------------------------
label | 3bfda7e2-287f-5822-b6e3-cb830ba280a4 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | bc60f98e-284b-5f37-8bc1-ac727c9cb3ce |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Conduit-Marker Tape
label | 7381eb02-49e4-520c-8fd0-b26db9055f7f |  | note | REFERENCE:
label | c2bf3ac7-ab7c-594f-96f5-f109e7932e91 |  | note | IFC Drawings
label | 7e02cdd9-0398-5944-afa0-5db623058789 |  | note | L1-CHE-STD-043
label | b94ff2ec-1aac-59f5-8fe5-4248f960c653 |  | note | ---------------------------------
label | 81412166-ba8a-55ca-9b59-235f2c899d0c |  | note | ACCEPTANCE CRITERIA: 150mm wide orange coloured PVC "DANGER RAILWAY SIGNALLING CABLES" marker tape shall be installed in all trenches 300 mm below ground level
label | c690abbf-ab12-5914-829b-d95faa19c75c |  | note | ---------------------------------
label | f41986e5-7413-52f1-9ddc-036817609578 |  | note | METHOD: Visual
label | 11d88636-d172-5400-a2b0-bb5c3c8231ae |  | note | ---------------------------------
label | ad0905a6-39ef-5193-97e1-3cfd5391896d |  | note | FREQUENCY: Each lot
label | aec97f61-5918-5dcb-a233-984c580cfbfd |  | note | ---------------------------------
label | aa25033c-e722-5350-9274-5763df478834 |  | note | CATEGORY: IP
label | deff2ded-2a89-5d98-92c2-fe2384bf8112 |  | note | ---------------------------------
label | fabd5efa-1213-5406-8692-5dab1d3b5cd4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | bfc755c7-c67f-5268-bd1a-492a48e0a829 |  | note | ---------------------------------
label | 07b3a91c-6157-53cc-9256-2c9ba6fbbb46 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 52987845-b45d-58de-9e63-87090cc0132f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Conduit-Backfill Installation
label | bb0b0cbb-e0e0-5228-8503-1937362ade6d |  | note | REFERENCE:
label | a45d370c-5d7b-5f4b-810a-b4e889495e97 |  | note | IFC Drawings
label | 4371c914-c424-5f9d-a66f-e653b1b7141b |  | note | L1-CHE-STD-043 clauses 6.15 and 6.16
label | ce02c79d-b3f5-54ea-b854-d66036e1796c |  | note | ---------------------------------
label | 64f9c4c9-b1fd-5183-bb16-59cc6ba2f215 |  | note | ACCEPTANCE CRITERIA:
label | 6b02e706-8e7d-5b7d-b4ab-b706dc83081a |  | note | Backfill per trench profile
label | 2e68b62d-a7b9-5d8f-ae91-a9100462c4b2 |  | note | – 150mm layers
label | 686426f4-3da9-59f8-80ce-b3436a5a7464 |  | note | Backfill material to pass through 30mm sieve and be free of material that could damage conduit.
label | 0c5d10e3-6418-5d33-9d62-c33458b26d28 |  | note | The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
label | 04750a70-15ff-56d3-acc0-a8e145a4efc1 |  | note | Trenches under road pavement - backfill to be same material as the road formation material.
label | 2cee32b8-c702-5c9e-bcf8-6d49a900e17b |  | note | ---------------------------------
label | 9fe470cc-fd6f-51d5-82cf-5ff37a00f2c9 |  | note | METHOD: Visual
label | 9500e0c5-9760-5b89-a5a0-577d8acc179d |  | note | ---------------------------------
label | 67282431-1eec-509b-8ed6-2d23a0b8c588 |  | note | FREQUENCY: Each lot
label | e82ad2e6-e119-512c-99c4-6513914e6098 |  | note | ---------------------------------
label | 1b653c0e-4073-564e-8aa3-6ae2355ea1a6 |  | note | CATEGORY: IP
label | ad8574c9-dc5e-595f-8133-747f48a05341 |  | note | ---------------------------------
label | c9174c2e-aa58-5563-929a-b071b1074b38 |  | note | RESPONSIBILITY: SE/Site Supervisor/NA/VicTrack Rep
label | 4a48148a-e07e-5e05-8eff-5cab4175a927 |  | note | ---------------------------------
label | fe7454c1-c64b-5192-ae65-34727c333cc2 |  | note | VERIFYING DOCUMENTS:
label | 24e0f884-b8f5-5e5b-9978-17918b3407ab |  | note | Sign ITP
label | d4e86ac3-6611-5a12-97f3-c4cc4af698ca |  | note | Attached Delivery Dockets
date | c5df2e16-1f19-5c30-8048-fc405d204f13 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Conduit-Compaction Testing
label | a8cb80bc-03d2-58c7-9d2b-da778a2f87af |  | note | REFERENCE: L1-CHE-STD-043 clauses 6.16
label | e8d88c48-beb7-5f33-88b9-1a2036bf092c |  | note | ---------------------------------
label | e7efeca5-f167-544a-a835-7b2506cb86f2 |  | note | ACCEPTANCE CRITERIA:
label | 89d90074-5c4a-5f4b-9e42-882e59455b34 |  | note | Compaction to achieve 95% Standard Compaction.
label | f10db769-dd26-5456-88bf-3ea243afed41 |  | note | The tests shall be taken on a frequency of one (1) test per 200 linear metres per layer or one (1) test per area per layer where any area of excavation is less than 200 metres long.
label | ba1e272f-1875-5d13-a4b7-a04c7e747379 |  | note | ---------------------------------
label | f56ecb4e-27cf-5e5d-acc8-dfd9812e718a |  | note | METHOD: Document Review, Visual
label | f7f83ba4-178a-51a6-a41b-7163abb95a0c |  | note | ---------------------------------
label | 56aaf35d-83ff-5841-9346-869dd335e1fa |  | note | FREQUENCY: Each Layer & Every 200m OR Per Area
label | 472e3681-cbe3-5a23-a8ff-8f92306f1737 |  | note | ---------------------------------
label | b5e1371d-3e00-57ff-a615-8ec6b76d43e5 |  | note | CATEGORY: IP
label | 42877131-f3a9-5ab6-9bca-781f9d26edf9 |  | note | ---------------------------------
label | 0d753054-d7c3-58e9-b9eb-408b36f268e4 |  | note | RESPONSIBILITY: SE/PE
label | cf202e91-8eb3-5e12-bd49-d98d29a38e2a |  | note | ---------------------------------
label | 0a25dde7-3e36-5ad2-8e91-5f6300e48db3 |  | note | VERIFYING DOCUMENTS:
label | 122d4f54-e4af-59b7-bbb3-bdc581d50ab9 |  | note | Sign ITP
label | 20cb7c81-f0cf-5363-a038-f8fc66cd4ee3 |  | note | Attached Test Report
date | 8e49f7fc-2999-5639-a3e6-b8b7681c66db |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Pit-Bedding
label | 6e929e59-d5f8-57fd-8009-96f265cc78bc |  | note | REFERENCE:
label | 9658d7d2-9abe-5cd7-8956-24c7785d3124 |  | note | IFC Drawings
label | 6c5f6177-0ffd-5707-b0e9-f9f522e60030 |  | note | L1-CHE-STD-043
label | b7ec8bb4-dc86-56dd-8bfa-644f239615a4 |  | note | ---------------------------------
label | a247260d-f501-5fd7-9b53-f413a0735320 |  | note | ACCEPTANCE CRITERIA:
label | a0984011-0f42-5a55-a1d9-fb15161d0e99 |  | note | All pits and chambers shall have a prepared foundation of “A” grade 20 mm crushed rock not less than 150 mm thick
label | c1d09a7c-d3ed-5f54-a9fd-edec88829dda |  | note | Gravel drainage sumps shall consist of 20 mm aggregate with a minimum depth of 300 mm
label | 50f1e8a2-a827-53f8-b2ff-ccb78b663626 |  | note | ---------------------------------
label | c5d90adc-01b6-54e0-9a3c-55ffe05dd8c5 |  | note | METHOD: Visual
label | f830c23a-a70f-5cf3-8595-6d5e26053574 |  | note | ---------------------------------
label | eed296fd-7fb8-5bc1-937b-bc54bd0f8be4 |  | note | FREQUENCY: Each Pit
label | f7ab3cb6-04e8-55ab-bffb-86b04478febe |  | note | ---------------------------------
label | 90daa935-7e09-5a43-bfcb-dbab224741e2 |  | note | CATEGORY: IP
label | 3f497314-bf57-5bee-b9f8-b9ccd7d05ac4 |  | note | ---------------------------------
label | ab8dcad5-16fc-5308-932b-22fded47d566 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f9156e77-bc1f-586c-9a23-91e2c8684b0f |  | note | ---------------------------------
label | 461ba30b-ce93-5089-b3e3-ab5fda6214b7 |  | note | VERIFYING DOCUMENTS:
label | f5026022-dc64-5d34-ae2d-00f52690fcee |  | note | Sign ITP
label | a2878826-dd88-56e2-995a-cb8750162fe0 |  | note | Attach Delivery Dockets
date | 5342bf1c-f0df-5dc2-a343-b2d8909b26fb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Pit-Orientation
label | ce9064b5-109b-526a-971d-c19cc2681482 |  | note | REFERENCE: IFC Drawings
label | 0280642f-737a-5590-9f72-9112da6e206c |  | note | ---------------------------------
label | edded9a4-e520-59f0-9c57-98a14063934b |  | note | ACCEPTANCE CRITERIA: Pit to be parallel to track and parallel to conduit route.
label | b4a077ab-795c-5a26-9eae-bf4fbfb3f34d |  | note | ---------------------------------
label | af57b689-c0d5-58bf-be95-36d643d7bfe9 |  | note | METHOD: Visual
label | e7ca725c-ad30-5223-8996-6314780bb38c |  | note | ---------------------------------
label | 376d7ae2-aada-5425-9e49-d51fbf3e684d |  | note | FREQUENCY: Each Pit
label | 5c1f5e69-cd27-5e3b-9fdf-2f1431886aea |  | note | ---------------------------------
label | d99272a3-3c8e-5447-b8ba-29dbe918d497 |  | note | CATEGORY: IP
label | b747a786-f899-50f1-9377-95eb6c73928f |  | note | ---------------------------------
label | 92647f0f-176c-5b53-882c-599d8d4c11a6 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 72c54259-ba01-5073-b551-ed1e26075f51 |  | note | ---------------------------------
label | 322c88be-4b7f-5c17-8c3b-ad076bc71b2d |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 51ac27ec-0dcf-565a-95e1-12a1236bd01a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Fit off-Conduit Entry
label | 8bbbc45b-ee01-51b5-bdaf-403ad7851ccb |  | note | REFERENCE:
label | be03c965-cd2e-5ee0-a058-1831f1c46b4e |  | note | IFC Drawings
label | 01876e0c-f2bb-5e77-908a-1c48a8cfd794 |  | note | L1-CHE-STD-043
label | 7fd62aaa-b2c0-5a48-9819-d5c9a80a25f1 |  | note | ---------------------------------
label | e0e4e69a-06ef-5b38-a7e3-0d4c1cea1312 |  | note | ACCEPTANCE CRITERIA:
label | ed7951ea-c24e-527e-8fe0-cb663b006187 |  | note | Entry holes shall be 100 mm minimum from the base of the pit or chamber.
label | 13b525b1-d879-5f54-a996-ce861ec029d8 |  | note | The end of conduits shall not protrude more than 50 mm into the pit space
label | f6a32e28-d01f-54a9-ba15-8b56c63eed06 |  | note | ---------------------------------
label | 5d75bd9b-de96-5191-8eb5-9dfd648a9aaf |  | note | METHOD: Visual
label | b4d9b324-be1d-5093-9ec8-059adc623451 |  | note | ---------------------------------
label | b3baead0-eb73-5c9f-97b1-98a96aadd1d1 |  | note | FREQUENCY: Each Pit
label | 498abb0c-19bf-5e2f-bbf1-49ef0c667e89 |  | note | ---------------------------------
label | c9bc3126-70db-54b1-9366-8c134c772ec7 |  | note | CATEGORY: IP
label | 30133cde-9dd6-5562-8ca7-6857e6b19159 |  | note | ---------------------------------
label | e48114f6-f5c7-5729-a035-8b8aa8adcb2e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 7edcbd9c-7e01-5b08-95f6-24f9d2cc1fa8 |  | note | ---------------------------------
label | 92912a63-8eac-57e9-bc1a-bb0883798201 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | c691f231-2c82-5b90-bc0e-ab3ad14a1a75 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Fit off-Spigots
label | 7255ceae-58bc-510f-863b-6a33fd42ebe6 |  | note | REFERENCE:
label | 7ca5bb9c-a102-5c6d-b8c6-941ec52a7d72 |  | note | IFC Drawings
label | de9d0d13-4c66-5231-b0b5-a02972ce97e7 |  | note | L1-CHE-STD-043
label | 18061692-2349-51e7-9095-2a4fb6e4ae5b |  | note | ---------------------------------
label | 7465b800-cb64-516b-bdb7-ebe6a452ba9d |  | note | ACCEPTANCE CRITERIA: Spigot bush to be installed on conduits being cabled
label | 4ae8467f-8654-5d38-95de-4d5adf754b0f |  | note | ---------------------------------
label | 0b69cf1c-a46e-599d-8c18-82d0a639f7e2 |  | note | METHOD: Visual
label | 6c5e3a4d-6db9-56fe-bc2c-3b7b51fe2496 |  | note | ---------------------------------
label | d0895e1f-9d08-5959-9e1a-a3eebd5505b7 |  | note | FREQUENCY: Each Pit
label | 78ed9aa3-dc10-51c6-bf47-88fbe802a22e |  | note | ---------------------------------
label | 219ebfbd-cdcc-5c84-9e45-5867411bb75e |  | note | CATEGORY: IP
label | 9dca2379-59dc-5b58-91ec-10b908e37ba4 |  | note | ---------------------------------
label | 1c0ebab7-24a7-51bd-a32a-50635882420e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 169b2ebf-6f6e-5a52-bcb2-35d015b123b1 |  | note | ---------------------------------
label | 9d81f594-c5a7-5c98-8bed-d1df32f5d1b9 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 0979e033-dd93-5f29-b3a8-313b09a94eb2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Fit off-Draw Ropes
label | 4074d254-e689-5c9c-9f97-b269db15761e |  | note | REFERENCE:
label | a267b033-a555-5d53-b4dd-1fe2b9897fcf |  | note | IFC Drawings
label | ffe70d7b-b6a1-5622-988a-405e7bf888ed |  | note | L1-CHE-STD-043
label | 3e5eef90-bf7f-505f-9a06-3842c33577a6 |  | note | ---------------------------------
label | 65bcfe82-503c-5768-8870-88d59a4bbd3a |  | note | ACCEPTANCE CRITERIA:
label | acce1bb7-df37-5294-82fb-b87c50735d48 |  | note | The draw wire shall be continuous for the complete length of the conduit run.
label | 313bc700-150a-534b-beb0-442d5e5b860a |  | note | The draw wire shall have a minim of 2 metres of slack within each and every pit along the conduit run, and shall be suitably anchored at each end of the conduit run and then sealed with proprietary end caps
label | ffde1b6f-e94c-5299-bf90-8c4c5500fed4 |  | note | ---------------------------------
label | ee0b0ff6-9dad-5764-9326-ba89586743e1 |  | note | METHOD: Visual
label | 874e57a5-0e14-5e7a-9da3-69e524fcb269 |  | note | ---------------------------------
label | 96367e10-6c83-5a08-9837-1aa5f429152c |  | note | FREQUENCY: Each Pit
label | 00190f78-a539-548a-bbf6-5c69803e65b6 |  | note | ---------------------------------
label | 883e55ea-7e8b-54f5-a219-da0b592abf84 |  | note | CATEGORY: IP
label | 99e71e22-eecc-546a-8dc5-c7d4b4b805bc |  | note | ---------------------------------
label | 44c930a8-3509-5152-b8ca-7c2b2cbe76f0 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | edcdb8cf-b135-5030-bbd7-72e0203ae5c9 |  | note | ---------------------------------
label | 883174bd-24a3-5be2-8dac-cedb0445ad96 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | a5cccea6-8f14-5a49-8402-41193885d3a6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Fit off-Step Irons
label | 71ba9b5f-fbe9-5728-9d92-d494ec994b43 |  | note | REFERENCE:
label | 59e86a22-60b7-5081-b4ac-a5b1f6e8582d |  | note | IFC Drawings
label | 0502276a-32b0-5767-8d91-0074cfd8e74f |  | note | L1-CHE-STD-043
label | 914b795a-58b9-5df8-b2b7-e11841d72fd0 |  | note | ---------------------------------
label | cec29dd4-e699-5327-b5bf-eecdb2dd3c65 |  | note | ACCEPTANCE CRITERIA:
label | e93bc8d7-cda1-5506-81d4-89a7d6e99ff9 |  | note | Unless otherwise noted on IFC drawings, the below is required:
label | 7733028a-e8bd-57b7-8247-4e0eb7fded38 |  | note | All other Pits: Step irons/rungs to be installed if pit is greater than 1.2m in depth (including lid thickness)
label | 24fe9aab-adb7-5973-b61d-8be74326db01 |  | note | ---------------------------------
label | 1f6219f9-7cc6-5208-a98e-80333a0d7477 |  | note | METHOD: Visual
label | 25c3c192-1f64-54f3-aa91-452f0c582486 |  | note | ---------------------------------
label | 346e6e51-4035-5a5c-bcf7-bff81f58b88b |  | note | FREQUENCY: Each Pit
label | e528e64e-f057-591b-b636-cfee0a0bafd0 |  | note | ---------------------------------
label | 2e074583-571f-584d-bc09-bd925efef47f |  | note | CATEGORY: IP
label | 6706d7b3-dbd1-5caa-88c1-2b5fc89c2bd7 |  | note | ---------------------------------
label | f0e39ad9-e689-5ec3-9fbe-a8c05631193a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3aa3d424-1548-56e6-85a9-19b0ec7d4675 |  | note | ---------------------------------
label | 896b5897-2e7d-5693-90c0-c5c9c3d5a447 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | e08f2208-5716-52cc-a783-ee811cbaf668 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 Fit off-Spare Conduits
label | 078867e8-e406-58df-9958-76fc1b922c48 |  | note | REFERENCE:
label | ca2d57c6-302e-5a42-aed2-4172bff4ff8a |  | note | IFC Drawings
label | 36351984-fc87-5e38-a1b7-0e2e6649c603 |  | note | L1-CHE-STD-043
label | 3012111c-4847-5725-99fa-bdfd25ff60da |  | note | ---------------------------------
label | cf4a0196-40fa-59df-8d7f-3539f285fbf6 |  | note | ACCEPTANCE CRITERIA: Spare conduits to be capped and to be included on survey report.
label | ccd0a270-bf9e-55ce-9549-071d72836b68 |  | note | ---------------------------------
label | 0cb07a3d-a54a-59ef-80cc-77b669db7808 |  | note | METHOD: Visual
label | f2200096-b4c8-5d5f-8a72-19abbd6f0dec |  | note | ---------------------------------
label | beba62ec-0a4b-5883-8f9c-3a139a67a528 |  | note | FREQUENCY: Each Pit
label | 6ede2914-d6cf-5ba0-a129-0682f334d118 |  | note | ---------------------------------
label | dafd858f-3a7a-554a-bd4f-d7e6c9fd764f |  | note | CATEGORY: IP
label | b02df474-2e99-53da-89f6-7838cb5b79c2 |  | note | ---------------------------------
label | a6a20aee-5690-5bdc-a56d-e6294174c92a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | cafef71a-cf2d-5d2a-aab0-fcb8f5a5634b |  | note | ---------------------------------
label | 54fe0f62-cf52-5942-bf4a-649567794564 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 4676cacf-b9b8-56b5-b1e1-4bea550a75dd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 Fit off-Pit Lables
label | bc774510-1e67-54f3-b0d8-6ed72694a0c0 |  | note | REFERENCE:
label | 43d45625-90e5-558b-8045-585aa41a0d64 |  | note | IFC Drawings
label | 0fde9cc3-a34c-5cbf-b986-ce3ea4800701 |  | note | L1-CHE-STD-043
label | f333f995-75c3-5fce-8b68-4a848ef6aa9a |  | note | ---------------------------------
label | e6c08311-c982-5f2d-8540-ec612694923d |  | note | ACCEPTANCE CRITERIA:
label | acac89bf-5341-5775-a85c-d4fdfd21d5b3 |  | note | Pit labels Brass Label (30mm x 150mm)
label | 5b925bb5-848f-5e3d-90f4-63cf6837146f |  | note | – Signalling: Railway Signals & Comms
label | 0f6a2a96-70fa-58b2-89be-1b470d8745c4 |  | note | ---------------------------------
label | 29c95b21-ecdb-572f-85fe-68ed656dc03d |  | note | METHOD: Visual
label | 74bc9ef6-3716-5590-89c8-2ea741a836fa |  | note | ---------------------------------
label | 147fc2b8-86be-543d-b95c-aff0c5ede740 |  | note | FREQUENCY: Each Pit Lid
label | 3d4de1a2-7265-5454-9d07-4346fe6be89a |  | note | ---------------------------------
label | 72956e06-dbf0-5da9-9191-1acb57adb6b6 |  | note | CATEGORY: IP
label | 7e7665bb-ed2a-5f40-91de-aab10d68f173 |  | note | ---------------------------------
label | 254a1fd4-4279-5046-8891-2d8807393326 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 47d1416b-47cc-59cf-bbe7-665d709a1f5f |  | note | ---------------------------------
label | b6e74064-69d9-528b-b4b5-34eaa31e81e7 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 3572ee51-69e6-5473-991e-15410fe046e9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.21 Protection and Labeling-Non Trafficable Pits
label | 74537bfe-bd02-5bba-914c-7cfe29834105 |  | note | REFERENCE:
label | 62993115-efe1-52b4-884b-208ff14853cc |  | note | L1-CHE-SPE-070
label | 2a9b9f59-b72f-5933-afba-6d5df565d237 |  | note | L1-CHE-STD-043
label | 5af97cbe-e89b-504e-9741-a03758e4e817 |  | note | L1-CHE-STD-070
label | 8f45259f-a956-5688-910b-5fa255b21517 |  | note | IFC Drawings
label | 80d97669-bbc3-59b4-8a76-78cca8d8316d |  | note | ---------------------------------
label | 80ca2703-6fe0-50d8-ac84-61f6f3fddea4 |  | note | ACCEPTANCE CRITERIA: Non trafficable pit lids to be 50mm above FSL and to have 2 x white bollardes installed at the corners of the pit.
label | 9be96390-54e6-5ada-af24-845c3b616ff5 |  | note | ---------------------------------
label | 60d0b6e3-52b8-53c8-8856-58b34fe67520 |  | note | METHOD: Visual
label | 30957d99-bfb8-586b-83d5-5f75de10d8db |  | note | ---------------------------------
label | 8069d1ad-5c98-5b2b-8c22-88fb3a42aac1 |  | note | FREQUENCY: Each Pit
label | faa20b86-4678-59cb-970a-f3f18672dfbe |  | note | ---------------------------------
label | 41622397-f593-5531-a5e4-5e9c6f20d3a8 |  | note | CATEGORY: IP
label | c007c3c0-a2dc-5720-beaa-3079c8240c6d |  | note | ---------------------------------
label | bc24713f-81f0-5a8b-ac6d-3ab41f8fe19d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 0cc72b46-e253-5361-9030-a5a2b77a93b9 |  | note | ---------------------------------
label | 4b4ed166-f883-5107-8165-adc02a622cec |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 668f537a-d632-5571-99fa-17ee060b9eec |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.22 Protectipon and Labeling-Cable Route Markers
label | 308e2b03-accf-5b8b-99fe-795ee5b8f94b |  | note | REFERENCE:
label | 71ddb68d-0bbf-507a-9372-31e8e6e10421 |  | note | IFC Drawings
label | 263dc0c4-3340-5102-b4b7-03feda6be638 |  | note | L1-CHE-STD-043
label | 5125832e-671f-52b8-9944-1a59ee3a024f |  | note | ---------------------------------
label | d2671f01-a9c3-543a-8cb3-275d72a32c22 |  | note | ACCEPTANCE CRITERIA:
label | 93e0618f-1dcc-5318-b825-d5cb96309d37 |  | note | Cable Route Markers
label | 853b8425-02f4-5ace-82ec-587108155c15 |  | note | – points entering & leaving the rail corridor
label | f0cefdb1-d911-5ec2-8187-9552e0e10cbd |  | note | – no greater than 100m spacing
label | e649b8ac-32f1-5444-8b00-537df1320ddd |  | note | – Change of direction (more than 5 degrees)
label | 1ed495c9-9aef-5e93-8678-70e05391a4e5 |  | note | – White posts with marker plates for conduit runs
label | e395cb99-6144-5cb0-ad96-650b76ddbd25 |  | note | ---------------------------------
label | 81b77381-6629-53a2-a893-247fe79b5664 |  | note | METHOD: Visual
label | 0985cebe-1def-512f-92ae-bc730a988dce |  | note | ---------------------------------
label | ea701261-9498-5bcb-93f9-b8ec2b725d7c |  | note | FREQUENCY: Per Cable Route
label | 65386ae2-883d-5221-94ed-26a22132499a |  | note | ---------------------------------
label | b63d58ed-e8f9-5671-8046-e9bbe93cce42 |  | note | CATEGORY: IP
label | b8bb3e47-c43b-549f-95cd-60e092049be6 |  | note | ---------------------------------
label | d5196054-fc1f-509b-aec6-f643489da1e4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4afeefd4-9674-5fe1-bb0c-049d2fdcda6f |  | note | ---------------------------------
label | ce5bead0-63ef-5a2e-b157-2b592800aea3 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 47978279-2b2f-5cf0-9978-383fda0bf60c |  | date | Date Completed:
checkpoint-group |  |  | section | Post Construction
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey file
label | be9a9767-598f-55d9-b62e-6fe4bc49af73 |  | note | REFERENCE: L1-CHE-SPE-070 Section 13.1
label | 4c3cb599-54f9-536c-810b-04b59256021f |  | note | ---------------------------------
label | 0634eec1-8e0f-5718-818d-c6194eddf328 |  | note | ACCEPTANCE CRITERIA:
label | fa412b32-6ae3-56b9-8672-a431c7966709 |  | note | Survey report to include but not limited to:
label | c6d93540-80df-5318-87c4-1dc0575d9b7a |  | note | – Cable joint locations.
label | 22a94382-c2bf-57c5-ab67-7f8e174a0a82 |  | note | – Cable pit locations (Corners)
label | 51555784-b70a-504c-b4f3-31ca27971cad |  | note | – Pit dimensions & pit lid type
label | 9b139d67-d045-5d21-b3fe-b68903028092 |  | note | – Under line crossings
label | fcc9aa93-72bc-5a56-bcf0-900290fc1301 |  | note | – Under road crossings
label | 4b7fbdf4-329d-5c02-87d3-52619c849d85 |  | note | – Changes of direction
label | a3bad155-2a72-534a-b18c-0d3fa88cebdc |  | note | – Spare Conduits
label | 1152deeb-150c-5e5c-8b8f-9b2268ba5ce8 |  | note | – Conduits labelled as per trench profile
label | 64122a68-b1ab-5368-8574-bc8936dae21d |  | note | – every 10m
label | 84ead3a6-4aba-52c1-9bdc-1e7c25b039cc |  | note | – Other significant points of the cable route
label | 2780a2b3-e530-5280-94ad-911919a1acf1 |  | note | ---------------------------------
label | bc507128-316e-5aa5-bfb2-32b52cc45927 |  | note | METHOD: Document Review
label | 36cd25a4-0407-5016-9866-c1318046e926 |  | note | ---------------------------------
label | 9be53b44-5938-5aab-bade-3935dce84b37 |  | note | FREQUENCY: Each Design Pack
label | 392a4c1d-e173-5d3f-a1f9-4886fc476b6d |  | note | ---------------------------------
label | 767d69b5-3bc4-546f-ac43-e656d10d6f52 |  | note | CATEGORY: IP
label | 085c3445-3fbc-58d6-9298-e04b24cf2bae |  | note | ---------------------------------
label | 17a465e6-40d2-5452-83a8-4b71d1e2dc16 |  | note | RESPONSIBILITY: SE/PE
label | f73a314d-2b88-581a-8158-45652fcc659b |  | note | ---------------------------------
label | 94e495fa-034e-5cfa-ac91-f8d311a3c2b8 |  | note | VERIFYING DOCUMENTS:
label | c99b6b47-0d0a-5b74-96d8-449bd06092eb |  | note | Sign ITP
label | 673290c6-8e14-5da2-9d73-2be4cc96f757 |  | note | Attached Survey Report
date | d54036ab-a595-53f7-be54-fd9296cb7114 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Engineering Redline mark-up
label | b79d37da-091a-584a-a128-6e49f2c91217 |  | note | REFERENCE: IFC Drawings
label | 512fb310-5067-5523-afd0-0ac0fcfbca38 |  | note | ---------------------------------
label | a0d1852f-3170-5af7-adc9-59d98c119b64 |  | note | ACCEPTANCE CRITERIA: As constructed cable plans shall be provided for the entire cable installation and in accordance with AS 4799 and the PTV Infrastructure Drafting Standard.
label | c53c31a8-c877-582d-aa93-0f840a6b3381 |  | note | ---------------------------------
label | 9ea9210d-c8aa-5c37-b580-61cbf07995e9 |  | note | METHOD: Document Review
label | b46c4cad-47c5-513b-8c1d-8dad62bdd0d2 |  | note | ---------------------------------
label | c198fee0-003a-54df-bfa9-99c78deccb7e |  | note | FREQUENCY: Each Design Pack
label | 48ebbd47-f19b-5dbe-b88d-b12b323a208d |  | note | ---------------------------------
label | a508def2-7c12-5093-98b1-4a7f2ca2bb7b |  | note | CATEGORY: IP
label | 7dfc6101-7172-5b36-96c0-b348b6a2ef37 |  | note | ---------------------------------
label | 8510736f-fe54-54d2-9bbb-60712a5faee3 |  | note | RESPONSIBILITY: SE/PE
label | 32f80c9d-4aa0-5aec-a1d0-5a9fec01cfd9 |  | note | ---------------------------------
label | 9ea2d452-7d7b-5002-b08b-0f67dab9df82 |  | note | VERIFYING DOCUMENTS:
label | 80e0023f-7fce-5a6d-bfe4-3806dfa8c5ab |  | note | Sign ITP
label | 0d8cf878-4f95-583d-9084-f15adac248e1 |  | note | Attached RLMU
date | 08864fe6-0201-5aea-bda0-1e94a4e5767f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 9cf75333-a764-5237-854c-936b0df0b862 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | dade164b-c80b-555b-a6e4-ea3fee3d10f5 |  | textbox | Name:
text | be2b6a30-c9b1-5bad-b529-d52f43218a9b |  | textbox | Position:
date | eeb4cecb-fb9d-5ee6-8835-3afa32185565 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-013-STR-Pile Cap Construction | itp |  |  |  | Yes | ITP-013-STR-Pile Cap Construction Rev 0 | e29a5e1b-8f35-4a6c-aaaa-644d6ccc31e4
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 9537e0d6-10e6-5017-a771-0286fc3d36cc |  | note | Document Title: ITP-013-STR-Pile Cap Construction
label | 39e76b87-b4df-5933-9711-6cc693e2e6aa |  | note | ITP Description: Pile Cap Construction
label | b36e25c6-b26a-58bf-a2df-d9af4aa3b601 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 548fe2b6-45c0-5e55-a006-4310dfc64007 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 301ed352-43a1-5945-bcfb-8919ae0df611 |  | note | Revision Number: 0
label | 499deaa6-ac9a-503e-b9f9-78247084b9be |  | note | Revision Date: 01/12/22
label | db1de2cf-bef8-538c-8ea4-c58101742a73 |  | note | ITP created by: Victor Mira
label | e094fef1-1793-5707-83c0-a3fa7c9768ef |  | note | ITP approved for use by: Victor Mira
label | d7afed2d-2342-5000-bc66-86e84d768526 |  | note | 1.1 Non Dependent
label | 9fda75b7-e628-521f-8df2-61904b584a56 |  | note | Reference: VicRoads Section 602 October 2007
label | 452cfbd9-edc0-5f32-b1ad-42be068b887f |  | note | 1.2 Non Dependent
label | f17613fc-1a91-5070-9e1f-fd8b733637e1 |  | note | Reference: VicRoads Section 610 February 2020
label | c85d8da6-5e6f-55b4-a8c1-79667fd1b7bd |  | note | 1.3 Non Dependent
label | 96380b3b-dbde-5005-9fc3-c447196238f3 |  | note | Reference: VicRoads Section 611 November 2018
label | df4f3ad9-383d-5d4f-bf06-2eb92a8dbf6b |  | note | 1.4 Non Dependent
label | 0052eacb-88cc-5a80-9f4f-0153f446471b |  | note | Reference: VicRoads Section 614 June 2017
label | 1dd5b02c-b293-509c-a0ab-1b33ae031005 |  | note | 1.5 Non Dependent
label | 106f9158-6bdb-543c-b230-2b804ebdfc0e |  | note | Reference: AS3810.1 2018
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 77840da2-3cbe-52b4-a7a8-86e106a9984a |  | note | REFERENCE:
label | 8bf686c7-4ecf-5808-b2f6-60160d22fe3b |  | note | 610.07
label | 5900934b-475c-57a2-a18b-2f2b6d169f9f |  | note | Table 610.071
label | 4aae9b62-df11-5e99-a598-0be4740779df |  | note | IFC Drawings
label | 996cc973-f52d-5655-b739-c13000343e93 |  | note | – – – – – – – – – – – – – – – – –
label | 0d808b45-2a1f-5c6b-b770-994f4e34ed3d |  | note | ACCEPTANCE CRITERIA:
label | c9e95c98-e1ad-51b5-b34d-3fd6fa37f667 |  | note | • Concrete Mix is Registered with VicRoads.
label | e84023b0-1827-5c69-9cee-0e1926a65f29 |  | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 486b9f5c-6026-597a-b623-f74c3752b5d0 |  | textbox | Enter: Teambinder Material Approval number
label | bf894c69-9df9-5bf4-ad96-165c4171e059 |  | note | – – – – – – – – – – – – – – – – –
label | c1503edf-d4a7-5e35-b77f-ed104d2c1ce8 |  | note | METHOD: Document Review
label | 034ecb16-3638-5e26-9752-45d0e0b035e0 |  | note | – – – – – – – – – – – – – – – – –
label | 25d85e4a-9f90-5e3b-a487-b7a503f412a8 |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 6b8e7c31-5317-573e-a635-20090eaa37cc |  | note | – – – – – – – – – – – – – – – – –
label | faacc0ed-d23c-57f0-a55e-25b9ca20a154 |  | note | CATEGORY: HP
label | 16c7c894-531e-55f1-9328-d8d04eff0e70 |  | note | – – – – – – – – – – – – – – – – –
label | 73c476f7-27a3-5e8f-bad6-d5896cb7f118 |  | note | RESPONSIBILITY: Nominated Authority
label | f90986ad-d2b9-5632-849b-58634b19e24e |  | note | – – – – – – – – – – – – – – – – –
label | ed78c1da-546c-5585-9f16-fc7174023a03 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 4763dc47-dd24-5113-b2b8-1de0948a9c79 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 81a7e293-eb20-5f8f-b3d6-b0c69594876d |  | note | REFERENCE: 611.05 (a)
label | a781f34f-b69c-54f2-9277-48afdc7adb10 |  | note | – – – – – – – – – – – – – – – – –
label | 8d98135f-c205-5841-9777-7d736d14145e |  | note | ACCEPTANCE CRITERIA:
label | d415f1dd-e647-5b23-b41d-1782069844f6 |  | note | • Current ACRS certification for materials and for bar processing.
label | 0bed4fe9-2d1d-5909-bd0b-759ec7a76cc2 |  | note | • Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 47c74bce-7d91-5c71-8eea-ea945bb74efc |  | textbox | Enter: Teambinder Material Approval number
label | a2d532a6-6f7d-5ba6-814a-fe28543bf34f |  | note | – – – – – – – – – – – – – – – – –
label | 42643542-026e-5bf5-b0d2-fb78df2a2448 |  | note | METHOD: Document Review
label | 6cb07bc7-ea02-5aa9-bf9d-5bb4d6aaf57b |  | note | – – – – – – – – – – – – – – – – –
label | 9430b6c0-9bd4-5483-bf0e-75f37e58ab5a |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | ba185520-4ce7-5a10-b01e-e9dfcb318f4a |  | note | – – – – – – – – – – – – – – – – –
label | c99e59af-e153-5512-944c-b4c97331af8b |  | note | CATEGORY: HP
label | 7b76b7a1-362f-58a5-bdd3-b4fde7957047 |  | note | – – – – – – – – – – – – – – – – –
label | 03f962cd-9866-5968-8d12-56179b5ba365 |  | note | RESPONSIBILITY: Nominated Authority
label | 4647b8c9-1027-5e02-a82c-8388749f686e |  | note | – – – – – – – – – – – – – – – – –
label | 1c9df22c-672a-5acc-a64e-576c31c264bf |  | note | VERIFYING DOCUMENTS: This ITP
date | a4516bd0-2f9a-5e30-85f2-8faea10fd560 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | e30df8fd-d0a8-503c-a5ff-7113032df71d |  | note | REFERENCE: 610.26 (a)
label | 797e454c-d125-51b3-9f9b-515378730d36 |  | note | – – – – – – – – – – – – – – – – –
label | 171d7509-4395-516e-a0db-c0b4c7b5958a |  | note | ACCEPTANCE CRITERIA:
label | 3351d11f-b1e5-5775-948e-4f129dcd4822 |  | note | • Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | fc2ea57c-4ba8-57a9-9d1d-14e15488241b |  | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 9ffdbed2-6db7-54c0-8a11-e27868a30c2d |  | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | c759c006-0919-5f9a-9382-7433dfa75baa |  | textbox | Enter: Teambinder Material Approval number
label | 4097a1eb-5a36-5df1-92ff-666abaf8a6f4 |  | note | – – – – – – – – – – – – – – – – –
label | 19d9e1a8-7f48-50f3-ab52-fe403239e07a |  | note | METHOD: Document Review
label | 9f2aa242-0712-5fbf-8378-33b925df56af |  | note | – – – – – – – – – – – – – – – – –
label | 8c48164b-ade9-5d05-97ed-02102b6f81c4 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 82280f6f-eb73-5be0-8f96-ee9f26864715 |  | note | – – – – – – – – – – – – – – – – –
label | fa238b83-7459-5f3d-b098-555eb6281c3f |  | note | CATEGORY: HP
label | b72eb3f4-b68f-5987-bc23-0016de7162b9 |  | note | – – – – – – – – – – – – – – – – –
label | 803c782c-03f7-5c4b-99ad-d271f7d62d05 |  | note | RESPONSIBILITY: Nominated Authority
label | 51eb03f2-fdf9-5fb7-8315-7a95f414c7a7 |  | note | – – – – – – – – – – – – – – – – –
label | 1568d4cc-0073-5395-b690-746afd11381b |  | note | VERIFYING DOCUMENTS: This ITP
date | ea24d8d6-ce2e-5126-9a80-337757c41e84 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Evaporative Retardant
label | 5baecc5e-3a30-5ab2-ae63-7f147bf5323f |  | note | REFERENCE: 610.17 (f)
label | 4bfbf535-b4fe-50aa-bbaf-07ed453c7b47 |  | note | – – – – – – – – – – – – – – – – –
label | ba1fa5dd-ffd4-5030-b377-52e50907e893 |  | note | ACCEPTANCE CRITERIA:
label | 97b7839e-9c53-59a8-93fc-3d9b11662f6d |  | note | • Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 7cd0b209-e05e-583e-899f-08691d2e06b0 |  | textbox | Enter: Teambinder Material Approval number
label | 3c5a5845-0726-5f97-a3b5-e65042c0db77 |  | note | – – – – – – – – – – – – – – – – –
label | 2594326a-eff5-5aa2-982a-2499055e9db6 |  | note | METHOD: Document Review
label | 1803432e-5879-5104-8275-b68494668738 |  | note | – – – – – – – – – – – – – – – – –
label | 2a6c0e74-008e-5d5e-a029-9b76996c14d0 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | 064ecc01-0810-5b14-a502-30c5dbaeeec1 |  | note | – – – – – – – – – – – – – – – – –
label | d99a5b5c-8c4d-5b82-b59f-d9722c783e53 |  | note | CATEGORY: HP
label | 61317cb3-d735-516c-8e36-63b338ac6c3a |  | note | – – – – – – – – – – – – – – – – –
label | 28ccddef-1f15-5a93-95df-e11bb1110656 |  | note | RESPONSIBILITY: Nominated Authority
label | 06960362-f7cd-500e-84e7-2edd541adb18 |  | note | – – – – – – – – – – – – – – – – –
label | f3c73957-e34e-5499-96a0-ce4c70dc6cdd |  | note | VERIFYING DOCUMENTS: This ITP
date | 1c700ecd-159b-56e7-b932-feb752194e81 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | 6639e5da-4af4-5d75-9d78-7c13fab06341 |  | note | REFERENCE: 610.23 (d)
label | 3f523261-666f-5360-b4b6-3f080bd7260c |  | note | – – – – – – – – – – – – – – – – –
label | 3bd69980-f38c-5aa9-b154-f041669c1bd6 |  | note | ACCEPTANCE CRITERIA:
label | 3ef89396-c644-5620-9031-f9ba8e99434d |  | note | • Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | e74c98c8-1fac-5d88-b81b-10115649f161 |  | textbox | Enter: Teambinder Material Approval number
label | c8c26647-ad7a-56ea-a86c-c943ebdf2a48 |  | note | – – – – – – – – – – – – – – – – –
label | 5d81fd21-51b6-5eac-b0be-137d4aa69e66 |  | note | METHOD: Document Review
label | ca59e8b8-2e0f-58a8-9880-912306c9b560 |  | note | – – – – – – – – – – – – – – – – –
label | e9780934-1cd8-5843-90d1-9ce4fb731ca1 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | 0dc4b7cc-8a75-5e9f-8108-8d8f42d66957 |  | note | – – – – – – – – – – – – – – – – –
label | 69dccb87-f0bf-58e6-af99-6e249b686e3a |  | note | CATEGORY: HP
label | b99af72b-82fb-5348-b0fc-c8f36e60d259 |  | note | – – – – – – – – – – – – – – – – –
label | a5194b14-34dd-5bf8-8ab9-3a8cc44a313d |  | note | RESPONSIBILITY: Nominated Authority
label | 03cf607d-c46c-5658-80c2-4f0f976f9649 |  | note | – – – – – – – – – – – – – – – – –
label | 960fc029-df24-5242-a4a7-a885d1c0a701 |  | note | VERIFYING DOCUMENTS: This ITP
date | e96c8b4b-ea5c-56ae-a02b-56d45bc387c8 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
label | 56033bd8-92bd-5796-8c35-c40831f14d26 |  | note | REFERENCE: 610.18 (a) (i)
label | 35e6b3c0-b877-5e96-a3ff-f69e9559f9e8 |  | note | – – – – – – – – – – – – – – – – –
label | 7b90a47a-812e-52bc-b38b-751b04068132 |  | note | ACCEPTANCE CRITERIA:
label | a54bb344-117e-53aa-a7c2-fefd6dc1e492 |  | note | • Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
text | 8684a9b7-12d5-56d5-9d45-db7c126d4bdf |  | textbox | Enter: Teambinder Approval number
label | b181179a-f67d-5e1a-85dd-6c733837f0ce |  | note | – – – – – – – – – – – – – – – – –
label | f62964ae-0ac3-59b1-b26e-1d9cd85c50b0 |  | note | METHOD: Document Review
label | 4b10acd8-b4ea-5c4d-9bb3-0890e6bd2dda |  | note | – – – – – – – – – – – – – – – – –
label | 9d85f99a-cf85-5a2f-8d08-fd7469e22347 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 5c78c291-9a53-5388-9ab4-d13ebcd4b648 |  | note | – – – – – – – – – – – – – – – – –
label | 5c27cfea-ab5b-5633-b01a-2ad2e8fc485c |  | note | CATEGORY: HP
label | d935d828-8061-56a2-87d9-6973c22b3513 |  | note | – – – – – – – – – – – – – – – – –
label | 36132bea-d192-5d31-b560-d191ea84d975 |  | note | RESPONSIBILITY: Nominated Authority
label | 6c98a61b-9c34-5ee0-9703-98c31202668f |  | note | – – – – – – – – – – – – – – – – –
label | e383aecf-d2ab-5d65-86d4-37981485c631 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 28fd0526-6e8a-5366-b90f-a1939238b36a |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Concrete Sampling and Testing Procedure
label | 9bf97174-a24e-5a7f-8ef2-03eada6000ae |  | note | REFERENCE: 610.18 (a) (v)
label | a805eb1d-8e9c-57d8-90d1-d5b9add5db1c |  | note | – – – – – – – – – – – – – – – – –
label | f829bbc3-e103-5b66-952d-cc699a984ef3 |  | note | ACCEPTANCE CRITERIA:
label | 9045fa32-0310-5cc5-be53-b1fd7e13acf6 |  | note | • Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
text | cfef85b2-b3da-55d0-803e-d8ac23714bda |  | textbox | Enter: Teambinder Approval number
label | 1c4fbc93-1269-5efc-b872-04fe5351202d |  | note | – – – – – – – – – – – – – – – – –
label | 4bed68ee-fe9b-58ad-a6b2-7bd9c225e4e7 |  | note | METHOD: Document Review
label | 831ad3fd-4021-50b5-b024-1e47b1e15357 |  | note | – – – – – – – – – – – – – – – – –
label | 5a57d245-9c1b-5d73-b2ff-2fadda27ccb4 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | bfd37efe-69a8-5daf-ae97-88d65b0b7a03 |  | note | – – – – – – – – – – – – – – – – –
label | 4e23c772-2a6b-512d-bdc2-fe1d241f3311 |  | note | CATEGORY: HP
label | 8adfba96-a46f-53e6-8d44-bb716f6b0eb5 |  | note | – – – – – – – – – – – – – – – – –
label | f1bfa603-acdb-56d2-92a7-a749fd40df8f |  | note | RESPONSIBILITY: Nominated Authority
label | 4cdbd056-d66e-5d5c-b7b7-bd7898796e8d |  | note | – – – – – – – – – – – – – – – – –
label | 7c77ac64-7090-52a1-8bfc-e956749d5181 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | e871b1e3-f88c-56cf-9e79-a59735fc75d3 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
label | caae385c-daf1-5096-80d5-6e76fcf3803e |  | note | REFERENCE: 610.18 (a) (iv)
label | 205ea65c-59d0-5d1a-b924-3c305216d072 |  | note | – – – – – – – – – – – – – – – – –
label | 63e828c8-25f4-5ca1-9487-202138abed08 |  | note | ACCEPTANCE CRITERIA:
label | 25c4fd32-9872-505b-8ae3-3794b219eac1 |  | note | • Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | 70c7d522-dabe-5f3a-8f60-ca1e238a3cb6 |  | note | • Minutes of this meeting to be submitted to the Nominated Authority.
text | 5e124d36-c34b-5f73-952f-0a29d9018fa5 |  | textbox | Enter: Teambinder Approval number
label | f1ab8116-e6cb-55f7-8050-b4e8b05e98a0 |  | note | – – – – – – – – – – – – – – – – –
label | 7c250af0-74af-5183-94f8-4b8f31439b2d |  | note | METHOD: Document Review
label | 8414664e-b0bf-59e1-b87c-d911bc2ca7ac |  | note | – – – – – – – – – – – – – – – – –
label | c83c280c-3cdc-5a32-8411-213c718d7547 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 7dd82aa8-a08a-5521-948b-d6f2bf5f28be |  | note | – – – – – – – – – – – – – – – – –
label | 0f8f92c7-8b40-5b8f-a23b-bfd72ee3f645 |  | note | CATEGORY: HP
label | e05626c8-a85a-5493-aabc-d930b98b9b6d |  | note | – – – – – – – – – – – – – – – – –
label | 6f40aa42-7fce-5965-bdb5-65a85c6b8196 |  | note | RESPONSIBILITY: Nominated Authority
label | 117e5e8a-7dc8-5efe-bbaf-800a125da239 |  | note | – – – – – – – – – – – – – – – – –
label | e4ca6508-470b-538a-afa8-a14867092c44 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 935de38b-875d-58dd-b167-779cfd24228b |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
label | 7b079b2a-e460-5fa5-ad9b-a3bdace03df9 |  | note | REFERENCE: 610.17 (a)
label | 6f3e4406-d02a-50b4-898b-c7c7479ce32b |  | note | – – – – – – – – – – – – – – – – –
label | 920db9ed-9329-5cc4-af7a-70bc146dc982 |  | note | ACCEPTANCE CRITERIA:
label | 0a4024a7-4e2b-5af9-890e-bb420112e6ff |  | note | • Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
text | e055efc8-ef2a-5582-8eaa-209305554684 |  | textbox | Enter: Teambinder Approval number
label | 932a8aaa-497e-54b9-a6ff-63857f99eaf9 |  | note | – – – – – – – – – – – – – – – – –
label | 6804e185-8a41-5c20-9530-da731d18374e |  | note | METHOD: Document Review
label | a8758758-8069-5ea1-93fe-14a4da69d239 |  | note | – – – – – – – – – – – – – – – – –
label | 406b67c6-26ad-509c-8b38-1865531e387a |  | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
label | f33d510c-2f6c-5824-9e58-3d82647b3fe3 |  | note | – – – – – – – – – – – – – – – – –
label | 647e3d4e-41ab-50bc-99c5-9fd6b661995d |  | note | CATEGORY: HP
label | 476130d3-a3db-5124-8bc8-b693e66bbed9 |  | note | – – – – – – – – – – – – – – – – –
label | af68356f-ac24-5ebf-8bd0-b77e4b28c142 |  | note | RESPONSIBILITY: Nominated Authority
label | b3101959-9b81-5da1-a0e6-1045951ca3b9 |  | note | – – – – – – – – – – – – – – – – –
label | 8fe8d31d-41c0-56f3-8e6e-b9222b95d899 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0f9b0c2c-8121-598c-818f-876d6d8f130e |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
label | 8d1d5327-2f3d-5cf7-b9c0-159c304803f0 |  | note | REFERENCE: 610.23 (a)
label | a2fae9ce-8829-53f9-9600-69f764db72ca |  | note | – – – – – – – – – – – – – – – – –
label | 647b5494-9ad6-5f0c-9607-6f498389c039 |  | note | ACCEPTANCE CRITERIA:
label | 395fe7e0-0f1a-5ac3-bc15-44028df73a0b |  | note | • Curing methodology/procedure to be submitted for review to the Nominated Authority.
text | 5d9e38c2-2e22-59ff-b1d1-3bb2331228c8 |  | textbox | Enter: Teambinder Approval number
label | 5d66bebe-2585-54ae-91c8-c74d0261bc1e |  | note | – – – – – – – – – – – – – – – – –
label | a1f1ed26-7e2a-560a-8191-24bb6674e5b2 |  | note | METHOD: Document Review
label | 65934380-80fc-5908-ad01-58f43aa7209e |  | note | – – – – – – – – – – – – – – – – –
label | 32551c8c-e3b5-50af-9f9a-ba64cbabf626 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 664442af-3b00-58f5-904c-ddd5dee2581c |  | note | – – – – – – – – – – – – – – – – –
label | 1a271b99-68b5-5d00-94af-77c7ee40b495 |  | note | CATEGORY: HP
label | 1d4438f7-5fb6-520d-b4b5-d0eb063f87e2 |  | note | – – – – – – – – – – – – – – – – –
label | ec5231c3-7416-5fda-a132-0bf015154085 |  | note | RESPONSIBILITY: Nominated Authority
label | ada5b814-f946-5ab1-b287-eb7b3069c487 |  | note | – – – – – – – – – – – – – – – – –
label | 7c1acb6b-5183-50a7-aed8-04f948882459 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 64fd3522-7d64-523f-941f-205602481d63 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Concrete Drilling Procedure
label | 17343267-381f-5726-a936-f4cef22fa69d |  | note | REFERENCE: 610.46
label | 77edfcc6-c0ec-5af0-80af-753e3a52b2f5 |  | note | – – – – – – – – – – – – – – – – –
label | f159cfaf-8dea-522a-b680-fcfef2dc24d7 |  | note | ACCEPTANCE CRITERIA:
label | 21a3b103-bdb9-57e1-ab21-6dc927f6077e |  | note | • Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | f4016fe4-9acf-50fd-b258-225dbf67ae38 |  | note | • The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
text | b9e15548-a459-5a87-91eb-5c79dde545c0 |  | textbox | Enter: Teambinder Approval number
label | acc62fa3-0ffa-5105-9bed-2609e763ea35 |  | note | – – – – – – – – – – – – – – – – –
label | 6073fc64-af40-5f94-8bd3-512f1e5c7a88 |  | note | METHOD: Document Review
label | b494b93c-aa64-56a3-8318-6f412082f51e |  | note | – – – – – – – – – – – – – – – – –
label | b8e5889c-c01c-547a-bb16-ebca825d0d91 |  | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
label | ea740f62-d13f-5d7e-a27e-4528e5a6f790 |  | note | – – – – – – – – – – – – – – – – –
label | 4b19292a-060f-55e5-adc6-12c4cc12d640 |  | note | CATEGORY: HP
label | 3711cfc5-cca1-57fe-b97c-6174e9396a22 |  | note | – – – – – – – – – – – – – – – – –
label | 816b6a07-9cf5-5c96-b08b-e20d9160982c |  | note | RESPONSIBILITY: Nominated Authority
label | 363ef277-cfd1-5916-b9bf-67141f8bf46c |  | note | – – – – – – – – – – – – – – – – –
label | 36a51185-c15c-55a2-ad2c-1656720a4980 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | cc6922bb-50a5-53eb-ade1-5ef73ba7f9f3 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 Temprature difference measuring-Calibration
label | 855ed2c6-f89f-5826-a206-5b43c52db918 |  | note | REFERENCE: MRPA Quality Management Plan
label | 948f3be3-f84e-5300-88ed-445694ca49a0 |  | note | – – – – – – – – – – – – – – – – –
label | ddeff652-a29d-5534-8ed8-259f287deee2 |  | note | ACCEPTANCE CRITERIA:
label | 89df13bd-69e7-55da-9a79-0e270ebfe342 |  | note | • Calibration records are valid and up to date.
label | 1c0c6ae6-a3af-599b-8463-6ce49acd7d6e |  | note | Attach: Calibration certificate
label | 233555c0-2479-502b-a05e-a2a33dcf946e |  | note | – – – – – – – – – – – – – – – – –
label | a21ea0d1-f238-5f5f-b3dd-cecb9f7a8ff2 |  | note | METHOD: Document review
label | 4e157ca7-5d65-54f0-9f2d-d7b7e3c0552f |  | note | – – – – – – – – – – – – – – – – –
label | 8eb2fb9d-9d91-5d02-85ae-7866afb64228 |  | note | FREQUENCY: Where applicable
label | e7350344-2f3d-5254-86bf-17c42fed9e0c |  | note | – – – – – – – – – – – – – – – – –
label | e1074c1c-6958-5796-a564-07ac06274422 |  | note | CATEGORY: HP*
label | 0ed01805-89b9-5ee2-866e-010660664010 |  | note | – – – – – – – – – – – – – – – – –
label | 7f9a8e8f-8409-5e90-8273-4475ab9f06d2 |  | note | RESPONSIBILITY: PE
label | 513e80d6-6145-5212-a06d-ea5a924b68d1 |  | note | – – – – – – – – – – – – – – – – –
label | 3c546660-4785-505b-9e17-f803891bde9e |  | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
date | 1bf25038-4545-512b-8450-177fb45be54a |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 8ba0feac-b66e-59b4-939e-7d10bb7486fc |  | note | REFERENCE: MRPA Quality Management Plan
label | b753b8d3-af69-5ea9-87f5-6a588b823999 |  | note | – – – – – – – – – – – – – – – – –
label | 03f9870f-1883-5c74-8a4a-7b1511494891 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | f14d70bf-f0da-5b41-856f-0ae628e1bb23 |  | note | – – – – – – – – – – – – – – – – –
label | 6d3843b5-48c7-575a-81c0-0be6899e4f39 |  | note | METHOD: Document Review
label | 6bfdfa72-318e-5124-9dc2-ca2fec9bc05c |  | note | – – – – – – – – – – – – – – – – –
label | 7faa375f-d12a-5321-9725-d7434c8431ed |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 49fc630b-0600-512b-a67a-e93a1a06894f |  | note | – – – – – – – – – – – – – – – – –
label | 36dcf768-12fb-52c1-861d-831251476edf |  | note | CATEGORY: HP*
label | 6aefb2ef-9c05-51b2-b8d2-49ed49f9773d |  | note | – – – – – – – – – – – – – – – – –
label | ee7117fd-405c-5d03-86b8-30bb0d874f9e |  | note | RESPONSIBILITY: All
label | 0435f20d-060b-5a68-9334-ddcb7447312c |  | note | – – – – – – – – – – – – – – – – –
label | d853ab1b-6278-5e8d-9419-8cb8c733aad5 |  | note | VERIFYING DOCUMENTS: This ITP
date | 847fb292-a8b6-5af9-a5fd-ee5835de75c6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | f27cbe1b-aecd-5bbe-9664-90757d11167d |  | note | REFERENCE:
label | 44650ab4-667f-5800-9133-95b5f9248d32 |  | note | IFC Drawings
label | 53c5d341-e358-533d-a635-15133a642183 |  | note | 610.47 (a)
label | 42553cf0-cf67-57c8-bbc1-2d079988c890 |  | note | Table 610.472
label | b97ac717-9fa0-559f-99f8-9d736e185ca8 |  | note | – – – – – – – – – – – – – – – – –
label | e9d39b0b-0950-58c3-ae1d-5d9da2e722c0 |  | note | ACCEPTANCE CRITERIA:
label | e133fb56-1b87-58f8-af12-5f8440654cb3 |  | note | • Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | fe448c4d-ccf7-58d1-9015-2bde51327ec8 |  | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | ac3e5a97-814d-5160-9710-e035024d82f0 |  | note | – – – – – – – – – – – – – – – – –
label | f8cc10bc-dcc4-5a9b-bc29-8e9c455873e7 |  | note | METHOD: Measure, Visual
label | 1fc955f4-2443-5b76-897d-c8b1e91b247d |  | note | – – – – – – – – – – – – – – – – –
label | 65e2526e-4f90-5130-8848-ffcbcdb52ee7 |  | note | FREQUENCY: Each element
label | e435584b-00c3-5c26-87a3-6c83d3c2299e |  | note | – – – – – – – – – – – – – – – – –
label | d6582612-9b52-51ac-bd4e-90270b30fc3c |  | note | CATEGORY: IP
label | 1d760725-d4c9-5442-aa73-e50a80628f7a |  | note | – – – – – – – – – – – – – – – – –
label | de51f7f3-5cf7-598d-9fca-3ca793a11967 |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | 54d9bd50-c626-5781-bfea-c3ec4c19e4e7 |  | note | – – – – – – – – – – – – – – – – –
label | 08a7ee06-e84c-595d-9288-d7a2ad1c050c |  | note | VERIFYING DOCUMENTS: This ITP
date | fe398c0d-78d7-5cd7-8ff7-2d4824c47369 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Piles
label | ddd20467-8bfe-5c6a-a89a-106c92be1d88 |  | note | REFERENCE: IFC Drawing
label | 946c46e3-1415-50d8-98cd-19eea09dc610 |  | note | – – – – – – – – – – – – – – – – –
label | 66fdd58c-2e50-522f-aac3-17aa4ed105eb |  | note | ACCEPTANCE CRITERIA:
label | ef1b9b07-f773-5349-972a-28e77b2528ad |  | note | • Related piling Lots are closed.
label | 084c0f97-076b-5217-a5b0-6121468a6e45 |  | note | – Pile design strength is achieved.
label | de3b62c2-4e1b-5a42-8618-d2367041de5c |  | note | – Integrity and Dynamic tests performed and interpreted.
label | ad4a6fb9-88d2-5bb5-a932-3cb191e065e5 |  | note | – Pile is broken back to the design level.
label | f9d032d9-f66f-5e5f-8d18-85b20894804f |  | note | – As-Built Survey performed.
label | a80ee40e-cddc-5701-9920-e9c48085da00 |  | note | – Related piling NCMs are closed.
text | bf88119f-2d95-5679-8180-86332f1661bd |  | textbox | Enter: piling Lot numbers:
label | f75f2dcb-17f3-55d8-83dc-ccb27dfef6df |  | note | – – – – – – – – – – – – – – – – –
label | 9851cf31-db1e-5ba4-b1ce-6d9dbd6e52be |  | note | METHOD: Doument Check
label | d6071318-41d8-5dd8-960e-af3b74ab36b6 |  | note | – – – – – – – – – – – – – – – – –
label | 2cc2324e-d52f-5722-8d1f-4d9e5c0b607a |  | note | FREQUENCY: Each Element
label | 0bf71792-9da9-543f-93ff-1e8897e133e7 |  | note | – – – – – – – – – – – – – – – – –
label | 5802dc25-8566-5857-9a56-e0e1db3b2c85 |  | note | CATEGORY: HP*
label | 940ef90f-136d-5abd-bbfe-1ee65d8ef3ce |  | note | – – – – – – – – – – – – – – – – –
label | 9072513f-1d38-5342-89f4-505b220050ef |  | note | RESPONSIBILITY: PE
label | f61e508e-4b04-58ee-9ea0-59fff0d2df1b |  | note | – – – – – – – – – – – – – – – – –
label | b24d9dcd-b013-5c3d-9151-bb36946232f2 |  | note | VERIFYING DOCUMENTS: Piling Lots
date | 860a69f3-4d8f-5c11-976d-f6b692f7117b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Excavation support
label | e1b01e5f-7aef-5a33-ac61-182605089b62 |  | note | REFERENCE: 602.02
label | f17d13cd-6acc-5de5-ab5d-7024468de96e |  | note | – – – – – – – – – – – – – – – – –
label | c3f578f9-4b52-5091-b34b-743964f09d58 |  | note | ACCEPTANCE CRITERIA:
label | a154ebf1-471e-529d-b4e7-7ec5d618b8b4 |  | note | • For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
text | cf644a87-2fa6-55ae-a36b-d123b3276780 |  | textbox | Enter: Teambinder Approval number
label | f6621765-7deb-58c6-9e91-ffb0ca40d073 |  | note | – – – – – – – – – – – – – – – – –
label | 612ac64e-5c03-5dec-99cf-87e47f605802 |  | note | METHOD: Document Review
label | 43738dbb-0da5-542c-9c95-a85b39d21970 |  | note | – – – – – – – – – – – – – – – – –
label | 0372bfda-7421-5b5e-8e07-bfea56701950 |  | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
label | 7322e95f-b1eb-5b4c-9455-5afb75073f06 |  | note | – – – – – – – – – – – – – – – – –
label | 945aaa14-8092-5c62-a599-2e69292f1e11 |  | note | CATEGORY: WP
label | 5cdb349c-9947-5954-826e-f03d076a5742 |  | note | – – – – – – – – – – – – – – – – –
label | cdb6ce8f-0da2-518b-83ef-1e0a8a8be17e |  | note | RESPONSIBILITY: SE/PE/SPE
label | cf1bf5d5-5d41-5b31-989b-4cca237cc585 |  | note | – – – – – – – – – – – – – – – – –
label | 86c40481-5925-574a-8a3b-a95879ae6d6b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 1a0c2238-2853-5d87-ab9b-50cfc7910b93 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Excavation Inspection
label | d886ccb2-1955-547e-94b6-6afb781e2119 |  | note | REFERENCE: 602.03
label | a27ed158-8fbf-51ea-b545-bdebcd8ddea7 |  | note | – – – – – – – – – – – – – – – – –
label | 9e255c37-dcea-57e1-b77c-e45da9fb6457 |  | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | 3397f3d3-2545-52cf-9e2c-5dc3b6ba6076 |  | note | – – – – – – – – – – – – – – – – –
label | 014fc285-a637-59c6-8e72-1fe71edccbe1 |  | note | METHOD: Visual
label | a1057273-f4fb-5225-be79-7a224ba4f80f |  | note | – – – – – – – – – – – – – – – – –
label | 2d591db6-2b3a-55ab-9e4b-3a042f61a30a |  | note | FREQUENCY: Where applicable, prior to placing blinding concrete
label | 161a862e-67d9-510b-99df-071a63d7f727 |  | note | – – – – – – – – – – – – – – – – –
label | 8d1f508c-a882-5b43-87f2-427d8b81d99a |  | note | CATEGORY: HP
label | ee61aa3f-9521-5d47-ad75-cb99b4d9e8d0 |  | note | – – – – – – – – – – – – – – – – –
label | 064db2df-4a20-5468-ac14-6ed2692dd7cd |  | note | RESPONSIBILITY: Nominated Authority
label | afe9a744-0055-5aa0-ad70-1936f4452c0b |  | note | – – – – – – – – – – – – – – – – –
label | 39a6aa2d-73a7-563b-b8b0-e724bf7b68e2 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 5767be11-91b6-5365-b741-93a4718f7cc5 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Formwork Design and Construction
label | f989043c-a888-5fea-9c7e-9cbe8ae78563 |  | note | REFERENCE:
label | 225bc97b-5721-52d4-8034-3bbadc309547 |  | note | IFC Drawings
label | 9ec08803-66ac-57f6-8a09-f55203642feb |  | note | 614.04
label | 39e6699b-ccb9-552a-967c-4fb263951423 |  | note | 614.05
label | 934dbe8c-169d-5f85-a46b-21ccdcb7ea31 |  | note | 614.06
label | 312d84a7-f950-5c5f-b317-b50a325bf7b9 |  | note | – – – – – – – – – – – – – – – – –
label | 0299bbb2-b569-5f9c-9544-2c50aa30cee9 |  | note | ACCEPTANCE CRITERIA:
label | 7907d739-3bfc-592b-b36b-cb8dfefd26c4 |  | note | • Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | dcc4e3cf-41e2-5d75-89a7-7de97a78f25a |  | note | • Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | 3051bd3f-635c-5f9c-925e-472b09676885 |  | note | • Formwork shall not be placed where steel & fixtures cannot be inspected.
label | 425b575e-1805-58cb-9ab6-9da60ce912c8 |  | note | – – – – – – – – – – – – – – – – –
label | c555b353-6195-549b-bd31-a2d0c2686486 |  | note | METHOD: Document Review, Visual, Measure
label | 5353c29f-fe92-515e-9c1d-5a1561ab28ad |  | note | – – – – – – – – – – – – – – – – –
label | 07efec0b-f68e-5d3c-b789-6fbc8e29e10d |  | note | FREQUENCY: Each type of element
label | 144bab4e-15f7-50dd-bbcd-cf027e63d2f4 |  | note | – – – – – – – – – – – – – – – – –
label | bab9036a-ef98-5f2c-adec-0bb7b3174779 |  | note | CATEGORY: IP
label | 3937d2b2-6e77-5a1a-85e9-883216487af7 |  | note | – – – – – – – – – – – – – – – – –
label | 4e0ba5aa-c2c3-5319-a233-f10a482ab31b |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | ebc8675d-8cde-5474-8a87-0c476fac7464 |  | note | – – – – – – – – – – – – – – – – –
label | 9f9c4298-1d1d-5fa8-bf05-389ea71fea76 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0a7062ad-69fa-5266-ad9b-74c8b2d41e76 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | e0fcfe68-a581-5abc-bfe3-d3546aaf3371 |  | note | REFERENCE: 614.08
label | 9964a3b2-569e-52a4-b82f-601e3749902f |  | note | – – – – – – – – – – – – – – – – –
label | e08f99eb-c19f-5a83-8601-9f3e2b0b61ed |  | note | ACCEPTANCE CRITERIA:
label | 313efdac-cb4f-5c08-b47e-bc56fae6a1b9 |  | note | • The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | 8d83ac28-748c-5b02-ad7f-b165d16ebe14 |  | note | • Pile caps with heights greater than 2.0 metres
label | 62b106ea-1262-5daf-8074-7f50ec390b7f |  | note | • Any member for which self-compacting concrete is proposed.
label | 475d3dca-b7ca-55d3-8cc0-86b5343090ce |  | note | Attach: Attachment A
label | 43ad4170-69b1-59ab-8538-38840a803846 |  | note | Attach: Attachment B
label | fddf2cb5-0f69-5d43-adbc-8b665c1fa6f5 |  | note | – – – – – – – – – – – – – – – – –
label | 01a1924f-1740-5db2-9907-f1dff9187e67 |  | note | METHOD: Document Review, Visual, Measure
label | 5458ee80-9e29-53d0-b409-5ecf040e1d04 |  | note | – – – – – – – – – – – – – – – – –
label | 07c83501-d41f-5369-8b37-7608f7abec2f |  | note | FREQUENCY: Each element (where greater than 2m)
label | eef2a5fc-2be4-501f-a68a-9af88a2f254b |  | note | – – – – – – – – – – – – – – – – –
label | 5e7bdc60-6c9e-573f-9634-4e59a6b4f521 |  | note | CATEGORY: HP
label | 94524740-a166-5ac9-96cf-1d22a72d7dd5 |  | note | – – – – – – – – – – – – – – – – –
label | aaa188cd-aa66-59ea-9c43-89d4917fdf41 |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | 94d4427b-aba3-5201-904c-70f195bbd6e6 |  | note | – – – – – – – – – – – – – – – – –
label | 984043e0-2959-52bb-86e5-5284ef600921 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | ca1d067a-37d5-5aa0-b1e1-2492d6c4e0f2 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | 8533ddc2-cbfe-5ad2-b9dd-0dba4b1ad828 |  | note | REFERENCE: 614.08
label | d3d30b71-1b76-5ced-bb34-d70716af06ba |  | note | – – – – – – – – – – – – – – – – –
label | cdb48712-4f35-5593-8d59-150b118a4c4c |  | note | ACCEPTANCE CRITERIA:
label | 04458d77-ca8a-5c97-ba2a-954a3324e395 |  | note | • The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | c641968d-06bb-59fe-8ed3-62cfeae83f43 |  | note | • Pile caps with heights less than 2.0 metres
label | 4ab4b83a-ca1d-5350-9f32-f8283908b83c |  | note | Attach: Attachment C
label | 88865b05-f395-5a9c-94da-88aabeb2d48b |  | note | – – – – – – – – – – – – – – – – –
label | ed636648-d3a2-5f49-b94d-584db1eee48d |  | note | METHOD: Document Review, Visual, Measure
label | 9f805cc6-339a-5d97-9a0d-6d7161c020cb |  | note | – – – – – – – – – – – – – – – – –
label | 5c528937-cad6-5b3c-befc-ed4ed8cdaeef |  | note | FREQUENCY: Each element (where 2m or less)
label | b15f0711-44b7-5db6-aced-10d3bdcf8817 |  | note | – – – – – – – – – – – – – – – – –
label | 0a9bfa5d-ba02-5153-a959-ad44904011a0 |  | note | CATEGORY: HP
label | e54dd52b-1367-5caa-ac51-9993dfa56b60 |  | note | – – – – – – – – – – – – – – – – –
label | b8a93224-619f-5426-a7b6-210363ecce49 |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | 56b2d3d6-1589-5763-a8bc-101f0976bdf5 |  | note | – – – – – – – – – – – – – – – – –
label | d26c9106-d6e0-542e-adbc-7fce02ff3fd4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | f9e8a1b3-e9d1-59bb-ad2f-bb693f3b9824 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Pre-pour Survey
label | e2da9334-2255-5c8b-b7ee-d75f00d8a313 |  | note | REFERENCE:
label | f5881060-ef34-5ac6-954c-5ff4d84d2606 |  | note | 610.47 (a)
label | 264e9db8-e178-5d8c-910d-7dc83977075d |  | note | Table 610.472
label | f47f9c17-59d1-5ae6-b843-c950b6273195 |  | note | – – – – – – – – – – – – – – – – –
label | bef58e38-821b-54ff-af2e-77a3a44cd706 |  | note | ACCEPTANCE CRITERIA:
label | 2b894aff-08e2-5b5c-ae26-851afeccc642 |  | note | • A pre-pour survey carried out by a surveyor.
label | 69c4e856-a22b-5505-a1ff-ffda3d9ee1b5 |  | note | • Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | a8afea04-b18e-56b1-aa17-d9cfe7644f5b |  | note | – – – – – – – – – – – – – – – – –
label | 3d80ea93-709f-5b11-9305-5751e09a1a7d |  | note | METHOD: Measure, Visual
label | f90fac72-027f-57e0-a50d-0a51fc70be07 |  | note | – – – – – – – – – – – – – – – – –
label | 1ca91f2b-f160-5b4c-9827-65c9bae6ab37 |  | note | FREQUENCY: Each element
label | ccd5ba4a-d85e-5f79-8872-b951a625b5b9 |  | note | – – – – – – – – – – – – – – – – –
label | 7855acd7-4f97-53e5-a817-085f570030f9 |  | note | CATEGORY: HP*
label | 755a2c93-44d2-566d-ae90-22ec0941002e |  | note | – – – – – – – – – – – – – – – – –
label | 97ecbd8c-adf0-5ed5-8936-006b9f5204be |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | df858dac-b1a0-5a85-aa0d-68fa06d27166 |  | note | – – – – – – – – – – – – – – – – –
label | 4b13eb06-f99b-5048-9957-6345c475cb6b |  | note | VERIFYING DOCUMENTS: This ITP
date | e5acf8c2-f406-5797-9445-d3ee66f404be |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement Placement
label | 946334a3-fbc6-5467-b276-f85d24ff0a32 |  | note | REFERENCE:
label | 8d625f43-d333-5a35-b53b-aa79b32345b2 |  | note | IFC Drawings
label | f4846816-7eda-51da-9fd4-36196006940c |  | note | 611.06
label | f5a45f27-fcb6-533b-84ab-02b10756c37e |  | note | 611.09
label | 905d251b-cfab-5a44-b487-0c353f24a694 |  | note | 611.10
label | 531cbeeb-8306-5780-8b3c-8d05eda6b3f1 |  | note | 611.11
label | d0e3c5e6-2ef8-5a19-b0f6-658e0d89453b |  | note | 611.12
label | 7a788079-4991-5d0f-92e8-1aff26712351 |  | note | – – – – – – – – – – – – – – – – –
label | eff62d22-7c38-54e9-be0a-db7a6eb1676d |  | note | ACCEPTANCE CRITERIA:
label | 379eaca9-ef85-5dac-938f-55baaae530e5 |  | note | • The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 13cf7a8d-dff6-5046-96e7-132e9f957c62 |  | note | • Projecting reinforcement is the correct length and location.
label | 5e51e022-0028-54f4-8805-8570afa0b158 |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | 62d61194-84af-5f3f-8eb8-7a71e2cfff4f |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | ec75959e-be82-5fc3-abb3-c74a154c5a8b |  | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 31597d6b-f5cb-5603-bdbd-b9270ecd3d5f |  | note | • Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | c20b77ee-cb69-5a2b-8345-27d91f9c8946 |  | note | – – – – – – – – – – – – – – – – –
label | 0d959bc9-1e60-58f5-bf1b-07027bd65d2d |  | note | METHOD: Measure, Visual
label | 7c021ee0-426c-53a1-a8cf-31c64ab3176b |  | note | – – – – – – – – – – – – – – – – –
label | 224c947d-c41d-50f5-baa7-c0727b356d58 |  | note | FREQUENCY: Each element
label | 04a01851-8309-554f-87ec-48bba7fda981 |  | note | – – – – – – – – – – – – – – – – –
label | ff4055ff-d7d8-5d3c-8a03-3111cbafa43e |  | note | CATEGORY: IP
label | 58a0d69e-a905-5513-be92-8a2dad6a7e87 |  | note | – – – – – – – – – – – – – – – – –
label | d514293b-fad4-53e6-bc27-854bba6b531e |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 7c5ead58-6e21-5fc7-b2bb-8603f86a826d |  | note | – – – – – – – – – – – – – – – – –
label | d6cbaecc-f60c-557b-a0e4-6a220f60386d |  | note | VERIFYING DOCUMENTS: This ITP
date | ace4e8d2-cf74-5c41-80d5-c0bf0b580ee1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Cast-in Items
label | 867cd10e-9fa1-5126-aec3-f69c72b256d6 |  | note | REFERENCE:
label | b8749262-2713-5814-8b7a-c8e08854a61a |  | note | IFC Drawings
label | 52c108bb-fc94-56e7-8f96-76c7e39da906 |  | note | 610.47 (a)
label | fcf0d529-1cc4-5b40-8dc5-4dc061bb9955 |  | note | Table 610.472
label | eab73f90-f7a6-587e-9bed-7bca0adfa7ee |  | note | AS3810.1 Table 3.3.6.2
label | 3a68e729-61a7-55e5-8498-1514c4b015ca |  | note | – – – – – – – – – – – – – – – – –
label | 25c466ef-51b3-5911-b327-d3796665406f |  | note | ACCEPTANCE CRITERIA:
label | b7338832-9226-5bce-a052-cb4726d79475 |  | note | • All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | a5bf10ae-eb56-50c0-a6e2-2a18c4d3d6ab |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 38d02f77-5f3d-505f-9165-86eddac98571 |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | f8648265-6675-59df-84c1-e1555b939944 |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 681485d4-da3a-54d7-8b32-c6a05fac4e06 |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 381e3254-5a0d-5d6d-8316-734789d9c303 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | b7ccb225-8645-5f29-acd8-87a5011d69b7 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | a45ffd1b-1d71-5a85-99a2-82c498ca147e |  | note | iii. Ducts and conduit location = ±12mm
label | ce23c99f-63b1-5f33-885e-bc6e34f94f65 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 25b0497e-b2d6-59c8-8c17-833d8b8905fb |  | note | – – – – – – – – – – – – – – – – –
label | 0360ec34-6d47-59d0-b54b-f9a8b988d5ff |  | note | METHOD: Measure, Visual
label | b9fa1471-a31e-5173-9e41-05ef2f4863f5 |  | note | – – – – – – – – – – – – – – – – –
label | 6272cf5b-191f-55d5-b48c-25b43cf93fdc |  | note | FREQUENCY: Where applicable, each element
label | f985c651-6dba-5bca-b354-06a0a7c0e621 |  | note | – – – – – – – – – – – – – – – – –
label | 82782dc1-0ba4-5cd6-b469-71737a08a887 |  | note | CATEGORY: IP
label | 5b40996d-7ef1-57e1-83e3-1c6028b061c1 |  | note | – – – – – – – – – – – – – – – – –
label | 0b4cda05-bbbb-5b60-8b83-586d77bf1af0 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 641161a9-6db2-536b-a155-e367156c3134 |  | note | – – – – – – – – – – – – – – – – –
label | b82b3d02-0202-5dbf-9e00-35f498cffabe |  | note | VERIFYING DOCUMENTS: This ITP
date | e0b8b495-b1cc-51a2-b989-4a7ff7ae63ee |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Thermal Differential Monitoring
label | bb04dc58-efbb-50a2-951b-b6f8d90646d5 |  | note | REFERENCE: 610.22
label | 2e775b28-5b8f-5bcf-9367-d9272e671733 |  | note | – – – – – – – – – – – – – – – – –
label | ab406813-69d6-5023-9392-a77e7ca624df |  | note | ACCEPTANCE CRITERIA:
label | a19c79af-bb29-5c1a-826a-9aed6f1a0b5c |  | note | • Thermal differential monitoring thermocouples installed.
label | d97cd9d7-64f0-5675-8aa4-119f67ecbc11 |  | note | • Only applicable if the element has:
label | 1b32eb0a-3d19-5286-9654-b9a8f34a5f6b |  | note | i. the smallest sectional dimension exceeding 500mm
label | 4bf64596-e249-5224-810e-7fccd1ef9b97 |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | 4659e61c-49da-52e5-aed4-14630a3d2fbb |  | note | – – – – – – – – – – – – – – – – –
label | 79116c33-1704-5fa8-9463-f278aa0d8a82 |  | note | METHOD: Measure
label | d855ecbd-d9b8-5b41-8a5c-0456043d667c |  | note | – – – – – – – – – – – – – – – – –
label | db8b5cb6-e0fa-58ce-9095-262a9e334e0f |  | note | FREQUENCY: Where applicable, each element
label | 82a86f7d-de8a-511c-9647-1cd6a3c1c123 |  | note | – – – – – – – – – – – – – – – – –
label | c14e4684-9ecd-5e62-a698-00591e776e0a |  | note | CATEGORY: IP
label | 85fd0daf-202b-522c-8a3a-bda4bd4eef71 |  | note | – – – – – – – – – – – – – – – – –
label | f0dc3358-3d95-5882-9665-acbc01d7d8cc |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 00cf5eb1-01e8-5a74-ad7c-ba4318123a23 |  | note | – – – – – – – – – – – – – – – – –
label | 9d178f9d-1769-50aa-bf77-2fcd9c90c410 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6fe9a628-8965-576d-8ef9-c3190f3d936a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Pre-pour Inspection
label | e280bf7d-1f46-5dc5-8dac-88ed5cfa1b75 |  | note | REFERENCE:
label | c863f2a1-fd3b-5bab-a852-663592acfbb5 |  | note | IFC Drawings
label | c9d06aae-0ff3-5dd3-92e5-01d8eacdc9cd |  | note | 610.18 (a) (ii) & (iii)
label | 701d1f97-eb22-5fcb-a789-a5e283122816 |  | note | – – – – – – – – – – – – – – – – –
label | ea3fb228-a655-575b-b607-2e4f107d98c2 |  | note | ACCEPTANCE CRITERIA:
label | 1fb586fe-5db3-52f6-b260-2292d4898faf |  | note | • Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | ab4e2a15-425f-57e9-9fee-dcdb750cd443 |  | note | • All foreign material has been completely removed from the forms.
label | a2ab0acb-29b9-55f6-aa69-0c2cd6f6ee24 |  | note | – – – – – – – – – – – – – – – – –
label | f22ea55e-73e9-5bf4-bf35-694bf120569f |  | note | METHOD: Measure, Visual
label | 31207fa7-67c8-589e-b67d-dec9e6b8a733 |  | note | – – – – – – – – – – – – – – – – –
label | 0538fb70-86ae-5ff2-b904-c493a2ab187d |  | note | FREQUENCY: Each element
label | 4661ddbd-a134-505d-9620-321ff44698e8 |  | note | – – – – – – – – – – – – – – – – –
label | 5b243b78-9456-5c7d-a519-81d9d2298605 |  | note | CATEGORY: HP
label | caa873f6-2533-5ae2-be3f-38ea3beba202 |  | note | – – – – – – – – – – – – – – – – –
label | 491b9d42-c770-5125-9624-b4d5991d31d0 |  | note | RESPONSIBILITY: Nominated Authority
label | 2a0be196-46d4-5639-b096-1f83d6e7ad54 |  | note | – – – – – – – – – – – – – – – – –
label | 6c364b38-4938-52eb-baf2-7efc7bd6f576 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
date | b4e0e1c5-78c6-5890-8961-e58f0b10bbb8 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.10 Weather Conditions & Evaporation Limits
label | 6a6b66b9-11c8-5bbe-9380-98975f264607 |  | note | REFERENCE:
label | 7e778dbd-0fe2-5dd9-9e0d-3cfd16a8e382 |  | note | Hot and/or Cold Weather Concreting Procedure
label | b992e6b7-4a9b-5895-ba36-ec10eb1403b6 |  | note | 610.17
label | 71f948cd-5a1d-5033-a53d-d93d87df9b78 |  | note | 610.17 (a) & (e)
label | b2d7b4ca-003f-547c-a741-b4e3f12940de |  | note | Table 610.171
label | 8fd85287-6d6f-59b9-92ad-90888b74a524 |  | note | – – – – – – – – – – – – – – – – –
label | 8c9ec6f5-aa7e-511e-bf6e-7da142956de0 |  | note | ACCEPTANCE CRITERIA:
label | 2786a2e5-83fe-5437-abbd-c38230b66157 |  | note | • All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 86fdb993-4769-5568-b3bb-9085193b96e5 |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | c92f416d-f8d7-5d51-a051-da60e0792e4a |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | a7dfdafe-8cff-58da-9645-4783b1730e73 |  | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | da93e4af-f1d2-5908-be1e-66a0a6426e34 |  | note | Record: Required information on the Concrete Pour Record.
label | c1c81973-89ee-5e72-bfd1-f4e44b82d147 |  | note | – – – – – – – – – – – – – – – – –
label | 820f6d86-93b4-5537-99fe-d8268b5fc094 |  | note | METHOD: Measure, Visual
label | 0861ada3-9f2b-530d-9523-2cce9e7b7a06 |  | note | – – – – – – – – – – – – – – – – –
label | 8b80e31b-f382-5f1b-af0c-425de5f6b90c |  | note | FREQUENCY: Each element
label | 25faeda0-5465-5560-983a-f80b1243f6af |  | note | – – – – – – – – – – – – – – – – –
label | 9acd93b1-a42f-5e39-a98e-08cccaa1c785 |  | note | CATEGORY: IP
label | 43a366ad-10e7-5565-9b3b-db214d009c50 |  | note | – – – – – – – – – – – – – – – – –
label | 70068ffd-5059-5b52-92d9-8d2af6da476a |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | b9e58c15-9726-51b0-a9bd-71f63a951697 |  | note | – – – – – – – – – – – – – – – – –
label | e28dbd0b-fb00-5da6-97b0-4972dc26e8cb |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 0b5f8fff-4b94-59d9-9656-f16950bd7459 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Sampling Frequency
label | 1452cca1-dc72-57d7-86df-1b9e35738a50 |  | note | REFERENCE:
label | b3aceef1-ed07-5540-813d-cf7eb17017e0 |  | note | Site Sampling & Testing Procedure
label | 77ec71f7-092c-55f4-bfc8-fe63ada99426 |  | note | 610.16 (b)
label | de990f64-8e16-56de-adc9-a0c79673d991 |  | note | – – – – – – – – – – – – – – – – –
label | edac4b44-b1f8-5653-af68-e7e1c94185b2 |  | note | ACCEPTANCE CRITERIA:
label | b1ef43b6-82f7-5159-9d01-ed78d3a16956 |  | note | • Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | ae1f0b4e-15d8-5a97-a34c-2be72805138f |  | note | ○ 0m3 to 10m3 = 1 sample
label | b484235e-bd93-5297-bb2c-7e9504bf928c |  | note | ○ 10m3 to 25m3 = 2 samples
label | 49eb095e-c166-5abb-9f7d-74e7910eaa63 |  | note | ○ 25m3 to 50m3 = 3 samples
label | 24752c47-ba31-5ba1-b109-c94625b018d8 |  | note | ○ 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
label | 820e7551-6f72-552b-a01b-131c92c479eb |  | note | • For each additional 50m3 and additional sample shall be taken.
label | 1cadad57-646f-5da4-bd97-48cd3bfcf813 |  | note | • Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | d6857fdc-0baa-5fa6-a87a-3baf003f17d6 |  | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | ebb543af-8d72-59b1-b425-77f1b2aee9a2 |  | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | f2604a58-3560-5466-b450-41289d44e868 |  | note | • Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | 9c87c8e4-90c0-5cf8-82a2-63037e36fe5a |  | note | Record: Required information on the Concrete Pour Record.
label | c6725099-cf05-522a-93f4-4840f210738f |  | note | – – – – – – – – – – – – – – – – –
label | bd2ae5bf-e653-52f7-8c9d-7d4fe6d454f0 |  | note | METHOD: Test
label | 25768238-1f26-5a99-9598-b08419abe6a6 |  | note | – – – – – – – – – – – – – – – – –
label | 0d6004ba-31cd-5a35-a011-c7be320106c4 |  | note | FREQUENCY: Each element
label | 096c0802-62a3-5914-959f-a09a39093caf |  | note | – – – – – – – – – – – – – – – – –
label | a3df8aff-f5bc-553c-b8ff-787251123c8f |  | note | CATEGORY: IP
label | e4c31a74-8be0-5363-8a53-23e5806a302a |  | note | – – – – – – – – – – – – – – – – –
label | 7b1e685b-9ac8-5493-91a3-1d562e6ff637 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | a07abac0-3ffa-5fdf-8ca0-0bd1709de2af |  | note | – – – – – – – – – – – – – – – – –
label | 7fe2ece7-533c-57bf-a2e1-cf631f9b9e98 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 89c641c6-3d27-5e6e-b88b-76a275374e4a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Concrete Testing - Slump
label | 3ed606ae-8eb9-5202-a415-445af3193c61 |  | note | REFERENCE: 610.16 (c)
label | f2f03d88-ca8c-5301-a788-f2a6a270bf16 |  | note | – – – – – – – – – – – – – – – – –
label | 9132a241-bfa4-5a08-ba9f-a4f0ab85e75b |  | note | ACCEPTANCE CRITERIA:
label | 8af0e6ab-d1ed-52d0-aeb1-ab6551377fd7 |  | note | • Slump testing tolerances =
label | 32b74541-e010-5f55-bf6b-6de82399fc54 |  | note | <60mm = ±10mm
label | e44cc7a2-0e76-5f81-9a00-2365d3235430 |  | note | ≥60mm to ≤80mm = ±15mm
label | 4cc8d5ae-e808-51ea-a386-5a8e731ade93 |  | note | >80mm to ≤110mm = ±20mm
label | 6258816a-05e4-5463-b433-262a0fbcaaca |  | note | >110mm to ≤150mm = ±30mm
label | 7b33e682-64ef-5620-8ed1-b21e6c56dc09 |  | note | >150mm = ±40mm
label | c2498530-2ca1-5674-9316-2710b3796149 |  | note | Record: Required information on the Concrete Pour Record.
label | 97befe9a-65c8-5949-9ef8-59be5ed55d06 |  | note | – – – – – – – – – – – – – – – – –
label | 909cd082-9628-5875-9a10-1c93bb0d3b0f |  | note | METHOD: Test
label | 2d3d8eee-c3cb-5409-9f59-8f1bf1f17feb |  | note | – – – – – – – – – – – – – – – – –
label | cdc720da-70e2-5fdf-9198-b7c25a304b11 |  | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
label | a090156f-481d-5e75-8ed1-158287b61a0f |  | note | – – – – – – – – – – – – – – – – –
label | 9acfc5bb-fc3f-533b-bdaa-2231fb83227a |  | note | CATEGORY: IP
label | c4e877ac-032b-5a92-b0ff-cfb8d55b239b |  | note | – – – – – – – – – – – – – – – – –
label | becc38d4-0d8f-5c0d-874d-10cba0dd66cb |  | note | RESPONSIBILITY: Concrete Tester
label | 89da971c-5975-58b7-b7b0-992b9e2f74e3 |  | note | – – – – – – – – – – – – – – – – –
label | 0c7319b9-618f-53df-86a5-8e97e290528b |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 15707944-a36c-5c81-8c00-99a29672c0cc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Concrete Testing - Spread, Passability & Viscosity
label | 964ac323-56ec-5716-a287-08c5c5344836 |  | note | REFERENCE: 610.13 (b)
label | e1edf20b-a90a-5f95-999f-83abbee0c2c9 |  | note | – – – – – – – – – – – – – – – – –
label | 7172fae8-f067-5887-89e5-0163d98f71b4 |  | note | ACCEPTANCE CRITERIA:
label | ea33fcd2-c10a-58c2-95e6-ebb08a11c621 |  | note | • Spread range = 550mm to 750mm
label | ed6e5811-652a-59ee-8aa9-66c68f778bbe |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | b6a16d87-e02f-54c0-b676-33035907c92c |  | note | • Passability = ≤10mm (aggregate height differential)
label | 2cadf85f-9196-5edc-8a29-bb7179b95ee6 |  | note | Record: Required information on the Concrete Pour Record.
label | 10211731-1892-5fd4-8427-03062c8fdbac |  | note | – – – – – – – – – – – – – – – – –
label | 6687948d-aa5b-5170-a76b-5a55d4536bd0 |  | note | METHOD: Test
label | 27c6086d-120b-5a23-8ec6-f81d642bb247 |  | note | – – – – – – – – – – – – – – – – –
label | 61f06bd0-c389-5f9c-bd12-641a71cfbe44 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 81203724-6d9e-53c7-aea6-1354b5117e79 |  | note | – – – – – – – – – – – – – – – – –
label | 6c090134-c042-5985-a379-3f907f675c66 |  | note | CATEGORY: IP
label | 684bd9eb-e14a-5c10-876a-e553a54a8048 |  | note | – – – – – – – – – – – – – – – – –
label | f4e783dc-6b9a-5c9a-9f5f-477f8c312298 |  | note | RESPONSIBILITY: Concrete Tester
label | 2e7c1181-b10d-5075-97be-c44e6cd3aeae |  | note | – – – – – – – – – – – – – – – – –
label | fa262b0c-d93f-5615-9b26-26d8a0610869 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | ebf07ea4-09cf-5c56-a288-dafb48e5f45b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Concrete Testing - Compressive Strength Cylinders
label | d4d16b07-fa0f-54c0-9f3b-eb903a0c7261 |  | note | REFERENCE: Site Sampling & Testing Procedure
label | 2cb198d8-6769-517a-b96d-53f06eb3a223 |  | note | – – – – – – – – – – – – – – – – –
label | 7d4c5699-4f49-5525-a931-5d1ad12433a5 |  | note | ACCEPTANCE CRITERIA:
label | c31e9627-a352-54d3-b8c3-1f17d9893688 |  | note | • Correct quantity of cylinders manufactured per sample.
label | 44aff761-7320-5a4b-b331-75ed0c4927c1 |  | note | Record: Required information on the Concrete Pour Record.
label | bca6fea0-eb5b-52ea-9d32-b5d8f642fdef |  | note | – – – – – – – – – – – – – – – – –
label | 4e45590c-7700-535c-966e-1224d66f652a |  | note | METHOD: Test
label | a935b494-7df6-57bf-b545-af545c8f1ab2 |  | note | – – – – – – – – – – – – – – – – –
label | a0d2f127-494a-567a-ba4c-39cf08d956f4 |  | note | FREQUENCY: Each sample
label | 2c98093d-3c63-52b4-a55e-3d7604ca4f7c |  | note | – – – – – – – – – – – – – – – – –
label | f61e4e65-5043-5bc8-95c3-aaae69df8df2 |  | note | CATEGORY: IP
label | 41d04a20-b59e-5106-a6ec-19a212c8fd4f |  | note | – – – – – – – – – – – – – – – – –
label | 6a78ffea-800f-535d-9985-776b649ec151 |  | note | RESPONSIBILITY: Concrete Tester
label | 24a30eb6-73dc-54bf-b259-157780b51993 |  | note | – – – – – – – – – – – – – – – – –
label | f690b7aa-b4cb-50b9-84f1-a80e7aa92cd3 |  | note | VERIFYING DOCUMENTS: This ITP
date | 47ad1564-5f81-509d-b158-e861f1852689 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Supply & Discharge Rates
label | 5fb3d281-49cf-5e7a-836c-a6531534c344 |  | note | REFERENCE: 610.13 (a) & (f)
label | 48b85441-3bf9-5f2d-8ca6-702f8f638b3d |  | note | – – – – – – – – – – – – – – – – –
label | 8bbcdff3-9295-528a-b597-4da7d210a1ba |  | note | ACCEPTANCE CRITERIA:
label | 81b2aec8-fd8b-5da5-92ae-d1b8b8bf4853 |  | note | • Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | b2753004-47b5-5c36-9cae-86f2be94f089 |  | note | • No water is to be added once discharge commences.
label | 21e87a76-cb17-5deb-810b-5632d54aca18 |  | note | • Maximum time between batching trucks is 25 minutes.
label | f0c62352-1f52-557b-9af9-75530de12c8b |  | note | • Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | c4190844-30be-593b-ad55-5dc3d5fa192e |  | note | • Concrete that stiffens or is showing signs of stiffening shall not be used.
label | 4aeecf42-a903-56e0-b686-ae23614e4720 |  | note | Record: Required information on the Concrete Pour Record.
label | 17dfcb50-cfdf-533c-a6f8-23ec86163b81 |  | note | – – – – – – – – – – – – – – – – –
label | e3f2887b-9b1e-5bb2-aef8-bccd58fa5e6f |  | note | METHOD: Measure, Visual
label | b6c64d56-48b5-554c-9deb-85f4be729204 |  | note | – – – – – – – – – – – – – – – – –
label | ac5714bb-a84c-58ee-b713-3f1ead49f9ae |  | note | FREQUENCY: Each load
label | 2b486b31-ab25-55f7-a438-ccb78f741ca4 |  | note | – – – – – – – – – – – – – – – – –
label | 2e1eeca9-a1a5-5c93-8b12-f2bc8a5d4fba |  | note | CATEGORY: IP
label | 29c1c572-fe13-5068-9a36-bc9a52299c2c |  | note | – – – – – – – – – – – – – – – – –
label | a4e791f2-875d-5ca1-8a1b-8609236002b6 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 3a3276ba-7703-5c29-be6b-8570b0394c59 |  | note | – – – – – – – – – – – – – – – – –
label | 822fcb2a-634b-5ed6-bd12-96e0f571979b |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 173f4b65-f265-5a39-89e9-3542804b079d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Placement & Compaction
label | 0d4f9af7-78d3-5f64-90df-5d0152a99ad2 |  | note | REFERENCE:
label | c8e769b7-464d-5490-a1ea-68f6078949fd |  | note | Placement & Compaction Work Procedure
label | b5882319-1af3-5665-a52a-cf6db4d15e0d |  | note | 610.18 (a) & (b)
label | e63938c0-86cb-54d4-8ed4-fd84d9cf9d3d |  | note | 610.18 (d) (i)
label | 0ee29b00-ccd9-50b8-8787-63af43a998af |  | note | – – – – – – – – – – – – – – – – –
label | b1e5d60d-d63f-5eca-85ae-82a6bbc664da |  | note | ACCEPTANCE CRITERIA:
label | 031eff1a-ab4b-5640-8a45-297da9cffa14 |  | note | • All concrete batches are traceable.
label | bcbac07c-ff86-5da7-a67d-64defa0ef1d6 |  | note | • Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | b1d4bc77-c44e-5ab9-8f1f-0891b20677f4 |  | note | • Concrete is not dropped freely from a height exceeding 2m.
label | df84a8a9-0455-5b3c-811e-19686b95f9e7 |  | note | • Concrete is not moved horizontally by use of vibrators.
label | 6688d6b3-e9e2-58cf-91da-9e38b0a01192 |  | note | • Adequate compaction is ensured
label | 688ff7f8-e3ec-5281-a6bf-95c5e573deb9 |  | note | • Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | 59a3aea9-9aa9-596c-b61f-c8e6bad08a86 |  | note | • Concrete layers are not more than 350mm
label | e6dd75e7-f622-5a7c-9a4e-2ddc533f4026 |  | note | • Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | 1a5accbf-e60b-5229-bd8c-758205790647 |  | note | • Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | 277ddb4d-6cce-5fde-a91d-2759da590c34 |  | note | Record: Required information on the Concrete Pour Record.
label | 394e32b7-75c8-5181-b792-ce7c5d1ee497 |  | note | Attach: Concrete Pour Record
label | 1770c552-de39-5d0d-b2c3-02ee8e219bdd |  | note | Attach: Concrete Dockets
label | 4e40b09b-fff2-5fb6-9972-ae4b021c3133 |  | note | – – – – – – – – – – – – – – – – –
label | 47408aad-08ae-51a9-9e27-177346f7a7f0 |  | note | METHOD: Visual
label | 2c196314-af18-531e-8ee5-0343e32abb48 |  | note | – – – – – – – – – – – – – – – – –
label | 3dd4d41e-dd8a-5107-bcf3-2d2bca6b03fe |  | note | FREQUENCY: Each load
label | 0b539478-52d8-51bf-90d9-34bc27c755e5 |  | note | – – – – – – – – – – – – – – – – –
label | 618019fc-9f21-5711-8444-1951dcedfa85 |  | note | CATEGORY: SP
label | 5a342f99-2ca7-5a82-b86a-c2f259081974 |  | note | – – – – – – – – – – – – – – – – –
label | 60d14922-8fbd-571c-bdb1-8e2f66fa4090 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 1e373b17-cd35-5673-9811-24601276a920 |  | note | – – – – – – – – – – – – – – – – –
label | 54f270fd-6e69-558e-b07d-f39fa0b4593b |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 93f99e9f-3817-5a7f-b5c9-0c59667afe88 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Surface Finishes
label | 17a07c3b-0c9c-5092-b8e7-5d7ef2440076 |  | note | REFERENCE:
label | e2cef093-8321-5ac3-a611-53d8bf9edaa1 |  | note | IFC Drawings
label | 6c0dab3e-2e7f-5f3e-bab5-d07d87c7ef35 |  | note | 610.31
label | 8fd2183c-f12d-53f4-bee0-06a89e6f3aee |  | note | 610.20
label | 20d6eb92-0442-5d03-9116-aaf308382cc7 |  | note | – – – – – – – – – – – – – – – – –
label | c411d54c-176a-57c7-be2e-90182feddfb7 |  | note | ACCEPTANCE CRITERIA:
label | 9d9d3be7-69da-5d0b-a70b-3781c1bca755 |  | note | • Surface finish as per IFC drawings.
label | c3ed7cc6-01df-5118-aabf-c407f9edbb2e |  | note | • Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 67a5ff47-37c4-597f-9a66-569d677b9014 |  | note | • Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 6ce1c90e-f492-5529-9ca9-1196e5bfe540 |  | note | – – – – – – – – – – – – – – – – –
label | c87692a9-c00c-59ff-b8da-253f472063aa |  | note | METHOD: Visual
label | 402c3862-5dda-57a8-a8a4-b8d3d358dc3f |  | note | – – – – – – – – – – – – – – – – –
label | d204fd90-9d44-5a94-b125-f9f2f9d626be |  | note | FREQUENCY: Each element
label | 0b8b62b6-7744-5ac7-abfb-bcd5451bbe9d |  | note | – – – – – – – – – – – – – – – – –
label | ed60af92-ced1-5a03-b04d-9b68e1f7f9ed |  | note | CATEGORY: IP
label | af1e20d5-4c2b-534b-82ef-f9709d88f454 |  | note | – – – – – – – – – – – – – – – – –
label | ee023a2f-d3ff-5cbe-8b2b-a76fa6d50c7b |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | b2f8c654-292a-5585-9fc2-431117476bcd |  | note | – – – – – – – – – – – – – – – – –
label | 8f28e900-62ca-5520-ad77-7d71f05f09d3 |  | note | VERIFYING DOCUMENTS: This ITP
date | d7f93665-f5da-578b-bd5d-c13817fc1fc7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Curing-Top Surface
label | 0f59ca59-0855-5195-91f3-e6b3f4a0ccb6 |  | note | REFERENCE: IFC Drawings
label | f3a8c7d5-c866-584f-ba26-082ac553f93b |  | note | – – – – – – – – – – – – – – – – –
label | 83135336-c0d9-52df-989a-d6cffc1af6d1 |  | note | ACCEPTANCE CRITERIA: Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | cb15502e-b351-5197-a712-c470379e0f0d |  | note | – – – – – – – – – – – – – – – – –
label | 3ee2a640-e409-57a9-94c0-08f37056f3ab |  | note | METHOD: Visual
label | c587fedb-3c02-5383-9280-ac83b8aad24c |  | note | – – – – – – – – – – – – – – – – –
label | b2e1b64b-c764-5d15-9879-f46cf581278e |  | note | FREQUENCY: Each element
label | 232ac7fa-ce98-53bf-ad7c-e4f4ef03edf4 |  | note | – – – – – – – – – – – – – – – – –
label | 151bc871-f552-5583-adf4-3ed2a6de4927 |  | note | CATEGORY: IP
label | 3e85173b-7f45-5332-8504-241633f7a556 |  | note | – – – – – – – – – – – – – – – – –
label | e26de55e-358a-5e24-add4-03b4854d2780 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 32bf79c4-56b3-5d29-a8c9-4b3b316ddaef |  | note | – – – – – – – – – – – – – – – – –
label | a9735ceb-0b84-56aa-9dea-d7cbe1dd7328 |  | note | VERIFYING DOCUMENTS: This ITP
date | 53aa5c70-ac4d-5699-9940-7498d29e940f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Curing after formwork removal
label | f6f11f89-22f7-54ea-93bf-6baa2863f8f5 |  | note | REFERENCE: IFC Drawings
label | d86b3c7c-492a-5e88-9f49-3a3cdb708f9a |  | note | – – – – – – – – – – – – – – – – –
label | 2bec6921-e611-5c27-9cf9-9e0d43a6c20b |  | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | 4d87184e-6d52-59d8-8086-c3255461b2b6 |  | note | – – – – – – – – – – – – – – – – –
label | 56fc2a62-c96e-572c-924c-e2b3e97411fb |  | note | METHOD: Visual
label | e3b195ee-1973-5189-8d0b-8542368aeb94 |  | note | – – – – – – – – – – – – – – – – –
label | a64ac6d9-3f14-541c-b9a9-5d37ab7204fb |  | note | FREQUENCY: Each element
label | 429d030c-0900-5167-b21a-89a2cff2c253 |  | note | – – – – – – – – – – – – – – – – –
label | 3dcbd85f-e14b-5d51-b187-9b055676da6c |  | note | CATEGORY: IP
label | 59694591-5214-5a1c-9d1c-784b13918392 |  | note | – – – – – – – – – – – – – – – – –
label | 9742d88e-cc87-5a12-806a-474f85bf936f |  | note | RESPONSIBILITY: SE
label | 324052a2-c7c3-58ff-b666-6bca3bdaa285 |  | note | – – – – – – – – – – – – – – – – –
label | 9aa0d60a-c753-5c98-82c0-25c0e9b618a2 |  | note | VERIFYING DOCUMENTS: Thip ITP
date | 1344b742-e566-5bde-9b5a-0b484f5d4a36 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Thermal Differential Monitoring
label | 356309dd-0854-5aa7-99bb-5d0be899f125 |  | note | REFERENCE: 610.22
label | 3a1d378d-782b-5f50-a464-ba0ba53b8fe0 |  | note | – – – – – – – – – – – – – – – – –
label | ed121305-a9c2-5107-9a6e-058ca45afbca |  | note | ACCEPTANCE CRITERIA:
label | ec241c83-5d3d-5083-86e6-6338ebf6e009 |  | note | • Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | 28fb4f87-26b6-5fcd-9e66-7ca7eb267ac3 |  | note | • Only applicable if the element has:
label | 4d738641-cede-56f7-8582-987bf658f2e5 |  | note | i. the smallest sectional dimension exceeding 500mm
label | 11582b6a-e8c6-59f6-8d47-608a61da693f |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | 434fd5a8-188d-55d5-ba34-31524038cbdf |  | note | Attach: Thermal Monitoring Report
label | 50074c5b-9659-550c-81d6-588c8cc2c9bb |  | note | – – – – – – – – – – – – – – – – –
label | d6264ead-8a8e-5cd4-bb9d-e068b35bfd18 |  | note | METHOD: Document Review
label | 80c635b0-404c-5b21-a422-ac8ca570e910 |  | note | – – – – – – – – – – – – – – – – –
label | 7a149964-6c2a-5455-863f-a228545cc1c6 |  | note | FREQUENCY: Where applicable, each element
label | b1084a03-96f1-58d7-af4e-a8c87e7fe81a |  | note | – – – – – – – – – – – – – – – – –
label | 436067ff-2155-5453-b6e5-37d9d3ea9056 |  | note | CATEGORY: IP
label | 16e06079-300c-5dbe-9714-f5529165d448 |  | note | – – – – – – – – – – – – – – – – –
label | d314f234-d118-5e30-be8a-8143ec72c46c |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | fb3a9b50-f028-5ee8-9706-7a0eddc7213e |  | note | – – – – – – – – – – – – – – – – –
label | 3c702d29-ac73-59a3-9d0d-35d758b5e4b9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3f014c2b-65a6-5642-b8b9-6e34d5e56540 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Early Age Compressive Strength Test Results - Removal of Formwork
label | f97cc589-8fec-5062-8fe1-de15750ff948 |  | note | REFERENCE: IFC Drawings
label | e6ab1798-70ed-5d4f-85cd-a2868596af84 |  | note | – – – – – – – – – – – – – – – – –
label | 4899e8d1-d248-57f7-81fe-ef6e496c5ce8 |  | note | ACCEPTANCE CRITERIA:
label | 30527d45-e8d9-59e3-8bad-65ca8cfd1802 |  | note | • Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
label | 469a9cba-d5df-5fdf-b745-d02370ce6c26 |  | note | • Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | a16d936d-78a5-5e5b-8890-f6b8e2b01cfc |  | note | – – – – – – – – – – – – – – – – –
label | 78a04093-465e-5156-b793-e8c0bfd57edc |  | note | METHOD: Document Review
label | 596e31f8-c8ad-5526-8de4-74c3000a4f9e |  | note | – – – – – – – – – – – – – – – – –
label | e27ddfde-9871-5004-8a5f-3c8db77bdfc4 |  | note | FREQUENCY: Where applicable, each element
label | 23e2d4eb-8907-5be6-8fe8-943e14e2e74e |  | note | – – – – – – – – – – – – – – – – –
label | 62923a3e-809d-51a5-a854-a24fd95bc2ae |  | note | CATEGORY: IP
label | dbffe1df-7998-5493-abf5-88963a7f6f9b |  | note | – – – – – – – – – – – – – – – – –
label | 68d281aa-1766-5001-95f0-ef0dccc71294 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 8cba79cd-9494-5a03-b0aa-d7c6a9056173 |  | note | – – – – – – – – – – – – – – – – –
label | a191609d-7c5d-5001-a8cd-833a7fe5212e |  | note | VERIFYING DOCUMENTS: This ITP
date | ef0dcd2d-42b0-51c7-add5-68e3297794de |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Surface Inspection - Cracks
label | 7af2a1ca-edd0-50cf-b4d0-25c8ff806458 |  | note | REFERENCE: 610.24
label | 9b3f5b88-4753-5f79-9700-e49ae864145e |  | note | – – – – – – – – – – – – – – – – –
label | c99fc664-62a4-5d9b-9116-330a97d0bcf3 |  | note | ACCEPTANCE CRITERIA:
label | 6a6ff5d0-170c-50b8-9d54-5a2d03e0a974 |  | note | • No cracks greater than 0.2mm (exposure classification B1)
label | 5703a680-b7b7-5fa2-a7ad-83bfec04df25 |  | note | • If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 8c2403e8-3cff-5c64-8fbe-dd2c49ff0719 |  | note | – – – – – – – – – – – – – – – – –
label | 242108b2-3c07-5e1d-b91b-145a49991c1d |  | note | METHOD: Visual, Measure
label | f231c696-b940-5eef-b0ed-9226e721a9c4 |  | note | – – – – – – – – – – – – – – – – –
label | 212e4dc5-2b8c-5fce-b09d-5403e6af8bc3 |  | note | FREQUENCY: Each element
label | a6fd48ff-a784-5310-a993-8093acb9be37 |  | note | – – – – – – – – – – – – – – – – –
label | 1ede8642-d976-5d3b-9a79-a1f7deb4509e |  | note | CATEGORY: IP
label | 40e98d04-108b-587e-8e89-c78ef6a20996 |  | note | – – – – – – – – – – – – – – – – –
label | 6199c9a6-99c7-5b81-91bb-e1e178264d13 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 31046137-8038-5021-871c-ea8440770daf |  | note | – – – – – – – – – – – – – – – – –
label | fcd1312c-1e35-5c03-9ca1-c0a91bf83d2b |  | note | VERIFYING DOCUMENTS: This ITP
date | a72b1611-5160-59af-8458-4ddac403bb37 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Surface Inspection - Surface Finish
label | e6a402fc-ab6f-5891-952c-78f328e663a9 |  | note | REFERENCE:
label | db75d93b-ad09-533c-9665-f9e760e87861 |  | note | IFC Drawings
label | 4377cc09-261c-5c84-80dd-fee1f5990e41 |  | note | 610.31 (a) - (n)
label | afe5f5c2-78c6-5862-bac2-de7d772e749f |  | note | 610.32
label | c79b192d-c67b-5142-97a7-84325db9f2f4 |  | note | – – – – – – – – – – – – – – – – –
label | 792b2c99-730d-5d18-92ea-82f92262ba6a |  | note | ACCEPTANCE CRITERIA:
label | a05a05db-7317-5b5e-bcbd-a592788c4f77 |  | note | • Comply with the IFC drawings and specifications.
label | 8e247ef4-6538-5909-90f6-55ea757698ac |  | note | • Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | 9a2e1b5a-73c1-53c6-9333-84ec9706743b |  | note | – – – – – – – – – – – – – – – – –
label | 16f057fd-985e-50c2-bf77-fa428d67a481 |  | note | METHOD: Visual
label | ec8aed63-ccf6-5415-b58e-82cba0e9f64c |  | note | – – – – – – – – – – – – – – – – –
label | ffb3dc50-b88f-5e12-804a-66f32eb94dc4 |  | note | FREQUENCY: Each element
label | 4047f76f-4ac7-5a73-ae20-fd2f1c01a675 |  | note | – – – – – – – – – – – – – – – – –
label | 720330b4-4cf8-528b-985c-ffddd05226d6 |  | note | CATEGORY: IP
label | 2e810ca5-a7f5-56a0-8d3c-cb47c8eaf465 |  | note | – – – – – – – – – – – – – – – – –
label | 9a3bfce9-5712-5422-918b-b18c6daf927f |  | note | RESPONSIBILITY: SE/PE/SPE
label | f589ae8a-8777-5683-88b0-abf07bb9e88e |  | note | – – – – – – – – – – – – – – – – –
label | f9995a79-33f5-5bb1-a044-1d63c5a5a3a7 |  | note | VERIFYING DOCUMENTS: This ITP
date | 09098749-cf7a-50f1-9863-cbefe3109834 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Measurement of Concrete Cover
label | d90c9a97-a1bd-5ce1-b31b-953a7001895a |  | note | REFERENCE: 610.34
label | 64fe079f-e963-5d7a-b44b-d0498e581f24 |  | note | – – – – – – – – – – – – – – – – –
label | 64606b8f-7495-5cf8-97c2-7de09a704775 |  | note | ACCEPTANCE CRITERIA:
label | 7e6951aa-1f62-5bad-8eee-4a60c50f0d87 |  | note | • Concrete covermeter check one 3m2 test area for every 25m2 exterior surface area.
label | e28594b2-7851-5708-b4fa-38d9bd14ec73 |  | note | • Minimum 10 no. measurements recorded in each area.
label | fcf90f7a-ba4a-56f9-bbd9-4d07153ce411 |  | note | • Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | 3448decd-38cd-5ad8-bfa0-45de4a255012 |  | note | Attach: Covermeter Check Record
label | 5d5c3fc0-5b42-5082-96f6-f4f999de3b93 |  | note | – – – – – – – – – – – – – – – – –
label | a516d570-bacf-5413-b069-9f0d5de52c2b |  | note | METHOD: Measure
label | 9f2049a9-f1a9-5829-a66c-86645b7c600c |  | note | – – – – – – – – – – – – – – – – –
label | 71e9cdab-06d4-5f44-a310-cd1900bd8591 |  | note | FREQUENCY: Each element
label | 1d61ac57-f022-5380-99c6-a78a8234609b |  | note | – – – – – – – – – – – – – – – – –
label | fd45f040-b717-5f67-ba9b-9f038eab4f65 |  | note | CATEGORY: IP
label | 3872fd87-eabc-5576-9beb-999457bb5aa9 |  | note | – – – – – – – – – – – – – – – – –
label | 57b3deb8-1b42-5a95-95cb-106a84561b39 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e9823746-001d-5e03-9d90-c8def7f44923 |  | note | – – – – – – – – – – – – – – – – –
label | c0ff9809-8794-5707-b7d0-cf2b28c7c4a3 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0dc690be-cce7-5027-b417-c15f0c9084e0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | 0a7ac88a-2c2f-5d4d-8ec8-0ca532e87171 |  | note | REFERENCE:
label | 3335375b-8e54-5988-9c08-3a691e7b4b18 |  | note | Early Loading and Trafficking of Decks and Approach Slab Procedure
label | 639c0854-dbf8-5a19-8af3-cd39f3c8d236 |  | note | 610.35
label | 52b0e50c-3a03-564a-9167-bb07c77e957c |  | note | – – – – – – – – – – – – – – – – –
label | f52006cd-023d-5ff9-b2ff-b0019240dda6 |  | note | ACCEPTANCE CRITERIA:
label | b4c24037-ba8d-5af5-a36b-e941fba59156 |  | note | • Fill is not placed against concrete within 14 days of pour.
label | 50b467be-8bcf-56c3-b1a3-7d2fbd8e0dd7 |  | note | • Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
label | e2c2bcfc-f99d-5704-a04d-3f5f14c434a1 |  | note | Attach: Concrete Test Results or Maturity Test Results
label | 6e17f5e7-5cf9-5063-bcf1-4f36d12d10ff |  | note | – – – – – – – – – – – – – – – – –
label | 35a04116-43ad-567d-a674-989837a91c83 |  | note | METHOD: Document Review
label | 9b3546cc-da67-5cdb-b386-224d4a5d9359 |  | note | – – – – – – – – – – – – – – – – –
label | b00b1924-dfde-5707-8dd8-bc25b83b9d2f |  | note | FREQUENCY: Where applicable, each substructure element
label | 9b888b61-781c-5235-8b84-9651109270e2 |  | note | – – – – – – – – – – – – – – – – –
label | 4ae874a2-27fa-5c4b-bfab-c438fa2e7eec |  | note | CATEGORY: SP
label | 712bca8e-a87e-56ed-8ae1-03d19815d806 |  | note | – – – – – – – – – – – – – – – – –
label | f81ca7ae-e75c-5d54-a202-1b87b884c3df |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 82dc7313-25f6-52a4-9cb6-4feb84e9de1b |  | note | – – – – – – – – – – – – – – – – –
label | 1f000f91-cea3-55c2-bd6f-d8d665f269cc |  | note | VERIFYING DOCUMENTS: This ITP
date | 5cbf1990-a102-59ea-af70-b96de977f938 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Compressive Strength Test Results
label | 373b180e-c399-5edc-a8c4-abb3f61811e8 |  | note | REFERENCE:
label | 9869a9ce-eda9-5827-94ce-e72550e4bb9d |  | note | IFC Drawings
label | 098f940f-0afa-59b0-b7e4-9569e3647286 |  | note | Table 610.05.051
label | be55346d-e7e8-5c7a-bb27-e3c930897c38 |  | note | 610.16 (g)
label | 6700f49c-7396-5368-a621-6bc904818859 |  | note | – – – – – – – – – – – – – – – – –
label | 1d81514e-4e3c-5b93-aef0-0444d34b0df2 |  | note | ACCEPTANCE CRITERIA:
label | 610b03b6-3b8e-5aaf-aa34-aabf2388e14d |  | note | • 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 73d90ec9-f250-5611-ae22-250045969eb4 |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 0ab90d7c-2bc2-53b6-ae5c-57930c936fa9 |  | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 017a3bc0-5288-5669-ae41-f9a378d966fa |  | note | Attach: Compressive Strength Test Results
label | 4d04eae6-118e-5e2d-b558-707aeb9379f6 |  | note | – – – – – – – – – – – – – – – – –
label | 865d27f3-fe01-599d-8851-7447ed2fe9f7 |  | note | METHOD: Document Review
label | 38bb6a54-bb5a-5f92-ad1d-779b11c8957d |  | note | – – – – – – – – – – – – – – – – –
label | 8e369124-91ed-5a4a-9172-d7e5890fcb6a |  | note | FREQUENCY: Each cylinder
label | 47b44ee6-ae73-552b-a691-d17f16a85286 |  | note | – – – – – – – – – – – – – – – – –
label | a3b6b4cd-dbd5-5221-987e-cefb73adce2f |  | note | CATEGORY: IP
label | 38ba2c6d-a04b-5903-bc77-6f7e3f124d85 |  | note | – – – – – – – – – – – – – – – – –
label | b65358ce-0191-5f0d-ab17-4df2762fe219 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 42a82826-d716-51f1-951e-3fa4285d904b |  | note | – – – – – – – – – – – – – – – – –
label | aa45e722-6947-5e10-bdf8-a4e3c83a5a0b |  | note | VERIFYING DOCUMENTS: This ITP
date | bf7d65f5-9dac-52c1-b569-4197022fc37b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.10 As-built Survey
label | d7e8ff7c-50e7-5cf4-ae8c-30caef91875c |  | note | REFERENCE:
label | 1599c253-205e-5c2f-98d5-fcac9a04600b |  | note | IFC Drawings
label | 44c95ad8-95a7-522a-9504-ba03ed72444c |  | note | 610.47
label | 9137267f-b496-5b42-9148-6e6c469c8735 |  | note | Table 610.472
label | 35b35e41-235a-543f-95d6-1e75a4cfb7eb |  | note | – – – – – – – – – – – – – – – – –
label | 6bc27c65-15be-58e9-b0af-b00736193966 |  | note | ACCEPTANCE CRITERIA:
label | fa72a6d3-7dcd-55bf-9ae0-1b8a76165ed2 |  | note | • Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | a38585cc-2b53-5fd5-a638-412b8714c8ba |  | note | Attach: Survey As-builts / Survey Report
label | bc890b9a-90cf-5e9d-9a6e-3eeb6b47677a |  | note | – – – – – – – – – – – – – – – – –
label | f0cc7762-626d-587c-972f-f96193708d07 |  | note | METHOD: Document Review
label | 7b877311-d6e9-59db-bf02-525d6cec871f |  | note | – – – – – – – – – – – – – – – – –
label | 85180d42-702d-55d9-ba6f-4060d963d8da |  | note | FREQUENCY: Each element
label | 0ba069b7-8b18-5188-8fd7-f9968134d756 |  | note | – – – – – – – – – – – – – – – – –
label | 47fbf245-1794-5764-b06f-e5dcd8e0adc7 |  | note | CATEGORY: IP
label | eada6bb0-f5f2-5cb9-a55f-de282b6da14e |  | note | – – – – – – – – – – – – – – – – –
label | e9d5238b-a695-5ca5-b526-ca5684857dce |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 278d7b5a-4688-5104-b20b-5ae2b62c4090 |  | note | – – – – – – – – – – – – – – – – –
label | 3297b5b4-0e03-5b00-907b-f9e2a70304a0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1a8d7f9b-471a-5a79-8a93-3f6d995ff20a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.11 Non-conformance Report (NCR) Closure
label | 4bacd47b-0e8e-56d2-8534-1c2ceb44f669 |  | note | REFERENCE: MRPA Quality Management Plan
label | 1fc5516a-4c6c-5c6d-907f-23ae916f36f3 |  | note | – – – – – – – – – – – – – – – – –
label | 471483f7-2a71-5d17-92db-d2206b000461 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 1ab24e33-7231-5ea5-9b88-36e2a2bd063e |  | note | – – – – – – – – – – – – – – – – –
label | 0df896f4-206e-5f2b-a5b4-a66006a2a6cf |  | note | METHOD: Document Review
label | 84b6316c-70ab-5af6-89f1-a11ecb983387 |  | note | – – – – – – – – – – – – – – – – –
label | fa93e875-9310-5968-a442-9757c30613ba |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | e2692000-6e84-591a-a47f-d6ff9ba05d8b |  | note | – – – – – – – – – – – – – – – – –
label | ea7b90fc-8edf-55f0-a10a-d0e631908d4f |  | note | CATEGORY: HP*
label | c721f139-be9f-5d60-afa5-4d53a5fea655 |  | note | – – – – – – – – – – – – – – – – –
label | 048f8b1c-d034-561d-b120-66e8ad92953f |  | note | RESPONSIBILITY: SE/PE/SPE
label | 15392e12-8f34-5a83-8e86-77841115efef |  | note | – – – – – – – – – – – – – – – – –
label | a1505510-008d-5ced-9058-6eb9022f5619 |  | note | VERIFYING DOCUMENTS: This ITP
date | 41696981-4ed7-5a00-a6a1-217fc4d05550 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 223c6d4a-d884-5c06-a58e-f662e2e97602 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | fb790ecb-babd-5b44-8ade-9caead5801ec |  | textbox | Name:
text | 4ea57428-8664-5b98-bc5e-0ee1638c1fc4 |  | textbox | Position:
date | 98e44f9c-2d50-5830-8b8a-9bdfb0330e1a |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-017-STR-Structural Concrete | itp |  |  |  | Yes | ITP-017-STR-Structural Concrete Rev 0 | e3141fb2-2c58-41ba-b75d-43f2e0859876
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 8e3fd827-23da-528b-a230-20c3c2c89aaa |  | note | Document Title: ITP-017-STR-Structural Concrete
label | ddb77cab-ae24-54ea-8b73-23664de396f5 |  | note | ITP Description: Structural Concrete
label | 19ed3a55-0a41-5052-93c9-179f2b029aad |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | a71119bf-b777-50f7-954e-ba2ca6de553e |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | d27bf423-c337-55ef-925c-671faa7f8e24 |  | note | Revision Number: 0
label | 7317f4b8-8f41-5ea5-9237-f6eb860fc18a |  | note | Revision Date: 01/12/222
label | 7669651d-bbbd-5ae7-9114-81e9e0410d7d |  | note | ITP created by: Victor Mira
label | 26fa0fbd-f335-528c-b9c3-9d306cf79ddc |  | note | ITP approved for use by: Victor Mira
label | 2305510d-d3cd-55ff-8a8a-b8aa1f3abe70 |  | note | 1.1 Non Dependent
label | 08da34f5-e5fc-56b2-84d8-171ed92875b2 |  | note | Reference: VicRoads Section 602 October 2007
label | 63be11af-f157-5dd6-a93e-b9bb7cfcdbbe |  | note | 1.2 Non Dependent
label | 490e0a0e-0aed-5f32-b5ad-643122ae5b16 |  | note | Reference: VicRoads Section 610 February 2020
label | 54abfd2a-61b7-5f50-8ce5-152fd9457965 |  | note | 1.3 Non Dependent
label | 1ee8208b-c713-5ef4-add8-2767f3e36b71 |  | note | Reference: VicRoads Section 611 November 2018
label | 777f1f43-713f-56d5-86da-bf51790f65ea |  | note | 1.4 Non Dependent
label | e6d5ca89-5bba-546d-9052-16ccb886f3e5 |  | note | Reference: VicRoads Section 614 June 2017
label | 2c97e495-7c0b-510f-af7d-2475e4addfea |  | note | 1.5 Non Dependent
label | dc7d2331-3fd4-5d15-8c4e-2454a19e43a6 |  | note | Reference: AS3810.1 2018
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | e28f92aa-9a59-57ea-9ce7-d2e7aef3119a |  | note | REFERENCE: 610.07
label | dea212d4-5959-5eba-b529-23c27edde3fb |  | note | Table 610.071
label | 10b8e4cd-0a94-5481-8200-da1ed91383b5 |  | note | IFC Drawings
label | 59293ada-3eb4-5f21-8ac9-dde06e670471 |  | note | – – – – – – – – – – – – – – – – –
label | f43e83e1-2e53-557b-98b2-9b07173b66d1 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | e009e038-bd8c-5b95-b3d7-f84f80614218 |  | note | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 53da3fd5-3a85-5a36-b29a-337d72ad46e3 |  | textbox | Enter: Teambinder Material Approval number
label | 930101ee-f8f1-55bd-8fa9-41bc077285c4 |  | note | – – – – – – – – – – – – – – – – –
label | aa1dad1c-f88d-5cf9-b503-796b5acc197e |  | note | METHOD: Document Review
label | a136ba88-62ec-5b95-80fb-b15fc7f12936 |  | note | – – – – – – – – – – – – – – – – –
label | a1ce5216-c1d2-5982-9f87-e4842d3413dd |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 56a3f1a3-a17b-52d5-aede-c3528fb034d5 |  | note | – – – – – – – – – – – – – – – – –
label | ec0042a2-5207-593a-b6a1-c470888d5b70 |  | note | CATEGORY: HP
label | db4baf20-1c84-5615-9789-d376e1ee016d |  | note | – – – – – – – – – – – – – – – – –
label | c7aa5e4f-0423-58f0-ab25-008bcd2abd28 |  | note | RESPONSIBILITY: Nominated Authority
label | 0ece13c6-b2e8-51e1-9bad-2195c28f44a5 |  | note | – – – – – – – – – – – – – – – – –
label | 9533b8c5-605f-5568-be0d-359d8b6bfe98 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 957e21fe-1ede-523c-9325-3a7ecfefef87 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | a8d2e2a4-10a7-5d7c-81cf-7909bfd4f53b |  | note | REFERENCE: 611.05 (a)
label | 76414d22-7218-5f97-a553-af55ba5d3797 |  | note | – – – – – – – – – – – – – – – – –
label | 13efe343-b8b3-5509-ac26-31ac3437b9b6 |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | d2ae9937-e219-5feb-a6a9-1d4a1421af06 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 5cb1d591-587f-518e-88a5-62990b2535e1 |  | textbox | Enter: Teambinder Material Approval number
label | 08d087aa-8b86-5eb3-8a19-7f5908b58ec3 |  | note | – – – – – – – – – – – – – – – – –
label | 4816a714-e406-5c17-823a-5b42809879a3 |  | note | METHOD: Document Review
label | a8e54af3-af8e-504c-92a8-5c0489321ff8 |  | note | – – – – – – – – – – – – – – – – –
label | be907d7d-faf3-5ff2-a286-a62dc101a20f |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | eac016c3-5d03-5922-bbe2-20d9aff91614 |  | note | – – – – – – – – – – – – – – – – –
label | b7ffb5fc-e94c-56c4-a173-f00f8a90b621 |  | note | CATEGORY: HP
label | 58c5d631-be7b-5655-b51b-b37623337383 |  | note | – – – – – – – – – – – – – – – – –
label | ed2d3bd8-1b9a-5cd5-a9af-b144361abab7 |  | note | RESPONSIBILITY: Nominated Authority
label | b1c067f9-3811-5b93-a4ba-2154b37300e5 |  | note | – – – – – – – – – – – – – – – – –
label | dfce3f5e-9861-5067-b266-dc9a58877520 |  | note | VERIFYING DOCUMENTS: This ITP
date | bf3150b8-95a6-50f5-988a-c62f3cea2894 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 93390d74-08e4-5ba0-92b2-44e28bdf3c79 |  | note | REFERENCE: 610.26 (a)
label | c8c9abc2-8d8a-5f49-a53e-1b257209c261 |  | note | – – – – – – – – – – – – – – – – –
label | e150b8fe-9681-59b1-a4c5-4abc740133ea |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | b45580ea-e7da-5ca1-9411-9f1de1547d17 |  | note | Concrete aspros require annual compressive strength and soluble salt testing is required.
label | aca9455f-93d6-53bc-8eda-13bd52895c08 |  | note | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 50c97631-a1f8-5bc9-bb2f-95f9ee1f6465 |  | textbox | Enter: Teambinder Material Approval number
label | 7e0ce8a5-c86e-50ea-958f-302d1ef67595 |  | note | – – – – – – – – – – – – – – – – –
label | 6429cf95-b3dd-59ae-a29e-7595adb1925d |  | note | METHOD: Document Review
label | 61bfe108-e108-5722-935e-e925a2acdc46 |  | note | – – – – – – – – – – – – – – – – –
label | 686085e9-944b-53c5-ba2c-abc0139a4b7f |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | dddf55f6-dc1c-582c-9603-1e70346bb9fc |  | note | – – – – – – – – – – – – – – – – –
label | 439d1376-5458-5f4e-8b1b-f9de4fe1f213 |  | note | CATEGORY: HP
label | 25d670b7-4ef6-5792-a8ae-f85bf491f22a |  | note | – – – – – – – – – – – – – – – – –
label | 319654b2-d8a8-581c-92d4-57f406806404 |  | note | RESPONSIBILITY: Nominated Authority
label | cc6e72c3-2b30-5cf2-a20d-f087fc27d7bc |  | note | – – – – – – – – – – – – – – – – –
label | b3019efa-f86b-5a2b-b050-4199251b4170 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2256dceb-cc55-5596-aba2-956cab1bcd0f |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Evaporative Retardant
label | bdface88-9c2d-5e01-abe8-e01c981ba9ec |  | note | REFERENCE: 610.17 (f)
label | 461affea-941c-54b8-842c-d4464821b93d |  | note | – – – – – – – – – – – – – – – – –
label | 146e0438-0422-58c7-a7ed-a1f9d6e446b1 |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | f2b0775c-258d-5b1f-b82b-1430bbd7993d |  | textbox | Enter: Teambinder Material Approval number
label | 3d1862ce-0d43-5e6f-98d0-d07fa8879b84 |  | note | – – – – – – – – – – – – – – – – –
label | 96a42d5b-5a3f-517e-9358-cf3f9ea65347 |  | note | METHOD: Document Review
label | 83ce725f-89fb-51d2-a3bb-3df3fad4d5d4 |  | note | – – – – – – – – – – – – – – – – –
label | 1b71b441-9197-5f1c-87fa-089836e6975f |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | 4ccf8a44-c78b-567c-8daa-02a3b0e3e7ff |  | note | – – – – – – – – – – – – – – – – –
label | 2d8d8f4d-61cf-51a4-8b0b-d5129c245c4f |  | note | CATEGORY: HP
label | bf8c6b15-78f4-5232-86d3-79a5ba26f9bc |  | note | – – – – – – – – – – – – – – – – –
label | c15ad1f3-4b2b-5eff-baec-2c4c1b5d52e6 |  | note | RESPONSIBILITY: Nominated Authority
label | 91dc398c-876c-5f76-9c7a-f8907b2618c4 |  | note | – – – – – – – – – – – – – – – – –
label | a3095cc5-134c-53b7-83c2-5c4383673433 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5e28b783-849c-5c8e-b66e-a2265d179f32 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | 4de5eff7-0d32-5c01-9622-ecb262814c2c |  | note | REFERENCE: 610.23 (d)
label | 1181e2ab-ad63-5fd7-b7a3-b57bbf910e94 |  | note | – – – – – – – – – – – – – – – – –
label | 13abb926-f58e-5644-af61-720f6e76f5e1 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | e2aaa0a8-6e61-506e-809e-24861c32c781 |  | textbox | Enter: Teambinder Material Approval number
label | 12eab585-9b5d-5a92-9a66-5d5a20b4129f |  | note | – – – – – – – – – – – – – – – – –
label | e76aa8e7-89c1-517a-af54-39498bf93674 |  | note | METHOD: Document Review
label | af2c0685-089f-5ec2-86e8-8af01b084c98 |  | note | – – – – – – – – – – – – – – – – –
label | 706613e3-131a-5379-816f-50084d5fbfb8 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | 7622dcee-249b-5d2d-9db0-509b5fd6b3c9 |  | note | – – – – – – – – – – – – – – – – –
label | 09fdde4f-b8ba-598b-891f-1cf52884df66 |  | note | CATEGORY: HP
label | f50f8fda-eb66-51ad-a14e-e4c10d73618b |  | note | – – – – – – – – – – – – – – – – –
label | 7144d828-8804-5e92-b5f2-a72f622d3007 |  | note | RESPONSIBILITY: Nominated Authority
label | 6f1478c8-cbae-51b1-9c95-1c802e1c0f4c |  | note | – – – – – – – – – – – – – – – – –
label | a35c1ea6-f6bd-551a-a861-777d09a8c120 |  | note | VERIFYING DOCUMENTS: This ITP
date | 50f9c480-b986-5398-bb0f-6f811bebe065 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
label | 1279a74a-8556-53d2-877a-3ce9537a2e67 |  | note | REFERENCE: 610.18 (a) (i)
label | 1a6b49fe-28b2-59e4-b23e-53fac00476f0 |  | note | – – – – – – – – – – – – – – – – –
label | 70f3573d-c374-5345-a00a-1ead12cd6f49 |  | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
text | 50c0dc0d-326f-5521-afe2-50da57368db4 |  | textbox | Enter: Teambinder Approval number
label | 6e196461-0401-5c6e-bb1f-2834da31d05a |  | note | – – – – – – – – – – – – – – – – –
label | 956c014f-643e-5af1-9a40-b4559ec738f7 |  | note | METHOD: Document Review
label | 9fce6246-45f4-5514-8221-62b54de0a25f |  | note | – – – – – – – – – – – – – – – – –
label | b6e0aa30-92d5-53e5-9b41-c1195c3a2e12 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 73054d29-5293-5c1f-b549-11cc3e87353c |  | note | – – – – – – – – – – – – – – – – –
label | d14d3530-c2a5-5a50-b6fe-ce5408dc20f0 |  | note | CATEGORY: HP
label | 71488272-e67f-55fe-84f5-1d5f61c681a8 |  | note | – – – – – – – – – – – – – – – – –
label | 67a4cc33-9df6-5344-b0d1-9f33ca73dc90 |  | note | RESPONSIBILITY: Nominated Authority
label | ae34d12d-09e6-5d6b-bfa6-543c6291bbc9 |  | note | – – – – – – – – – – – – – – – – –
label | e2e2957a-f1af-50c4-b0f2-c453c0d28ac4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 3ad41ef8-38ff-5a8c-a246-0594ba013757 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Concrete Sampling and Testing Procedure
label | d15b4003-1313-5860-baa3-c4ac11d89d15 |  | note | REFERENCE: 610.18 (a) (v)
label | 24154d72-b622-5c02-8a58-08f1bbb242cb |  | note | – – – – – – – – – – – – – – – – –
label | 60003287-8501-55b1-aed4-7930fba608c0 |  | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
text | 70ad205b-7867-5db9-a2af-0fa24aaffb3d |  | textbox | Enter: Teambinder Approval number
label | 70664fc9-510f-5bd1-a90d-a3d44c0adc57 |  | note | – – – – – – – – – – – – – – – – –
label | 7403751c-f582-55eb-8605-ecc11f3bf937 |  | note | METHOD: Document Review
label | 5795eb22-edcf-54ca-9ab8-a9d35d48f9ec |  | note | – – – – – – – – – – – – – – – – –
label | 9e5804df-c5ee-513b-adce-60604ae374a1 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 59803fd4-838d-5075-a9c9-906cb72e28ee |  | note | – – – – – – – – – – – – – – – – –
label | 491fe38e-06a3-5921-8155-31a6e8fc8253 |  | note | CATEGORY: HP
label | aeddf62c-89d1-5392-836e-bd7be06b9332 |  | note | – – – – – – – – – – – – – – – – –
label | fa62beaf-b1c1-5b18-a09c-075738160596 |  | note | RESPONSIBILITY: Nominated Authority
label | 6d00aa41-fbed-5a0d-9cb9-ccd6b97f535d |  | note | – – – – – – – – – – – – – – – – –
label | 38c163f3-dd0e-528d-b3d8-2b7647988b0d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | bfc56018-dc53-5df1-98cd-f6caf1f91c7a |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
label | 7352ccb9-783e-5bdb-ad61-9f5c415e54fe |  | note | REFERENCE: 610.18 (a) (iv)
label | e06b6b06-c173-5ec9-8524-a772da335898 |  | note | – – – – – – – – – – – – – – – – –
label | f4f7722d-ab39-5468-a21b-c07a2b1ddc5a |  | note | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | 5744d018-b6f6-5cc0-8c0e-2944a80f08a6 |  | note | Minutes of this meeting to be submitted to the Nominated Authority.
text | 95e60c3f-71c6-5d4e-80d3-b67e628c53ca |  | textbox | Enter: Teambinder Approval number
label | 8e6f27b8-2002-5643-9cd4-52ac40caa189 |  | note | – – – – – – – – – – – – – – – – –
label | c40679e5-dca2-52eb-89f6-21f6d0f9411a |  | note | METHOD: Document Review
label | af3fa568-fa15-527f-a212-3c87f312b3d4 |  | note | – – – – – – – – – – – – – – – – –
label | a47f56c3-8191-51ab-a686-0b1cbe2e6467 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 963f49e6-8a95-5b90-9164-cdab925313fa |  | note | – – – – – – – – – – – – – – – – –
label | a0277409-15d9-5efb-b3b1-0bdb1725d5ac |  | note | CATEGORY: HP
label | a1255b58-3696-5ecf-9561-b480144c34c9 |  | note | – – – – – – – – – – – – – – – – –
label | a88d7e20-dca8-5b11-ba3d-a6f2ab2ee239 |  | note | RESPONSIBILITY: Nominated Authority
label | d7bd0758-4bda-5c59-9062-c8ccdb24f4e4 |  | note | – – – – – – – – – – – – – – – – –
label | cfc2c948-1ede-5f76-8174-171f9be216a5 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 67802979-5b9d-5c5f-bb4e-8bda9c02e5c1 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
label | 053f2459-b848-5d25-8a16-440e09ba448f |  | note | REFERENCE: 610.17 (a)
label | 1ab5a6f2-c32c-5bb2-9946-cde730c70438 |  | note | – – – – – – – – – – – – – – – – –
label | d7e1a5e1-534c-5a96-824c-51e2c785194c |  | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
text | e85da90b-9387-51c6-81dc-b65ceb1a4d93 |  | textbox | Enter: Teambinder Approval number
label | dbca611f-34b1-5e5c-a2f5-fa21a966fe71 |  | note | – – – – – – – – – – – – – – – – –
label | 1cf78d76-8400-5ca5-92cf-ff7c3eb3a229 |  | note | METHOD: Document Review
label | 55f752be-62a6-5804-bbcb-36760516dbf1 |  | note | – – – – – – – – – – – – – – – – –
label | 738bfac4-b9b4-5329-9289-b11d632a16ec |  | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
label | 1f2e4541-60ea-51ba-aa49-a6005eab86cf |  | note | – – – – – – – – – – – – – – – – –
label | 436881c4-bcff-5314-b755-90fc96c7bcc8 |  | note | CATEGORY: HP
label | d73b70b2-acda-5ba7-8ebf-d8eedf4e2254 |  | note | – – – – – – – – – – – – – – – – –
label | a939d355-4db9-5e72-8a4a-34508f0dd9e8 |  | note | RESPONSIBILITY: Nominated Authority
label | 0e450db3-5744-58bc-ad3e-c37f3a2738d0 |  | note | – – – – – – – – – – – – – – – – –
label | 9cdc5357-18c4-5a60-9fd9-3f1a75aeab5b |  | note | VERIFYING DOCUMENTS: This ITP
date | 0e5ee7c2-97d3-54f0-88da-1bac2e680a89 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
label | aeaab3cb-5b59-57fb-b5b8-91859e4ae6fd |  | note | REFERENCE: 610.23 (a)
label | 996c6f9d-e59e-565b-9c27-735901e36e65 |  | note | – – – – – – – – – – – – – – – – –
label | 5dcbfc79-48f7-5959-9957-6ff375ff5319 |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
text | 2d89f432-b9bb-5ab0-98aa-79e4e512084c |  | textbox | Enter: Teambinder Approval number
label | 26076933-0c81-5789-8d16-5f01c411aea1 |  | note | – – – – – – – – – – – – – – – – –
label | f0d357f6-2e40-5b41-bb72-0063047c9cda |  | note | METHOD: Document Review
label | 516610aa-08a9-5e1b-9dce-1913b08c1ba0 |  | note | – – – – – – – – – – – – – – – – –
label | 3a89eb44-6a5f-549d-975c-fca5224d5bea |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 70777884-b38b-5a7d-9823-d500a1e1adbd |  | note | – – – – – – – – – – – – – – – – –
label | 90bb445b-1bdd-5ede-bd77-eca96c368263 |  | note | CATEGORY: HP
label | f9dcf478-2cd4-56e4-8254-a8f7893104f8 |  | note | – – – – – – – – – – – – – – – – –
label | b1c6f7e3-0a72-5a38-a0b9-52e1381f5254 |  | note | RESPONSIBILITY: Nominated Authority
label | 98b528fa-ba26-5ed0-b1ec-968b597dc32f |  | note | – – – – – – – – – – – – – – – – –
label | e4d2362c-6e2c-5374-855d-deb74778d247 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 05cf3f72-892b-5f18-b037-ae0ac9ec6c29 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Concrete Drilling Procedure
label | d939f2b1-3f05-585a-9607-5869372dedc8 |  | note | REFERENCE: 610.46
label | 1890c4e1-ade9-5e1c-a9da-2886defad72d |  | note | – – – – – – – – – – – – – – – – –
label | 57d605bd-39b1-575c-9241-b4f37e88a402 |  | note | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | 12119cac-e7a0-5edd-806c-59ab4ec54784 |  | note | The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
text | fb21f1ef-931b-5f21-af15-d787ec71af42 |  | textbox | Enter: Teambinder Approval number
label | 708f735a-ec0f-50d3-9fa9-41c506eccffa |  | note | – – – – – – – – – – – – – – – – –
label | 17e2f0b4-601e-591f-b3b0-48b97835d7e8 |  | note | METHOD: Document Review
label | 9d08155b-9d49-514a-ace5-5ffc80ee2a8e |  | note | – – – – – – – – – – – – – – – – –
label | 9a548087-9e39-5afa-bed0-aa38bbe11d9a |  | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
label | dab300a0-46da-5e71-b564-569a81d2a47f |  | note | – – – – – – – – – – – – – – – – –
label | 904e9a32-aa69-5933-b0e4-f2d4bbdc1124 |  | note | CATEGORY: HP
label | a3849c64-daa1-5016-9d12-79f334e8c675 |  | note | – – – – – – – – – – – – – – – – –
label | 3fbe237d-2d42-5f92-bc80-45aed66e01e7 |  | note | RESPONSIBILITY: Nominated Authority
label | 6530dedf-219f-5120-ab37-a5f4d31c1493 |  | note | – – – – – – – – – – – – – – – – –
label | aea96922-6979-5921-a062-e25373c469e0 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | d87b7ffd-726d-515c-a00f-d2754174b612 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Temprature difference measuring-Calibration
label | c0a17f4d-2828-58cd-a3f4-1f873e4fd84a |  | note | REFERENCE: MRPA Quality Management Plan
label | 26bc0725-2e99-5214-bf52-55a79b2c0df8 |  | note | – – – – – – – – – – – – – – – – –
label | 7aed2314-7767-5961-b739-77f7a9616917 |  | note | ACCEPTANCE CRITERIA: Calibration records are valid and up to date.
label | 60df07da-5b5a-5c44-8843-6ec8a27a1dda |  | note | Attach: Calibration certificate
label | 7d8cd0f6-f494-546f-9ddc-6a63ecda251d |  | note | – – – – – – – – – – – – – – – – –
label | 8fb08665-1d6b-5df3-b8f8-d70c9b4e3ace |  | note | METHOD: Document review
label | a6a94883-741f-543a-826e-ba2f3a5522bd |  | note | – – – – – – – – – – – – – – – – –
label | 4921e93c-6c33-5bba-b814-efd4b1b1161f |  | note | FREQUENCY: Where applicable
label | dafad8c0-5920-55ef-9798-b9ab7af53982 |  | note | – – – – – – – – – – – – – – – – –
label | f12b12cd-3b1a-520c-a62c-7043de3116bd |  | note | CATEGORY: HP*
label | 8cac72b0-ce6d-51db-894a-266de7def5e8 |  | note | – – – – – – – – – – – – – – – – –
label | 7b9675a5-5e75-501e-aebd-8162ead7e5a8 |  | note | RESPONSIBILITY: PE
label | fbd45182-2226-5704-84bc-76cad26ed27c |  | note | – – – – – – – – – – – – – – – – –
label | ed27b032-1b17-5794-94d6-3c76d7a8c8bf |  | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
date | 1d098dbb-0616-5f70-8b4b-d4b86a9e4352 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 484ddb9c-9df2-5ec2-be72-b07985c0693b |  | note | REFERENCE: MRPA Quality Management Plan
label | 0898020f-0efb-5a74-92ed-eb23789329d6 |  | note | – – – – – – – – – – – – – – – – –
label | 8041162f-51c3-5a76-9ff7-d53f15e5a3fc |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 838ecba3-356c-567a-b302-710fad01da0c |  | note | – – – – – – – – – – – – – – – – –
label | 5134b801-6ee4-5bcb-9f5c-17ed8c32c8a9 |  | note | METHOD: Document Review
label | 810fc4a5-badc-5337-86c2-c22f617bcc5b |  | note | – – – – – – – – – – – – – – – – –
label | f64ac3f8-4b91-5e82-bffc-4718a0ece842 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 552841af-76c5-577c-912f-da2109a05bbd |  | note | – – – – – – – – – – – – – – – – –
label | 2f218139-da7a-569c-86bc-1cac29c1f8ed |  | note | CATEGORY: HP*
label | 9efee202-e59e-5409-8666-6b97e79ab3bc |  | note | – – – – – – – – – – – – – – – – –
label | 9f124fed-59ed-5782-9f73-d44c405581fc |  | note | RESPONSIBILITY: All
label | 5333c8bf-6e42-5196-8b39-9ce3e957ca82 |  | note | – – – – – – – – – – – – – – – – –
label | 99b1c984-3ce3-5528-bdda-52511292a083 |  | note | VERIFYING DOCUMENTS: This ITP
date | e16690cf-be5b-5b3e-9d1b-8137dae0eebc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | 1c5306f3-0827-5e92-9647-5333aea5f7be |  | note | REFERENCE: IFC Drawings
label | a80221e0-060d-575b-970e-d13c62108266 |  | note | 610.47 (a)
label | f28b5b6e-21d1-5572-9643-09bcf4008feb |  | note | Table 610.472
label | 6e8d9b3a-0421-5abb-857b-57a12ff1d656 |  | note | – – – – – – – – – – – – – – – – –
label | d3635884-03d7-50fe-b3d7-413c4fb5c393 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | 564b06e1-8888-5182-b660-98c444bb5249 |  | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | 23114c33-b0a6-538b-aa40-c7c4337d4d6d |  | note | – – – – – – – – – – – – – – – – –
label | bcb50610-65fb-5371-a8e0-786b7935b8d2 |  | note | METHOD: Measure, Visual
label | 89f2d7fb-bbe4-5b8b-ac1c-1cba285c135b |  | note | – – – – – – – – – – – – – – – – –
label | 4f019e30-f98d-58ef-ab06-971910e8dbbf |  | note | FREQUENCY: Each element
label | e3f77f27-77ad-5f82-bf51-1937c59525e3 |  | note | – – – – – – – – – – – – – – – – –
label | 17641360-f11e-59cd-99c9-770046df4dcb |  | note | CATEGORY: IP
label | 4c2cf59a-adf7-5cf9-8b25-7785e5325fcc |  | note | – – – – – – – – – – – – – – – – –
label | 3b7649a4-7496-5f75-8ff6-0fb81516df67 |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | 25ddacde-f8d2-5ae4-8415-a98edbce3067 |  | note | – – – – – – – – – – – – – – – – –
label | b6a70018-069d-5b4e-9832-2ccaa43023c8 |  | note | VERIFYING DOCUMENTS: This ITP
date | fbbcb94e-a78d-5511-a99b-afcc5d5a40f6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Excavation support
label | 904c053f-6cbc-5c7c-b30f-e8399fe690ca |  | note | REFERENCE: 602.02
label | 24389be5-15c1-5567-9c5c-abe99d66405b |  | note | – – – – – – – – – – – – – – – – –
label | 3410e730-c35b-5b1a-98ff-f21bf4cf5405 |  | note | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
text | 15829932-e27c-5deb-b5de-ebd1c439020b |  | textbox | Enter: Teambinder Approval number
label | c3d1d254-66e7-5192-9ecd-1ec39f46dae8 |  | note | – – – – – – – – – – – – – – – – –
label | 8beb6976-cc51-532a-8b62-1caf289e1bb4 |  | note | METHOD: Document Review
label | 0ff1aac9-4d88-5211-b019-5ed4439f13dc |  | note | – – – – – – – – – – – – – – – – –
label | 5931ee51-006b-57a0-ae8a-c496d721f1bb |  | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
label | 10583164-ca17-5d5d-9c98-11334a4984e5 |  | note | – – – – – – – – – – – – – – – – –
label | 9ac2b9c9-9ed4-512b-a249-ffed687a3ee9 |  | note | CATEGORY: WP
label | d17a20e1-6342-55bd-a318-32dc84173300 |  | note | – – – – – – – – – – – – – – – – –
label | ac57ad92-eb0d-5f9f-9380-89982a3afc51 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c4949eed-ea98-5a34-adaa-843e02b5ec5c |  | note | – – – – – – – – – – – – – – – – –
label | 2657fdab-3aef-5043-bee9-a33407f5903b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 521e3b54-d3db-5dd5-9b62-7db1a3fb08f3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Excavation Inspection
label | 77ba54a1-62b7-57a8-88b1-2c2f81741d40 |  | note | REFERENCE: 602.03
label | 0d36f603-b3e4-598d-ba51-e469cb535302 |  | note | – – – – – – – – – – – – – – – – –
label | db3e7228-1095-5324-988b-d7fa8a061702 |  | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | 7f0c91c5-b464-5924-8d09-2cf603440bd7 |  | note | – – – – – – – – – – – – – – – – –
label | f9a2b4c4-84fb-5175-849d-620d53053683 |  | note | METHOD: Visual
label | c8f0986e-3a73-5dfb-802b-f7508e53817e |  | note | – – – – – – – – – – – – – – – – –
label | 4bde44ca-5948-54c8-9630-13aadf5e7b0e |  | note | FREQUENCY: Where applicable, prior to placing blinding concrete
label | b81c9885-a7d8-5d48-88f6-2d78247ff639 |  | note | – – – – – – – – – – – – – – – – –
label | 68a0a414-d66d-58eb-bb28-8ecde8b41c16 |  | note | CATEGORY: HP
label | e1072d2a-5857-55c1-86e8-5d40f2fafcdd |  | note | – – – – – – – – – – – – – – – – –
label | 9e0be892-9fea-5a80-9075-5395659b7568 |  | note | RESPONSIBILITY: Nominated Authority
label | 77061b3a-202a-55e4-96b2-f98cd5f7fec3 |  | note | – – – – – – – – – – – – – – – – –
label | 719aa59b-927a-5316-a54d-cdc5a6e4ba8b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | f844dc06-d51a-5b9d-b1be-0b75954dd1a9 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Formwork Design and Construction
label | df508126-df03-55de-9dc7-e917273da6fd |  | note | REFERENCE: IFC Drawings
label | b38c5740-963f-5915-bf81-85c37671ddd9 |  | note | 614.04
label | ee42a8e1-1f3c-5a03-83c6-41145d150548 |  | note | 614.05
label | f567aaec-0c24-5a22-8f7e-52589e7d8d1f |  | note | 614.06
label | 3caa1a5a-a3d9-55f8-9f4e-bec2edbb2555 |  | note | – – – – – – – – – – – – – – – – –
label | c7ef406f-a6f4-5b51-8d2e-3d53976d06ac |  | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | 3bc45c19-668f-571f-a391-446edf3a3895 |  | note | Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | a383ad9e-36cf-5976-adfe-b7470ba05dec |  | note | Formwork shall not be placed where steel & fixtures cannot be inspected.
label | 27408afc-a169-50ec-97ad-647d0546f1b1 |  | note | – – – – – – – – – – – – – – – – –
label | d6e409c2-c358-5d19-95d6-c347d43197e8 |  | note | METHOD: Document Review, Visual, Measure
label | 51ac8429-8e91-5af2-8aca-f058537b7271 |  | note | – – – – – – – – – – – – – – – – –
label | bded8db6-9635-5d56-b8e9-1562f9763c5c |  | note | FREQUENCY: Each type of element
label | 38929a71-ddfa-5af7-b017-9b7f0892c384 |  | note | – – – – – – – – – – – – – – – – –
label | 734d4cb7-88df-5707-98ef-43f64277d4e6 |  | note | CATEGORY: IP
label | 8c5d9459-e071-5f72-9581-acdbf98f12bd |  | note | – – – – – – – – – – – – – – – – –
label | c3690a0d-e755-58fc-8c64-301b0d58bfdb |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | de4b26da-e0e8-50b1-8179-7880899f6466 |  | note | – – – – – – – – – – – – – – – – –
label | 013b090b-405e-5cbe-9d1d-1ba5eca7a4b9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 518f3b6e-e040-5348-923e-5b1cc53843d5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | 061b38fb-f38b-5cea-b7f5-9a6447b80ba6 |  | note | REFERENCE: 614.08
label | 0211cb3f-5527-5fe0-b8d7-8df027e9df67 |  | note | – – – – – – – – – – – – – – – – –
label | 4f460a87-ad96-5921-9148-2c9e95138c11 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | 5153db0d-789b-55e0-94d5-1b8d87e19518 |  | note | Walls with heights greater than 2.0 metres
label | 70f06a8d-a79b-5084-8973-09102217f7f2 |  | note | Any member for which self-compacting concrete is proposed.
label | cbbfcc69-8ade-5ec9-b7af-d488a02b8182 |  | note | Attach: Attachment A
label | b82b8523-4d5e-54be-9297-56b372eff5a8 |  | note | Attach: Attachment B
label | 45f5be41-fb7f-5bfe-8708-ece88e53d8dd |  | note | – – – – – – – – – – – – – – – – –
label | 099d63b1-bb8e-5bd8-9894-99a840c742c3 |  | note | METHOD: Document Review, Visual, Measure
label | 4ac4ba6d-1b8a-5012-b8d1-362dd30bfec5 |  | note | – – – – – – – – – – – – – – – – –
label | 9288b58f-a85b-5a28-b977-8bdf03542080 |  | note | FREQUENCY: Each element (where greater than 2m)
label | 4253c34e-de27-54fe-a8e4-6959d50fb70e |  | note | – – – – – – – – – – – – – – – – –
label | be74cd59-491c-5f82-b2d1-2904f0821918 |  | note | CATEGORY: HP
label | 4f805b79-2a5c-59ae-8011-4a0917dc70b3 |  | note | – – – – – – – – – – – – – – – – –
label | 7eabee06-a0ee-5892-91d7-d06bdde4268b |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | 27692f3f-cc8a-5cf7-be77-c3cc6ede941b |  | note | – – – – – – – – – – – – – – – – –
label | cf40508c-6e96-571a-a967-549638fc52c0 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 5a39844b-3af2-53fe-a186-bffa7069e074 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | 81590773-c3e0-5f9f-8f70-1aedb0dc4cd9 |  | note | REFERENCE: 614.08
label | d3e4a654-7fa2-5e06-9493-d430e35696cc |  | note | – – – – – – – – – – – – – – – – –
label | e518c732-8684-5400-a242-6de484f83138 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | c23600f5-99cc-59da-bf7c-cb0363ae8e61 |  | note | Walls with heights less than 2.0 metres
label | 735d7eb7-4283-5e49-9faf-af6904e9db28 |  | note | Attach: Attachment C
label | 7f8518a1-f063-5121-bc12-239c6c26fc50 |  | note | – – – – – – – – – – – – – – – – –
label | f49a152d-66e6-5420-9710-431fcbc4ea6e |  | note | METHOD: Document Review, Visual, Measure
label | 4c3eca97-c7af-5b36-9f86-0649294ba72a |  | note | – – – – – – – – – – – – – – – – –
label | 57fd4e3f-0a7c-52ea-8c7c-1eb5f281a553 |  | note | FREQUENCY: Each element (where 2m or less)
label | 2005cccd-59be-552e-a1fc-450a7119ddf3 |  | note | – – – – – – – – – – – – – – – – –
label | f2fde8fe-94b1-5c5a-80b6-d9d2b3697052 |  | note | CATEGORY: HP
label | 7584a341-3735-5c0c-8bfd-bc261337cf28 |  | note | – – – – – – – – – – – – – – – – –
label | 4a7407be-263d-588d-b4da-46cf3b410a5e |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | 60828a6d-49e3-5317-891b-e7515b0726e5 |  | note | – – – – – – – – – – – – – – – – –
label | 1b707cc0-5c6e-5549-af65-32c6f1228a29 |  | note | VERIFYING DOCUMENTS:
date | 1b34035d-4774-5406-b6df-77f51c7fc65a |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Pre-pour Survey
label | b4caa24c-06a6-5ad8-9f0b-6e93e29012e1 |  | note | REFERENCE: 610.47 (a)
label | f9d3ba54-67c5-5d7a-8884-e9bfca5573c7 |  | note | Table 610.472
label | 93be031d-2bb3-5cbe-b539-93c0ab0ba2ba |  | note | – – – – – – – – – – – – – – – – –
label | eb1879dc-ad72-5cb1-a877-1def691dd182 |  | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
label | e0fd125f-a35d-5843-86de-6fcbefb52125 |  | note | Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | 0a333e07-5b62-54bf-865e-c8243f422220 |  | note | – – – – – – – – – – – – – – – – –
label | b8f1e137-f995-5f9a-848d-8c3f5bfbc9b7 |  | note | METHOD: Measure, Visual
label | 71ca8da0-7896-5662-bb93-e5bdda42e4d6 |  | note | – – – – – – – – – – – – – – – – –
label | 1930a77a-45fe-5a7e-9f50-c555d5e684d2 |  | note | FREQUENCY: Each element
label | fb782291-cdbd-592b-8384-3675a10595af |  | note | – – – – – – – – – – – – – – – – –
label | 8a4a7feb-46d9-5951-9cd3-91f44c85d63f |  | note | CATEGORY: HP*
label | 4a9c585b-e712-5bd1-a421-d845335d1431 |  | note | – – – – – – – – – – – – – – – – –
label | fb277d69-2c14-5c38-ba40-22c68003c070 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 3436026b-5eb8-578a-b58e-e62ecb500761 |  | note | – – – – – – – – – – – – – – – – –
label | b9967146-58ee-567f-87de-82abc4b6da37 |  | note | VERIFYING DOCUMENTS: This ITP
date | 62bea4a4-a0dd-5d19-a9b6-0cd7d098d8e4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement Placement
label | d6dccae4-7b33-5aad-a62e-48f29e49aa15 |  | note | REFERENCE: IFC Drawings
label | 6451313c-4b37-5a4e-b6a1-492320221bf4 |  | note | 611.06
label | 9248db9d-23c2-57b1-b1ce-862c5898a764 |  | note | 611.09
label | 1fa376b1-fb4b-552d-9c3c-ce8c764868da |  | note | 611.10
label | f7e785fc-fd60-5136-a785-4136ae37ad56 |  | note | 611.11
label | ab7951a7-859d-5b2a-8516-deb512da6b88 |  | note | 611.12
label | fbabbb77-7170-5df8-bb5c-aadf5c887259 |  | note | – – – – – – – – – – – – – – – – –
label | 06126771-7065-553d-9de9-ce2bfd6b4648 |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | ec377d9a-cfa1-5809-8069-931254a1aa14 |  | note | Projecting reinforcement is the correct length and location.
label | d02bcee6-9b21-549d-aa14-ab0c22d1b5de |  | note | Splice lengths achieve the minimum length and are in contact for this length.
label | a5cb2ca4-d055-5635-a707-b0e23852fd7f |  | note | The reinforcement surface condition is free from dirt, debris and damage.
label | d7d7d7e5-626f-5517-9cb3-77049d4aa078 |  | note | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | af88c269-37f0-59ed-9dae-0151da6e722b |  | note | Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | ef5257f1-b8db-5b08-8ebc-44aef9c37e46 |  | note | – – – – – – – – – – – – – – – – –
label | 1c93f0e7-429d-5823-a40b-f97a1aba5620 |  | note | METHOD: Measure, Visual
label | 883f47e5-4c2c-5178-b63a-79d9e0d1f4f0 |  | note | – – – – – – – – – – – – – – – – –
label | d6912561-00d5-5ca9-8818-8d09c5fa3af0 |  | note | FREQUENCY: Each element
label | 8177105c-486e-5e10-8822-2c30326e2252 |  | note | – – – – – – – – – – – – – – – – –
label | 943de708-1c4e-5455-890e-2d165e7849e2 |  | note | CATEGORY: IP
label | 9b0f6a76-dab4-50cf-bb2b-70b056c06dc5 |  | note | – – – – – – – – – – – – – – – – –
label | f8a12c13-3c09-54a1-a537-6dba40e968cd |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 56c69621-de60-5e0c-820a-49197f055bd2 |  | note | – – – – – – – – – – – – – – – – –
label | be130ce8-d549-540d-9879-b727c8d7519c |  | note | VERIFYING DOCUMENTS: This ITP
date | d48c78fc-1c99-589f-82a1-c4ba3801c5b4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | 84041649-23ee-5410-8bf7-39dc4da1587c |  | note | REFERENCE: IFC Drawings
label | a596d7a7-132d-5f17-9482-9a1661b0dacc |  | note | 610.47 (a)
label | 64e229b1-4aec-5e79-9f75-b41b2546b536 |  | note | Table 610.472
label | 6daaca2e-a81f-59d9-b629-9c488ccffafc |  | note | AS3810.1 Table 3.3.6.2
label | 2551a06c-6504-5da4-9201-6cb3e774f763 |  | note | – – – – – – – – – – – – – – – – –
label | f07d0b11-fa8f-5390-b9a1-22bf28b6f272 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | d38c5733-8f95-51af-bb38-e7d60122af63 |  | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | af27a9c9-19a2-563a-9861-13326afc70e0 |  | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 882863b6-7b7b-56ae-a0ac-2758e5b78da4 |  | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
label | dc31d82c-ea72-5d44-a7b5-9d7d86588539 |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 5c803560-68ca-5811-b1a3-6343c3db495f |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 3ad85b61-a534-5820-8b55-ffac04ec96ba |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 18089280-70cf-562c-9e86-3080c9ecf583 |  | note | iii. Ducts and conduit location = ±12mm
label | 4ef6cbf7-8b0d-5962-910c-b50ca0a3e688 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 59a5b23d-8725-5743-99b6-600ccf46cc51 |  | note | – – – – – – – – – – – – – – – – –
label | e7dfc1a4-66ca-5cf8-b1cb-1849f24d824c |  | note | METHOD: Measure, Visual
label | dac1194d-5fdb-5163-8268-0055dc5de6da |  | note | – – – – – – – – – – – – – – – – –
label | 8130799d-0e50-570f-b0d6-712c1a7e771e |  | note | FREQUENCY: Where applicable, each element
label | c09022a2-cd5e-5bb6-844c-f72207c5d744 |  | note | – – – – – – – – – – – – – – – – –
label | 3b1ee683-0d34-578c-9a58-c568eff4685e |  | note | CATEGORY: IP
label | 96ba585c-df75-567b-9558-cd84f4a99663 |  | note | – – – – – – – – – – – – – – – – –
label | 8b3ef175-f45c-5030-b2c8-4d19e3857a52 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 5e0cb299-050c-5053-9633-05692da1a623 |  | note | – – – – – – – – – – – – – – – – –
label | 1386f2c8-5202-5a14-b71b-d94c228984d0 |  | note | VERIFYING DOCUMENTS: This ITP
date | a8dd6890-0a79-5271-96bc-b6eb20b357a0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Thermal Differential Monitoring
label | b9048bd2-b0cc-5cae-b3a5-52224fc16194 |  | note | REFERENCE: 610.22
label | b3a723a5-891f-593e-934b-3eff75f700b3 |  | note | – – – – – – – – – – – – – – – – –
label | 2afc67d2-6093-5b71-b4fd-138a6ce7b569 |  | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
label | 93fdf2a0-6a9e-5d1b-a37e-79a9a8891d71 |  | note | Only applicable if the element has:
label | c629eb98-09f3-524e-b86e-4af61cf5e7a3 |  | note | i. the smallest sectional dimension exceeding 500mm
label | 09afb03e-87dd-5ca6-a1b1-6802b319d663 |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | b69e6fb3-146f-5fc6-8512-1c60238c023a |  | note | – – – – – – – – – – – – – – – – –
label | 8bd6f450-a23a-5b9e-8f3f-2dd6fdb4686a |  | note | METHOD: Measure
label | c3d9caac-416b-5080-bb85-5df5fddcd1a3 |  | note | – – – – – – – – – – – – – – – – –
label | ae665e32-3038-5026-93df-c57f4e3ddbf0 |  | note | FREQUENCY: Where applicable, each element
label | 8297fe8f-5137-5b4f-9db2-5e0daa14b098 |  | note | – – – – – – – – – – – – – – – – –
label | 4ef6f72f-1a03-5f6b-92f4-d9342c3b6532 |  | note | CATEGORY: IP
label | 4eaf2c27-cbb3-53be-b5df-44a05ed39eea |  | note | – – – – – – – – – – – – – – – – –
label | ec5ffcda-f53c-55b8-b52b-e54bccae0151 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 18f33142-039e-592e-bfdc-ea6937bc4fae |  | note | – – – – – – – – – – – – – – – – –
label | fad4c05b-ee84-59cc-81e9-fa645f3fed31 |  | note | VERIFYING DOCUMENTS: This ITP
date | 7a5fce71-5601-5752-ad62-a1886a29b346 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pre-pour Inspection
label | 8db47cad-b2dd-5b9f-807c-977b666181e5 |  | note | REFERENCE: IFC Drawings
label | ec933c09-31b9-5e8e-baf6-7395f9efe2e8 |  | note | 610.18 (a) (ii) & (iii)
label | d43f409f-0772-5038-80d9-d37893b35d2e |  | note | – – – – – – – – – – – – – – – – –
label | 983450f6-5ab4-5911-b5d2-b02c58b59ee2 |  | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 5965816c-524d-5c5a-b165-d1c8ecb7430d |  | note | All foreign material has been completely removed from the forms.
label | 44528149-f3d7-5308-867c-e1dcb4067d4a |  | note | ATTACH: Pre-Pour Checklist
label | 5e4e4a69-fa05-58ae-9e7c-bdcf5d6bc88a |  | note | – – – – – – – – – – – – – – – – –
label | d2aa50d0-22d5-5c30-8e96-b1f8b6ce5af0 |  | note | METHOD: Measure, Visual
label | f31f5f94-0972-52a0-b5ca-de7a88bcff95 |  | note | – – – – – – – – – – – – – – – – –
label | 9bca5061-190e-5859-9eec-cfb16858f685 |  | note | FREQUENCY: Each element
label | bbcc6701-decc-5cbd-9e2e-56dde231ad46 |  | note | – – – – – – – – – – – – – – – – –
label | 977321dd-e8b3-5c5b-b4fa-5c4fc782df1b |  | note | CATEGORY: HP
label | 40cbbd0d-e137-5f88-802e-b9f5c5bb14fc |  | note | – – – – – – – – – – – – – – – – –
label | ac271235-e75f-509f-b061-8ca9ef8692ac |  | note | RESPONSIBILITY: Nominated Authority
label | 7eebb606-fd87-501d-90c2-c9746c216f23 |  | note | – – – – – – – – – – – – – – – – –
label | a52540e2-91c4-5015-b8d0-e5abd56c1a24 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
date | 2f628d87-a7d4-51dd-91ff-a406fbac93c0 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.9 Weather Conditions & Evaporation Limits
label | 9fe01274-f36d-5521-b460-10c4a01ec00e |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure
label | c269f485-5a56-5699-bf4e-a4ff274f2f0f |  | note | 610.17
label | 96850a35-7fbb-51f0-b6df-306edae96f0a |  | note | 610.17 (a) & (e)
label | 32dfba0c-7321-5507-a37c-0d1287202c13 |  | note | Table 610.171
label | 0339cea9-0e8b-5c38-a7ea-039b8255ff76 |  | note | – – – – – – – – – – – – – – – – –
label | 65bc0234-daf6-55f7-8864-195a0cb88cf3 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 074b48bf-b3a8-50d3-9696-1c4d223de788 |  | note | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 4d7fe576-a6e1-5532-9139-aa4d477d7447 |  | note | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 314c7612-6612-5ae7-8ad6-30ef1c7b1488 |  | note | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 03e7681e-389e-5c2f-8c2e-9be54b4413af |  | note | Record: Required information on the Concrete Pour Record.
label | e375881e-fa2d-56bb-add6-cec2a014441c |  | note | – – – – – – – – – – – – – – – – –
label | e438a60d-3ece-5f1f-aff7-481ec3a1059c |  | note | METHOD: Measure, Visual
label | b6330181-f656-566c-93f0-231a20c1a3b6 |  | note | – – – – – – – – – – – – – – – – –
label | d80d8457-6a72-51ef-9b52-4af193161e1b |  | note | FREQUENCY: Each element
label | 645ee66f-057b-50bd-9e01-1f83058bfa59 |  | note | – – – – – – – – – – – – – – – – –
label | d29882e4-077b-5f19-9283-ec0f3557d301 |  | note | CATEGORY: IP
label | 65b9dcc5-9f2d-5c6f-b966-a2f28ed2cdc6 |  | note | – – – – – – – – – – – – – – – – –
label | 20aab4b0-1bf0-58e5-ab6d-39ea7c516fce |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | fc615046-c160-54f2-b1d9-7fcfb2f24d25 |  | note | – – – – – – – – – – – – – – – – –
label | ae25125b-3a8d-5631-bbe4-653f6203c047 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | a7f152c9-44bd-541c-b9f1-9e6072342fe2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Sampling Frequency
label | 560d4a4f-8786-54c9-ac72-f83f8033883e |  | note | REFERENCE: Site Sampling & Testing Procedure
label | 7adfc62e-cf3b-58cf-b70c-ea9c13013670 |  | note | 610.16 (b)
label | e594c7b8-e6b7-5c90-a6e6-eab3ff082e60 |  | note | – – – – – – – – – – – – – – – – –
label | 13c1a868-dcb1-5c12-9ff0-a94db1a30dd3 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 1b5b1cc1-cc95-544b-ab26-73841cd13c5d |  | note | 0m³ to 10m³ = 1 sample
label | 3c543000-86c5-5a2f-af45-f13212d4a7eb |  | note | 10m³ to 25m³ = 2 samples
label | 78485189-1b32-54c6-aff1-fd815c36a918 |  | note | 25m³ to 50m³ = 3 samples
label | b23e5365-25ca-52c2-b6fe-291a4232e88e |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | aa7b88f3-0ae5-52a0-b907-3c654d84fb47 |  | note | For each additional 50m³ and additional sample shall be taken.
label | cd7ed898-1d67-5854-aeba-b2ab95b80e59 |  | note | Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | ef989076-f543-5af5-abaf-ccfbdfde981a |  | note | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 1bebe5d2-f2a9-542a-a3c8-f3e6d1d444d2 |  | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 9ab2f6f1-9768-543b-b4b1-e2869403f6cd |  | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | 8631f722-90dc-565b-afc0-5495456dc844 |  | note | Record: Required information on the Concrete Pour Record.
label | e22f0793-6332-5164-bd0c-6177e586170e |  | note | – – – – – – – – – – – – – – – – –
label | 11c59a03-f559-5961-a79d-c18dc26971bd |  | note | METHOD: Test
label | 1e9e82a9-aa46-5536-bac4-4b31b5df66be |  | note | – – – – – – – – – – – – – – – – –
label | c3953fbc-f991-5cfa-ba7e-d49d00e2ce75 |  | note | FREQUENCY: Each element
label | ec2f2926-6c37-5738-9162-85a0433e0a3a |  | note | – – – – – – – – – – – – – – – – –
label | c6ba9ea8-39b2-5aad-aa5a-f4e44bf06949 |  | note | CATEGORY: IP
label | d8750f8e-2e11-500d-857c-4a85e41d4fd0 |  | note | – – – – – – – – – – – – – – – – –
label | a8b78777-08c0-5d2e-aecb-87d0592eb475 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | c530e118-6517-506e-bc6e-30a0a3ca6b1d |  | note | – – – – – – – – – – – – – – – – –
label | 38f613b4-af5a-5a09-806a-b7fa6add4c88 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | cd3bcca3-929a-5079-a87d-6b499172e55d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Slump
label | 64c01566-c04c-5f6a-9dd4-e26ac36d6810 |  | note | REFERENCE: 610.16 (c)
label | d9a0dd26-c4ad-561a-9138-21707149485e |  | note | – – – – – – – – – – – – – – – – –
label | de4d3d82-5ac4-5e8e-bbff-526b7008e11d |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | d4323dc2-5f54-5d63-95c8-185702c2ea5f |  | note | <60mm = ±10mm
label | cfc3baf2-49f6-579d-8325-d54e8974c6c6 |  | note | ≥60mm to ≤80mm = ±15mm
label | 1d6fe1b5-3fe5-5d95-b8df-332fcd5c10c8 |  | note | >80mm to ≤110mm = ±20mm
label | d7a211b8-8cd6-57c0-b1a8-3199d27a346c |  | note | >110mm to ≤150mm = ±30mm
label | 47a10d6f-ea70-5d24-abd9-096d2187d265 |  | note | >150mm = ±40mm
label | db5f4dee-77f2-52b9-9682-268e973b8f18 |  | note | Record: Required information on the Concrete Pour Record.
label | 61f935c2-ede2-509e-b9fa-8e5b988d211c |  | note | – – – – – – – – – – – – – – – – –
label | 9d5a27f1-ddca-56ea-a128-b179a346353e |  | note | METHOD: Test
label | 3a1471a5-3292-5d32-bc09-e338e8021770 |  | note | – – – – – – – – – – – – – – – – –
label | b4bdb9dd-5a40-5fc5-9302-fed8ce6934dc |  | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
label | b776b619-6ca4-50ce-9109-e165dc06eb82 |  | note | – – – – – – – – – – – – – – – – –
label | 6134328a-d79d-5099-92cf-6b4525d414e6 |  | note | CATEGORY: IP
label | bfa9c7f6-fa98-5c20-8a2f-9d8b96079f1d |  | note | – – – – – – – – – – – – – – – – –
label | 6c83d0d6-330e-5730-9f2e-30edb6e9d3f7 |  | note | RESPONSIBILITY: Concrete Tester
label | aa56be29-08a9-5246-94d0-4eb1f4bfd0c8 |  | note | – – – – – – – – – – – – – – – – –
label | 360f82ac-1493-5718-81fe-d7aaebfc21c9 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | a6dfe133-bd79-57da-9d70-d22414fb8822 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Concrete Testing - Spread, Passability & Viscosity
label | bf1c99da-cb88-5fdc-b90c-3c634160e78f |  | note | REFERENCE: 610.13 (b)
label | b7401421-45f5-5854-97c6-822978115d2f |  | note | – – – – – – – – – – – – – – – – –
label | 101dd398-f795-5679-8e3f-4a3e030fbed9 |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | c6b480da-2fe2-56d9-ab96-4bc0884d76ba |  | note | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | b468041d-69df-5471-a4d0-02cc27e30801 |  | note | Passability = ≤10mm (aggregate height differential)
label | a6141834-71a4-5ef5-ac9a-6f12cbd5b583 |  | note | Record: Required information on the Concrete Pour Record.
label | 04cb53de-530d-506c-acec-327618ae71ad |  | note | – – – – – – – – – – – – – – – – –
label | caad693e-1a92-5142-8983-ab50913c0465 |  | note | METHOD: Test
label | 125f3d1e-00e5-5fa9-8202-18331aa82e78 |  | note | – – – – – – – – – – – – – – – – –
label | 895dae52-b1dc-5e12-90a8-4efd9a3ddc46 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | f6083c94-3c19-58ce-b7ca-f8164659a7e2 |  | note | – – – – – – – – – – – – – – – – –
label | bebb53b5-3449-56fe-98b8-09a8509a6644 |  | note | CATEGORY: IP
label | 314daeee-e9e7-5597-97ab-8bcef5ceafb2 |  | note | – – – – – – – – – – – – – – – – –
label | ddd7a811-11d2-5686-9dd5-cae0a11294b7 |  | note | RESPONSIBILITY: Concrete Tester
label | fb4b3a4c-52f2-5a07-b783-cacebb883be4 |  | note | – – – – – – – – – – – – – – – – –
label | a4124beb-96c1-5b3a-bd71-81ac7de70093 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 9f1b720a-1fef-536e-bfd3-99e6b50af669 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Concrete Testing - Compressive Strength Cylinders
label | 6ed3690f-f708-5983-9af8-f944fe5dd2ed |  | note | REFERENCE: Site Sampling & Testing Procedure
label | 1af961f9-0980-53bc-b0c9-8e1a324fc994 |  | note | – – – – – – – – – – – – – – – – –
label | 18994062-959d-5a73-85ec-0a50d3247df9 |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | 3ff88970-9ad6-537c-a593-dfbe000d6ad0 |  | note | Record: Required information on the Concrete Pour Record.
label | 3e70ee77-105e-5f12-bb1d-6a2602d3902a |  | note | – – – – – – – – – – – – – – – – –
label | d9437383-110f-591c-9092-e228c92b7e73 |  | note | METHOD: Test
label | d7233b0c-efbf-5883-a58a-4829f87a7bbf |  | note | – – – – – – – – – – – – – – – – –
label | 899f5e07-9838-5456-a47a-7e973daaffb9 |  | note | FREQUENCY: Each sample
label | 72a43b43-8428-5b81-bbfe-0e90957ff5ce |  | note | – – – – – – – – – – – – – – – – –
label | a56b97d0-e3de-535f-bc74-36927d3bb7b4 |  | note | CATEGORY: IP
label | 39db11b8-f1b8-54f9-8c59-b03b78ac0308 |  | note | – – – – – – – – – – – – – – – – –
label | 9d5bf260-1b0f-51e6-970f-e379aa16fd86 |  | note | RESPONSIBILITY: Concrete Tester
label | f36f6d56-250f-5ed4-bf65-a959d236a3d2 |  | note | – – – – – – – – – – – – – – – – –
label | 97201ca5-e6d2-51b1-b1ea-62b013df6e50 |  | note | VERIFYING DOCUMENTS: This ITP
date | f486caaa-1b5d-518f-8a77-31a35b466574 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Supply & Discharge Rates
label | 5129683b-5564-53d2-a4d7-c7b1b5a0140f |  | note | REFERENCE: 610.13 (a) & (f)
label | d2c9478c-3535-52c5-bda2-0dcd5798e695 |  | note | – – – – – – – – – – – – – – – – –
label | aeafeec6-7f86-5ea8-8229-e4f6b3f76d48 |  | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | 693dcb85-fe1d-538d-995f-6b00ece7b9f5 |  | note | No water is to be added once discharge commences.
label | d0f6a405-1e99-5381-92cd-7a8338ec1090 |  | note | Maximum time between batching trucks is 25 minutes.
label | 6225b39e-4c01-5f57-a6c7-50287734669a |  | note | Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | bd642174-e45b-5982-8a44-1772c732809b |  | note | Concrete that stiffens or is showing signs of stiffening shall not be used.
label | 559bdb20-2134-5d89-ad73-b88bae9d0bde |  | note | Record: Required information on the Concrete Pour Record.
label | cccd50d3-5b9a-5ff0-a9c9-8804c09a613a |  | note | – – – – – – – – – – – – – – – – –
label | e9885db9-8344-58ca-8960-fa7658cf750e |  | note | METHOD: Measure, Visual
label | 68c11600-ab78-5682-83f1-5b8f0f468c4e |  | note | – – – – – – – – – – – – – – – – –
label | d247202b-c93f-520c-8292-dd577c13392f |  | note | FREQUENCY: Each load
label | 386ef3e0-aeb6-5d0f-a9b6-adde72121f36 |  | note | – – – – – – – – – – – – – – – – –
label | ae43ab49-7b6a-51f3-bff7-121d750522cb |  | note | CATEGORY: IP
label | 8dd7e9db-7c1c-53cd-af4e-657ad5548277 |  | note | – – – – – – – – – – – – – – – – –
label | 8f3fdf2f-7bcd-53c1-9d5a-fdf85ee6f30f |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | a7bc5032-1047-5dd8-9c73-75972f9eda5a |  | note | – – – – – – – – – – – – – – – – –
label | 97ad2ffc-60d3-5d52-afb6-fc043f2fbac3 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | bf387c79-c7a6-531e-89c8-f2327b21dd5f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Placement & Compaction
label | ff4b2685-eb86-5261-8b43-2cef2da88a45 |  | note | REFERENCE: Placement & Compaction Work Procedure
label | 42e6b050-a1b2-54a5-b332-e7a5f35513f0 |  | note | 610.18 (a) & (b)
label | 53a092ca-b72b-5996-aa97-10602738faaa |  | note | 610.18 (d) (i)
label | 144e1bb3-ca0c-5c32-b2fe-69e654aafa2a |  | note | – – – – – – – – – – – – – – – – –
label | 3eac832f-3e39-530f-b21d-2151fdbeea13 |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | 33eb829b-a990-54df-b6e5-f0cdd16e1eb4 |  | note | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 86333b35-9482-567e-813f-41d12b009e6e |  | note | Concrete is not dropped freely from a height exceeding 2m.
label | 89293af6-14c2-5104-b330-111ec9fb475a |  | note | Concrete is not moved horizontally by use of vibrators.
label | df02485a-6db9-5f7c-93e6-6723b815f962 |  | note | Adequate compaction is ensured
label | 5d12c0d9-f3ac-5604-8423-084a77b9d2e2 |  | note | Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | f3fd8b4f-f214-57ba-9799-bbdebddf2103 |  | note | Concrete layers are not more than 350mm
label | 3f860a61-9cc1-5fbe-ae8a-db1f2b1833ea |  | note | Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | 775dea2c-4e10-56ec-a592-43c98b031c0f |  | note | Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | 9f7c274c-6422-55ef-a22e-8c0e402c7045 |  | note | Record: Required information on the Concrete Pour Record.
label | c9c73189-6771-51ac-a3d0-b0c2afcaf44b |  | note | Attach: Concrete Pour Record
label | d26dff16-2656-55e4-9e41-f3b1f24f9f9c |  | note | Attach: Concrete Dockets
label | df26204d-99d2-5541-a189-7d5e49e0e4d4 |  | note | – – – – – – – – – – – – – – – – –
label | 3e52cce6-fcee-5618-ba2c-46b13ae7eba2 |  | note | METHOD: Visual
label | 80f9d01d-e838-586a-8ab0-e24bcac18171 |  | note | – – – – – – – – – – – – – – – – –
label | 27c104ab-a4fe-5bb4-9d21-7e065a206021 |  | note | FREQUENCY: Each load
label | 2d34961b-7972-5207-8872-b6dd611bbe49 |  | note | – – – – – – – – – – – – – – – – –
label | 173152ab-abf6-5253-b133-08b8943a5165 |  | note | CATEGORY: SP
label | 903e214a-e453-5f27-948a-4aaa6872e76c |  | note | – – – – – – – – – – – – – – – – –
label | bc2c43f9-4b04-5cd7-87a1-a94dc8929001 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 9c8bb76c-9005-50de-ba74-b103c317d208 |  | note | – – – – – – – – – – – – – – – – –
label | a85d65de-2a0f-5aae-8180-4f8ec760ee92 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 3cb0b954-7540-5a78-a36f-cf6e7191edaa |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Surface Finishes
label | 03756d9c-221b-5475-a87e-4c7f1d9541c7 |  | note | REFERENCE: IFC Drawings
label | 17ca536c-e450-5ac6-90e5-43c2e89e75da |  | note | 610.31
label | 6db08b58-6101-5eda-81a9-1680cf535af7 |  | note | 610.20
label | 33a0a9fb-501e-5ebe-9041-554f2fc5e85b |  | note | – – – – – – – – – – – – – – – – –
label | b30ad291-d32d-58eb-a4ac-49964c0f002d |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | cc83ebaf-4300-5c6f-aca0-cb13758f0fb5 |  | note | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 48cd39d9-9fb3-5a82-8843-368b68aef520 |  | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | e8e882ac-927d-57d9-ac9f-61e94307cf26 |  | note | – – – – – – – – – – – – – – – – –
label | 4c1896c3-4de4-5921-9ee1-c66deef8075b |  | note | METHOD: Visual
label | 3d88c0ad-9342-50b1-925c-7f746187056a |  | note | – – – – – – – – – – – – – – – – –
label | e56a080b-090c-51dc-9ed8-11a1fa4ebe55 |  | note | FREQUENCY: Each element
label | 5c355b8c-7e58-5a06-a9db-69dd155156be |  | note | – – – – – – – – – – – – – – – – –
label | 9be43de1-8423-5b5a-ba9c-3e63310846f1 |  | note | CATEGORY: IP
label | 58bb0f2b-9e0d-544b-b5ed-098649c2c7ea |  | note | – – – – – – – – – – – – – – – – –
label | 421aa8a1-5ca2-504b-aef0-cb3e122d6cc6 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 2295feb0-7123-57ec-bc77-89194c215eb4 |  | note | – – – – – – – – – – – – – – – – –
label | 3126e3e1-9a9f-5731-9e6f-3a56d2ccac27 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1d94e937-65c0-58bf-88c4-08073f1011dc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Curing-Top Surface
label | 20c005fe-8894-5b40-9d1a-486dcdf0c403 |  | note | REFERENCE: IFC Drawings
label | 069ff23e-8edf-56b0-b699-b78efaa107a1 |  | note | – – – – – – – – – – – – – – – – –
label | 1c71f729-a5dc-5ee3-8075-81fab68020f3 |  | note | ACCEPTANCE CRITERIA: Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | 4e71edfb-80f2-5768-8ea1-299dd12d15d5 |  | note | – – – – – – – – – – – – – – – – –
label | 52289edf-f778-5251-a3fd-ac90f61be86b |  | note | METHOD: Visual
label | 53c02ad3-a7c3-5221-bfce-81ce6380acfc |  | note | – – – – – – – – – – – – – – – – –
label | 84a41063-5591-5c7b-b7bd-71ad9218818d |  | note | FREQUENCY: Each element
label | 8f4a8c50-1b5e-5a7f-a8c0-7cbc8e121846 |  | note | – – – – – – – – – – – – – – – – –
label | 33d5bae3-4970-5307-b3a4-f6e1e3b59265 |  | note | CATEGORY: IP
label | 442a927f-a0c0-54f1-a05a-a3f6c8c2af40 |  | note | – – – – – – – – – – – – – – – – –
label | eb68492e-fcb3-59cf-8f64-2154d5931521 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | da5630b5-f295-5c7d-922c-a0f03e7cb14b |  | note | – – – – – – – – – – – – – – – – –
label | 4b497aff-72c5-56cd-99dd-19747842fdfc |  | note | VERIFYING DOCUMENTS: This ITP
date | bd78fe33-87b7-5521-b755-2d350e322d15 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Curing after formwork removal
label | d9cbcd40-3bd7-5670-9429-664bdf279446 |  | note | REFERENCE: IFC Drawings
label | c45de6bc-0135-561a-8d77-98d7c2cff721 |  | note | – – – – – – – – – – – – – – – – –
label | aa0943f7-7c65-5882-94a8-313c86afbb0e |  | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | 204cee60-6881-541f-8ce9-340b72c339db |  | note | – – – – – – – – – – – – – – – – –
label | 43889d07-2d39-5a3b-b4f7-7495f8437d18 |  | note | METHOD: Visual
label | c313be1d-e95b-5053-ab97-b0142696074e |  | note | – – – – – – – – – – – – – – – – –
label | a185274e-1ad5-5b7b-854d-3c197997bc68 |  | note | FREQUENCY: Each element
label | 896e4af7-5184-5da6-b82e-aab1fe6bec58 |  | note | – – – – – – – – – – – – – – – – –
label | 70e6ea2b-33f3-57f3-83b2-19d1a038babe |  | note | CATEGORY: IP
label | d384f1bb-c8f0-57ae-918c-a949ee1b638a |  | note | – – – – – – – – – – – – – – – – –
label | cf62618a-bd5d-5210-9b6c-0453971b6c61 |  | note | RESPONSIBILITY: SE
label | 84914b0a-f9f8-5663-b6bc-521ed2b66757 |  | note | – – – – – – – – – – – – – – – – –
label | 66bfc3dc-3ac0-5659-9f97-34eaf0486f1d |  | note | VERIFYING DOCUMENTS: This ITP
date | 099b7cc4-f164-5d70-9bc8-23017dffecde |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Thermal Differential Monitoring
label | 5233f3b7-bb10-5c21-bc2d-002891aeadc3 |  | note | REFERENCE: 610.22
label | 61383814-22f7-599a-8a98-bf6c4b911f74 |  | note | – – – – – – – – – – – – – – – – –
label | 03a69cb3-7ab9-539a-9ce9-04e1e4b830ef |  | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | 14a96b83-5333-5879-bffc-2585a2e46689 |  | note | Only applicable if the element has:
label | 42802b70-5bb1-563e-b432-3a614fc58157 |  | note | i. the smallest sectional dimension exceeding 500mm
label | 6e1bb9fb-6ab0-5511-a8a3-759082381547 |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | fddfbadd-e5de-599e-afc2-de7b61f2d2ee |  | note | Attach: Thermal Monitoring Report
label | 3fad3ad1-87d5-5cd8-9604-0bdf064baf2e |  | note | – – – – – – – – – – – – – – – – –
label | 2ab3117e-6e86-504f-bbfb-824cee7d49e9 |  | note | METHOD: Document Review
label | bca46697-a06e-53a5-b110-74cf13ef4ba4 |  | note | – – – – – – – – – – – – – – – – –
label | 468b7d1e-514a-551c-a10a-b27ba7612ca6 |  | note | FREQUENCY: Where applicable, each element
label | bfeaf98e-48eb-5811-a650-11dd689eb76b |  | note | – – – – – – – – – – – – – – – – –
label | 712847ed-8f2f-5c78-b8d8-08552c803ded |  | note | CATEGORY: IP
label | bc39d707-1f20-51c9-9847-b5517d9288e3 |  | note | – – – – – – – – – – – – – – – – –
label | 564240b4-27bf-59e7-9cdd-f4f0ad1a4925 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 5370be64-f5f1-57aa-9f6a-aab985766959 |  | note | – – – – – – – – – – – – – – – – –
label | fd9d0447-927e-5b19-a1d7-eff5269e2f63 |  | note | VERIFYING DOCUMENTS: This ITP
date | 59279cf0-3d5d-5af6-964d-4ed791b13154 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Early Age Compressive Strength Test Results - Removal of Formwork
label | f5af9ef9-3528-5cea-980e-83e39183254c |  | note | REFERENCE: IFC Drawings
label | f83e0c92-1283-5996-95b7-94f65703e977 |  | note | – – – – – – – – – – – – – – – – –
label | a1416e1e-f786-536d-9570-4730f1e6ff70 |  | note | ACCEPTANCE CRITERIA: Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
label | 49c84540-9492-5bce-9c77-fa917f1f73b2 |  | note | Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | 4672420f-4676-5e82-b652-66e910cf40f0 |  | note | – – – – – – – – – – – – – – – – –
label | 6ebf5c01-0e9d-5ff3-a465-1466d1b513ea |  | note | METHOD: Document Review
label | 4d0b754b-196d-5b04-9a9a-22c2feb81994 |  | note | – – – – – – – – – – – – – – – – –
label | fc362f45-0f51-5231-a2e1-e8df94eabf78 |  | note | FREQUENCY: Where applicable, each element
label | 4dbd254e-8cb5-5737-a037-73a68ec92970 |  | note | – – – – – – – – – – – – – – – – –
label | 7b8fee1c-ddad-588f-8aff-dd2af6a5580e |  | note | CATEGORY: IP
label | 94b106cc-f6e2-53cb-bec5-e597e13af181 |  | note | – – – – – – – – – – – – – – – – –
label | 1ebf1999-a38d-5742-9f13-5e965691ead3 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 5247e68e-ecfb-557e-b1ce-fd793b3cf2ff |  | note | – – – – – – – – – – – – – – – – –
label | 2e46bc09-b954-5e86-978c-8675c8a94a65 |  | note | VERIFYING DOCUMENTS: This ITP
date | 540449d7-88e6-5880-9116-39de79050085 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Surface Inspection - Cracks
label | 26bd503b-1a61-58a6-9921-6b5783f153eb |  | note | REFERENCE: 610.24
label | 9a1a0d66-ba98-5180-8280-cee4187c258e |  | note | – – – – – – – – – – – – – – – – –
label | bf46270f-f299-5fc8-95f6-234917052993 |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1)
label | aed59650-b1d6-52af-b624-a18c08ae5517 |  | note | If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | cc8f2203-843d-5946-9dcf-4a8f0500cec8 |  | note | – – – – – – – – – – – – – – – – –
label | 6903b658-7479-5af9-92a0-ee886eefd996 |  | note | METHOD: Visual, Measure
label | 875c617e-4c2d-53f8-a12a-359e57bb544d |  | note | – – – – – – – – – – – – – – – – –
label | 24b18c10-5ac8-53ed-92af-8a2485b8eb1c |  | note | FREQUENCY: Each element
label | 9f5ba0bb-4f12-5f32-a37d-64558e4debd1 |  | note | – – – – – – – – – – – – – – – – –
label | aa76341f-c7ba-50f6-8a36-33e61f28f7b1 |  | note | CATEGORY: IP
label | db7dfb12-7b13-5593-b43f-d2326ae839ca |  | note | – – – – – – – – – – – – – – – – –
label | 62253afb-dabd-580e-a6f0-0460dd981764 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d1351feb-4e63-5d00-865a-9bc7a0f2f253 |  | note | – – – – – – – – – – – – – – – – –
label | 866de170-5903-5d75-9314-e533c8070938 |  | note | VERIFYING DOCUMENTS: This ITP
date | bfffd3ea-b21c-50fb-b18f-7c4a32f88cdd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Surface Inspection - Surface Finish
label | 2e3d1ca2-4ef9-5ef0-b011-4f65df2c4b8c |  | note | REFERENCE: IFC Drawings
label | 23182c8d-f6d8-515e-926f-61084c06d177 |  | note | 610.31 (a) - (n)
label | 4b950364-b5b1-55f7-b9fc-4548eea4b64f |  | note | 610.32
label | 2ca7f63f-e687-58d3-b357-b5d334b8a430 |  | note | – – – – – – – – – – – – – – – – –
label | 01e0df98-6ef4-5e20-9cbb-f2312be6a471 |  | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
label | 6a700b98-0874-50f0-8171-3b0e56a10975 |  | note | Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | c89edfbe-1238-5c03-9aaf-55ff270a2ea2 |  | note | – – – – – – – – – – – – – – – – –
label | 8fe249ff-9eb6-558b-bced-a806f142f6b7 |  | note | METHOD: Visual
label | 453491c1-ba36-5a2d-b326-3f527c7a5413 |  | note | – – – – – – – – – – – – – – – – –
label | 7682fa1b-23d3-5b24-aae2-700dcfdc777c |  | note | FREQUENCY: Each element
label | 282e2650-d448-5f32-8bd5-fbf171ce820a |  | note | – – – – – – – – – – – – – – – – –
label | 6c5ddecc-99ec-57dc-91b2-36dcaa88a976 |  | note | CATEGORY: IP
label | 5bfacdd9-f6b8-5c2f-a496-306f657964c8 |  | note | – – – – – – – – – – – – – – – – –
label | c26c04a4-c441-5bf1-9a40-51a6f7805396 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c55d8cda-3286-5d5f-9503-fa60fd1b007d |  | note | – – – – – – – – – – – – – – – – –
label | e569c712-e16a-56a5-bea0-70cd77c0c88d |  | note | VERIFYING DOCUMENTS: This ITP
date | 89238ae3-445d-5dd8-af0d-55dc3b611cf0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Measurement of Concrete Cover
label | 2b911015-d1ab-5674-920e-afa4cb0f476e |  | note | REFERENCE: 610.34
label | f4e0537e-ae4c-5a62-9592-64d8d140b637 |  | note | – – – – – – – – – – – – – – – – –
label | b6efcf9e-0174-5891-b130-fca5f14376d9 |  | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | 15256877-ba99-5e1d-91a8-48f521254149 |  | note | Minimum 10 no. measurements recorded in each area.
label | 9b3ab2ed-eaca-5e11-892f-7f2d429eb4eb |  | note | Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | 74859886-1c2a-59d6-9ded-0f9a15cd95a5 |  | note | Attach: Covermeter Check Record
label | e4eb4994-3c67-5036-8737-bc3e3b1c33ed |  | note | – – – – – – – – – – – – – – – – –
label | fb036163-040b-56e3-8a59-aff1af6a2367 |  | note | METHOD: Measure
label | ad7a8077-9076-59ed-936a-63ac884632c3 |  | note | – – – – – – – – – – – – – – – – –
label | 75b45957-bbfc-55ac-a02d-f4d1856b1593 |  | note | FREQUENCY: Each element
label | 530c3deb-dd58-5939-b61e-cac3b6f08064 |  | note | – – – – – – – – – – – – – – – – –
label | a88e67bb-674a-5b7e-9410-192359155d70 |  | note | CATEGORY: IP
label | db292379-f58d-5d52-b53d-e154566f3a5a |  | note | – – – – – – – – – – – – – – – – –
label | aa8555c9-4719-5663-a17c-ba005f4f48bc |  | note | RESPONSIBILITY: SE/PE/SPE
label | d6464b7e-e29a-5444-93e5-8d89942f5c0e |  | note | – – – – – – – – – – – – – – – – –
label | 47be8880-b778-5c11-8d9c-fd428cdc628b |  | note | VERIFYING DOCUMENTS: This ITP
date | c460922c-244b-5a08-af6d-13d84ba41123 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | 1b54646b-1b29-5a1a-a516-2fadf20096ea |  | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure
label | 4412e4b2-7df0-5c72-84ce-5888475b6bb8 |  | note | 610.35
label | 012f6176-156a-5602-9170-d439ba43686d |  | note | – – – – – – – – – – – – – – – – –
label | 791add12-90c3-5d6b-af84-8e839e26ecc6 |  | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
label | f0449e40-088a-5b91-954a-40bb469eca43 |  | note | Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
label | e6eab9bf-6ed3-5ff8-a515-83b83c44fd2f |  | note | Attach: Concrete Test Results or Maturity Test Results
label | 8af38397-caed-5566-bec8-4f3c48683c58 |  | note | – – – – – – – – – – – – – – – – –
label | b2cbe5f5-4815-5803-b4eb-60d6d7ea0311 |  | note | METHOD: Document Review
label | 779d771a-5f0b-5499-9f62-d658eefaa75b |  | note | – – – – – – – – – – – – – – – – –
label | 6ef1f64b-1ebd-5c03-b6bf-b320e180f3c6 |  | note | FREQUENCY: Where applicable, each substructure element
label | ec167fec-ad2b-512b-857d-c9b277899e21 |  | note | – – – – – – – – – – – – – – – – –
label | 5f9a015c-9a25-5ea4-b292-2be2e3e0a737 |  | note | CATEGORY: SP
label | 7bbf1125-caf4-5bf5-995a-00a880cf9357 |  | note | – – – – – – – – – – – – – – – – –
label | 51c177f1-f9f9-541f-a65b-be89e3fecb84 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 19d7587c-6ecd-5a62-8e62-4bba41eb8c51 |  | note | – – – – – – – – – – – – – – – – –
label | d581497a-4ef7-56d6-b8a2-c3feebf4d54d |  | note | VERIFYING DOCUMENTS: This ITP
date | cb058c64-f173-5256-ab45-3208ac8dd279 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Compressive Strength Test Results
label | b5188730-4ce1-56ae-b78f-c3b417134e0e |  | note | REFERENCE: IFC Drawings
label | 2c66621b-9034-5c2e-a127-cee3fb1657ee |  | note | Table 610.05.051
label | a24cf975-89c9-5798-871e-cc9980e3fe95 |  | note | 610.16 (g)
label | 0affeb42-a4be-519b-acd1-224474895810 |  | note | – – – – – – – – – – – – – – – – –
label | 01972f3c-6291-59bb-8d4a-4c91bcff0143 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 061c13b1-6420-57a2-86c1-d8b99b01cdd2 |  | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | e9dd5f19-a89a-5426-8782-ac6302084528 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 60a41712-0ab1-5e70-b476-4e943f9979a7 |  | note | Attach: Compressive Strength Test Results
label | 908355dc-bcad-5578-8150-7ebff13098a0 |  | note | – – – – – – – – – – – – – – – – –
label | cec44a47-bfcf-5d9b-a8c0-4f1b91aacedf |  | note | METHOD: Document Review
label | 1275d12f-c204-581a-aacb-c2cc2f0dfd24 |  | note | – – – – – – – – – – – – – – – – –
label | 992e5e8e-7a77-54dd-808c-4de45fd6a027 |  | note | FREQUENCY: Each cylinder
label | 24499514-0881-5f7a-853b-5b2fd9bd6813 |  | note | – – – – – – – – – – – – – – – – –
label | d400a452-d7a7-5f86-a6fd-4584dd7e237a |  | note | CATEGORY: IP
label | aa0777f9-42e4-506f-aff8-510b636b6763 |  | note | – – – – – – – – – – – – – – – – –
label | 5c8a5adc-df11-546c-9f5a-96b5a1122b20 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 94be2966-2561-5e3e-9fd5-dad269cc79ae |  | note | – – – – – – – – – – – – – – – – –
label | 931c5a59-f985-5a4a-ab59-c9474f4a3733 |  | note | VERIFYING DOCUMENTS: This ITP
date | b468f25c-6366-5491-8960-324590abaadb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 As-built Survey
label | 56894a34-3b58-5fa4-906c-c116c880615d |  | note | REFERENCE: IFC Drawings
label | 90688c05-f782-53d1-8571-8adaefcf9817 |  | note | 610.47
label | b19240e2-c264-5ae5-be37-ba4f2063ad7d |  | note | Table 610.472
label | 446717e2-0a6d-5988-91b9-3c69ec75cce5 |  | note | – – – – – – – – – – – – – – – – –
label | a31f127d-cec9-5578-bdbf-70b76a517a4d |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | f482476c-227b-510c-bfe8-0bd24c591681 |  | note | Attach: Survey As-builts / Survey Report
label | 67cb4fca-5739-52ff-8df0-903b9b1c2a07 |  | note | – – – – – – – – – – – – – – – – –
label | 64c08216-50eb-5cc8-86ea-73a140e2ee4e |  | note | METHOD: Document Review
label | 9ef32fa2-054c-5e86-affa-d2c8229dd4a8 |  | note | – – – – – – – – – – – – – – – – –
label | 7050ac23-6a22-5758-92e1-f47205c3dd83 |  | note | FREQUENCY: Each element
label | b0944d26-8a3e-56b2-98b7-da0317af1171 |  | note | – – – – – – – – – – – – – – – – –
label | 0c9cf177-85c2-5d83-9817-f56b314faac8 |  | note | CATEGORY: IP
label | e40c6f0a-2034-5219-921b-2373d39d2e4e |  | note | – – – – – – – – – – – – – – – – –
label | de3fa952-4a9b-5b71-80b7-9d6e13c5a2b1 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | bcdc4f83-fb66-54f1-b306-8690c2a7d353 |  | note | – – – – – – – – – – – – – – – – –
label | 4bc90829-e99d-5c26-bd67-8e8a08c42532 |  | note | VERIFYING DOCUMENTS: This ITP
date | e17dbb7f-e80e-5551-9681-4b07517b14ae |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Non-conformance Report (NCR) Closure
label | e2c46fb7-b0c1-5505-875a-8c9b40034327 |  | note | REFERENCE: MRPA Quality Management Plan
label | 7ea9266c-ece8-5956-b80d-1919dea34f03 |  | note | – – – – – – – – – – – – – – – – –
label | 3addc6fe-77a1-5a65-b4d4-e506bd1d158f |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 0ddced91-ed66-5a75-b20a-f1a87e6269f8 |  | note | – – – – – – – – – – – – – – – – –
label | a4c5cc64-c274-59bb-981e-907dff8a8fdd |  | note | METHOD: Document Review
label | 45276387-dbb8-51f8-a798-c3ecc6c52709 |  | note | – – – – – – – – – – – – – – – – –
label | 9643e8c6-63c4-5417-a47f-74060f3ae05a |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | b2de3941-b4f3-564e-ac34-fdfcfd5b73a8 |  | note | – – – – – – – – – – – – – – – – –
label | 6797bb66-df86-5eb8-b4f1-4fc1896ef357 |  | note | CATEGORY: HP*
label | cdaac92d-bc79-5de9-9442-43725c4b9ff3 |  | note | – – – – – – – – – – – – – – – – –
label | c758c11b-7a37-5a6a-a7b2-943fd6ba6d40 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 69d52d00-19fb-5fc2-a990-5e476c0617eb |  | note | – – – – – – – – – – – – – – – – –
label | 22d8f8e8-23a6-5a51-8b1e-9edcc5ea680f |  | note | VERIFYING DOCUMENTS: This ITP
date | 3593df6e-a187-55c8-b778-3ea62d47057f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 3915d7e8-c45d-52ad-890f-e1b8d3ad1bdf |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 4a737430-4f3f-55b8-b857-1bdfa8bbba25 |  | textbox | Name:
text | abf20f02-814a-5752-84a8-ac6c8b6ab06c |  | textbox | Position:
date | c481e701-3ffa-5d36-8c56-e4fc29c5fe74 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-067-CIV-CAMMS-Line marking | itp |  |  |  | Yes | ITP-067-CIV-CAMMS-Line marking Rev 0 | ed9ffbb7-7306-4a3d-91c2-c8929b64a261
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 88264a22-f0c2-5e56-b16d-ea884dd1003f |  | note | Document Title: ITP-067-CIV-CAMMS-Line marking
label | bbf9eea8-dbaa-52f6-a6f6-4aad2f5a9ee9 |  | note | ITP Description: CAMMS-Line marking
label | 044bbbe5-b010-5b9a-a481-f37ce44dcb5a |  | note | ITP number: 067-CIV
label | ae3f94e8-023c-526a-b9f3-06c57fe17dcc |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 4ef8e0f3-5003-508f-838e-e991e2d0691d |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | eee6647c-7bbc-5aca-bff1-b1906ad5f48a |  | note | Revision Number: 0
label | 814b4b83-4c2e-5407-be82-549ed20eaf3d |  | note | Revision Date: 13/10/2023
label | af68125a-63dc-5b4b-9a45-fe56ce49d434 |  | note | ITP created by: Victor Mira
label | e6fe9703-05ee-5b51-9706-152c31fc4cb1 |  | note | ITP approved for use by: Victor Mira
label | 5256cfb7-74e4-54b0-8577-25c55a23212b |  | note | 1.1 Non Dependent
label | ef14733c-0a99-5cdf-afde-22d43f979fa7 |  | note | Reference: Vicroads Section 721 February 2017
label | 7b90b911-96a9-5ded-96ae-e7babceabfe0 |  | note | 1.2 Non Dependent
label | 092d22b4-a438-5f8b-9c0f-3266250269e2 |  | note | Reference: Vicroads Section 175 November 2019
label | 65f58373-f09f-586c-99c8-34429f211901 |  | note | 1.3 Non Dependent
label | 44f33045-cfc3-5fc2-ab58-942531381a2c |  | note | Reference: Vicroads Section 853 February 1994
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.2 Type of marking material as shown on design drawings and shall conform to the Standard
label | 3d5c4cd8-49d0-5316-9b84-efd3c7c7feaf |  | note | REFERENCE: Vicroads 721.A05
label | f0534e3e-0991-5678-964b-ce30afa14ee4 |  | note | – – – – – – – – – – – – – – – – –
label | f189b898-39a5-5b73-8da1-ea98bfd3a20c |  | note | ACCEPTANCE CRITERIA: Type as per relevant design drawings, obtain Conformance Certificates and test reports from supplier
label | 6e198228-658c-53c4-b272-5661e0f12f28 |  | note | ○ Provide the principle a list of materials that to be used with a certificate of conformance with associated test report
label | 7f8a2f72-cb3b-5a54-9c69-4d0124f40f2c |  | note | – – – – – – – – – – – – – – – – –
label | 1431c28d-bf9b-5f21-a69f-42cb1203e326 |  | note | METHOD: Document Review
label | 0f8c99dd-a7f9-55cc-8780-eee5d20f928b |  | note | – – – – – – – – – – – – – – – – –
label | 329a6566-f5bc-5fb9-9f5e-1433dd87b0e7 |  | note | FREQUENCY: Once
label | 8b299750-43a4-5ac9-9667-65dd2767d8aa |  | note | – – – – – – – – – – – – – – – – –
label | d861c530-cd01-5ea3-ba68-cd0c7895f1bf |  | note | CATEGORY: IP
label | 48bd07c8-1196-5163-a7b4-35d9d58e8910 |  | note | – – – – – – – – – – – – – – – – –
label | c7f0ec9c-c4b0-5ce1-8d69-07c5b6b2f0fa |  | note | RESPONSIBILITY: SE/PE/SPE
label | ef6d14b4-aa8b-5520-a49a-cbbc3f5a0c7b |  | note | – – – – – – – – – – – – – – – – –
label | 662ffc83-d191-5595-8a44-e613b26f22aa |  | note | VERIFYING DOCUMENTS: Material certificate
date | 4807e776-67e3-50f9-83e2-861c7d61ce6d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Raised Pavement Markers
label | b8e36d28-841f-5801-8a7d-4ae0834b6df1 |  | note | REFERENCE: Vicroads 721.A05
label | e45bf111-e8d6-56df-992c-aad95c2a17f4 |  | note | – – – – – – – – – – – – – – – – –
label | 38a865f3-bcab-5a4e-bc3d-e3a38e439ed2 |  | note | ACCEPTANCE CRITERIA: Raised pavement markers shall comply with the relevant requirements of AS 1906, Part 3 as listed in Section 175.
label | cdafdfc0-4929-5557-83b0-fb71b8715c54 |  | note | (ii) Temporary raised reflective pavement markers shall comply with the relevant requirements of AS 1906 as listed in Section 175, and shall be at least 100 mm in width and to a height of 50 mm with white reflective material on both sides and include protective covers for the reflective material
label | 01f9e44f-c79d-5492-aa1a-e2de5a89b2ef |  | note | – – – – – – – – – – – – – – – – –
label | 76b51fed-9d46-5b14-a9cb-81b1968c258d |  | note | METHOD: Document Review
label | e1d7e5a6-c105-57ef-9677-adaf7f5210c6 |  | note | – – – – – – – – – – – – – – – – –
label | ffb8810c-da50-5c2e-a0be-1ba47af33410 |  | note | FREQUENCY: Per Material
label | a4be4886-6774-5842-b78f-8e98e8be52e8 |  | note | – – – – – – – – – – – – – – – – –
label | 08ac1612-cf83-5eb6-81ff-9faf4d9b44d8 |  | note | CATEGORY: IP
label | 7d5fa267-1b0d-546b-b623-c3c062f842bf |  | note | – – – – – – – – – – – – – – – – –
label | 275f5f76-7533-53b1-92c7-146080fdfbb8 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 084581d6-6779-503e-b83f-3797fc12bd01 |  | note | – – – – – – – – – – – – – – – – –
label | e1e5dbcd-da44-51ea-982f-4e47716b45b0 |  | note | VERIFYING DOCUMENTS: Material certificate
date | 14a10157-314e-5876-9b4a-a2d3cec25636 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Adhesive
label | 18ad33d4-7992-555e-8a86-8720ff4d453b |  | note | REFERENCE: Vicroads 721.A05
label | d3590d0a-0906-573d-9ac1-26d455f9aad8 |  | note | – – – – – – – – – – – – – – – – –
label | 88663f61-bf5e-54b6-b4c5-50f370fb244b |  | note | ACCEPTANCE CRITERIA: Hot melt bitumen adhesive shall comply with Section 853 - Hot Melt Bitumen Adhesive for Raised Pavement Marker Installation.
label | ea00ef43-0eb1-56b9-be00-c79b46e1e3d4 |  | note | ○ Other types of adhesive materials shall only be used with the approval of the Superintendent
label | 7f3fc4f3-1750-5b81-ab79-a9b7cdb1d3b7 |  | note | – – – – – – – – – – – – – – – – –
label | 0cf579e8-53a3-50df-bc1d-b22e1d93d928 |  | note | METHOD: Document Review
label | 6ba6a14b-e007-5f4b-a462-7c5d9c0d2408 |  | note | – – – – – – – – – – – – – – – – –
label | 48a46eab-9261-570a-b858-1b4bd27f28d0 |  | note | FREQUENCY: Per Material
label | e6605968-bf81-58cf-bcbf-a18f97446be4 |  | note | – – – – – – – – – – – – – – – – –
label | fd2045bd-89ce-5dff-8df3-2c386fcc00c8 |  | note | CATEGORY: IP
label | cb1db447-5911-56f1-bbad-8cf79049c1f1 |  | note | – – – – – – – – – – – – – – – – –
label | 37c967d5-d67a-5dea-adad-88b72eb12c99 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e3171786-4d0f-5b4b-9184-7d27706e6c1c |  | note | – – – – – – – – – – – – – – – – –
label | d14885fe-59d7-5aac-a736-b43d9af1873c |  | note | VERIFYING DOCUMENTS: Material certificate
date | 73cda65b-f35e-51e1-ad76-38ecaf1a2269 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Line marking and Road marking Paint
label | d89047be-1d9b-56f6-bdd7-c3ac7afc32ab |  | note | REFERENCE: Vicroads 721.A05
label | 00e2aa43-7778-5592-a1da-54eb79a4d93e |  | note | – – – – – – – – – – – – – – – – –
label | 3f481817-250b-5d6e-bc64-32a73fafd200 |  | note | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent-borne paint or AS/NZS 4049.3 for water-borne paint as listed in Section 175.
label | 266196de-383e-5e8b-b52c-d3eab65c576e |  | note | – – – – – – – – – – – – – – – – –
label | 053374f1-2893-57bf-a852-7897931c6b43 |  | note | METHOD: Document Review
label | 60877ca9-b6d5-5de5-8b19-1efc2f568868 |  | note | – – – – – – – – – – – – – – – – –
label | 331bb275-48e7-5a55-9bb2-f5fc27fb22dc |  | note | FREQUENCY: Per Material
label | fff418f6-b83b-57a6-a1f9-e0bad64a3a90 |  | note | – – – – – – – – – – – – – – – – –
label | 9d63d566-0542-545a-8c57-80040587c0d9 |  | note | CATEGORY: IP
label | abc1d978-9bba-5aa1-b76b-85ada113874a |  | note | – – – – – – – – – – – – – – – – –
label | 85c3aec5-aa1e-5828-ae8c-c69a32100998 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7a846ecf-7d9c-521b-8122-93c5842f925f |  | note | – – – – – – – – – – – – – – – – –
label | 12e52f6e-de84-51b6-bfa1-17d83e9024b5 |  | note | VERIFYING DOCUMENTS: Material certificate
date | fdf69a54-340b-5faf-8f04-b3f5543dfc4d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Glass beads
label | c4c7198e-ef82-5c9a-b1a3-233d3ec4cb8b |  | note | REFERENCE: Vicroads 721.A05
label | ec59b5ba-cca5-5dcd-83a0-95f2b149fa40 |  | note | – – – – – – – – – – – – – – – – –
label | d68dd8bd-46c5-594f-b774-d980d58c0174 |  | note | ACCEPTANCE CRITERIA: Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
label | 3120f07b-051a-5f29-90ac-2186abfecbe4 |  | note | – – – – – – – – – – – – – – – – –
label | fa25a813-93f0-51e2-b746-867b04a69fc7 |  | note | METHOD: Document Review
label | 73f01a71-0277-587d-9b95-45f7871d35e7 |  | note | – – – – – – – – – – – – – – – – –
label | e2e697f8-6001-5675-8986-0b66f0d878b9 |  | note | FREQUENCY: Per Material
label | d98c8887-d8c7-51b9-8d8d-a0bdee3cb4ce |  | note | – – – – – – – – – – – – – – – – –
label | dc54d889-b5a0-55e4-9bfd-c0cd77b1b8f9 |  | note | CATEGORY: IP
label | 7c68b3ad-cec2-5df7-8813-66469acd8619 |  | note | – – – – – – – – – – – – – – – – –
label | cb2847d2-dca4-569d-8d28-30d3276763f0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | ba4a405e-a636-5799-b02f-341b665b10e2 |  | note | – – – – – – – – – – – – – – – – –
label | 1e6422bc-2ba8-5512-a30e-285a25b78525 |  | note | VERIFYING DOCUMENTS: Material certificate
date | 27d9d07a-09e0-52a7-b32e-4c20fce83e55 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Glass beads
label | 259143bd-4b7d-5912-aa76-219f6b7982ae |  | note | REFERENCE: Vicroads 721.A05
label | a60a7ad9-51da-5503-9961-994e3a48e3a6 |  | note | – – – – – – – – – – – – – – – – –
label | 1020fdad-3d40-51e8-97f2-5eb26b4d259b |  | note | ACCEPTANCE CRITERIA: Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
label | 6687541e-b7a7-5e76-85b6-809a990f487a |  | note | – – – – – – – – – – – – – – – – –
label | b1dc4c27-cfc1-5e15-af2b-1e632c820666 |  | note | METHOD: Document Review
label | 8f9cedd0-72d2-51e5-9503-f013bc3a88de |  | note | – – – – – – – – – – – – – – – – –
label | f50f6155-5a12-5b18-a515-7fe59be6cd1d |  | note | FREQUENCY: Per Material
label | 51d7439b-ebb7-52a4-9ce3-fbf148b8b6cd |  | note | – – – – – – – – – – – – – – – – –
label | 7bb9f6d8-a12b-5e08-80a7-4d8e1e10eba1 |  | note | CATEGORY: IP
label | 3abc636a-0527-582c-8327-2293fc289e3c |  | note | – – – – – – – – – – – – – – – – –
label | e96f3867-1334-58ce-89fd-7c73bc79a056 |  | note | RESPONSIBILITY: SE/PE/SPE
label | b518637e-45e1-5123-a44f-b82bf8ac8c37 |  | note | – – – – – – – – – – – – – – – – –
label | 49cc0cbe-53c5-52d3-a852-19d75aea542f |  | note | VERIFYING DOCUMENTS: Material certificate
date | 68319b39-c6b2-5c76-afb1-58d87466a9cf |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 2.1 Accreditation to Painting Contractors Certification Program
label | ddbecf78-35e3-5f56-8f1e-e0d10bc5071c |  | note | REFERENCE: Vicroads 721.D01
label | 4e78a207-6995-5733-9cd3-0071ad4a2893 |  | note | – – – – – – – – – – – – – – – – –
label | d2aa9856-6138-5804-84e3-6e8f9e5d35c2 |  | note | ACCEPTANCE CRITERIA: Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO.
text | 6fdfa379-450b-53c2-8615-4a68e47bb708 |  | textbox | Enter: Teambinder Approval number
label | cf9486db-f5d5-5dd6-8171-81937a5d36dc |  | note | – – – – – – – – – – – – – – – – –
label | 0c0bb230-5076-52e8-95e2-57488c2fb3cf |  | note | METHOD: Document Review
label | d0cb92f4-dbc0-5e32-959d-546b87b18815 |  | note | – – – – – – – – – – – – – – – – –
label | 23945da0-f6c2-57d5-9eb3-23078a4755ef |  | note | FREQUENCY: Once
label | 87abd3cb-ace5-5a07-9735-4203611e74ef |  | note | – – – – – – – – – – – – – – – – –
label | 2a0d9ca8-4e18-5b20-915b-ef8334e77dd0 |  | note | CATEGORY: HP
label | 54fee893-ea54-505b-986d-e218f90439e4 |  | note | – – – – – – – – – – – – – – – – –
label | 3df96645-fd1d-5d5e-8920-6f115e1eceed |  | note | RESPONSIBILITY: Nominated Authority
label | d4c4192b-7a51-5a8b-9945-f1dda9627268 |  | note | – – – – – – – – – – – – – – – – –
label | a2ad733c-ba12-5d30-a54e-9c15200d13f8 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, PCCP Accreditation
date | cdf42a3c-233a-54ed-94b7-3cde5532f8b6 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1 Surface preparation
label | 19d0098c-38de-5711-b185-5afd27bdfa1b |  | note | REFERENCE: Vicroads 721.A06, Vicroads 721.A09
label | 6762fe2e-398d-5682-b06f-24bf5a031546 |  | note | – – – – – – – – – – – – – – – – –
label | 5a26f756-4c3c-5141-a2cf-56e0d721677a |  | note | ACCEPTANCE CRITERIA: The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
label | a8455a26-c158-5e39-9d99-6bb22b889957 |  | note | ○ The area around making area is also clean to avoid tracking into the marking area
label | 71c5a4cf-fdbb-5da8-8f2c-a120228b8357 |  | note | ○ Removal of existing unsound, obsolete or redundant pavement markings
label | 3aa5b007-6c01-5a43-a904-911a7580b419 |  | note | ○ Removal of any foreign materials and debris within reasonable limits.
label | 41bf68b9-990b-57fb-a66a-2da05cf0a4e1 |  | note | – – – – – – – – – – – – – – – – –
label | 1e2eb047-45b7-5c9f-b67e-afef2c4da6a9 |  | note | METHOD: Measure, Visual, Document Review
label | 78648296-ea95-5fa2-a39f-027150e0896e |  | note | – – – – – – – – – – – – – – – – –
label | 305bbb99-5d71-530d-ade1-3fb47e974ad6 |  | note | FREQUENCY: Per Lot
label | 29602dd8-80bf-58b3-a1e2-9d2f5ad51ee2 |  | note | – – – – – – – – – – – – – – – – –
label | 89b1e16c-a3a3-5ebc-9a99-777c167611d4 |  | note | CATEGORY: IP
label | b567c19a-1361-5346-ac26-2df460f10bdd |  | note | – – – – – – – – – – – – – – – – –
label | 92c00167-9df1-5c57-9712-21db0834238e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9bd82e77-afdb-5bc9-82e0-391d5b122f43 |  | note | – – – – – – – – – – – – – – – – –
label | 7d8971c3-bda0-564f-be75-aa7412a922b9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8c90fa45-b0ff-5dfa-a1ff-2396264170a7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Redundant pavement / unsuitable marking markers removal
label | f5c6ce6a-fc25-5c32-9153-9a939490629b |  | note | REFERENCE: Vicroads 721.A12, Vicroads 721.A06, Vicroads 721.A08
label | ccd02e8e-ce69-5f5c-ab9e-98075805f585 |  | note | – – – – – – – – – – – – – – – – –
label | 722444e3-d2d5-549f-947a-cb29670aa909 |  | note | ACCEPTANCE CRITERIA: Where removal of existing pavement marking/unsuitable pavement marking to the standard is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
label | 347b1479-7a70-5643-8cc1-ec3e85a30024 |  | note | – – – – – – – – – – – – – – – – –
label | 57baf991-3227-59e4-8f0b-4b3b83702029 |  | note | METHOD: Visual /Site Inspection & Document Review
label | c321414e-1a23-5607-8ea5-ab1edb9b3ff1 |  | note | – – – – – – – – – – – – – – – – –
label | 1450eddb-ed2d-58e2-beb9-13a2d715ca01 |  | note | FREQUENCY: Per Lot
label | abe3372a-c648-513c-a9cc-109269822137 |  | note | – – – – – – – – – – – – – – – – –
label | 77f8fa36-9ff9-5781-9dda-3b0eac457e7f |  | note | CATEGORY: HP*
label | c7c58424-ccea-5b64-9369-58da60fa5532 |  | note | – – – – – – – – – – – – – – – – –
label | 1e42bf7e-1c93-5276-8477-34a4ace4e1db |  | note | RESPONSIBILITY: Nominated Authority
label | 0e08d093-f315-58c8-86dc-13b5af099b11 |  | note | – – – – – – – – – – – – – – – – –
label | aa1de47f-1913-591b-8c7d-6cfd7608ba26 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | f4841ad6-90a8-59a3-a6a5-db1b1da32e83 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Set out the works for installation of pavement markings / raised markers
label | f1a31089-153d-548f-91ce-a51deecb3779 |  | note | REFERENCE: Vicroads 721.B05
label | ea4ee8fc-8bba-51e6-a6ca-1905e16e5f3e |  | note | – – – – – – – – – – – – – – – – –
label | f57f7b89-af3e-567b-aaa2-3f6d255ee6e2 |  | note | ACCEPTANCE CRITERIA: Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless a written exemption has been granted by the Superintendent
label | 2dcfa4ef-9cdf-5bbb-a5a9-8e38c58ce03f |  | note | – – – – – – – – – – – – – – – – –
label | 1562d565-6d10-5ebc-8560-7a2bdf2d3303 |  | note | METHOD: Survey Document Review
label | b20442fd-dfc2-5bf9-a4a0-196656f6d614 |  | note | – – – – – – – – – – – – – – – – –
label | c8381078-5346-5aa8-89b3-78352b1aa3b3 |  | note | FREQUENCY: Per Lot
label | ffdc4436-79c1-539a-9682-46497a074cef |  | note | – – – – – – – – – – – – – – – – –
label | d96a72d9-4dcf-56cc-9ab9-67f1db0e19c0 |  | note | CATEGORY: HP
label | b35e5ef4-0138-5c98-9231-4ef76cd57c95 |  | note | – – – – – – – – – – – – – – – – –
label | 6384e5bb-15f3-558e-b028-e09b5d4c90bc |  | note | RESPONSIBILITY: Nominated Authority
label | 8616c346-2762-550d-9c96-b93d044e1635 |  | note | – – – – – – – – – – – – – – – – –
label | 927be1e1-ee2f-5415-814f-3099aafe9833 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 95b82eb6-9101-5993-82d1-e2e32a4b616a |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 3.4 Application of pavement marking / markers
label | 654e6012-100f-56bd-a00e-18cb0fb8716e |  | note | REFERENCE: Vicroads 721
label | 6fb20234-6571-5b65-8b6d-ace40379d72a |  | note | – – – – – – – – – – – – – – – – –
label | a6cdf044-a8e5-5a3d-aedb-125f9387aa55 |  | note | ACCEPTANCE CRITERIA: Check conditions for application of marking paint & materials.
label | b75619b5-136d-5822-90b6-ca3ef8e8d953 |  | note | (i) Paints and markers installed as per manufacturer’s recommendations.
label | f68fe9f5-b56b-53f6-a6f1-5de0f51d5155 |  | note | (ii) The same materials used with those nominated in the certifications.
label | ccd428b3-75d9-5c38-935e-bf88a10adc2b |  | note | (ii) All longitudinal lines have been applied by the nominated machine unless approved by superintendent
label | 8972cd6a-e370-5302-8f7a-3df4ef290c71 |  | note | (iv) Verify markings are straight or with smooth, even curves where intended.
label | 4686e30d-3041-56bd-8ac6-4e1217322fef |  | note | (v) Edges are clean sharp cut off.
label | 565c4959-d2de-58ed-9688-12f2cbc155f4 |  | note | (vi) Markings uniform in appearance, texture, width & thickness & free from unbeaded areas
label | b831933c-f049-587b-aee5-17ce4cbd7b55 |  | note | (vii) Waterorne Paint & Glass Beads application rate conform to the requirements of Vic road 721.E01 requirements.
label | 7c2d4b70-a59e-5e7e-b0a5-e38c6c8df085 |  | note | (viii) Markings are neat & free from traffic damage or other defects
label | 2c24888c-b5a2-566d-9f8e-a3a95bfe1dfd |  | note | (ix) Marking protected from traffic until hardened
label | 568c6e74-0632-5dd9-8a87-28fbc3428f50 |  | note | – – – – – – – – – – – – – – – – –
label | f62c906b-65a6-5688-b10c-bbb069a3343f |  | note | METHOD: Visual /Site Inspection & Document Review
label | bfeb578e-0e7d-580d-ab52-28dfc97a5dfa |  | note | – – – – – – – – – – – – – – – – –
label | 9950ad89-25ae-5db8-b9b4-7ba5e96fb64e |  | note | FREQUENCY: Per Lot
label | 6fa598ab-a110-5c9b-8a06-9afbf050214b |  | note | – – – – – – – – – – – – – – – – –
label | dada92ad-eb45-5499-b268-5dcc7a95e54a |  | note | CATEGORY: IP
label | 6e706030-f956-52f7-8de7-90b057f74fda |  | note | – – – – – – – – – – – – – – – – –
label | 8a5cd7fe-5031-5f1a-9d64-d395366d37d0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a98fd226-b912-5daa-8d45-d59eed668a9c |  | note | – – – – – – – – – – – – – – – – –
label | 6a2b02dc-a24c-5bf5-95c2-1e523736b2da |  | note | VERIFYING DOCUMENTS: This ITP
date | f24c610d-eac7-5e49-998e-78fbe45094ef |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Tolerances for new marking/marker installations
label | 014d8c32-4611-5bd0-a1bb-60391b416d4b |  | note | REFERENCE: Vicroads 721.A10 Table 721.A101
label | 47c32c45-f472-5292-919b-ef4df7353b67 |  | note | – – – – – – – – – – – – – – – – –
label | d4e22362-b673-584f-aa4b-8d0e92ef8f2f |  | note | ACCEPTANCE CRITERIA: Pavement marking :
label | 94355852-e01f-5958-b31f-d8d908af9e39 |  | note | ○ Distance between the centreline of the marking and the centreline of the set out mark - <30 mm
label | 1a383df7-db1b-5883-8d05-b5995e11daf3 |  | note | ○ Distance between the centreline of the completed marking and the centreline of the previous marking - <15 mm
label | 7fc6c0bf-3159-57e9-9b72-956963b38d90 |  | note | ○ Width of completed painted markings - ±10 mm of the specified dimensions
label | c394d8bd-7af1-554f-bff1-6c1520fd3883 |  | note | ○ Width of completed markings for long life materials0 mm to +10 mm
label | 036c6c57-c275-5644-9a06-9b19620dc43a |  | note | ○ Length of completed stripes and blocks - 0% to +10% of the specified length
label | 982d9b85-1c9f-568d-83ee-20d452ee2bde |  | note | ○ Gap between double lines - - 10 mm to +0 mm of the required 100 mm gap
label | cebed4ee-87de-5269-9645-e6c9d7b78a7f |  | note | Raised Pavement Markers:
label | 28b94f64-0ebd-5c27-b28d-a121cb3210d3 |  | note | (i)Markers in line with broken segments
label | b3a7160a-f6d4-5016-b74f-dc271d7a1d39 |  | note | ○ Transverse position - ±25 mm of the centreline of segments
label | 5e5ba1ae-6bab-5f78-a728-bb1fb12d8cc2 |  | note | ○ Longitudinal position - ±0.5 m of the specified position
label | a4413542-c051-57bf-aa61-fe7bf2e904c0 |  | note | (ii) Markers in a longitudinal group
label | ddcab53a-5f0b-51ef-bc0a-bb65131927b5 |  | note | ○ Transverse position - ±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
label | 85339573-dce6-515a-a8a6-0abc07a5310a |  | note | ○ Longitudinal position - ±0.5 m
label | a8a66043-350c-5c96-ae7d-9242e9ad68b2 |  | note | ○ Spacing of markers within the group - 50 mm of specified spacing
label | 5dc8666b-d2fc-517f-9be3-078755077a5f |  | note | (iii) Markers adjacent to an unbroken line
label | 14a35de7-fd41-5ddc-954e-b8106aa01221 |  | note | ○ Clearance to edge line - ±5 mm of the specified dimensions
label | 58eb32c7-4af2-526f-b096-0b74ed01d715 |  | note | ○ Longitudinal mismatch between markers in transverse pairs - <25 mm
label | 5562daf7-a917-596d-a63b-49bdd8b0f2f0 |  | note | ○ Longitudinal position - Lesser of: 0.5 m or 10%
label | 0a032f4e-5d9c-560d-bad5-acc480b48365 |  | note | (iv) Orientation of reflective markers - Lower edge of the reflective face at 85º to 95º to centreline of roadway or adjacent line
label | a2b7dca6-4f71-533f-bb49-fe94048d0c41 |  | note | ○ Thermoplastic profiled lines
label | dfddc90a-ece2-5c3d-a8a9-be5c02facb4e |  | note | (i) Tolerances on dimension
label | b7604007-9dbb-55ca-ad46-e1ff03c97dc8 |  | note | ○ Line width - +20 mm, - 5 mm
label | ec991d82-24e1-5f61-a95f-1998804d7dca |  | note | ○ Line height - +2 mm, - 0 mm
label | d40e0069-056b-54da-ba8e-f1b49750fe7f |  | note | ○ Extrusion breadth - +10 mm, - 0 mm
label | 9c7190c6-2f8b-5ecc-a185-36a7f6d239bc |  | note | ○ Extrusion spacing - ±15 mm
label | cc40588a-274b-5145-93b9-04a6b60cc457 |  | note | ○ Extrusion shape - ±25 mm at any point from rectangular shape
label | 9758808a-a035-5b59-a4e0-4b796cdbbb1d |  | note | (ii) Tolerances on position
label | bb793b75-4eec-5f1c-99d4-f3778c47a4e3 |  | note | ○ Distance between the centreline of the marking and the centreline of the set out - <30 mm
label | 6287eb19-8174-51cd-9d27-c133580487b1 |  | note | ○ Length of the completed lines - - 0% to +5% of the specified length
label | 03a09ab6-f904-53ea-ac4d-a9d9e1027a69 |  | note | ○ Longitudinal position of individual extrusions - ±50 mm of any previously applied profiled lining
label | ceaa0e78-449c-5952-948f-7af46aee1bcd |  | note | – – – – – – – – – – – – – – – – –
label | 72150af7-1cdc-543f-92ee-8a7a1a0b45cd |  | note | METHOD: Visual /Site Inspection & Document Review
label | 374932e4-828b-5a3a-99c5-79de0809003c |  | note | – – – – – – – – – – – – – – – – –
label | 70d3ea4b-f772-58b3-8cf5-f834c8fcbbbb |  | note | FREQUENCY: Per Lot
label | f12eaa56-b218-50d3-96b9-6e59b13ab904 |  | note | – – – – – – – – – – – – – – – – –
label | d4f0d803-9a8d-52af-948d-cc573c448f2a |  | note | CATEGORY: IP
label | c9be1fb1-09d6-5983-8356-4ade79e0d358 |  | note | – – – – – – – – – – – – – – – – –
label | fe8a186e-f740-5133-9ec0-536cd07c0b92 |  | note | RESPONSIBILITY: SE/PE/SPE
label | dd0209a0-e5ea-5595-ab50-81d7c888cd47 |  | note | – – – – – – – – – – – – – – – – –
label | ed5ee6c2-ca59-5fd8-9256-e9a9354a1cec |  | note | VERIFYING DOCUMENTS: This ITP
date | 1c4afe89-3077-5b1e-b027-bfd395b2aab2 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 3.6 Retroreflectivity Report
label | 3aee0fc0-abcb-5584-9097-4976186f1f94 |  | note | REFERENCE: Vicroads 721.B06 (b)
label | 15cd57e2-696d-5e8e-814e-0f78ffd38745 |  | note | – – – – – – – – – – – – – – – – –
label | e936276c-bbdb-56b7-a68d-2e16552b7c6b |  | note | ACCEPTANCE CRITERIA: Complete and forward Retro reflectivity Report in a form approved by the Superintendent showing the level of retro reflectivity determined for each test lot in accordance with the requirements of Clause 721.A12.
label | 7d89a0af-f118-5c11-b3ad-07fc91eba076 |  | note | – – – – – – – – – – – – – – – – –
label | eee5f806-6b19-5d4a-89d0-5028449b4d6e |  | note | METHOD: Document Review
label | 4207d87f-d197-5132-84b1-8141559e6465 |  | note | – – – – – – – – – – – – – – – – –
label | c77d2b66-cbd6-5079-9a37-2a022609f138 |  | note | FREQUENCY: Per lot
label | ceacda12-eec7-5957-97e8-19927149ceef |  | note | – – – – – – – – – – – – – – – – –
label | 99564e49-6274-5cea-8756-2366402c7b51 |  | note | CATEGORY: HP*
label | e6a29025-cc54-5013-a60c-76d6851df228 |  | note | – – – – – – – – – – – – – – – – –
label | 36fa9a79-1092-53c2-9277-a714b73fecca |  | note | RESPONSIBILITY: SE/PE/SPE
label | 26f5d68e-7128-5192-9b87-14a70160f0ed |  | note | – – – – – – – – – – – – – – – – –
label | 46b473cb-8a97-59e7-bb08-afd06306d3c5 |  | note | VERIFYING DOCUMENTS: This ITP
date | 66458b51-b808-5db5-960f-42b6f02a528f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Job Completion Report
label | 809432e8-2a99-5da0-88cb-f474ec4583b3 |  | note | REFERENCE: Vicroads 721.B06 (a)
label | 4607aaa8-8db6-5364-9e2f-4b4ba37b7a83 |  | note | – – – – – – – – – – – – – – – – –
label | 2ef8e1eb-7989-5e65-b279-0aeeb0f2552b |  | note | ACCEPTANCE CRITERIA: For New Markings the Contractor shall complete and forward to the Superintendent a Job Completion Report (Pavement Markings).
label | 1d4ff86a-4d83-53bf-917a-7208b029d87a |  | note | – – – – – – – – – – – – – – – – –
label | 90b77f68-8d89-5896-a575-1afb08a6d55e |  | note | METHOD: Document review
label | 0a410cbd-340e-5bb3-96fd-c70e240a72d0 |  | note | – – – – – – – – – – – – – – – – –
label | 246b7e3f-b5b3-5029-9127-0490853101bd |  | note | FREQUENCY: Per lot When applicable
label | 92da376b-6470-5340-a02a-f71f23a18185 |  | note | – – – – – – – – – – – – – – – – –
label | a60cc62b-21ee-52b8-acd5-06edb6131141 |  | note | CATEGORY: HP*
label | 7e384554-f1e7-506b-8a6f-4e30a805e0eb |  | note | – – – – – – – – – – – – – – – – –
label | 66f67a24-ce5c-5140-8fd9-64a3df2a61ac |  | note | RESPONSIBILITY: SE/PE/SPE
label | 52637fd2-6a51-51dd-9f16-7d1cc7594eaa |  | note | – – – – – – – – – – – – – – – – –
label | 0f723e3f-c8dc-5c51-a9ef-c302f9081a79 |  | note | VERIFYING DOCUMENTS: This ITP
date | ed6b6b1c-ee23-5b66-9753-7b79a1591df1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | d7253df6-206e-5baf-9dcc-ddb3f9886f39 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | e1a83f84-d2fa-5229-8caf-a9f9dc758859 |  | textbox | Name:
text | 0af60caf-12a9-54be-b1b2-8013ce4af119 |  | textbox | Position:
date | 56b381fc-894f-54a5-8f49-a73bb39a8642 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Type A Fill - Road Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Type A Fill - Road Rev 0 | edb8489a-90f8-492d-ad04-69bd2b474d92
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | fa515f9e-725f-50f4-be1f-a6b2bc0541c0 |  | note | Document Title: ITP-CIV-CAMMS-Type A Fill - Road (Supply and Install)
label | 97300609-12a7-5628-bdc9-4acf6f82efef |  | note | ITP Description: CAMMS-Type A Fill - Road (Supply and Install)
label | 8734d226-5cc2-54e7-842c-e6bd4aa94f1b |  | note | Discipline (e.g. CIV/STR/RAIL: CIV-CAMMS-
label | 88c0230b-74ba-53fb-a74f-612a6c03abe6 |  | note | Revision Number: 0
label | 42ec91ab-4274-588a-852a-d85e0c89c4a4 |  | note | Revision Date: 18/08/22
label | 9ad2ab18-80fe-5bc2-9a88-69329621b123 |  | note | ITP created by: Victor Mira
label | 3bbb779b-ced0-53b0-a080-606bd8a2c886 |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 018bec5b-629f-5969-8100-1e4c5529b396 |  | note | Reference - IFC Drawings
label | 8cbdf062-1778-5cd1-a8ab-1bdc122a39ff |  | note | VicRoads Standard Section 176 (Sept 2008)
label | 0c735927-5aa1-56df-931d-d58294b87d74 |  | note | VicRoads Section 204 (Dec 2015)
label | e438ad5b-24c0-53c6-bb70-2929e7257ec4 |  | note | Code of Practice RC500.20
label | 674407cd-00b1-590c-962b-d62a428b746b |  | note | Code of Practice RC500.5
checkpoint-group |  |  | section | 2 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance
label | 52961df4-f35e-5d8d-82bf-34d730d52a16 |  | note | Reference - Section 204.04 b)
label | 2b84e997-c714-5362-9f95-282d970aae03 |  | note | Table 204.041
label | f17b8615-076f-554f-8675-ff64038d2b4c |  | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | 608a3896-a8d7-596c-8ca9-4da4672c6af7 |  | note | • Assigned CBR≥%8%
label | e464fc1f-72d2-5a65-b593-44ed4d1dbca9 |  | note | • Swell ≤ 1.5%
label | 2d679f7b-5d52-5854-8eda-0aafbbb2da10 |  | note | • Permeability ≤ 5X10-9 m/s
label | 0a5eb090-42c7-5d1c-bc0f-e31a073c22f7 |  | note | Grading:
label | 5f88c050-5e87-5579-857d-b9d1b035bdd5 |  | note | • 75.0mm 100%
label | 3ae4cdd7-51ca-5616-9415-d04690a9e3fe |  | note | • 4.75mm 40-80%
label | 6d63dda9-dba8-543d-a9e0-f0985b64a6c6 |  | note | • 0.075mm 10-40%
label | eeac30c5-2700-5c75-acc5-6ba749e43852 |  | note | Reference: Material approval in Teambinder:
label | cda2de01-6a7d-5f28-8d63-0f36fc87acc9 |  | note | Method - Document Review
label | d6121d7e-6b4b-5ca9-a452-1c50748a0e11 |  | note | Frequency - Once, for each material type
label | 36ba39b7-95e1-5196-8164-087c2589eb83 |  | note | Category - HP
label | 42edf10c-17f6-57f4-9c84-f7aac02872dc |  | note | Responsibility - SE/Nominated Authority
label | 91575386-20e0-54b4-b069-1a864be914dc |  | note | Verifying Documents - Supplier Material Conformance Certificate
date | 65b4a28f-3523-5468-990f-692107621028 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Pre-Commencement of Fill Works
label | fb7772ea-2928-5d64-abab-0ee9b87e1cff |  | note | Reference - Section 204.10 (b)
label | ec3730a7-01bf-5755-960f-3f4e1b23bcd2 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | 9cce999f-8537-54a9-abae-acf605fbd48f |  | note | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | 81c14dc5-6a68-5f22-ade4-cbc5723ca03f |  | note | No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
label | 24ce2e68-0372-52f6-add6-ee4eb9d97e6c |  | note | Reference: Subgrade Preparation Lot Number:
label | 72e592d4-a744-5a52-b960-ce3f7dbd89ba |  | note | Method - Visual Inspection
label | b2f64a05-cffb-5566-aa65-28e05d141005 |  | note | Frequency - Prior to commencement of fill works
label | 66dcfc49-21e5-5b0b-9a45-8c84d9cdfe58 |  | note | Category - HP
date | 13565228-a81e-5942-8c99-5229585c694d |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out
label | 30c10061-aff5-5bc9-aa94-796e7d07b33f |  | note | Reference - Design Drawings
label | d7969291-daf8-5361-8143-e74dd381be04 |  | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | 3d48b9e5-abde-5723-941a-f5e4c9059610 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | 5258f66f-c674-5ad9-9712-5886318e988e |  | note | Method - Visual Inspection
label | fde88d89-17aa-5f75-a538-1e641c33e93f |  | note | Frequency - Each lot prior to commencement
label | 38ebe156-645a-5099-9e5c-f3ae8675baac |  | note | Category - HP*
label | e2c3ab2d-6b12-5b78-b5ff-8d02acdef3d9 |  | note | Responsibility - PE
label | 1334341a-5529-5ccd-9c25-b9a7fbfaf32f |  | note | Verifying Documents - Signed ITP, Lot Map
date | 816184eb-104c-568e-a94d-de06a313982e |  | date | Date Completed:
checkpoint-group |  |  | section | 5 - Type A Fill/Verge Activities
checkpoint-status |  |  | checkpoint | 5.1 - Placing of Fill
label | 10a30941-797a-5736-b71f-1d174ef825e3 |  | note | Reference - Section 204.10
label | 46a51074-c20d-517d-a240-16d0b558d981 |  | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | 24482d9d-703f-54e2-a8b8-6ae7925ac326 |  | note | Method - Visual
label | 9c54fdcc-ea3d-55ba-b52f-4835b17783d5 |  | note | Frequency - Each Lot
label | 7f36413a-813c-521b-b651-2c103157bf9e |  | note | Category - WP
label | ddf80980-2c39-5800-9501-c8dd434433d3 |  | note | Responsibility - SE/Site Supervisor
label | 4f873408-d309-5ff5-998c-542e364fd02b |  | note | Verifying Documents - Sign ITP
date | 8c36b90c-0958-598d-a959-7e727f65e2be |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Test Roll
label | f4a061de-a12b-5084-8de9-640029279965 |  | note | Reference - Section 173.03
label | 6eccbb57-8df9-5a8e-8c4a-555d3e5987c8 |  | note | Section 204.12
label | fbe291ce-3e8c-5377-b11f-08143e04a3a5 |  | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | 3599d283-f2fa-5c96-b4e5-c23465d3e320 |  | note | Method - Test Roll as per 173.03
label | 6c992841-fee6-51b2-a3a1-32051004a40f |  | note | Frequency - Each Lot/Layer
label | 4edbbf9b-4847-569d-81a9-d9abebd8b03d |  | note | Category - HP
label | 400b3a64-12e9-5cbe-97ac-db2f2b596b27 |  | note | Responsibility - SE/Nominated Authority
label | 34e5ad96-641b-55d8-a8a2-24376cc9bb90 |  | note | Verifying Documents - Sign ITP
date | 5cbd3f60-fad9-5892-b980-c82082334a76 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Compaction Testing
label | b8b3c8d7-33a3-58d3-a561-3e1930458ead |  | note | Reference - Table 204.131
label | a1dbf03b-67cd-5e63-882c-6939e036cee2 |  | note | Section 204.14 c)
label | ef6c5d7e-8572-5283-a992-28f525bcefc8 |  | note | Table 204.142
label | e34d5ef2-1a8c-53e4-9578-d8ed9e73838a |  | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
label | e295bf20-dffe-5b11-87eb-278ad1f8b7ed |  | note | • Standard Compactive Effort
label | b12f097d-95e1-5bf8-a832-916d5ca5c44c |  | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
label | 425d90db-9612-5760-b6bd-f7b2abe0aeec |  | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | 2389cf5d-6466-526b-a6fd-0ec28abd17ea |  | note | • Compaction and Moisture content
label | ca29e7d1-606e-5b6e-a706-34843002790f |  | note | – Scale A: Characteristic Density Ratio 99%.
label | 63acc9df-b7b7-53ce-ae4b-0950afec8641 |  | note | – Scale B: Characteristic Density Ratio 98%.
label | 777c8f29-d538-5aff-94f4-75a846a360e0 |  | note | – Scale C: Mean Value of Density Ratio: 100%
label | caf2e321-d739-5cf9-a38f-59305f497b8b |  | note | • Lot size - the leser of one day's production or 5,000sqm
label | 34ef067b-3014-5764-a326-41fb4eae33a0 |  | note | ATTACH: COMPACTION TEST RESULTS
label | a720b536-e8fb-58ff-af18-e2db5f08069f |  | note | Method - Review Document
label | 2fb8878a-b625-5104-b78d-2b0da93eb7c3 |  | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | 2d8e7252-3e96-5b79-a7c9-cecffb02c606 |  | note | Category - IP
label | dce3259c-fb0b-5538-bf83-c4df9ac3673f |  | note | Responsibility - SE/Site Supervisor
label | 553ac4b0-36df-50e9-82c7-104e7128387d |  | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
date | a1d675cc-fc87-505f-aae6-a37cc84b600d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Preparation of final surface
label | 6d01447b-a809-5b49-9af2-7f6e86402e30 |  | note | Reference - Section 204.15, 204.03 (g)
label | e767c8a5-0078-5476-bb7b-7926409953e6 |  | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | 41f83b44-5488-5334-8481-d901ed8e7365 |  | note | Method - Measure
label | 69367945-9730-5217-96a0-204370fffeb4 |  | note | Frequency - Top layer
label | db8a951c-0e5e-5c3d-a387-76451ab7a69e |  | note | Category - IP
label | d8b8e5e6-d4fc-5027-a81b-ea5961c07630 |  | note | Verifying Documents - Signed ITP
date | edee2230-6168-54e2-be86-64039f426ab2 |  | date | Date Completed:
checkpoint-group |  |  | section | 6 - Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Post Compaction Material Property Testing
label | bb0d89d1-f72f-56fa-bb92-16a96eac3fab |  | note | Reference - Table 204,041
label | 4ba0990d-0700-5429-9530-e31d7f1c83b4 |  | note | Table 204.141
label | 3d09453b-17b7-5880-9aea-b7ead27cdeb6 |  | note | Section 204.14 a) or b)
label | 3495ea21-f51b-5520-8229-c695eb0982fc |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | 8b9c3047-19e0-5b46-8ad6-2e964479af81 |  | note | ○ CBR ≥ 3% and Swell ≤ 1.5%
label | 96daf3d7-a326-5738-8f56-e418b3ce3827 |  | note | ○ Max Permeability = 5X10-9 m/s
label | feb7e7a9-1c92-55d0-8223-39ca9ba5898c |  | note | ○ Grading:
label | 5fa340e4-ff15-5779-bf7f-383eee7cdac8 |  | note | – 75.0mm 100%
label | 9ab3deef-722e-5a2e-b455-8dcce7e3df30 |  | note | – 4.75mm 40-80%
label | 829356d0-435b-5216-b154-d6d62db69c1a |  | note | – 0.075mm 10-40%
label | f7ee26ef-22c3-535d-8a5d-7804c59aeab6 |  | note | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 9f738045-ba9a-5e24-b806-69cedc1a0f19 |  | note
label | 25504062-fe8a-5690-a0eb-38547679aea4 |  | note | • Scale A:
label | 2a177682-bfe9-5906-aa46-ccc53e5a4f9c |  | note | ○ CBR & Swell
label | b4c410a0-a85e-5091-8bac-6d98f55272b5 |  | note | – Initial - 1 Lot Test to determine Assigned CBR and swell
label | a1173ecc-851a-57da-9381-0effdde57a1d |  | note | – Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | 8c3d11e2-6b56-528d-b00c-fc2e871d9f72 |  | note | ○ Max Permeability
label | 74c505de-bbc7-5273-b506-62746af86cec |  | note | – Initial - 1 test per 2 lots
label | d6c83e8a-ac42-54c0-80c1-2b7b81a2fcba |  | note | – Reduced - 1 test per 4 lots
label | 6d9cd051-887d-5067-bbc0-fd96db1ce0e4 |  | note | ○ Grading:
label | 46f33495-9e1a-5fac-9f82-073e283b5521 |  | note | – Initial - 1 test for each lot tested for compaction
label | 79608768-053c-5bfd-8049-cde5900b9910 |  | note | – Reduced - 1 test for every second lot tested for compaction
label | 5f3929d6-dad3-57d1-95d2-95f1894678c7 |  | note | ○ Max. PI x%Passing 0.425mm & PI
label | 1ab1c814-37fb-5d08-9f92-33705982d8a5 |  | note | – Initial - 1 test per 2 lots
label | 193ee824-1799-5758-b303-4f7723f48ed7 |  | note | – Reduced - 1 test per 4 lots
label | 098bac24-c5cd-5bc1-bf48-e1d25ee4703b |  | note
label | d7279bfc-b393-5cfa-ab42-7160757a8942 |  | note | • Scale B:
label | 86a07eef-1877-51e5-ab87-608df36ad50e |  | note | ○ 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 28b3d773-0acf-5f5e-92ba-1178e00303ea |  | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 30484dac-ef41-54df-be37-b2d52f2989ab |  | note | Attach: Post compaction test results:
label | af3528b8-d553-5b59-a0ed-04d6698192db |  | note | Method - Review Document
label | 5bc2f759-b240-56f4-9729-ffdcaf912423 |  | note | Frequency - Refer to Section 204
label | e8c7de5d-064f-53b5-9497-c5bd5514f29e |  | note | Category - IP
label | 17d676e5-45e6-5a7b-9ada-7246e5724141 |  | note | Responsibility - SE/Site Supervisor
label | 4f155af7-dd4b-5401-a95e-7421be4560a8 |  | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
date | 6743d660-3b85-5d91-af3e-205f6367606e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Survey Conformance
label | bf50e102-c79b-5e43-9ead-a105c4c57979 |  | note | Reference - VicRoads 204.03f,g and h
label | 9dce3e4e-1270-54de-96fb-348b5c43dd79 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ae38df25-897c-5211-84ed-8f3f20faff9e |  | note | • Level tolerances Scale A:
label | cf950a01-4114-522d-b232-659392494930 |  | note | ○ Range x = +5, -15mm
label | ec92f603-63c1-5ad7-9c6b-aa1cce517b56 |  | note | ○ Max S = 12 mm
label | 6fb0b1b3-94df-56de-a37d-d50af6c924a7 |  | note | ○ 80 measurements per lot
label | 4ca8d217-17f9-5e23-b2ea-567ab48749ad |  | note
label | 58863008-f389-5761-b88c-f2aec5e8f9e5 |  | note | • Level tolerances Scale B:
label | da1a054e-c73a-5ca2-8952-d14a9f08a5fc |  | note | ○ Range x = +5, -25mm
label | 4a7fe63b-8db2-5fc8-835f-f7176415f404 |  | note | ○ Max S = 15 mm
label | 82f1e0b9-2d72-58b6-a143-c6cd3a2671d1 |  | note | ○ 40 measurements per lot
label | d8d3dcc7-5eab-52f7-8ccb-bc4fa9f60eb3 |  | note
label | 836d5878-3366-5c1c-ae12-9e6aa995e2d5 |  | note | • Level tolerances Scale C:
label | eeb0db66-f235-5c61-a58f-01840c674f38 |  | note | ○ Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | f2420367-fc5d-5b83-8e4f-2025c87d0a56 |  | note | Method - Document Review
label | 1f514e32-32b8-5d3d-8186-64697b9ac3cd |  | note | Frequency - Top of Type A/Verge
label | 6a070776-b4e1-5a61-aa58-a915991d99ab |  | note | Category - IP
label | bb4f1859-acdd-56c6-be07-92c49dae9332 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 2ea5f4a4-9b1c-5598-9135-f0ba09b51584 |  | note | Verifying Documents - This ITP, Survey Conformance Report
date | efa91caf-46e3-52e4-814a-eb557dff8193 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | c799b033-002b-5446-8331-dbdd44ff462c |  | note | Reference - MRPA Quality Management Plan
label | 214394a3-4310-5345-904f-e4b3d5355fae |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 39144b33-71e6-5f50-bd53-1ac47fd79396 |  | note | Method - Document Review
label | 17aa7abb-f4ef-58d5-aba4-81c2f9e26f39 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | fa4f174e-e0a2-5337-8ed1-0fbe8c28359c |  | note | Category - HP*
label | 94fc5723-8787-5651-b0c4-0276d3d06a31 |  | note | Responsibility - SE/PE/SPE
label | 6f4190b7-97fc-592c-a29d-84b3c3218bf0 |  | note | Verifying Documents - This ITP
date | 54372667-9ea5-58d7-9f6e-46de2b7e2a23 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | feaf9877-5850-5df2-9d17-a0caf19f37e9 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | e930627d-27ef-5029-8a23-ede9b15893fe |  | textbox | Print Name:
text | eb09d6b2-026f-5443-8fb6-736bd2eff34e |  | textbox | Position:
date | 6e09ce7e-6aae-50ec-adbf-8cd2313eb441 |  | date | Date:
checklist-sectioned |  |  | checklist | ITP-008-CIV-Stormwater Drainage Supply & Installation | itp |  |  |  | Yes | ITP-008-CIV-Stormwater Drainage Supply & Installation Rev 0 | f0057fe0-c8e4-484c-80e0-9ef7aa4b232d
checkpoint-group |  |  | section | 1.0 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | e2751394-2957-525f-b752-cd15f3e93bee |  | note | Document Title: ITP-008-CIV-Stormwater Drainage Supply & Installation
label | 5019af8e-450e-5050-9bb2-cd6c42de5ef5 |  | note | ITP Description: Stormwater Drainage Supply & Installation
label | 172f3998-4372-53a2-a02b-2e90fa989d1a |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 046a2a61-0ee1-5330-b5bc-65f69d82c49a |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 4ad1f441-8313-5241-86b4-5bb4474713fe |  | note | Revision Number: 0
label | 384b60d7-b146-5da2-a856-88c9d9ef3c3a |  | note | Revision Date: [Date of approval]
label | 73c335ba-638e-5b45-9ac4-d99100aa5118 |  | note | ITP created by: Jon De Castro
label | 296996d7-91fd-5df7-a787-2d4629431844 |  | note | ITP approved for use by: Aldrin Guinchoma
label | 91595832-721e-5119-ae8a-d28c10ba08e0 |  | note | 1.1 - Non Dependent
label | b146aa0c-1173-5045-83e4-36d2901ee8da |  | note | Reference Documents: VicRoads Section 701 (May 2020)
label | 94bac89d-2576-5a14-96b6-f196f0de95c9 |  | note | Acceptance Criteria: N/A
label | e4ed74af-684a-51cf-908b-0deb33078edd |  | note | Method: N/A
label | 9a027dd9-91ba-5d2b-b96d-009adf96567e |  | note | Frequency: N/A
label | 340d6721-def1-50a3-abb4-c51cc399fb1d |  | note | Category: N/A
label | 449581df-0a10-5d08-953c-7e3c70046e44 |  | note | Verifying Documents: N/A
label | 4bc2b308-8c13-533a-bc48-602f09c8f6a9 |  | note | 1.2 - Non Dependent
label | 64360c7e-b6cb-58f2-83cc-41a1562d95aa |  | note | Reference Documents: VicRoads Section 705 (June 2021)
label | 257f28e8-437f-5aea-a9bb-ed5a7b97e8a1 |  | note | 1.3 - Non Dependent
label | 51272973-df6c-5283-8e84-e03d6fe6e451 |  | note | Reference Documents: IFC Drawings
label | 861f54ae-12f4-5da0-bdfb-516cef8f6498 |  | note | 1.4 - Non Dependent
label | b9d149de-1927-5fdd-8c27-d40776fdabaa |  | note | Reference Documents: CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
label | 1396c4ce-335b-5b9b-ae1c-e665b2e91b77 |  | note | 1.5 - Non Dependent
label | b2fff9aa-850f-53bd-add0-e0d44437e8e9 |  | note | Reference Documents: CHK-002-CIV-Stormwater Drainage Pits Installation Rev 0
checkpoint-group |  |  | section | 2.0 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Drainage Reinforced Concrete Pipes (RCP)
label | 72dd290f-837f-55cc-bf3b-c55c6792532b |  | note | REFERENCE:
label | b40fed04-6b40-5613-8d60-834bac321bb1 |  | note | • Section 701.04
label | 98e98bdd-a9a6-5be8-8ccd-274a17ff2996 |  | note | • Section 701.05
label | 344ff1da-7654-5c00-bb93-6d2216a891d6 |  | note | • Section 701.09
label | 11c9af9a-5e28-578e-905c-56b2abc3e07a |  | note | ---------------------------------
label | 2b0c7c20-764a-562a-940b-fc7ace7496fe |  | note | ACCEPTANCE CRITERIA:
label | a40b56c2-df35-5041-83a3-13a3c183ac80 |  | note | • Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and Sections 701.05 & 701.09
label | 6aee0c3f-7898-5bf8-ad4b-cdb07916bbd0 |  | note | • Precast reinforced concrete box culverts shall comply with the requirements of Section 701.04
label | cda608e8-9a71-5970-a53f-084af8a5ad31 |  | note | • Rubber ring joints shall comply with the requirements of AS 1646
text | dc6fb512-378b-56a9-9222-8257568a81a1 |  | textbox | Enter: Teambinder Material Approval number
label | 8e9ca2b8-be43-5b28-a718-d10196777443 |  | note | ---------------------------------
label | 1fae7860-71c3-55bb-ad05-26274ff95d79 |  | note | METHOD: Document Review
label | 36d6ee04-2dc6-56d7-a667-2a1384d214cd |  | note | ---------------------------------
label | e9ef7a52-186d-513b-b0dc-bd2ec1e5163c |  | note | FREQUENCY: Each lot
label | 247263c0-6668-5b0d-9172-54f76c6c6edd |  | note | ---------------------------------
label | a1c990ac-0d23-5d4d-abe3-3da3063fb6c1 |  | note | CATEGORY: HP
label | f8f2e736-2e91-5c4c-96dc-8e96e1f32801 |  | note | ---------------------------------
label | 39700d8d-a5cd-5848-b825-1dacb76a395c |  | note | RESPONSIBILITY: Nominated Authority
label | 9f51a136-3f27-5f83-8258-406f04c4b7d0 |  | note | ---------------------------------
label | 68c7eee8-569d-5236-ba91-6a0e43aa5fa8 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 50bdf263-5863-55fc-a4bd-957d81ba3c17 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Drainage Flexible Pipes
label | 74632b10-4d0d-55b2-b026-a145b877657a |  | note | REFERENCE: Section 701.08
label | a7fc5cf8-dbe3-58a4-b6e4-471090697a38 |  | note | ---------------------------------
label | adf9f13d-323a-5212-94a1-aafd73f6fceb |  | note | ACCEPTANCE CRITERIA:
label | 543e0cfa-287b-5ea7-9b32-27c73e0753a5 |  | note | • Flexible pipes shall be supplied in accordance with 701.08
text | 17bc7a1c-0736-5058-a6bf-1f1f0742943f |  | textbox | Enter: Teambinder Material Approval number
label | 817618f7-1658-52b0-bfe1-c9aa134839ac |  | note | ---------------------------------
label | 837d8eaf-5751-5a78-817a-7c21618a16dc |  | note | METHOD: Document Review
label | b6e796b2-9a7a-57b1-9138-5d1bbb4ca446 |  | note | ---------------------------------
label | e77996f8-d4b1-5cc1-802d-0292c343e87d |  | note | FREQUENCY: Each lot
label | 35c33040-a2f6-56c1-b2e0-4cea343d982f |  | note | ---------------------------------
label | 639c70b9-886f-58dd-ade9-e449c110d2d6 |  | note | CATEGORY: HP
label | 98c15e25-c9c9-54c4-b803-a1172126e4e8 |  | note | ---------------------------------
label | de577255-0edd-506a-8684-9075564b54ca |  | note | RESPONSIBILITY: Nominated Authority
label | 49b7d6aa-8bca-5302-aea3-aed2dd02e2fd |  | note | ---------------------------------
label | ff81cd81-14d0-5ba0-b3aa-b499ee63244f |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 5b40e90c-cbde-5e08-8cef-d1bf8e7198c7 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Precast Drainage Pit
label | 3fa0aa0f-3654-53b1-95e7-e835c3b9d8a9 |  | note | REFERENCE:
label | 25440711-896e-5641-8139-236b4990e065 |  | note | • Section 705.07
label | 7fa67d8f-a1b0-57fc-9c0b-ab13bcb7cc46 |  | note | • Section 705.04
label | fbb2fd70-a471-57a9-8309-49288930bfcd |  | note | • Section 705.09
label | 7913efe1-067a-5eb8-b434-c2cce846b0c6 |  | note | ---------------------------------
label | d0c7518e-795a-5b6b-97e6-83068391d03d |  | note | ACCEPTANCE CRITERIA:
label | cbedd37f-4f0b-5baf-b0a1-421932cb0e03 |  | note | • Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
label | 5aac7492-a3be-5911-bf7b-c6a1905831b4 |  | note | • All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
text | ec7b98e7-ccd9-5762-980b-4fa79177fb8f |  | textbox | Enter: Teambinder Material Approval number
label | ee4e8ff5-348a-5019-863b-8b683ef540a8 |  | note | ---------------------------------
label | aa19b129-af88-56dc-96e9-fa75c13f0330 |  | note | METHOD: Document Review
label | 7b82fcba-f576-541b-bd63-9f0cba858232 |  | note | ---------------------------------
label | b6375994-d9e1-5f5e-9836-4dbec8764120 |  | note | FREQUENCY: Each lot
label | fc1a170a-c961-540e-884a-315bc1a380dc |  | note | ---------------------------------
label | ae5a3819-e6e8-526c-884c-39bba251a6ac |  | note | CATEGORY: HP
label | 60189a5a-7b63-5d01-83a9-6122b149ece5 |  | note | ---------------------------------
label | 2d028e7d-af87-5a9f-82cd-f51f2dd5ced0 |  | note | RESPONSIBILITY: Nominated Authority
label | ec465bf5-5e4b-557c-830e-c7d3570135c9 |  | note | ---------------------------------
label | 90b1a268-19bd-5742-a620-60ba29befa23 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 5696ace7-acea-5890-a748-f8bb814833ac |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Cast in Place Drainage Pit
label | 90301796-48c9-5307-93dd-0b2c24e1e5a6 |  | note | REFERENCE:
label | d32dde1f-0bef-5c14-9594-bdefb5005b12 |  | note | • Section 705.06
label | 9f6b36d2-b3a8-58cf-b6d1-caa407526fa1 |  | note | • IFC Drawings
label | 29239391-3d09-53e3-94d6-2342bd1b2e8c |  | note | ---------------------------------
label | 179ca199-6f23-528d-87ee-4b169f58d298 |  | note | ACCEPTANCE CRITERIA:
label | 3a261e5a-ee13-5c83-94a7-216b436379ee |  | note | • Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | eb05070e-f6e1-5fdf-b6aa-692852f8efe6 |  | note | ---------------------------------
label | a3eeb1b6-98f4-5601-b509-8c7e7804a9cd |  | note | METHOD: Document Review
label | 2447fd27-2168-5814-9cd8-ec071f9ef28f |  | note | ---------------------------------
label | 55cfbef8-31f1-5cdd-b047-86e60e3c9a24 |  | note | FREQUENCY: Each lot
label | 3d84a244-333f-53c0-85b9-78cbce98aef1 |  | note | ---------------------------------
label | 578ae35d-16a7-5397-96a2-a5a2851f0a96 |  | note | CATEGORY: HP
label | 1c40ba4d-db0f-57e4-8b31-be58ea1caa65 |  | note | ---------------------------------
label | 6c24d75a-3e53-55ff-84ea-3dbac70469bf |  | note | RESPONSIBILITY: Nominated Authority
label | cb6b5aac-5409-5417-a934-811072fc1add |  | note | ---------------------------------
label | 8b68dbf4-5ebc-56d1-928a-c2162e0beb01 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 633abd7e-78ec-5cc8-b0d4-16eaf6397ed0 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Drainage Pit - Step Irons
label | 686f6058-be99-52db-8238-1e8179e6a39f |  | note | REFERENCE:
label | 4d856409-8bd6-5b83-ad2f-7d6c4e727559 |  | note | • Section 705.04
label | e8af6840-5858-58ee-92c1-8f064a9e1d93 |  | note | • Section 705.12
label | 93584fc6-7d99-58e4-bddb-dc2433650371 |  | note | ---------------------------------
label | 91d990cb-12f1-57e6-b300-69633f42166c |  | note | ACCEPTANCE CRITERIA:
label | aaedf0ec-4477-51a1-a3c3-27089038ec6c |  | note | • Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | 0ee6b4b8-6c20-59fb-ae6b-b016d11f4f08 |  | note | • Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
text | 00a03e3f-a75e-5ea8-958e-43d53d005200 |  | textbox | Enter: Teambinder Material Approval number
label | 75db50e3-a3df-50f6-8910-2bf5f23c241a |  | note | ---------------------------------
label | 3d91385f-1a44-5b19-b521-46b45340fa9f |  | note | METHOD: Document Review
label | 557bbb07-c9e8-572c-8e3b-7afaf630d9ee |  | note | ---------------------------------
label | f85923aa-ce1b-5b4f-9407-4402b4faa1fc |  | note | FREQUENCY: Each lot
label | f491e346-ba19-5481-87d2-9eb2c0bb1485 |  | note | ---------------------------------
label | f7422b37-791a-53d0-94eb-d935e5df7c50 |  | note | CATEGORY: HP
label | 5cc66eb4-216f-5b93-a323-fce1d4b8963f |  | note | ---------------------------------
label | 2209f915-d607-54b3-88be-8278724c2ff3 |  | note | RESPONSIBILITY: Nominated Authority
label | 9cc290ca-c270-5b8c-8663-bec5347d0d15 |  | note | ---------------------------------
label | c49db9df-28ba-5e0d-82de-a9f22ea0c5ab |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 817b6f0a-ce4c-5671-bc7a-a6e5bbdd8726 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 Drainage Bedding Material
label | 3b556434-e477-54d2-b1d1-7a88179818ea |  | note | REFERENCE: Section 701.09
label | b27a2c85-1d4e-5562-b15a-9d3389539b62 |  | note | ---------------------------------
label | d0f8924f-168d-5319-97ca-deb72c0c9de3 |  | note | ACCEPTANCE CRITERIA:
label | 17e61d0e-3e91-5c9f-a7b9-3e474eee8e06 |  | note | • Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | 0e5360ca-5dee-5a18-983f-1fc8d0ccff95 |  | textbox | Enter: Teambinder Material Approval number
label | 042933ba-2af5-57ae-8a55-b79ac51e0957 |  | note | ---------------------------------
label | e167d2b7-c37d-54cb-abe2-fd8bb7e96d45 |  | note | METHOD: Document Review
label | a1fad11f-1f34-5c4c-9a00-3492e0c597b4 |  | note | ---------------------------------
label | abb01105-0742-5c45-95c2-ac3cd7f43faa |  | note | FREQUENCY: Each lot
label | 655ab0e2-88d1-5b32-b272-dabf46a9a8f2 |  | note | ---------------------------------
label | b35d3f3d-56c2-5d8c-9451-f86a8d519371 |  | note | CATEGORY: HP
label | 080f1303-d61c-5d59-a97a-94882ef424a0 |  | note | ---------------------------------
label | c7f1f432-852b-5f95-9918-9ab8f8fd6a36 |  | note | RESPONSIBILITY: Nominated Authority
label | 88775c85-8a25-58ea-a97c-5d630e270aa2 |  | note | ---------------------------------
label | 663edf75-9bff-5b25-8bde-436300070a1f |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 92178d96-9d01-58a9-9b1e-9d78e761c0c6 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 Drainage Backfill Material
label | 2a3108e2-1b4d-5820-b7eb-c2996d1cca43 |  | note | REFERENCE:
label | fc3c85be-c6e3-5c84-ad09-7b980b7d4183 |  | note | • Section 701.09
label | 24e1d0f2-425f-5830-9ac7-e6547d64381c |  | note | • Section 701.19
label | 27265410-0ba9-5cda-9875-7095aa411b4c |  | note | ---------------------------------
label | f60e378b-03d0-5f53-b414-f86cab31f286 |  | note | ACCEPTANCE CRITERIA:
label | 2d8de61c-ae75-5f07-9171-aa922e19bdf0 |  | note | • Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | 455b3605-80b4-59e2-a444-1690737d651f |  | note | • Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
text | c5861fd6-e5eb-5d4d-854d-22e695fb7ed7 |  | textbox | Enter: Teambinder Material Approval number
label | 4a392498-198c-5889-9123-66992ad5b393 |  | note | ---------------------------------
label | e8919ef5-e9f6-533d-80b6-689169bdb7fc |  | note | METHOD: Document Review
label | cd265166-e4f9-538e-af3c-a22790cd8765 |  | note | ---------------------------------
label | 8c75de63-a7db-59ee-b6af-90b7cb014034 |  | note | FREQUENCY: Each lot
label | 81c79b49-dacd-5c81-a2e5-2c359424fa50 |  | note | ---------------------------------
label | 84872e85-7a9d-5586-b9aa-9033abd780e7 |  | note | CATEGORY: HP
label | 2acbaa76-7c19-5093-b234-e1cd3fa72639 |  | note | ---------------------------------
label | ca8bf2e0-3536-5fb8-abd1-22545ce216a2 |  | note | RESPONSIBILITY: Nominated Authority
label | b35beef5-a3ac-58b2-ad7e-d1f4e55ea944 |  | note | ---------------------------------
label | 4cc41ffc-2bee-572b-a742-6aeebb04e585 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 67e17d2f-a210-5871-bffe-13a1a9e1884e |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 - Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 Subcontractor ITP (where required)
label | 4911583c-93fb-50b5-90bc-8fb7134adfc7 |  | note | REFERENCE: Subcontractor ITP
label | b27a6cf9-e4d0-5eca-89eb-62cfd02ca5b7 |  | note | ---------------------------------
label | 947402dd-909a-544b-9006-f19d712ccba8 |  | note | ACCEPTANCE CRITERIA: Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
label | 7fd5184f-d403-54a1-bf39-62ef944cbdb5 |  | note | ---------------------------------
label | 61c2ace9-9865-527b-a9a1-48ab3ec95fc1 |  | note | METHOD: Document Review
label | d5d7fcd2-4259-5d1a-830d-2347f5cc2f6a |  | note | ---------------------------------
label | 529b37b6-c0d5-5e32-911b-a21eaf550ff8 |  | note | FREQUENCY: Each Lot
label | ce562711-8d44-58c8-87b8-b9bdc481ff36 |  | note | ---------------------------------
label | e2d703cc-9d58-5284-a17c-77dd05dd377f |  | note | CATEGORY: HP*
label | a5fb7c65-4553-5b66-8ae5-ec498bd0b5cd |  | note | ---------------------------------
label | c3af47a3-5832-5b02-96d9-65a66d8279be |  | note | RESPONSIBILITY: PE
label | b422fd10-14f2-58ed-a579-d90c0f8fbad4 |  | note | ---------------------------------
label | d4df0739-d035-5cba-b797-034b9f5cbd24 |  | note | VERIFYING DOCUMENTS: Subcontractor ITP
date | 9c14985f-bb42-5b07-a893-5772e3b29b43 |  | date | Date Completed:
checkpoint-group |  |  | section | 4.0 - Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set Out - Pits & Pipes
label | f5ba4c92-cc56-54f1-93cd-82da408a1099 |  | note | REFERENCE:
label | d012c4a9-46ad-567c-9376-62731d8a86b7 |  | note | • IFC Drawings
label | 7196cbdd-aeee-5b1f-8d4b-2ab9f7c49ec3 |  | note | • Section 701.10
label | fa558275-abca-52fd-80b4-b8cd7e1bbbf8 |  | note | ---------------------------------
label | 1ca25bbe-f672-5b46-a588-020f6cf83c95 |  | note | ACCEPTANCE CRITERIA:
label | d11320fd-309c-5134-a390-3aa3c0350691 |  | note | • Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | ad8abb4f-53cf-534e-8cf3-ef8ef160b6cb |  | note | • Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | e9a8a5a9-8020-5be6-9a37-211601238514 |  | note | ---------------------------------
label | 1b31f3d2-7587-5b30-aa7d-b2f0b8dced6d |  | note | METHOD: Survey
label | cc658ed6-675a-5790-aabd-003421d47e5d |  | note | ---------------------------------
label | 1178068a-96f7-53a8-a9ae-93b90d4c80f7 |  | note | FREQUENCY: Each Lot
label | 880ed773-b9a8-5779-a571-f084df55c4c5 |  | note | ---------------------------------
label | 11d65277-f8e5-5097-b39d-98d3c5708271 |  | note | CATEGORY: HP*
label | 6d620ee5-0d15-5a80-8aa3-a8affd9bfeee |  | note | ---------------------------------
label | 8293ff39-44e1-58e6-a454-5028fc97ccf5 |  | note | RESPONSIBILITY: PE
label | a6d5aeec-bc8b-5323-ae46-3279c5532d30 |  | note | ---------------------------------
label | fbccf4c4-0d12-56b5-91b3-cd0a75e016d9 |  | note | VERIFYING DOCUMENTS:
label | 7b9bec99-d0d0-5727-8d10-c7b39e7f7dd0 |  | note | • CHK-001-CIV-Stormwater Drainage Pipes Installation
label | 999708a8-e016-55f2-890b-75999ded1f21 |  | note | • CHK-002-CIV-Stormwater Drainage Pits Installation
date | 666545f8-f8ba-5137-880c-aff036702ebb |  | date | Date Completed:
checkpoint-group |  |  | section | 5.0 - Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Pits - Excavation
label | d9090fdd-20ad-574e-8465-0fc76d6f5392 |  | note | REFERENCE:
label | b2fb1d38-ad86-57c2-a4fe-4e249c3ba8b0 |  | note | • IFC Drawings
label | ff6aab59-1004-507d-b41c-c92389eca0c8 |  | note | • Section 705.05
label | 07357c1a-ad93-57a1-bcff-53b39d7449af |  | note | ---------------------------------
label | 6a9ad102-9a8b-5ef0-85fc-72194a727375 |  | note | ACCEPTANCE CRITERIA:
label | 9723be50-9eb1-5960-89c7-e4d9303ce6e8 |  | note | • Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | 3fd052ce-8ab8-5acd-935d-61bb562d313c |  | note | ---------------------------------
label | 6bcb8219-be37-5ec4-8596-22d502197a5f |  | note | METHOD:
label | ed5836a0-3b4d-57ea-9928-65fda8bd97e7 |  | note | • Visual inspection
label | f778cf7b-43c3-55cc-8c6d-5050fa41ea0b |  | note | • Measure
label | 54c3e994-a8c3-5121-8ad4-0bae986d1312 |  | note | ---------------------------------
label | 6117072c-8781-5de9-a09c-90055cae3de7 |  | note | FREQUENCY: Each Lot
label | 6ab9f6c1-74cc-5859-a285-90784ccdc5e4 |  | note | ---------------------------------
label | 9df2089c-fe42-5439-911a-96de66dcaadd |  | note | CATEGORY: IP
label | 99ebbc6d-5b9a-5bdb-aad6-64b137d629c5 |  | note | ---------------------------------
label | c47408f1-aa41-5ed9-b9e4-fc8a772b29c4 |  | note | RESPONSIBILITY: SE
label | 17840d3f-8e91-5c48-8a40-caf49203d41c |  | note | ---------------------------------
label | 9d6156fa-5482-54d7-a75c-08faa1c3b2ea |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 21ce4176-f476-5cb7-b3b4-8786edc6890a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pits - Placement of Bedding Material
label | 31c53472-11b3-5ea8-90d0-9b6295344c08 |  | note | REFERENCE:
label | d1f4ed0a-390a-5d64-8fff-f32bdd169efc |  | note | • IFC Drawings
label | 8251bb28-f753-5518-a071-24aa07b84189 |  | note | • Section 705.05
label | 4088c04b-2a32-5f61-8494-4940f767c0b4 |  | note | ---------------------------------
label | 0c93b7d2-5155-5e6d-bb96-a7b406cbe4a2 |  | note | ACCEPTANCE CRITERIA:
label | cfbbc8ec-f843-5872-b19e-ee905ebb832a |  | note | • Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | 7a029243-e41e-5bc5-b5ee-2ac20b5c2aa3 |  | note | > 80mm for clay foundations
label | 64946dcb-f321-501b-8940-fe690480fb3b |  | note | > 150mm for rock foundations
label | 1347c019-6ded-56b7-bdda-346edd321bb9 |  | note | ---------------------------------
label | acf5346a-8895-5d77-9a26-e9b8a53decb2 |  | note | METHOD:
label | 783c6881-47e2-546f-99b4-d634d11512fa |  | note | • Visual inspection
label | 45dc97f8-fc22-54cf-a93e-fb63f5968537 |  | note | • Measure
label | c0e3c5ba-247f-5c41-8eef-06312b5a8056 |  | note | ---------------------------------
label | e244410e-73e7-554a-8e3d-304bc94691fe |  | note | FREQUENCY: Each Lot
label | bbefca17-2c8c-56ca-a1c6-d5ec0f120bca |  | note | ---------------------------------
label | afdcaee1-a6b2-5b3b-83c7-9892b89538c8 |  | note | CATEGORY: IP
label | 9105a25f-7422-549c-9f3c-6e7899512131 |  | note | ---------------------------------
label | 0a7356e2-7656-5b31-8d08-0582297fe0cd |  | note | RESPONSIBILITY: SE
label | c9bf96c4-eccc-58fc-9402-f1d721830cdc |  | note | ---------------------------------
label | 8eac134a-b2f9-5f68-942e-bf6edc4db7ea |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 0cb20ae2-0cbd-5c45-8651-aab785e419ab |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Pits - Bedding Testting
label | 58015304-b47a-5dcb-8e63-1b5366b71454 |  | note | REFERENCE:
label | fbb39d7b-166a-5429-9ba6-e3794056d6fa |  | note | • IFC Drawings
label | 98e08fab-5ef6-5e13-8efc-405449648e42 |  | note | • Section 701.20
label | c869aed3-abb5-534e-b11b-a37b84e91434 |  | note | ---------------------------------
label | ecc32a69-4377-5963-908e-c1d2d66609ee |  | note | ACCEPTANCE CRITERIA:
label | d71a11cf-2663-55c1-9466-4f3436604f19 |  | note | • Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | 04f1304b-0429-5c02-a464-9b94114bac8c |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 3d011ec3-b5c5-5d60-960b-f353bc090509 |  | note | ---------------------------------
label | 67472862-948d-59d6-9ae3-893190402d83 |  | note | METHOD: Compaction Test
label | df4b8302-29aa-5d8f-9fc7-4d668b975e4b |  | note | ---------------------------------
label | 6b90db13-b6a2-5f68-b7a5-4f74326cb37f |  | note | FREQUENCY: Each Lot
label | cdaf2f4a-01fd-50cd-ac8d-e4f025a8bd54 |  | note | ---------------------------------
label | 48f92296-0c1a-5f58-8c74-25d7b3ebff21 |  | note | CATEGORY: IP
label | 01636edf-4548-5d1c-a7c9-479b3b299495 |  | note | ---------------------------------
label | 36c42651-5d48-5a30-87b7-f43235165080 |  | note | RESPONSIBILITY: SE
label | 62ab82be-7424-5077-b7ce-3cdb53682e9c |  | note | ---------------------------------
label | bc13b31b-3670-57f4-b551-d406f28e5f2a |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 4334dded-8720-5ca5-99d1-fcab46763d81 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Pits - Placement of Precast Drainage Pit
label | fc8fc2d2-523a-50d6-bd8d-24cc8985752e |  | note | REFERENCE:
label | 6a4bcd2e-35f6-5e24-b510-32a48b630a8c |  | note | • IFC Drawings
label | a2bc7f20-2bbe-5d13-b0c5-09248044e7a0 |  | note | • Section 701.10
label | 4fd3f9ae-f79a-50b6-a149-c8be2d0c2ac8 |  | note | ---------------------------------
label | abe61a0e-57fd-5d0f-9c44-4bc2bb6b958f |  | note | ACCEPTANCE CRITERIA:
label | 1ee6d1a9-d3cb-5cff-bb83-695222db36cf |  | note | Survey pick-up to verify:
label | 93c14a19-a150-5749-9a13-357eb6769bb0 |  | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | f25cae3b-fb64-5643-9fd6-da22e4fafb31 |  | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | c4ce9071-fd21-58e2-bc5d-498600b96446 |  | note | ---------------------------------
label | 08ec9d15-d893-5ef2-a073-52191af6d8c5 |  | note | METHOD:
label | f5f9d7b6-d086-5965-bf5d-29862501fc7f |  | note | • Visual inspection
label | f57bbef0-a546-58a5-a633-fedd60ebf00a |  | note | • Measure
label | e1f7ec90-d422-5a20-8c36-6868f8356c46 |  | note | ---------------------------------
label | 55be9116-7b3a-53f1-868b-523c03354ccd |  | note | FREQUENCY: Each Lot
label | 8192d9f8-1159-5b8d-a6eb-6e3e3c4ecf0f |  | note | ---------------------------------
label | 2c1cec38-fd99-5bc9-980a-1a49b6cf11f9 |  | note | CATEGORY: IP
label | 12ae1edf-90b2-5558-b420-7199426444d0 |  | note | ---------------------------------
label | 7367cf72-0c0e-5bde-9cc9-0efd8cb1360e |  | note | RESPONSIBILITY: SE
label | b54cac99-1c84-51ba-a74a-f0cd1e3883f3 |  | note | ---------------------------------
label | b25a37a9-ea3e-5f78-97dc-a4aa964fc6f1 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 88643f05-573b-5120-b5cf-b6717c9425e8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Pits - Cast in Place Drainage Pit
label | 6a41d046-af65-5037-8980-e1d220046d61 |  | note | REFERENCE:
label | 480f1597-f5e5-572e-9506-938acafddbf8 |  | note | • IFC Drawings
label | 78b5d320-b9b7-5d27-924f-8e8251040c13 |  | note | • Section 705.06
label | 443d4c39-096b-512b-9a77-57ebddcd702d |  | note | • Section 610
label | 74b91421-f758-532c-970c-d2cc10ef2d53 |  | note | • Section 611
label | 1cbbf914-680c-5824-af60-ced3bd7c8b93 |  | note | ---------------------------------
label | 50b697c0-d19a-5729-b33f-4c9bb71c879a |  | note | ACCEPTANCE CRITERIA:
label | 6d2e4778-e3b9-50dc-bba3-a62361723dac |  | note | • Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
label | 138b769d-13e1-5533-90f7-b1f61a97b9a6 |  | note | • Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | 850e07cf-4722-5568-86d1-27f2b67b5229 |  | note | ---------------------------------
label | ac2da850-40c9-5f26-af2e-35e300fb11d9 |  | note | METHOD:
label | aa2b47f2-88f5-532c-94f2-0714686a63fd |  | note | • Survey
label | 2a7cfc41-3d6e-59ec-a527-bead44b3f325 |  | note | • Measure
label | 19f81144-3789-576c-8d65-c05e51268bba |  | note | ---------------------------------
label | f6786af2-8cd2-59ae-aa68-f6c2e11d5011 |  | note | FREQUENCY: Each Lot
label | 5f9d7abd-2cec-5cd1-8e34-1d8877bdfb52 |  | note | ---------------------------------
label | 241381ae-c821-5989-8644-3a5e65096baa |  | note | CATEGORY: IP
label | 8e8aa289-4a2a-5f07-8504-139d01468310 |  | note | ---------------------------------
label | 8d879b05-c46f-5380-bf4e-a9db394761e9 |  | note | RESPONSIBILITY: SE
label | 913053a1-49f8-52b0-9926-b2bd8294e017 |  | note | ---------------------------------
label | 73233301-a44d-56a8-b1f8-bd99be4f1d7d |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | f7a6aad5-4a6b-50ae-8575-698f9ec04125 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Pits - Jointing & Drainage Connections
label | 37a20f1c-dd86-5a5f-8dbc-955d58b44456 |  | note | REFERENCE: Section 705.11
label | 8ac5cde8-8fad-586f-9a13-c872aa78c138 |  | note | ---------------------------------
label | 27a806fa-e7ea-5301-a3c9-c77d2a03669d |  | note | ACCEPTANCE CRITERIA:
label | 737b3cde-62f9-5761-bf7f-80814adeca7c |  | note | • All connections to drainage pits shall be neatly made in accordance with Section 705.11.
label | 182a0ade-2c04-59d3-86c1-392008fd953e |  | note | • Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | 1bc08f59-49ed-5ff9-871d-f2b2e6ee8f5b |  | note | • Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | a83a08ed-a1a5-5974-884a-b2c728ab428e |  | note | • Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | ff05fe47-c5e9-5fc8-9854-8725f04a3d9d |  | note | ---------------------------------
label | 519bd56b-5f17-560a-b7da-f508f6cf04fd |  | note | METHOD:
label | 509664a4-ae43-55b1-a57a-261e9a97afdc |  | note | • Visual inspection
label | 81113ca8-2859-5e49-b107-b0deab2f891a |  | note | • Measure
label | 367c97fe-3c21-5e9f-ba4c-cec7674d17b0 |  | note | ---------------------------------
label | a120acf8-587b-5396-9d04-9b7a0f42ea24 |  | note | FREQUENCY: Each Lot
label | be2d93c1-ce9c-56c4-8b28-cca8e101eb95 |  | note | ---------------------------------
label | 0c664acb-adb7-5b7e-85f2-e62921d77b7c |  | note | CATEGORY: IP
label | c5658ad7-1cb9-52f7-9243-df29ac789a36 |  | note | ---------------------------------
label | 5429ee84-215f-58b9-8284-96ca994e66b3 |  | note | RESPONSIBILITY: SE
label | 390611d0-7862-5d03-ada4-f8f608a03421 |  | note | ---------------------------------
label | 1ef9014c-87d4-5e9c-90f0-e180fef5e6be |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | fb493ab1-a11f-5bcc-be4a-6c59d5888421 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pits - Shaping of Floor
label | 2d260c04-8767-53a7-b1ef-f8e02cbe78e1 |  | note | REFERENCE: Section 705.13
label | 492b4301-d3b1-590c-922a-76f713b00d25 |  | note | ---------------------------------
label | f50f0028-0120-5203-8910-0c4b2395c670 |  | note | ACCEPTANCE CRITERIA:
label | 3d73c0b9-4cef-5771-84f4-bc2a09f49fb2 |  | note | • Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | 6e0a229f-bf35-5be8-bd8d-ec02c7b7967a |  | note | ---------------------------------
label | 8493535f-9e12-5a70-b2b8-8043aaa9f7b7 |  | note | METHOD:
label | 117a3e63-4fc1-5b23-b312-d36205c27915 |  | note | • Visual inspection
label | 3c591d15-90a7-5e30-b143-e60edcc45a1e |  | note | • Measure
label | 2e2520e5-16bc-5f50-a8a3-e51c426b9c71 |  | note | ---------------------------------
label | d410eecc-49a1-5c40-8472-649ed2b02173 |  | note | FREQUENCY: Each Lot
label | 0381907f-b328-59a3-b289-4b8ae428475a |  | note | ---------------------------------
label | b14e852e-4df1-5b86-85bd-4217b6bda365 |  | note | CATEGORY: IP
label | dafebe31-2ed9-543d-bc38-7743bf581d17 |  | note | ---------------------------------
label | c8553e28-168f-5cb8-b365-98ecd2591065 |  | note | RESPONSIBILITY: SE
label | 122ec5c8-4882-5ce8-b51f-584187a6f567 |  | note | ---------------------------------
label | 7eb7c4ec-f1ed-58e3-bc7d-16c18841dc65 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 1c778f64-a650-51af-bebd-0142fbab4275 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pits - Step Irons
label | 6eccb508-780e-5415-9e3d-cc70915ef4d9 |  | note | REFERENCE:
label | 68980c60-1036-518e-9dd6-795ee4e782c5 |  | note | • IFC Drawings
label | a1659860-abd7-5238-a38c-4902ef8b6bf1 |  | note | • Section 705.12
label | eed30823-6e84-55b2-9ea5-b9010ed1c62b |  | note | ---------------------------------
label | 0241ae25-cd02-5144-8134-9921b1172310 |  | note | ACCEPTANCE CRITERIA:
label | 2a2014d0-bec8-5300-94b4-e48ea40d247b |  | note | • Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | b65f2e42-5a58-5aa4-87fc-865936f7d0eb |  | note | • Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | b558c6fc-fe9c-5a7a-b07c-986617df6e65 |  | note | ---------------------------------
label | 0110630d-54b2-5394-a126-9878236fd338 |  | note | METHOD:
label | f052a075-0598-53d2-b2b3-5481f636c2c0 |  | note | • Visual inspection
label | 695f4266-2cd4-5204-82b0-ee1438525598 |  | note | • Measure
label | 6deba9e0-af83-58db-86c8-cd93af2e944d |  | note | ---------------------------------
label | 362b5101-5022-5604-9b84-2288858c376a |  | note | FREQUENCY: Each Lot
label | 7945e76e-8122-5224-9ad0-a8b5d16cd2f3 |  | note | ---------------------------------
label | 84a5ed44-3046-5cd7-b6aa-bbc8575354db |  | note | CATEGORY: IP
label | 22532fd9-60f2-5602-9b4b-9b25e291542e |  | note | ---------------------------------
label | fdd309df-22a4-5e2a-98ae-64bc7f9f55e3 |  | note | RESPONSIBILITY: SE
label | ab8398d0-9064-57c9-9b04-63a2e9597abe |  | note | ---------------------------------
label | c123437c-027d-5cde-ad91-6b1cdbd2055f |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | f5d5a723-4b4e-51cb-bbae-8b8d60de49e0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Pits - Fitting of Covers
label | be80c5b3-d487-56e9-896a-3c933721141b |  | note | REFERENCE:
label | 4fbea3a6-ab89-54a0-9601-d8ca75f18992 |  | note | • IFC Drawings
label | 4c11ada6-8eff-548e-a557-36fd9f4f09c0 |  | note | • Section 705.17
label | 91b9d085-2092-5d2f-9a1d-32bd54b21d3c |  | note | ---------------------------------
label | 613caead-f73d-5c43-9b50-c09753dfdd31 |  | note | ACCEPTANCE CRITERIA:
label | 08a3f876-d840-58fb-8c99-6ec4ecb97de4 |  | note | • Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
label | 1b19124d-3855-5eae-b733-afcc5434dce8 |  | note | • Height shall be within 10mm of the design level.
label | 319dac53-38ba-5592-90f1-67fd8167bb48 |  | note | ---------------------------------
label | b68971a4-fc65-5986-a69a-77a1ea51ecb4 |  | note | METHOD:
label | 71770c54-5b1f-5739-a4a0-10416de0cd0f |  | note | • Visual inspection
label | 1340edc4-88bd-550b-86cc-cb64ded3807c |  | note | • Measure
label | 592bd8fa-db20-5acf-a5b2-f6ea7473330d |  | note | ---------------------------------
label | 4a53ff84-6fa1-5bc9-bd70-dc3d607a2f0f |  | note | FREQUENCY: Each Lot
label | 14cc3f04-7a89-5143-920a-768d140beb68 |  | note | ---------------------------------
label | 7add3bc7-b614-5a27-ac14-01b8b38db6d8 |  | note | CATEGORY: IP
label | b5f71305-7962-5361-8803-338561dbb1ca |  | note | ---------------------------------
label | b680088d-0d87-57ae-8ba9-cf2b889f9504 |  | note | RESPONSIBILITY: SE
label | aa2a6998-cc74-5996-9dad-c49e5f867e7c |  | note | ---------------------------------
label | a18fb9aa-56ac-592c-8d8f-c75099d7f8b0 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | ab95933e-5bd4-5d15-8913-baac5207662a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Pits - Pit Lids
label | 4dd1d453-ec93-5971-877a-44c6af8e5a78 |  | note | REFERENCE: IFC Drawings
label | 87a5342d-db56-51d8-a441-19f5e97cc454 |  | note | ---------------------------------
label | 654cb06e-1493-54db-b8ec-1e9f2e5b7989 |  | note | ACCEPTANCE CRITERIA:
label | 0a879cab-526d-5b90-aaa3-1bacf9e0b0f1 |  | note | • All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | 5a21187c-98c4-500f-9615-5384b3ad6037 |  | note | ---------------------------------
label | 1dd6817d-a12d-508a-8ef3-229af0f7520e |  | note | METHOD: Visual inspection
label | fd14c551-cefc-5cbc-bcc2-d51e8ee58010 |  | note | ---------------------------------
label | a5cc1c9d-9b86-5050-9e54-fa673f8903a4 |  | note | FREQUENCY: Each Lot
label | 755bf258-ce9e-58ab-9e62-b9ca4aa31a8e |  | note | ---------------------------------
label | fd0f5f9c-17da-518e-8f75-e95a134e593b |  | note | CATEGORY: IP
label | 42fb48f4-f66d-5395-844a-695be8f9c3a2 |  | note | ---------------------------------
label | 969bf20c-0ab3-53e9-926e-203fbc5a5225 |  | note | RESPONSIBILITY: SE
label | d06b5b78-0645-5bea-9e36-70aad86cd62f |  | note | ---------------------------------
label | 4617416c-9e4c-5700-b6aa-eaae7c7aa193 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | bb75bcc6-f642-5501-b0dd-82c0e2475289 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Pits - Backfilling Around Drainage Pits
label | 986238ec-3c01-56bd-a658-83d9783949d9 |  | note | REFERENCE: Section 705.18
label | 04a3a570-b95d-54ea-84b2-0622a5053c12 |  | note | ---------------------------------
label | bea3de94-671a-55e1-afec-4861fafc04b2 |  | note | ACCEPTANCE CRITERIA:
label | be70134b-3223-5cac-84d2-b32b615e63e2 |  | note | • Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | 5c37d3a9-30b3-509e-9b58-1eecc138e4ef |  | note | ---------------------------------
label | 8afcc5c0-7338-5a01-bd9b-34b2cd500513 |  | note | METHOD:
label | 3560df30-5b49-51e6-9e70-eb93e36545cd |  | note | • Visual inspection
label | 069c82e4-15f1-5aef-a1ae-165edc02fe7e |  | note | • Measure
label | 6522f5b5-d725-5dd0-a3e5-47c7dd1fa637 |  | note | ---------------------------------
label | 28a96f30-e268-5bb4-b89f-cad5f02f0639 |  | note | FREQUENCY: Each Lot
label | d6382286-6468-5749-a961-a9d368406880 |  | note | ---------------------------------
label | 54319fb6-fdfb-5ae9-8d5c-ad2957857760 |  | note | CATEGORY: IP
label | f2ac6cab-2280-5ad6-b8d6-44f9edb95bd9 |  | note | ---------------------------------
label | 83fc22a4-8103-52af-a95d-3812650e5cd8 |  | note | RESPONSIBILITY: SE
label | f08696c9-c1d0-55bb-8d53-f9d514d19430 |  | note | ---------------------------------
label | f6ec18a8-4a1c-5774-9908-2075269dbedc |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | c4458eb9-7501-55dc-a2aa-7bb34b6a98de |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Pipes - Trench Excavation
label | 825fa705-9050-5597-90f3-00bff881b062 |  | note | REFERENCE:
label | d4bd3fdc-9c96-5e41-952c-8a4308b6022a |  | note | • IFC Drawings
label | ee0781f5-ae46-5154-8436-547d71761da2 |  | note | • Section 701.15
label | 3a9f162b-651a-599b-91b8-579ff1e4d2b3 |  | note | ---------------------------------
label | 957645c1-33c5-55f9-bb5e-e54646c2e816 |  | note | ACCEPTANCE CRITERIA:
label | ad9ed1c8-00bf-55b7-9285-a37b2d45d6e2 |  | note | • Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | bff779d2-7e46-5201-98b5-3c0e856b7493 |  | note | > 300mm, < 600mm for RCP
label | ee3b641b-51a4-52fd-9a3a-957981544cb0 |  | note | > 150mm for Flexible Pipe
label | cbf9b86a-e15b-539c-9d91-19f43511cfc9 |  | note | • The base of the trench shall be compacted to refusal using mechanical plant.
label | 5aaac2b6-0838-5c9a-b39a-d7bc67b4fa59 |  | note | ---------------------------------
label | 793e46bd-339f-515d-813d-e40e3973c6db |  | note | METHOD:
label | 1904dd1e-dd79-540b-b04a-5f2e18cbaeae |  | note | • Visual inspection
label | 564f4027-936c-5d11-b082-7da0e56b2710 |  | note | • Measure
label | 59c30003-b4e9-5713-ab4d-2ca8c5a18d1e |  | note | ---------------------------------
label | 81b37202-ef81-5903-932d-050692d4b07c |  | note | FREQUENCY: Each Lot
label | c5955e7e-6d4e-51ac-907b-311690f285f7 |  | note | ---------------------------------
label | 51ec9f0e-d9f7-5b1c-96c8-a23bd3d9353f |  | note | CATEGORY: IP
label | 98840b93-f8ac-5dbb-aa05-42c52980d17b |  | note | ---------------------------------
label | fee2bc0b-b5f0-55f8-9433-ef788f4a2905 |  | note | RESPONSIBILITY: SE
label | e775e3c8-8267-57fb-89e3-44e0e267ffdd |  | note | ---------------------------------
label | e99cdd42-60c9-54ce-8379-f73c5e77fb52 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | d2e65ada-36a5-5218-9138-144a7841eda1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Pipes - Bedding Placement
label | 0e0be699-77d5-51cd-b098-b4006e835eea |  | note | REFERENCE:
label | 72c6c51f-edea-5fe2-8ea9-2b4ca856cf96 |  | note | • IFC Drawings
label | ca0e2abf-3808-5fd1-ab7a-fe69ea7f3241 |  | note | • Section 701.16
label | a146065c-4e9f-55e7-a57b-1086b66294db |  | note | ---------------------------------
label | 69d8c09e-f4d6-5ec1-8423-28e32b7870e0 |  | note | ACCEPTANCE CRITERIA:
label | 5ff1818c-d783-5de6-90c3-54d9f7625d93 |  | note | • Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | 3c9dbd09-5166-52a3-96d1-a89830d5dd9c |  | note | > 100mm where D<1500mm
label | 3a9c3b3f-cc53-5910-a616-24ca18a5e0ec |  | note | > 200mmwhwere D≥1500mm
label | 7c45ac09-17f1-5956-a14c-098093c254e1 |  | note | • Bedding material shall be placed and compacted in layers <150mm loose thickness
label | d16b5bcc-527e-573f-8521-3db97e74d166 |  | note | ---------------------------------
label | 5295f10d-38d5-572c-bad4-c6df53d3f0ce |  | note | METHOD:
label | 4a94a0a7-c2e7-533d-aaa2-d5da8c48983e |  | note | • Visual inspection
label | cca4141c-b4ec-5113-9d9e-c4b99012d50f |  | note | • Measure
label | 711a8490-4e76-57ee-b643-93ab2b893013 |  | note | ---------------------------------
label | b36c776d-29d2-5769-9b7a-7d2c5a88459e |  | note | FREQUENCY: Each Lot
label | 32166b85-6859-5ebf-b1f2-9aa61f9e4394 |  | note | ---------------------------------
label | 24807a68-53df-5c55-8306-78ba40a324c0 |  | note | CATEGORY: IP
label | 871f6f7e-43da-554a-b2da-17291b8747c6 |  | note | ---------------------------------
label | 43832779-2508-5636-97de-a7e598d09cde |  | note | RESPONSIBILITY: SE
label | ffc57698-048b-5416-a0d3-6e96858125e5 |  | note | ---------------------------------
label | 72f9ff23-3b72-5fdf-9dd3-174f16386f5c |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | a4166f13-4e68-5005-864d-72497c2fc716 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Pipes - Bedding Testting
label | 10928101-2b30-58eb-85da-765c8bbc8739 |  | note | REFERENCE:
label | 2f443549-74df-5c9c-bba6-02a07c6b914d |  | note | • IFC Drawings
label | f573bc6d-c43c-5410-b91f-8b4747d223dd |  | note | • Section 701.20
label | 3202c20d-dac3-5665-93c6-5dcf687938f6 |  | note | ---------------------------------
label | 086b3155-879b-585a-b32a-4d3956fb669c |  | note | ACCEPTANCE CRITERIA:
label | da3eef78-54ff-55c1-ae10-e4ee962efa5f |  | note | • Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | 9f8e1bdc-218b-51bc-b85e-c120eda2ba28 |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 9c38abd8-cdfc-5d35-9f50-ad09bfc5dcc9 |  | note | ---------------------------------
label | bfa2395a-2287-5b47-820a-a038b7993855 |  | note | METHOD: Compaction Test
label | d7c418e7-cad5-57ab-ba35-366e78876c07 |  | note | ---------------------------------
label | 69083f0e-bd45-56ab-836b-506223a45fc1 |  | note | FREQUENCY: Each Lot
label | 48d2bae0-2573-5a68-8caf-c811ffa365bb |  | note | ---------------------------------
label | 61cf5c86-0d4e-5108-b5e4-82cacae831c4 |  | note | CATEGORY: IP
label | 7eca22e3-6fa2-5fce-9933-d788ad68d868 |  | note | ---------------------------------
label | 32c91886-0bc4-5dc1-9116-60b3ead6ac43 |  | note | RESPONSIBILITY: SE
label | 9c08ceb1-9e48-535c-9673-384f8a85451f |  | note | ---------------------------------
label | 5d714ec2-7bb1-5976-b1d7-b9ddb1c0f466 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | 53ee4a78-b292-54a0-8153-0d7bfa3997b6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Pipes - Placement of Pipe - RCP
label | 19709c44-cdfb-5188-a888-1dfbd79a68b2 |  | note | REFERENCE:
label | b3b553f8-050c-5470-9e6d-d6b080cc9e6a |  | note | • IFC Drawings
label | 22f1ec40-5e9c-512b-80bb-f26d7d7c70fe |  | note | • Section 701.17
label | f8f253b0-ca33-56c2-89bf-6305a02d25fd |  | note | • Section 701.20
label | bd43a944-9f03-520b-9f3f-e1818aaf4420 |  | note | ---------------------------------
label | 886035bd-c738-5f10-a9d0-bf844a297e1b |  | note | ACCEPTANCE CRITERIA:
label | 9af674da-62e0-5ce0-ae5f-5de161b4fa97 |  | note | • Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
label | 4d803245-12b4-5014-bcd0-0ec29bad596c |  | note | • Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
label | f0bacef0-3561-58a5-af6f-56c1e9788281 |  | note | • Gaps between spigot and socket are in accordance with the manufacturers specifications
label | 09cb1ffd-bfae-5e31-8520-4969fd6bae43 |  | note | • The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
label | 97d08a9e-28f9-5ba2-9ea4-4639e51417f8 |  | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | 9ad18ded-9158-5e8d-b812-bb48537bea21 |  | note | • The spacing for multiple row culverts shall be as shown in Table 701.171
label | 381caf37-ea10-5bc2-bd97-3c03e4d59d52 |  | note | ---------------------------------
label | 861dd98c-b807-5951-995c-a2c8c9f2f845 |  | note | METHOD:
label | 1ecbb728-4e3f-5664-b030-12aaafb9e5c5 |  | note | • Visual inspection
label | 6612264c-f04b-5d62-a109-dcc7b77fe1ff |  | note | • Measure
label | a959c07a-113d-545d-b099-b6d0eb8469b4 |  | note | ---------------------------------
label | 41d418d5-0fb0-51c8-9afe-5ac647e22fe4 |  | note | FREQUENCY: Each Lot
label | 840f1982-aef1-5dd2-883f-23bf1ec20f37 |  | note | ---------------------------------
label | 29a0049b-34b3-5dce-bdb8-e393cdba97da |  | note | CATEGORY: IP
label | 860c7906-fafd-5390-bd2e-b7eba2b91b4a |  | note | ---------------------------------
label | d522d516-1de6-5635-97e7-eadf637ad1ec |  | note | RESPONSIBILITY: SE
label | c2ecdb98-c201-55dc-a5b5-467a38e83019 |  | note | ---------------------------------
label | 7c27adff-2795-5210-8a39-01c3aa397326 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | cf0982bd-7481-5281-a6f9-69caad78c82b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Pipes-Placement of Pipe - Flexible Pipe
label | 77939416-4402-53a3-becd-ba4ecc8e93b7 |  | note | REFERENCE:
label | 04103d7b-a54d-5592-960b-d1c5decae299 |  | note | • IFC Drawings
label | 7fb3f3f1-25f2-59fe-9fd7-7c08eab0d898 |  | note | • Section 701.17
label | 597ed688-69da-5264-9587-97df2ef58c59 |  | note | • Section 701.22
label | 06b84d03-90b0-5010-87f6-cc0ac5fddd33 |  | note | ---------------------------------
label | 8eabb116-80c9-5e5e-8f80-4aed960691e9 |  | note | ACCEPTANCE CRITERIA:
label | 3c404933-5c7c-5493-aec4-32da6371936b |  | note | • All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
label | 9e484397-69e6-5d18-91a7-732d782f5d3b |  | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | 1d046eda-fc8a-5182-bbbf-4afe2aa71cc9 |  | note | ---------------------------------
label | ec14303d-a5b9-59c5-8f48-72fe2d5a19af |  | note | METHOD: Visual inspection
label | 3f2059e2-f365-5645-bc1b-103338ec7c1e |  | note | ---------------------------------
label | 3d4176d2-0c4e-5b4e-a6b8-fa0fc0243ad8 |  | note | FREQUENCY: Each Lot
label | 8f8b967d-61ef-5b5a-9292-cf24fd2e46dc |  | note | ---------------------------------
label | 9a1cd252-a89b-52f6-a7dd-1fb3e0b8a6b4 |  | note | CATEGORY: IP
label | 1d14b302-1c79-5ec7-b2de-8cfcb0637987 |  | note | ---------------------------------
label | b0b376ab-71bf-5c75-9f4b-b51c6c4669ee |  | note | RESPONSIBILITY: SE
label | b07c028c-3e61-5b9b-8055-392f29180170 |  | note | ---------------------------------
label | f4a44e7d-7519-5955-a9e3-0239a622b5e6 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | 03454355-e625-5b36-b33e-8816a794df53 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Pipes - Lifting Holes
label | 611d0660-de20-50d2-ae78-b822da73ce00 |  | note | REFERENCE: Section 701.18
label | 969fff30-944b-50c7-bcc5-051634db6b25 |  | note | ---------------------------------
label | 8f263795-2065-55e8-95e5-f3ca37cf44d2 |  | note | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | 0c312676-f16d-5c77-b861-f262ba0ea108 |  | note | ---------------------------------
label | 98ae1f3a-a2a9-58c2-be5d-784b04dc6956 |  | note | METHOD: Visual inspection
label | 7ba8658b-39e5-59fb-a3d4-09c779e4c59a |  | note | ---------------------------------
label | ac2cd612-bc36-50d0-9522-2d23e77a34bb |  | note | FREQUENCY: Each Lot
label | 6a129a82-09ec-5b67-b592-9f19c9aecd81 |  | note | ---------------------------------
label | 7f86853d-6d30-56ab-a2a3-97bb7026ae8a |  | note | CATEGORY: IP
label | 60ea5dd9-6a50-5b49-abea-d48927eaf3be |  | note | ---------------------------------
label | 15b0c0d5-8ae8-5fd7-9106-fc8a3f688c71 |  | note | RESPONSIBILITY: SE
label | 8565fd07-818c-5b50-a98e-23fdde7e8861 |  | note | ---------------------------------
label | 382cc0b0-faef-5976-90ee-b27fdc400f25 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | 9dde3ebb-fad0-5b87-9efb-c1831e352566 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Pipes - As-built survey pick-up
label | 4d21a00b-d197-57e6-83af-30a90739bf99 |  | note | REFERENCE:
label | 2d859a68-4f2f-5bf6-8992-dce7db89637e |  | note | • IFC Drawings
label | 06aa52e4-7963-51e1-9e2f-826ea249569f |  | note | • Section 710.10
label | 114b541a-957e-5bde-b253-2b7ba4f20c30 |  | note | ---------------------------------
label | d827eff9-19bc-56fd-b988-dae7e0b456cd |  | note | ACCEPTANCE CRITERIA:
label | 3c047fbd-2d7d-551c-a3e9-75cff5946c81 |  | note | Each run of underground drainage shall be Survey verified prior to backfilling.
label | eb5d4b84-d1a5-516f-b017-751d40159317 |  | note | – Offset pits to kerb +/- 20mm
label | b6d46f49-d242-5618-ab5f-a96026b3e07a |  | note | – Plan location pits not adjacent to kerb +/- 100mm
label | 18082fc2-f894-5222-beb0-1afb8adbfc23 |  | note | – Invert level of pipes at pits +/- 50mm
label | 820b3135-c5a2-5357-b5a6-536093bf4496 |  | note | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
label | c3d5dd27-8dee-5ed8-b1ea-dee55224f815 |  | note | ---------------------------------
label | 902fb734-612f-5a16-b193-9e7f739931b5 |  | note | METHOD: Survey
label | 12aa7995-8f31-53f0-b163-ed5120ccbf46 |  | note | ---------------------------------
label | 3c01f23f-7286-52a6-92c6-c7686eda215b |  | note | FREQUENCY: Each Lot
label | 24018108-1211-56de-9907-75f252a86fb4 |  | note | ---------------------------------
label | 9ed231c4-c6e1-54f4-bc3d-bdaf51a45884 |  | note | CATEGORY: IP
label | 94d2e69f-cd2d-5e08-bb5a-5c175b8f256e |  | note | ---------------------------------
label | 4c4f73b1-b56f-5696-9bc0-ff44a26bfd76 |  | note | RESPONSIBILITY: SE
label | ab4e5d2d-96dd-57a0-82c5-d532dbc0e596 |  | note | ---------------------------------
label | 316e3e3e-1001-5dab-893d-bbc35dd9d140 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | b73df8bf-eac6-5560-ad0e-64e8512699a5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 Pipes - Backfill Placement
label | 7a2cc00b-b1cc-527f-8d22-03f4125ae6bb |  | note | REFERENCE:
label | 5d657d4f-23ea-5397-8786-155ed1be4ca3 |  | note | • IFC Drawings
label | 015b0c3e-9397-5093-b8ec-412fba0058df |  | note | • Section 701.16
label | fdb9f601-c31d-502d-9be1-731a68557708 |  | note | ---------------------------------
label | 80a4900f-5f17-569a-beee-fe943ba08d83 |  | note | ACCEPTANCE CRITERIA:
label | 5c9a683e-9e14-517a-86d7-3ee0399cc06d |  | note | • Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | 4183f836-400b-5d9c-b08c-dfa4fb1e4b33 |  | note | • Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
label | 3a4dd02a-1c26-5a1f-a92b-4ba8070d37db |  | note | ---------------------------------
label | 4ebc29ec-2c70-557c-9edb-1f78fb6d160f |  | note | METHOD:
label | 5f554034-a70b-5ad2-8ae7-54bdb95a7d56 |  | note | • Visual inspection
label | 11aea135-448d-5db9-a24e-c39640f8671e |  | note | • Measure
label | 5702d10e-bfec-5800-8171-45db2f39e28a |  | note | ---------------------------------
label | 15d7540a-1c98-594a-b1c7-74bfdf7213dd |  | note | FREQUENCY: Each Lot
label | a842ae5c-b054-5a31-bfd6-7773570de5fe |  | note | ---------------------------------
label | f1b9b065-0790-56a6-884e-5e2ad8ef0c46 |  | note | CATEGORY: IP
label | 8740f231-fbbc-572c-9e31-54e10cbcc747 |  | note | ---------------------------------
label | 1068f614-ec91-5189-bf31-959ef937b6c4 |  | note | RESPONSIBILITY: SE
label | 6a16cf15-54c5-5d8e-8deb-6c6bfb3e90fb |  | note | ---------------------------------
label | 9009af6a-5d29-55ba-b9b1-18b6fc1ba44e |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | 424a8e3e-d74c-5fe0-b02e-a2f2fa5dfa7c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 Pipes - Backfill Testing
label | c0f57d05-a90a-5f42-a4fd-2035b0359677 |  | note | REFERENCE:
label | 240d1e6f-201e-588a-acfc-277091fc902b |  | note | • IFC Drawings
label | b10f906d-b651-5575-9448-14128cf0174d |  | note | • Section 701.20
label | 5d09bbfe-add9-5d6e-a9ec-ea56fc676d59 |  | note | • Section 701.29
label | 0184bf96-4aba-5da0-a7d3-4c5e35090006 |  | note | ---------------------------------
label | aec7f6aa-0c24-5ddf-9bb4-3d975182baa8 |  | note | ACCEPTANCE CRITERIA:
label | 13d82307-84f9-5a53-b699-aae4cbf04399 |  | note | • Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | ae0bd65a-ec8d-53e4-ba2b-13477e8a55f5 |  | note | • Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | c03a32fb-3d27-54aa-8d93-af3ce64e2690 |  | note | ---------------------------------
label | 0b1b66a2-4864-524c-aad6-f57088886010 |  | note | METHOD: Visual inspection
label | b11c62e5-c555-5efb-a73a-0f926777c508 |  | note | ---------------------------------
label | 9370d6e8-dd47-55ad-8c07-6903160e46f8 |  | note | FREQUENCY: Each Lot
label | 56843ccb-f3a8-5fba-9d8c-786b9a54a59b |  | note | ---------------------------------
label | 1ee078f2-134f-5422-8773-3ba878e7d9f5 |  | note | CATEGORY: HP*
label | 2974e8f9-54fe-5ef7-af35-6649f8b7832d |  | note | ---------------------------------
label | 5691bf3e-3123-5615-99d4-5bbc2d344ed1 |  | note | RESPONSIBILITY: PE
label | 287fe581-0dfc-5691-8fa2-667d7253348e |  | note | ---------------------------------
label | 46711938-2ef5-5edb-aca9-50f2ccf6e0f8 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | 4dfc0104-bc2d-555e-b62b-d9cc5036b219 |  | date | Date Completed:
checkpoint-group |  |  | section | 6.0 - Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Flushing & CCTV
label | 159bcd39-4510-5d40-b35a-a73ea651ce01 |  | note | REFERENCE:
label | 85eb4301-7474-514f-9f38-62cdc9084881 |  | note | • Section 701.28
label | 199a2224-acbd-54fa-8eea-d04e18edc644 |  | note | • Section 701.30
label | 2f6f6ab6-c932-5214-a874-85efec932a96 |  | note | ---------------------------------
label | 2f08cb28-1de9-504a-9364-5f86797c454b |  | note | ACCEPTANCE CRITERIA:
label | 07d34c6d-4fce-5ae3-a415-ea0f5c5079ee |  | note | • All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | 249e3201-6888-5be5-b685-f746065fcde5 |  | note | • All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | 237b88b9-b9da-5b2a-9a80-0df04d10ac7e |  | note | ---------------------------------
label | ff9fa6ff-9e71-5852-bbb2-13739ac55962 |  | note | METHOD: Record Review
label | f389914d-4d0b-5dbe-b9b7-28e2e820ded2 |  | note | ---------------------------------
label | f8f37fab-04e8-5c74-8d53-d2495c69ba8c |  | note | FREQUENCY: Each lot
label | 8acb0aa0-3068-5a46-961d-62312e2623b2 |  | note | ---------------------------------
label | 96d0f832-eedf-5084-9ea5-59ecaccf4a98 |  | note | CATEGORY: HP
label | 62622c57-ec3a-50ab-9166-8eb0f9a5dda0 |  | note | ---------------------------------
label | 1c5b6976-8baf-53a9-9319-9c0144060b8c |  | note | RESPONSIBILITY: Nominated Authority
label | 471c5513-2d4d-523d-a58a-60449d0dc30a |  | note | ---------------------------------
label | cb4fcdf8-61ab-55d4-b90b-e7821dceee52 |  | note | VERIFYING DOCUMENTS:
label | ee8c0b8e-5930-5fed-b111-e7b8f1c60b1d |  | note | • This ITP
label | fb7f222d-f561-50da-985c-d590d3dadcb1 |  | note | • CCTV Reports
date | 89c14410-158b-57c5-96b3-aeb87f767805 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 As Built Survey
label | a1cbc581-66c4-5e05-a23f-fadbf1e2fbe4 |  | note | REFERENCE: Section 701.10
label | efc6cec3-d607-55c0-8239-0782991995d5 |  | note | ---------------------------------
label | 55262a37-0d2e-5ca6-b05a-6ff06ca4db1b |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | 02c4346b-8e00-5208-8c5c-aa1de16dcf94 |  | note | ---------------------------------
label | f52c8f8c-9c05-5b6f-8037-79b28e1395fa |  | note | METHOD: Document Review
label | de761392-0047-587c-a3f2-2fd0932bd6e8 |  | note | ---------------------------------
label | ea43d0ee-a987-511e-b271-2ea8e9fda5e8 |  | note | FREQUENCY: Each lot
label | 7fb86dcd-3dc6-559a-85a7-8631eccae803 |  | note | ---------------------------------
label | 110b14aa-3038-5595-b2f6-cd63226ff707 |  | note | CATEGORY: IP
label | fb040add-5fb9-5536-a003-c11fcc6f1eff |  | note | ---------------------------------
label | 2db84356-8873-5015-8045-cada1b970b65 |  | note | RESPONSIBILITY: SE
label | 530ddf72-8ccb-53cc-9a5c-2d8349a3229d |  | note | ---------------------------------
label | 8ae65123-89ac-5501-8dba-e2e0216c33db |  | note | VERIFYING DOCUMENTS:
label | 55a676b8-b806-5935-ab7a-a51dd5aecae2 |  | note | • This ITP
label | 96f24d11-a0b5-5d69-949f-8227c170c978 |  | note | • As Built Survey Report
date | beb9e650-b340-5765-87e5-b09d457ecc08 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Repairs to Damaged Pipes
label | 038a7a6e-a304-5ebb-b7e1-0a51274a1504 |  | note | REFERENCE: Section 701.31
label | e9432abc-0c4f-5dc7-888e-168e15b6ff6a |  | note | ---------------------------------
label | 0173f728-70ee-5417-adae-6a0aea3f32c3 |  | note | ACCEPTANCE CRITERIA:
label | 6bcc2ce3-ed44-50b2-9b6a-44701160d2fe |  | note | Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | f618e6b1-34a1-531b-b50c-aa7fba22db8f |  | note | • cracks wider than 0.5 mm
label | 9f8b5068-1ab9-531d-9bbd-f5f7c9aae961 |  | note | • spalling of concrete
label | 9edcb5ef-f6ce-538f-9b48-9d2ebfd9a07d |  | note | • exposed reinforcement
label | 8ed994c7-cbb1-547b-9090-b5d6e80a5090 |  | note | • joints that are not fully engaged.
label | 59e1e2f2-97ae-5229-966c-3ac9ae0591dd |  | note | Any pipes with defects greater than the following limits shall be removed and replaced:
label | 0870eccd-4e03-5eae-9068-938d23586755 |  | note | • longitudinal cracks greater than 2 mm
label | 83393a75-a530-5d41-8ad4-e23d14474209 |  | note | • circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | 6692fa63-5d8f-5831-8ef6-929b56682247 |  | note | • circumferential cracks around part of the circumference with width greater than 4 mm
label | 6bc4a133-19e7-5411-8afe-02503f4ee0d1 |  | note | • penetrations with area greater than 400 mm2
label | 4501d997-9869-54f5-9cb1-67f46ab400b1 |  | note | • pipe joints that are separated.
label | 0e7286d5-1869-5a58-963f-856f4e6a05e2 |  | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | a8700aec-529d-5566-b849-80f68eb57c4e |  | note | • hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | 45dee190-fa62-5295-936b-71ee9ab223ef |  | note | • fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | bc65d82f-c362-5102-8618-e6777e9b4b4e |  | note | • spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | 45da4401-85f5-50d9-b09c-7f529b639a67 |  | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | 3f40ad12-8e66-5f63-abec-60de09e76ff2 |  | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | f9000906-fcae-5aae-94a5-e783cc100ada |  | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | f1a172b5-0aa5-55c2-b18a-1d544ce7a3c8 |  | note | ---------------------------------
label | 8f9b90c1-10e6-515f-8c66-e5943ce759f0 |  | note | METHOD:
label | 228b213a-b69d-5ed9-b7e3-eab859726860 |  | note | • Document Review for Repair Procedure
label | 848a4b12-318f-5617-8fac-01dbfce80e11 |  | note | • CCTV Report Review
label | d4fa9bc6-d851-5231-801f-0425ca0325d5 |  | note | • Visual Inspection
label | 0e38733b-6976-5add-a297-022942d7130b |  | note | ---------------------------------
label | b3616051-16a7-5568-9967-7c79d6c51df6 |  | note | FREQUENCY: Each lot
label | 6fc051fe-5677-5366-bf9a-703c0e74672a |  | note | ---------------------------------
label | 19756bf2-ae3c-526e-8add-54c0ab597a45 |  | note | CATEGORY: HP
label | ffa2c7e9-7463-52b3-914c-7ac855ad642e |  | note | ---------------------------------
label | 6a195576-b829-52de-b4ee-f20cdecdd1f9 |  | note | RESPONSIBILITY: Nominated Authority
label | 6c8fec64-4055-5e2a-8abf-b4ff42accdca |  | note | ---------------------------------
label | acf23e40-f118-5f6e-9986-6167a9b0a02a |  | note | VERIFYING DOCUMENTS:
label | a1d3f3d9-d2d4-53e1-9186-d58e9d462b4a |  | note | • This ITP
label | 56482cbe-d340-5bac-8407-8e3116d7c06b |  | note | • Approved Repair Procedure
label | fe8797fd-8317-5e34-a714-0204cda238c5 |  | note | • Post Repair CCTV Report
date | 5b8a6c6b-8844-55f3-a248-cce7f23916a5 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | cfafe55a-2b51-58d8-9710-cb8dbd02c4d9 |  | note | REFERENCE: MRPA Quality Management Plan
label | fabcd401-4f32-5273-8889-f467a7a18aca |  | note | ---------------------------------
label | 9f316faa-ee12-5b8c-bbf1-0c5515759ea8 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | 4bff4195-fcec-5526-82b5-77dcadb7a1f9 |  | note | ---------------------------------
label | 0a880d20-403a-5491-80bb-26fc301dd006 |  | note | METHOD: Document Review
label | 1a195a48-0ded-5bfa-b366-89bd3b5354f1 |  | note | ---------------------------------
label | 96e014b3-dfa6-58ca-801b-59683ecf740e |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | c28bc619-9ba4-5c04-b8a3-015bf7b6358e |  | note | ---------------------------------
label | f4f54f2a-be70-5d95-ba01-d82945aabebf |  | note | CATEGORY: HP*
label | f0ece616-3252-5d28-a099-ee55ada31ce6 |  | note | ---------------------------------
label | 452185ca-1ed3-5ad7-9191-61c727168d13 |  | note | RESPONSIBILITY: PE
label | e64fc34e-d7e5-576c-b893-8d9e4276f649 |  | note | ---------------------------------
label | 40e013b2-3180-5dc4-b90d-a48292079636 |  | note | VERIFYING DOCUMENTS: This ITP
date | cb9564e8-9395-5d94-b48a-c0db0d2fc8e1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | fa8d856f-ad43-55f1-969a-6d1badd09428 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 5fcc9e4b-42d2-58eb-ba33-f3ceea67d3f0 |  | textbox | Name:
text | e6feccf9-68b6-520b-a7cd-3e7668aede9e |  | textbox | Position:
date | fe36629f-e735-5b19-8bed-95332a57a4b6 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | CHK-001-CIV-Stormwater Drainage Pipes Installation | itp |  |  |  | Yes | CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 1 | f23e8c72-1285-4052-838f-3463eb36ef27
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 6a8f1633-4b09-5c94-b40b-9ca5edd687b8 |  | note | Document Title: CHK-CIV-CAMMS-Stormwater Drainage Pipes Installation
label | 0b3a7186-b641-51db-bca8-64217c383364 |  | note | ITP Description: CAMMS-Stormwater Drainage Pipes Installation
label | 1d4561fa-0836-5b7d-ad02-50cfe06fa99b |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 164ae465-489c-5d7c-a7bd-3422fd501cbe |  | note | Revision Number: A
label | fbaaf70f-6716-5f75-968c-580cd5081831 |  | note | Revision Date: [Date of Approval]
label | 10fec5c8-9542-5a1f-9767-19751cb7911f |  | note | ITP created by: Victor Mira
label | 4e0b007b-7894-5499-9242-ab879aee2211 |  | note | ITP approved for use by: [Approval Authority]
label | f246eecc-feb9-5032-adca-04fa9534acd0 |  | note | 1.1 - Non Dependent
label | fa445180-8b36-5e55-8e2f-7edc0aeb6222 |  | note | REFERENCE: VR 701
label | a48c6c84-0cb7-5894-9224-e7ac2cd48ed8 |  | note | 1.2 - Main ITP
label | 8bc32ed1-500b-519c-a0b3-cd8fe0d3df3e |  | note | REFERENCE: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
label | 9d3f5831-b66a-5a2d-a7be-2e5a779f2d6c |  | note | ACCEPTANCE CRITERIA: This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0
text | 8dc89c47-748b-5b59-a46a-4a42794f9c41 |  | textbox | Enter: Main ITP Lot Number
checkpoint-group |  |  | section | 2 - Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Bedding
label | 112d26e8-0175-5314-a1e7-db8cfa045dc7 |  | note | REFERENCE: VR 701
label | 75aacb90-6e8f-5309-b446-6a38d42bd36e |  | note | – – – – – – – – – – – – – – – – –
label | 25b97db7-59b5-5924-9528-8df0e2daf019 |  | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
label | 492d4227-f88e-504b-ab9b-5fff3b98cc2e |  | note | ATTACH: Bedding Material Delivery Docket
label | 2ac92082-816d-5838-84ee-ed1335283457 |  | note | – – – – – – – – – – – – – – – – –
label | 02b9aa51-e443-5aa5-82c4-b0ece6d20240 |  | note | METHOD: Document Review
label | 5269e997-a8aa-59bc-af57-78ffbab9cf6c |  | note | – – – – – – – – – – – – – – – – –
label | e730dab4-bc3d-5f6d-a9b4-b017b2a892aa |  | note | FREQUENCY: Each Lot
label | fefd9f14-7787-5092-aade-ad86a34963b6 |  | note | – – – – – – – – – – – – – – – – –
label | 83a5f27f-80ff-5e34-9070-821eb28f196f |  | note | CATEGORY: HP*
label | 7e26365d-5e79-561f-9e2d-167ee3cb559f |  | note | – – – – – – – – – – – – – – – – –
label | 50ff810f-395c-5b68-b5cc-01eea969e170 |  | note | RESPONSIBILITY: SE
label | 79784687-eade-5ebf-b8e3-d6837dddce4c |  | note | – – – – – – – – – – – – – – – – –
label | 0f8510b3-ded5-5a2c-9aac-b3535b7caa48 |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
label | 3ec7fe8d-7961-568a-8331-29c39a8d950c |  | note | – – – – – – – – – – – – – – – – –
date | 1d66d0b3-509c-5d7f-b0cf-b61eec5a353f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Backfill Material
label | 56d7ec6b-61ee-59a2-9be2-9429bf66a37c |  | note | REFERENCE: VR 701
label | df5cf847-a4d3-5fb7-8423-e82133d0af55 |  | note | – – – – – – – – – – – – – – – – –
label | ff0c8b82-0fdd-59f3-9a18-aae7f01714b2 |  | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
label | 9f5a9b27-4256-5980-b382-1fcb6108741a |  | note | ATTACH: Backfill Material Delivery Docket
label | 35fc5e36-fe1f-51de-8f78-08a1bebdb780 |  | note | – – – – – – – – – – – – – – – – –
label | b9a7d378-4f4c-5d6b-be0f-478a941d5e67 |  | note | METHOD: Document Review
label | a788699a-d55a-592c-b6ad-75a16ddcba6c |  | note | – – – – – – – – – – – – – – – – –
label | d6d01014-16d2-5d4e-825e-f9261b71108f |  | note | FREQUENCY: Each Lot
label | 84c2ba7d-3463-5dc9-966a-25760aaf8220 |  | note | – – – – – – – – – – – – – – – – –
label | d9100fa7-f178-52a5-84a8-8f8d7660f01f |  | note | CATEGORY: HP*
label | 14907310-5068-5fca-8d69-b15390472813 |  | note | – – – – – – – – – – – – – – – – –
label | a662a49f-dafb-5701-9750-aa783c18308e |  | note | RESPONSIBILITY: SE
label | 05ab2f3d-5825-5afe-88fa-bb84045cb7a6 |  | note | – – – – – – – – – – – – – – – – –
label | f5b37a86-9f51-5fb3-bb94-cc23c74c398f |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
label | b71debd0-3f04-50b3-9e81-760f7ec7a8ae |  | note | – – – – – – – – – – – – – – – – –
date | 40b15b94-2f7f-556e-9d39-40c7fdf1587a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Stabilized Sand
label | 983e9905-6157-5ef7-bbde-4a7d41254935 |  | note | REFERENCE: VR 701
label | a85555ee-aa0f-590c-8f2c-53ab0fb68873 |  | note | – – – – – – – – – – – – – – – – –
label | 9224dc97-25ff-5f49-a9b4-34ea8bebe0bd |  | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
label | 076fe3d7-dfe9-5cac-a474-d1ff3f80e2d2 |  | note | ATTACH: Selected Backfill Material Delivery Docket
label | 8899fb2f-664d-5657-a485-083e93111301 |  | note | – – – – – – – – – – – – – – – – –
label | b2d73a35-f083-50c3-817d-633be81866a9 |  | note | METHOD: Document Review
label | 57d0e470-0f1d-5ae1-ad23-76c4b34171e5 |  | note | – – – – – – – – – – – – – – – – –
label | e957e8e6-b179-5c79-bdf7-bf668fe51817 |  | note | FREQUENCY: Each Lot
label | c2071fa6-368d-5beb-8b9e-e07696a45d75 |  | note | – – – – – – – – – – – – – – – – –
label | 1735e300-65ae-5406-b839-07e1c622ce4b |  | note | CATEGORY: HP*
label | 94b7d5a1-d72a-5526-915f-9a61345a6dcc |  | note | – – – – – – – – – – – – – – – – –
label | b9efd279-7fa6-5e38-a215-94727713b997 |  | note | RESPONSIBILITY: SE
label | b322ab5a-a8ea-5481-8ac7-a3838aceaf1a |  | note | – – – – – – – – – – – – – – – – –
label | 28162e12-6028-53e3-9a1c-5852e4e2ee74 |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
label | e023cc1a-a789-570c-92e6-378731e571da |  | note | – – – – – – – – – – – – – – – – –
date | 6b6f0f46-73bb-5a6f-b5af-b48181348ac9 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Subcontractor QA Submissions and ITP
label | 6282a1e9-8d72-5e96-a3a7-37fb6666f74d |  | note | REFERENCE: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
label | 61ab24f6-109f-5167-8054-10ae90af74fa |  | note | – – – – – – – – – – – – – – – – –
label | c148ebd6-21ce-5c08-bec9-cf7e5b756d38 |  | note | ACCEPTANCE CRITERIA: Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
label | 24faa741-a0c9-57c0-ab9f-7b3a27fca0f4 |  | note | ATTACH: Subcontractor Signed ITP
label | 98a1c72a-4e21-5d95-baa1-7966a8e79a37 |  | note | – – – – – – – – – – – – – – – – –
label | b9807d33-109b-52bb-8adf-736312ca57c3 |  | note | METHOD: Document Review
label | 7a11df47-e2b0-5209-a3de-617750f6c6bd |  | note | – – – – – – – – – – – – – – – – –
label | 464802ba-391b-50a0-bcd9-65ba55fd83f7 |  | note | FREQUENCY: Each Lot (in case undertaken by subcontractor)
label | 966f7ff4-618f-57af-ad5e-3c9904f43d87 |  | note | – – – – – – – – – – – – – – – – –
label | 505ef43a-ce43-5a66-994e-30e9d528919d |  | note | CATEGORY: HP*
label | ff98f790-7b18-5c9a-be14-1d29070c3dbe |  | note | – – – – – – – – – – – – – – – – –
label | 01082698-ddab-5173-8d49-26eb0897107c |  | note | RESPONSIBILITY: SE
label | 6fc64aba-f133-50b5-8760-36f07d4984b9 |  | note | – – – – – – – – – – – – – – – – –
label | 0625b969-138c-552d-bcc5-e5dcfd302769 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
label | 9b471f4b-012d-5d60-9716-002e7dd4a567 |  | note | – – – – – – – – – – – – – – – – –
date | f35a4d9d-6d48-54c8-a89f-90b3b8278926 |  | date | Date Completed:
checkpoint-group |  |  | section | 4 - Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-Out-
label | 9e1eab0d-90c2-5a47-aed3-fe3f2d3b4c35 |  | note | REFERENCE: 710.10
label | 0781fa78-5eee-5ff9-9ac2-8e6ee61915b0 |  | note | – – – – – – – – – – – – – – – – –
label | 92e8a024-0e45-51b7-97d9-5e964a48be22 |  | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | fe48275c-f106-5ba9-ad70-c0bfde5f216d |  | note | • The culverts constructed shall be constructed true to line and level.
label | fed43d41-3ae0-525f-b73e-f23220828fbd |  | note | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
label | bda96671-4eb1-5594-81ca-e33f232d968b |  | note | – – – – – – – – – – – – – – – – –
label | c1a2097f-6ca8-5e22-8d54-ae43aa9da9db |  | note | METHOD: Survey, Measure
label | 47f753c5-0020-5f74-8a2f-9deadd1a68c1 |  | note | – – – – – – – – – – – – – – – – –
label | 4f4d1a07-9894-56d0-a07a-15f29d44daed |  | note | FREQUENCY: Each Lot
label | 194fffbd-00f9-58f2-8882-1953bbf33f69 |  | note | – – – – – – – – – – – – – – – – –
label | b461c80f-b758-5a44-a4d1-d99991604efb |  | note | CATEGORY: HP*
label | 26c7bfde-8541-52b6-b07a-437f453e8cb2 |  | note | – – – – – – – – – – – – – – – – –
label | d74cf8b9-494f-52f8-baeb-b46847d24d30 |  | note | RESPONSIBILITY: SE
label | d0fc71cc-330b-5b4b-a9e9-cbfdc8e90594 |  | note | – – – – – – – – – – – – – – – – –
label | 5c92ad1c-d406-5d54-b9d3-6e2d1c6116f7 |  | note | VERIFYING DOCUMENTS: This ITP, Main Lot Map
label | f060859b-2f7c-513b-8ef8-1d6112c96234 |  | note | – – – – – – – – – – – – – – – – –
date | b9e0eb7b-92de-57d7-b245-cedabcd644e8 |  | date | Date Completed:
checkpoint-group |  |  | section | 5 - Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Trench Excavation
label | a8a4c0ed-238d-578c-814f-27a33ad3b596 |  | note | REFERENCE: VR 701.15
label | 5b8a71bd-974a-5ccb-894a-0f8c4ec2ecbc |  | note | – – – – – – – – – – – – – – – – –
label | 5ff02dc8-e03f-5c07-b3a6-2457f98e9d2f |  | note | ACCEPTANCE CRITERIA: For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
label | 0a20bac1-7659-5d41-b250-21bd2163499f |  | note | ○ Horizontal Clearance to wall of trench
label | 2a375815-ea78-544f-8cd4-c248d4ad0ab0 |  | note | ○ Pipe Culverts:
label | 9861827d-d988-5741-9f51-78bf5afe0c39 |  | note | • 300mm<Horizontal clearance for corrugated metal culverts<1000mm
label | 7cc6b6b1-29dd-57aa-bcdb-17928599cea2 |  | note | • 300mm<Horizontal clearance for other Pipe culverts<600mm
label | b694e911-d623-5e09-b8c8-8fbdd18a3b98 |  | note | ○ Box Culverts:
label | b149a6d9-05b9-5ce2-bbac-067141047ef3 |  | note | • 0.5 times the height of the culvert<Horizontal clearance<overall height of the culvert
label | 00cacc65-5275-5b2b-985f-2204fb4ba98e |  | note | – – – – – – – – – – – – – – – – –
label | eca53355-8244-5ad9-9b8e-474494d34b30 |  | note | METHOD: Measure
label | 8163e263-f0b9-5e7f-80bb-6b7459021d00 |  | note | – – – – – – – – – – – – – – – – –
label | 2d1cb8c9-c516-5d90-8695-dabd7d16ad30 |  | note | FREQUENCY: Each Lot
label | 58cc7f7d-cd49-5736-a297-6b2b937562dc |  | note | – – – – – – – – – – – – – – – – –
label | 5f8c790d-2fc3-5710-93ef-fc19db9974ed |  | note | CATEGORY: IP
label | a496f792-576d-5106-bd13-30ff63734ea3 |  | note | – – – – – – – – – – – – – – – – –
label | fe1cb052-44ee-50d0-aea7-46229e87b6f4 |  | note | RESPONSIBILITY: SE
label | c7049752-5a73-5c55-9285-ae044fde16c5 |  | note | – – – – – – – – – – – – – – – – –
label | 7c0e286e-f99c-577c-aa85-ee052ecfc6c4 |  | note | VERIFYING DOCUMENTS: This ITP
label | efe3f6e0-99d3-5eff-ba08-5c755270b673 |  | note | – – – – – – – – – – – – – – – – –
date | e82f9cf7-befd-5914-ad63-a4458832fec7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Trench Base
label | a919ace4-072e-5ef0-833f-cfae52e5f773 |  | note | REFERENCE: VR 701.15
label | b54a2b70-fc77-5b96-a4d0-622045d6a701 |  | note | – – – – – – – – – – – – – – – – –
label | 90f15287-cd41-539f-afa4-95e8d33a1083 |  | note | ACCEPTANCE CRITERIA: The base of the trench shall be compacted to refusal using mechanical plant
label | 61ee2723-be41-5f70-b725-6468ed869c35 |  | note | – – – – – – – – – – – – – – – – –
label | b0c34977-7992-56d2-823d-2be2844c1896 |  | note | METHOD: Visual
label | b9791a45-407e-5a45-9119-728fd55cb099 |  | note | – – – – – – – – – – – – – – – – –
label | f3f2e14d-c7e7-5472-af2a-2b3b93f65cb1 |  | note | FREQUENCY: Each Lot
label | e192e1f3-2f06-50c6-ae51-379ebb92fd7b |  | note | – – – – – – – – – – – – – – – – –
label | 4589c7c7-d448-55ec-bf29-9f2348f7dce5 |  | note | CATEGORY: SP
label | 773a6cb5-13f5-562b-bb3f-f067ac298101 |  | note | – – – – – – – – – – – – – – – – –
label | 48ebb2d8-70d5-5a56-915a-b26aa4fc889b |  | note | RESPONSIBILITY: SE
label | 91a03416-60b2-5a5c-ac5c-e25658d66068 |  | note | – – – – – – – – – – – – – – – – –
label | 3c30d0fe-00bb-5c0c-ba7d-9faa3842df84 |  | note | VERIFYING DOCUMENTS: This ITP
label | 328a6db3-7d2e-5184-9344-44cf8c5f14af |  | note | – – – – – – – – – – – – – – – – –
date | 5309ba00-2f1a-5cd7-b736-e741557af9ce |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Bedding-Placement and compaction
label | 8d99643d-d532-5918-89b4-52430361fd3e |  | note | REFERENCE: VR 701.16, VR 701.20 (a)
label | f16029e7-78b2-54c3-9bb6-83fab71a8df5 |  | note | – – – – – – – – – – – – – – – – –
label | 436dc547-17cf-5428-bd87-78fd20d17c26 |  | note | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
label | 919938bd-a576-5db3-96aa-092f24d43652 |  | note | • 100 mm where D < 1500 mm
label | 1768a0bd-f69a-54fb-8d97-8c18d708d69a |  | note | • 200 mm where D ≥ 1500 mm
label | 8f275c2a-5891-5dac-83f9-1aa88a37407a |  | note | – Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | 5a24a4ad-22dc-566a-ad8d-6f9b978b6524 |  | note | – Bedding shall be compacted to refusal using hand held mechanical equipment.
label | 1ef81008-18e1-5b65-8326-09a2d19b3ff7 |  | note | – Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer
label | 6de7d30a-075a-53c6-8a0e-5d5113541bde |  | note | – – – – – – – – – – – – – – – – –
label | 3bcc94b7-2e21-5f14-b9dc-7a5aacc8d57b |  | note | METHOD: Visual, Measure
label | 1a1e3dc2-de04-5838-9be5-c565b0237f52 |  | note | – – – – – – – – – – – – – – – – –
label | cc18b923-7981-5012-b423-606f4ec36272 |  | note | FREQUENCY: Each Lot
label | 47d6d7b3-2bf2-5526-9171-1b086c658523 |  | note | – – – – – – – – – – – – – – – – –
label | d362886f-1cd7-56a6-8d77-33c6dc5a7d11 |  | note | CATEGORY: SP
label | 31adce63-eead-55d1-a027-aabcb78b1768 |  | note | – – – – – – – – – – – – – – – – –
label | 0884af87-9664-5db6-875c-e79b984348ff |  | note | RESPONSIBILITY: SE
label | cec9e406-f21b-5794-8c83-dd31364b9a60 |  | note | – – – – – – – – – – – – – – – – –
label | 81948628-d0de-5cf5-9cdf-6e9ed677ded6 |  | note | VERIFYING DOCUMENTS: This ITP
label | afcb40e4-874d-5dbe-886d-aa259dfda4e2 |  | note | – – – – – – – – – – – – – – – – –
date | a335b4c6-12ba-51d0-b2e4-fb1b65f3197e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Laying pipes-Bedding conformity
label | 4b55453e-54cc-5b81-b236-694c90f2e939 |  | note | REFERENCE: VR 701.17
label | 5fa976e9-cdb6-5f2b-be03-6d5a195498eb |  | note | – – – – – – – – – – – – – – – – –
label | f015c67d-a538-5759-8995-3071f808e479 |  | note | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
label | 6875e759-ba42-5773-8886-a4d29e6eb897 |  | note | – – – – – – – – – – – – – – – – –
label | 92792248-6425-5e1a-b924-50abe1090317 |  | note | METHOD: Visual
label | 9ff55620-dda5-5364-b771-6c3bc5a65f45 |  | note | – – – – – – – – – – – – – – – – –
label | 15f79af3-8eab-504a-be49-a3353fd77382 |  | note | FREQUENCY: Each Lot
label | b97c0bd2-04b8-5f94-bfe6-e44673b3e27a |  | note | – – – – – – – – – – – – – – – – –
label | 193dbdf2-eb36-5b42-bb07-e6bc66967e86 |  | note | CATEGORY: HP*
label | 6f322c0d-f8d7-5225-929d-1d424d1bbddb |  | note | – – – – – – – – – – – – – – – – –
label | cf6d003b-2cd9-5835-9b96-4f975e51be5b |  | note | RESPONSIBILITY: SE
label | c1ab84af-64b2-5dd1-a32d-c2cd44a5a0bf |  | note | – – – – – – – – – – – – – – – – –
label | 0176d83e-c1fb-5c4d-b51d-988f73be76d1 |  | note | VERIFYING DOCUMENTS: This ITP
label | 82fc6d8f-1dd9-530d-8d0f-c60ca0d92739 |  | note | – – – – – – – – – – – – – – – – –
date | d7f89450-ccb7-5815-b0b7-47677e49190a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Pipe Laying
label | 2e3567de-b9ee-5474-bdea-ca0553841e2f |  | note | REFERENCE: VR 701.16, VR 701.17
label | 01534b4c-6ae1-5bea-bc5c-5620cfc9146d |  | note | – – – – – – – – – – – – – – – – –
label | 7f46ca30-52b5-5868-aac9-0e56c0a8f6d1 |  | note | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall commence from the downstream end.
label | dc45c946-4e1d-5ffe-900d-bbfe75f217bc |  | note | – Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
label | 2292ba0b-29d1-5b0e-a75b-447825e14ed1 |  | note | – The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
label | f117a149-2056-5835-9534-21ebefb058df |  | note | – The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
label | 0fcc6c34-1522-56fa-9111-b036947eaf36 |  | note | – When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
label | 7104eda8-7b3d-5993-a4cd-baa128790e59 |  | note | – – – – – – – – – – – – – – – – –
label | 292e43d8-ddce-5d8e-91a0-25b8de3f9da4 |  | note | METHOD: Visual
label | a60f8010-2e14-5277-a25b-ff2cb7d91843 |  | note | – – – – – – – – – – – – – – – – –
label | e778ad26-8d05-518c-8d23-9e6055da1ab6 |  | note | FREQUENCY: Each Pipe
label | 982971d9-f01c-5481-b117-5aec20d99d23 |  | note | – – – – – – – – – – – – – – – – –
label | 2f2438e3-38dc-5632-9c8b-dd7a90b2774c |  | note | CATEGORY: SP
label | 43314ecb-814c-5a8b-bcea-45639c5e0eb0 |  | note | – – – – – – – – – – – – – – – – –
label | 5501d278-3f9a-5126-b6c8-c277555bab8c |  | note | RESPONSIBILITY: SE
label | fc5d1676-aa80-5739-b247-ca9e5407aaf6 |  | note | – – – – – – – – – – – – – – – – –
label | a75dd251-bdbe-5206-8181-475d1d4b18b2 |  | note | VERIFYING DOCUMENTS: This ITP
label | 093e87b6-b6b3-5e53-b407-e957f04767cf |  | note | – – – – – – – – – – – – – – – – –
date | cce2bc9f-2c4c-5454-84e7-b36ef9ec793e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Pipe Joints and rotation
label | 060bd2ab-2885-5b7f-9bf5-322311dce3a7 |  | note | REFERENCE: VR 70.18
label | 5bbb5370-e76c-5af6-b9ae-82e4ef2e2600 |  | note | – – – – – – – – – – – – – – – – –
label | b72ad68f-e69f-521d-94f0-09bfa00120d6 |  | note | ACCEPTANCE CRITERIA: All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
label | c4fbdb16-d695-5dd1-a671-ba255a233a0f |  | note | – Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
label | 6b61051b-d4f6-5fc8-8a2f-c8b7fe6f66ec |  | note | – – – – – – – – – – – – – – – – –
label | 49003247-f5b5-57d5-94b6-e292a88b7dac |  | note | METHOD: Visual
label | f21e2aa1-1e07-5303-9eb7-f55aee514da0 |  | note | – – – – – – – – – – – – – – – – –
label | e05d0a00-52c4-542b-ba67-e70f865bc495 |  | note | FREQUENCY: Each Pipe
label | 8cc34092-bd94-5e95-a5df-e8071372fe12 |  | note | – – – – – – – – – – – – – – – – –
label | 6243fed9-9799-549e-a8a7-53e3633ebfe6 |  | note | CATEGORY: SP
label | ea87ce1e-1230-5bb3-bb1d-9759077e9022 |  | note | – – – – – – – – – – – – – – – – –
label | 10871007-a23d-525d-aa14-3efc7adf1727 |  | note | RESPONSIBILITY: SE
label | 206e9b87-8b8a-5527-939e-12290bda7909 |  | note | – – – – – – – – – – – – – – – – –
label | 8b53d03a-2d9f-5c70-b054-506e2654083e |  | note | VERIFYING DOCUMENTS: This ITP
label | 024b711b-3a7a-57d3-a945-3016c853c1c4 |  | note | – – – – – – – – – – – – – – – – –
date | 2b2f8633-dc6f-53fc-b07d-94c4d63b18e9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Conformity with drawings
label | 8b716f3d-88d4-5b91-b74a-a9ae7ca87891 |  | note | REFERENCE: VR 701.10
label | 1419699f-4779-5d88-9dc8-cdf453ab6a57 |  | note | – – – – – – – – – – – – – – – – –
label | 47e510b4-2712-5429-8cc8-12d6eb2f5737 |  | note | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
label | cbcc04ab-2424-5ad4-a3ff-fe51ee1c14a0 |  | note | • Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | 4442fe07-59d6-5fb9-8b93-6ed9f7f2b367 |  | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | ba1f8a7d-fda1-579c-ac5e-4e57fdc3f423 |  | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | 6f7058d9-ca7a-558c-9eab-afbcf9a3fe26 |  | note | (c) invert level of pipes at pits ±50 mm
label | 2e33953a-6e6c-57db-8627-9810b8f1fd8f |  | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | c4ee982f-e3dc-50cf-8148-78f299a316db |  | note | ATTACH: Survey Report
label | 01498990-95f0-5726-a96d-f6515d3c4743 |  | note | – – – – – – – – – – – – – – – – –
label | ce261310-80f4-51e8-b2d5-97297b071a19 |  | note | METHOD: Measure
label | 611cdcbd-f067-562f-9d80-82d9bce709f0 |  | note | – – – – – – – – – – – – – – – – –
label | 3f5e785d-c4ea-5418-b2e5-4f60953f9f7c |  | note | FREQUENCY: Each Lot
label | 311191b9-2f7b-5561-8d5f-d86c48ce5d26 |  | note | – – – – – – – – – – – – – – – – –
label | 98e81741-685a-5ba0-8c82-c413da099f42 |  | note | CATEGORY: HP*
label | af71a0ab-1f1f-5aba-9ab4-926ef4c1f53d |  | note | – – – – – – – – – – – – – – – – –
label | 41117d9f-2024-5101-97b5-9a7ec50efd16 |  | note | RESPONSIBILITY: SE
label | 130c50dd-92b9-509c-9fa3-dd6d63a3834b |  | note | – – – – – – – – – – – – – – – – –
label | 1982cb35-c5ea-5ea2-ba71-dffd30f32f54 |  | note | VERIFYING DOCUMENTS: Survey Report
label | d52b837c-5d57-56d3-93cc-8969d4d33d21 |  | note | – – – – – – – – – – – – – – – – –
date | 2129b440-25f7-51b4-ae91-5cd75088a64a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Backfill-Under area to be paved
label | 887a6c93-afe9-535c-bf3f-9f315156d88c |  | note | REFERENCE: VR 701.19 (a) i
label | 280a9ec0-b8e0-56e5-83aa-b130d8ad45cc |  | note | – – – – – – – – – – – – – – – – –
label | 4fa58f1d-416a-5735-8bb9-8deca3060c32 |  | note | ACCEPTANCE CRITERIA: Culvert under area to be paved
label | 9ba6cfb8-ace7-5d68-8751-ffd6e62c007f |  | note | – Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
label | 3409691a-177a-5044-8995-a8ba5ee163bf |  | note | – Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
label | d86fca46-f491-50fa-bbe5-cf7980316864 |  | note | – – – – – – – – – – – – – – – – –
label | 417190e4-1c2e-5794-a268-0ff91a2a8bfe |  | note | METHOD: Visual
label | 1b6dc6a0-94b5-509b-b3aa-2f8ff134fd87 |  | note | – – – – – – – – – – – – – – – – –
label | 71735c95-8785-5f25-a675-8cb4ca75a79e |  | note | FREQUENCY: Each Lot
label | fd5a4c94-0d60-510d-ad20-94a27a840112 |  | note | – – – – – – – – – – – – – – – – –
label | 76ab1f82-4472-57a5-9700-12f337bd7a1d |  | note | CATEGORY: SP
label | c4d18859-e11b-5c70-9f0e-5ba17b6a0306 |  | note | – – – – – – – – – – – – – – – – –
label | 43a95796-dac7-58d1-8299-24107bd1cc9c |  | note | RESPONSIBILITY: SE
label | d6d267d8-36ff-5df8-a2c5-54d026e9e8bb |  | note | – – – – – – – – – – – – – – – – –
label | be6070ca-ed7f-5a0d-b05e-cf90fc3f6405 |  | note | VERIFYING DOCUMENTS: This ITP
label | 24c925f3-d8df-5b9a-884d-d88438d7afb9 |  | note | – – – – – – – – – – – – – – – – –
date | e32e60b3-02d2-504d-b616-1723749b2085 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Backfill-Under area not to be paved
label | 73824c56-773b-5a67-9107-35b226b63f02 |  | note | REFERENCE: VR 701.19 (a) ii
label | 00edb995-d3f4-50f0-9ede-1655720acb1b |  | note | – – – – – – – – – – – – – – – – –
label | 5062e60e-46aa-500f-b235-d471ded408c7 |  | note | ACCEPTANCE CRITERIA: The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level
label | 8efc5420-89f7-5f5d-8b03-138daaca0e68 |  | note | – – – – – – – – – – – – – – – – –
label | 5c9885f1-e78e-565f-8e9a-c9b16c32c358 |  | note | METHOD: Visual
label | 42e78396-47ed-5a7e-a05f-161bad54fff9 |  | note | – – – – – – – – – – – – – – – – –
label | 6159cb10-8895-5c91-8a04-f10cd4882fda |  | note | FREQUENCY: Each Lot
label | 49a33bb5-a5fe-514c-b77c-aef7696afc8b |  | note | – – – – – – – – – – – – – – – – –
label | 5d60988a-72b8-574b-9d61-9f7472f66f12 |  | note | CATEGORY: SP
label | d8857176-2e31-5bf6-a9ba-314d010deb19 |  | note | – – – – – – – – – – – – – – – – –
label | a284344b-d8a6-58ec-8c18-2e51bb7ee3cc |  | note | RESPONSIBILITY: SE
label | d8b74215-068b-5bd9-99ac-52928db24a2a |  | note | – – – – – – – – – – – – – – – – –
label | 02249dac-c30e-59ef-8ad8-c8ad0dbde4df |  | note | VERIFYING DOCUMENTS: This ITP
label | c197c6c4-3a45-5f82-a533-5960b42c405c |  | note | – – – – – – – – – – – – – – – – –
date | fdb61a0e-70fd-5eda-b1af-e51d0a1729db |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Backfilling with cement stabilised sand
label | 9008cb95-a264-5db3-af73-0539eaab7286 |  | note | REFERENCE: VR 701.19 (c)
label | 786bead9-4906-5c48-86de-0b3864a25184 |  | note | – – – – – – – – – – – – – – – – –
label | e7f084ea-c7bd-5d0d-b4dc-d86ad0719b9a |  | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height
label | 9606e787-c9bf-5f7e-8fc4-dbae4ae4efe8 |  | note | – – – – – – – – – – – – – – – – –
label | 0c85a82e-a1c1-572e-9f7b-e2f264d64f2f |  | note | METHOD: Visual
label | fb519463-908e-5f49-b82e-67ece094b189 |  | note | – – – – – – – – – – – – – – – – –
label | 91aa3881-b108-52d8-b15c-b25ba8cc446a |  | note | FREQUENCY: Each Lot
label | 04584fdf-29cb-5cb3-ae76-7abc41055722 |  | note | – – – – – – – – – – – – – – – – –
label | e767dca2-0284-55cf-af60-b00f6e558e07 |  | note | CATEGORY: SP
label | 62924015-fd38-529b-ac99-e7a9910f7856 |  | note | – – – – – – – – – – – – – – – – –
label | b621d760-d70d-5447-90bc-01d9469f78f9 |  | note | RESPONSIBILITY: SE
label | 5804fa22-430f-5397-a018-c86e8b4050c1 |  | note | – – – – – – – – – – – – – – – – –
label | 47a28f49-c46b-5937-b0b6-a90e0c60ad88 |  | note | VERIFYING DOCUMENTS: This ITP
label | e304782c-7b86-5cb0-a494-82b01e49c1bc |  | note | – – – – – – – – – – – – – – – – –
date | 3bcba2e9-16bf-5fbe-810b-9d227abcbd73 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Backfill Placement
label | a16745af-6aad-5fcf-a6d9-8a54b15eb2d8 |  | note | REFERENCE: VR 701.20
label | 8f5804c0-06f2-51c5-9958-0f8518795d11 |  | note | – – – – – – – – – – – – – – – – –
label | 034c1494-4936-5921-977f-af924ff4e381 |  | note | ACCEPTANCE CRITERIA: Backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | 9a3be1bd-058c-5a94-b9a3-3c0ac2dcca4d |  | note | – – – – – – – – – – – – – – – – –
label | f375c072-9e5b-53e0-9d64-581323249479 |  | note | METHOD: Visual
label | 20895346-6083-508f-8a4d-4fc2f3ed88ea |  | note | – – – – – – – – – – – – – – – – –
label | 82665dcc-96de-5e94-80f4-fd4723f6cbaf |  | note | FREQUENCY: Each Lot
label | 65d2a652-39c3-5ec5-86c9-d2748c087c70 |  | note | – – – – – – – – – – – – – – – – –
label | 92d94ec5-3861-5f5a-86d1-d7d59df22225 |  | note | CATEGORY: SP
label | 39159a19-3923-5262-963b-354b22625637 |  | note | – – – – – – – – – – – – – – – – –
label | 02670583-2a34-5a49-a5da-4e69761db2c5 |  | note | RESPONSIBILITY: SE
label | 583c9c8a-c62e-5177-b781-9ef9763d9a1b |  | note | – – – – – – – – – – – – – – – – –
label | 76811fb0-d488-5c24-8f62-ae5300a66b0f |  | note | VERIFYING DOCUMENTS: This ITP
label | dc469d97-af7a-5aef-8647-9f3fbd93e97a |  | note | – – – – – – – – – – – – – – – – –
date | 4cfb7c3c-4aca-51f8-9e8a-d28ef83c8ace |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 - Backfill Compaction
label | b71b933e-e49c-5fca-bef8-011168f558b8 |  | note | REFERENCE: VR 701 (b)
label | bd2a6219-ec30-5546-9d23-1ac784899ee8 |  | note | – – – – – – – – – – – – – – – – –
label | f2f84038-14a8-5c91-a8e6-34bfaa2df979 |  | note | ACCEPTANCE CRITERIA: 20% of all bedding/Backfill layers for each culvert shall be tested.
label | 49a61fb0-af56-551d-8c2e-49d387c0983f |  | note | – Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
label | 943374f7-ec4b-5106-95d8-a0746464e4c5 |  | note | – Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | ee2f5221-a7df-560a-9165-05f8c219cbfd |  | note | – – – – – – – – – – – – – – – – –
label | 7976bbef-5d6a-5e11-a43b-02635d1e2d1b |  | note | METHOD: Test
label | 0dc28c23-ce6b-50a9-98f4-936ba9ab765d |  | note | – – – – – – – – – – – – – – – – –
label | 0b75dba7-a850-5a83-acae-7efb71b70730 |  | note | FREQUENCY: Each Lot
label | fded4bcd-6a48-5d3b-b959-ac1c46c2098e |  | note | – – – – – – – – – – – – – – – – –
label | 21b11351-62e6-5328-a358-4c1b95152b59 |  | note | CATEGORY: HP*
label | 9c1ef8ae-34a8-507a-8bac-2ded96ea53aa |  | note | – – – – – – – – – – – – – – – – –
label | d5d5bb35-ed96-5131-a3f1-09da4d4de04d |  | note | RESPONSIBILITY: PE
label | c87e57c7-ec77-5147-b4e8-27ee39ed7c88 |  | note | – – – – – – – – – – – – – – – – –
label | 7f4db9f4-ff20-59c9-8baa-3467ee01478f |  | note | VERIFYING DOCUMENTS: This ITP
label | 4bd438fc-bfdc-5578-9b4a-621e5a695a52 |  | note | – – – – – – – – – – – – – – – – –
date | c0b09011-b20f-5991-980d-07d4c3bf3585 |  | date | Date Completed:
checkpoint-group |  |  | section | 6 - Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Compaction and Moisture content tests
label | c0024530-12e9-5f22-9423-7a419fe125f5 |  | note | REFERENCE: VR 701.20
label | 6af2e3a0-e2a7-57e6-a6a9-931afa349b6d |  | note | – – – – – – – – – – – – – – – – –
label | 7552da4b-4c09-556b-af2e-2582d04dcf91 |  | note | ACCEPTANCE CRITERIA: Bedding and backfill shall be assessed for compaction and or moisture in lots.
label | 230e78d4-0328-5235-9759-18b0ab1eeeb0 |  | note | • The number of tests per lot shall be three.
label | ceb3e844-02df-5710-9832-bfd4a6a0d041 |  | note | • A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
label | d82e25c4-873c-5882-9f44-f1af8c914c4b |  | note | • Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
label | 52bb3852-8e6d-557a-b353-8f178003c24a |  | note | ATTACH: Compaction and Moisture content test results:
label | 0db151a5-1c2a-566c-990f-13d97efc521d |  | note | – – – – – – – – – – – – – – – – –
label | c43599ba-6376-5b4b-bc7e-771ff96cc1e2 |  | note | METHOD: Document Review
label | 9686cb47-fbe0-595c-a3f5-c01f8e21fa7b |  | note | – – – – – – – – – – – – – – – – –
label | 6916e9b2-8680-5025-9c8a-da5f75ef13a5 |  | note | FREQUENCY: Each Lot
label | 1c5eae59-2261-5d2c-a0f2-a9cdf189b5a3 |  | note | – – – – – – – – – – – – – – – – –
label | b39a2ebb-1e40-57d8-a30c-f34cd8f87e91 |  | note | CATEGORY: IP
label | 270c8cd4-03e4-5162-aa51-29d546848f0f |  | note | – – – – – – – – – – – – – – – – –
label | 5de6d807-23de-59cb-b8cd-b1f7a92adbb6 |  | note | RESPONSIBILITY: SE/PE
label | 21b30764-944c-561f-9bfe-22a2b6ae2a09 |  | note | – – – – – – – – – – – – – – – – –
label | 7458dbdf-6f90-583f-98ee-1bcad095aa33 |  | note | VERIFYING DOCUMENTS: Test Results
label | ec9e0fd7-d7cb-5ba5-9817-ae408cb7364f |  | note | – – – – – – – – – – – – – – – – –
date | 00e6ceab-778c-5df3-b4f3-c52267bf7afd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 8f262dab-c0b7-5f71-8960-831b1316ed11 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 17e5af41-0df2-510f-a3c1-8c72014dbc7b |  | textbox | Name:
text | 6300f5e0-9901-5e49-8be5-1588f1b0c1fe |  | textbox | Position:
date | 21a469a4-1741-584d-90e4-934d3687735d |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Unbound Flexible Pavement Construction Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Unbound Flexible Pavement Construction Rev 0 | f744d3ee-8c8f-4d67-a40d-fdb4ba43a3d4
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | b55c62ca-d792-5c30-b0a4-165e6a9296ea |  | note | Document Title: ITP-CIV-CAMMS-Unbound Flexible Pavement
label | 13f61ea6-3ac9-54c7-8d07-91a9066e6cbe |  | note | ITP Description: Unbound Flexible Pavement
label | 91b15e8d-0d0b-5667-8294-4f4e79cfb9b1 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 793cf508-63f8-5dfa-9f91-19bbdbe8d3cc |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CAMMS-
label | c3cea942-d328-5d3d-9301-a38552e4b570 |  | note | Revision Number: 0
label | e02035c2-00ad-5a12-bc04-0339495ab972 |  | note | Revision Date: 06/09/2022
label | abe33643-1e73-5566-bd3a-285677a8a75e |  | note | ITP created by: Victor Mira
label | 4f1461ef-2092-5ac4-a88b-9338ac36061c |  | note | ITP approved for use by: Aldrin Guinchoma
label | 227fb451-4571-57fc-95ce-599f2b621019 |  | note | 1.1 - Non Dependent
label | 36666f14-99f3-509b-8ce3-015e4a2b269e |  | note | Reference Documents: IFC Drawings
label | 559a7b5a-6740-54f3-869d-fd62c4fae118 |  | note | 1.2 - VicRoads Section 173 (10/9/2008)
label | 4fba219a-4678-5882-b5cd-987e808a70d5 |  | note | 1.3 - VicRoads Section 304 (13/8/13)
label | da660cb4-376d-519e-97f7-dcdc526ca729 |  | note | 1.4 - VicRoads Section 801 (19/07/18)
label | 7130887a-d95c-5e6f-9d3a-dc7cb4e4656c |  | note | 1.5 - VicRoads Section 812 (13/07/16)
checkpoint-group |  |  | section | 2 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Crushed Rock Mix Design
label | 68a902b3-c1e6-58de-8a46-20956b389639 |  | note | REFERENCE:
label | 4751b681-53e9-50fb-9db1-f83c07a8cc8f |  | note | Section 304.03
label | 8366ef5e-cc0e-5be9-8149-d293b9b30d27 |  | note | Section 304.05
label | ef8fd89a-7800-54f7-b587-5a28a61016f8 |  | note | Section 812.04
label | 67800bb9-7a78-5310-a90c-6c024e688be7 |  | note | Table 812.121
label | ac927852-f881-5e43-a56c-1ca11bb27a13 |  | note | IFC Drawings
label | 56367f0e-c33c-52c9-9d34-40e4e1747f63 |  | note | ---------------------------------
label | 1fc216b2-a2c7-5b37-89b6-c99990ceb593 |  | note | ACCEPTANCE CRITERIA:
label | da489b47-34b2-5c45-b1fe-90c26f52f2e1 |  | note | All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
text | acbada30-6bf8-5bf5-ba43-018dbe1d3068 |  | textbox | Enter: Teambinder Material Approval number
label | 099915b6-b0d9-561c-9bb7-92e54a1116d7 |  | note | ---------------------------------
label | 3900d7b9-c07e-52fa-8f1d-86ae4e9fd37a |  | note | METHOD: Document Review
label | 2101cb7a-99ef-5ec2-bfd1-cea79804647b |  | note | ---------------------------------
label | 85b19f5a-03b1-510c-8558-23c4737fb7ad |  | note | FREQUENCY: Material conformance as per Table 812.121
label | b4a9dc93-de53-57c7-9561-921f67ffc044 |  | note | ---------------------------------
label | 555fbab6-8e5d-57a1-91cb-1d352fa09110 |  | note | CATEGORY: HP
label | d9a34524-0503-5175-892a-1c2d2e3e6c1e |  | note | ---------------------------------
label | 2d43b345-40cf-5d30-a968-821a51fa5092 |  | note | RESPONSIBILITY: NA
label | 8d4cecf1-e86b-5dc8-be7c-63e2fa39f2f9 |  | note | ---------------------------------
label | b63fcff2-a5d2-500a-a79c-0d274b0342b4 |  | note | VERIFYING DOCUMENTS: TeamBinder Material Approval Number
date | d30a2296-79f3-5e6a-8161-e8b8d8bcf821 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 Subgrade Preparation
label | 0a77fc9a-cd97-5345-8cff-4a6fc6d3d8f6 |  | note | REFERENCE: 304.04
label | 9dcd28bd-0e21-52f5-a571-296f0ca43c53 |  | note | ---------------------------------
label | cb8fe355-79ec-5e91-95de-540868fc6533 |  | note | ACCEPTANCE CRITERIA:
label | 94a030a0-8ac3-5b26-8c0a-981d645bfe6b |  | note | Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
label | ba45e699-1062-50d6-a60d-f2384b1e070e |  | note | Reference: Subgrade Preparation/Type fill Lot Number:
label | e65e0f0e-ac83-5c56-80fd-3e58620f803a |  | note | ---------------------------------
label | d76d8c23-44e0-5753-abed-0a5bd24e52a5 |  | note | METHOD: Document Review
label | d3d08d4b-4d83-5a85-9834-704cb4f24441 |  | note | ---------------------------------
label | 72110011-8105-5b79-83ab-918691611c35 |  | note | FREQUENCY: Each Lot
label | 8b0cfad9-5cc9-5e43-9116-cd31f46e6e47 |  | note | ---------------------------------
label | 3355057c-9191-58fb-82c2-0e2e4c78d8ff |  | note | CATEGORY: HP*
label | ac4c4c19-812f-5c8f-b649-796ca7403866 |  | note | ---------------------------------
label | a041c668-9c95-5dbe-8ac9-a28267432740 |  | note | RESPONSIBILITY: PE
label | d52543bb-4727-57f2-8082-5dc5c53b9a26 |  | note | ---------------------------------
label | f454bbb4-6c59-54cc-9591-49abecd42a2f |  | note | VERIFYING DOCUMENTS: Underlying layer Lot number
date | 778513dc-057c-5981-bec9-8982df6bb7d9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Select Scale
label | 6d7cc770-950a-5318-ba93-7526a788e108 |  | note | REFERENCE:
label | 9e0feb14-2d60-5d3d-9a30-684020a484ae |  | note | Project Requirement Specifications
label | 345e0b14-ff5b-501d-95f0-bab4580add89 |  | note | IFC Drawings
label | c9ea8d1a-b337-558b-8992-b7b8af7bf17e |  | note | ---------------------------------
label | 68266dd1-c597-515f-a440-08efd011da97 |  | note | ACCEPTANCE CRITERIA:
label | 169bbf9e-dcf6-557a-bbb0-2ae098ea66ea |  | note | Specify site specific scale:
text | 2ee37d7a-3f91-5504-8744-be908d03fb74 |  | textbox | Enter: Site Specific Scale (A, B or C)
label | 27c5eb12-913d-5cef-a7e7-e6164acbdaf5 |  | note | ---------------------------------
label | 6ccad292-f733-5c7f-ae80-818943703a86 |  | note | METHOD: Document Review
label | 412ccf13-5431-5267-9990-7fa814d45626 |  | note | ---------------------------------
label | 425894c3-d09f-5482-8cc3-3347d2a2b0f6 |  | note | FREQUENCY:
label | f26abbaf-eb6d-57ef-89d8-22b799a6dd2b |  | note | Prior to Commencement
label | d3083ceb-b2d9-5a35-868f-1f4e26ad6ff5 |  | note | Each lot
label | 5c59ba97-8280-55a9-bc8a-66f0e3f262cd |  | note | ---------------------------------
label | 4052575c-0a81-5592-b760-0dd21175a9cd |  | note | CATEGORY: HP*
label | 96230fa2-a7d4-5cec-8deb-18f5a366fc1a |  | note | ---------------------------------
label | 51aea4e4-e81c-58da-ac21-c24d8ed4e072 |  | note | RESPONSIBILITY: PE
label | 07cc8e69-c803-5efa-9d6f-6b48a3c6d09b |  | note | ---------------------------------
label | 1033ea59-d351-56e5-a79c-12094146064b |  | note | VERIFYING DOCUMENTS: Sign ITP
date | e1f4ea25-c5b1-55fe-a09b-c4843baac350 |  | date | Date Completed:
checkpoint-group |  |  | section | 4 - Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out and Lot size
label | 5409ac50-a78f-5950-8b06-bcf37ce72cbc |  | note | REFERENCE:
label | 4c19df48-11f4-531f-bc86-f6865ceb1c11 |  | note | IFC Drawings
label | cceac362-32e6-507a-ad53-4c37ca164790 |  | note | Section 304.06
label | 170aa09d-0885-5d35-a47e-0c925a63c77b |  | note | ---------------------------------
label | f2536fbe-317f-5649-a038-213dd81753c3 |  | note | ACCEPTANCE CRITERIA:
label | b7a59640-6cd5-5d6b-8df2-cb035a3e1e2b |  | note | Lot size shall be the lesser of 4000sqm or a days production.
label | 223d9cf2-cd4d-51dc-89cd-83caf06ecf51 |  | note | Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
label | 77993d6a-47a9-5e11-9b74-2a0344b9ad6c |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | 78862ad8-2c08-597d-b451-6f6913661239 |  | note | ---------------------------------
label | 1b0127dd-e441-5bf3-9f28-d8afce054975 |  | note | METHOD:
label | 03bbaece-49ba-51ee-a8b6-85409b1e8678 |  | note | Survey
label | 5e8c7bc6-8b59-5370-8374-26540f992247 |  | note | Document Review
label | a7b4571e-e366-5365-95ca-a222693655f4 |  | note | Measure
label | d6fdc7cf-b8b2-5439-834b-ae4d475f04db |  | note | ---------------------------------
label | 9d2cdf13-c855-5900-b6cc-a515aa229f1c |  | note | FREQUENCY: Each lot
label | 4f354337-be00-58e9-accd-40b8cdfeee2a |  | note | ---------------------------------
label | 1dc9dd2c-bb17-5487-9dd0-4c1d60bd872f |  | note | CATEGORY: IP
label | c79e69dc-90c8-539d-ae83-9e860a75283b |  | note | ---------------------------------
label | 3612b60d-3a6b-5de9-bbb3-a9603110d6d1 |  | note | RESPONSIBILITY: Surveyor/SE
label | baad0808-19d1-5990-906a-37a6846bc62a |  | note | ---------------------------------
label | 74f337a1-f617-587d-830b-44ef45fff1c2 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 6b29f2dc-d36c-5639-ace0-7e28e720bacf |  | date | Date Completed:
checkpoint-group |  |  | section | 5 - Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Crushed Rock Delivery Dockets
label | e888277f-1119-5abc-bde0-3647bfbd6740 |  | note | REFERENCE: 304.04
label | 9b32beba-3398-529a-9eb3-a4d19e57e47b |  | note | ---------------------------------
label | e1ecc8d3-5d85-5c23-8886-5cda59fe8a62 |  | note | ACCEPTANCE CRITERIA:
label | a6b49288-492f-5abd-b2ac-1ae5a31074a1 |  | note | A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
label | 88c936af-18b0-51fc-b2d8-747430a81813 |  | note | ATTACH: Delivery Docket(s)
label | 011452d6-a4f6-57df-ad3f-db8feb166519 |  | note | ---------------------------------
label | 68a06e94-9efa-55c7-b92e-1f7c046c5eb8 |  | note | METHOD: Document Review
label | f7d2b292-9a4a-507c-ba5a-ef93de679049 |  | note | ---------------------------------
label | 6b907202-b678-520b-8506-116d64178633 |  | note | FREQUENCY: Each Lot
label | 267477f9-cf95-584a-8363-024cec832c52 |  | note | ---------------------------------
label | 947f035d-6efb-58b5-b824-092854a9f7d6 |  | note | CATEGORY: IP
label | d1f46f3b-a35b-54ea-a419-c01e1fcf9db4 |  | note | ---------------------------------
label | 3caab89e-bfc9-554b-a065-4dcfcb211cff |  | note | RESPONSIBILITY: SE
label | c3329b50-052c-54c4-bcea-3c0986b403e2 |  | note | ---------------------------------
label | b198e82a-183c-563b-904a-eda4658982cf |  | note | VERIFYING DOCUMENTS:
label | 6132c422-e79a-5df2-be45-21d3b0f64041 |  | note | Attached Docket
label | 6436ad19-a2ae-5872-a193-35ce744e89b8 |  | note | Sign ITP
date | 24cd4e46-6e38-5838-88f9-72d86df445aa |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Placement of Material
label | 8021135a-1436-5029-b0cb-96a8fd49333c |  | note | REFERENCE:
label | 3f4067c4-d870-585d-b660-4e16952a2c43 |  | note | Section 304.03
label | ee1f82d7-82ae-5a24-968e-3ad41d06f65d |  | note | Section 304.06
label | 63a05123-8bc2-598a-9401-7d03f626a506 |  | note | Section 304.08
label | 3de5777d-3ca0-5c9c-b26a-c6ead229f516 |  | note | ---------------------------------
label | 49e70309-4983-5e6e-b417-dd3386e990a4 |  | note | ACCEPTANCE CRITERIA:
label | c85841d3-dd1d-5850-82d6-e1dc626e568b |  | note | Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
label | 4e8d0fe1-8fa0-5ec3-9773-d5bd30221c4c |  | note | Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
label | d1dfcd97-121a-50f5-892f-fd78991c19b6 |  | note | Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | c75e935f-40e5-5057-ac3d-a32f38ef2c4a |  | note | At no location shall water pond on the surface of any pavement layer.
label | fbd5db62-ba6b-536b-b6a0-b6b97e7848cc |  | note | ---------------------------------
label | 1d406a74-ac29-573b-b35a-568538547b59 |  | note | METHOD: Visual and Measure
label | d020afee-fac8-5ba2-a7d6-709a59be7493 |  | note | ---------------------------------
label | 7cfdcb63-aaeb-545c-b9ea-e7a9ddf586c0 |  | note | FREQUENCY: Each lot
label | 27c4e985-587b-51c8-9e83-b01c5e30e895 |  | note | ---------------------------------
label | a1dbe192-093e-5485-af8d-3a78bab7e384 |  | note | CATEGORY: IP
label | 3e8b5874-dd25-58af-a441-239088a5dd32 |  | note | ---------------------------------
label | 4ba77cfe-fe4f-550b-8f1e-55dc230895d4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fc53907c-6bcd-576a-9f2d-2e5d6334e699 |  | note | ---------------------------------
label | e53d2792-cbb5-5125-8bad-117e2f924f53 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 03c5fa2f-caa1-530d-aaca-4125f1c757d4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Construction - Jointing
label | 64123a85-1d02-5f19-9453-4844d573de1d |  | note | REFERENCE: Section 304.07
label | ba4668de-6477-5670-8461-6a5ae415f54d |  | note | ---------------------------------
label | 539f24af-9fba-5ec9-aee8-ba60a8a5f3fc |  | note | ACCEPTANCE CRITERIA:
label | 864dd519-79f4-50e0-92c6-ab97ff7c9c4a |  | note | The layout of joints shall conform to the following requirements:
label | 0af072d6-394f-5d3d-ab66-66ba9ebd508f |  | note | (a)material shall be spread in such a manner as to minimize the number of joints;
label | 4bd06322-9544-5c96-8c06-de20a3497113 |  | note | (b)for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | 293aa40a-5624-5c73-8d3f-548e0a2b5868 |  | note | (c)transverse joints shall be offset from one layer to the next by not less than 2 m;
label | 5851416f-b2d0-5856-bfe2-cd580837e20b |  | note | (d)longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | 4f1feef5-2283-5963-851e-6ecfa3f790e0 |  | note | (e)longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | 5ba5b430-c84f-5350-a141-b00bfb8907e0 |  | note | ---------------------------------
label | a008ea52-f60c-5d98-ae21-349d8aa97603 |  | note | METHOD: Visual and Measure
label | d3aef334-c0d8-5fed-87e5-78bb78ea1c92 |  | note | ---------------------------------
label | d3001caf-47ae-5d67-935e-4d884711ac6e |  | note | FREQUENCY: Each lot
label | cdbc1da8-6ff2-5ecf-ae52-a4a4a529149d |  | note | ---------------------------------
label | 4f2c5ec1-2d52-56da-94f7-e43c8608f8da |  | note | CATEGORY: IP
label | 733883d5-a871-5443-a545-980606eff550 |  | note | ---------------------------------
label | b5133e64-d470-5d51-9f01-874f3b929876 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | bf948f03-ceb3-52b7-ae63-0a571afdc19b |  | note | ---------------------------------
label | 41bdf602-39cc-523b-b28a-4f6429b5ecb2 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 76dacd57-462d-5753-99e4-c913c373f31d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Compaction test (Frequency)
label | 8eecee5b-2b46-57ab-91d1-5362ecc28d53 |  | note | REFERENCE: 304 .11 (b)
label | 3a573e89-60c3-5c2d-b255-c62a548d3bf7 |  | note | ---------------------------------
label | 1dca3086-5fa6-59a5-ba35-15162f7ffdce |  | note | ACCEPTANCE CRITERIA:
label | e980943f-1537-5888-950e-2e8dfd9cbd62 |  | note | The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
label | 1ba1c076-c564-5b1c-8f94-755249eba709 |  | note | The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
label | 15d9c8df-722e-5604-abb0-2b0f830e128b |  | note | Scales A and B: 6 samples
label | b7cdb2eb-cd50-5a38-a86f-017578def4c3 |  | note | Scale C: 3 Samples
label | 2a8363d9-5a75-5d22-8637-18f5f0b04d61 |  | note | Pass: Tested
label | 532b0cb4-2d40-50f4-a32e-db77e21c3973 |  | note | NA: Not Tested
label | 860d4b10-a8aa-58ff-b905-fc12cecb4fc3 |  | note | ---------------------------------
label | e003a94e-eef6-5287-b134-01eb5bc6783c |  | note | METHOD: Visual
label | 9ee6a47a-f402-5008-93b5-54ee050f6093 |  | note | ---------------------------------
label | 3a7488f0-38b7-5766-a23f-96e8038e63da |  | note | FREQUENCY: Each Lot Where applicable
label | 782c5fba-caef-5c66-95fd-0167f90cbcd3 |  | note | ---------------------------------
label | 1021c69c-3d0f-56ed-900d-584499651654 |  | note | CATEGORY: IP
label | d3e9ae6e-a945-5e6e-942b-b4abd51ad972 |  | note | ---------------------------------
label | 37e92ba0-65a0-58c7-8626-5a6055929544 |  | note | RESPONSIBILITY: SE
label | 1041ba27-50b1-575a-a56d-7733d3f838fc |  | note | ---------------------------------
label | 600a8c1f-4e05-587b-9ba7-6f24a9f1ce90 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | b0b5ee3c-8310-5622-9e6c-6a8162bf8bad |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Post Compaction Materials Testing (Frequency)
label | b507b699-4342-5a28-aea5-ac48c6cac71f |  | note | REFERENCE: 304.11 (c)
label | a5d5af23-a01a-53e9-bf88-70a69fd1f3e5 |  | note | ---------------------------------
label | 9e0638ae-1a18-5088-ac74-cdb9cb682e69 |  | note | ACCEPTANCE CRITERIA:
label | da2ff6e4-cc41-509e-914f-728ec3f5ee68 |  | note | ○ SCALE A: The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
label | 0f9d2dc2-3598-5c28-b3e9-7712afcdbb58 |  | note | Compaction:
label | 81a2653b-8fda-5543-9096-e40701a996ce |  | note | Lower Subbase: none
label | 0fd9fe5d-f6cf-534b-9164-ac7353d6ddc0 |  | note | Upper Subbase: 1 in 4
label | 0ac3d048-5861-53f1-a1e1-51b8913fbc15 |  | note | Base: 1 in 2
label | 2069c7c6-0080-58f7-9443-a94aafb579f2 |  | note | PI:
label | 858ba2ca-eeca-5b4e-9ca0-543366de3fdc |  | note | Upper Subbase and Lower Base: 1 (two samples) in 8
label | 37d0a479-e77c-5e75-a2af-65c687781b18 |  | note | Upper Base: 1 (two samples) in 4
label | 485cec2a-0513-5c16-b762-0e7d66310019 |  | note | ○ SCALE B: the first lot of each pavement course shall be tested for post-compaction grading and PI.
label | 316b2364-ac93-59f1-819a-850f1ea59e6c |  | note | ○ SCALE C: Post compaction grading and PI testing is not required (CHOOSE NA)
label | 579f35ea-5b48-5542-8564-8fd388ae9091 |  | note | ---------------------------------
label | 16549729-6931-5d7f-87f5-5036437aff82 |  | note | METHOD: Visual
label | 80e04843-a658-58f7-bf22-98a3e8d8522f |  | note | ---------------------------------
label | 56ef0c12-cea3-5771-b7b2-a19ab8154b88 |  | note | FREQUENCY: Each Lot Where applicxable
label | d75f02ab-81c8-57c2-b40e-76e6e5a512aa |  | note | ---------------------------------
label | 84931af5-1c11-5fdb-8657-23047830793a |  | note | CATEGORY: IP
label | 2e9c2c8d-3328-52fc-8c0e-191de90ac8b2 |  | note | ---------------------------------
label | 32af05aa-d46d-5418-9b8f-fec60d590ab5 |  | note | RESPONSIBILITY: SE
label | 4d6afa15-f53d-58c7-bdad-f3650682e000 |  | note | ---------------------------------
label | 86acb60a-93cd-5887-be3a-63c9d0d8f896 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 81129061-42f6-5fbb-aa43-6b3072cd91db |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Proof Roll
label | 436c3a55-c9f4-542c-9ff8-38c32884b96b |  | note | REFERENCE: Section 304.08
label | e3ef5946-659f-5ae2-8758-a4f417086f89 |  | note | ---------------------------------
label | d29ace57-b6cf-5013-8212-86cc74662812 |  | note | ACCEPTANCE CRITERIA: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
label | ee2920f8-bb61-52ba-ae01-fe5e45f9a058 |  | note | ---------------------------------
label | d2e78016-9b70-5b72-9eff-2417fc32f749 |  | note | METHOD: Visual
label | 7bad6757-d77d-5a7d-ae8d-dfabb95b4f33 |  | note | ---------------------------------
label | 4bd6b641-949d-5c8a-b39a-8144c277812a |  | note | FREQUENCY: Each lot
label | da7df698-a768-5127-92cf-65a242eb470d |  | note | ---------------------------------
label | fddf0efe-1dfa-5cff-b778-6bdb74967567 |  | note | CATEGORY: HP
label | 163788a4-d81f-594d-b9f3-f40c200138f0 |  | note | ---------------------------------
label | 8106c381-8e83-5474-b61d-104057cf7a6c |  | note | RESPONSIBILITY: Nominated Authority
label | df37c5f6-1b1f-5beb-af87-3e046c24022e |  | note | ---------------------------------
label | 413a0a31-4a84-53f2-98cb-52cc7cd052b7 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | dff9c164-91a3-5d47-a3c0-351e611a0fd7 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 Protection of compacted layer
label | 05eec8b2-a56e-5c65-b425-426229b33c74 |  | note | REFERENCE: Section 304.09
label | 764dc145-4b8c-5cc8-a696-831bb6cbda36 |  | note | ---------------------------------
label | 24319235-d618-565d-9f28-6a9da47ea55e |  | note | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
label | 2567b0c4-945d-5d4b-9a04-c005587560a2 |  | note | ---------------------------------
label | 4a86fc96-c807-5f5e-b561-fe23a476c4ba |  | note | METHOD: Visual
label | 03b437f3-48d3-5f77-a43b-8c5f98f660a6 |  | note | ---------------------------------
label | 909a33c3-42f3-5d76-8c3e-07fcd4208e1d |  | note | FREQUENCY: Each lot
label | e73be73e-2caa-5a8b-9435-334d5033636e |  | note | ---------------------------------
label | d342a9a3-22ba-5ec9-b19d-32d731b56139 |  | note | CATEGORY: IP
label | d28b7024-d37d-5642-8fb2-4cd767fa3a1e |  | note | ---------------------------------
label | e01790d6-026d-5b3c-89b0-7a8cd5653259 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8ed8244f-1839-5523-9f32-ad25e98233bd |  | note | ---------------------------------
label | 42bcd6ad-c661-55a5-ae72-f016fa54264f |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 062dd11f-9616-58f3-9788-e2ac28490f0f |  | date | Date Completed:
checkpoint-group |  |  | section | 6 - Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Compaction Testing (results)
label | 85d432d4-6c9a-570f-91e6-629a343c9981 |  | note | REFERENCE:
label | f4e32e1a-b6fe-5466-bea1-0b88e395cfb7 |  | note | Section 173
label | 8f712bb4-defe-59ea-a933-37c1a597055c |  | note | Section 304.08
label | 7079092d-bd25-59a0-9e2b-652cb4b97b15 |  | note | Table 304.081
label | e411fe84-d11e-5fa9-9496-de630c30d1c6 |  | note | ---------------------------------
label | 589abf5d-285a-5439-8d17-a24df0e85fa5 |  | note | ACCEPTANCE CRITERIA:
label | 01108911-6712-5751-be85-f7a08494f74c |  | note | During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
label | aca9c562-4300-5293-a22f-9e8d17f5c30f |  | note | Density Ratio to be based on tests performed with Modified Comp active Effort.
label | 221a2a46-7bd3-5c22-9500-ffdf0fc25280 |  | note | ○ Scale A:
label | e5e6adab-18c0-54ae-938f-671bbeec1a67 |  | note | – Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
label | 2f1515bb-165e-5c04-9da2-baac231cb577 |  | note | – Base Layer CDR ≥ 100%
label | b76766b4-8cf6-5e3d-8502-8034a2f9f476 |  | note | ○ Scale B:
label | c0a9ca9d-fa0a-5fb0-9d86-9e61efffb97e |  | note | – Subbase Layer CDR ≥ 97%–
label | 577cc1b3-3a37-5144-b05c-bfaab5492732 |  | note | – Base Layer CDR ≥ 98%
label | 3528040c-2567-5199-9e7d-1f92e09049fe |  | note | – 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
label | 63058b58-127d-5b52-81b8-875a483ff8aa |  | note | ○ Scale C:
label | 6d11b966-004a-5908-b849-887bdc59a05b |  | note | – Mean Value of Density Ratio (3 tests):
label | 1de1e6ea-80d6-5bd3-bcb3-42bfbdb299cb |  | note | – Subbase Layers >98%
label | 9b52a5dc-252f-5720-b504-cecea3810693 |  | note | – Base Layers >100%
label | 6249b548-bf8b-53f7-b900-0f20a5fd0278 |  | note | ATTACH: Compaction Test Results
label | 25f6798e-eeb5-5185-8c96-3ec18b63f1d8 |  | note | ---------------------------------
label | 359cf896-8ca6-5695-9994-89b460f3bbba |  | note | METHOD: Document Review
label | 2e2cbf31-0f2d-5aca-af6c-9115b48aa7f1 |  | note | ---------------------------------
label | 52704361-bdc8-5d5f-86de-678065c24165 |  | note | FREQUENCY: Each Lot Where applicxable
label | 71d1806e-12dc-559e-b11d-0358f10670ac |  | note | ---------------------------------
label | 7fbb39ac-ad51-50e6-9a87-a30597f37e90 |  | note | CATEGORY: IP
label | 9c945e17-5e38-5ea2-bc2b-6fcd7fae42c2 |  | note | ---------------------------------
label | a202f23b-623c-5509-b1b5-b2dde76c7342 |  | note | RESPONSIBILITY: PE
label | 70a41860-71b7-56a3-a0dc-e62479cd30cd |  | note | ---------------------------------
label | 5f261207-de99-5126-a8ef-b57aee0c62e2 |  | note | VERIFYING DOCUMENTS: Compaction Test Rersults
date | 83433fe2-b080-51b3-9c8d-15ade7ca7b6e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Post Compaction Materials Testing (Results)
label | 513b8e86-e315-5db1-a856-2df69fbe9e79 |  | note | REFERENCE:
label | 31fff90d-b7f1-5bd5-afbc-11eced2ed0e0 |  | note | Section 304.10
label | 781cae46-8135-5359-874e-fc57594960c4 |  | note | Section 304.11
label | f65daeeb-d048-59ce-a7c6-9a1f84f236c9 |  | note | RC 500.02
label | 05788357-72d5-5995-b60b-e797d68ee422 |  | note | ---------------------------------
label | 21743c15-4db3-5604-9c79-cf9db691c0ec |  | note | ACCEPTANCE CRITERIA:
label | c04d89d7-a8ac-5d11-87c1-25e88bbb0466 |  | note | Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
label | 75b5c973-7435-5508-aef9-6b75b005d04b |  | note | ○ 20mm Class 3:
label | 45f592d6-1945-5fc6-ac95-18c8e577d3db |  | note | – Grading
label | 3ddea421-fe35-578c-8bf4-47ae3953b58d |  | note | 26.5mm 100%
label | b4750c40-241d-5222-8a56-760755eee81e |  | note | 19.0mm 95-100%
label | f2401ea0-0eca-54ca-b36f-f4fb49c6fbeb |  | note | 13.2mm 75-95%
label | b70c938d-987f-552c-ae7c-6c42c6a52fa3 |  | note | 9.5mm 60-90%
label | e1a3c8a5-4eb6-52a2-9606-d2204f20833c |  | note | 4.75mm 42-76%
label | 078676b2-5201-53fc-a7ff-a8058b2cb81b |  | note | 2.36mm 28-61%
label | 86c7bb21-ec27-57eb-b64c-193db13ed4ec |  | note | 0.425mm 14-29%
label | 3124e430-4cf6-532c-a6b2-3b66e59db80f |  | note | 0.075mm 6-14%
label | de401da6-9ab2-5da4-956f-dc5c0f22cccd |  | note | PI between 0 to 10
label | 461e843d-b478-5ff7-a68b-6c64b7cd0fe0 |  | note | ○ 20mm Class 4:
label | 4dcd3bb4-7eca-58b6-a1cc-204255b8706f |  | note | – Grading
label | d8369a0d-92cc-501a-9bce-863178479d5d |  | note | 26.5mm 100%
label | 43c19236-42ba-5332-8623-d2e568828df8 |  | note | 4.75mm 42-76%
label | 5f6c1716-785b-527b-a24a-ed7c70e976e2 |  | note | 0.425mm 10-28%
label | 5ee8ec8d-86b9-524e-8df7-772609a9dee3 |  | note | 0.075mm 2-14%
label | deeef6e8-8c43-5000-841d-46cd6f0a24f2 |  | note | PI between 0 to 20
label | 45672309-51fd-50b2-9f3d-ffe2b83e6112 |  | note | PI x % passing 0.425 mm sieve (max) 450
label | cb06c1ef-8283-5132-b42d-b705c223ddd6 |  | note | ○ Scale C: Post compaction material te
label | 6c89b3fc-8d22-55d3-8c72-c3682f3d63c3 |  | note | ---------------------------------
label | 484e37b2-afdc-5b38-9627-fb4c23b5f342 |  | note | METHOD: Document Review
label | 875a1b92-887d-5778-9ae3-ca9d69fbe79e |  | note | ---------------------------------
label | 29fd9910-1802-5016-966a-cdae2f93fe57 |  | note | FREQUENCY: Each Lot Where applicable
label | 39cd36af-4b92-5781-bba1-4dcb8affec4e |  | note | ---------------------------------
label | 6002bb76-8930-556d-a914-31c56e22c18f |  | note | CATEGORY: IP
label | c3fa00cd-28f4-5bbf-bd85-1d5b5642bf1d |  | note | ---------------------------------
label | e3eca85f-abc7-5f41-b835-2ae0b5f4557f |  | note | RESPONSIBILITY: PE
label | 652ce04c-220c-579d-8fd9-8aca4552514d |  | note | ---------------------------------
label | c361a182-ac46-5253-b266-4119a9fc975c |  | note | VERIFYING DOCUMENTS: Compaction Test Rersults
date | c1e5dbc3-1643-5ed6-b90c-40416a02ee28 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Survey As-Built - Surface Level
label | 09a18864-81ae-526a-9689-e749deda7e62 |  | note | REFERENCE:
label | f1f1e660-e4dd-5292-9f1c-abb723e0a4dc |  | note | IFC Drawings
label | f0262e6a-0e62-506f-836a-f6bc2a022a8c |  | note | Section 304.06
label | 8dc87aac-7c92-5426-9621-70a7d0cc4cc3 |  | note | Table 304.061
label | 7065bbff-a65b-5462-b501-a4782e82fecf |  | note | Table 304.062
label | 4a100fce-5675-5309-85b2-deca0551efae |  | note | ---------------------------------
label | 00037401-05f9-5321-b6a6-90d2a9633e89 |  | note | ACCEPTANCE CRITERIA:
label | cec57e67-6746-5957-90ab-e12c7e38489f |  | note | No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
label | cee12b34-33fc-5b2e-ab1a-2cbcad30ef1d |  | note | Subbase course shall be not < the specified thickness by more than 15 mm.
label | 95f9d542-8e6f-5924-a3ae-0506dbcbafee |  | note | Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
label | d771d4af-b012-5c5c-9c89-6e2e990563af |  | note | The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
label | a0c46964-1526-5a07-b1a6-45e194764894 |  | note | ○ Scale A: A minimum of 80 measurements per lot
label | e900a0e5-0215-5b94-8284-48c02e7bdbe9 |  | note | Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
label | e95b82a6-c5a0-5523-a85f-da0d2a48950c |  | note | Base: mean range ±5mm, maximum Standard Deviation of 8mm
label | 377ba864-1658-57cf-b1d9-dc54734452a8 |  | note | ○ Scale B: A minimum of 40 measurements per lot
label | 59242fc7-7163-5d4b-8611-55ef6076c227 |  | note | Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
label | 28d868ec-0a0c-5bd3-a476-b7f53e3488cf |  | note | Base: mean range ±8mm, maximum Standard Deviation of 10mm
label | a6a6221d-3bb5-5c58-9f24-e6ff08cf2f78 |  | note | ○ Scale C:
label | 268559e6-f051-5554-9718-4217592c3e58 |  | note | Lower Subbase (mm) +15/ -25
label | bab41298-b6be-585f-8641-4662942476c9 |  | note | Upper Subbase (mm) +10/ -25
label | 1593b53b-202b-5541-8b75-9eb657a30b70 |  | note | Base (mm) +/-15
label | 8323ed6f-f6bc-59c0-afdd-5ab4a0c3c61f |  | note | ---------------------------------
label | b36345d6-71dd-51fd-afd5-1bf4f9429b64 |  | note | METHOD: Document Review
label | f0f90a9b-4ed2-55d4-8210-19273fe72597 |  | note | ---------------------------------
label | 508dce27-1df2-5661-a131-772f88f75134 |  | note | FREQUENCY: Each lot
label | 404fe49d-18b4-55e1-8e7a-8fb49df33373 |  | note | ---------------------------------
label | 4c74e684-d08c-54e9-8cf9-f226ef378843 |  | note | CATEGORY: IP
label | 82285ee8-50dc-5f94-991f-6612bdb35eda |  | note | ---------------------------------
label | ba98b8dc-2aa2-5cce-a494-4418b282a37c |  | note | RESPONSIBILITY: PE/Surveyor
label | a9c04c23-4a3a-5b6f-94e4-4fc54437bf76 |  | note | ---------------------------------
label | 3b910d95-599b-5354-95d7-ff2d038a7baa |  | note | VERIFYING DOCUMENTS: Survey Conformance Report
date | a5e3ef50-8e92-5128-9dab-248deabb16fd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 466a1ce8-e38e-5edb-9ae0-330f1362419a |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 3f9dca37-9bf9-58ab-82ae-87009338a9d8 |  | textbox | Name:
text | 217c0efb-6411-59ce-b868-f024c44b8d48 |  | textbox | Position:
date | 2fad6147-33e2-5546-a328-edf245079e42 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP