## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-089-STR-SSB-Precast Driven Piles installation
ITP Description: |  | SSB-Precast Driven Piles installation
Discipline (e.g. CIV/STR/RAIL: |  | 089-STR
Revision Number: |  | 0
Revision Date: |  | 2024-04-19
ITP created by: |  | Victor Mira
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Station Street, Beaconsfield
Inspection & Test Plan - Driven Piles
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-04-19
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | AS 2159-2019 | NA | NA | NA | NA | NA | NA | NA | NA
1.2 | Non Dependent | Vicroads Section 605 June 2018 | NA | NA | NA | NA | NA | NA | NA | NA
1.3 | Non Dependent | VicRoads BTN 023 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Precast element | IFC Drawings 610.46 (a), Table 610.463 (November 2018) 610.47 (a) Table 610.473 (March/June 2019) | Precast supplier is required to provide the Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Post-pour check sheet / ITP vi. Covermeter check record vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast as per VR 610 Minimum age before driving: Steam cured 7 days after the date of casting Moist cured 14 days after the date of casting provided that in all cases the specified concrete strength has been achieved. ATTACH BIRTH CERTIFICATE | Document Review | Each element | HP | PE/Nominated Authority | This ITP Birth Certificate
2.2 | Precast piles | VR 605.01 | Care must be taken to ensure that piles are not damaged during transport, handling and driving. Piles shall be inspected for their length and cross section prior installtion. Piles shall be inspected for any defects. | Visual | Each pile | HP* | SE/PE | This ITP
3 | Preliminaries - Procedures & Documentation
3.1 | Driving System | VR 605.02 | If a drop-hammer is used, the height of fall of the hammer shall not exceed 2 m. The Contractor shall provide details of the driving system including the make, model and rated energy of the hammer, the mass of the helmet, and the proposed cap-block and cushion materials. These details, including calculations which demonstrate that the proposed driving system has sufficient energy to achieve the specified pile test load, shall be submitted to the Superintendent for review not less than 14 days prior to the commencement of pile driving. If a drop-hammer is used, the height of fall of the hammer shall not exceed 2 m. Enter: Teambinder Approval number [free text box] | Document review | Prior driving | HP | PE/Nominated Authority | This ITP ConQA Hold Point Release
3.2 | Monitoring | 605.04 | Set measurements shall be taken to verify capacity of each pile driven, recorded as traces during driving to show the temporary compression of the pile and the permanent set. Traces must be taken relative to a stable hurdle supported securely by posts at least one pile diameter from each side of the pile. Where set measurements cannot be undertaken due to OH&S issues, the Contractor shall provide alternative methods to the Superintendent for review at least 7 days prior to pile driving. Enter: Teambinder Approval number: [free text box] | Document review |  | HP | PE/Nominated Authority | This ITP ConQA Hold Point Release
3.3 | Pile testing-Prequalified consultant | 605.07 (b) | All high strain dynamic testing shall be undertaken by a prequalified consultant and approved by the Superintendent. The consultant shall be independent of the piling contractor and advised to the Superintendent at least 2 weeks prior to testing. The test procedure and test reports shall conform to the requirements of AS 2159. Enter: Teambinder Approval number: [free text box] | Document review | Each test | HP | PE/Nominated Authority | This ITP ConQA Hold Point Release
3.4 | Pile-Approval for using HILEY Formula | 605.04 605.05 (a) BTN 023 | pile testing using the Hiley Formula may only be used for bridges of low significance and where high strain dynamic pile testing is not practical. Advice should be sought from Technical Consulting Geotechnical Services if pile testing using the Hiley Formula is to be adopted. The dispensation conditions for Pile Driving Analyser (PDA) for predominantly laterally loaded piles may be applied to embedded retaining walls or other structures, subject to compliance with the criteria listed in Table 1 of BTN 023. Where any of the conditions cannot be fulfilled, relevant structural and geotechnical reports must be provided to the DTP Chief Engineer – Roads for review and approval. Enter: Teambinder Approval number: [free text box] | Document review | When Applicable | HP | PE/Nominated Authority | This ITP ConQA Hold Point Release
4 | Pre-construction Activities
4.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | SE/PE | This ITP
4.2 | Pile-Ultimate Capacity- Wave Equation-First pile in the group | 605.05 (b) | The initial pile in each pile group shall be monitored with Dynamic Testing Equipment DURING DRIVING. The records shall be subjected to closed form dynamic solution and wave equation analysis. Pile stresses during driving shall not exceed 0.8x fc) compression and 1.1x SQR(fc) tension for concrete piles, where fc is the concrete strength. The measured stresses in the pile induced during pile driving and ultimate pile capacity calculations shall be submitted to the Superintendent for eview prior to driving further piles. Initial pile in the group: [Free Text box] | Document Review | One for Each Pile Group (First pile in each group) | HP | PE/Nominated Authority | This ITP ConQA Hold Point Release
4.3 | Survey Set out | VR 605.04 (c ) | Survey activities undertaken to ensure and validate that all Works meet location requirements within the tolerances: pile head centre, ± 50 mm of the specified position. | Survey | Each pile prior driving | IP | SE/Surveyor | This ITP
5 | Construction Activities
5.1 | Driving-Pile protection | 605.04 | During driving, the tops of the piles shall be held and guided by a suitable helmet and protected by a cushioning material, to avoid damage to the pile. Piles shall be guided into the specified position and shall not be bent or sprung into place during or after driving. | Visual | Each element | IP | SE | This ITP
5.2 | Pile alignment and Straightness | 605.04 | The Contractor shall ensure that piles achieve the specified accuracy of level and position. The following tolerances shall apply to piles after driving: - pile alignment: deviation from the vertical or the specified rake shall not exceed 20 mm per metre length of pile - pile straightness: deviation from vertical shall not exceed 5 mm per metre length of pile | Visual Measure | Each element | IP | SE | This ITP
5.3 | Pile driving-Monitoring | 605.04 | Set measurements shall be taken to verify capacity of each pile driven, recorded as traces during driving to show the temporary compression of the pile and the permanent set. Traces must be taken relative to a stable hurdle supported securely by posts at least one pile diameter from each side of the pile. | Visual | Each element | IP | SE | This ITP
5.4 | Pile Driving operation | 605.04 | Each pile shall be driven in a continuous operation and not left partly driven. | Visual | Each element | IP | SE | This ITP
5.5 | Pile Extension | 605.10 (c ) BTN 023 - 3.2.7 605.04 | precast extensions may be used provided that - the mechanical joints must comply with the requirements of AS 5100.3 clause 6.4 and BTN 023 -design of mechanical joints must comply with the durability requirements of AS 5100.3 Section 4 - the precast extension must have a minimum length of 5 metres - the joint location is determined by the structural design engineer. - Mechanical joints must not be located within 5 m of the underside of a pile-cap or in aggressive groundwater Driving shall re‑commence as soon as the splice is completed. | Visual Measure | When Applicable | IP | SE | This ITP
5.6 | Pile-Ultimate Capacity- HILEY Formula | 605.05 (a) | Piles shall achieve the specified ultimate load capacity. If using Hiley Formula is permitted: The values of the coefficients EF, E and C1, which are dependent upon the type of equipment used and the rake of the piles, shall be nominated by the Contractor and reviewed by the Superintendent. If using Hiley Formula is permitted: Coefficients C2 and C3 shall be measured by the Contractor for each pile during driving simultaneously with the measurement of set per blow. Contractor ITP to be attached: | Document review | Each pile when permitted | IP | Nominated Authority | Contractor ITP/Pile driving record
5.7 | Pile-Ultimate Capacity- Wave Equation-Other than the first pile | 605.05 (b) I 605.07 (b) ii | The driving criteria for each pile group shall be determined by testing the first pile driven in each group in accordance with clause 605.07(b)(i). All piles within that group shall be driven to a set not exceeding the driving set as determined by the PDA test on the basis of wave equation analysis. Refer to Pile driving record | Document review | Each Pile | IP | Nominated Authority | Contractor ITP/Pile driving record
5.8 | Pile driving records | 605.06 AS 2159 Clause 7.7 | Pile driving records shall be in accordance with Section 7.7 – AS 2159. The following records must be retained for each pile driven: - Sequence of driving in th pile group - length of each segment prior to driving - date of driving - Final toe level - set measurements for the last 10 blows and temporary compression for one of the blows - calculated ultimate pile capacity - measured stresses in the pile. Attach: pile driving record | Document review | Each Pile | IP | Nominated Authority | Contractor ITP/Pile driving record
5.9 | Re-Strike test | 605.04 605.08 | If the ultimate load capacity is not achieved at the specified level, the pile shall have a restrike test undertaken in accordance with clause 605.08 – Restrike Test. If directed by the Superintendent, the pile shall be driven until the specified ultimate load capacity is achieved. Restrike testing shall be conducted not less than 24 hours after initial driving. Attach: Re-Strike record | Document review | When Applicable | IP | Nominated Authority | Contractor ITP/Pile driving record
6 | Post-construction Activities
6.1 | Pile testing-High Strain DynamicTesting | 605.07 (b) I AS 2159 Appendix B | High-strain dynamic pile testing shall be performed to confirm that the design pile capacity and integrity has been achieved. The pile driving system shall have adequate energy to mobilise a test pile by a single hammer blow. Testing shall be carried out by use of a PDA or approved equivalent and data obtained from each test shall be analysed using CAPWAP or TNOWAVE or approved equivalent. The driving resistance and corresponding set per blow of the test pile shall be measured during PDA testing to extrapolate the results of the test pile to the piles in the pile group. The test results are required to demonstrate meeting the acceptance criteria shown on the drawings. The measured ultimate capacity of the test pile shall be equal to or greater than the pile test load shown on the drawings. Pile testing shall be carried out in the presence of the Superintendent. Attach: High Strain dynamic pile test results | Test Document Review | When applicable two test per group (First pile and other nominated pile) | HP | Nominated Authority | Contractor ITP/Pile driving record
6.2 | Pile -Driving | 605.04 | Piles forced up by the driving of adjacent piles shall be re driven to the specified toe level. | Measure | When Applicable | IP | SE/PE | This ITP
6.3 | As-built Survey | VR 605.04 (c ) | The following tolerances apply to piles: i. Centre of pile head plan location = ±50mm Attach: Survey As-builts / Survey Report | Document Review | Each pile | IP | Surveyor SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /