## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-089-STR-SSB-Precast Driven Pile Installation | itp |  |  |  |  | ITP-089-STR-SSB-Precast Driven Pile Installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-065-CIV-Camms-Landscaping-Ground Preparation
label | ITP Description: Landscaping - Ground Preparation (Subcontractor)
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: AS 2159-2019
label | 1.2 Non Dependent
label | Reference: Vicroads Section 605 June 2018
label | 1.3 Non Dependent
label | Reference: VicRoads BTN 023
section | Preliminaries - Materials
checkpoint | 2.1 Precast element
label | REFERENCE: IFC Drawings 610.46 (a), Table 610.463 (November 2018) 610.47 (a) Table 610.473 (March/June 2019)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Precast supplier is required to provide the Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Post-pour check sheet / ITP
label | vi. Covermeter check record
label | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast as per VR 610
label | Minimum age before driving:
label | ○ Steam cured 7 days after the date of casting
label | ○ Moist cured 14 days after the date of casting
label | ○ provided that in all cases the specified concrete strength has been achieved.
label | ATTACH BIRTH CERTIFICATE
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Birth Certificate
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Precast piles
label | REFERENCE: VR 605.01
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Care must be taken to ensure that piles are not damaged during transport, handling and driving.
label | ○ Piles shall be inspected for their length and cross section prior installtion.
label | ○ Piles shall be inspected for any defects.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Driving System
label | REFERENCE: VR 605.02
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: If a drop-hammer is used, the height of fall of the hammer shall not exceed 2 m.
label | ○ The Contractor shall provide details of the driving system including the make, model and rated energy of the hammer, the mass of the helmet, and the proposed cap-block and cushion materials.
label | ○ These details, including calculations which demonstrate that the proposed driving system has sufficient energy to achieve the specified pile test load, shall be submitted to the Superintendent for review not less than 14 days prior to the commencement of pile driving.
label | ○ If a drop-hammer is used, the height of fall of the hammer shall not exceed 2 m.
textbox | Enter: Teambinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior driving
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Monitoring
label | REFERENCE: 605.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Set measurements shall be taken to verify capacity of each pile driven, recorded as traces during driving to show the temporary compression of the pile and the permanent set. Traces must be taken relative to a stable hurdle supported securely by posts at least one pile diameter from each side of the pile. Where set measurements cannot be undertaken due to OH&S issues, the Contractor shall provide alternative methods to the Superintendent for review at least 7 days prior to pile driving.
textbox | Enter: Teambinder Approval number: [free text box]
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 Pile testing-Prequalified consultant
label | REFERENCE: 605.07 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All high strain dynamic testing shall be undertaken by a prequalified consultant and approved by the Superintendent. The consultant shall be independent of the piling contractor and advised to the Superintendent at least 2 weeks prior to testing.
label | ○ The test procedure and test reports shall conform to the requirements of AS 2159.
textbox | Enter: Teambinder Approval number: [free text box]
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each test
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 Pile-Approval for using HILEY Formula
label | REFERENCE: 605.04, 605.05 (a) BTN 023
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pile testing using the Hiley Formula may only be used for bridges of low significance and where high strain dynamic pile testing is not practical. Advice should be sought from Technical Consulting Geotechnical Services if pile testing using the Hiley Formula is to be adopted.
label | ○ The dispensation conditions for Pile Driving Analyser (PDA) for predominantly laterally loaded piles may be applied to embedded retaining walls or other structures, subject to compliance with the criteria listed in Table 1 of BTN 023. Where any of the conditions cannot be fulfilled, relevant structural and geotechnical reports must be provided to the DTP Chief Engineer – Roads for review and approval.
textbox | Enter: Teambinder Approval number: [free text box]
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When Applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Pre-construction Activities
checkpoint | 4.1 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to starting Works and at regular intervals
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Pile-Ultimate Capacity- Wave Equation-First pile in the group
label | REFERENCE: 605.05 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The initial pile in each pile group shall be monitored with Dynamic Testing Equipment DURING DRIVING.
label | ○ The records shall be subjected to closed form dynamic solution and wave equation analysis.
label | ○ Pile stresses during driving shall not exceed 0.8x fc) compression and 1.1x SQR(fc) tension for concrete piles, where fc is the concrete strength.
label | ○ The measured stresses in the pile induced during pile driving and ultimate pile capacity calculations shall be submitted to the Superintendent for eview prior to driving further piles.
textbox | Initial pile in the group:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: One for Each Pile Group (First pile in each group)
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 Survey Set out
label | REFERENCE: VR 605.04 (c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements within the tolerances:
label | ○ pile head centre, ± 50 mm of the specified position.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile prior driving
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Driving-Pile protection
label | REFERENCE: 605.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: During driving, the tops of the piles shall be held and guided by a suitable helmet and protected by a cushioning material, to avoid damage to the pile.
label | ○ Piles shall be guided into the specified position and shall not be bent or sprung into place during or after driving.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Pile alignment and Straightness
label | REFERENCE: 605.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall ensure that piles achieve the specified accuracy of level and position. The following tolerances shall apply to piles after driving:
label | ○ pile alignment: deviation from the vertical or the specified rake shall not exceed 20 mm per metre length of pile
label | ○ pile straightness: deviation from vertical shall not exceed 5 mm per metre length of pile
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Pile driving-Monitoring
label | REFERENCE: 605.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Set measurements shall be taken to verify capacity of each pile driven, recorded as traces during driving to show the temporary compression of the pile and the permanent set. Traces must be taken relative to a stable hurdle supported securely by posts at least one pile diameter from each side of the pile.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Pile Driving operation
label | REFERENCE: 605.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Each pile shall be driven in a continuous operation and not left partly driven.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Pile Extension
label | REFERENCE: 605.10 (c) BTN 023 - 3.2.7 605.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: precast extensions may be used provided that
label | ○ the mechanical joints must comply with the requirements of AS 5100.3 clause 6.4 and BTN 023
label | ○ design of mechanical joints must comply with the durability requirements of AS 5100.3 Section 4
label | ○ the precast extension must have a minimum length of 5 metres
label | ○ the joint location is determined by the structural design engineer.
label | ○ Mechanical joints must not be located within 5 m of the underside of a pile-cap or in aggressive groundwater
label | Driving shall re‑commence as soon as the splice is completed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When Applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Pile-Ultimate Capacity- HILEY Formula
label | REFERENCE: 605.05 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Piles shall achieve the specified ultimate load capacity.
label | If using Hiley Formula is permitted:
label | ○ The values of the coefficients EF, E and C1, which are dependent upon the type of equipment used and the rake of the piles, shall be nominated by the Contractor and reviewed by the Superintendent.
label | If using Hiley Formula is permitted:
label | ○ Coefficients C2 and C3 shall be measured by the Contractor for each pile during driving simultaneously with the measurement of set per blow.
label | Contractor ITP to be attached:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile when permitted
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
date | Date Completed:
checkpoint | 5.7 Pile-Ultimate Capacity- Wave Equation-Other than the first pile
label | REFERENCE: 605.05 (b) I, 605.07 (b) ii
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The driving criteria for each pile group shall be determined by testing the first pile driven in each group in accordance with clause 605.07(b)(i).
label | ○ All piles within that group shall be driven to a set not exceeding the driving set as determined by the PDA test on the basis of wave equation analysis.
label | ○ Refer to Pile driving record
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
date | Date Completed:
checkpoint | 5.8 Pile driving records
label | REFERENCE: 605.06 AS 2159 Clause 7.7
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pile driving records shall be in accordance with Section 7.7 – AS 2159. The following records must be retained for each pile driven:
label | ○ Sequence of driving in th pile group
label | ○ length of each segment prior to driving
label | ○ date of driving
label | ○ Final toe level
label | ○ set measurements for the last 10 blows and temporary compression for one of the blows
label | ○ calculated ultimate pile capacity
label | ○ measured stresses in the pile.
label | Attach: pile driving record
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
date | Date Completed:
checkpoint | 5.9 Re-Strike test
label | REFERENCE: 605.04, 605.08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: If the ultimate load capacity is not achieved at the specified level, the pile shall have a restrike test undertaken in accordance with clause 605.08 – Restrike Test. If directed by the Superintendent, the pile shall be driven until the specified ultimate load capacity is achieved.
label | ○ Restrike testing shall be conducted not less than 24 hours after initial driving.
label | Attach: Re-Strike record
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When Applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
date | Date Completed:
section | Construction Activities
checkpoint | 6.1 Pile testing-High Strain DynamicTesting
label | REFERENCE: 605.07 (b) I AS 2159 Appendix B
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: High-strain dynamic pile testing shall be performed to confirm that the design pile capacity and integrity has been achieved.
label | ○ The pile driving system shall have adequate energy to mobilise a test pile by a single hammer blow.
label | ○ Testing shall be carried out by use of a PDA or approved equivalent and data obtained from each test shall be analysed using CAPWAP or TNOWAVE or approved equivalent.
label | ○ The driving resistance and corresponding set per blow of the test pile shall be measured during PDA testing to extrapolate the results of the test pile to the piles in the pile group.
label | ○ The test results are required to demonstrate meeting the acceptance criteria shown on the drawings.
label | ○ The measured ultimate capacity of the test pile shall be equal to or greater than the pile test load shown on the drawings.
label | ○ Pile testing shall be carried out in the presence of the Superintendent.
label | Attach: High Strain dynamic pile test results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When applicable two test per group (First pile and other nominated pile)
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 Pile -Driving
label | REFERENCE: 605.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Piles forced up by the driving of adjacent piles shall be re driven to the specified toe level.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When Applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 As-built Survey
label | REFERENCE: VR 605.04 (c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | i. Centre of pile head plan location = ±50mm
label | Attach: Survey As-builts / Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-151-STR-SSB-Shotcrete | itp |  |  |  |  | ITP-151-STR-SSB-Shotcrete Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-151-STR-Shotcrete-SSB
label | ITP Description: Shotcrete-SSB
label | Discipline (e.g. CIV/STR/RAIL): 151-STR
label | Revision Number: 0
label | Revision Date: 19/04/2024
label | ITP created by: Mike Freeman
label | ITP approved for use by: Mike Freeman
label | 1.1 Non Dependent
label | Reference: VicRoads Section 610 June 2019
label | 1.2 Non Dependent
label | Reference: VicRoads Section 611 November 2018
label | 1.3 Non Dependent
label | Reference: VicRoads Section 684 April 2019
label | 1.4 Non Dependent
label | Reference: AS3810.1 2018
section | Preliminaries - Materials
checkpoint | 2.1 Concrete Mix
label | REFERENCE: 684.04 (a) 684.04 (d) (i & ii) 684.05 (a) (i & ii) Table 684.051 684.05 (b) Table 684.052 610.07 Table 610.071
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
label | ○ Maximum drying shrinkage shall meet the values shown on table 684.052.
label | Where applicable, steel fibres shall:
label | i. be deformed
label | ii. have a minimum tensile strength of 800MPa
label | iii. have an aspect ratio between 40 and 70
label | iv. have a minimum dosage rate as per table 684.051
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | REFERENCE: 684.04 (c), 611.05 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once for each supplier, 14 days of award of contract
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 2.3 Galvanising (for Reinforcement)
label | REFERENCE: 684.04 (c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All reinforcement and tie wire used in the Works shall be hot-dipped galvanised in accordance with AS4680.
label | Note: MRPA has D.o.T direction and approval to use black anchor bars
label | See:
label | ○ MRP-016-C-ACD-REP-17-NWA-CSW-0001 (Clyde Road)
label | ○ MRP-072-C-AURE-REP-20-DPK-CSW-0001 (Robinsons Road)
label | Attach: Galvaniser's Certificate of Compliance
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: For each reinforcement delivery from each galvaniser
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 2.4 Bar Chairs/Aspros Certification
label | REFERENCE: 610.26 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 2.5 Evaporative Retardant
label | REFERENCE: 684.10 (b), 684.11, 610.17 (f)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 2.6 Curing Compound
label | REFERENCE: 684.12, 610.23 (d)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Shotcrete Work Method Statement
label | REFERENCE: 684.07 (a), 684.07 (d) (i), 684.07 (d)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Shotcrete WMS, detailing the proposed equipment and preparation works, to be submitted for review to the Nominated Authority.
label | ○ Any changes to the approved WMS shall be deemed a new Hold Point.
textbox | Enter: Teambinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Contractor Competency
label | REFERENCE: 684.06, 684.07 (a), 684.07 (d)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Personnel undertaking the shotcrete works, including the nozzle operator, supervisor and finisher, shall have a minimum of 5 years experience in shotcrete application.
label | ○ Any changes to personnel shall be deemed a new Hold Point.
textbox | Enter: Teambinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, 4 weeks prior to commencement of works and for any personnel changes
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 Test Panels
label | REFERENCE: 684.07 (b - d), 684.07 (d) (i), 684.10 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: For each combination of nozzle operator, concrete mix and spraying equipment, 2 no. test panels (750mm x 750mm x the maximum design thickness or 150mm min.), shall be cast.
label | – The panels shall be cast using the same reinforcement design and in the same orientation as the Works - panels shall not be cast horizontally on the ground.
label | – For each test panel, 8 no. core samples shall be taken, perpendicular to the surface, no closer than 125mm from the edge and after 48 hours minimum.
label | Core samples shall be tested for:
label | ○ 1 no. 3 day compressive strength
label | ○ 1 no. 7 day compressive strength
label | ○ 2 no. 28 day compressive strength
label | ○ 2 no. VPV tests
label | ○ 2 no. visual inspection showing reinforcement encasement in concrete
label | Any changes to approved test panel combinations is deemed a new Hold Point.
label | Where existing test results for the same combinations exist, this is considered to be a pre-qualification and new test panels are not required.
textbox | Enter: Teambinder Approval Number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, 4 weeks prior to placement of concrete, for each combination of personnel, concrete mix and equipment
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 Concrete Sampling and Testing Procedure
label | REFERENCE: 684.08 (a), 610.18 (a) (v)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 Shotcrete Prequalification Toolbox Meeting
label | REFERENCE: 684.07 (d) (ii)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Shotcrete prequalification toolbox meeting held to discuss the quality requirements.
label | ○ Minutes of this meeting to be submitted to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to placement of concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 Hot and/or Cold Weather Concreting Procedure
label | REFERENCE: 684.10 (b), 610.17 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, 2 weeks prior to placement of concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.7 Curing Methodology (for Concrete and Grout)
label | REFERENCE: 684.12, 610.23 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Pre-construction Activities
checkpoint | 4.1 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to starting Works and at regular intervals
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: All
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Substrate Preparation
label | REFERENCE: IFC Drawings Shotcrete WMS 684.09 (a - c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Substrate shall be formed to the correct line and grade to provide adequate thickness for the works and shaped (or repaired - for concrete) to prevent any abrupt changes in thickness of the shotcrete.
label | ○ Any loose materials, oils, grease and coatings of any description shall be removed.
label | ○ Smooth concrete substrates shall be roughened to create a construction joint.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.3 Subsurface Drainage
label | REFERENCE: IFC Drawings 684.09 (a), 702.03, 702.06, 702.07, 702.09 (f)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Subsurface drains shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists.
label | ○ The drainage shall be wrapped in geotextile, full height of the structure and located as shown on the IFC drawings against the substrate to prevent encasement in concrete.
label | ○ Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.4 Waterstop Seals, Compressible Seals & Isolation Joints
label | REFERENCE: IFC Drawings, Product TDS
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Waterstop seals, compressible seals and isolation joints shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
label | ○ Seals and isolation joints must be full height of the structural element(s) and located as per the IFC drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, at each existing structural element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Reinforcement Placement
label | REFERENCE: IFC Drawings 684.04 (c), 684.09 (c), 611.06, 611.09, 611.10, 611.11, 611.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | ○ Tie wire is to match the reinforcement it is securing, with contact between dissimilar metals isolated with zinc-rich spray paint, electrical tape or have a minimum gap of 10mm.
label | ○ Layers are spaced apart using bent reinforcement, not bar chairs.
label | ○ Projecting reinforcement is the correct length and location.
label | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the shotcrete application.
label | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Cast-in Items
label | REFERENCE: IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | ii. Running dimensions of a group of the above = ±6mm
label | iii. Ducts and conduit location = ±12mm
label | iv. Diameter of ducts and conduits = ±3mm
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Pre-pour Inspection
label | REFERENCE: IFC Drawings Bonded Anchors ITP 684.10 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All preparation works on the substrate have been completed and the surface moistened without free-standing water to prevent premature drying of the shotcrete.
label | ○ Evidence that the reinforcement and embedments are conforming to the requirements of the specifications and the IFC drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 Weather Conditions & Evaporation Limits
label | REFERENCE: Hot and/or Cold Weather Concreting Procedure 684.10 (b), 610.17, 610.17 (a) & (e) Table 610.171
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | Record: Required information on the Concrete Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Concrete Testing - Sampling Frequency
label | REFERENCE: Site Sampling & Testing Procedure 684.08 (a), RC 377.01, 610.16 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | ○ 0m³ to 10m³ = 1 sample
label | ○ 10m³ to 25m³ = 2 samples
label | ○ 25m³ to 50m³ = 3 samples
label | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | For each additional 50m³ and additional sample shall be taken.
label | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads.
label | Record: Required information on the Concrete Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Concrete Testing - Slump
label | REFERENCE: 684.08 (a), 610.16 (c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | ○ <60mm = ±10mm
label | ○ ≥60mm to ≤80mm = ±15mm
label | ○ >80mm to ≤110mm = ±20mm
label | ○ >110mm to ≤150mm = ±30mm
label | ○ >150mm = ±40mm
label | Record: Required information on the Concrete Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each sample of Standard or Superplasticised Concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Concrete Tester
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Concrete Testing - Compressive Strength Cylinders
label | REFERENCE: Site Sampling & Testing Procedure
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | Record: Required information on the Concrete Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each sample
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Concrete Tester
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.8 Supply & Discharge Rates
label | REFERENCE: 684.05 (c), 610.13 (a) & (f)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | ○ No water is to be added once discharge commences.
label | ○ Maximum time between batching trucks is 25 minutes.
label | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
label | Record: Required information on the Concrete Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each load
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.9 Application Process
label | REFERENCE: Shotcrete Work Method Statement 684.10 (b), 684.13, 610.18 (a) & (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | ○ Probes or non-corrosive thickness indicators shall be used during the application to determine the actual application thickness.
label | ○ The spray nozzle shall be held to ensure placement of concrete behind and around all steel reinforcement.
label | ○ For vertical surfaces, application shall commence at the bottom and overhead surfaces shall be applied from the shoulder to the crown.
label | ○ Each layer of the sprayed concrete shall be built up by making several passes over the working area with a maximum layer thickness of 150mm.
label | ○ Concrete shall not be sprayed through more than one layer of reinforcement in one application.
label | ○ Where a layer of sprayed concrete is to be covered by succeeding layers, it shall be allowed to set prior to application of the succeeding layer without the need for curing compounds.
label | ○ The surface shall be checked for soundness, segregated, loose or otherwise uncompacted sprayed concrete removed, repaired as specified, cleaned, and wetted using a blast of air and water, leaving a dense, homogenous monolithic layer.
label | Record: Required information on the Concrete Pour Record.
label | Attach: Concrete Pour Record
label | Attach: Concrete Dockets
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each load
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: SP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS:
date | Date Completed:
checkpoint | 5.10 Surface Finishes
label | REFERENCE: IFC Drawings 684.11, 684.14, 610.31, 610.20
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | ○ Where surface finish is not detailed, structural concrete retaining walls, soil nail walls, tunnel linings, CP Overlay and other structural components forming part of permanent Works shall have a class 2 finish to reduce the chance of cracking.
label | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.11 Curing
label | REFERENCE: Curing Methodology 684.10 (b), 610.23 Table 610.231
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: SP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Concrete Testing - Core Sample Frequency
label | REFERENCE: Site Sampling & Testing Procedure 684.04 (d) Table 684.041, 610.16 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below:
label | ○ 0m³ to 25m³ = 1 sample
label | ○ 25m³ to 50m³ = 2 samples
label | For each additional 50m³ an additional sample shall be taken.
label | Each sample shall consist of 5 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum.
label | Core samples shall be tested for:
label | ○ 1 no. 7 day compressive strength
label | ○ 2 no. 28 day compressive strength
label | ○ 2 no. VPV tests
label | Note: MRPA has D.o.T acceptance to remove the 3 day core and take core samples on test panels in lieu of completed Works
label | See:
label | ○ MRP-MRPA-GNC-XCN-0096
label | ○ E-mail from D.o.T 7.06.2021
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.2 Compressive Strength & VPV Test Results
label | REFERENCE: IFC Drawings 684.08 (e) (i - iii) Table 610.051, Table 610.061, 610.16 (g)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength and VPV results comply with table 610.061.
label | ○ Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects.
label | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%.
label | Attach: Compressive Strength Test Results
label | Attach: Core Sample Compressive Strength Test Results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each cylinder and core sample
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 Surface Inspection
label | REFERENCE: IFC Drawings 684.08 (b), 684.15, 684.16, 610.31 (a) - (n), 610.32, 610.24
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Surface to be as per the required class of finish with no visible lack of compaction, dry patches, voids or sand pockets.
label | ○ Soundness inspection shall be conducted with a small hammer to locate ‘drummy’ or ‘hollow’ response areas which indicate a possible lack of bond, delamination or other defect.
label | ○ For core sample penetrations and if any visual defects are observed, follow Structural Concrete Cementitious Patch Repair ITP for investigation and repair.
label | ○ No cracks greater than 0.2mm (exposure classification B1)
label | ○ If cracking is observed, complete the Structural Concrete Crack Repair ITP for investigation and repair.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP and/or Structural Concrete Crack Repair ITP
date | Date Completed:
checkpoint | 6.4 Fibre Wash-out Test Results
label | REFERENCE: 684.08 (c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Fibre wash-out test results shall be within 1% of the concrete mix design fibre dosage rate.
label | Attach: Fibre Wash-out Test Results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each test
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.5 As-built Survey
label | REFERENCE: IFC Drawings 684.13, 610.47 Table 610.472
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | ○ Where a shape is required, ±25mm with no depressions greater than 15mm.
label | Attach: Survey As-builts / Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.6 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP