## VAR1
1 | Tender and Testing conformance | Review specifications and performance standard requirements for project | Pre-contract Signing | Checklist | Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender. | Tested to specification requirements ITP Checklist is relevant to product required |  | H |  | 1 - Tender and Testing conformance | CHARACTERISTICS - Review specifications and performance standard requirements for project | STAGE/FREQUENCY - Pre-contract Signing | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender. | ACCEPTANCE CRITERIA - Tested to specification requirements ITP Checklist is relevant to product required | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - | 1 - Tender and Testing conformance
2 | Preliminary activities (requiring Principal’s notification) | Notification provided of any changes in design or structures that effect products to be used | Before ordering products and Beginning Installation | Checklist | Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client | Reviewed and changes do not alter quantities and types of products to be installed | Submit details of changes to client and agree to changes in scope or products to be used | H | S | 2 - Preliminary activities (requiring Principal’s notification) | CHARACTERISTICS - Notification provided of any changes in design or structures that effect products to be used | STAGE/FREQUENCY - Before ordering products and Beginning Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client | ACCEPTANCE CRITERIA - Reviewed and changes do not alter quantities and types of products to be installed | INSPECTION/TEST PROCEDURE - Submit details of changes to client and agree to changes in scope or products to be used | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - S | CHARACTERISTICS - Review specifications and performance standard requirements for project
3 | Preliminary activities (requiring Contractor’s acceptance) | Approvals required obtained or safety documentation is supplied and induction requirements outlined | Before ordering products and Beginning Installation | Checklist | variations requested if required, SWMS sent for review and inductions organised. | Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted | Documents sent and acceptance confirmed with Client | H | W | 3 - Preliminary activities (requiring Contractor’s acceptance) | CHARACTERISTICS - Approvals required obtained or safety documentation is supplied and induction requirements outlined | STAGE/FREQUENCY - Before ordering products and Beginning Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - variations requested if required, SWMS sent for review and inductions organised. | ACCEPTANCE CRITERIA - Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted | INSPECTION/TEST PROCEDURE - Documents sent and acceptance confirmed with Client | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - W | STAGE/FREQUENCY - Pre-contract Signing
4 | pre installation site investigation/measur e up completed confirmed. | Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability | Before installation | Checklist | structures match and conditions on site are suitable for installation to begin | Structural and physical characteristics match | Job pack issued to Installer with relevant ITP Checklist included | H | S | 4 - pre installation site investigation/measur e up completed confirmed. | CHARACTERISTICS - Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability | STAGE/FREQUENCY - Before installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - structures match and conditions on site are suitable for installation to begin | ACCEPTANCE CRITERIA - Structural and physical characteristics match | INSPECTION/TEST PROCEDURE - Job pack issued to Installer with relevant ITP Checklist included | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - S | RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender.
ACCEPTANCE CRITERIA - Tested to specification requirements ITP Checklist is relevant to product required
INSPECTION/TEST PROCEDURE -
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT -
2 - Preliminary activities (requiring Principal’s notification)
CHARACTERISTICS - Notification provided of any changes in design or structures that effect products to be used
STAGE/FREQUENCY - Before ordering products and Beginning Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client
ACCEPTANCE CRITERIA - Reviewed and changes do not alter quantities and types of products to be installed
INSPECTION/TEST PROCEDURE - Submit details of changes to client and agree to changes in scope or products to be used
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT - S
3 - Preliminary activities (requiring Contractor’s acceptance)
CHARACTERISTICS - Approvals required obtained or safety documentation is supplied and induction requirements outlined
STAGE/FREQUENCY - Before ordering products and Beginning Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - variations requested if required, SWMS sent for review and inductions organised.
ACCEPTANCE CRITERIA - Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted
INSPECTION/TEST PROCEDURE - Documents sent and acceptance confirmed with Client
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT - W
4 - pre installation site investigation/measur e up completed confirmed.
CHARACTERISTICS - Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability
STAGE/FREQUENCY - Before installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - structures match and conditions on site are suitable for installation to begin
ACCEPTANCE CRITERIA - Structural and physical characteristics match
INSPECTION/TEST PROCEDURE - Job pack issued to Installer with relevant ITP Checklist included
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT - S

## VAR2
Access point location(s) | AS5532 7.3 (h) AS1891.4 3.2.2 | Prestart installation work | Checklist | Manufacturer recommendation | Visual | Measurement | x | S | S | Access point location(s) | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2 | STAGE/FREQUENCY - Prestart installation work | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Manufacturer recommendation | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - x | INSTALL SUPERVISOR - S | CLIENT - S | Access point location(s)
Safe transition to roof | AS1891.6.2.2, (e ) Other selection criteria AS1657 4.8.3 | On Installation | Checklist | Installation Instruction followed | Visual | Measurement | x | S | S | Safe transition to roof | CHARACTERISTICS - AS1891.6.2.2, (e ) Other selection criteria AS1657 4.8.3 | STAGE/FREQUENCY - On Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - x | INSTALL SUPERVISOR - S | CLIENT - S | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
Access hatch connection to the structure | RIS Access Hatch Installation Requirement | On Installation | Checklist | Installation Instruction followed | Visual | Measurement | x | S | S | Access hatch connection to the structure | CHARACTERISTICS - RIS Access Hatch Installation Requirement | STAGE/FREQUENCY - On Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - x | INSTALL SUPERVISOR - S | CLIENT - S | STAGE/FREQUENCY - Prestart installation work
Access hatch Location | RIS Access Hatch Installation Requirement | On Installation | Checklist | Installation Instruction followed | Visual | Measurement | x | S | S | Access hatch Location | CHARACTERISTICS - RIS Access Hatch Installation Requirement | STAGE/FREQUENCY - On Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - x | INSTALL SUPERVISOR - S | CLIENT - S | RECORDS - Checklist
Transfer sling location | RIS Access Hatch Installation Requirement | On Installation | Checklist | Installation Instruction followed | Visual | Measurement | x | S | S | Transfer sling location | CHARACTERISTICS - RIS Access Hatch Installation Requirement | STAGE/FREQUENCY - On Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - x | INSTALL SUPERVISOR - S | CLIENT - S | REQUIREMENT/STANDARD/SPECIFICATION - Manufacturer recommendation
Transfer anchor location | RIS Access Hatch Installation Requirement | On installation | Checklist | Installation Instruction followed | Visual | Measurement | x | S | S | Transfer anchor location | CHARACTERISTICS - RIS Access Hatch Installation Requirement | STAGE/FREQUENCY - On installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - x | INSTALL SUPERVISOR - S | CLIENT - S | ACCEPTANCE CRITERIA - Visual
Number of fixings, location of fixings and location of supports and specific bracing | RIS Access Hatch Installation Requirement | On installation | Checklist | Installation Instruction followed | Visual | Measurement | x | S | S | Number of fixings, location of fixings and location of supports and specific bracing | CHARACTERISTICS - RIS Access Hatch Installation Requirement | STAGE/FREQUENCY - On installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - x | INSTALL SUPERVISOR - S | CLIENT - S | INSPECTION/TEST PROCEDURE - Measurement
Prevention of corrosion | RIS Access Hatch Installation Requirement | On installation | Checklist | Installation Instruction followed | Visual | Measurement | x | S | S | Prevention of corrosion | CHARACTERISTICS - RIS Access Hatch Installation Requirement | STAGE/FREQUENCY - On installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - x | INSTALL SUPERVISOR - S | CLIENT - S | INSTALLER - x
Product marking and signage | RIS Access Hatch Installation Requirement | On installation | Checklist | Installation Instruction followed | Visual | Measurement | x | S | S | Product marking and signage | CHARACTERISTICS - RIS Access Hatch Installation Requirement | STAGE/FREQUENCY - On installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - x | INSTALL SUPERVISOR - S | CLIENT - S | INSTALL SUPERVISOR - S
Instructions for general use | AS1891.2 1.4 System Acceptance Criteria a. AS/NZS 1891.4.2009 Section (9). RIS Access Hatch Installation Requirement | On installation | Checklist | Manufacturer recommendations | Visual | Visual |  | H | H | Instructions for general use | CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS/NZS 1891.4.2009 Section (9). RIS Access Hatch Installation Requirement | STAGE/FREQUENCY - On installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Manufacturer recommendations | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Visual | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - H | CLIENT - S
Safe transition to roof
CHARACTERISTICS - AS1891.6.2.2, (e ) Other selection criteria AS1657 4.8.3
STAGE/FREQUENCY - On Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - x
INSTALL SUPERVISOR - S
CLIENT - S
Access hatch connection to the structure
CHARACTERISTICS - RIS Access Hatch Installation Requirement
STAGE/FREQUENCY - On Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - x
INSTALL SUPERVISOR - S
CLIENT - S
Access hatch Location
CHARACTERISTICS - RIS Access Hatch Installation Requirement
STAGE/FREQUENCY - On Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - x
INSTALL SUPERVISOR - S
CLIENT - S
Transfer sling location
CHARACTERISTICS - RIS Access Hatch Installation Requirement
STAGE/FREQUENCY - On Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - x
INSTALL SUPERVISOR - S
CLIENT - S
Transfer anchor location
CHARACTERISTICS - RIS Access Hatch Installation Requirement
STAGE/FREQUENCY - On installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - x
INSTALL SUPERVISOR - S
CLIENT - S
Number of fixings, location of fixings and location of supports and specific bracing
CHARACTERISTICS - RIS Access Hatch Installation Requirement
STAGE/FREQUENCY - On installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - x
INSTALL SUPERVISOR - S
CLIENT - S
Prevention of corrosion
CHARACTERISTICS - RIS Access Hatch Installation Requirement
STAGE/FREQUENCY - On installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - x
INSTALL SUPERVISOR - S
CLIENT - S
Product marking and signage
CHARACTERISTICS - RIS Access Hatch Installation Requirement
STAGE/FREQUENCY - On installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Installation Instruction followed
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - x
INSTALL SUPERVISOR - S
CLIENT - S
Instructions for general use
CHARACTERISTICS - AS1891.2 1.4 System Acceptance Criteria a. AS/NZS 1891.4.2009 Section (9). RIS Access Hatch Installation Requirement
STAGE/FREQUENCY - On installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Manufacturer recommendations
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Visual
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT - H

## VAR3
Access point location(s) | Systems can be accessed safely by trained persons without the risk of an uncontrolled fall. | Access point location(s) | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall. | Access point location(s)
Safe transition to roof | Access hatches that use ladders have provision for opening and closing the roof access hatch with the use of one hand. | Safe transition to roof | REFERENCE - Access hatches that use ladders have provision for opening and closing the roof access hatch with the use of one hand. | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall.
Access hatch location | Access hatch opens away from the fall position or includes handrails to any fall zone on a pitched roof, or, when within 2m of a roof or structural edge. | Access hatch location | REFERENCE - Access hatch opens away from the fall position or includes handrails to any fall zone on a pitched roof, or, when within 2m of a roof or structural edge. | Safe transition to roof
Hatch handrails | Handrails to the hatch on the top side are located on three sides with grab rails incorporated into the design. | Hatch handrails | REFERENCE - Handrails to the hatch on the top side are located on three sides with grab rails incorporated into the design. | REFERENCE - Access hatches that use ladders have provision for opening and closing the roof access hatch with the use of one hand.
Hatch transfer strop location | Strop must be positioned to enable user to reach and connect without falling and position themselves in restraint to a safe location on the roof without a risk of falling. | Hatch transfer strop location | REFERENCE - Strop must be positioned to enable user to reach and connect without falling and position themselves in restraint to a safe location on the roof without a risk of falling. | Access hatch location
Operational safety | Where a hatch has a pinch point handling position, the pinch points when opening or closing the hatch are marked with pinch point signage. | Operational safety | REFERENCE - Where a hatch has a pinch point handling position, the pinch points when opening or closing the hatch are marked with pinch point signage. | REFERENCE - Access hatch opens away from the fall position or includes handrails to any fall zone on a pitched roof, or, when within 2m of a roof or structural edge.
Number of fixings, location of fixings and location of line specific bracing | Hatch is fixed to concrete structure with a minimum of 4 x M8 Hilti Dyna bolts OR a minimum of 4 x 4.8mm stainless rivets fixed to the upstand for roof sheet applications. Additional bracing is installed to prevent collapse of the hatch under a load. Back flashing has been installed for roof sheet applications. | Number of fixings, location of fixings and location of line specific bracing | REFERENCE - Hatch is fixed to concrete structure with a minimum of 4 x M8 Hilti Dyna bolts OR a minimum of 4 x 4.8mm stainless rivets fixed to the upstand for roof sheet applications. Additional bracing is installed to prevent collapse of the hatch under a load. Back flashing has been installed for roof sheet applications. | Hatch handrails
Prevention of corrosion | Dissimilar metals are not used or separated with EPDM, foam or tape. | Prevention of corrosion | REFERENCE - Dissimilar metals are not used or separated with EPDM, foam or tape. | REFERENCE - Handrails to the hatch on the top side are located on three sides with grab rails incorporated into the design.
Site clean up and picture evidence if handover is not possible | Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product. | Site clean up and picture evidence if handover is not possible | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product. | Hatch transfer strop location
Systems Installation completion action | Single user signage is installed in visible location. | Systems Installation completion action | REFERENCE - Single user signage is installed in visible location. | REFERENCE - Strop must be positioned to enable user to reach and connect without falling and position themselves in restraint to a safe location on the roof without a risk of falling.
Operational safety
REFERENCE - Where a hatch has a pinch point handling position, the pinch points when opening or closing the hatch are marked with pinch point signage.
Number of fixings, location of fixings and location of line specific bracing
REFERENCE - Hatch is fixed to concrete structure with a minimum of 4 x M8 Hilti Dyna bolts OR a minimum of 4 x 4.8mm stainless rivets fixed to the upstand for roof sheet applications. Additional bracing is installed to prevent collapse of the hatch under a load. Back flashing has been installed for roof sheet applications.
Prevention of corrosion
REFERENCE - Dissimilar metals are not used or separated with EPDM, foam or tape.
Site clean up and picture evidence if handover is not possible
REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of the installed product.
Systems Installation completion action
REFERENCE - Single user signage is installed in visible location.