## VAR1
1 | Tender and Testing conformance | Review specifications and performance standard requirements for project | Pre-contract signing | Checklist | Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender. | Tested to specification requirements ITP Checklist is relevant to product required |  | H |  | 1 - Tender and Testing conformance | CHARACTERISTICS - Review specifications and performance standard requirements for project | STAGE/FREQUENCY - Pre-contract signing | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender. | ACCEPTANCE CRITERIA - Tested to specification requirements ITP Checklist is relevant to product required | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - | 1 - Tender and Testing conformance
2 | Preliminary activities (requiring Principal’s notification) | Notification provided of any changes in design or structures that effect products to be used | Before ordering products and beginning installation | Checklist | Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client | Reviewed and changes do not alter quantities and types of products to be installed | Submit details of changes to client and agree to changes in scope or products to be used | H | S | 2 - Preliminary activities (requiring Principal’s notification) | CHARACTERISTICS - Notification provided of any changes in design or structures that effect products to be used | STAGE/FREQUENCY - Before ordering products and beginning installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client | ACCEPTANCE CRITERIA - Reviewed and changes do not alter quantities and types of products to be installed | INSPECTION/TEST PROCEDURE - Submit details of changes to client and agree to changes in scope or products to be used | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - S | CHARACTERISTICS - Review specifications and performance standard requirements for project
3 | Preliminary activities (requiring Contractor’s acceptance) | Approvals required obtained or safety documentation is supplied and induction requirements outlined | Before ordering products and beginning installation | Checklist | variations requested if required, SWMS sent for review and inductions organised. | Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted | Documents sent and acceptance confirmed with Client | H | W | 3 - Preliminary activities (requiring Contractor’s acceptance) | CHARACTERISTICS - Approvals required obtained or safety documentation is supplied and induction requirements outlined | STAGE/FREQUENCY - Before ordering products and beginning installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - variations requested if required, SWMS sent for review and inductions organised. | ACCEPTANCE CRITERIA - Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted | INSPECTION/TEST PROCEDURE - Documents sent and acceptance confirmed with Client | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - W | STAGE/FREQUENCY - Pre-contract signing
4 | pre installation site investigation/measur e up completed confirmed. | Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability | Before installation | Checklist | structures match and conditions on site are suitable for installation to begin | Structural and physical characteristics match | Job pack issued to Installer with relevant ITP Checklist included | H | S | 4 - pre installation site investigation/measur e up completed confirmed. | CHARACTERISTICS - Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability | STAGE/FREQUENCY - Before installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - structures match and conditions on site are suitable for installation to begin | ACCEPTANCE CRITERIA - Structural and physical characteristics match | INSPECTION/TEST PROCEDURE - Job pack issued to Installer with relevant ITP Checklist included | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - S | RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender.
ACCEPTANCE CRITERIA - Tested to specification requirements ITP Checklist is relevant to product required
INSPECTION/TEST PROCEDURE -
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT -
2 - Preliminary activities (requiring Principal’s notification)
CHARACTERISTICS - Notification provided of any changes in design or structures that effect products to be used
STAGE/FREQUENCY - Before ordering products and beginning installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client
ACCEPTANCE CRITERIA - Reviewed and changes do not alter quantities and types of products to be installed
INSPECTION/TEST PROCEDURE - Submit details of changes to client and agree to changes in scope or products to be used
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT - S
3 - Preliminary activities (requiring Contractor’s acceptance)
CHARACTERISTICS - Approvals required obtained or safety documentation is supplied and induction requirements outlined
STAGE/FREQUENCY - Before ordering products and beginning installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - variations requested if required, SWMS sent for review and inductions organised.
ACCEPTANCE CRITERIA - Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted
INSPECTION/TEST PROCEDURE - Documents sent and acceptance confirmed with Client
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT - W
4 - pre installation site investigation/measur e up completed confirmed.
CHARACTERISTICS - Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability
STAGE/FREQUENCY - Before installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - structures match and conditions on site are suitable for installation to begin
ACCEPTANCE CRITERIA - Structural and physical characteristics match
INSPECTION/TEST PROCEDURE - Job pack issued to Installer with relevant ITP Checklist included
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT - S

## VAR2
0 | CHARACTERISTICS - | STAGE/FREQUENCY - | RECORDS - | REQUIREMENT/STANDARD/SPECIFICATION - | ACCEPTANCE CRITERIA - | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - | CLIENT - | 0
0 | CHARACTERISTICS - | STAGE/FREQUENCY - | RECORDS - | REQUIREMENT/STANDARD/SPECIFICATION - | ACCEPTANCE CRITERIA - | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - | CLIENT - | CHARACTERISTICS -
0 | CHARACTERISTICS - | STAGE/FREQUENCY - | RECORDS - | REQUIREMENT/STANDARD/SPECIFICATION - | ACCEPTANCE CRITERIA - | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - | CLIENT - | STAGE/FREQUENCY -
0 | CHARACTERISTICS - | STAGE/FREQUENCY - | RECORDS - | REQUIREMENT/STANDARD/SPECIFICATION - | ACCEPTANCE CRITERIA - | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - | CLIENT - | RECORDS -
0 | CHARACTERISTICS - | STAGE/FREQUENCY - | RECORDS - | REQUIREMENT/STANDARD/SPECIFICATION - | ACCEPTANCE CRITERIA - | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - | CLIENT - | REQUIREMENT/STANDARD/SPECIFICATION -
0 | CHARACTERISTICS - | STAGE/FREQUENCY - | RECORDS - | REQUIREMENT/STANDARD/SPECIFICATION - | ACCEPTANCE CRITERIA - | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - | CLIENT - | ACCEPTANCE CRITERIA -
0 | CHARACTERISTICS - | STAGE/FREQUENCY - | RECORDS - | REQUIREMENT/STANDARD/SPECIFICATION - | ACCEPTANCE CRITERIA - | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - | CLIENT - | INSPECTION/TEST PROCEDURE -
0 | CHARACTERISTICS - | STAGE/FREQUENCY - | RECORDS - | REQUIREMENT/STANDARD/SPECIFICATION - | ACCEPTANCE CRITERIA - | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - | CLIENT - | INSTALLER -
0 | CHARACTERISTICS - | STAGE/FREQUENCY - | RECORDS - | REQUIREMENT/STANDARD/SPECIFICATION - | ACCEPTANCE CRITERIA - | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - | CLIENT - | INSTALL SUPERVISOR -
CLIENT -
0
CHARACTERISTICS -
STAGE/FREQUENCY -
RECORDS -
REQUIREMENT/STANDARD/SPECIFICATION -
ACCEPTANCE CRITERIA -
INSPECTION/TEST PROCEDURE -
INSTALLER -
INSTALL SUPERVISOR -
CLIENT -
0
CHARACTERISTICS -
STAGE/FREQUENCY -
RECORDS -
REQUIREMENT/STANDARD/SPECIFICATION -
ACCEPTANCE CRITERIA -
INSPECTION/TEST PROCEDURE -
INSTALLER -
INSTALL SUPERVISOR -
CLIENT -
0
CHARACTERISTICS -
STAGE/FREQUENCY -
RECORDS -
REQUIREMENT/STANDARD/SPECIFICATION -
ACCEPTANCE CRITERIA -
INSPECTION/TEST PROCEDURE -
INSTALLER -
INSTALL SUPERVISOR -
CLIENT -
0
CHARACTERISTICS -
STAGE/FREQUENCY -
RECORDS -
REQUIREMENT/STANDARD/SPECIFICATION -
ACCEPTANCE CRITERIA -
INSPECTION/TEST PROCEDURE -
INSTALLER -
INSTALL SUPERVISOR -
CLIENT -
0
CHARACTERISTICS -
STAGE/FREQUENCY -
RECORDS -
REQUIREMENT/STANDARD/SPECIFICATION -
ACCEPTANCE CRITERIA -
INSPECTION/TEST PROCEDURE -
INSTALLER -
INSTALL SUPERVISOR -
CLIENT -
0
CHARACTERISTICS -
STAGE/FREQUENCY -
RECORDS -
REQUIREMENT/STANDARD/SPECIFICATION -
ACCEPTANCE CRITERIA -
INSPECTION/TEST PROCEDURE -
INSTALLER -
INSTALL SUPERVISOR -
CLIENT -
0
CHARACTERISTICS -
STAGE/FREQUENCY -
RECORDS -
REQUIREMENT/STANDARD/SPECIFICATION -
ACCEPTANCE CRITERIA -
INSPECTION/TEST PROCEDURE -
INSTALLER -
INSTALL SUPERVISOR -
CLIENT -
0
CHARACTERISTICS -
STAGE/FREQUENCY -
RECORDS -
REQUIREMENT/STANDARD/SPECIFICATION -
ACCEPTANCE CRITERIA -
INSPECTION/TEST PROCEDURE -
INSTALLER -
INSTALL SUPERVISOR -
CLIENT -

## VAR3
0 | REFERENCE - | 0
REFERENCE -