## VAR1
1 | Tender and Testing conformance | Review specifications and performance standard requirements for project | Pre-contract signing | Checklist | Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender. | Tested to specification requirements ITP Checklist is relevant to product required |  | H |  | 1 - Tender and Testing conformance | CHARACTERISTICS - Review specifications and performance standard requirements for project | STAGE/FREQUENCY - Pre-contract signing | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender. | ACCEPTANCE CRITERIA - Tested to specification requirements ITP Checklist is relevant to product required | INSPECTION/TEST PROCEDURE - | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - | 1 - Tender and Testing conformance
2 | Preliminary activities (requiring Principal’s notification) | Notification provided of any changes in design or structures that effect products to be used | Before ordering products and beginning installation | Checklist | Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client | Reviewed and changes do not alter quantities and types of products to be installed | Submit details of changes to client and agree to changes in scope or products to be used | H | S | 2 - Preliminary activities (requiring Principal’s notification) | CHARACTERISTICS - Notification provided of any changes in design or structures that effect products to be used | STAGE/FREQUENCY - Before ordering products and beginning installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client | ACCEPTANCE CRITERIA - Reviewed and changes do not alter quantities and types of products to be installed | INSPECTION/TEST PROCEDURE - Submit details of changes to client and agree to changes in scope or products to be used | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - S | CHARACTERISTICS - Review specifications and performance standard requirements for project
3 | Preliminary activities (requiring Contractor’s acceptance) | Approvals required obtained or safety documentation is supplied and induction requirements outlined | Before ordering products and beginning installation | Checklist | variations requested if required, SWMS sent for review and inductions organised. | Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted | Documents sent and acceptance confirmed with Client | H | W | 3 - Preliminary activities (requiring Contractor’s acceptance) | CHARACTERISTICS - Approvals required obtained or safety documentation is supplied and induction requirements outlined | STAGE/FREQUENCY - Before ordering products and beginning installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - variations requested if required, SWMS sent for review and inductions organised. | ACCEPTANCE CRITERIA - Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted | INSPECTION/TEST PROCEDURE - Documents sent and acceptance confirmed with Client | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - W | STAGE/FREQUENCY - Pre-contract signing
4 | pre installation site investigation/measur e up completed confirmed. | Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability | Before installation | Checklist | structures match and conditions on site are suitable for installation to begin | Structural and physical characteristics match | Job pack issued to Installer with relevant ITP Checklist included | H | S | 4 - pre installation site investigation/measur e up completed confirmed. | CHARACTERISTICS - Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability | STAGE/FREQUENCY - Before installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - structures match and conditions on site are suitable for installation to begin | ACCEPTANCE CRITERIA - Structural and physical characteristics match | INSPECTION/TEST PROCEDURE - Job pack issued to Installer with relevant ITP Checklist included | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - S | RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender.
ACCEPTANCE CRITERIA - Tested to specification requirements ITP Checklist is relevant to product required
INSPECTION/TEST PROCEDURE -
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT -
2 - Preliminary activities (requiring Principal’s notification)
CHARACTERISTICS - Notification provided of any changes in design or structures that effect products to be used
STAGE/FREQUENCY - Before ordering products and beginning installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client
ACCEPTANCE CRITERIA - Reviewed and changes do not alter quantities and types of products to be installed
INSPECTION/TEST PROCEDURE - Submit details of changes to client and agree to changes in scope or products to be used
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT - S
3 - Preliminary activities (requiring Contractor’s acceptance)
CHARACTERISTICS - Approvals required obtained or safety documentation is supplied and induction requirements outlined
STAGE/FREQUENCY - Before ordering products and beginning installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - variations requested if required, SWMS sent for review and inductions organised.
ACCEPTANCE CRITERIA - Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted
INSPECTION/TEST PROCEDURE - Documents sent and acceptance confirmed with Client
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT - W
4 - pre installation site investigation/measur e up completed confirmed.
CHARACTERISTICS - Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability
STAGE/FREQUENCY - Before installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - structures match and conditions on site are suitable for installation to begin
ACCEPTANCE CRITERIA - Structural and physical characteristics match
INSPECTION/TEST PROCEDURE - Job pack issued to Installer with relevant ITP Checklist included
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT - S

## VAR2
Access point location(s) | AS1657 J2.2, 5.4.1 CHAR(AMP) G5 | Prestart installation work | Checklist | Standard/Specification | Visual | Measurement | X | S | S | Access point location(s) | CHARACTERISTICS - AS1657 J2.2, 5.4.1 CHAR(AMP) G5 | STAGE/FREQUENCY - Prestart installation work | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - X | INSTALL SUPERVISOR - S | CLIENT - S | Access point location(s)
Labelling of Installation | AS1657 8.2 Labelling of Installation | On Installation | Checklist | Standard/Specification | Visual | Measurement | X | S | S | Labelling of Installation | CHARACTERISTICS - AS1657 8.2 Labelling of Installation | STAGE/FREQUENCY - On Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - X | INSTALL SUPERVISOR - S | CLIENT - S | CHARACTERISTICS - AS1657 J2.2, 5.4.1 CHAR(AMP) G5
Material | AS/NZS 1664.1 CHAR(AMP) AS/NZS 1664.2 | On Installation | Checklist | Standard/Specification | Visual | Measurement | X | S | S | Material | CHARACTERISTICS - AS/NZS 1664.1 CHAR(AMP) AS/NZS 1664.2 | STAGE/FREQUENCY - On Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - X | INSTALL SUPERVISOR - S | CLIENT - S | STAGE/FREQUENCY - Prestart installation work
Headroom | AS1657 3.1.5 | On Installation | Checklist | Standard/Specification | Visual | Measurement | X | S | S | Headroom | CHARACTERISTICS - AS1657 3.1.5 | STAGE/FREQUENCY - On Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - X | INSTALL SUPERVISOR - S | CLIENT - S | RECORDS - Checklist
Safety below access areas | AS1657 4.5 CHAR(AMP) 4.6 | On Installation | Checklist | Standard/Specification | Visual | Measurement | X | S | S | Safety below access areas | CHARACTERISTICS - AS1657 4.5 CHAR(AMP) 4.6 | STAGE/FREQUENCY - On Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - X | INSTALL SUPERVISOR - S | CLIENT - S | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
Provision of a barrier | AS1657 5.4.1 | On Installation | Checklist | Standard/Specification | Visual | Measurement | X | S | S | Provision of a barrier | CHARACTERISTICS - AS1657 5.4.1 | STAGE/FREQUENCY - On Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - X | INSTALL SUPERVISOR - S | CLIENT - S | ACCEPTANCE CRITERIA - Visual
Stability and structural capacity | AS1657 6.1.1 | On Installation | Checklist | Standard/Specification | Visual | Measurement | X | S | S | Stability and structural capacity | CHARACTERISTICS - AS1657 6.1.1 | STAGE/FREQUENCY - On Installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - X | INSTALL SUPERVISOR - S | CLIENT - S | INSPECTION/TEST PROCEDURE - Measurement
Finished surfaces, height and hand clearance | AS1657 5.6.1, 5.6.2 CHAR(AMP) 5.6.3 | On installation | Checklist | Standard/Specification | Visual | Measurement | X | S | S | Finished surfaces, height and hand clearance | CHARACTERISTICS - AS1657 5.6.1, 5.6.2 CHAR(AMP) 5.6.3 | STAGE/FREQUENCY - On installation | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Measurement | INSTALLER - X | INSTALL SUPERVISOR - S | CLIENT - S | INSTALLER - X
Documentation to be supplied | AS1657 8.3 | On completion | Checklist | Standard/Specification | Visual | Visual |  | H | S | Documentation to be supplied | CHARACTERISTICS - AS1657 8.3 | STAGE/FREQUENCY - On completion | RECORDS - Checklist | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification | ACCEPTANCE CRITERIA - Visual | INSPECTION/TEST PROCEDURE - Visual | INSTALLER - | INSTALL SUPERVISOR - H | CLIENT - S | INSTALL SUPERVISOR - S
CLIENT - S
Labelling of Installation
CHARACTERISTICS - AS1657 8.2 Labelling of Installation
STAGE/FREQUENCY - On Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - X
INSTALL SUPERVISOR - S
CLIENT - S
Material
CHARACTERISTICS - AS/NZS 1664.1 CHAR(AMP) AS/NZS 1664.2
STAGE/FREQUENCY - On Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - X
INSTALL SUPERVISOR - S
CLIENT - S
Headroom
CHARACTERISTICS - AS1657 3.1.5
STAGE/FREQUENCY - On Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - X
INSTALL SUPERVISOR - S
CLIENT - S
Safety below access areas
CHARACTERISTICS - AS1657 4.5 CHAR(AMP) 4.6
STAGE/FREQUENCY - On Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - X
INSTALL SUPERVISOR - S
CLIENT - S
Provision of a barrier
CHARACTERISTICS - AS1657 5.4.1
STAGE/FREQUENCY - On Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - X
INSTALL SUPERVISOR - S
CLIENT - S
Stability and structural capacity
CHARACTERISTICS - AS1657 6.1.1
STAGE/FREQUENCY - On Installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - X
INSTALL SUPERVISOR - S
CLIENT - S
Finished surfaces, height and hand clearance
CHARACTERISTICS - AS1657 5.6.1, 5.6.2 CHAR(AMP) 5.6.3
STAGE/FREQUENCY - On installation
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Measurement
INSTALLER - X
INSTALL SUPERVISOR - S
CLIENT - S
Documentation to be supplied
CHARACTERISTICS - AS1657 8.3
STAGE/FREQUENCY - On completion
RECORDS - Checklist
REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
ACCEPTANCE CRITERIA - Visual
INSPECTION/TEST PROCEDURE - Visual
INSTALLER -
INSTALL SUPERVISOR - H
CLIENT - S

## VAR3
0 | REFERENCE - | 0
REFERENCE -