## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 46694R3 - ITP | itp |  |  |  |  | 46694R3 - ITP
section | INSPECTION TEST PLAN AND CHECKLIST
checkpoint | 1 - Tender and Testing conformance
label | CHARACTERISTICS - Review specifications and performance standard requirements for project
label | STAGE/FREQUENCY - Pre-contract Signing
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Confirm product is tested and designed to required project performance, international or national standards detailed in specifications at time of tender.
label | ACCEPTANCE CRITERIA - Tested to specification requirements ITP Checklist is relevant to product required
label | INSTALL SUPERVISOR - H
holdpoint | HOLD POINT
checkpoint | 2 - Preliminary activities (requiring Principal’s notification)
label | CHARACTERISTICS - Notification provided of any changes in design or structures that effect products to be used
label | STAGE/FREQUENCY - Before ordering products and Beginning Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Specification, drawings remain unchanged since tender was accepted and contract signed or new plans and specifications are issued and reviewed, changes are accepted by client
label | ACCEPTANCE CRITERIA - Reviewed and changes do not alter quantities and types of products to be installed
label | INSPECTION/TEST PROCEDURE - Submit details of changes to client and agree to changes in scope or products to be used
label | INSTALL SUPERVISOR - H
label | CLIENT - S
holdpoint | HOLD POINT
checkpoint | 3 - Preliminary activities (requiring Contractor’s acceptance)
label | CHARACTERISTICS - Approvals required obtained or safety documentation is supplied and induction requirements outlined
label | STAGE/FREQUENCY - Before ordering products and Beginning Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - variations requested if required, SWMS sent for review and inductions organised.
label | ACCEPTANCE CRITERIA - Change of design or quantities is agreed to and variations issued is SWMS and Induction accepted and conducted
label | INSPECTION/TEST PROCEDURE - Documents sent and acceptance confirmed with Client
label | INSTALL SUPERVISOR - H
label | CLIENT - W
holdpoint | HOLD POINT
checkpoint | 4 - Pre installation site investigation/measur e up completed confirmed.
label | CHARACTERISTICS - Progress of work and condition of the structure is confirmed, visual inspection where required is completed for compatibility and suitability
label | STAGE/FREQUENCY - Before installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - structures match and conditions on site are suitable for installation to begin
label | ACCEPTANCE CRITERIA - Structural and physical characteristics match
label | INSPECTION/TEST PROCEDURE - Job pack issued to Installer with relevant ITP Checklist included
label | INSTALL SUPERVISOR - H
label | CLIENT - S
holdpoint | HOLD POINT
section | Pre-Start/Installation
checkpoint | Plans and specifications have been reviewed and are current. Existing ITP checklists are suitable for project. Contract is signed.
checkpoint | SWMS and any other documents have been provided, reviewed and accepted by the client
checkpoint | Variations outlined and agreed, no changes or additions are required, job pack and ITP are included to project file.
checkpoint | Site inspected or reviewed, structural match confirmed with materials ordered, instation surface condition is undamaged and installation ready
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature: