## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 46694R302 - ITP - LEVEL 29 - Installation of RIS Anchor Points SA 141 Trimdek | itp |  |  |  |  | 46694R302 - ITP - LEVEL 29 - Installation of RIS Anchor Points SA 141 Trimdek
section | INSPECTION TEST PLAN
checkpoint | Access point location (s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile match
label | CHARACTERISTICS - AS5532 6.3.1.3 (a)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum sheet width
label | CHARACTERISTICS - AS5532 6.3.1.3 (iii)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum sheet length
label | CHARACTERISTICS - AS5532 6.3.1.3 (v)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum fixings and type
label | CHARACTERISTICS - AS5532 6.3.1.3 (c)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof sheet stabilisation fixings
label | CHARACTERISTICS - AS5532 7.3 (c)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position and orientation of anchor point to roof
label | CHARACTERISTICS - AS5532 6.3.1.3 (v)
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional pendulum fixing points to roof to allow safe transition and
label | CHARACTERISTICS - AS1891.4 Table 2.1 restraint technique
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Number of fixing and location of fixing to anchor point
label | CHARACTERISTICS - AS5532 6.3.1.3 (c)
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS5532 5.1
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS5532 7.2.3 a, b & c
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS5532 7.1 a, b, c, d, e, f & g
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions)
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall
checkpoint | Roof profile and minimum BMT match and corrosion check completed TRIMDEK
label | REFERENCE - Roof profile type matched minimum BMT .42 and roof sheeting displays no signs of surface corrosion
checkpoint | Minimum roof sheet width and length
label | REFERENCE - 3 x normal lapped roof sheets wide and crossing a minimum of three purlins or battens. Roof sheet can be fixed directly to purlin or timber batten which is fixed directly to structural steel or timber truss/rafter or additionally, purlin/tophat, blue metal/top hat and top hat/reroof.
checkpoint | Position and orientation of anchor point to Trimdek roof
label | REFERENCE - Centred between purlins/batten smiley face located away from the intended working edge for pendulum applications
checkpoint | Anchor point fixing to roof
label | REFERENCE - 8 x 8mm Bulb Tite Rivets.
checkpoint | Roof sheet fixings
label | REFERENCE - Screw fixed at crest over minimum 3 purlin/batten with a minimum 15 - 12x14x50 metal/timber tek screw in the 3 purlin/batten
checkpoint | GABLE END AND PENDULUM POINTS
label | REFERENCE - Pendulum anchors 2 x 8mm Bulb Tite Rivets to adjacent roof sheet lap 150mm apart
checkpoint | Anchor points to roof to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - The distance to the next anchor is less than the length to the closest edge, unless mitigated by other means
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to the roof anchor point rating. Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Corrosion prevention
label | REFERENCE - Dissimilar metals are separated by foam, tape, EPDM barrier or sealant. NOTE: It's acceptable to have some paper remain on the FOAM during installation.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of each anchor point.
checkpoint | Anchor systems installation completion action
label | REFERENCE - Anchor fit for use sticker/tag filled in and attached to the anchor point, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature:
checklist | 46694R301 - ITP - LEVEL 29 - Installation of RIS Anchor Points SA 141 Kliplok | itp |  |  |  |  | 46694R301 - ITP - LEVEL 29 - Installation of RIS Anchor Points SA 141 Kliplok
section | INSPECTION TEST PLAN
checkpoint | Access point location (s)
label | CHARACTERISTICS - AS5532 7.3 (h) AS1891.4 3.2.2
label | STAGE/FREQUENCY - Prestart installation work
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile match
label | CHARACTERISTICS - AS5532 6.3.1.3 (a)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum sheet width
label | CHARACTERISTICS - AS5532 6.3.1.3 (iii)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum sheet length
label | CHARACTERISTICS - AS5532 6.3.1.3 (v)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof profile minimum fixings and type
label | CHARACTERISTICS - AS5532 6.3.1.3 (c)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Roof sheet stabilisation fixings
label | CHARACTERISTICS - AS5532 7.3 (c)
label | STAGE/FREQUENCY - On Installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Position and orientation of anchor point to roof
label | CHARACTERISTICS - AS5532 6.3.1.3 (v)
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Additional pendulum fixing points to roof to allow safe transition and
label | CHARACTERISTICS - AS1891.4 Table 2.1 restraint technique
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Number of fixing and location of fixing to anchor point
label | CHARACTERISTICS - AS5532 6.3.1.3 (c)
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Measurement
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Prevention of corrosion
label | CHARACTERISTICS - AS5532 5.1
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Product marking and signage
label | CHARACTERISTICS - AS5532 7.2.3 a, b & c
label | STAGE/FREQUENCY - On installation
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Visual
label | INSTALLER - X
label | INSTALL SUPERVISOR - S
label | CLIENT - S
checkpoint | Instructions for general use
label | CHARACTERISTICS - AS5532 7.1 a, b, c, d, e, f & g
label | STAGE/FREQUENCY - On Completion
label | RECORDS - Checklist
label | REQUIREMENT/STANDARD/SPECIFICATION - Standard/Specification
label | ACCEPTANCE CRITERIA - Visual
label | INSPECTION/TEST PROCEDURE - Completion Handover
label | INSTALL SUPERVISOR - H
label | CLIENT - H
holdpoint | HOLD POINT
section | CHECKLIST - Installation (Refer to Installation Instructions) / Fill in the appropriate section based on the installed roof sheet.
checkpoint | Access point location(s)
label | REFERENCE - Systems can be accessed safely by trained persons without the risk of an uncontrolled fall
checkpoint | Minimum roof sheet width and length
label | REFERENCE - 3 x normal lapped roof sheets wide and crossing a minimum of three purlins or battens. Roof sheet must be fixed directly to purlin or timber batten which is fixed directly to structural steel or timber truss/rafter or additionally, purlin/tophat, blue metal/top hat and top hat/reroof.
label | ○ WARNING: DO NOT INSTALL ON RISERS AND KLIPLOK SHEETING APPLICATIONS
section | CHECKLIST - METLOK 500, KLIP-LOK 406
checkpoint | Roof profile and minimum BMT match and corrosion check completed
label | REFERENCE - Roof profile type matched minimum BMT .48 and roof sheeting displays no signs of surface corrosion
checkpoint | Roof sheet fixings
label | REFERENCE - Check that the roof sheet is fixed off securely to the underlying purlin;
label | Some examples of inspection methods:
label | ○ Visual check from inside of building that clips are installed. Visual check at the gutter line that clips are installed.
label | ○ Verify the roof is installed as per manufacturers instruction via Roofers warranty.
label | ○ Drill pilot hole over purlin where anchor is being positioned to check clips are installed.
section | CHECKLIST - KLIP-LOK 700
checkpoint | Roof profile and minimum BMT match and corrosion check completed
label | REFERENCE - Roof profile type matched minimum BMT.42 and roof sheeting displays no signs of surface corrosion
checkpoint | Roof sheet fixings
label | REFERENCE - Check that the roof sheet is fixed off securely to the underlying purlin;
label | Some examples of inspection methods:
label | ○ Visual check from inside of building that clips are installed. Visual check at the gutter line that clips are installed.
label | ○ Verify the roof is installed as per manufacturers instruction via Roofers warranty.
label | ○ Drill pilot hole over purlin where anchor is being positioned to check clips are installed.
checkpoint | METLOK 500, KLIP-LOK 406 and KLIP-LOK 700 fixings
label | REFERENCE - METLOK 500, KLIP-LOK 406 and KLIP-LOK 700 2 x 14 x 14 x 75 Roof Teks penetrating the support Purlin or Batten above the anchor point for access below the anchor and on pendulum points.
label | ○ METLOK 500, KLIP-LOK 406 and KLIP-LOK 700 2 x 14 x 14 x 75 Roof Teks penetrating the support Purlin or Batten below the anchor where the anchor point is used above the anchor or at pendulum points.
checkpoint | Anchor point fixing to roof
label | REFERENCE - Minimum 8 x 8mm Bulb Tite Rivets, 2 x 14 x 14 x 75 Roof Teks.
checkpoint | Position and orientation of anchor point to all clip fixed roof profiles
label | REFERENCE - Centred over purlin/battens smiley face located away from the intended working edge for pendulum applications
checkpoint | Anchor points to roof to prevent lateral swing fall are installed or mitigation agreed
label | REFERENCE - The distance to the next anchor is less than the length to the closest edge, unless mitigated by other means
checkpoint | Anchor at entry point with a stainless steel Strop
label | REFERENCE - Anchor strop must be positioned to enable user to reach and connect to.
label | ○ Strop is marked and rated to or above the roof anchor point rating.
label | ○ Mallion/Quicklink connection to roof anchor point is secured and mechanically tightened or chemically set with loctite.
label | COMMENTS - Not applicable as anchor is not within the Fall Zone.
bool | Tick if is not applicable
checkpoint | Corrosion prevention
label | REFERENCE - Dissimilar metals are separated by foam, tape, EPDM barrier or sealant. NOTE: It's acceptable to have some paper remain on the FOAM during installation.
checkpoint | Site clean up and picture evidence if handover is not possible
label | REFERENCE - Site has been cleared of swarf or other debris installation inspection completed and witnessed by the customers representative. Where a client cannot sign for handover, clear high resolution pictures have been taken of each anchor point.
checkpoint | Anchor systems installation completion action
label | REFERENCE - Anchor fit for use sticker/tag filled in and attached to the anchor point, mark with confirmed rating. Entry point signage updated and installed.
section | Project Completion
checkpoint | Handover operating and systems documentation issued
checkpoint | I have carried out all necessary inspections and verify that the above items/activities conform to the contract specification/documents
textbox | Name:
date | Date:
holdpoint | Signature: